## CPY_Format
|  |  |  | Master Document Index (MDI) |  | ABBREVIATION | [7 empty] | DOCUMENT NO. | REV.
[6 empty] | **Revision Purpose of Issued Document |  |  |  | *Owner Feedback (Comment) |  | ***Classification
[6 empty] | IFR = Issue For Review |  | IFF = Issue For Final |  | A1 = App. w/o comments | R1 = No comments | Class 1 = For Approval |  | LSP-2W91-0001 | A
[6 empty] | IFA = Issue For Approval |  | ASB = Issue For As-Built |  | A2 = App. with comments, re-submit not required | R2 = Comments as noted | Class 2 = For Review
[6 empty] | IFC = Issue For Construction |  | AFC = Approved for Construction |  | A3 = App. with comments, re-submit for review |  | Class 3 = For Information
Owner: |  |  |  | Plant Name: |  | IFI = Issue For Information |  | IMP = Issue for Implementation |  | A4 = Not App., re-submit for approval |  |  |  | Issue Date
[6 empty] | IFP = Issue For Planning |  | / Execution
Document Code : | [5 empty] | IFD = Issue For Design |  | CAN = Issue for Cancellation |  | Period for Company's comment |  | __________ | Working Days
Item | Org. | Document No. | Document Name |  | Classification
Category Code: A92 Procedures & Standards
| CO | OL1-2A92-0001 | VARIATION ORDER PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CO | OL1-2A92-0002 | CAR & THIRD PARTY INSURANCE CLAIM PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: B92 Procedures & Standards
| PC | OL1-2B92-0001 | PLANNING SCHEDULING AND PROGRESS MEASUREMENT PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: C92 Procedures & Standards
| PL | OL1-2C92-0001 | PROJECT PROCUREMENT EXECUTION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0002 | PROJECT QCS COORDINATION PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0005 | PROJECT QCS REQUIREMENTS FOR SUPPLIERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0007 | PRESCRIPTIONS FOR PREPARATION OF DOCUMENTATION PACKAGE FOR TRANSPORTATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0008 | PROJECT QCS EXPEDITING PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0009 | PROJECT QCS INSPECTION PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0013 | SPARE PARTS & SPECIAL TOOLS INSTRUCTIONS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0014 | PROJECT EXPEDITING AND INSPECTION LEVEL DEFINITION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0015 | TRANSPORTATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0016 | PARKING MARKING AND SHIPPING INSTRUCTIONS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C92-0017 | PROJECT SITE SERVICES CONDITIONS FOR SUPPLIER SPECIALISTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: C93 Policy , Guidelines & Memo
| PL | OL1-2C93-0001 | General Supply Rules for Supplier Documentation |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00043
Return Date
Owner Cmmt*
Category Code: D92 Procedures & Standards
| CM | OL1-2D92-0001 | CONSTRUCTION SUBCONTRACTING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E01 Electrical design basis
| EE | OL1-2E01-2001 | ELECTRICAL BASIS OF FURNACE DETAILED DESIGN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E02 Abbreviation and standard symbols
| EE | OL1-2E02-0001 | ELECTRICAL DRAWINGS LEGEND AND SYMBOLS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E03 Project electrical specification
| EE | OL1-2E03-0035 | TYPICAL INSTALLATION STANDARDS FOR ELECTRICAL EQUIPMENT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E04 Electrical requirement for package unit
| EE | OL1-2E04-6000 | General Design Rule for Package Equipment Electrical System |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00008 | TPSK-LSPA1-T-EE-00126
[6 empty] | Return Date | 2018-08-24 | 2018-10-12
[6 empty] | Owner Cmmt* | A3 | R1
Category Code: E05 Electrical Equipment datasheets
| EE | OL1-2E05-1100 | Typical Data Sheet for Medium Voltage Switchgears |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00476
Return Date
Owner Cmmt*
| EE | OL1-2E05-3001 | Typical Data Sheet for LV Motors |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00358
Return Date
Owner Cmmt*
| EE | OL1-2E05-3500 | Typical Data Sheet For Low Voltage Variable Voltage Variable Frequency System |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00358
Return Date
Owner Cmmt*
Category Code: E08
| EE | OL1-2E08-0001 | MEDIUM VOLTAGE (> 1 KV, ≤ 52 KV) SWITCHBOARD SCHEDULE FOR SUBSTATION E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E08-0002 | MEDIUM VOLTAGE (> 1 KV, ≤ 52 KV) SWITCHBOARD SCHEDULE FOR SUBSTATION C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E08-0003 | LOW VOLTAGE (≤ 1 KV) SWITCHBOARD SCHEDULE FOR SUBSTATION E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E08-0004 | LOW VOLTAGE (≤ 1 KV) SWITCHBOARD SCHEDULE FOR SUBSTATION C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E08-0005 | LOW VOLTAGE (≤ 1 KV) SWITCHBOARD SCHEDULE FOR SATELLITE SUBSTATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E10 Power system studies
| EE | OL1-2E10-0001 | ELECTRICAL CABLE SIZING CALCULATION NOTES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0002 | ELECTRICAL POWER BALANCE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0003 | LIGHTING SYSTEM CALCULATION NOTES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0004 | SHORT CIRCUIT ANALYSIS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0005 | LOAD FLOW AND VOLTAGE DROP ANALYSIS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0006 | MOTOR STARTING ANALYSIS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0007 | REACCELERATION STUDY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0008 | HARMONIC ANALYSIS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0009 | EMC STUDY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0010 | ELECTRICAL RELIABILITY ANALYSIS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0011 | INSULATION COORDINATION STUDY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E11 Arc flash studies
| EE | OL1-2E11-0001 | FLASH PROTECTION STUDY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E12 Protective relay selection and coordination study
| EE | OL1-2E12-0001 | PROTECTIVE RELAY SELECTIVITY STUDY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E13 Electrical equipment sizing
| EE | OL1-2E13-0001 | POWER FACTOR IMPROVEMENT SYSTEM SIZING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E13-0002 | AC UPS SYSTEM SIZING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E13-0003 | DC SYSTEM SIZING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E14 Single line diagram
| EE | OL1-2E14-0001 | KEY SINGLE LINE DIAGRAM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E14-0002 | INTERLOCKING SYSTEM PHYLOSOPHY DRAWING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E14-0003 | SUBSTATION E SINGLE LINE DIAGRAM (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E14-0004 | SUBSTATION C SINGLE LINE DIAGRAM (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E14-0005 | SATELLITE SUBSTATION SINGLE LINE DIAGRAM (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E14-1001 | PRELIMINARY SINGLE LINE DIAGRAM - OLEFINS UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E15 Electrical load schedule
| EE | OL1-2E15-0001 | PRELIMINARY ELECTRICAL LOAD SCHEDULE - OLEFINS UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0002 | ELECTRICAL EQUIPMENT LIST |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0003 | EX-EQUIPMENT REGISTER LIST |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0004 | ELECTRICAL CONSUMERS LIST |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-1001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-2001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-3001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-4001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-5001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-6001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E17 Motor list
| EE | OL1-2E17-1001 | PRELIMINARY MOTOR LIST - OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E18 Control and Signal List
| EE | OL1-2E18-0001 | SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SUBSTATION E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E18-0002 | SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SUBSTATION C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E18-0003 | SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SATELLITE SUBSTATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E19 Control schematic and control logic diagrams
| EE | OL1-2E19-0001 | MEDIUM VOLTAGE PROTECTION DIAGRAMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E19-0002 | LOW VOLTAGE PROTECTION DIAGRAMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E20 Substation equipment layout
| EE | OL1-2E20-0001 | SUBSTATION E EQUIPMENT LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E20-0002 | SUBSTATION C EQUIPMENT LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E20-0003 | SATELLITE ELECTRICAL / INSTRUMENT EQUIPMENT LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E22 Cable tray layout for substation
| EE | OL1-2E22-0001 | SUBSTATION E CABLE ROUTING LAYOUT (N…) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E22-0002 | SUBSTATION C CABLE ROUTING LAYOUT (N…) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E22-0003 | SATELLITE SUBSTATION CABLE ROUTING LAYOUT (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E23 Wiring drawing for substation system
| EE | OL1-2E23-0001 | ELECTRICAL INTERCONNECTION WIRING LIST FOR SUBSTATION E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E23-0002 | ELECTRICAL INTERCONNECTION WIRING LIST FOR SUBSTATION C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E23-0003 | ELECTRICAL INTERCONNECTION WIRING LIST FOR SATELLITE SUBSTATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E31 Power equipment layout
| EE | OL1-2E31-0001 | OVERALL ELECTRICAL MAIN CABLE ROUTING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0002 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0003 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0004 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0005 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0006 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0007 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0008 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0009 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0010 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0011 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0012 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0013 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0014 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0015 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0016 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-0017 | ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1001 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1002 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1003 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E32 Main cable route layout
| EE | OL1-2E32-0001 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0002 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0003 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0004 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0005 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0006 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0007 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0008 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0009 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0010 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0011 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0012 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0013 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0014 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0015 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-0016 | POWER LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1001 | USC 36M FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1002 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1003 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1004 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1005 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1006 | USC 36M FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1007 | USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1008 | USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1009 | USC 36M FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E34 Power and control cable arrangement drawing
| EE | OL1-2E34-0001 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0002 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0003 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0004 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0005 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0006 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0007 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0008 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0009 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0010 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0011 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0012 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0013 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0014 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0015 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0016 | CABLE ROUTING CROSS SECTIONS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E35
| EE | OL1-2E35-0001 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0002 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0003 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0004 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0005 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0006 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0007 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0008 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0009 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0010 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0011 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0012 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0013 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0014 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0015 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E35-0016 | WELDING AND RECEPTACLES PANEL SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E36
| EE | OL1-2E36-0001 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0002 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0003 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0004 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0005 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0006 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0007 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0008 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0009 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0010 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0011 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0012 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0013 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0014 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0015 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E36-0016 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E42 Lighting and receptacle panel board circuit schedule
| EE | OL1-2E42-0001 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0002 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0003 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0004 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0005 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0006 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0007 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0008 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0009 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0010 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0011 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0012 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0013 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0014 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0015 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0016 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1001 | USC 36M FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1002 | USC 36M FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1003 | USC 36M FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E43 Lighting and receptacle system layout
| EE | OL1-2E43-0001 | STREET LIGHTING SYSTEM LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0005 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0006 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0007 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0008 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0009 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0010 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0011 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0012 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0013 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0014 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0015 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0016 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0017 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0018 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0019 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0020 | LIGHTING LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1001 | USC 36M FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1002 | USC 36M FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1003 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1004 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1005 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1006 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1007 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1008 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1009 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1010 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1011 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1012 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1013 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1014 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1015 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2018 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2019 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2020 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4016 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4017 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4018 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4019 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4020 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6016 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6017 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6018 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6019 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6020 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E44 Lighting and receptacle system wiring layout
| EE | OL1-2E44-0001 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0002 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0003 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0004 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0005 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0006 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0007 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0008 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0009 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0010 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0011 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0012 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0013 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0014 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0015 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0016 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E50 Grounding and lightning network calculation
| EE | OL1-2E50-0001 | EARTHING AND LIGHTNING SYSTEM CALCULATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E52 Grounding and lightning system layout
| EE | OL1-2E52-0001 | OVERALL EARTHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0002 | OVERALL LIGHTNING PROTECTION LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0003 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0004 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0005 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0006 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0007 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0008 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0009 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0010 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0011 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0012 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0013 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0014 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0015 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0016 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0017 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0018 | EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0021 | SUBSTATION E EARTHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0022 | SUBSTATION C EARTHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0023 | SATELLITE SUBSTATION EARTHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1001 | USC 36M FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1002 | USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1003 | USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E55
| EE | OL1-2E55-0030 | MR SAFETY SUPERVISORY SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-0031 | MR INTERCOM/PAGING / AUDIBLE ALARM SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-0117 | MR EMERGENCY DIESEL GENERATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-1100 | Material Requisition for Medium Voltage Switchgears |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00476
Return Date
Owner Cmmt*
| EE | OL1-2E55-1200 | MR FOR LV SWITCHGEARS AND LV BUS DUCTS (≤ 1 KV) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-1500 | MR FOR TRANSFORMERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-1600 | MR FOR POWER CAPACITOR BANKS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-1700 | MR FOR MV VARIABLE FREQUENCY DRIVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-1800 | MR FOR SMCS SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-2000 | MR FOR AC AND DC UPS SYSTEMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-3001 | Material Requisition For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00359
Return Date
Owner Cmmt*
| EE | OL1-2E55-3100 | MR FOR MV ELECTRIC MOTORS AND D/S |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-5300 | MR FOR POWER AND LIGHTING DISTRIBUTION PANELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-8000 | MR FOR CATHODIC PROTECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-8100 | MR FOR ELECTRICAL HEAT TRACING SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-9000 | MR FOR ELECTRICAL CABLES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-9200 | MR FOR POWER MATERIALS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-9300 | MR FOR GROUNDING AND LIGHTNING MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-9301 | MR FOR LIGHTING MATERIALS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-9400 | MR FOR CABLE TRAYS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E55-9500 | MR FOR CONDUITS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E57
| EE | OL1-2E57-1100 | Particular Technical Specification for Medium Voltage Switchgears |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00476
Return Date
Owner Cmmt*
| EE | OL1-2E57-3001 | Particular Technical Specification For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00359
Return Date
Owner Cmmt*
Category Code: E60 Cable drum schedule
| EE | OL1-2E60-0001 | ELECTRICAL CABLE DRUM SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E61 Cable schedule
| EE | OL1-2E61-0001 | ELECTRICAL CABLE SCHEDULE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E63 Construction material and Bill of quantities
| EE | OL1-2E63-0002 | TECHNICAL SPECIFICATION FOR ELECTRICAL INSTALLATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-1001 | ELECTRICAL BULK MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-2001 | ELECTRICAL BULK MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-3001 | ELECTRICAL BULK MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-4001 | ELECTRICAL BULK MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-5001 | ELECTRICAL BULK MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-6001 | ELECTRICAL BULK MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E92 Procedures & Standards
| EE | OL1-2E92-0001 | General Design Rules For Smartplant Electrical |  | Class 2 | Purpose** | IFR | IFI
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00008 | TPSK-LSPA1-T-EE-00396
[6 empty] | Return Date | 2018-08-24
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E92-0002 | COORDINATION PROCEDURE FOR SMARTPLANT ELECTRICAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E92-0003 | COORDINATION PROCEDURE FOR ETAP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: F40
| FF | OL1-2F40-5001 | FIRE & GAS DEVICES LAYOUT COMMON AREA |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5002 | FIRE & GAS DEVICES LAYOUT METERING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5003 | FIRE & GAS DEVICES LAYOUT MAIN PIPE RACK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5004 | FIRE & GAS DEVICES LAYOUT AREA SUBSTATION E & FAR E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5005 | FIRE & GAS DEVICES LAYOUT AREA SUBSTATION C & FAR C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5006 | FIRE & GAS DEVICES LAYOUT FURNACES UTILITY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5007 | FIRE & GAS DEVICES LAYOUT QUENCH |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5008 | FIRE & GAS DEVICES LAYOUT PROCESS 20B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5009 | FIRE & GAS DEVICES LAYOUT PROCESS 20C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5010 | FIRE & GAS DEVICES LAYOUT PROCESS COLD COMPRESSORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5011 | FIRE & GAS DEVICES LAYOUT PROCESS CGC |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5012 | FIRE & GAS DEVICES LAYOUT BUTADIENE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5013 | FIRE & GAS DEVICES LAYOUT COOLING WATER UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5014 | FIRE & GAS DEVICES LAYOUT UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5015 | FIRE & GAS DEVICES LAYOUT WASTE WATER TREATMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F40-5016 | FIRE & GAS DEVICES LAYOUT FLARE AREA |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: F41
| FF | OL1-2F41-5001 | FIRE AND GAS CAUSE & EFFECT CHART FAR-E SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F41-5002 | FIRE AND GAS CAUSE & EFFECT CHART FAR-C SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F41-5003 | FIRE AND GAS CAUSE & EFFECT CHART CCB SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: F94 Forms & Templates
| FF | OL1-2F94-0001 | FIRE&GAS DETECTION SYSTEMS SPECIFICATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G01 All Project Philosophies and Process design standard and All Project Studies Records
| PE | OL1-2G01-0001 | JSD for P&ID Preparation |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00006
[6 empty] | Return Date | 2018-08-21
Owner Cmmt*
| PE | OL1-2G01-0002 | Cold Box Design Specification |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G01-0003 | Plate-Fin Exchanger Design Specification |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
Category Code: G02 Design Basis
| PE | OL1-2G02-0001 | Process Design Basis |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00002
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G02-0002 | Equipment Basis Of Design |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00002
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G02-0003 | Flare and Blowdown System Design Basis |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00034
[6 empty] | Return Date | 2018-09-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G02-0006 | Furnace Process Basis of Design |  | Class 3 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-31 | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00004 | TPSK-LSPA1-T-PE-00376
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3
Category Code: G05 Equipment and Unit Functional Design
| PE | OL1-2G05-1001 | Area Basis of Design - 10 Feed Preparation |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00011
[6 empty] | Return Date | 2018-08-27
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-1101 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G05-1301 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G05-1501 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G05-2001 | Area Basis of Design - 20-21 Quench and Dilution Steam |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00011
[6 empty] | Return Date | 2018-08-27
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2101 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G05-2201 | Area Basis of Design - 22-24 Compresssion Train |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00022
[6 empty] | Return Date | 2018-09-05
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2301 | Area Basis of Design - 23 Caustic and Spent Caustic Pretreatment |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00014
[6 empty] | Return Date | 2018-08-31
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2501 | Area Basis of Design - 25 Cold Fractionation |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00011
[6 empty] | Return Date | 2018-08-27
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2601 | Area Basis of Design - 26 Hot Fractionation |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00014
[6 empty] | Return Date | 2018-08-31
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-2602 | Area Basis of Design - 262 C3 Hydrogenation |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00307
Return Date
Owner Cmmt*
| PE | OL1-2G05-2701 | Area Basis of Design - 270 Gasoline Hydrogenation -GHU-1 |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00307
Return Date
Owner Cmmt*
| PE | OL1-2G05-2702 | Area Basis of Design - Area 275 C4-C5 Hydrogenation |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00307
Return Date
Owner Cmmt*
| PE | OL1-2G05-2801 | Area Basis of Design - 28 Refrigeration |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00022
[6 empty] | Return Date | 2018-09-05
[6 empty] | Owner Cmmt* | A1
| PE | OL1-2G05-3001 | Area Basis of Design - 30 BDU |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00150
Return Date
Owner Cmmt*
| PE | OL1-2G05-4001 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G05-5001 | Area Basis of Design - 50 ISBL Supporting Utilities |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00003
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-5301 | Area Basis of Design - 53 Cooling Tower System |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-07-31 | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-00003
[6 empty] | Return Date | 2018-08-17
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-5501 | Area Basis of Design - 55 Flare System |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00016
[6 empty] | Return Date | 2018-08-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G05-5601 | Area Basis of Design - 56 Waste Water Treatment System |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-07 | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-00011
[6 empty] | Return Date | 2018-08-27 | 2018-10-12
[6 empty] | Owner Cmmt* | A3 | A3
| PE | OL1-2G05-6001 | SIZING OF STEAM DRUM & SUPERHEATER PSVS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G21 Hydraulic Calculation
| PE | OL1-2G21-11XX | HYDRAULICS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-12XX | HYDRAULICS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-13XX | HYDRAULICS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-14XX | HYDRAULICS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-15XX | HYDRAULICS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G21-16XX | HYDRAULICS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G22 Flare Calculation
| PE | OL1-2G22-0001 | Flare Load Summary |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00229
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
Category Code: G30 Process Equipment Data Sheets
| PE | OL1-2G30-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00227 | TPSK-LSPA1-T-PE-00463
[6 empty] | Return Date | 2018-12-05
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00451
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1003 | Process Equipment Datasheet - 10-E-1001 - LPG Steam Vaporizer |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00179
Return Date
Owner Cmmt*
| PE | OL1-2G30-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1101 | Process Equipment Datasheet - 10-H-1100 - USM 36M Cracking Furnace Yields |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00360
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-1102 | Anticipated Operating Conditions - 10-H-1100 - USC 36M Gas Cracking Furnace |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00224
Return Date
Owner Cmmt*
| PE | OL1-2G30-1105 | API FIRED HEATER DATA SHEET (36M FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1106 | Process Equipment Datasheet - 10-H-1100 - USC 36M Burner |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241
Return Date
Owner Cmmt*
| PE | OL1-2G30-1107 | Process Equipment Datasheet - 10-D-1100 - USC 36M Cracking Furnace Steam Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-11 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00478
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00432
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00459
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00459
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1111 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan |  | Class 2 | Purpose** | IFD
[6 empty] | Rev. | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00222
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-1112 | Process Equipment Datasheet - 10-M-1100 - USC 36M Attemperator |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00330
Return Date
Owner Cmmt*
| PE | OL1-2G30-1151 | USC 36M EFFLUENT MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1152 | USC 36M DECOKE MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00372
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1202 | Anticipated Operating Conditions - 10-H-1200/1600 - USC 132U Liquid Cracking Furnace |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00224
Return Date
Owner Cmmt*
| PE | OL1-2G30-1206 | Process Equipment Datasheet - 10-H-1200 - 1600 - USC 132U Burner |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241
Return Date
Owner Cmmt*
| PE | OL1-2G30-1207 | Process Equipment Datasheet - 10-D-1200-1600 - USC 132U Cracking Furnace Steam Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-11 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00478
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00433
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00449
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1211 | Process Equipment Datasheet - 10-C-1200 1600 - USC 132U Induced Draft Fan |  | Class 2 | Purpose** | IFD
[6 empty] | Rev. | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00222
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-1212 | Process Equipment Datasheet - 10-M-1200 1600 - USC 132U Attemperator |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00330
Return Date
Owner Cmmt*
| PE | OL1-2G30-1213 | Process Equipment Datasheet - 10-M-1201 - 1601 A-F - USC 132U Dilution Steam Mixing Tee |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00434
Return Date
Owner Cmmt*
| PE | OL1-2G30-1251 | USC 132SU EFFLUENT MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1252 | USC 132SU DECOKE MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1302 | AOCS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1305 | API FIRED HEATER DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1306 | BURNERS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1307 | STEAM DRUM PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1308 | SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1309 | TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1311 | ID FAN DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1312 | ATTEMPERATOR DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1313 | MIXING TEE PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1351 | USC 132SU EFFLUENT MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1352 | USC 132SU DECOKE MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1406 | BURNERS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1407 | STEAM DRUM PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1408 | SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1409 | TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1411 | ID FAN DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1412 | ATTEMPERATOR DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1413 | MIXING TEE PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1451 | USC 132SU EFFLUENT MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1452 | USC 132SU DECOKE MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1506 | BURNERS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1507 | STEAM DRUM PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1508 | SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1509 | TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1511 | ID FAN DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1512 | ATTEMPERATOR DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1513 | MIXING TEE PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1551 | USC 132SU EFFLUENT MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1552 | USC 132SU DECOKE MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1606 | BURNERS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1607 | STEAM DRUM PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1608 | SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1609 | TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1611 | ID FAN DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1612 | ATTEMPERATOR DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1613 | MIXING TEE PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1651 | USC 132SU EFFLUENT MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1652 | USC 132SU DECOKE MOV - DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1910 | PROCESS EQUIPMENT DATA SHEET - 10-PK-1910 - DMDS INJECTION PACKAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-29 | 2018-09-28 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00114 | TPSK-LSPA1-T-PE-00242
[6 empty] | Return Date | 2018-09-28 | 2018-10-24 | 2018-11-30
[6 empty] | Owner Cmmt* | A3 | R2 | A1
| PE | OL1-2G30-1951 | PROCESS EQUIPMENT DATA SHEET - 10-D-1950 - DECOKE AIR RECEIVER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00402
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2002 | AOCS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2005 | API FIRED HEATER DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00071 | TPSK-LSPA1-T-PE-00202
[6 empty] | Return Date | 2018-10-09 | 2018-11-30
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-2007 | PROCESS EQUIPMENT DATA SHEET - 10-F-2008 - QUENCH OIL FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2008 | PROCESS EQUIPMENT DATA SHEET - 10-E-2008 - VLP STEAM GENERATORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2009 | PROCESS EQUIPMENT DATA SHEET - 10-F-2009 - QO PUMP PURGE OIL FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2010 | Process Equipment Datasheet - 10-F-2008 A-C Quench Oil Filter |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350
Return Date
Owner Cmmt*
| PE | OL1-2G30-2014 | Process Equipment Datasheet - 10-F-2009 A-B QO Pump Purge Oil Filter |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350
Return Date
Owner Cmmt*
| PE | OL1-2G30-2015 | Process Equipment Datasheet - 10-E-2008 A-C - LS2 Steam Generators |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00305
Return Date
Owner Cmmt*
| PE | OL1-2G30-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00437
[6 empty] | Return Date | 2018-12-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2024 | Process Equipment Datasheet - 10-P-2026 A-B - Light Fuel Oil Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
Owner Cmmt*
| PE | OL1-2G30-2025 | Process Equipment Datasheet - 10-F-2026 A-B Cracker Bottoms Product Filter |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350
Return Date
Owner Cmmt*
| PE | OL1-2G30-2026 | Process Equipment Datasheet - 10-E-2026 - FO Product Cooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298
Return Date
Owner Cmmt*
| PE | OL1-2G30-2028 | Process Equipment Datasheet - 10-F-2028 A-B - FO Pump Purge Oil Filter |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350
Return Date
Owner Cmmt*
| PE | OL1-2G30-2036 | Process Equipment Datasheet - 10-X-2036 - Quench Fitting |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00338
Return Date
Owner Cmmt*
| PE | OL1-2G30-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00347
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
Owner Cmmt*
| PE | OL1-2G30-2048 | Process Equipment Datasheet - 10-E-2048 - Heavy Fuel Oil Product Cooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298
Return Date
Owner Cmmt*
| PE | OL1-2G30-2049 | Process Equipment Datasheet - 10-F-2048 A-B Heavy Fuel Oil Filters |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350
Return Date
Owner Cmmt*
| PE | OL1-2G30-2090 | Process Equipment Datasheet - 10-D-2090 - Quench Oil Drain Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00368
Return Date
Owner Cmmt*
| PE | OL1-2G30-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371
Return Date
Owner Cmmt*
| PE | OL1-2G30-2092 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2090 - QUENCH OIL DRAIN SUMP EDUCTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00437
[6 empty] | Return Date | 2018-12-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2101 | Process Equipment Datasheet - 10-E-2100 A-F - Quench Water Cooler |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00143
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1
| PE | OL1-2G30-2104 | Process Equipment Datasheet - 10-F-2105 A-B Quench Oil Reflux Filter |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350
Return Date
Owner Cmmt*
| PE | OL1-2G30-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
Owner Cmmt*
| PE | OL1-2G30-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00070 | TPSK-LSPA1-T-PE-00202
[6 empty] | Return Date | 2018-10-09 | 2018-11-30
[6 empty] | Owner Cmmt* | A1 | A1
| PE | OL1-2G30-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453
Return Date
Owner Cmmt*
| PE | OL1-2G30-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper |  | Class 2 | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00253 | TPSK-LSPA1-T-PE-00401 | TPSK-LSPA1-T-PE-00437
[6 empty] | Return Date | 2018-12-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2125 | Process Equipment Datasheet - 10-E-2125 - Distillate Stripper Reboiler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00265
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2126 | Process Equipment Datasheet - 10-P-2126 A-B - Distillate Stripper Bottom Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371
Return Date
Owner Cmmt*
| PE | OL1-2G30-2136 | Process Equipment Datasheet - 10-D-2136 - Process Water Feed Coalescer |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453
Return Date
Owner Cmmt*
| PE | OL1-2G30-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2138 | Process Equipment Datasheet - 10-F-2136 A-B Process Water Feed Filters |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350
Return Date
Owner Cmmt*
| PE | OL1-2G30-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00189 | TPSK-LSPA1-T-PE-00401
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2145 | Process Equipment Datasheet - 10-E-2145 - Process Water Stripper Reboiler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194
Return Date
Owner Cmmt*
| PE | OL1-2G30-2146 | Process Equipment Datasheet - 10-P-2146 A-B - DSG Feed Pumps |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00069 | TPSK-LSPA1-T-PE-00202
[6 empty] | Return Date | 2018-10-09 | 2018-11-30
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-2147 | Process Equipment Datasheet - 10-E-2146 - DSG Feed Heater |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194
Return Date
Owner Cmmt*
| PE | OL1-2G30-2160 | Process Equipment Datasheet - 10-D-2160 - Dilution Steam Generator |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00115
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2164 | PROCESS EQUIPMENT DATA SHEET - 10-D-2165 - DSG REBOILER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2165 | Process Equipment Datasheet - 10-E-2165 A-D - DSG Reboilers |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00209 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2190 | Process Equipment Datasheet - 10-D-2190 - Quench Water Drain Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00368
Return Date
Owner Cmmt*
| PE | OL1-2G30-2191 | Process Equipment Datasheet - 10-P-2190- Quench Water Drain Drum Pump |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00346
Return Date
Owner Cmmt*
| PE | OL1-2G30-2192 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2190 - QUENCH WATER DRAING SUMP EDUCTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22 | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date | 2018-09-11
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2206 | Process Equipment Datasheet - 10-E-2206 - Wash Water Cooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00381
Return Date
Owner Cmmt*
| PE | OL1-2G30-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00266 | TPSK-LSPA1-T-PE-00479
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2212 | Process Equipment Datasheet - 10-P-2210 A-B - CG 1st Stage Condensate Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
Owner Cmmt*
| PE | OL1-2G30-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercooler |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2222 | Process Equipment Datasheet - 10-P-2220 A-B - CG 2nd Stage Condensed HC Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
Owner Cmmt*
| PE | OL1-2G30-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264 | TPSK-LSPA1-T-PE-00480
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2300 | Process Equipment Datasheet - 10-T-2300 - Caustic Tower |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18 | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00060 | TPSK-LSPA1-T-PE-00290
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00383
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2302 | Process Equipment Datasheet - 10-P-2302 A-B - Strong Caustic Circulating Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00382
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2305 | Process Equipment Datasheet - 10-E-2305 - Caustic Tower Feed Heater |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00259
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00382
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00383
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00102
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00254
Return Date
Owner Cmmt*
| PE | OL1-2G30-2311 | Process Equipment Datasheet - 10-P-2310 A-B - Wash Oil Circulating Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2312 | PROCESS EQUIPMENT DATA SHEET - 10-D-2312 - SPENT WASH OIL DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2313 | Process Equipment Datasheet - 10-X-2312 - Spent Wash Oil Mixer |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2314 | Process Equipment Datasheet - 10-F-2310 A-B - Wash Oil Circulating Filter |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2315 | Process Equipment Datasheet - 10-X-2310 - Spent Caustic Mixer |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2317 | PROCESS EQUIPMENT DATA SHEET - 10-P-2316 - SPENT CAUSTIC DISCHARGE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2319 | Process Equipment Datasheet - 10-F-2320 A-B - Spent Caustic Pump Discharge Filters |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00255
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2320 | Process Equipment Datasheet - 10-TK-2320 - Spent Caustic Storage Tank |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20 | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00068 | TPSK-LSPA1-T-PE-00203
[6 empty] | Return Date | 2018-10-09 | 2018-11-30
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-2321 | Process Equipment Datasheet - 10-P-2320 A-B - Spent Caustic Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252
Return Date
Owner Cmmt*
| PE | OL1-2G30-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00111
Return Date
Owner Cmmt*
| PE | OL1-2G30-2323 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2322 - SKIM OIL SUMP EDUCTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2326 | Process Equipment Datasheet - 10-E-2326 - Spent Caustic Stripper Feed Heater |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00381
Return Date
Owner Cmmt*
| PE | OL1-2G30-2327 | PROCESS EQUIPMENT DATA SHEET - 10-D-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2328 | PROCESS EQUIPMENT DATA SHEET - 10-P-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper |  | Class 2 | Purpose** | IFA | IFA | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-10-11 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00160 | TPSK-LSPA1-T-PE-00384
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2350 | Process Equipment Datasheet - 10-PK-2350 - Wet Air Oxidation Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00180
Return Date
Owner Cmmt*
| PE | OL1-2G30-2389 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2390 - CAUSTIC DRAIN SUMP EDUCTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27 | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00369
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2391 | Process Equipment Datasheet - 10-P-2390 - Caustic Drain Drum Pump |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00444
Return Date
Owner Cmmt*
| PE | OL1-2G30-2392 | Process Equipment Datasheet - 10-D-2392 - Spent Caustic Drain Drum |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27 | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00369
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2393 | Process Equipment Datasheet - 10-P-2392 - Spent Caustic Drain Drum Pump |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252
Return Date
Owner Cmmt*
| PE | OL1-2G30-2394 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2392 - SPENT CAUSTIC DRAIN SUMP EDUCTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-14 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00315 | TPSK-LSPA1-T-PE-00480
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2406 | Process Equipment Datasheet - 10-E-2405 - Gas Dryer Feed Chiller |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00239
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439
Return Date
Owner Cmmt*
| PE | OL1-2G30-2411 | Process Equipment Datasheet - 10-D-2411 - Cracked Gas Mercury Adsorber |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00339
Return Date
Owner Cmmt*
| PE | OL1-2G30-2412 | Process Equipment Datasheet - 10-E-2412 - HP Depropanizer Feed Chiller |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00239
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2415 | Process Equipment Datasheet - 10-D-2415 - CG Liquid Dryer Feed Coalescer |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00339
Return Date
Owner Cmmt*
| PE | OL1-2G30-2416 | Process Equipment Datasheet - 10-P-2415 A-B - CG Liquid Dryer Feed Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
Owner Cmmt*
| PE | OL1-2G30-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00301
[6 empty] | Return Date | 2018-11-30
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2430 | PROCESS EQUIPMENT DATA SHEET - 10-E-2430 - REGEN GAS FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2432 | PROCESS EQUIPMENT DATA SHEET - 10-E-2432 - REGEN GAS SHP HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2434 | PROCESS EQUIPMENT DATA SHEET - 10-E-2435 - REGEN GAS EFFLUENT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2435 | PROCESS EQUIPMENT DATA SHEET - 10-D-2435 - REGEN GAS SEPARATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2436 | PROCESS EQUIPMENT DATA SHEET - 10-D-2436 - MERCURY ADSORBER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-27
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2440 | Process Equipment Datasheet - 10-T-2440 - HP Depropanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date | 2018-10-03
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2443 | Process Equipment Datasheet - 10-P-2445 A-B - HP Deprop Reboiler Cond Pump |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00408
Return Date
Owner Cmmt*
| PE | OL1-2G30-2444 | Process Equipment Datasheet - 10-D-2445 - HP Deprop Reboiler Cond Pot |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00474
Return Date
Owner Cmmt*
| PE | OL1-2G30-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00267 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2450 | Process Equipment Datasheet - 10-T-2450 - LP Depropanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date | 2018-10-03
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00259 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-27
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2453 | Process Equipment Datasheet - 10-P-2450 A-B - LP Depropanizer Reflux-Product Pump |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285
Return Date
Owner Cmmt*
| PE | OL1-2G30-2455 | Process Equipment Datasheet - 10-E-2455 A-B - LP Depropanizer Reboilers |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00228
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2456 | Process Equipment Datasheet - 10-D-2455 - LP Deprop Reboiler Cond Pot |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00474
Return Date
Owner Cmmt*
| PE | OL1-2G30-2457 | Process Equipment Datasheet - 10-P-2455 A-B - LP Deprop Reboiler Cond Pump |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00408
Return Date
Owner Cmmt*
| PE | OL1-2G30-2460 | Process Equipment Datasheet - 10-D-2460 - C2 Hydrog Arsine Guard Bed |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453
Return Date
Owner Cmmt*
| PE | OL1-2G30-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2465 | Process Equipment Datasheet - 10-E-2465 - C2 Hydrog Feed Heater |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391
Return Date
Owner Cmmt*
| PE | OL1-2G30-2466 | PROCESS EQUIPMENT DATA SHEET - 10-D-2465 - C2 HYDROG FEED HEATER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2467 | PROCESS EQUIPMENT DATA SHEET - 10-P-2465 - C2 HYDROG FEED HEATER COND PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2470 | Process Equipment Datasheet - 10-R-2470 A-C - C2 Hydrog Reactor |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00299
[6 empty] | Return Date | 2018-11-29
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2471 | Process Equipment Datasheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391
Return Date
Owner Cmmt*
| PE | OL1-2G30-2472 | Process Equipment Datasheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391
Return Date
Owner Cmmt*
| PE | OL1-2G30-2474 | Process Equipment Datasheet - 10-E-2474 - C2 Hydrog Aftercooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391
Return Date
Owner Cmmt*
| PE | OL1-2G30-2480 | Process Equipment Datasheet - 10-D-2480 - CG Secondary Dryer |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00386
Return Date
Owner Cmmt*
| PE | OL1-2G30-2500 | Process Equipment Datasheet - 10-E-2500 - Propylene Refrig Subcooler |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-11 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-09-28
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G30-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-11-05 | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00475
[6 empty] | Return Date | 2018-10-02 | 2018-11-26
[6 empty] | Owner Cmmt* | A1 | A2
| PE | OL1-2G30-2503 | Process Equipment Datasheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-02 | 2018-11-26
[6 empty] | Owner Cmmt* | A1 | A2
| PE | OL1-2G30-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07 | 2018-11-26
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2505 | Process Equipment Datasheet - 10-E2506 and 10-E2508 - Demeth Prefrac Feed Cooler No 3 and No 4 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07 | 2018-11-26
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07 | 2018-11-26
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2510 | Process Equipment Datasheet - 10-T-2510 - 10-D-2510 - Demethanizer Prefractionator & Reflux Drum |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00092 | TPSK-LSPA1-T-PE-00306
[6 empty] | Return Date | 2018-10-24 | 2018-11-29
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-2511 | Process Equipment Datasheet - 10-E-2510 - Demeth Prefrac Condenser |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1
| PE | OL1-2G30-2515 | Process Equipment Datasheet - 10-E-2515 - Demeth Prefrac Reboiler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2520 | Process Equipment Datasheet - 10-T-2520 - 10-D2520 - Residue Gas Rectifier & Reflux Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00172 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2521 | Process Equipment Datasheet - 10-E-2520 - Rectifier Condenser |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2526 | Process Equipment Datasheet - 10-E-2525 - Hydrogen Core Exchanger |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1
| PE | OL1-2G30-2531 | Process Equipment Datasheet - 10-E-2530 - Demeth Feed Cooler |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-11-09 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00306 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-10-24 | 2018-11-29
[6 empty] | Owner Cmmt* | A3 | A3
| PE | OL1-2G30-2541 | Process Equipment Datasheet - 10-E-2540 - Demethanizer Condenser |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1
| PE | OL1-2G30-2545 | Process Equipment Datasheet - 10-E-2545 - Demethanizer Reboiler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2546 | Process Equipment Datasheet - 10-E-2546 - Demethanizer Bottoms Cooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00464
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2550 | Process Equipment Datasheet - 10-TX-2550 - 10-C-2550 - Residue Gas Expander - Recompressor |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-29 | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00114
[6 empty] | Return Date | 2018-09-28 | 2018-10-24
[6 empty] | Owner Cmmt* | A3 | R1
| PE | OL1-2G30-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00190
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00191 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2571 | Process Equipment Datasheet - 10-E-2570 - Deethanizer Condenser |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-02 | 2018-11-26
[6 empty] | Owner Cmmt* | A3 | A2
| PE | OL1-2G30-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00227 | TPSK-LSPA1-T-PE-00446
[6 empty] | Return Date | 2018-12-05
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2574 | Process Equipment Datasheet - 10-D-2575 - Deethanizer Reboiler Cond Pot |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00474
Return Date
Owner Cmmt*
| PE | OL1-2G30-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A2 | A1
| PE | OL1-2G30-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A2 | A1
| PE | OL1-2G30-2577 | Process Equipment Datasheet - 10-P-2575 A-B - Deethanizer Reboiler Cond Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00408
Return Date
Owner Cmmt*
| PE | OL1-2G30-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-10-31
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2582 | Process Equipment Datasheet - 10-E-2582 - C2 Tower Reflux Cooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00265
[6 empty] | Return Date | 2018-11-20
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2585 | Process Equipment Datasheet - 10-E-2585 - C2 Tower Bottoms Reboiler |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1
| PE | OL1-2G30-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2587 | Process Equipment Datasheet - 10-E-2587 - C2 Tower Side Reboiler |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A1
| PE | OL1-2G30-2591 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439
Return Date
Owner Cmmt*
| PE | OL1-2G30-2610 | Process Equipment Datasheet - 10-D-2610 - C3 Hydrog Arsine Guard Bed |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00345
Return Date
Owner Cmmt*
| PE | OL1-2G30-2620 | PROCESS EQUIPMENT DATA SHEET - 10-R-2620 - C3 HYDROG REACTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2621 | PROCESS EQUIPMENT DATA SHEET - 10-E-2620 - C3 HYDROG AFTERCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2622 | PROCESS EQUIPMENT DATA SHEET - 10-D-2620 - C3 HYDROG RECYCLE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2623 | PROCESS EQUIPMENT DATA SHEET - 10-P-2620 - C3 HYDROG RECYCLE PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14 | 2018-10-12 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00169 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-10-03
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A2 | A2
| PE | OL1-2G30-2632 | Process Equipment Datasheet - 10-D-2630 - Secondary Deeth Reflux Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00287
Return Date
Owner Cmmt*
| PE | OL1-2G30-2633 | Process Equipment Datasheet - 10-P-2630 A-B - Secondary Deeth Reflux Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277
Return Date
Owner Cmmt*
| PE | OL1-2G30-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-11-05 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00438
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A2 | A2
| PE | OL1-2G30-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A2 | A1
| PE | OL1-2G30-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00201 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2644 | PROCESS EQUIPMENT DATA SHEET - 10-D-2645 - C3 TOWER REBOILER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12 | 2018-11-05 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00438
[6 empty] | Return Date | 2018-10-01 | 2018-11-26
[6 empty] | Owner Cmmt* | A1 | A2
| PE | OL1-2G30-2646 | Process Equipment Datasheet - 10-P-2646 A-B - Propane Recycle Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277
Return Date
Owner Cmmt*
| PE | OL1-2G30-2647 | Process Equipment Datasheet - 10-P-2647 - HP Propylene - Off Spec Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00302
Return Date
Owner Cmmt*
| PE | OL1-2G30-2660 | Process Equipment Datasheet - 10-T-2660 - Debutanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-14 | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00169
[6 empty] | Return Date | 2018-10-03
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A2 | A1
| PE | OL1-2G30-2662 | Process Equipment Datasheet - 10-D-2660 - Debutanizer Reflux Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00287
Return Date
Owner Cmmt*
| PE | OL1-2G30-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-27 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00101 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A1 | A1
| PE | OL1-2G30-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00112 | TPSK-LSPA1-T-PE-00370
[6 empty] | Return Date | 2018-10-12 | 2018-12-10
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-2667 | PROCESS EQUIPMENT DATA SHEET - 10-D-2666 - C5 / PYGAS SURGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2668 | PROCESS EQUIPMENT DATA SHEET - 10-P-2666 - C5 / PYGAS PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371
Return Date
Owner Cmmt*
| PE | OL1-2G30-2700 | PROCESS EQUIPMENT DATA SHEET - 10-R-2700 - GHU-1 REACTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2701 | PROCESS EQUIPMENT DATA SHEET - 10-E-2701 - GHU-1 FEED / EFFLUENT EXCHANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2702 | PROCESS EQUIPMENT DATA SHEET - 10-E-2702 - GHU-1 S/U HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2703 | PROCESS EQUIPMENT DATA SHEET - 10-E-2705 - GHU-1 RECYCLE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2704 | PROCESS EQUIPMENT DATA SHEET - 10-P-2705 - GHU-1 RECYCLE PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2705 | PROCESS EQUIPMENT DATA SHEET - 10-D-2705 - GHU-1 HOT SEPARATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2706 | PROCESS EQUIPMENT DATA SHEET - 10-D-2706 - GHU-1 COLD SEPARATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2707 | PROCESS EQUIPMENT DATA SHEET - 10-E-2706 - GHU-1 COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2710 | PROCESS EQUIPMENT DATA SHEET - 10-T-2710 - DEPENTANIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2711 | PROCESS EQUIPMENT DATA SHEET - 10-E-2710 -DEPENTANIZER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2712 | PROCESS EQUIPMENT DATA SHEET - 10-D-2710 - DEPENTANIZER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2713 | PROCESS EQUIPMENT DATA SHEET - 10-P-2710 - DEPENTANIZER REFLUX PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2714 | PROCESS EQUIPMENT DATA SHEET - 10-P-2714 - C5 CUT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2715 | PROCESS EQUIPMENT DATA SHEET - 10-E-2715 - DEPENTANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2716 | PROCESS EQUIPMENT DATA SHEET - 10-E-2714 - C5 CUT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2717 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2720 - RERUN TOWER EDUCTOR PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2718 | PROCESS EQUIPMENT DATA SHEET - 10-D-2720 - RERUN TOWER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2719 | PROCESS EQUIPMENT DATA SHEET - 10-P-2720 - RERUN TOWER REFLUX / PRODUCT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2720 | PROCESS EQUIPMENT DATA SHEET - 10-T-2720 - RERUN TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2721 | PROCESS EQUIPMENT DATA SHEET - 10-E-2720 - RERUN TOWER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2722 | PROCESS EQUIPMENT DATA SHEET - 10-E-2722 - GHU-1 PRODUCT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2723 | PROCESS EQUIPMENT DATA SHEET - 10-E-2724 - WASH OIL CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2724 | PROCESS EQUIPMENT DATA SHEET - 10-D-2724 - WASH OIL DEGASSING DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2725 | PROCESS EQUIPMENT DATA SHEET - 10-E-2725 - RERUN TOWER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2726 | PROCESS EQUIPMENT DATA SHEET - 10-P-2726 - PYGAS FUEL OIL PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2727 | PROCESS EQUIPMENT DATA SHEET - 10-E-2726 - PYGAS FUEL OIL COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2728 | PROCESS EQUIPMENT DATA SHEET - 10-P-2724 - RECYCLE WASH OIL PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2730 | PROCESS EQUIPMENT DATA SHEET - 10-E-2730 - HYDROG REGEN HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2735 | PROCESS EQUIPMENT DATA SHEET - 10-D-2735 - REGEN HYDROG DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2750 | PROCESS EQUIPMENT DATA SHEET - 10-D-2750 - C4 / C5 HYDROG SURGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2751 | PROCESS EQUIPMENT DATA SHEET - 10-P-2750 - C4 / C5 HYDROG FEED PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2754 | PROCESS EQUIPMENT DATA SHEET - 10-X-2755 - C4 / C5 HYDROG MIXER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2755 | PROCESS EQUIPMENT DATA SHEET - 10-E-2755 - C4 / C5 HYDROG S/U HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2760 | PROCESS EQUIPMENT DATA SHEET - 10-R-2760 - C4 / C5 HYDROG REACTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2761 | PROCESS EQUIPMENT DATA SHEET - 10-E-2761 - C4 / C5 HYDROG VENT CHILLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2762 | PROCESS EQUIPMENT DATA SHEET - 10-D-2760 - C4 / C5 HYDROG RECYCLE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2763 | PROCESS EQUIPMENT DATA SHEET - 10-E-2760 - C4 / C5 HYDROG VENT CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2764 | PROCESS EQUIPMENT DATA SHEET - 10-P-2760 - C4 / C5 HYDROG RECYCLE PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2765 | PROCESS EQUIPMENT DATA SHEET - 10-E-2765 - C4 / C5 HYDROG RECYCLE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2790 | Process Equipment Datasheet - 10-D-2790 - Light Oil Drain Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00482
Return Date
Owner Cmmt*
| PE | OL1-2G30-2791 | PROCESS EQUIPMENT DATA SHEET - 10-P-2790 - LIGHT OIL DRAIN DRUM PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2792 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-2790 - LIGHT OIL DRAIN SUMP EDUCTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22 | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date | 2018-09-11
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2801 | Process Equipment Datasheet - 10-P-2805 A-B - Propylene Product Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277
Return Date
Owner Cmmt*
| PE | OL1-2G30-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00348
[6 empty] | Return Date | 2018-11-09 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2806 | Process Equipment Datasheet - 10-E-2805 A-B - C3 Refrig Condensers |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A1 | A2
| PE | OL1-2G30-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00273
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A1 | A1
| PE | OL1-2G30-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2815 | Process Equipment Datasheet - 10-D-2815 - C3R Drain Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439
Return Date
Owner Cmmt*
| PE | OL1-2G30-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22 | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date | 2018-09-11
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A1 | A2
| PE | OL1-2G30-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* | A1 | A2
| PE | OL1-2G30-2854 | Process Equipment Datasheet - 10-D-2855 - C2R Surge Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218
[6 empty] | Return Date | 2018-11-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2855 | Process Equipment Datasheet - 10-P-2855 A-B - Ethylene Product Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00379
Return Date
Owner Cmmt*
| PE | OL1-2G30-2856 | Process Equipment Datasheet - 10-E-2855 - C2R Condenser |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-11 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-09-28 | 2018-11-26
[6 empty] | Owner Cmmt* | A2 | A1
| PE | OL1-2G30-2857 | Process Equipment Datasheet - 10-E-2857 - HP Ethylene Product Vaporizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12 | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date | 2018-10-01 | 2018-11-26
[6 empty] | Owner Cmmt* | A1 | A1
| PE | OL1-2G30-2858 | Process Equipment Datasheet - 10-E-2858 - HP Ethylene Product Superheater |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00223
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2860 | Process Equipment Datasheet - 10-D-2860 - C2R 1st Stage Suction Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208
Return Date
Owner Cmmt*
| PE | OL1-2G30-2865 | Process Equipment Datasheet - 10-D-2865 - C2R Drain Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00445
Return Date
Owner Cmmt*
| PE | OL1-2G30-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-09 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2880 | Process Equipment Datasheet - 10-D-2880 - C2R 3rd Stage Suction Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208
Return Date
Owner Cmmt*
| PE | OL1-2G30-2882 | Process Equipment Datasheet - 10-E-2882 - LP Ethylene Product Cooler No 1 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2884 | Process Equipment Datasheet - 10-E-2884 - LP Ethylene Product Cooler No 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G30-2900 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2900 - PH CTRL / CORROSION INHIBITOR INJ PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2902 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2902 - EMULSION BREAKER INJ PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2904 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2904 - WATER STRIPPER CHEMICAL INJ PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2906 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2906 - DSG ANTI-FOULANT INJ PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2910 | PROCESS EQUIPMENT DATA SHEET - 10-TK-2910 - WASH OIL DAY TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2911 | PROCESS EQUIPMENT DATA SHEET - 10-P-2910 - WASH OIL INJECTION PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2912 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2912 - CAUSTIC TOWER ANTI-FOULANT INJ PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2914 | Process Equipment Datasheet - 10-PK-2914 - Neutralization Injection Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00181
Return Date
Owner Cmmt*
| PE | OL1-2G30-2920 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2920 - POLYMERIZATION INHIBITOR INJ PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2922 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2922 - CO INJECTION PACKAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2930 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2930 - METHANOL INJECTION PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-2940 | PROCESS EQUIPMENT DATA SHEET - 10-PK-2940 - C4 POLYMER INHIBITOR INJECTION PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3000 | PROCESS EQUIPMENT DATA SHEET - 10-T-3000 - PREDISTILLATION TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3001 | PROCESS EQUIPMENT DATA SHEET - 10-E-3000 - PREDISTILLATION CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3002 | PROCESS EQUIPMENT DATA SHEET - 10-P-3002 - PREDISTILLATION FEED PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3003 | PROCESS EQUIPMENT DATA SHEET - 10-P-3000 - PREDISTILLATION REFLUX PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3004 | PROCESS EQUIPMENT DATA SHEET - 10-E-3004 - PREDISTILLATION TRIM REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3005 | PROCESS EQUIPMENT DATA SHEET - 10-E-3005 - PREDISTILLATION REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3006 | PROCESS EQUIPMENT DATA SHEET - 10-D-3000 - PREDISTILLATION REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3007 | PROCESS EQUIPMENT DATA SHEET - 10-D-3002 - PREDISTILLATION FEED DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3010 | PROCESS EQUIPMENT DATA SHEET - 10-D-3010 - C4 FEED DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3014 | PROCESS EQUIPMENT DATA SHEET - 10-E-3014 - C4 SOLVENT VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3015 | PROCESS EQUIPMENT DATA SHEET - 10-E-3015 - C4 VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3016 | PROCESS EQUIPMENT DATA SHEET - 10-P-3016 - HEAVY END DISCHARGE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3018 | PROCESS EQUIPMENT DATA SHEET - 10-E-3018 - SOLVENT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3020 | PROCESS EQUIPMENT DATA SHEET - 10-T-3020 - MAIN WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3021 | PROCESS EQUIPMENT DATA SHEET - 10-D-3020 - MAIN WASHER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3022 | PROCESS EQUIPMENT DATA SHEET - 10-P-3020 - MAIN WASHER REFLUX PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3023 | PROCESS EQUIPMENT DATA SHEET - 10-E-3020 - MAIN WASHER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3026 | PROCESS EQUIPMENT DATA SHEET - 10-P-3026 - MAIN WASHER BOTTOM PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3030 | PROCESS EQUIPMENT DATA SHEET - 10-T-3030 - AFTER WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3031 | PROCESS EQUIPMENT DATA SHEET - 10-E-3030 - AFTER WASHER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3032 | PROCESS EQUIPMENT DATA SHEET - 10-P-3030 - AFTER WASHER REFLUX PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3033 | PROCESS EQUIPMENT DATA SHEET - 10-D-3030 - AFTER WASHER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3036 | PROCESS EQUIPMENT DATA SHEET - 10-P-3036 - AFTER WASHER BOTTOM PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3040 | PROCESS EQUIPMENT DATA SHEET - 10-T-3040 - RECTIFIER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3044 | PROCESS EQUIPMENT DATA SHEET - 10-E-3044 - SOLVENT HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3045 | PROCESS EQUIPMENT DATA SHEET - 10-E-3045 - SOLVENT HEAT EXCHANGER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3046 | PROCESS EQUIPMENT DATA SHEET - 10-P-3046 - DEGASSER FEED PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3047 | PROCESS EQUIPMENT DATA SHEET - 10-P-3045 - RECTIFIER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3050 | PROCESS EQUIPMENT DATA SHEET - 10-T-3050 - DEGASSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3055 | PROCESS EQUIPMENT DATA SHEET - 10-E-3055 - DEGASSER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3056 | PROCESS EQUIPMENT DATA SHEET - 10-P-3056 - DEGASSER BOTTOM PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3060 | PROCESS EQUIPMENT DATA SHEET - 10-T-3060 - ACETYLENE WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3061 | PROCESS EQUIPMENT DATA SHEET - 10-E-3060 - ACETYLENE WASHER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3062 | PROCESS EQUIPMENT DATA SHEET - 10-E-3062 - ACETYLENE CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3063 | PROCESS EQUIPMENT DATA SHEET - 10-P-3060 - WWASTE WATER PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3064 | PROCESS EQUIPMENT DATA SHEET - 10-P-3062 - C4 ACETYLENE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3065 | PROCESS EQUIPMENT DATA SHEET - 10-P-3061 - WASTE HC PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3066 | PROCESS EQUIPMENT DATA SHEET - 10-D-3062 - ACETYLENE ACCUMULATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3067 | PROCESS EQUIPMENT DATA SHEET - 10-D-3060 - C4 FEED DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3070 | PROCESS EQUIPMENT DATA SHEET - 10-T-3070 - DIRECT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3071 | PROCESS EQUIPMENT DATA SHEET - 10-C-3070 - RECYCLE GAS COMPRESSOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3072 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-3070 - RECYCLE GAS STEAM EJECTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3073 | Process Equipment Data Sheet - 10-C-3070 - BDU Recycle Gas Compressor |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00344
Return Date
Owner Cmmt*
| PE | OL1-2G30-3076 | PROCESS EQUIPMENT DATA SHEET - 10-P-3076 - DIRECT COOLER PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3080 | PROCESS EQUIPMENT DATA SHEET - 10-T-3080 - BUTADIENE TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3081 | PROCESS EQUIPMENT DATA SHEET - 10-D-3080 - BUTADIENE TOWER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3082 | PROCESS EQUIPMENT DATA SHEET - 10-E-3080 - BUTADIENE TOWER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3084 | PROCESS EQUIPMENT DATA SHEET - 10-E-3084 - BUTADIENE TOWER TRIM REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3085 | PROCESS EQUIPMENT DATA SHEET - 10-E-3085 - BUTADIENE TOWER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3086 | PROCESS EQUIPMENT DATA SHEET - 10-P-3086 - C4 / C5 HC PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3087 | PROCESS EQUIPMENT DATA SHEET - 10-P-3080 - BUTADIENE TOWER REFLUX PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3090 | PROCESS EQUIPMENT DATA SHEET - 10-T-3090 - BUTADIENE DRYING TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3095 | PROCESS EQUIPMENT DATA SHEET - 10-E-3095 - BUTADIENE DRYING TOWER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3096 | PROCESS EQUIPMENT DATA SHEET - 10-E-3096 - BUTADIENE PRODUCT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3097 | PROCESS EQUIPMENT DATA SHEET - 10-P-3096 - BUTADIENE PRODUCT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3098 | PROCESS EQUIPMENT DATA SHEET - 10-E-3098 - BUTADIENE PRODUCT SUBCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3100 | PROCESS EQUIPMENT DATA SHEET - 10-D-3100 - SOLVENT REGEN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3101 | PROCESS EQUIPMENT DATA SHEET - 10-A-3100 - SOLVENT REGEN AGITATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3110 | PROCESS EQUIPMENT DATA SHEET - 10-T-3110 - WATER WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3111 | PROCESS EQUIPMENT DATA SHEET - 10-D-3110 - WATER WASHER ACCUMULATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3112 | PROCESS EQUIPMENT DATA SHEET - 10-E-3110 - WATER WASHER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3113 | PROCESS EQUIPMENT DATA SHEET - 10-P-3110 - SOLVENT RETURN PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3120 | PROCESS EQUIPMENT DATA SHEET - 10-E-3120 - REGEN STEAM EJECTOR COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3121 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-3121 - REGEN STEAM EJECTOR NO. 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3122 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-3120 - REGEN STEAM EJECTOR NO. 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3123 | PROCESS EQUIPMENT DATA SHEET - 10-PK-3120 - REGEN STEAM EJECTOR PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3126 | PROCESS EQUIPMENT DATA SHEET - 10-D-3126 - EJECTOR SEAL DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3127 | PROCESS EQUIPMENT DATA SHEET - 10-P-3126 - WASTE WATER RETURN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3150 | PROCESS EQUIPMENT DATA SHEET - 10-E-3150 - CONDENSATE HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3151 | PROCESS EQUIPMENT DATA SHEET - 10-D-3150 - CONDENSATE FLASH DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3160 | PROCESS EQUIPMENT DATA SHEET - 10-E-3160 - CONDENSATE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3161 | PROCESS EQUIPMENT DATA SHEET - 10-D-3160 - CONDENSATE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3162 | PROCESS EQUIPMENT DATA SHEET - 10-P-3160 - CONDENSATE RECYCLE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3180 | PROCESS EQUIPMENT DATA SHEET - 10-D-3180 - BLOWDOWN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3190 | PROCESS EQUIPMENT DATA SHEET - 10-D-3190 - NMP SLOP DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3191 | PROCESS EQUIPMENT DATA SHEET - 10-EJ-3190 - NMP SLOP SUMP EDUCTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3192 | PROCESS EQUIPMENT DATA SHEET - 10-P-3190 - SOLVENT SLOP PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3900 | PROCESS EQUIPMENT DATA SHEET - 10-TK-3900 - NMP STORAGE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3901 | PROCESS EQUIPMENT DATA SHEET - 10-P-3900 - NMP STORAGE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3902 | PROCESS EQUIPMENT DATA SHEET - 10-P-3902 - SOLVENT INHIBITOR DOSING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3903 | PROCESS EQUIPMENT DATA SHEET - 10-D-3902 - SOLVENT INHIBITOR DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3904 | PROCESS EQUIPMENT DATA SHEET - 10-D-3904 - PRODUCT INHIBITOR DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3905 | PROCESS EQUIPMENT DATA SHEET - 10-P-3904 - PRODUCT INHIBITOR DOSING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3906 | PROCESS EQUIPMENT DATA SHEET - 10-D-3906 - ANTI FOAM AGENT DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3907 | PROCESS EQUIPMENT DATA SHEET - 10-P-3906 - ANTIFOAM DOSING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3908 | PROCESS EQUIPMENT DATA SHEET - 10-D-3908 - PREDISTILLATION INHIBITOR DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-3909 | PROCESS EQUIPMENT DATA SHEET - 10-P-3908 - PREDISTILLATION INHIBITOR DOSING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-4002 | AOCS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-4005 | API FIRED HEATER DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5002 | AOCS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5005 | API FIRED HEATER DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5100 | Process Equipment Datasheet - 10-D-5100 - Deaerator |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09 | 2018-11-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00151 | TPSK-LSPA1-T-PE-00318
[6 empty] | Return Date | 2018-11-05
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00366
[6 empty] | Return Date | 2018-11-14 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5110 | Process Equipment Datasheet - 10-TK-5110 - Condensate Tank |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00374
Return Date
Owner Cmmt*
| PE | OL1-2G30-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-00363
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5112 | Process Equipment Datasheet - 10-D-5112 - Suspect Condensate Flash Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00274
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00366
[6 empty] | Return Date | 2018-11-14 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5114 | Process Equipment Datasheet - 10-D-5114 - LP Condensate Flash Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00274
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5115 | Process Equipment Datasheet - 10-PK-5115 - Condensate Carbon Filter Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00362
Return Date
Owner Cmmt*
| PE | OL1-2G30-5120 | Process Equipment Datasheet - 10-TK-5120 - Raw Condensate Tank |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00364
Return Date
Owner Cmmt*
| PE | OL1-2G30-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-00363
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5125 | Process Equipment Datasheet - 10-PK-5125 - Condensate Polisher Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00373
Return Date
Owner Cmmt*
| PE | OL1-2G30-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331
[6 empty] | Return Date | 2018-12-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5141 | Process Equipment Datasheet - 10-P-5140 A-B - Intermittent Blowdown Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-12-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-12-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5201 | Process Equipment Datasheet - 10-E-5200 - MP Ethylene Superheater |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00275
[6 empty] | Return Date | 2018-11-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00321
Return Date
Owner Cmmt*
| PE | OL1-2G30-5211 | PROCESS EQUIPMENT DATA SHEET - 10-D-5210 - PILOT GAS VAPORIZER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5220 | PROCESS EQUIPMENT DATA SHEET - 10-E-5220 - PILOT GAS SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5350 | Process Equipment Datasheet - 10-PK-5350 - Cooling Tower |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25 | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00226
[6 empty] | Return Date | 2018-10-13 | 2018-11-14
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-5351 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5351 - OLEFINS CW PUMPS SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-10-24 | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075
[6 empty] | Return Date |  | 2018-11-14 | 2018-11-14
[6 empty] | Owner Cmmt* |  | A1 | A1
| PE | OL1-2G30-5355 | Process Equipment Datasheet - 10-PK-5355 - Side Stream Filter Pkg |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25 | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00226
[6 empty] | Return Date | 2018-10-13 | 2018-11-14
[6 empty] | Owner Cmmt* | A3 | A1
| PE | OL1-2G30-5360 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5360 - CTU CW PUMPS SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps |  | Class 2 | Purpose** | IFA | IFD | IFD
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24 | 2018-10-24 | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075
[6 empty] | Return Date | 2018-10-24 | 2018-11-14 | 2018-11-14
[6 empty] | Owner Cmmt* | A3 | A1 | A1
| PE | OL1-2G30-5370 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5370 - CW FILTER BACKWASH SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5371 | PROCESS EQUIPMENT DATA SHEET - 10-P-5370 - CW FILTER BACKWASH PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5390 | Process Equipment Datasheet - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375
Return Date
Owner Cmmt*
| PE | OL1-2G30-5392 | Process Equipment Datasheet - 10-PK-5392 - Mild Steel Corr Inhibitor Inj Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375
Return Date
Owner Cmmt*
| PE | OL1-2G30-5394 | Process Equipment Datasheet - 10-PK-5394 - Dispersant Inj Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375
Return Date
Owner Cmmt*
| PE | OL1-2G30-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375
Return Date
Owner Cmmt*
| PE | OL1-2G30-5398 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5398 - 98% SULFURIC ACID INJ PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00485
Return Date
Owner Cmmt*
| PE | OL1-2G30-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00168 | TPSK-LSPA1-T-PE-00417
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5501 | PROCESS EQUIPMENT DATA SHEET - 10-P-5500 - HOT BLOWDOWN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5510 | Process Equipment Datasheet - 10-D-5510 - Cold Flare Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00397
Return Date
Owner Cmmt*
| PE | OL1-2G30-5511 | PROCESS EQUIPMENT DATA SHEET - 10-E-5510 - COLD FLARE BLOWDOWN VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5512 | PROCESS EQUIPMENT DATA SHEET - 10-E-5512 - COLD FLARE SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5513 | PROCESS EQUIPMENT DATA SHEET - 10-E-5513 - METHANOL VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5514 | PROCESS EQUIPMENT DATA SHEET - 10-D-5513 - METHANOL VAPROIZER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5515 | PROCESS EQUIPMENT DATA SHEET - 10-D-5515 - METHANOL MAKE-UP DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5520 | Process Equipment Datasheet - 10-D-5520 - Vent Collection Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00365
Return Date
Owner Cmmt*
| PE | OL1-2G30-5521 | Process Equipment Datasheet - 10-PK-5520 - LP Vent Blower Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00332
[6 empty] | Return Date | 2018-12-06
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00142 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5551 | PROCESS EQUIPMENT DATA SHEET - 10-P-5550 - HP FLARE KNOCK OUT DRUM PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439
Return Date
Owner Cmmt*
| PE | OL1-2G30-5553 | PROCESS EQUIPMENT DATA SHEET - 10-E-5552 - LPG VAPORIZER / SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5554 | PROCESS EQUIPMENT DATA SHEET - 10-P-5552 - LPG UNLOADING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5560 | Process Equipment Datasheet - 10-PK-5560 - HP - Polyolefins Flare Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00398
Return Date
Owner Cmmt*
| PE | OL1-2G30-5565 | PROCESS EQUIPMENT DATA SHEET - 10-D-5565 - LLDPE LP FLARE KNOCK OUT DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5570 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5570 - ENCLOSED GROUND FLARE PACKAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5600 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5600 - PYGAS AREA OILY WASTEWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5601 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5601 - BUTADIENE AREA OILY WASTEWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5602 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5602 - QW AREA OILY WASTEWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5603 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5603 - CGC AREA OILY WASTEWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5604 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5604 - REFRIG AREA OILY WASTEWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5605 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5605 - FURNACE AREA OILY WASTEWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5606 | PROCESS EQUIPMENT DATA SHEET - 10-P-5600 - PYGAS AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5607 | PROCESS EQUIPMENT DATA SHEET - 10-P-5601 - BUTADIENE AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5608 | PROCESS EQUIPMENT DATA SHEET - 10-P-5602 - QW AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5609 | PROCESS EQUIPMENT DATA SHEET - 10-P-5603 - CGC AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5610 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5610 - HYDROBLAST SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5611 | PROCESS EQUIPMENT DATA SHEET - 10-P-5610 - HYDROBLAST PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5612 | Process Equipment Datasheet - 10-F-5610 - Hydroblast Filter |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00454
Return Date
Owner Cmmt*
| PE | OL1-2G30-5613 | PROCESS EQUIPMENT DATA SHEET - 10-P-5604 - REFRIG AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5614 | PROCESS EQUIPMENT DATA SHEET - 10-P-5605 - FURNACE AREA OILY WATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5615 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5615 - OLEFINS STORMWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5616 | PROCESS EQUIPMENT DATA SHEET - 10-P-5615 - OLEFINS STORMWATER SUMP PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5620 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5620 - OLEFINS HOLDING BASIN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5621 | PROCESS EQUIPMENT DATA SHEET - 10-P-5621 - OLEFINS HOLDING BASIN SKIM OIL PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5622 | PROCESS EQUIPMENT DATA SHEET - 10-P-5620 - OLEFINS HOLDING BASIN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5625 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5625 - SANITARY LIFT STATION IFAR 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5626 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5626 - SANITARY LIFT STATION IFAR 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5627 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5627 - SANITARY LIFT STATION WEST GATE HOUSE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5628 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5628 - SANITARY LIFT STATION EAST GATE HOUSE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5630 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5630 - CT AREA OILY WASTEWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5631 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5631 - CWWT AREA OILY WASTEWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5632 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5632 - HP FLARE AREA OILY WASTEWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5633 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5633 - HP FLARE AREA STORMWATER SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5635 | PROCESS EQUIPMENT DATA SHEET - 10-P-5630 - CT AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5636 | PROCESS EQUIPMENT DATA SHEET - 10-P-5631 - CWWT AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5637 | PROCESS EQUIPMENT DATA SHEET - 10-P-5632 - HP FLARE AREA OILY WASTEWATER SUMP PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5638 | PROCESS EQUIPMENT DATA SHEET - 10-P-5633 - HP FLARE AREA STORMWATER SUMP PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5640 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5640 - OILY WASTEWATER EQUALIZATION TANKS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5641 | PROCESS EQUIPMENT DATA SHEET - 10-P-5641 - WASTEWATER EQ TANK SKIMMED OIL PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5642 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5642 - COOLING WATER BLOWDOWN BASIS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5643 | PROCESS EQUIPMENT DATA SHEET - 10-P-5642 - COOLING WATER BD BASIN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5645 | PROCESS EQUIPMENT DATA SHEET - 10-P-5640 - OILY WASTEWATER EQ TANK PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00282 | TPSK-LSPA1-T-PE-00441
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5654 | PROCESS EQUIPMENT DATA SHEET - 10-P-5655 - EQUALIZATION PIT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5655 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5655 - EQUALIZATION PIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5656 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5656 - FINAL CHECK BASIN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5657 | PROCESS EQUIPMENT DATA SHEET - 10-P-5656 - FINAL CHECK BASIN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5658 | PROCESS EQUIPMENT DATA SHEET - 10-PIT-5658 - FINAL CHECK PIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442
[6 empty] | Return Date | 2018-11-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5674 | PROCESS EQUIPMENT DATA SHEET - 10-P-5675 - SLOP OIL TRANSFER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5675 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5675 - SLOP OIL TANKS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5676 | PROCESS EQUIPMENT DATA SHEET - 10-TK-5676 - OILY SLUDGE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5677 | PROCESS EQUIPMENT DATA SHEET - 10-P-5676 - OILY SLUDGE TRANSFER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5690 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5690 - SLOP TANK POLYMER INJECTION PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5692 | PROCESS EQUIPMENT DATA SHEET - 10-PK-5692 - SLOP OIL TANK ACID INJECTION PKG |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5900 | Process Equipment Datasheet - 10-TK-5900 - Sulfuric Acid Tank |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00364
Return Date
Owner Cmmt*
| PE | OL1-2G30-5901 | PROCESS EQUIPMENT DATA SHEET - 10-P-5900 - SULFURIC ACID PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456
Return Date
Owner Cmmt*
| PE | OL1-2G30-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456
Return Date
Owner Cmmt*
| PE | OL1-2G30-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456
Return Date
Owner Cmmt*
| PE | OL1-2G30-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00406
Return Date
Owner Cmmt*
| PE | OL1-2G30-5951 | PROCESS EQUIPMENT DATA SHEET - 10-P-5950 - SODIUM HYPOCHLORITE METERING PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-6002 | AOCS PDS (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G30-6005 | API FIRED HEATER DATA SHEET (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-4G30-1001 | Process Equipment Datasheet - USC 36M Cracking Furnace Yields |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00117
Return Date
Owner Cmmt*
| PE | OL1-4G30-1008 | See document number 036909C-1011-PDS-0630-1108 or OL1-2G30-1108 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-1009 | See document number 036909C-1011-PDS-0610-1109 or OL1-2G30-1109 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-1010 | See document number 036909C-1011-PDS-0610-1110 or OL1-2G30-1110 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-1011 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-4G30-2001 | Process Equipment Datasheet - USC 132U Cracking Furnace Yields |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00117
Return Date
Owner Cmmt*
| PE | OL1-4G30-2008 | See document number 036909C-1012-PDS-0630-1208 or OL1-2G30-1208 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-2009 | See document number 036909C-1012-PDS-0610-1209 or OL1-2G30-1209 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-2011 | Process Equipment Data sheet - 10-C-1200-1600 - USC 132U Induced Draft Fan |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
Category Code: G31 Process Instrument Data sheets
| PE | OL1-2G31-1112 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-11YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-1212 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-12YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-1312 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-13YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-1412 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-14YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-1512 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-15YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-1612 | ATTEMPERATOR DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-16YY | RESTRICTION ORIFICE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXA | AREA 30 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXB | AREA 53 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXC | AREA 55 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXD | AREA 56 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G31-XXXX | RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G32 Process Safety Valve Data sheets
| PE | OL1-2G32-11XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-12XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-13XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-14XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-15XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-16XX | PRESSURE RELIEF VALVE DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXA | AREA 30 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXB | AREA 53 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXC | AREA 55 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXD | AREA 56 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G32-XXXE | PSV DATA SHEETS & INDEX & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G40 Block Flow Diagram
| PE | OL1-2G40-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme |  | Class 3 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
Category Code: G41 Process Flow Diagrams
| PE | OL1-2G41-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam and Condensate System |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G41-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
Category Code: G42 Utility Flow Diagrams
| PE | OL1-2G42-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable and Demin Water Systems |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate and Boiler Feedwater Systems |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air and Nitrogen Systems |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare and Blowdown System |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
| PE | OL1-2G42-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage |  | Class 2 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-23 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155
[6 empty] | Return Date | 2018-10-29
[6 empty] | Owner Cmmt* | A3
Category Code: G43 Process and Instrument Diagrams (P&ID)
| PE | OL1-2G43-0001 | P&ID - Olefins Unit 10 - Common - Abbreviations And Numbering |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-0002 | P&ID - Olefins Unit 10 - Common - Piping Symbols |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-0003 | P&ID - Olefins Unit 10 - Common - Instrumentation Symbols |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-0004 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 1 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-0005 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 2 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-0010 | P&ID - Olefins Unit 10 - Common - Instrument Details |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-0011 | P&ID - Olefins Unit 10 - Common - EIV Block Valves Typical |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1001 | P&ID - FEED PREPARATION - FURNACE LIQUID FEED |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1002 | P&ID - FEED PREPARATION - FURNACE LPG FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1003 | P&ID - FEED PREPARATION - FURNACE LPG FEED VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1004 | P&ID - FEED PREPARATION - FURNACE LPG FEED SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1023 | P&ID - FEED PREPARATION - C2 FEED SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1030 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1031 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1035 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION (UTILITY) - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1036 | P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION (UTILITY) - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed-Sheet 4 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent And Decoke MOVs |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - SHP Steam Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply Export Steam |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1160 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 UTILITY STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1170 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 UTILITY DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV's |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SLE Drain Header |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - VHP Steam Drum |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-SLE And TLX Risers |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply Export Steam |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
Return Date
Owner Cmmt*
| PE | OL1-2G43-1260 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 UTILITY STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1261 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 UTILITY DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1315 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 CONVECTION SECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1316 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1317 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1318 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1319 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1320 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1321 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1325 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 TLX EXCHANGER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1327 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1328 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 VHP STEAM DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1329 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1331 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM COILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1340 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 BURNERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1345 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 DECOKING EFFLUENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1350 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 FLUE GAS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1360 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1361 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1415 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 CONVECTION SECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1416 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1417 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1418 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1419 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1420 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1421 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1425 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 TLX EXCHANGER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1427 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1428 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 VHP STEAM DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1429 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1431 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM COILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1440 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 BURNERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1445 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 DECOKING EFFLUENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1450 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 FLUE GAS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1460 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1461 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1515 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 CONVECTION SECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1516 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1517 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1518 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1519 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1520 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1521 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1525 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 TLX EXCHANGER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1527 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1528 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 VHP STEAM DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1529 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1531 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM COILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1540 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 BURNERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1545 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 DECOKING EFFLUENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1550 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 FLUE GAS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1560 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1561 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1615 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 CONVECTION SECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1616 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1617 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1618 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1619 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1620 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1621 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1625 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 TLX EXCHANGER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1627 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 INTERMITTENT BLOWDOWN HEADER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1628 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 VHP STEAM DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1629 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM DRUM-USX AND TLX RISERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1631 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM COILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1640 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 BURNERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1645 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 DECOKING EFFLUENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1650 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 FLUE GAS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1660 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1661 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1901 | P&ID - FEED PREPARATION & FURNACES AUX - DMDS INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1910 | P&ID - FEED PREPARATION & FURNACES AUX - DECOKE COMPRESSOR - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1911 | P&ID - FEED PREPARATION & FURNACES AUX - DECOKE COMPRESSOR - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1915 | P&ID - FEED PREPARATION & FURNACES AUX - DECOKE AIR RECEIVER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2001 | P&ID - QUENCH OIL - QUENCH OIL FRACTIONATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2003 | P&ID - QUENCH OIL - QUENCH OIL CIRCULATING PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2005 | P&ID - QUENCH OIL - QUENCH OIL FILTRATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2006 | P&ID - QUENCH OIL - VLP STEAM GENERATION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2007 | P&ID - QUENCH OIL - VLP STEAM GENERATION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2020 | P&ID - QUENCH OIL - LIGHT FUEL OIL STRIPPER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2021 | P&ID - QUENCH OIL - FUEL OIL PRODUCT COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2022 | P&ID - QUENCH OIL - FUEL OIL FILTRATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2025 | P&ID - QUENCH OIL - HEAVY FUEL OIL STRIPPER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2026 | P&ID - QUENCH OIL - HEAVY FUEL OIL PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2027 | P&ID - QUENCH OIL - HEAVY FUEL OIL PRODUCT COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2040 | P&ID - QUENCH OIL DRAIN COLLECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2042 | P&ID - QUENCH OIL DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2101 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2102 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2104 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH OIL FRACTIONATOR REFLUX |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2106 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2108 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2110 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2115 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DRAIN DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2117 | P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2120 | P&ID - QUENCH WATER / DILUTION STEAM - DISTILLATE STRIPPER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2122 | P&ID - QUENCH WATER / DILUTION STEAM - DISTILLATE STRIPPER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2123 | P&ID - QUENCH WATER / DILUTION STEAM - PROCESS WATER STRIPPER FEED |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2125 | P&ID - QUENCH WATER / DILUTION STEAM - PROCESS WATER STRIPPER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2126 | P&ID - QUENCH WATER / DILUTION STEAM - PRCOESS WATER STRIPPER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2127 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR FEED PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2130 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR FEED HEATING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2131 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2132 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2133 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2134 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2135 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2137 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM SUPERHEATING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2138 | P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM BLOWDOWN COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2201 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS 1ST STAGE SUCTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2203 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 1ST AND 2ND STAGES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2204 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 1ST STAGE AFTERCOOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2206 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 2ND STAGE SUCTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2208 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 2ND STAGE AFTERCOOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2210 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD STAGE SUCTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2211 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD AND 4TH STAGES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2212 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD STAGE AFTERCOOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2214 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE SUCTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2215 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE AFTERCOOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2217 | P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE DISCHARGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2220 | P&ID - CRACKED GAS COMPRESSION - WASH WATER COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2222 | P&ID - CRACKED GAS COMPRESSION - WASH WATER INJECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2224 | P&ID - CRACKED GAS COMPRESSION - WASH OIL INJECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2301 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2303 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - WEAK/INTERMEDIATE CAUSTIC CIRCULATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2305 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - STRONG CAUSTIC CIRCULATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2310 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - FRESH CAUSTIC STORAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2311 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DEOILING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2313 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DEGASSING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2315 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT WASH OIL DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2316 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC DRAIN SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2318 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DRAIN SUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2319 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SKIM OIL DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2320 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2325 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER FEED HEATING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2326 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2328 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2329 | P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - WAO PACKAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2401 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CAUSTIC TOWER OVERHEAD CHILLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2402 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CAUSTIC TOWER OVERHEAD KO DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2404 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIER FEED COALESCER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2406 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIERS - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2407 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIERS - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2409 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2410 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2411 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2412 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION GAS HEATING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2414 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION GAS COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2416 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - FUEL GAS MERCURY ABSORBER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2419 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS MERCURY ABSORBER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2420 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER FEED CHILLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2422 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2423 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2425 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2426 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2427 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2428 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER PRODUCT/REFLUX PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2430 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - 5TH STAGE CRACKED GAS COMPRESSION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2432 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS COMPRESSOR 5TH STAGE AFTERCOOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2433 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION FEED ARSINE REMOVAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2435 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION FEED HEATING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2437 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2438 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR A INTERCOOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2439 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2440 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR B INTERCOOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2442 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2444 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CG SECONDARY DEHYDRATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2446 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REFLUX CHILLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2447 | P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REFLUX |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2501 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED CHILLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2503 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2505 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2507 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2511 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2513 | P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2515 | P&ID - COLD FRACTIONATION - RESIDUE GAS RECTIFIER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2517 | P&ID - COLD FRACTIONATION - RESIDUE GAS RECTIFIER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2520 | P&ID - COLD FRACTIONATION - DEMETHANIZER FEED COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2521 | P&ID - COLD FRACTIONATION - DEMETHANIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2522 | P&ID - COLD FRACTIONATION - DEMETHANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2525 | P&ID - COLD FRACTIONATION - RESIDUE GAS EXPANDER SUCTION/DISCHARGE DRUMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2527 | P&ID - COLD FRACTIONATION - RESIDUE GAS EXPANDER/RECOMPRESSOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2529 | P&ID - COLD FRACTIONATION - HYDROGEN RECOVERY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2530 | P&ID - COLD FRACTIONATION - PROPYLENE REFRIGERANT SUBCOOLER SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2531 | P&ID - COLD FRACTIONATION - PROPYLENE REFRIGERANT SUBCOOLER SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2532 | P&ID - COLD FRACTIONATION - PRESSURE SWING ABSORPTION UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2541 | P&ID - COLD FRACTIONATION - DEETHANIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2543 | P&ID - COLD FRACTIONATION - DEETHANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2546 | P&ID - COLD FRACTIONATION - DEETHANIZER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2547 | P&ID - COLD FRACTIONATION - DEETHANIZER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2551 | P&ID - COLD FRACTIONATION - DEMETHANIZER BOTTOMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2552 | P&ID - COLD FRACTIONATION - C2 SPLITTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2553 | P&ID - COLD FRACTIONATION - C2 SPLITTER BOTTOMS REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2554 | P&ID - COLD FRACTIONATION - C2 SPLITTER INTER-REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2556 | P&ID - COLD FRACTIONATION - ETHANE RECYCLE PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2601 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION ARSINE GUARD BED |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2602 | P&ID - HOT FRACTIONATION - C3 GUARD ADSORBERS - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2603 | P&ID - HOT FRACTIONATION - C3 GUARD ADSORBERS - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2605 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION REACTORS - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2606 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION REACTORS - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2608 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION AFTERCOOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2610 | P&ID - HOT FRACTIONATION - C3 HYDROGENATION RECYCLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2615 | P&ID - HOT FRACTIONATION - SECONDARY DEETHANIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2616 | P&ID - HOT FRACTIONATION - SECONDARY DEETHANIZER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2620 | P&ID - HOT FRACTIONATION - C3 SPLITTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2621 | P&ID - HOT FRACTIONATION - C3 SPLITTER REBOILERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2622 | P&ID - HOT FRACTIONATION - C3 SPLITTER BOTTOMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2625 | P&ID - HOT FRACTIONATION - DEBUTANIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2627 | P&ID - HOT FRACTIONATION - DEBUTANIZER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2628 | P&ID - HOT FRACTIONATION - DEBUTANIZER OVERHEAD PRODUCT/REFLUX |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2629 | P&ID - HOT FRACTIONATION - DEBUTANIZER BOTTOMS COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2630 | P&ID - HOT FRACTIONATION - C5/PYGAS SURGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2701 | P&ID - GHU & C4/C5 HYDROG - GHU-1 FEED HEATING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2702 | P&ID - GHU & C4/C5 HYDROG - GHU-1 REACTORS - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2703 | P&ID - GHU & C4/C5 HYDROG - GHU-1 REACTORS - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2704 | P&ID - GHU & C4/C5 HYDROG - GHU-1 HOT SEPARATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2705 | P&ID - GHU & C4/C5 HYDROG - GHU-1 COLD SEPARATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2706 | P&ID - GHU & C4/C5 HYDROG - GHU-1 DEPENTANIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2707 | P&ID - GHU & C4/C5 HYDROG - GHU C5 CUT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2708 | P&ID - GHU & C4/C5 HYDROG - GHU-1 DEPENTANIZER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2710 | P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2711 | P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2712 | P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER REFLUX/PRODUCT PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2713 | P&ID - GHU & C4/C5 HYDROG - GHU-1 PRODUCT COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2715 | P&ID - GHU & C4/C5 HYDROG - GHU-1 RECYCLE WASH OIL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2716 | P&ID - GHU & C4/C5 HYDROG - PYGAS FUEL OIL PRODUCT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2720 | P&ID - GHU & C4/C5 HYDROG - REACTIVATION GAS HEATING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2722 | P&ID - GHU & C4/C5 HYDROG - REGENERATION DECOKE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2730 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED SURGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2732 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2733 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED HEATING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2734 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION REACTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2736 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION RECYCLE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2737 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION VENT CHILLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2738 | P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION RECYCLE/PRODUCT COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2740 | P&ID - GHU & C4/C5 HYDROG - LIGHT OIL DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2801 | P&ID - REFRIGERATION - C3 REFRIGERANT COMPRESSOR SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2802 | P&ID - REFRIGERATION - C3 REFRIGERANT COMPRESSOR SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2803 | P&ID - REFRIGERATION - C3 REFRIGERANT CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2804 | P&ID - REFRIGERATION - C3 REFRIGERANT RECEIVER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2805 | P&ID - REFRIGERATION - HP C3 REFRIGERATION DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2806 | P&ID - REFRIGERATION - C3 REFRIGERANT 4TH STAGE SUCTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2808 | P&ID - REFRIGERATION - C3 REFRIGERANT 3RD STAGE SUCTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2810 | P&ID - REFRIGERATION - C3 REFRIGERANT 2ND STAGE SUCTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2812 | P&ID - REFRIGERATION - C3 REFRIGERANT 1ST STAGE SUCTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2814 | P&ID - REFRIGERATION - C3 REFRIGERANT DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2815 | P&ID - REFRIGERATION - C3 REFRIGERANT DRAIN COLLECTION HEADER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2816 | P&ID - REFRIGERATION - PROPYLENE PRODUCT PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2818 | P&ID - REFRIGERATION - PROPYLENE PRODUCT CHILLING SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2819 | P&ID - REFRIGERATION - PROPYLENE PRODUCT CHILLING SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2821 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT COMPRESSOR SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2822 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT COMPRESSOR SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2824 | P&ID - REFRIGERATION - C2 REFRIGERANT DESUPERHEATERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2825 | P&ID - REFRIGERATION - C2 REFRIGERANT DESUPERHEATERS AND CONDENSING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2828 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT SURGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2830 | P&ID - REFRIGERATION - HP ETHYLENE LIQUID PRODUCT CHILLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2834 | P&ID - REFRIGERATION - HP ETHYLENE VAPOR PRODUCT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2836 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 3RD STAGE SUCTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2838 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 2ND STAGE SUCTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2840 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 1ST STAGE SUCTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2842 | P&ID - REFRIGERATION - LP ETHYLENE PRODUCT COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2844 | P&ID - REFRIGERATION - C2 REFRIGERANT DRAIN COLLECTION HEADER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2846 | P&ID - REFRIGERATION - ETHYLENE REFRIGERANT DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2901 | P&ID - OLEFINS RECOVERY AUXILLARY - EMULSION BREAKER INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2902 | P&ID - OLEFINS RECOVERY AUXILLARY - PH CONTROL INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2903 | P&ID - OLEFINS RECOVERY AUXILLARY - POLYMERIZATION INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2904 | P&ID - OLEFINS RECOVERY AUXILLARY - PROCESS WATER STRIPPER CHEMICAL INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2905 | P&ID - OLEFINS RECOVERY AUXILLARY - CORROSION INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2906 | P&ID - OLEFINS RECOVERY AUXILLARY - DSG ANTI-FOULANT INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2915 | P&ID - OLEFINS RECOVERY AUXILLARY - WASH OIL STORAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2920 | P&ID - OLEFINS RECOVERY AUXILLARY - QUENCH OIL PUMP TURBINE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2922 | P&ID - OLEFINS RECOVERY AUXILLARY - QUENCH WATER PUMP TURBINE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2924 | P&ID - OLEFINS RECOVERY AUXILLARY - DSG FEED PUMP TURBINE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2930 | P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2932 | P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2934 | P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2950 | P&ID - OLEFINS RECOVERY AUXILLARY - EXPANDER/RECOMPRESSOR AUXILIARIES - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2951 | P&ID - OLEFINS RECOVERY AUXILLARY - EXPANDER/RECOMPRESSOR AUXILIARIES - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2952 | P&ID - OLEFINS RECOVERY AUXILLARY - EXPANDER/RECOMPRESSOR AUXILIARIES - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2955 | P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2960 | P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2965 | P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2970 | P&ID - OLEFINS RECOVERY AUXILLARY - C2 REFRIGERANT COMP. TURBINE DETAILS - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2975 | P&ID - OLEFINS RECOVERY AUXILLARY - C2 REFRIGERANT COMP. TURBINE DETAILS - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-2980 | P&ID - OLEFINS RECOVERY AUXILLARY - GHU RERUN TOWER EJECTOR PACKAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3001 | P&ID - C4 UNIT - PREDISTILLATION FEED DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3002 | P&ID - C4 UNIT - PREDISTILLATION FEED PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3003 | P&ID - C4 UNIT - PREDISTILLATION TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3004 | P&ID - C4 UNIT - PREDISTILLATION TOWER REBOILERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3006 | P&ID - C4 UNIT - PREDISTILLATION TOWER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3008 | P&ID - C4 UNIT - FEED VAPORIZER DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3010 | P&ID - C4 UNIT - C4 EVAPORATORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3012 | P&ID - C4 UNIT - MAIN WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3014 | P&ID - C4 UNIT - MAIN WASHER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3016 | P&ID - C4 UNIT - RECTIFIER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3017 | P&ID - C4 UNIT - RECTIFIER BOTTOMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3018 | P&ID - C4 UNIT - AFTERWASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3020 | P&ID - C4 UNIT - AFTERWASHER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3021 | P&ID - C4 UNIT - SOLVENT HEAT EXCHANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3022 | P&ID - C4 UNIT - SOLVENT HEATING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3024 | P&ID - C4 UNIT - SOLVENT COOLING/DEGASSING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3025 | P&ID - C4 UNIT - DEGASSING TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3026 | P&ID - C4 UNIT - DEGASSING TOWER REBOILERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3027 | P&ID - C4 UNIT - ACETYLENE WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3028 | P&ID - C4 UNIT - ACETYLENE CONDENSING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3029 | P&ID - C4 UNIT - HC/WATER SEPARATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3030 | P&ID - C4 UNIT - RECYCLE GAS COMPRESSION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3032 | P&ID - C4 UNIT - BUTADIENE TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3033 | P&ID - C4 UNIT - BUTADIENE TOWER REBOILERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3035 | P&ID - C4 UNIT - BUTADIENE TOWER OVERHEAD |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3037 | P&ID - C4 UNIT - BUTADIENE DRYING COLUMN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3038 | P&ID - C4 UNIT - BUTADIENE PRODUCT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3050 | P&ID - C4 UNIT - SOLVENT RECOVERY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3051 | P&ID - C4 UNIT - SOLVENT REGENERATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3053 | P&ID - C4 UNIT - SOLVENT CONDENSING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3054 | P&ID - C4 UNIT - WASH WATER ACCUMULATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3055 | P&ID - C4 UNIT - WASTE WATER RECOVERY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3060 | P&ID - C4 UNIT - CONDENSATE FLASH DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3061 | P&ID - C4 UNIT - CONDENSATE RECYCLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3901 | P&ID - C4 UNIT - SOLVENT STORAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3903 | P&ID - C4 UNIT - SOLVENT INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3905 | P&ID - C4 UNIT - PRODUCT INHIBITOR INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-3907 | P&ID - C4 UNIT - ANTI-FOAM AGENT INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5001 | P&ID - UTILITY SYSTEMS - DEMINERALIZATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5010 | P&ID - Olefins Unit 10 - Water System Treated Potable Demin - Supporting Utilities Auxiliaries Treated Water |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5020 | P&ID - UTILITY SYSTEMS - POTABLE WATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5101 | P&ID - UTILITY SYSTEMS - STEAM LETDOWN STATIONS - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5102 | P&ID - UTILITY SYSTEMS - STEAM LETDOWN STATIONS - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5105 | P&ID - UTILITY SYSTEMS - DEAERATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5110 | P&ID - UTILITY SYSTEMS - SHP BOILER FEEDWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5111 | P&ID - UTILITY SYSTEMS - BOILER FEEDWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5113 | P&ID - UTILITY SYSTEMS - SHP BOILER FEEDWATER DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5114 | P&ID - UTILITY SYSTEMS - BOILER FEEDWATER DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5115 | P&ID - UTILITY SYSTEMS - SUSPECT CONDENSATE FLASH DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5118 | P&ID - UTILITY SYSTEMS - SUSPECT CONDENSATE COOLING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5120 | P&ID - UTILITY SYSTEMS - CONDENSATE CARBON FILTERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5125 | P&ID - UTILITY SYSTEMS - RAW CONDENSATE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5127 | P&ID - UTILITY SYSTEMS - CONDENSATE POLISHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5130 | P&ID - UTILITY SYSTEMS - CONDENSATE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5132 | P&ID - UTILITY SYSTEMS - LOW PRESSURE CONDENSATE FLASH DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5134 | P&ID - UTILITY SYSTEMS - INTERMITTENT FURNACE BLOWDOWN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5140 | P&ID - UTILITY SYSTEMS - SHP STEAM DISTRIBUTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5143 | P&ID - UTILITY SYSTEMS - HP STEAM DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5144 | P&ID - UTILITY SYSTEMS - HP STEAM DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5150 | P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5151 | P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5152 | P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5160 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5161 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5162 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5163 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5164 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5165 | P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5170 | P&ID - UTILITY SYSTEMS - SHP/HP CONDENSATE COLLECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5172 | P&ID - UTILITY SYSTEMS - MP CONDENSATE COLLECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5175 | P&ID - UTILITY SYSTEMS - LP CONDENSATE COLLECTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5176 | P&ID - UTILITY SYSTEMS - LP CONDENSATE COLLECTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5179 | P&ID - UTILITY SYSTEMS - VLP CONDENSATE COLLECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5201 | P&ID - UTILITY SYSTEMS - FUEL GAS SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5203 | P&ID - UTILITY SYSTEMS - PILOT GAS VAPORIZER AND SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5210 | P&ID - UTILITY SYSTEMS - FUEL GAS DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5211 | P&ID - UTILITY SYSTEMS - FUEL GAS DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5301 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 1 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5302 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 2 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5303 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 3 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5305 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 1 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5306 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 2 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5307 | P&ID - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5310 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5311 | P&ID - Olefins Unit 10 - Cooling Water - Ctu Cooling Water Supply |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5315 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5317 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Filter Backwash |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5320 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 01 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5321 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 02 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5322 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 03 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5323 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 04 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5324 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 05 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5325 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 06 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5326 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 07 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5327 | P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 8 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5351 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5352 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5401 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5402 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5403 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5404 | P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5410 | P&ID - UTILITY SYSTEMS - INSTRUMENT AIR RECEIVER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5411 | P&ID - UTILITY SYSTEMS - INSTRUMENT AIR DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5412 | P&ID - UTILITY SYSTEMS - INSTRUMENT AIR DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5420 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5421 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5422 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5423 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5424 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5425 | P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5501 | P&ID - UTILITY SYSTEMS - HOT FLARE KO DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5502 | P&ID - UTILITY SYSTEMS - COLD FLARE KO DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5510 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5511 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5512 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5513 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5514 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5515 | P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5520 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5521 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5522 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5523 | P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5526 | P&ID - UTILITY SYSTEMS - PROPYLENE BLOWDOWN HEADER - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5527 | P&ID - UTILITY SYSTEMS - PROPYLENE BLOWDOWN HEADER - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5530 | P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5531 | P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5532 | P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5533 | P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5536 | P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5537 | P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5538 | P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5539 | P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5540 | P&ID - UTILITY SYSTEMS - VOC VENT COLLECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5551 | P&ID - UTILITY SYSTEMS - HP FLARE KO DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5553 | P&ID - UTILITY SYSTEMS - HP FLARE PILOT GAS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5555 | P&ID - UTILITY SYSTEMS - HP FLARE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5565 | P&ID - UTILITY SYSTEMS - ENCLOSED GROUND FLARE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5575 | P&ID - UTILITY SYSTEMS - LLDPE FLARE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5601 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5602 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5603 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5604 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5605 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5606 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5607 | P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 7 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5620 | P&ID - UTILITY SYSTEMS - OLEFINS STORM WATER COLLECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5630 | P&ID - UTILITY SYSTEMS - OLEFINS HOLDING BASIN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5640 | P&ID - UTILITY SYSTEMS - SANITARY LIFT STATION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5641 | P&ID - UTILITY SYSTEMS - SANITARY LIFT STATION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5651 | P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5652 | P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5653 | P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5901 | P&ID - UTILITY SYSTEMS - COOLING WATER CHEMICAL INJECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5902 | P&ID - UTILITY SYSTEMS - COOLING WATER CORROSION INHIBITOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5903 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - CW Hypochlorite Chemical Injection |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5904 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Chemical Injection |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
| PE | OL1-2G43-5905 | P&ID - UTILITY SYSTEMS - NEUTRALIZING AMINE INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5907 | P&ID - UTILITY SYSTEMS - OXYGEN SCAVENGER INJECTION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5920 | P&ID - UTILITY SYSTEMS - COOLING WATER SUPPLY PUMP TURBINES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5925 | P&ID - UTILITY SYSTEMS - SHP BFW PUMP TURBINE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5930 | P&ID - UTILITY SYSTEMS - SHP BFW LUBE OIL PUMP TURBINE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-5932 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Pumps |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491
Return Date
Owner Cmmt*
Category Code: G44 Heat and Material Balance
| PE | OL1-2G44-1001 | Overall Material Balance |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00009
[6 empty] | Return Date | 2018-08-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G44-1002 | Heat & Material Balance - Design Case 6 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032
Return Date
Owner Cmmt*
| PE | OL1-2G44-1003 | Heat & Material Balance - Design Case 8 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032
Return Date
Owner Cmmt*
| PE | OL1-2G44-1004 | Heat & Material Balance - Design Case 9 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032
Return Date
Owner Cmmt*
| PE | OL1-2G44-1010 | Heat and Material Balance - ISBL Supporting Utilities |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00128
Return Date
Owner Cmmt*
| PE | OL1-2G44-1011 | Heat & Material Balance - Cooling Water System |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00116
Return Date
Owner Cmmt*
| PE | OL1-2G44-1012 | HEAT & MATERIAL BALANCE - AREA-55 (FLARE SYSTEM) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G44-1013 | HEAT & MATERIAL BALANCE - AREA-56 (WWT SYSTEM) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G50 Interlocking Description
| PE | OL1-2G50-1001 | SHUTDOWN INTERLOCK NARRATIVE (36M FURNACE) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-2001 | SHUTDOWN INTERLOCK NARRATIVE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-3001 | SHUTDOWN INTERLOCK NARRATIVE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-4001 | SHUTDOWN INTERLOCK NARRATIVE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-5001 | SHUTDOWN INTERLOCK NARRATIVE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-6001 | SHUTDOWN INTERLOCK NARRATIVE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G60 Battery Limit and Tie-in
| PE | OL1-2G60-0001 | BATTERY LIMIT SUMMARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1101 | TIE-IN SUMMARY - FURNACE AREA 10-H-1100 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1201 | TIE-IN SUMMARY - FURNACE AREA 10-H-1200 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1301 | TIE-IN SUMMARY - FURNACE AREA 10-H-1300 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1401 | TIE-IN SUMMARY - FURNACE AREA 10-H-1400 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1501 | TIE-IN SUMMARY - FURNACE AREA 10-H-1500 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G60-1601 | TIE-IN SUMMARY - FURNACE AREA 10-H-1600 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G61 Equipment List
| PE | OL1-2G61-9001 | EQUIPMENT LIST - OLEFINS UNIT 10 |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G62 Utility Summary
| PE | OL1-2G62-1001 | Steam Balance |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00059
[6 empty] | Return Date | 2018-10-04
Owner Cmmt*
| PE | OL1-2G62-1002 | OFF-DESIGN STEAM BALANCE - DESIGN CASES |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G62-1006 | Cooling Water Balance |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00054
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G62-1008 | Fuel Balance |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00049
Return Date
Owner Cmmt*
| PE | OL1-2G62-1010 | AIR & NITROGEN BALANCES |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G62-1011 | ELECTRICAL LOAD SUMMARY |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G63 Plant Efffluent Summary
| PE | OL1-2G63-1001 | EFFLUENT SUMMARY |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G64 Catalyst, Adsobent, and Chemicals Summary
| PE | OL1-2G64-1001 | CATALYST & CHEMICAL SUMMARY |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G74 Material Selection Guideline
| PE | OL1-2G74-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-1001 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-1003 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-1101 | Material Selection Diagram - Olefins Unit 10 - 11 - Furnaces - Gas Cracking Furnace |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-1201 | Material Selection Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-1901 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-1902 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2001 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2002 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2101 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2102 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2103 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2201 | Material Selection Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2301 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2302 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2303 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2304 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2305 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2401 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2402 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2403 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2404 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2405 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2501 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2502 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2503 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2504 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2505 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2506 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2601 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2602 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2603 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2604 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2701 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 REACTOR & DEPENTANIZER |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-2702 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 RERUN TOWER |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-2703 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - HYDROG REACTIVATION GAS SYSTEM |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-2704 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-2801 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2802 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2803 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2804 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-2901 | Material Selection Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | A2
| PE | OL1-2G74-3001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU PREDISTILLATION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3002 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU EVAPORATION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3003 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU RECTIFIER |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3004 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU DEGASSING |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3005 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU FRACTIONATION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU SOLVENT REGENERATION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3102 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU STEAM AND CONDENSATE SYSTEM |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-3901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 39 C4 UNIT AUX - BDU CHEMICAL STORAGE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5001 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 50 WATER SYSTEMS - TREATED, POTABLE, AND DEMIN WATER SYSTEMS |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5101 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - STEAM BALANCE DIAGRAM |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5102 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE AND BOILER FEEDWATER SYSTEMS |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5103 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE TREATMENT SYSTEM |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5104 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - FURNACE BLOWDOWN SYSTEM |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5201 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 52 FUEL SYSTEM - FUEL GAS SYSTEM |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5301 | Material Selection Diagram - Olefins Unit 10 - 53 Cooling Water System Cooling Water Diagram |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00399
Return Date
Owner Cmmt*
| PE | OL1-2G74-5311 | Material Selection Diagram - Olefins Unit 10 - 53-Cooling Water System Cooling Tower |  | Class 3 | Purpose** | IFA
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00399
Return Date
Owner Cmmt*
| PE | OL1-2G74-5401 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 54 AIR AND NITROGEN SYSTEM - PLANT AIR, INSTRUMENT AIR, AND NITROGEN SYSTEMS |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5501 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - FLARE AND BLOWDOWN SYSTEM |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5502 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - PROCESS VENT GAS COLLECTION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5511 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP FLARE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5512 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP FLARE AREA |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5601 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER COLLECTION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5602 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SURFACE RUNOFF COLLECTION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5603 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CRACKER HOLDING BASIN |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5604 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - DOMESTIC WASTEWATER COLLECTION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5611 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OSBL OILY WASTEWATER COLLECTION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5612 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER EQUILIZATION TANK |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5613 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CPI & IGF PACKAGES |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5614 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - BIOTREATMENT PACKAGE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5615 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CHECK BASIN |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5616 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLUDGE DEWATERING PACKAGE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5617 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLOP AND OIL SLUDGE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5901 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - CHEMICAL STORAGE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G74-5911 | MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - COMPLEX U & O CHEMICAL STORAGE |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G76 Supervisory Level Operating Procedures for all Process/Utility System(s). (Shall include Steady State, Stat-Up, Shutdown & transient Operations
| PE | OL1-2G76-1002 | BALANCE OF PLANT SUPERVISORY OPERATING MANUAL |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: G91 Index/List
| PE | OL1-2G91-1001 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1002 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1003 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1101 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1201 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1301 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1401 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1501 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-1601 | PIPING SPECIALTY ITEM INDEX |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2001 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2002 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2003 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2101 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2102 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2103 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2201 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2202 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2203 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2301 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2302 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2303 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2401 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2402 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2403 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2501 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 25 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2502 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 25 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2503 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 25 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2601 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 26 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2602 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 26 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2603 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 26 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2701 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 27 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2702 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 27 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2703 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 27 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2801 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 28 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2802 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 28 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2803 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 28 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2901 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 29 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2902 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 29 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-2903 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 29 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-3001 | PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 30 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-3002 | PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 30 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-3003 | RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 30 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5001 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 50 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5002 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 50 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5003 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 50 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5301 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 53 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5302 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 53 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5303 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 53 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5501 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 55 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5502 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 55 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5503 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 55 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5601 | PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 56 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5602 | PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 56 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G91-5603 | RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 56 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: H03 Project HVAC specification
| EE | OL1-2H03-0001 | Air Conditioning Ventilating And Ducting Design |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00165
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2H03-0002 | JOB SUPPLY SPEC. FOR HVAC SYSTEMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: H10 Calculation
| EE | OL1-2H10-0001 | HVAC THERMAL CALC. - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H10-0002 | HVAC THERMAL CALC. - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H10-0003 | HVAC THERMAL CALC. - GATEHOUSE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H10-0004 | HVAC THERMAL CALC. - OPERATION TOOL ROOM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: H20 System schematic diagram
| EE | OL1-2H20-0001 | HVAC PROCESS FLOW DIAGRAM - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H20-0003 | HVAC PROCESS FLOW DIAGRAM - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H20-0005 | HVAC PROCESS FLOW DIAGRAM - GATEHOUSE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H20-0007 | HVAC PROCESS FLOW DIAGRAM - OPERATION TOOL ROOM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: H21 Arrangement drawing
| EE | OL1-2H21-0001 | HVAC LAYOUT- ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H21-0005 | HVAC LAYOUT- ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H21-0010 | HVAC LAYOUT- GATEHOUSE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2H21-0015 | HVAC LAYOUT- OPERATION TOOL ROOM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: H55
| EE | OL1-2H55-0001 | MR HVAC SYSTEMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I20 Instrument datasheet
| IE | OL1-2I20-0101 | D/S MECHANICAL RESTRICTION ORIFICE AND ORIFICE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0102 | DATA SHEET FOR PITOT TUBE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0103 | D/S MECHANICAL ELECTROMAGNETIC FLOW METER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0104 | D/S MECHANICAL ROTAMETERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0106 | D/S MECHANICAL MASS FLOW MET.CORIOLIS EFFECT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0107 | D/S MECHANICAL VENTURI |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0108 | D/S MECHANICAL ULTRASONIC FLOW METER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0111 | D/S MECHANICAL TURBINE METER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0112 | D/S MECHANICAL VORTEX METER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0120 | DATA SHEET FOR CUSTODY TRANSFER METERING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0202 | D/S MECHANICAL MAGNETIC LEVEL GAUGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0203 | D/S MECHANICAL RADAR LEVEL INSTRUMENTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0211 | D/S MECHANICAL SPECIAL LEVEL TRANSMITTERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0212 | D/S MECHANICAL LEVEL GLASS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0301 | D/S MECHANICAL PRESSURE & DIFFER.PRESS.GAUGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0501 | D/S MECHANICAL CONTROL VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0503 | D/S MECHANICAL SPECIAL CONTROL VALVE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0504 | D/S MECHANICAL SEVERE SERVICE CONTROL VALVE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0505 | D/S ANTISURGE VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0506 | D/S MECHANICAL DESUPERHEATER VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0606 | D/S MECHANICAL PNEUMATIC ON OFF VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0608 | D/S MECHANICAL SPECIAL ON OFF VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0609 | D/S MECHANICAL ELECTRIC OPERATED VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0701 | D/S MECHANICAL SAFETY RELIEF VALVE & RUPTURE DISKS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-0801 | D/S MECHANICAL ELECTRONIC TRANSMITTER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1003 | VENTURI TUBE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1004 | ORIFICE PLATE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1005 | INSTRUMENT LEVEL GAUGE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1006 | D/P LEVEL TRANSMITTERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1010 | TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1015 | INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1017 | FLAME SCANNER DATA SHEETS CRACKING FURNACE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2003 | VENTURI TUBE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2004 | ORIFICE PLATE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2005 | INSTRUMENT LEVEL GAUGE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2006 | D/P LEVEL TRANSMITTERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2010 | TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2015 | INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2017 | FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-2601 | DATA SHEET FOR FIRE AND GAS DEVICES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3003 | VENTURI TUBE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3004 | ORIFICE PLATE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3005 | INSTRUMENT LEVEL GAUGE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3006 | D/P LEVEL TRANSMITTERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3010 | TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3015 | INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-3017 | FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4003 | VENTURI TUBE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4004 | ORIFICE PLATE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4005 | INSTRUMENT LEVEL GAUGE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4006 | D/P LEVEL TRANSMITTERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4010 | TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4015 | INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-4017 | FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5003 | VENTURI TUBE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5004 | ORIFICE PLATE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5005 | INSTRUMENT LEVEL GAUGE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5006 | D/P LEVEL TRANSMITTERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5010 | TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5015 | INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-5017 | FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6001 | CONTROL VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6002 | INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6003 | VENTURI TUBE DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6004 | ORIFICE PLATE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6005 | INSTRUMENT LEVEL GAUGE DATASHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6006 | D/P LEVEL TRANSMITTERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6007 | DATA SHEET FOR PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6008 | DATA SHEET FOR DRAFT PRESSURE GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6009 | PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6010 | TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6011 | TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6012 | TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6013 | TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6014 | TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6015 | INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6016 | O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-6017 | FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I21 Instrument Calculation sheet
| IE | OL1-2I21-0100 | FLOW ELEMENT CALCULATION SHEET |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I21-1001 | INTRINSIC SAFETY LOOP CALCULATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I30 Interlock Logic and Sequence Diagram
| IE | OL1-2I30-1001 | CAUSE AND EFFECT DIAGRAMS - AREA 10 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-1003 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 10 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-1101 | DCS INTERLOCK AND SEQUENCES DIAGRAMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-1102 | ESD INTERLOCK LOGIC DIAGRAMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2001 | CAUSE AND EFFECT DIAGRAMS - AREA 20 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2003 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 20 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2101 | CAUSE AND EFFECT DIAGRAMS - AREA 21 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2103 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 21 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2201 | CAUSE AND EFFECT DIAGRAMS - AREA 22 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2203 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 22 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2301 | CAUSE AND EFFECT DIAGRAMS - AREA 23 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2303 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 23 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2401 | CAUSE AND EFFECT DIAGRAMS - AREA 24 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2403 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 24 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2501 | CAUSE AND EFFECT DIAGRAMS - AREA 25 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2503 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 25 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2601 | CAUSE AND EFFECT DIAGRAMS - AREA 26 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2603 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 26 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2701 | CAUSE AND EFFECT DIAGRAMS - AREA 27 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2703 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 27 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2801 | CAUSE AND EFFECT DIAGRAMS - AREA 28 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2803 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 28 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2901 | CAUSE AND EFFECT DIAGRAMS - AREA 29 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2903 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 29 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-3001 | CAUSE AND EFFECT DIAGRAMS - AREA 30 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-3003 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 30 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5001 | CAUSE AND EFFECT DIAGRAMS - AREA 50 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5003 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 50 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5301 | CAUSE AND EFFECT DIAGRAMS - AREA 53 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5303 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 53 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5501 | CAUSE AND EFFECT DIAGRAMS - AREA 55 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5503 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 55 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5601 | CAUSE AND EFFECT DIAGRAMS - AREA 56 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-5603 | INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 56 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I31 Typical installation / fabrication drawing
| IE | OL1-2I31-0001 | INSTR.SUPPORTS TYPICAL MOUNT.DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-0200 | LEVEL INSTRUMENT DESIGN, ISBL UNITS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-0201 | LEVEL INSTRUMENT DESIGN, OSBL UNITS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1003 | FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1005 | PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1012 | PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1019 | FLOW TRANSMITTER - LIQUID SERVICE #900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1020 | PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1021 | LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1022 | PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2001 | O2 COMBUSTIBLE ANALYZER PROCESS CONNECTION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2002 | O2 COMBUSTIBLE ANALYZER INSTRUMENT ELECTRICAL CONNECTION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2003 | FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2004 | PRESSURE GAUGE - GAS SERVICE DRAFT REMOTE MOUNTING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2005 | PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2006 | EYE-HYE LEVEL COMPONENTS ON STEAM DRUM ELECTRICAL CONNECTION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2007 | COT INSERTION WELL T-C CONNECTION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2008 | INSTRUMENT SUPPORT DETAIL EYE-HYE LEVEL CONTROL UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2009 | INSTRUMENT PROCESS DETAILS DRAFT D-P TRANSMITTER GAS SERVICE REMOTE MOUNTED |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2010 | INSTRUMENT SUPPORT DETAILS DUAL STAND 4FT-4IN OUTSIDE HANDRAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2011 | INSTRUMENT SUPPORT DETAILS TRIPLE STAND 4FT-4IN OUTSIDE HANDRAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2012 | PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2013 | THERMOCOUPLE HEAD ELECTRICAL CONNECTION DETAIL 3-4IN CONDUIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2014 | TEMPERATURE TRANSMITTER ELECTRICAL CONNECTION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2015 | LUBE OIL VENDOR JUNCTION BOX TO FIE CHARM BOX ELECTRICAL CONNECTION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2016 | INSTRUMENT SUPPORT DETAIL EYE-HYE MINIATURE LEVEL INDICATOR |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2017 | PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2018 | PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2019 | FLOW TRANSMITTER - LIQUID SERVICE #900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2020 | PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2021 | LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2022 | PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2023 | LEVEL GAUGE - STEAM SERVICE DIRECT MTD W ELECTRIC TRACED |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I34 Instrument main cable layout
| IE | OL1-2I34-0001 | INSTR.MAIN CABLE ROUTING COMMON AREA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0002 | INSTR.MAIN CABLE ROUTING METERING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0003 | INSTR.MAIN CABLE ROUTING MAIN PIPE RACK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0004 | INSTR.MAIN CABLE ROUTING AREA SUBSTATION E & FAR E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0005 | INSTR.MAIN CABLE ROUTING AREA SUBSTATION C & FAR C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0006 | INSTR.MAIN CABLE ROUTING FURNACES UTILITY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0007 | INSTR.MAIN CABLE ROUTING QUENCH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0008 | INSTR.MAIN CABLE ROUTING PROCESS 20B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0009 | INSTR.MAIN CABLE ROUTING PROCESS 20C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0010 | INSTR.MAIN CABLE ROUTING PROCESS COLD COMPRESSORS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0011 | INSTR.MAIN CABLE ROUTING PROCESS CGC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0012 | INSTR.MAIN CABLE ROUTING BUTADIENE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0013 | INSTR.MAIN CABLE ROUTING COOLING WATER UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0014 | INSTR.MAIN CABLE ROUTING UTILITIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0015 | INSTR.MAIN CABLE ROUTING WASTE WATER TREATMENT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0016 | INSTR.MAIN CABLE ROUTING FLARE AREA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I34-0017 | INSTR.OVERALL CABLE ROUTING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I35 Instrument, Junction box and instrument air supply station plot plan drawing
| IE | OL1-2I35-0001 | INSTRUMENT LAYOUT COMMON AREA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0002 | INSTRUMENT LAYOUT METERING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0003 | INSTRUMENT LAYOUT MAIN PIPE RACK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0004 | INSTRUMENT LAYOUT AREA SUBSTATION E & FAR E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0005 | INSTRUMENT LAYOUT AREA SUBSTATION E & FAR C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0006 | INSTRUMENT LAYOUT FURNACES UTILITY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0007 | INSTRUMENT LAYOUT QUENCH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0008 | INSTRUMENT LAYOUT PROCESS 20B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0009 | INSTRUMENT LAYOUT PROCESS 20C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0010 | INSTRUMENT LAYOUT PROCESS COLD COMPRESSORS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0011 | INSTRUMENT LAYOUT PROCESS CGC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0012 | INSTRUMENT LAYOUT BUTADIENE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0013 | INSTRUMENT LAYOUT COOLING WATER UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0014 | INSTRUMENT LAYOUT UTILITIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0015 | INSTRUMENT LAYOUT WASTE WATER TREATMENT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0016 | INSTRUMENT LAYOUT FLARE AREA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0020 | INSTRUMENT AIR DISTRIBUTION LAYOUT COMMON AREA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0021 | INSTRUMENT AIR DISTRIBUTION LAYOUT METERING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0022 | INSTRUMENT AIR DISTRIBUTION LAYOUT MAIN PIPE RACK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0023 | INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION E & FAR E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0024 | INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION C & FAR C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0025 | INSTRUMENT AIR DISTRIBUTION LAYOUT FURNACES UTILITY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0026 | INSTRUMENT AIR DISTRIBUTION LAYOUT QUENCH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0027 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0028 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0029 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS COLD COMPRESSORS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0030 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS CGC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0031 | INSTRUMENT AIR DISTRIBUTION LAYOUT BUTADIENE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0032 | INSTRUMENT AIR DISTRIBUTION LAYOUT COOLING WATER UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0033 | INSTRUMENT AIR DISTRIBUTION LAYOUT UTILITIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0034 | INSTRUMENT AIR DISTRIBUTION LAYOUT WASTE WATER TREATMENT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0035 | INSTRUMENT AIR DISTRIBUTION LAYOUT FLARE AREA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I42 Junction box Arrangement Drawing
| IE | OL1-2I42-0001 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-E SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0002 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-C SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0003 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR FL SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0004 | INSTRUMENT AND F&G WIRING DRAWINGS FOR CCB AND OTHER BUILDINGS SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT GRADE TO EL AAFT-AIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1100 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1100 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT GRADE TO EL AAFT-AIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1200 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1200 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT GRADE TO EL AAFT-AIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1300 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1300 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT GRADE TO EL AAFT-AIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1400 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1400 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT GRADE TO EL AAFT-AIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1500 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1500 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT GRADE TO EL AAFT-AIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600- AT EL AAFT-AIN TO EL BBFT-BIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1600 AT EL BBFT-BIN TO EL CC6FT-CIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL CCFT-CIN TO EL DDFT-DIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL DDFT-DIN TO EL. EEFT-E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL EEFT-EIN TO EL FF1FT -F |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL FFFT-FIN TO EL GGFT-GIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL GGFT TO GIN TO EL HHFT -HIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL HHFT-HIN TO EL IIFT-IIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1600 AT EL IIFT-IIN TO EL JJFT-JIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL JJFT - JIN TO EL KKFT-KIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL KKFT - KIN TO EL LLFT-LIN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I43 Instrument cable list and cable cutting plan
| IE | OL1-2I43-0001 | INSTRUMENT CABLE LIST FOR FAR C SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0002 | INSTRUMENT CABLE LIST FOR FAR E SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0003 | INSTRUMENT CABLE LIST FOR FAR FL SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0004 | INSTRUMENT CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0011 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR C SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0012 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR E SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0013 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR FL SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0014 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FORCCB AND OTHER BULDINGS SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I44 Power Supply Distribution Drawing
| IE | OL1-2I44-1001 | INST.POW.SUP.DISTRIBUTION FOR CCB |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1002 | INST.POW.SUP.DISTRIBUTION FOR FAR C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1003 | INST.POW.SUP.DISTRIBUTION FOR FAR E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1004 | INST.POW.SUP.DISTRIBUTION FOR FAR FL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I46 Layout of instrument cabinets / panels in Control Room and Rack Room
| IE | OL1-2I46-1001 | CONTROL & TECH.ROOM LAYOUT, CENTRAL CONTROL BUILDING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I46-1002 | FAR C INSTRUMENT EQUIPMENT LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I46-1003 | FAR E INSTRUMENT EQUIPMENT LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I46-1004 | FAR FL INSTRUMENT EQUIPMENT LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I46-1005 | MAINTENANCE BUILDING INSTRUMENT EQUIPMENT LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I46-1006 | EMERGENCY CENTER BUILDING INSTRUMENT EQUIPMENT LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I47 Layout of instrument main and secondary cable route in Control Room and Rack Room
| IE | OL1-2I47-1001 | FAR E INSTRUMENT CABLE ROUTING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1002 | FAR C INSTRUMENT CABLE ROUTING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1003 | FAR FL INSTRUMENT CABLE ROUTING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1004 | INSTRUMENT CABLE ROUTING CENTRAL CONTROL BUILDING AND OTHER BUILDINGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1005 | CCB INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT PACKAGE A1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1006 | FAR E INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1007 | FAR C INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1008 | FAR FL INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1021 | TELECOM LOCATION AND CABLE ROUTING FAR E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1022 | TELECOM LOCATION AND CABLE ROUTING FAR C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1023 | TELECOM LOCATION AND CABLE ROUTING FAR FL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1024 | TELECOM LOCATION AND CABLE ROUTING CENTRAL CONTROL BUILDING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1050 | SUB E INSTRUMENT CABLE ROUTING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1051 | SUB C INSTRUMENT CABLE ROUTING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I48 Layout of instrument grounding wiring in Control Room and Rack Room
| IE | OL1-2I48-1001 | INSTRUMENT & TELECOM GROUNDING PHILOSOPHY DIAGRAM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1002 | INSTRUMENT / TELECOM EARTHING LAYOUT CENTRAL CONTROL BUILDING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1003 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR E AND SUB E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1004 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR C AND SUB C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1005 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR FL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1006 | INSTRUMENT / TELECOM EARTHING LAYOUT OTHER BUILDINGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I49 Instrument Hook-up Drawing
| IE | OL1-2I49-4101 | INSTRUMENT/TELECOM AND FIBRE OPTIC CABLES MATERIALTAKE-OFF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4201 | CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4203 | SECONDARY CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4301 | JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES MATERIAL TAKE-OFF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4303 | CABLE GLANDS MAT.TAKE-OFF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4304 | MAIN CABLE TRANSIT (MCT) & ACCESSORIES MATERIAL TAKE OFF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I50 Hook-up drawing for process lead piping for each instrument
| IE | OL1-2I50-0001 | INSTRUMENT HOOK-UP DRAWINGS ISBL UNITS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I51 Hook-up drawing for IA and pneumatic
| IE | OL1-2I51-0001 | INSTRUMENT TYPICAL HOOK -UP |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I52 Hook-up drawing for Steam tracing
| IE | OL1-2I52-0001 | INSTRUMENT HOOK-UP DRAWINGS OSBL UNITS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I53 Instrument loop drawing diagram
| IE | OL1-2I53-0001 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - FURNACES UTILITY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0002 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - QUENCH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0003 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0004 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0005 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS COLD COMPRESSORS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0006 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS CGC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0007 | INSTRUMENT LOOP DRAWINGS FAR-E- METERING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0008 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION E & FAR E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0009 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION C & FAR C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0010 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - BUTADIENE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0011 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - COOLING WATER UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0012 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - UTILITIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0013 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - WASTE WATER TREATMENT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0014 | INSTRUMENT LOOP DRAWINGS FAR-FL DCS, ESD, FGS - FLARE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I55 In-line & On equipment
| IE | OL1-2I55-0101 | MR ORIFICE AND RESTRICTION ORIFICE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0102 | MR PITOT TUBE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0103 | MR ELECTROMAGNETIC FLOW METER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0104 | MR ROTAMETERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0106 | MR MASS FLOW MET.CORIOLIS EFFECT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0107 | MR VENTURI |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0108 | MR ULTRASONIC FLOW METER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0111 | MR TURBINE METER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0112 | MR VORTEX METER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0120 | MR CUSTODY TRANSFER SYSTEM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0202 | MR MAGNETIC LEVEL GAUGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0203 | MR RADAR LEVEL INSTRUMENTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0211 | MR SPECIAL LEVEL TRANSMITTERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0212 | MR LEVEL GLASS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0213 | MR LEVEL GLASS FOR STEAM DRUM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0302 | MR THERMOCOUPLE/RTD WITH WELL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0304 | MR THERMOMETER WITH WELL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0305 | MR MULTIPLE THERMOCOUPLE / RTD |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0402 | MR PRESSURE & DIFFER.PRESS.GAUGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0501 | MR CONTROL VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0503 | MR SPECIAL CONTROL VALVE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0504 | MR SEVERE SERVICE CONTROL VALVE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0505 | MR ANTISURGE VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0506 | MR DESUPERHEATER VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0606 | MR PNEUMATIC ON OFF VALVE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0608 | MR SPECIAL ON OFF VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0609 | MR ELECTRIC OPERATED VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0610 | MR FOR PNEUMATIC ACTUATORS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0701 | MR SAFETY RELIEF VALVE & RUPTURE DISKS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0801 | MR ELECTRONIC TRANSMITTER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-1001 | MR INTEGRATED CONTROL AND SAFETY SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-1701 | MR MACHINE MONITORING SYSTEM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2001 | MR ANALYSER HOUSE PACKAGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2002 | MR CEMS / O2 FLUE GAS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2004 | INLINE INSTRUMENT REQUISITION - VORTEX FLOW ELEMENT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2201 | INLINE INSTRUMENT REQUISITION - CONTROL VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2202 | INLINE INSTRUMENT REQUISITION - PRESSURE & SAFETY RELIEF VAVLE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2203 | INLINE INSTRUMENT REQUISITION - RESTRICTION ORIFICE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2205 | OFFLINE INSTRUMENT REQUISITION - FLAME SCANNER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2206 | OFFLINE INSTRUMENT REQUISITION - GAUGES - GLASS/LEVEL GAUGES CLARK RELIANCE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2207 | OFFLINE INSTRUMENT REQUISITION - LEVEL TRANSMITTER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2208 | OFFLINE INSTRUMENT REQUISITION - O2 & COMBUSTIBLE ANALYZER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2209 | OFFLINE INSTRUMENT REQUISITION - PH/CONDUCTIVITY ANALYZER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2210 | OFFLINE INSTRUMENT REQUISITION - PRESSURE & DIFF PRESSURE TRANSMITTER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2211 | OFFLINE INSTRUMENT REQUISITION - PRESSURE GAUGES/DRAFT GAUGES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2212 | OFFLINE INSTRUMENT REQUISITION - TEMPERATURE TRANSMITTER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2213 | OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE FOR FURNACE PROFILE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2214 | OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE TYPE K / RTD WITH WELL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2215 | OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE WITH COT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2216 | OFFLINE INSTRUMENT REQUISITION - LEVEL GAUGES - REFLUX TYPE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2301 | MR SIMPLE SPECIFIC COMPONENT AND PROPERTY ANALYZERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2401 | MR WATER ANALYZERS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2601 | MR FIRE AND GAS DEVICES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4101 | MR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4201 | MR CABLE TRAY AND ACCESSORIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4301 | MR FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4302 | MR CABLE GLANDS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4501 | MR MOUNTING ACCESSORIES (TUBING & FITTINGS) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4502 | MR SUNSHADES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4503 | MOUNTING ACCESSORIES (TUBING & FITTINGS) MATERIALTAKE-OFF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4505 | MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) TAKE-OFF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4507 | STEAM & ELECTRICALTRACING MAT.TAKE-OFF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4510 | MR MAIN CABLE TRANSIT (MCT) & ACCESSORIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4511 | MR FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I57
| IE | OL1-2I57-1001 | ICSS EXTENT OF SUPPLY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I57-1701 | MACHINE MONITORING SYSTEM EXTENT OF SUPPLY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I57-4501 | PARTICULAR TECNICAL SPECIFICATION FOR MOUNTING ACCESSORIES (TUBING & FITTINGS) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I61 SIL Study Document
| IE | OL1-2I61-1101 | SIS IMPLEMENTATION CALCULATION NOTES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I61-1102 | GENERAL SIS SAFETY REQUIREMENTS SPECIFICATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I61-1103 | PARTICULAR SIS SAFETY REQUIREMENTS SPECIFICATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I71 Control narative for complex loop
| IE | OL1-2I71-1001 | COMPLEX LOOP NARRATIVES - AREA 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-1101 | COMPLEX CONTROL NARRATIVES (36M FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-1201 | COMPLEX CONTROL NARRATIVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-1301 | COMPLEX CONTROL NARRATIVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-1501 | COMPLEX CONTROL NARRATIVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2001 | COMPLEX LOOP NARRATIVES - AREA 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2101 | COMPLEX LOOP NARRATIVES - AREA 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2201 | COMPLEX LOOP NARRATIVES - AREA 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2202 | SEQUENCE NARRATIVES - AREA 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2301 | COMPLEX LOOP NARRATIVES - AREA 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2302 | SEQUENCE NARRATIVES - AREA 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2401 | COMPLEX LOOP NARRATIVES - AREA 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2402 | SEQUENCE NARRATIVES - AREA 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2501 | COMPLEX LOOP NARRATIVES - AREA 25 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2601 | COMPLEX LOOP NARRATIVES - AREA 26 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2602 | SEQUENCE NARRATIVES - AREA 26 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2701 | COMPLEX LOOP NARRATIVES - AREA 27 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2702 | SEQUENCE NARRATIVES - AREA 27 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2801 | COMPLEX LOOP NARRATIVES - AREA 28 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-2901 | COMPLEX LOOP NARRATIVES - AREA 29 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-3001 | COMPLEX LOOP NARRATIVES - AREA 30 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-4001 | COMPLEX CONTROL NARRATIVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-5001 | COMPLEX LOOP NARRATIVES - AREA 50 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-5301 | COMPLEX LOOP NARRATIVES - AREA 53 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-5501 | COMPLEX LOOP NARRATIVES - AREA 55 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-5601 | COMPLEX LOOP NARRATIVES - AREA 56 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-6001 | COMPLEX CONTROL NARRATIVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I72
| IE | OL1-2I72-1001 | CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I72-2001 | CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I72-3001 | CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I72-4001 | CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I72-5001 | CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I72-6001 | CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I81 DCS System Document
| IE | OL1-2I81-1001 | CTRL & SAFETY SYST.CONNECTION DIAG. |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I81-1002 | CTRL & SAFETY SYST.ARCHITECTURE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I81-1003 | ELECTRIC.INSTRUMENT INTERF. |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I81-1004 | GRAPHIC DISLAYS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I81-1005 | OPERATOR TREND DISPLAY DEFINITION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I84 Analyzer system Document
| IE | OL1-2I84-2001 | ANALYZER SYST.BLOCK DIAGRAM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2002 | ANALYZER SHELTER LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2003 | ANALYZER SAMPLE LOOP ARRANGEMENT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I91 Index/List
| IE | OL1-2I91-0001 | INSTRUMENT LIST |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0002 | INSTRUMENT LIST - SUBSTATION E & FAR E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0003 | INSTRUMENT LIST - SUBSTATION C & FAR C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0004 | INSTRUMENT LIST - FURNACES UTILITY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0005 | INSTRUMENT LIST - QUENCH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0006 | INSTRUMENT LIST - PROCESS 20B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0007 | INSTRUMENT LIST - PROCESS 20C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0008 | INSTRUMENT LIST - PROCESS COLD COMPRESSORS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0009 | INSTRUMENT LIST - PROCESS CGC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0010 | INSTRUMENT LIST - BUTADIENE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0011 | INSTRUMENT LIST - COOLING WATER UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0012 | INSTRUMENT LIST - UTILITIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0013 | INSTRUMENT LIST - WASTE WATER TREATMENT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0014 | INSTRUMENT LIST - FLARE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0020 | INSTRUMENT CLASSES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0100 | INSTRUMENT CONTROL SYSTEMS EQUIPMENT LIST |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0102 | ICSS DATA BASE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0103 | INSTRUMENT RANGE, ALARM & TRIP LIST |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0104 | INSTRUMENT LIST - METERING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1001 | IN/OUT SUMMARY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1002 | INSTRUMENT INDEX |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1003 | FURNACE ANALYZER LIST |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2000 | ANALYZER LIST |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2002 | INSTRUMENT INDEX |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2003 | FURNACE ANALYZER LIST - FURNACES 10-H-1200 - 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-3002 | INSTRUMENT INDEX |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-3003 | FURNACE ANALYZER LIST - FURNACES 10-H-1300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-4002 | INSTRUMENT INDEX |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-4003 | FURNACE ANALYZER LIST - FURNACES 10-H-1400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-5002 | INSTRUMENT INDEX |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-5003 | FURNACE ANALYZER LIST - FURNACES 10-H-1500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-6002 | INSTRUMENT INDEX |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-6003 | FURNACE ANALYZER LIST - FURNACES 10-H-1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I92 Procedures & Standards
| IE | OL1-2I92-0050 | JSS FOR ANALYSER SYSTEMS & HOUSES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0051 | JSS MOUNTING ACCESSORIES (TUBING & FITTINGS) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0052 | JSS CABLE TRAY AND ACCESSORIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0053 | JSS FOR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0054 | JSS FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0055 | JSS FOR CABLE GLANDS AND ACCESSORIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0056 | JSS FOR SUNSHADES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0057 | JSS FOR CUSTODY TRANSFER SYSTEM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0058 | JSS FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0059 | JSS FOR MAIN CABLE TRANSIT & ACCESSORIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0060 | JSS FOR FIRE AND GAS DEVICES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0100 | JSS FOR FLOW METER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0101 | JSS DIFFERENTIAL PRESSURE FLOW ELEMENTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0200 | JSS LEVEL INSTRUMENTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0201 | JSS FOR SURGE PROTECTION DEVICES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0300 | JSS TEMPERATURE INSTRUMENTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0301 | JSS FOR PRESSURE & DIFF.PRESSURE INSTRUMENTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0404 | JSS ANTISURGE VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0405 | JSS DESUPERHEATERS VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0501 | JSS CONTROL VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0503 | JSS SPECIAL CONTROL VALVE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0504 | JSS SEVERE SERVICE CONTROL VALVE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0602 | JSS FOR ELECTRIC OPERATED VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0603 | JSS FOR SPECIAL ON OFF VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0604 | JSS FOR ACTUATORS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0606 | JSS FOR PNEUMATIC ON OFF VALVES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0701 | JSS FOR SAFETY RELIEF VALVE & RUPTURE DISKS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0801 | JSS ELECTRONIC TRANSMITER |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-1701 | JSS FOR MACHINE MONITORING SYST. |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: J92 Procedures & Standards
| HR | OL1-2J92-0002 | EMPLOYEE GRIEVANCE MANAGEMENT PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: J93 Policy , Guidelines & Memo
| HR | OL1-2J93-0004 | HUMAN RESOURCE POLICY AND PROCEDURES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: J94 Forms & Templates
| HR | OL1-2J94-0002 | WORKER CODE OF CONDUCT DECLARATION FORM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| HR | OL1-2J94-0004 | CHILD LABOR RISK ASSESSMENT CHECKLIST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| HR | OL1-2J94-0005 | FORCED LABOR RISK ASSESSMENT CHECKLIST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K10
| CV | OL1-2K10-0001 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CALC. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K10-0002 | ELECTRICAL SUBSTATION SUB-E - TRANSFORMERS & WALLS STRUCTURAL CALC. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K10-0003 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CALC. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K10-0004 | ELECTRICAL SUBSTATION SUB-C - TRANSFORMERS & WALLS STRUCTURAL CALC.STRUCTURAL CALC. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K10-0005 | GATEHOUSE - STRUCTURAL CALC. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K10-0006 | OPERATION TOOL ROOM - STRUCTURAL CALC. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K11 Design calculation for pile (including pile driven design)
| CV | OL1-2K11-0001 | CALCULATION NOTES FOR PILES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K12 Design calculation for paving
| CV | OL1-2K12-0001 | CALCULATION NOTES FOR ROAD AND PAVING THICKNESS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K13 Design calculation for foundations
| CV | OL1-2K13-0001 | CALCULATION NOTE FOR FOUNDATION OF 10-H-1100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0002 | CALCULATION NOTE FOR FOUNDATION OF 10-H-1200/1600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0003 | CALCULATION NOTE FOR FOUNDATION OF 10-D-1950 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0004 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0005 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0006 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5210 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0007 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2120 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0008 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2140 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0009 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2110 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0010 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5150 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0011 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2160 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0012 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2165 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0013 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2136 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0014 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2160 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0015 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2125A |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0016 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2136 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0017 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2165A/D |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0018 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2166 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0019 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2145 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0020 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2146 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0021 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2026 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0022 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2048 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0023 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5102A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0024 | CALCULATION NOTE FOR FOUNDATION PUMPS 10-P-2026A/B, 10-P-2126A/B, 10-P-2046A/B, 10-P-5140A/B, 10-P-2146A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0025 | CALCULATION NOTE FOR FOUNDATION OF 10-P-2105A/B AND 10-P-2006A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0026 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2105A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0027 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2009A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0028 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2008A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0029 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2026A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0030 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2028A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0031 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2136A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0032 | CALCULATION NOTE FOR FOUNDATION OF 10-X-2755 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0033 | CALCULATION NOTE FOR FOUNDATION OF 10-X-2036 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0034 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2440 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0035 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2450 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0036 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2300 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0037 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2330 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0038 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2410A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0039 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2435 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0040 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2436 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0041 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2240 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0042 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2245 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0043 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2445 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0044 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2455 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0045 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2220 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0046 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2210 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0047 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2230 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0048 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2405 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0049 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2415 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0050 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2310 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0051 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2312 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0052 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2316 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0053 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2326 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0054 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2330 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0055 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2411 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0056 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-2910 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0057 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2435 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0058 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2230A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0059 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2412 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0060 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2413 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0061 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2432 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0062 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2445A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0063 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2446 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0064 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2455A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0065 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2450 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0066 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2470 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0067 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2206 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0068 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2210A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0069 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2220A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0070 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2240A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0071 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2305 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0072 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2630 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0073 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2326 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0074 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2320A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0075 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2310A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0076 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2306A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0077 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0078 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0079 | CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-5112A/B, 10-P-2714A/B, 10-P-2710A/B, 10-P-2720A/B, 10-P-2721A/B, 10-P-2910 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0080 | CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-2724A/B, 10-P-2726A/B, 10-P-2750A/B, 10-P-2760A/B/C, 10-P-2705A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0081 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5100A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0082 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2900/2902/2906 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0083 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2920 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0084 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1920 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0085 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2350 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0086 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5555 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0087 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2048A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0088 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2580 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0089 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2640 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0090 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2570 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0091 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2510, 10-D-2510 AND 10-E-2510 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0092 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2540, 10-D-2540 AND 10-E-2540 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0093 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2520 AND 10-D-2520 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0094 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2480A |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0095 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2465 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0096 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2840 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0097 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2830 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0098 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2815 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0099 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2820 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0100 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2810 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0101 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2645 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0102 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2555 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0103 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2550 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0104 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5628, 10-PIT-5628, P-10-5628A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0105 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2575 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0106 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2880 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0107 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2870 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0108 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2860 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0109 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2865 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0110 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5632 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0111 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2587 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0112 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2850, 10-E-2850 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0113 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2305 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0114 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2575 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0115 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2576 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0116 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2645A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0117 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2502 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0118 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2515 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0119 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2546 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0120 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2548 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0121 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2545 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0122 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2805A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0123 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2807 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0124 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2809 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0125 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2857 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0126 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2858 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0127 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2856 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0128 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2855 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0129 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2853 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0130 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2852 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0132 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2582 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0133 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2504 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0134 | CALCULATION NOTE FOR FOUNDATION OF PSA PACKAGE 10-PK-2560, 10-D-2560A/F, 10-D-2565 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0135 | CALCULATION NOTE FOR PUMPS 10-P-2570A/B, 10-P-2575A/B, 10-P-2586A/B, 10-P-2647, 10-P-2646A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0136 | CALCULATION NOTE FOR PUMPS 10-P-2801A/B, 10-P-2805A/B, 10-P-2815, 10-P-2855A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0137 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2930, 10-D-2930 AND 10-P-2930 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0138 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2700A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0139 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2760 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0140 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2620 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0141 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2666 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0142 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2665A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0143 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2660 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0144 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2710 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0145 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2720 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0146 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2660 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0147 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2630 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0148 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2470A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0149 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2610 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0150 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2600A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0151 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2460 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0152 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2440 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0153 | CALCULATION NOTE FOR FOUNDATION OF 10-D-1000 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0154 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2635 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0155 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2636 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0156 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2472 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0157 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2474 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0158 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2465 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0159 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2460 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0160 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2440/2441/2442 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0161 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1020 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0162 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1015 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0163 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1001A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0164 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1000 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0165 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1005 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0166 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2912 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0167 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2922 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0168 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2940 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0169 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2705 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0170 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2706 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0171 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2735 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0172 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2724 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0173 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2730 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0174 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2722 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0175 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2755 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0176 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2725A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0177 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2726 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0179 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2702 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0180 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2701 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0181 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2706 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0182 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2008A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0183 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2710 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0184 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2720 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0185 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2720 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0186 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2724 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0187 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2714 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0188 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2882 AND 10-D-2882 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0189 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2884 AND 10-D-2884 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0190 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2715A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0191 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2100A/B/C/D/E/F |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0192 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2705 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0193 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-2320 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0194 | CALCULATION NOTE FOR FOUNDATION OF 10-E-1050 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0195 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1910 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0196 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5910 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0197 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5914 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0198 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5912 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0199 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2914 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0200 | CALCULATION NOTE FOR FOUNDATION OF IGNITION SYSTEM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0201 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION FOR 10-C-3070 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0202 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-3900 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0203 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3000 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0204 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3040 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0205 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3020 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0206 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3010 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0207 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3030 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0208 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3050 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0209 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3060 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0210 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3080 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0211 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3090 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0212 | CALCULATION NOTE FOR FOUNDATION OF 10-T-3070 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0213 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3100, 10-A-3100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0214 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3126 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0215 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3908 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0216 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3902 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0217 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3904 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0218 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3906 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0219 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3180 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0220 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3110 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0221 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3004A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0222 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3014A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0223 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3015 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0224 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3084 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0225 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3085A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0226 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3095 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0227 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3096 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0228 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3098 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0229 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3055A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0230 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3045A/B/C/D |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0231 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3044 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0232 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2585 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0233 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3150 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0234 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3160 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0235 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3005 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0236 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3070 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0237 | CALCULATION FOR FOUNDATION OF METERING STATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0238 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2765 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0239 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5560 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0240 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5560 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0241 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5394 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0242 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5398 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0243 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5355 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0244 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5392 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0245 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5390 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0246 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5396 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0247 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5550 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0248 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5500 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0249 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5510 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0250 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5513 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0251 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5515 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0252 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5520 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0253 | CALCULATION NOTE FOR FOUNDATION OF 10-C-5520A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0254 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5510 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0255 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5513 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0256 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5640 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0257 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5675A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0258 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5676 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0259 | CALCULATION NOTE FOR FOUNDATION OF 10-TX/C-2550 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0260 | CALCULATION NOTE FOR FOUNDATION OF 10-C-5650A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0261 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2800, 10-E-2800 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0262 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2850, 10-E-2850 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0263 | CALCULATION NOTE FOR FOUNDATION OF 10-C-2200, 10-E-2200 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0264 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5627, 10-PIT-5627, P-10-5627A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0265 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5397 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0266 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5692 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0267 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5693 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0268 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5694 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0269 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5671 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0270 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5672 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0271 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5697 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0272 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5690 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0273 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5691 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0274 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5670 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0275 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5670A/B, 10-P-5671A/B, 10-P-5644A/B, 10-P-5645A/B, 10-P-5646A/B, 10-P-5647A/B, 10-P-5675, 10-P-5676 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0276 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5646 AND 10-X-5646 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0277 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5644 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0278 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5644 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0279 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5653 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0280 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5650 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0281 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5110 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0282 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5120 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0283 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5130 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0284 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5552 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0285 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5565 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0286 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1950, 10-C-1950A/B, 10-E-1951A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0287 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5140 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0288 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5400 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0289 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5114 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0290 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5112, 10-E-5112 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0291 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5520 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0292 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5113 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0293 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5220 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0294 | CALCULATION NOTE FOR FOUNDATION OF 10-F-5610 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0295 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5552 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0296 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5110 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0297 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5191 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0298 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5192 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0299 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5115, 10-F-5115A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0300 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5125, 10-D-5125A/B, 10-F-5125A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0301 | CALCULATION NOTE FOR FOUNDATION OF 10-P-2106A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0302 | CALCULATION NOTE FOR SKID 10-P-2201A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0303 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5360A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0304 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5670 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0305 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5695 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0306 | CALCULATION NOTE FOR PUMPS 10-P-5900A/B, 10-P-5950A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0307 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5350 A/B/C/D/E/F/G/H |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0308 | CALCULATION NOTE FOR PUMPS 10-P-3080A/B, 10-P-3030A/B, 10-P-3000A/B, 10-P-3020A/B, 10-P-3061A/B, 10-P-3060A/B, 10-P-3062A/B, 10-P-3002A/B, 10-P-3902A/B, 10-P-3904A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0309 | CALCULATION NOTE FOR PUMPS 10-P-3096A/B, 10-P-3086A/B, 10-P-3036A/B, 10-P-3016A/B, 10-P-3900, 10-P-3160A/B, 10-P-3076A/B, 10-P-3906A/B, 10-P-3908A/B, 10-P-3110A/B, 10-P-3126A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0310 | CALCULATION NOTE FOR PUMPS 10-P-3046A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0311 | CALCULATION NOTE FOR PUMPS 10-P-3045A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0312 | CALCULATION NOTE FOR PUMPS 10-P-3026A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0313 | CALCULATION NOTE FOR PUMPS 10-P-3056A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0314 | CALCULATION NOTE FOR FOUNDATION OF 10-R-2620A |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0315 | CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2450A/B, 10-P-2455A/B, 10-P-2620A/B, 10-P-2666A/B, 10-P-2660A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0316 | CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2630A/B, 10-P-2310A/B, 10-P-2316A/B, 10-P-2326A/B, 10-P-2320A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0317 | CALCULATION NOTE FOR PUMPS 10-P-2302A/B, 10-P-2415A/B, 10-P-2445A/B, 10-P-2304, 10-P-2306A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0318 | CALCULATION NOTE FOR PUMPS 10-P-2200A/B, 10-P-2220A/B, 10-P-2210A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0319 | CALCULATION NOTE FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0320 | CALCULATION NOTE FOR PUMPS 10-P-5550A/B, 10-P-5552 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0321 | CALCULATION NOTE FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0322 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2000 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0323 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2020 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0324 | CALCULATION NOTE FOR FOUNDATION OF 10-T-2100 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0325 | CALCULATION NOTE FOR CONCRETE STRUCTURE OF 10-T-2040 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0326 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5605 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0327 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5610 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0328 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2390 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0329 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5603 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0330 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5604 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0331 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2090 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0332 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2190 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0333 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2790 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0334 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2322 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0335 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-3190 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0336 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5601 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0337 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5600 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0338 | CALCULATION OF BASIN FOR COOLING TOWER 10-PIT-5350 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0339 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5370 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0340 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5602 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0341 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2392 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0342 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5658 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0343 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5615 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0344 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5656 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0345 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5620A/B/C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0346 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5630 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0347 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5633 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0348 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5631 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0349 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5671 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0350 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5650A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0351 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5655 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0352 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5696 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0353 | CALCULATION NOTE FOR FOUNDATION OF CLARIFIER 10-TK-5651A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0354 | CALCULATION NOTE FOR FOUNDATION OF 10-X-2310 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0355 | CALCULATION NOTE FOR FOUNDATION OF SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0356 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0357 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0358 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0359 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0360 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0361 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0362 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0363 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0364 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0365 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0366 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5900 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0367 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5950 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0368 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2320 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0369 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2910 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0370 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-3900 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0371 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-PK-1910 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0372 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS FLARE UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0373 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0374 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0375 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0376 | CALCULATION FOR FOUNDATION OF SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0377 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0378 | CALCULATION NOTE FOR 10-SLW-5T02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0379 | CALCULATION NOTE FOR 10-SLW-5T01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0380 | CALCULATION NOTE FOR 10-SLW-0C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0381 | CALCULATION NOTE FOR 10-SLW-5W01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0382 | CALCULATION NOTE FOR 10-SLW-5F01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0383 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0384 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0385 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0386 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0387 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0388 | CALCULATION FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0389 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0390 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0391 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0392 | CALCULATION NOTE FOR FOUNDATION OF PLATFORMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0393 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5900 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0394 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5950 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0395 | CALCULATION NOTE FOR FOUNDATION OF 10-X-2312 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0396 | CALCULATION NOTE FOR SKID 10-P-2801A/B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0398 | CALCULATION FOR BASIN 10-PIT-5642 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0399 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2904 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K14 Design calculation for concrete structure (including reinforcement detail)
| CV | OL1-2K14-0001 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0002 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0003 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0004 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0005 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0006 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0007 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0008 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0009 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0010 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0011 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0012 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0013 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0014 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0015 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0016 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0017 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0018 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0019 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5T01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0020 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0021 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5F01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0022 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-5F01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0023 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0024 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0025 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0026 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0027 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0028 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A06 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0029 | CALCULATION NOTE FOR FOUNDATION AND ELEVATIONOF 10-STR-3A03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0030 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0031 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0032 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0033 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0034 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0035 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0036 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0037 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0038 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0039 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0040 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0041 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0042 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0043 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0044 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0045 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0046 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0047 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0048 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0049 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0050 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0051 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0052 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B06 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0053 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0054 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2D02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0055 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0056 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0057 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0058 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0059 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0060 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0061 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-1B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0062 | CALCULATION NOTE FOR FOUNDATION OF WASTE STORAGE BUILDING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0063 | CALCULATION NOTE FOR FOUNDATION OF LUBRIFICATION OIL & GREASE STORAGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0064 | CALCULATION NOTE FOR FOUNDATION OF GAS CYLINDER STORAGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0065 | CALCULATION NOTE FOR FOUNDATION OF TOOL ROOM OPERATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0066 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0067 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0068 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0069 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0070 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0071 | CALCULATION NOTE FOR FOUNDATION OF STORAGE SHELTER FOR CHENICALS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0169 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K15 Design calculation for steel structure (including connection joint)
| CV | OL1-2K15-0001 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0002 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0003 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0004 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0005 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0006 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0007 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0008 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0009 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0010 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-5T01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0011 | CALCULATION NOTES FOR STEEL 10-PRK-5F01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0012 | CALCULATION NOTE FOR STEEL OF 10-SHT-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0013 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0014 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0015 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0016 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0017 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0018 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0019 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0020 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0021 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0022 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0023 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B06 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0024 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0025 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2D02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0026 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0027 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0028 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0029 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0030 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0031 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0032 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-1B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0033 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0034 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0035 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0036 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0037 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0038 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0039 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0040 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0041 | CALCULATION NOTE FOR STEEL FOR WASTE STORAGE BUILDING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0042 | CALCULATION NOTE FOR STEEL FOR LUBRIFICATION OIL & GREASE STORAGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0043 | CALCULATION NOTE FOR STEEL FOR GAS CYLINDER STORAGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0044 | CALCULATION NOTE FOR STEEL FOR TOOL ROOM OPERATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0045 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0046 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A06 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0047 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0048 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0049 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0050 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0051 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0052 | CALCULATION FOR STEEL STRUCTURE 10-SHT-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0053 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0054 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0055 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0056 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0057 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0058 | CALCULATION NOTE FOR STEEL FOR STORAGE SHELTER FOR CHENICALS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0059 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K16 Design calculation for all drainage systems (including roof gutter, down spout, and grating cover)
| CV | OL1-2K16-0001 | UNDERGROUND CALCULATION NOTES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K18
| CV | OL1-2K18-0001 | CALCULATION NOTE FOR STEEL STRUCTURE OF 10-C-2200, 10-E-2200 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0002 | CALCULATION NOTE FOR STEEL STRUCTURE OF 10-C-2800, 10-E-2800 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0003 | CALCULATION NOTE FOR STEEL STRUCTURE OF 10-T-2040 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0004 | CALCULATION FOR STEEL COOLING TOWER 5350 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0005 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0006 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0007 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0008 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0009 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0010 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0011 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0012 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0013 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0014 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0015 | CALCULATION NOTE FOR STEEL SUPPORTS FLARE UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0016 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0017 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0018 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0019 | CALCULATION FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0020 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0021 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0022 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0023 | CALCULATION FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0024 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0025 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0026 | CALCULATION FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0027 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0028 | CALCULATION NOTE FOR STEEL SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0029 | CALCULATION NOTE FOR STEEL STRUCTURE OF 10-C-2850, 10-E-2850 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K18-0128 | CALCULATION NOTE FOR STEEL PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K20 Standard drawing for civil work
| CV | OL1-2K20-0001 | Construction Standards for Reinforced Concrete Works |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
Category Code: K21 Standard drawing for steel structure work
| CV | OL1-2K21-0001 | Construction Standards For Steel Structures |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
Category Code: K23 Land Developmemt Drawing
| CV | OL1-2K23-0001 | Standard Construction Drawings For Underground Systems |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
Category Code: K25 Plant Layouts
| CV | OL1-2K25-0001 | KEY PLAN FOR INSTALLATION DWGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K25-0002 | KEY PLAN FOR STRUCTURES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K27 Road and Drainage Layouts
| CV | OL1-2K27-0001 | ROADS, PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0002 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0003 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0004 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0005 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0006 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0007 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0008 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0009 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0011 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0013 | ROADS , PAVING AND FINISHING LAYOUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K29
| CV | OL1-2K29-0001 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K29-0020 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - TRANSFORMERS BAY CONSTR. DWGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K29-0030 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K29-0060 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - TRANSFORMERS BAY CONSTR. DWGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K29-0070 | GATEHOUSE - STRUCTURAL CONSTR. DWGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K29-0080 | OPERATION TOOL ROOM - STRUCTURAL CONSTR. DWGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K30 General Arrangement for Architectural drawings
| CV | OL1-2K30-0001 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - ARCHITECTURAL CONSTR. DWGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0010 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - PLUMBING DWGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0015 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - ARCHITECTURAL CONSTR. DWGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0025 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - PLUMBING DWGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0030 | GATEHOUSE - ARCHITECTURAL CONSTR. DWGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0035 | GATEHOUSE - PLUMBING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0040 | OPERATION TOOL ROOM - ARCHITECTURAL CONSTR. DWGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0045 | OPERATION TOOL ROOM - PLUMBING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K31 General Arrangement for Civil drawings
| CV | OL1-2K31-1000 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1020 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1040 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1060 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1080 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1100 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1120 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1160 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1180 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1200 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1220 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1240 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1260 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1280 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1300 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1320 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1340 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1360 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1380 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1400 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1420 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1440 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1480 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1500 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-5T01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1520 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-5F01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1540 | FOUNDATION FOR 10-PRK-5F01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1560 | FOUNDATION AND ELEVATION FOR 10-STR-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1580 | FOUNDATION AND ELEVATION FOR 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1600 | FOUNDATION AND ELEVATION FOR 10-STR-2E03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1620 | FOUNDATION AND ELEVATION FOR 10-STR-2E04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1640 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1660 | FOUNDATION AND ELEVATION FOR 10-STR-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1680 | FOUNDATION AND ELEVATION FOR 10-STR-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1700 | FOUNDATION AND ELEVATION FOR 10-STR-2B03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1720 | FOUNDATION AND ELEVATION FOR 10-STR-2B04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1740 | FOUNDATION AND ELEVATION FOR 10-STR-2B05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1760 | FOUNDATION AND ELEVATION FOR 10-STR-2B06 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1780 | FOUNDATION AND ELEVATION FOR 10-SHT-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1800 | FOUNDATION AND ELEVATION FOR 10-SHT-2D02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1820 | FOUNDATION AND ELEVATION FOR 10-STR-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1840 | FOUNDATION AND ELEVATION FOR 10-STR-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1860 | FOUNDATION AND ELEVATION FOR 10-STR-2C03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1880 | FOUNDATION AND ELEVATION FOR 10-STR-2C04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1900 | FOUNDATION AND ELEVATION FOR 10-STR-2C05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1920 | FOUNDATION AND ELEVATION FOR 10-SHT-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1940 | FOUNDATION AND ELEVATION FOR 10-SHT-1B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1960 | FOUNDATION AND ELEVATION FOR 10-STR-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1980 | FOUNDATION AND ELEVATION FOR 10-STR-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2000 | FOUNDATION AND ELEVATION FOR 10-STR-2A02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2020 | FOUNDATION AND ELEVATION FOR 10-STR-2A03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2040 | FOUNDATION AND ELEVATION FOR WASTE STORAGE BUILDING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2060 | FOUNDATION AND ELEVATION FOR STORAGE SHELTER FOR CHENICALS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2080 | FOUNDATION AND ELEVATION FOR LUBRIFICATION OIL & GREASE STORAGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2100 | FOUNDATION AND ELEVATION FOR GAS CYLINDER STORAGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2120 | FOUNDATION AND ELEVATION FOR TOOL ROOM OPERATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2140 | FOUNDATION FOR 10-SHT-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2160 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2180 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2200 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2220 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2240 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A06 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2260 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2280 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2300 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2320 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2360 | FOUNDATION FOR STRUCTURE 10-SHT-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2380 | FOUNDATION FOR STRUCTURE 10-SHT-5T01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2400 | FOUNDATION FOR STRUCTURE 10-SHT-5T02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2420 | FOUNDATION FOR STRUCTURE 10-SHT-5T03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2440 | FOUNDATION AND ELEVATION FOR 10-STR-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K32 General Arrangement for Steel Structure drawings
| CV | OL1-2K32-1001 | MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (36M FURNACE) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1003 | MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (36M FURNACE) |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1060 | STEEL FOR PIPE RACK 10-PRK-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1080 | STEEL FOR PIPE RACK 10-PRK-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1100 | STEEL FOR PIPE RACK 10-PRK-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1120 | STEEL FOR PIPE RACK 10-PRK-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1140 | STEEL FOR PIPE RACK 10-PRK-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1160 | STEEL FOR PIPE RACK 10-PRK-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1180 | STEEL FOR PIPE RACK 10-PRK-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1200 | STEEL FOR PIPE RACK 10-PRK-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1220 | STEEL FOR PIPE RACK 10-PRK-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240 | STEEL FOR PIPE RACK 10-PRK-5T01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1260 | STEEL FOR 10-PRK-5F01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1280 | STEEL FOR 10-SHT-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1300 | STEEL FOR STRUCTURE 10-STR-2E01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1320 | STEEL FOR STRUCTURE 10-STR-2E02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1340 | STEEL FOR STRUCTURE 10-STR-2E03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1360 | STEEL FOR STRUCTURE 10-STR-2E04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1380 | STEEL FOR STRUCTURE 10-STR-2D05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1400 | STEEL FOR STRUCTURE 10-STR-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1420 | STEEL FOR STRUCTURE 10-STR-2B02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1440 | STEEL FOR STRUCTURE 10-STR-2B03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1460 | STEEL FOR STRUCTURE 10-STR-2B04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1480 | STEEL FOR STRUCTURE 10-STR-2B05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1500 | STEEL FOR STRUCTURE 10-STR-2B06 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1511 | USC "36M" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1512 | USC "36M" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1513 | USC "36M" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1514 | USC "36M" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1515 | USC "36M" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1516 | USC "36M" FURNACE STEEL SHADOW BOX DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1517 | USC "36M" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1518 | USC "36M" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1519 | USC "36M" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1520 | USC "36M" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1521 | USC "36M" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1522 | USC "36M" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1523 | USC "36M" FURNACE STEEL END WALL TUBE SHEET ELEVATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1524 | USC "36M" FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1525 | USC "36M" FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1526 | USC "36M" FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1527 | USC "36M" FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1528 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1529 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1530 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1531 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1532 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1533 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1534 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1535 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1536 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1537 | USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1538 | USC "36M" FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1539 | USC "36M" FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1540 | USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1541 | USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1542 | USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1543 | USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1544 | USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1545 | USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1546 | USC "36M" FURNACE STEEL NAME PLATE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1550 | USC "36M" FURNACE STEEL STACK AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1551 | USC "36M" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1552 | USC "36M" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1553 | USC "36M" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1560 | USC "36M" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1561 | USC "36M" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1580 | USC "36M" FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1581 | USC "36M" FURNACE STEEL BREECHING SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1582 | USC "36M" FURNACE STEEL DUCT PLAN AND ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1583 | USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1584 | USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1585 | USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1586 | USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1587 | USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1600 | STEEL FOR STRUCTURE 10-STR-2C03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1601 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1602 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1603 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1604 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1605 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1606 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1607 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1608 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1609 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1610 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1611 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1612 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1613 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1614 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1615 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1616 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1617 | USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1618 | USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1619 | USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1620 | USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1621 | USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1622 | USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1623 | USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1631 | USC "36M" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1632 | USC "36M" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1640 | STEEL FOR STRUCTURE 10-STR-2C05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1641 | USC "36M" FURNACE STEEL ID FAN BOLTING PLAN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1651 | USC "36M" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1660 | STEEL FOR STRUCTURE 10-SHT-2B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1680 | STEEL FOR STRUCTURE 10-SHT-1B01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1700 | STEEL FOR STRUCTURE 10-STR-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1701 | USC "36M" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1702 | USC "36M" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1703 | USC "36M" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1704 | USC "36M" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1705 | USC "36M" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1706 | USC "36M" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1707 | USC "36M" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1708 | USC "36M" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1720 | STEEL FOR STRUCTURE 10-STR-2A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1740 | STEEL FOR STRUCTURE 10-STR-2A02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1760 | STEEL FOR STRUCTURE 10-STR-2A03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1780 | STEEL FOR STRUCTURE 10-STR-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1800 | STEEL FOR STRUCTURE 10-STR-2D02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1820 | STEEL FOR STRUCTURE 10-STR-2D03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1840 | STEEL FOR STRUCTURE 10-STR-2D04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1860 | STEEL FOR WASTE STORAGE BUILDING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1880 | STEEL FOR STORAGE SHELTER FOR CHEMICALS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1900 | STEEL FOR LUBRIFICATION OIL & GREASE STORAGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1901 | USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1902 | USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1903 | USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1904 | USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1905 | USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1906 | USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1907 | USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1908 | USC "36M" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1909 | USC "36M" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1910 | USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1911 | USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1912 | USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1913 | USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1914 | USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1920 | STEEL FOR GAS CYLINDER STORAGE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1940 | STEEL FOR TOOL ROOM OPERATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1960 | STEEL FOR STRUCTURE 10-STR-3A06 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1980 | STEEL FOR STRUCTURE 10-STR-3A03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2000 | STEEL FOR STRUCTURE 10-STR-3A05 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2020 | STEEL FOR STRUCTURE 10-STR-3A04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2040 | STEEL FOR STRUCTURE 10-STR-3A02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2060 | STEEL FOR STRUCTURE 10-STR-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2080 | STEEL FOR STRUCTURE 10-SHT-3A01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2100 | STEEL FOR STRUCTURE 10-SHT-2D01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2120 | STEEL FOR STRUCTURE 10-SHT-2D02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2140 | STEEL FOR STRUCTURE 10-STR-2C01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2160 | STEEL FOR STRUCTURE 10-STR-2C02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2161 | FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2162 | FURNACE STEEL MOMENT CONNECTION DETAIL AND MISCELLANEOUS DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2163 | FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2164 | FURNACE STEEL STANDARD FLOOR - TOE PLATE DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2180 | STEEL FOR STRUCTURE 10-STR-2C04 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2500 | USC "132U" & "36M" FURNACE GENERAL NOTES & ABBREVIATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2501 | USC "132U" & "36M" FURNACE STEEL FOUNDATION PLAN & LOADING DIAGRAM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2502 | USC "132U" & "36M" FURNACE STEEL BASE PLATE DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2503 | USC "132U" & "36M" FURNACE STEEL MISCELLANEOUS FOUNDATION PLAN & LOADING DIAGRAM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2504 | USC "132U" & "36M" FURNACE STEEL MISCELLANEOUS FOUNDATION PLAN & LOADING DIAGRAM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2511 | USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2512 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2513 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2514 | USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2515 | USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2516 | USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2517 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2518 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2519 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2520 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2521 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2522 | USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2540 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2541 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2542 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2543 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2544 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2545 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2546 | USC 132U Cracking Furnace Name Plate Details |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00423
Return Date
Owner Cmmt*
| CV | OL1-2K32-2550 | USC "132U" FURNACE STEEL STACK AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2551 | USC "132U" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2552 | USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2553 | USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2560 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2561 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2583 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2584 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2585 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2586 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2587 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2601 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2602 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2603 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2604 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2605 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2606 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2607 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2608 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2609 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2610 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2611 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2612 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2613 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2614 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2615 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2616 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2617 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2618 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2619 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2620 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2621 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2622 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2623 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2631 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2632 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2651 | USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2659 | USC "132U" & "36M" FURNACE STEEL MOMENT CONNECTION DETAIL & MISCELLANEOUS DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2660 | USC "132U" & "36M" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2701 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2702 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2703 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2704 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2705 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2706 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2707 | USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2708 | USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2801 | USC FURNACE STEEL ELEVATOR ACCESS PLATFORM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2802 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2803 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2804 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2805 | USC FURNACE STEEL ELEVATOR PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2908 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2909 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2910 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2911 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2912 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2913 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2914 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3000 | STEEL FOR STRUCTURE 10-SHT-5T01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3020 | STEEL FOR STRUCTURE 10-SHT-5T02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3040 | STEEL FOR STRUCTURE 10-SHT-5T03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3060 | STEEL FOR STRUCTURE 10-STR-5U01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3511 | USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3512 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3513 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3514 | USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3515 | USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3516 | USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3517 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3518 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3519 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3520 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3521 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3522 | USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3540 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3541 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3542 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3543 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3544 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3545 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3546 | USC "132U" FURNACE STEEL NAME PLATE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3550 | USC "132U" FURNACE STEEL STACK AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3551 | USC "132U" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3552 | USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3553 | USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3560 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3561 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3583 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3584 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3585 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3586 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3587 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3601 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3602 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3603 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3604 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3605 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3606 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3607 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3608 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3609 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3610 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3611 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3612 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3613 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3614 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3615 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3616 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3617 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3618 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3619 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3620 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3621 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3622 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3623 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3631 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3632 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3651 | USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3701 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3702 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3703 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3704 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3705 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3706 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3707 | USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3708 | USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3908 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3909 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3910 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3911 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3912 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3913 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3914 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4511 | USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4512 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4513 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4514 | USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4515 | USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4516 | USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4517 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4518 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4519 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4520 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4521 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4522 | USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4540 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4541 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4542 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4543 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4544 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4545 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4546 | USC "132U" FURNACE STEEL NAME PLATE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4550 | USC "132U" FURNACE STEEL STACK AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4551 | USC "132U" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4552 | USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4553 | USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4560 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4561 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4583 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4584 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4585 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4586 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4587 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4601 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4602 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4603 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4604 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4605 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4606 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4607 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4608 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4609 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4610 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4611 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4612 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4613 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4614 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4615 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4616 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4617 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4618 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4619 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4620 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4621 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4622 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4623 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4631 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4632 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4651 | USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4701 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4702 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4703 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4704 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4705 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4706 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4707 | USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4708 | USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4908 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4909 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4910 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4911 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4912 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4913 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-4914 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5511 | USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5512 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5513 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5514 | USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5515 | USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5516 | USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5517 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5518 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5519 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5520 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5521 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5522 | USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5540 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5541 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5542 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5543 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5544 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5545 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5546 | USC "132U" FURNACE STEEL NAME PLATE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5550 | USC "132U" FURNACE STEEL STACK AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5551 | USC "132U" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5552 | USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5553 | USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5560 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5561 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5583 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5584 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5585 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5586 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5587 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5601 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5602 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5603 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5604 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5605 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5606 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5607 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5608 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5609 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5610 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5611 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5612 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5613 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5614 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5615 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5616 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5617 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5618 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5619 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5620 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5621 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5622 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5623 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5631 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5632 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5651 | USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5701 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5702 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5703 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5704 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5705 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5706 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5707 | USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5708 | USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5908 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5909 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5910 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5911 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5912 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5913 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-5914 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6304 | FURNACE STEEL END WALL TUBE SHEET DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6511 | USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6512 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6513 | USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6514 | USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6515 | USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6516 | USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6517 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6518 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6519 | USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6520 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6521 | USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6522 | USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6540 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6541 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6542 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6543 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6544 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6545 | USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6546 | USC "132U" FURNACE STEEL NAME PLATE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6550 | USC "132U" FURNACE STEEL STACK AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6552 | USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6553 | USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6560 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6561 | USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6583 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6584 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6585 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6586 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6587 | USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6601 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6602 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6603 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6604 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6605 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6606 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6607 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6608 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6609 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6610 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6611 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6612 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6613 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6614 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6615 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6616 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6617 | USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6618 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6619 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6620 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6621 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6622 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6623 | USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6631 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6632 | USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6651 | USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6701 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6702 | USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6703 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6704 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6705 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6706 | USC "132U" FURNACE STEEL STAIR TOWER PLANS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6707 | USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6708 | USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6908 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6909 | USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6910 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6911 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6912 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6913 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6914 | USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7000 | STEEL FOR PIPE RACK 10-PRK-0P01 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7100 | STEEL FOR PIPE RACK 10-PRK-0P02 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7200 | STEEL FOR PIPE RACK 10-PRK-0P03 |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K34
| CV | OL1-2K34-0001 | FOUNDATION FOR 10-TK-5670 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0002 | FOUNDATION FOR 10-PK-5628, 10-PIT-5628, P-10-5628A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0003 | FOUNDATION FOR 10-PK-1950, 10-C-1950A/B, 10-E-1951A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0004 | FOUNDATION FOR 10-E-2765 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0005 | FOUNDATION FOR 10-E-2585 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0006 | FOUNDATION FOR SKID 10-P-2801A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0007 | FOUNDATION FOR 10-D-5200 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0008 | FOUNDATION FOR 10-E-5200 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0009 | FOUNDATION FOR 10-E-5210 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0010 | FOUNDATION FOR 10-E-5220 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0011 | FOUNDATION FOR 10-F-5610 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0012 | FOUNDATION FOR 10-T-2120 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0013 | FOUNDATION FOR 10-T-2140 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0014 | FOUNDATION FOR 10-D-2110 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0015 | FOUNDATION FOR 10-D-5150 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0016 | FOUNDATION FOR 10-D-2160 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0017 | FOUNDATION FOR 10-D-2165 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0018 | FOUNDATION FOR 10-D-2136 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0019 | FOUNDATION FOR 10-E-2125A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0020 | FOUNDATION FOR 10-E-2136 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0021 | FOUNDATION FOR 10-E-2160 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0022 | FOUNDATION FOR 10-E-2165A/D |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0023 | FOUNDATION FOR 10-E-2166 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0024 | FOUNDATION FOR 10-E-2146 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0025 | FOUNDATION FOR 10-E-2145 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0026 | FOUNDATION FOR 10-E-2026 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0027 | FOUNDATION FOR 10-E-2048 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0028 | FOUNDATION FOR 10-P-2106A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0029 | FOUNDATION FOR PUMPS 10-P-2026A/B, 10-P-2126A/B, 10-P-2046A/B, 10-P-5140A/B, 10-P-2146A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0030 | FOUNDATION FOR 10-P-2105A/B AND 10-P-2006A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0031 | FOUNDATION FOR 10-F-2105A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0032 | FOUNDATION FOR 10-F-2009A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0033 | FOUNDATION FOR 10-F-2008A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0034 | FOUNDATION FOR 10-F-2026A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0035 | FOUNDATION FOR 10-F-2028A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0036 | FOUNDATION FOR 10-F-2136A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0037 | FOUNDATION FOR 10-X-2755 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0038 | FOUNDATION FOR 10-X-2036 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0039 | FOUNDATION FOR 10-T-2450 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0040 | FOUNDATION FOR 10-T-2300 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0041 | FOUNDATION FOR 10-T-2440 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0042 | FOUNDATION FOR 10-T-2330 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0043 | FOUNDATION FOR 10-D-2410A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0044 | FOUNDATION FOR 10-D-2435 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0045 | FOUNDATION FOR 10-D-2436 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0046 | FOUNDATION FOR 10-D-2240 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0047 | FOUNDATION FOR 10-D-2245 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0048 | FOUNDATION FOR 10-D-2445 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0049 | FOUNDATION FOR 10-D-2455 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0050 | FOUNDATION FOR 10-D-2220 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0051 | FOUNDATION FOR 10-D-2210 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0052 | FOUNDATION FOR 10-D-2230 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0053 | FOUNDATION FOR 10-D-2405 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0054 | FOUNDATION FOR 10-D-2415 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0055 | FOUNDATION FOR 10-D-2310 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0056 | FOUNDATION FOR 10-D-2312 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0057 | FOUNDATION FOR 10-D-2316 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0058 | FOUNDATION FOR 10-D-2326 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0059 | FOUNDATION FOR 10-D-2330 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0060 | FOUNDATION FOR 10-TK-2910 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0061 | FOUNDATION FOR 10-E-2435 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0062 | FOUNDATION FOR 10-E-2230A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0063 | FOUNDATION FOR 10-E-2412 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0064 | FOUNDATION FOR 10-E-2413 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0065 | FOUNDATION FOR 10-E-2445A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0066 | FOUNDATION FOR 10-E-2446 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0067 | FOUNDATION FOR 10-E-2455A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0068 | FOUNDATION FOR 10-E-2450 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0069 | FOUNDATION FOR 10-E-2470 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0070 | FOUNDATION FOR 10-E-2206 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0071 | FOUNDATION FOR 10-E-2210A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0072 | FOUNDATION FOR 10-E-2220A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0073 | FOUNDATION FOR 10-E-2240A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0074 | FOUNDATION FOR 10-D-2305 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0075 | FOUNDATION FOR 10-E-2305 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0076 | FOUNDATION FOR 10-E-2630 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0077 | FOUNDATION FOR 10-E-2326 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0078 | FOUNDATION FOR PUMPS 10-P-2302A/B, 10-P-2415A/B, 10-P-2445A/B, 10-P-2304, 10-P-2306A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0079 | FOUNDATION FOR PUMPS 10-P-2200A/B, 10-P-2220A/B, 10-P-10-P-2210A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0080 | FOUNDATION PUMPS FOR 10-P-2450A/B, 10-P-2455A/B, 10-P-2620A/B, 10-P-2666A/B, 10-P-2660A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0081 | FOUNDATION PUMPS FOR 10-P-2630A/B, 10-P-2310A/B, 10-P-2316A/B, 10-P-2326A/B, 10-P-2320A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0082 | FOUNDATION FOR 10-F-2320A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0083 | FOUNDATION FOR 10-F-2310A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0084 | FOUNDATION FOR 10-F-2306A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0085 | FOUNDATION FOR ANALYZER HOUSE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0086 | FOUNDATION FOR ANALYZER HOUSE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0087 | FOUNDATION FOR 10-PK-2900/2902/2906 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0088 | FOUNDATION FOR 10-PK-2920 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0089 | FOUNDATION FOR 10-PK-1920 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0090 | FOUNDATION FOR 10-PK-2350 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0091 | FOUNDATION FOR 10-PK-5555 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0092 | FOUNDATION FOR SKID 10-P-2201A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0093 | FOUNDATION FOR 10-F-2048A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0094 | FOUNDATION FOR 10-T-2580 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0095 | FOUNDATION FOR 10-T-2640 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0096 | FOUNDATION FOR 10-T-2570 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0097 | FOUNDATION FOR 10-T-2510, 10-D-2510 AND 10-E-2510 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0098 | FOUNDATION FOR 10-T-2540, 10-D-2540 AND 10-E-2540 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0099 | FOUNDATION FOR 10-T-2520 AND 10-D-2520 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0100 | FOUNDATION FOR 10-D-2411 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0101 | FOUNDATION FOR 10-D-2480A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0102 | FOUNDATION FOR 10-D-2465 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0103 | FOUNDATION FOR 10-D-2840 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0104 | FOUNDATION FOR 10-D-2830 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0105 | FOUNDATION FOR 10-D-2815 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0106 | FOUNDATION FOR 10-D-2820 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0107 | FOUNDATION FOR 10-D-2810 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0108 | FOUNDATION FOR 10-D-2645 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0109 | FOUNDATION FOR 10-D-2555 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0110 | FOUNDATION FOR 10-D-2550 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0112 | FOUNDATION FOR 10-D-2575 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0113 | FOUNDATION FOR 10-D-2880 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0114 | FOUNDATION FOR 10-D-2870 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0115 | FOUNDATION FOR 10-D-2860 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0116 | FOUNDATION FOR 10-D-2865 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0117 | FOUNDATION FOR 10-E-2587 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0120 | FOUNDATION FOR 10-E-2432 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0121 | FOUNDATION FOR 10-E-2575 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0122 | FOUNDATION FOR 10-E-2576 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0123 | FOUNDATION FOR 10-E-2645A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0124 | FOUNDATION FOR 10-E-2502 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0125 | FOUNDATION FOR 10-E-2515 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0126 | FOUNDATION FOR 10-E-2546 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0127 | FOUNDATION FOR 10-E-2548 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0128 | FOUNDATION FOR 10-E-2545 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0129 | FOUNDATION FOR 10-E-2805A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0130 | FOUNDATION FOR 10-E-2807 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0131 | FOUNDATION FOR 10-E-2809 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0132 | FOUNDATION FOR 10-E-2857 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0133 | FOUNDATION FOR 10-E-2858 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0134 | FOUNDATION FOR 10-E-2856 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0135 | FOUNDATION FOR 10-E-2855 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0136 | FOUNDATION FOR 10-E-2853 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0137 | FOUNDATION FOR 10-E-2852 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0139 | FOUNDATION FOR 10-E-2582 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0140 | FOUNDATION FOR 10-E-2504 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0142 | FOUNDATION FOR 10-PK-2930, 10-D-2930 AND 10-P-2930 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0143 | FOUNDATION FOR 10-R-2700A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0144 | FOUNDATION FOR 10-R-2620A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0145 | FOUNDATION FOR 10-R-2760 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0146 | FOUNDATION FOR 10-E-2620 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0147 | FOUNDATION FOR 10-E-2666 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0148 | FOUNDATION FOR 10-E-2665A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0149 | FOUNDATION FOR 10-E-2660 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0150 | FOUNDATION FOR 10-T-2710 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0151 | FOUNDATION FOR 10-T-2720 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0152 | FOUNDATION FOR 10-T-2660 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0153 | FOUNDATION FOR 10-T-2630 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0154 | FOUNDATION FOR 10-R-2470A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0155 | FOUNDATION FOR 10-D-2610 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0156 | FOUNDATION FOR 10-D-2600A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0157 | FOUNDATION FOR 10-D-2460 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0158 | FOUNDATION FOR 10-D-2440 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0159 | FOUNDATION FOR 10-D-1000 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0160 | FOUNDATION FOR 10-E-2635 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0161 | FOUNDATION FOR 10-E-2636 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0162 | FOUNDATION FOR 10-E-2472 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0163 | FOUNDATION FOR 10-E-2474 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0164 | FOUNDATION FOR 10-E-2465 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0165 | FOUNDATION FOR 10-E-2460 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0166 | FOUNDATION FOR 10-E-2440/2441/2442 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0167 | FOUNDATION FOR 10-E-1020 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0168 | FOUNDATION FOR 10-E-1015 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0169 | FOUNDATION FOR 10-E-1001A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0170 | FOUNDATION FOR 10-E-1000 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0171 | FOUNDATION FOR 10-E-1005 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0172 | FOUNDATION FOR PUMPS 10-P-5112A/B, 10-P-2714A/B, 10-P-2710A/B, 10-P-2720A/B, 10-P-2721A/B, 10-P-2910 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0173 | FOUNDATION FOR PUMPS 10-P-2724A/B, 10-P-2726A/B, 10-P-2750A/B, 10-P-2760A/B/C, 10-P-2705A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0174 | FOUNDATION FOR 10-PK-2912 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0175 | FOUNDATION FOR 10-PK-2922 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0176 | FOUNDATION FOR 10-PK-2940 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0177 | FOUNDATION FOR 10-D-2705 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0178 | FOUNDATION FOR 10-E-2705 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0179 | FOUNDATION FOR 10-D-2706 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0180 | FOUNDATION FOR 10-D-2735 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0181 | FOUNDATION FOR 10-D-2724 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0182 | FOUNDATION FOR 10-E-2730 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0183 | FOUNDATION FOR 10-E-2722 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0184 | FOUNDATION FOR 10-E-2755 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0185 | FOUNDATION FOR 10-E-2725A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0186 | FOUNDATION FOR 10-E-2726 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0188 | FOUNDATION FOR 10-E-2702 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0189 | FOUNDATION FOR 10-E-2701 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0190 | FOUNDATION FOR 10-E-2706 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0191 | FOUNDATION FOR 10-E-2008A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0192 | FOUNDATION FOR 10-D-2710 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0193 | FOUNDATION FOR 10-D-2720 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0194 | FOUNDATION FOR 10-E-2720 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0195 | FOUNDATION FOR 10-E-2724 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0196 | FOUNDATION FOR 10-E-2715A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0197 | FOUNDATION FOR 10-E-2714 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0198 | FOUNDATION FOR 10-E-2882 AND 10-D-2882 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0199 | FOUNDATION FOR 10-E-2884 AND 10-D-2884 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0200 | FOUNDATION FOR 10-E-2100A/B/C/D/E/F |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0201 | FOUNDATION FOR 10-TK-2320 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0202 | FOUNDATION FOR 10-E-1050 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0203 | FOUNDATION FOR 10-PK-1910 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0204 | FOUNDATION FOR 10-PK-5910 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0205 | FOUNDATION FOR 10-PK-5914 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0206 | FOUNDATION FOR 10-PK-5912 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0207 | FOUNDATION FOR 10-PK-2914 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0208 | FOUNDATION FOR IGNITION SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0209 | FOUNDATION AND ELEVATION FOR 10-C-3070 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0210 | FOUNDATION FOR 10-TK-3900 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0211 | FOUNDATION FOR 10-T-3000 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0212 | FOUNDATION FOR 10-T-3040 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0213 | FOUNDATION FOR 10-T-3020 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0214 | FOUNDATION FOR 10-D-3010 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0215 | FOUNDATION FOR 10-T-3030 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0216 | FOUNDATION FOR 10-T-3050 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0217 | FOUNDATION FOR 10-T-3060 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0218 | FOUNDATION FOR 10-T-3090 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0219 | FOUNDATION FOR 10-T-3080 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0220 | FOUNDATION FOR 10-T-3070 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0221 | FOUNDATION FOR 10-D-3100, 10-A-3100 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0222 | FOUNDATION FOR 10-D-3908 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0223 | FOUNDATION FOR 10-D-3902 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0224 | FOUNDATION FOR 10-D-3904 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0225 | FOUNDATION FOR 10-D-3906 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0226 | FOUNDATION FOR 10-D-3180 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0227 | FOUNDATION FOR 10-D-3110 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0228 | FOUNDATION FOR 10-E-3004A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0229 | FOUNDATION FOR 10-E-3014A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0230 | FOUNDATION FOR 10-E-3015 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0231 | FOUNDATION FOR 10-E-3084 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0232 | FOUNDATION FOR 10-E-3085A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0233 | FOUNDATION FOR 10-E-3095 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0234 | FOUNDATION FOR 10-E-3096 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0235 | FOUNDATION FOR 10-E-3098 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0236 | FOUNDATION FOR 10-E-3055A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0237 | FOUNDATION FOR 10-E-3045A/B/C/D |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0238 | FOUNDATION FOR 10-E-3044 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0239 | FOUNDATION FOR 10-E-3150 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0240 | FOUNDATION FOR 10-E-3160 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0241 | FOUNDATION FOR 10-E-3005 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0242 | FOUNDATION FOR 10-E-3070 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0243 | FOUNDATION FOR PUMPS 10-P-2570A/B, 10-P-2575A/B, 10-P-2586A/B, 10-P-2647, 10-P-2646A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0244 | FOUNDATION FOR PUMPS 10-P-2802A/B, 10-P-2805A/B, 10-P-2815, 10-P-2855A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0245 | FOUNDATION FOR PUMPS 10-P-3046A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0246 | FOUNDATION FOR PUMPS 10-P-3045A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0247 | FOUNDATION FOR PUMPS 10-P-3026A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0248 | FOUNDATION FOR PUMPS 10-P-3056A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249 | FOUNDATION FOR PUMPS 10-P-3080A/B, 10-P-3030A/B, 10-P-3000A/B, 10-P-3020A/B, 10-P-3061A/B, 10-P-3060A/B, 10-P-3062A/B, 10-P-3002A/B, 10-P-3902A/B, 10-P-3904A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250 | FOUNDATION FOR PUMPS 10-P-3096A/B, 10-P-3086A/B, 10-P-3036A/B, 10-P-3016A/B, 10-P-3900, 10-P-3160A/B, 10-P-3076A/B, 10-P-3906A/B, 10-P-3908A/B, 10-P-3110A/B, 10-P-3126A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0252 | FOUNDATION FOR PUMPS 10-P-5900A/B, 10-P-5950A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0253 | FOUNDATION FOR PUMPS 10-P-5360A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0254 | FOUNDATION FOR PUMPS 10-P-5350 A/B/C/D/E/F/G/H |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0256 | FOUNDATION FOR 10-PK-2904 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0257 | FOUNDATION FOR 10-D-5560 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0258 | FOUNDATION FOR 10-PK-5560 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0259 | FOUNDATION FOR 10-PK-5355 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0260 | FOUNDATION FOR 10-PK-5394 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0261 | FOUNDATION FOR 10-PK-5398 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0262 | FOUNDATION FOR 10-PK-5397 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0263 | FOUNDATION FOR 10-PK-5392 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0264 | FOUNDATION FOR 10-PK-5390 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0265 | FOUNDATION FOR 10-PK-5396 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0266 | FOUNDATION FOR 10-D-3126 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0267 | FOUNDATION FOR 10-D-5550 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0268 | FOUNDATION FOR 10-D-5500 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0269 | FOUNDATION FOR 10-D-5510 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0270 | FOUNDATION FOR 10-D-5513 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0271 | FOUNDATION FOR 10-D-5515 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0272 | FOUNDATION FOR 10-D-5520 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0273 | FOUNDATION FOR 10-C-5520A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0274 | FOUNDATION FOR 10-PK-5125, 10-D-5125A/B, 10-F-5125A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0275 | FOUNDATION FOR 10-E-5513 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0276 | FOUNDATION FOR PUMPS 10-P-5550A/B, 10-P-5552 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0277 | FOUNDATION FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0278 | FOUNDATION FOR 10-TK-5640 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0279 | FOUNDATION FOR 10-TK-5675A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0280 | FOUNDATION FOR 10-TK-5676 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0281 | FOUNDATION FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0282 | FOUNDATION FOR 10-TX/C-2550 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0283 | FOUNDATION FOR 10-C-5650A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0287 | FOUNDATION FOR 10-PK-5627, 10-PIT-5627, P-10-5627A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0288 | FOUNDATION FOR 10-PK-5692 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0289 | FOUNDATION FOR 10-PK-5693 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0290 | FOUNDATION FOR 10-PK-5694 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0291 | FOUNDATION FOR 10-PK-5671 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0292 | FOUNDATION FOR 10-PK-5672 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0293 | FOUNDATION FOR 10-PK-5697 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0294 | FOUNDATION FOR 10-PK-5690 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0295 | FOUNDATION FOR 10-PK-5691 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0296 | FOUNDATION FOR 10-PK-5670 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0297 | FOUNDATION FOR 10-P-5670A/B, 10-P-5671A/B, 10-P-5644A/B, 10-P-5645A/B, 10-P-5646A/B, 10-P-5647A/B, 10-P-5675, 10-P-5676 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0298 | FOUNDATION FOR 10-D-5646 AND 10-X-5646 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0299 | FOUNDATION FOR 10-D-5644 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0300 | FOUNDATION FOR 10-PK-5644 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0301 | FOUNDATION FOR 10-PK-5653 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0302 | FOUNDATION FOR 10-PK-5650 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0303 | FOUNDATION FOR 10-TK-5110 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0304 | FOUNDATION FOR 10-TK-5120 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0305 | FOUNDATION FOR 10-TK-5130 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0306 | FOUNDATION FOR 10-D-5140 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0307 | FOUNDATION FOR 10-D-5400 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0308 | FOUNDATION FOR 10-D-5114 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0309 | FOUNDATION FOR 10-D-5112, 10-E-5112 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0310 | FOUNDATION FOR 10-D-5552 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0311 | FOUNDATION FOR 10-D-5565 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0312 | FOUNDATION FOR 10-E-5520 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0313 | FOUNDATION FOR 10-E-5113 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0314 | FOUNDATION FOR 10-E-5552 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0315 | FOUNDATION FOR 10-E-5110 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0316 | FOUNDATION FOR 10-P-5100A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0317 | FOUNDATION FOR 10-P-5102A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0318 | FOUNDATION FOR 10-PK-5191 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0319 | FOUNDATION FOR 10-PK-5192 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0320 | FOUNDATION FOR 10-PK-5115, 10-F-5115A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0321 | FOUNDATION FOR 10-PK-5125, 10-D-5125A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0322 | FOUNDATION OF 10-D-1950 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0323 | FOUNDATION FOR 10-TK-5900 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0324 | FOUNDATION FOR 10-TK-5950 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0325 | FOUNDATION FOR 10-PK-5695 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0326 | FOUNDATION FOR 10-PK-5696 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0327 | FOUNDATION FOR 10-X-2310 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0328 | FOUNDATION FOR 10-X-2312 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0329 | FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5900 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0330 | FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5950 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0331 | FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2320 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0332 | FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2910 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0333 | FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-3900 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0334 | FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-PK-1910 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1000 | FOUNDATION FOR 10-T-2000 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1020 | FOUNDATION FOR 10-T-2020 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1040 | FOUNDATION FOR 10-T-2100 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1060 | CONCRETE STRUCTURE FOR 10-T-2040 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1080 | FOUNDATION FOR 10-H-1100 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1100 | FOUNDATION FOR 10-H-1200/1600 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1120 | FOUNDATION FOR PSA PACKAGE 10-PK-2560, 10-D-2560A/F, 10-D-2565 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1140 | FOUNDATION FOR LIFTING STATION 10-PIT-5605 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1160 | FOUNDATION FOR LIFTING STATION 10-PIT-5610 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1180 | FOUNDATION FOR BASIN 10-PIT-2390 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1200 | FOUNDATION FOR LIFTING STATION 10-PIT-5603 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1220 | FOUNDATION FOR LIFTING STATION 10-PIT-5604 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1240 | FOUNDATION FOR BASIN 10-PIT-2090 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1260 | FOUNDATION FOR BASIN 10-PIT-2190 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1280 | FOUNDATION FOR BASIN 10-PIT-2790 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1300 | FOUNDATION FOR BASIN 10-PIT-2322 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1320 | FOUNDATION FOR BASIN 10-PIT-3190 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1340 | FOUNDATION FOR LIFTING STATION 10-PIT-5601 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1360 | FOUNDATION FOR LIFTING STATION 10-PIT-5600 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1400 | FOUNDATION FOR LIFTING STATION 10-PIT-5370 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1420 | FOUNDATION FOR BASIN 10-PIT-5602 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1440 | FOUNDATION FOR BASIN 10-PIT-2392 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1460 | FOUNDATION FOR BASIN 10-PIT-5658 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1480 | FOUNDATION FOR BASIN 10-PIT-5615 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1500 | FOUNDATION FOR BASIN 10-PIT-5656 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1520 | FOUNDATION FOR BASIN 10-PIT-5620A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1540 | FOUNDATION FOR LIFTING STATION 10-PIT-5630 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1560 | FOUNDATION FOR BASIN 10-PIT-5633 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1580 | FOUNDATION FOR LIFTING STATION 10-PIT-5631 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1600 | FOUNDATION FOR BASIN 10-PIT-5671 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1620 | FOUNDATION FOR BASIN 10-PIT-5650A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1640 | FOUNDATION FOR BASIN 10-PIT-5655 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1660 | FOUNDATION AND ELEVATION FOR 10-C-2200, 10-E-2200 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1680 | FOUNDATION FOR CLARIFIER 10-TK-5651A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1700 | FOUNDATION FOR METERING STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1720 | FOUNDATION FOR BASIN 10-PIT-5642 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1740 | FOUNDATION AND ELEVATION FOR 10-C-2800, 10-E-2800 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1760 | FOUNDATION AND ELEVATION FOR 10-C-2850, 10-E-2850 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1780 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1820 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1840 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1860 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1880 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1900 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1920 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1940 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1960 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1980 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2000 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2020 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2040 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2060 | FOUNDATION FOR SUPPORTS FLARE UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2080 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2100 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2120 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2140 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2160 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2180 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2200 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2220 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2240 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2260 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2280 | FOUNDATION FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2300 | FOUNDATION FOR 10-SLW-5T02 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2320 | FOUNDATION FOR 10-SLW-5T01 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2340 | FOUNDATION FOR 10-SLW-0C01 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2360 | FOUNDATION FOR 10-SLW-5W01 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2380 | FOUNDATION FOR 10-SLW-5F01 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2400 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2420 | FOUNDATION FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2440 | FOUNDATION FOR LIFTING STATION 10-PIT-5632 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2500 | BASIN FOR COOLING TOWER 10-PIT-5350 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K35
| CV | OL1-2K35-0001 | STEEL STRUCTURE FOR 10-T-2040 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1000 | STEEL STRUCTURE FOR 10-C-2200, 10-E-2200 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1020 | STEEL STRUCTURE FOR 10-C-2800, 10-E-2800 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1040 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2390 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1060 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2090 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1080 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2190 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1100 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2790 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1120 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2322 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1140 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-3190 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1160 | STEEL PLATF. FOR COOLING TOWER 5350 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1180 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2392 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1200 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5658 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1220 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5615 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1240 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5656 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1260 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5620A/B/C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1280 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5655 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1300 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1320 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1340 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1360 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1380 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1400 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1420 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1440 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1460 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1480 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1500 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1520 | STEEL FOR SUPPORTS FLARE UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1540 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1560 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1580 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1600 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1620 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1640 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1660 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1680 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1700 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1720 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1740 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1760 | STEEL FOR PLATFORMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1800 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5642 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1820 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5602 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1840 | STEEL STRUCTURE FOR 10-C-2850, 10-E-2850 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1860 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5633 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1880 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5650A/B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1900 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5671 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K35-1920 | STEEL FOR SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K36
| CV | OL1-2K36-0001 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0002 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0003 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0004 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0005 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0006 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0007 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0008 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0009 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0010 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0011 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0012 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0013 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-0020 | OVERALL UNDERGROUND INTERFACE POINTS LOCATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K36-1000 | MAJOR UNDERGROUND PIPING LAYOUT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K37
| CV | OL1-2K37-1020 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1040 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1060 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1080 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1100 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1120 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1140 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1160 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1180 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1200 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1220 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1240 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1260 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1280 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K37-1300 | GRADING UNDERGROUND AND FOUNDATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K38
| CV | OL1-2K38-0002 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0003 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0004 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0005 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0006 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0007 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0008 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0009 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0010 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0011 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0012 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0013 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0014 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0015 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-0016 | INSTALLATION DWG-DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1040 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1060 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1080 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1100 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1120 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1140 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1160 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1180 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1200 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1220 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1240 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1260 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1280 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1300 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1320 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1340 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1360 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1380 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1400 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1420 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1440 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1460 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1480 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1500 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1520 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1540 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1560 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1580 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1600 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1620 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1640 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1660 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1680 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1700 | CHANNELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K38-1720 | TRENCHES/DUCT BANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K39
| CV | OL1-2K39-0001 | BUILDING 3D MODEL VIEWS - SUB-E & FAR-1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K39-0003 | BUILDING 3D MODEL VIEWS - SUB-C & FAR-2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K39-0005 | BUILDING 3D MODEL VIEWS - GATEHOUSE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K39-0007 | BUILDING 3D MODEL VIEWS - OPERATION TOOL ROOM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K43 Soil investigation & resisitivity report
| CV | OL1-2K43-0002 | Technical Specification for Geotechnical Investigation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-10 | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00147 | TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date |  | 2018-11-01
[6 empty] | Owner Cmmt* |  | R1
| CV | OL1-2K43-0003 | Price List for Geotechnical Investigation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-10 | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00147 | TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date |  | 2018-11-01
[6 empty] | Owner Cmmt* |  | R1
| CV | OL1-2K43-0004 | Soil Investigation Plan |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-10 | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00145 | TPSK-LSPA1-T-CV-00163
Return Date
Owner Cmmt*
Category Code: K44
| CV | OL1-2K44-1020 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1040 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1060 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1080 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1100 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1120 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1140 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1160 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1180 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1200 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1220 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K44-1240 | PILING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K52
| CV | OL1-2K52-0001 | CIVIL WORKS MTL QTY SUMMARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K53
| CV | OL1-2K53-0001 | STEEL STRUCTURES MTL QTY SUMMARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K54
| CV | OL1-2K54-0001 | BUILDINGS QUANTITIES - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K54-0002 | BUILDINGS QUANTITIES - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K54-0003 | BUILDINGS QUANTITIES - GATEHOUSE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K54-0004 | BUILDINGS QUANTITIES - OPERATION TOOL ROOM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K60
| CV | OL1-2K60-0002 | ISO PRESSURE DWG UNIT 101B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0003 | ISO PRESSURE DWG UNIT 102A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0004 | ISO PRESSURE DWG UNIT 102B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0005 | ISO PRESSURE DWG UNIT 102C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0006 | ISO PRESSURE DWG UNIT 102D |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0007 | ISO PRESSURE DWG UNIT 102E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0008 | ISO PRESSURE DWG UNIT 103A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0009 | ISO PRESSURE DWG UNIT 100C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0010 | ISO PRESSURE DWG UNIT 103S |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0011 | ISO PRESSURE DWG UNIT 100M |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0012 | ISO PRESSURE DWG UNIT 105F |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0013 | ISO PRESSURE DWG UNIT 105T |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0014 | ISO PRESSUREDWG UNIT 105U |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0015 | ISO PRESSURE DWG UNIT 105W |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K60-0016 | ISO PRESSURE DWG UNIT 100S |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K61
| CV | OL1-2K61-0002 | ISO GRAVITY DWG UNIT 101B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0003 | ISO GRAVITY DWG UNIT 102A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0004 | ISO GRAVITY DWG UNIT 102B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0005 | ISO GRAVITY DWG UNIT 102C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0006 | ISO GRAVITY DWG UNIT 102D |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0007 | ISO GRAVITYDWG UNIT 102E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0008 | ISO GRAVITY DWG UNIT 103A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0009 | ISO GRAVITY DWG UNIT 100C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0010 | ISO GRAVITY DWG UNIT 103S |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0011 | ISO GRAVITY DWG UNIT 100M |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0012 | ISO GRAVITY DWG UNIT 105F |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0013 | ISO GRAVITY DWG UNIT 105T |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0014 | ISO GRAVITY DWG UNIT 105U |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0015 | ISO GRAVITY DWG UNIT 105W |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K61-0016 | ISO GRAVITY DWG UNIT 100S |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K92 Procedures & Standards
| CV | OL1-2K92-0001 | General Notes For Underground Works |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00086
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K92-0002 | General Notes For Precast Concrete Works |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00137
Return Date
Owner Cmmt*
| CV | OL1-2K92-0003 | General Notes For Concrete Works |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00086
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K92-0004 | General Notes For Steel Structures |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00086
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K92-0005 | GENERAL NOTES FOR PILES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K96
| CV | OL1-2K96-0001 | TECHNICAL SPECIFICATION FOR PILES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K96-0002 | TECH. SPEC. CONCRETE WORKS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K96-0003 | TECH. SPEC. PRECAST CONCRETE WORKS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K96-0004 | TECH. SPEC. STEEL STRUCT.EREC. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L01 Passive & Active Fire Protection Philosophy
| SE | OL1-2L01-0001 | FIREFIGHTING SYSTEM SPECIFICATION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L01-0002 | PASSIVE FIRE PROTECTION SPECIFICATION |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L02 Active Fire Protection System
| SE | OL1-2L02-0001 | DATASHEET FOR FIREFIGHTING EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L02-0011 | DATASHEET FOR DELUGE VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L02-0021 | DATASHEET FOR CLEAN AGENT FIRE EXTINGUISHING SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L02-0031 | DATASHEET FOR STEAM CURTAIN SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L02-0041 | DATASHEET FOR SPRINKLER SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L02-0051 | DATASHEET FOR SAFETY & LIFE SAVING EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L10
| SE | OL1-2L10-0001 | Noise Control |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-SE-00472
Return Date
Owner Cmmt*
| SE | OL1-2L10-0003 | ACUSTIC INSULATION SPECIFICATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L11
| SE | OL1-2L11-0001 | NOISE STUDY (NOISE MAP) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L20 Fire system calculation
| SE | OL1-2L20-0001 | FIRE WATER DEMAND CALCULATION AND HYDRAULIC STUDY FOR FW NETWORK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L20-0002 | HYDRAULIC CALCULATION FOR FIREWATER DELUGE/WATER SPRAY SYSTEM |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L20-0003 | DELUGE NOZZLES ARRANGEMENT CALCULATION NOTE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L40 Active Fire Fighting Systems
| SE | OL1-2L40-0001 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - SUBSTATION & FAR E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0002 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - SUBSTATION & FAR C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0003 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - COOLING WATER UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0004 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - WASTE WATER TREATMENT UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0005 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0006 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - FLARE UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0007 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - METERING STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0008 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - FURNACES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0009 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - FURNACES AND AUXILIARIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0010 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - QUENCH |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0011 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - C3 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0012 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - PROCESS COLD COMPRESSORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0013 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0014 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - BUTADIENE EXTRACT UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-0015 | FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - HOT FRACTIONATION / GHU UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-1000 | OVERALL FIRE WATER NETWORK DRAWING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-1001 | FIREWATER P&ID (MAIN NETWORK / DISTRIBUTION / DELUGE / SPRINKLER) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L40-2001 | FIREWATER PIPING LINE LIST (PLL) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L41 Passive Fire Protection Drawings
| SE | OL1-2L41-0001 | PASSIVE FIRE PROTECTION DRAWING - SUBSTATION & FAR E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0002 | PASSIVE FIRE PROTECTION DRAWING - SUBSTATION & FAR C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0003 | PASSIVE FIRE PROTECTION DRAWING - COOLING WATER UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0004 | PASSIVE FIRE PROTECTION DRAWING - WASTE WATER TREATMENT UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0005 | PASSIVE FIRE PROTECTION DRAWING - UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0006 | PASSIVE FIRE PROTECTION DRAWING - FLARE UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0007 | PASSIVE FIRE PROTECTION DRAWING - METERING STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0008 | PASSIVE FIRE PROTECTION DRAWING - FURNACES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0009 | PASSIVE FIRE PROTECTION DRAWING - FURNACES AND AUXILIARIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0010 | PASSIVE FIRE PROTECTION DRAWING - QUENCH |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0011 | PASSIVE FIRE PROTECTION DRAWING - C3 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0012 | PASSIVE FIRE PROTECTION DRAWING - PROCESS COLD COMPRESSORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0013 | PASSIVE FIRE PROTECTION DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0014 | PASSIVE FIRE PROTECTION DRAWING - BUTADIENE EXTRACT UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-0015 | PASSIVE FIRE PROTECTION DRAWING - HOT FRACTIONATION / GHU UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L41-1000 | OVERALL PASSIVE FIRE PROTECTION DRAWING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L42 Hazardous Area Classification
| SE | OL1-2L42-0002 | HAZARDOUS AREA CLASSIFICATION DRAWING, OLEFINS UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0003 | HAZARDOUS AREA CLASSIFICATION DRAWING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0005 | HAZARDOUS AREA CLASSIFICATION DRAWING - COOLING WATER UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0006 | HAZARDOUS AREA CLASSIFICATION DRAWING - WASTE WATER TREATMENT UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0007 | HAZARDOUS AREA CLASSIFICATION DRAWING - UTILITIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0008 | HAZARDOUS AREA CLASSIFICATION DRAWING - FLARE UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0009 | HAZARDOUS AREA CLASSIFICATION DRAWING - METERING STATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0010 | HAZARDOUS AREA CLASSIFICATION DRAWING - FURNACES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0011 | HAZARDOUS AREA CLASSIFICATION DRAWING - FURNACES AND AUXILIARIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0012 | HAZARDOUS AREA CLASSIFICATION DRAWING - QUENCH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0013 | HAZARDOUS AREA CLASSIFICATION DRAWING - C3 HYDROGENATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0014 | HAZARDOUS AREA CLASSIFICATION DRAWING - PROCESS COLD COMPRESSORS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0015 | HAZARDOUS AREA CLASSIFICATION DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0016 | HAZARDOUS AREA CLASSIFICATION DRAWING - BUTADIENE EXTRACT UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0017 | HAZARDOUS AREA CLASSIFICATION DRAWING - HOT FRACTIONATION / GHU UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0018 | HAZARDOUS AREA CLASSIFICATION DRAWING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L44 Life saving Equip & Escape Route Drawing
| SE | OL1-2L44-0001 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - SUBSTATION & FAR E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0002 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - SUBSTATION & FAR C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0003 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - COOLING WATER UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0004 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - WASTE WATER TREATMENT UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0005 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0006 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - FLARE UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0007 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - METERING STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0008 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - FURNACES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0009 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - FURNACES AND AUXILIARIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0010 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - QUENCH |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0011 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - C3 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0012 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - PROCESS COLD COMPRESSORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0013 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0014 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - BUTADIENE EXTRACT UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L44-0015 | LIFESAVING EQ. & ESCAPE ROUTE DRAWING - HOT FRACTIONATION / GHU UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L50
| SE | OL1-2L50-0001 | MATERIAL REQUISITION FOR FIREFIGHTING EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L51
| SE | OL1-2L51-0001 | MATERIAL REQUISITION FOR DELUGE VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L51-0002 | MATERIAL REQUISITION FOR CLEAN AGENT FIRE EXTINGUISHING SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L51-0003 | MATERIAL REQUISITION FOR STEAM CURTAIN SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L51-0004 | MATERIAL REQUISITION FOR SPRINKLER SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L52
| SE | OL1-2L52-0001 | MATERIAL REQUISITION FOR SAFETY & LIFE SAVING EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L60 All project study and Report pertain to Loss control and Safety Process safety report; HAZOP Report; LOPA Report; PSSR Reports; Risk analysis dossiers; and and Project Response;
| SE | OL1-2L60-0001 | HAZARD & OPERABILITY STUDY (FEED) REPORT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-1001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) REPORT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-2001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) REPORT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-3001 | SIL CLASSIFICATION REPORT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-4001 | SIL CLASSIFICATION REPORT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L62 Recommendation Monitoring System
| SE | OL1-2L62-0001 | HAZARD & OPERABILITY STUDY (FEED) CLOSEOUT REPORT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L62-1001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L62-2001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L65 Hazardous Source Data
| SE | OL1-2L65-0050 | HAZARDOUS AREA CLASSIFICATION SOURCE LIST, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L66 Register of Safety Devices
| SE | OL1-2L66-0001 | REGISTER FOR SAFETY DEVICES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L72 Loss Control and Safety procedure
| SE | OL1-2L72-0001 | PROCESS HAZARD ANALYSIS PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L72-0002 | SIL CLASSIFICATION PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: M03 Mechanical datasheet
| ME | OL1-2M03-1000 | Mechanical Equipment Data Sheet - LPG Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-1001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 36M |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00247
Return Date
Owner Cmmt*
| ME | OL1-2M03-1002 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1000 - LPG VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-1003 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1001 - LPG STEAM VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-1005 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1005 - LPG FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-1015 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1015 - LPG SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-1020 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1020 - LIQUID FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-1051 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-1050 - C2 FEED SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-1950 | Mechanical Equipment Datasheet - Decoking Air Compressor Package |  | Class 2 | Purpose** | IFA | IFQ | IFQ
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-11 | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00050 | TPSK-LSPA1-T-ME-00161 | TPSK-LSPA1-T-ME-00261
[6 empty] | Return Date | 2018-10-02 |  | 2018-11-29
[6 empty] | Owner Cmmt* | A3 |  | R1
| ME | OL1-2M03-1951 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-1950 - DECOKE AIR RECEIVER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2000 | Mechanical Equipment Data Sheet - Quench Oil Tower |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSL-LSPA1-T-ME-00420
Return Date
Owner Cmmt*
| ME | OL1-2M03-2001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 132U |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00247
Return Date
Owner Cmmt*
| ME | OL1-2M03-2002 | ELEVATOR DATA SHEET |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2003 | MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2006 | Mechanical Equipment Data Sheet - Quench Oil Pump |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26 | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00235 | TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2018-11-19
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2007 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2008 - QUENCH OIL FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2008 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2008 - VLP STEAM GENERATORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2009 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2009 - QO PUMP PURGE OIL FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2020 | Mechanical Equipment Data Sheet - Light Fuel Oil Stripper |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00447
Return Date
Owner Cmmt*
| ME | OL1-2M03-2024 | Mechanical Equipment Datasheet - Light Fuel Oil Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00457
Return Date
Owner Cmmt*
| ME | OL1-2M03-2025 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2026 - CRACKER BOTTOMS PRODUCT FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2026 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2026 - FUEL OIL PRODUCT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2028 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2028 - FO PUMP PURGE OIL FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-28 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00387 | TPSK-LSPA1-T-ME-00418
Return Date
Owner Cmmt*
| ME | OL1-2M03-2046 | Mechanical Equipment Datasheet - Heavy Fuel Oil Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00457
Return Date
Owner Cmmt*
| ME | OL1-2M03-2048 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2048 - HEAVY FUEL OIL PRODUCT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2049 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2048 - HEAVY FUEL OIL FILTERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2090 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2090 - QUENCH OIL DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2091 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2090 - QUENCH OIL DRAIN DRUM PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2100 | Mechanical Equipment Data Sheet - Quench Water Tower |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00443
Return Date
Owner Cmmt*
| ME | OL1-2M03-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler |  | Class 2 | Purpose** | IFA | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00058 | TPSK-LSPA1-T-ME-00154
[6 empty] | Return Date | 2018-09-28 | 2018-11-07
[6 empty] | Owner Cmmt* | A3 | R1
| ME | OL1-2M03-2104 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2105 - QUENCH OIL REFLUX FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2105 | Mechanical Equipment Datasheet - Quench Oil Reflux Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00457
Return Date
Owner Cmmt*
| ME | OL1-2M03-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-27 | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2018-11-19
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2110 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2110 - INTERCEPTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2120 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2120 - DISTILLTATE STRIPPER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2125 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2125 - DISTILLATE STRIPPER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2126 | Mechanical Equipment Datasheet - Distillate Stripper Bottom Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00410
Return Date
Owner Cmmt*
| ME | OL1-2M03-2136 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2136 - PROCESS WATER FEED COALESCER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2137 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2136 - PROCESS WATER STRIPPER FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2138 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2136 - PROCESS WATER FEED FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2140 | Mechanical Equipment Data Sheet - Process Water Stripper |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00458
Return Date
Owner Cmmt*
| ME | OL1-2M03-2145 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2145 - PROCESS WATER STRIPPER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26 | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00235 | TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2018-11-19
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2147 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2146 - DSG FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2160 | Mechanical Equipment Data Sheet - Dilution Steam Generator |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2161 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2160 - DILUTION STEAM SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2164 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2165 - DSG REBOILER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2165 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2165 - DSG REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2166 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2166 - DSG BLOWDOWN COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2190 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2190 - QUENCH WATER DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2191 | Mechanical Equipment Datasheet - Quench Water Drain Drum Pump |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00400
Return Date
Owner Cmmt*
| ME | OL1-2M03-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor |  | Class 2 | Purpose** | IFA | IFQ | IFQ
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-03 | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00038 | TPSK-LSPA1-T-ME-00127 | TPSK-LSPA1-T-ME-00280
[6 empty] | Return Date | 2018-09-28 |  | 2018-11-30
[6 empty] | Owner Cmmt* | A3 |  | R1
| ME | OL1-2M03-2206 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2206 - WASH WATER COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2210 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2210 - CG 1ST STAGE SUCTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2211 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2210 - CG 1ST STAGE AFTERCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2212 | Mechanical Equipment Datasheet - CG 1st Stage Condensate Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00413
Return Date
Owner Cmmt*
| ME | OL1-2M03-2220 | Mechanical Equipment Data Sheet - CG 2nd Stage Suction Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2221 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2220 - CG 2ND STAGE AFTERCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2222 | Mechanical Equipment Datasheet - CG 2nd Stage Condensed HC Pump |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00343
Return Date
Owner Cmmt*
| ME | OL1-2M03-2230 | Mechanical Equipment Data Sheet - CG 3rd Stage Suction Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2231 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2230 - CG 3RD STAGE AFTERCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2240 | Mechanical Equipment Data Sheet - CG 4th Stage Suction Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2241 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2240 - CG 4TH STAGE AFTERCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2245 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2245 - CG 4TH STAGE DISCHARGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2250 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-2200 - CRACKED GAS COMPRESSOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2300 | Mechanical Equipment Data Sheet - Caustic Tower |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00246 | TPSK-LSPA1-T-ME-00419
[6 empty] | Return Date | 2018-11-27
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2302 | Mechanical Equipment Datasheet - Strong Caustic Circulating Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00320
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00320 | TPSK-LSPA1-T-ME-00411
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2305 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2305 - CAUSTIC TOWER FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00320 | TPSK-LSPA1-T-ME-00411
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2307 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2306 - WEAK CAUSTIC STRAINER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2309 | Mechanical Equipment Data Sheet - Yellow Oil Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00484
Return Date
Owner Cmmt*
| ME | OL1-2M03-2310 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2310 - SPENT CAUSTIC DEOILING DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2311 | Mechanical Equipment Datasheet - Wash Oil Circulating Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00320
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2312 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2312 - SPENT WASH OIL DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2314 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2310 - WASH OIL CIRCULATION FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2316 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2316 - SPENT CAUSTIC DEGASSING DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2317 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2316 - SPENT CAUSTIC DISCHARGE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2319 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-2320 - SPENT CAUSTIC PUMP DISCHARGE FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2320 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-2320 - SPENT CAUSTIC STORAGE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2321 | Mechanical Equipment Datasheet - Spent Caustic Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00335
Return Date
Owner Cmmt*
| ME | OL1-2M03-2322 | Mechanical Equipment Data Sheet - Skim Oil Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2326 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2326 - SPENT CAUSTIC STRIPPER FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2327 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2328 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2330 | Mechanical Equipment Data Sheet - Spent Caustic Stripper |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00462
Return Date
Owner Cmmt*
| ME | OL1-2M03-2331 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2330 - SPENT CAUSTIC STRIPPER OVERHEAD DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2350 | Mechanical Equipment Datasheet for Wet Air Oxidation Package |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00390
Return Date
Owner Cmmt*
| ME | OL1-2M03-2390 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2390 - CAUSTIC DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2391 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2390 - CAUSTIC DRAIN DRUM PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2392 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2392 - SPENT CAUSTIC DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2393 | Mechanical Equipment Datasheet - Spent Caustic Drain Drum Pump |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00457
Return Date
Owner Cmmt*
| ME | OL1-2M03-2405 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2405 - GAS DRYER FEED KO DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2406 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2405 - GAS DRYER FEED CHILLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2410 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2410 - CRACKED GAS DRYER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2411 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2411 - CRACKED GAS MERCURY ADSORBER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2412 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2412 - HP DEPROPANIZER FEED CHILLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2413 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2413 - HP DEPROP FEED / OVERHEAD EXCHANGER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2415 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2415 - CG LIQUID DRYER FEED COALESCER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2416 | Mechanical Equipment Datasheet - CG Liquid Dryer Feed Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00413
Return Date
Owner Cmmt*
| ME | OL1-2M03-2420 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2420 - CG LIQUID DRYER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2430 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2430 - REGEN GAS FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2432 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2432 - REGEN GAS SHP HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2434 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2435 - REGEN GAS EFFLUENT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2435 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2435 - REGEN GAS SEPARATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2436 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2436 - MERCURY ADSORBER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2438 | Mechanical Equipment Data Sheet - HP Depropanizer Reflux Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00484
Return Date
Owner Cmmt*
| ME | OL1-2M03-2439 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2440 - HP DEPROPANIZER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2440 | Mechanical Equipment Datasheet - HP Depropanizer |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00215 | TPSK-LSPA1-T-ME-00416
Return Date
Owner Cmmt*
| ME | OL1-2M03-2441 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2441 - HP DEPROP REFLUX CHILLER NO. 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2442 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2442 - HP DEPROP REFLUX CHILLER NO. 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2443 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2445 - HP DEPROPANIZER COND PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2444 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2445 - HP DEPROP REBOILER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2445 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2445 - HP DEPROPANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2446 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2446 - LP DEPROPANIZER FEED COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2450 | Mechanical Equipment Data Sheet - LP Depropanizer |  | Class 2 | Purpose** | IFQ | IFQ | IFQ
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16 | 2018-11-06 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00183 | TPSK-LSPA1-T-ME-00283 | TPSK-LSPA1-T-ME-00412
[6 empty] | Return Date | 2018-11-05 | 2018-11-30
[6 empty] | Owner Cmmt* | A3 | R1
| ME | OL1-2M03-2451 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2450 - LP DEPROPANIZER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2452 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2450 - LP DEPROPANIZER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux-Product Pump |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00294
Return Date
Owner Cmmt*
| ME | OL1-2M03-2455 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2455 - LP DEPROPANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2456 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2455 - LP DEPROP REBOILER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2457 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2455 - LP DEPROPANIZER COND PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2460 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2460 - C2 HYDROG ARSINE GUARD BED |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2461 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2460 - C2 HYDROG FEED COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2465 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2465 - C2 HYDROG FEED HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2466 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2465 - C2 HYDROG FEED HEATER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2467 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2465 - C2 HYDROG FEED HEATER COND PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2470 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2470 - C2 HYDROG REACTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2471 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2470 - C2 HYDROG 1ST STAGE INTERCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2472 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2472 - C2 HYDROG 2ND STAGE INTERCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2474 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2474 - C2 HYDROG AFTERCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2480 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2480 - CG SECONDARY DRYER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2502 | Mechanical Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00461
Return Date
Owner Cmmt*
| ME | OL1-2M03-2503 | Mechanical Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00389
Return Date
Owner Cmmt*
| ME | OL1-2M03-2504 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 1 |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2506 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2506 - DEMETH PREFRAC FEED SEPARATOR NO. 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2508 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2508 - DEMETH PREFRAC FEED SEPARATOR NO. 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator & Reflux Drum |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00260 | TPSK-LSPA1-T-ME-00414
[6 empty] | Return Date | 2018-11-29
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M03-2515 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2515 - DEMETH PREFRACTIONATOR REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2520 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2520 - RESIDUE GAS RECTIFIER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2525 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2525 - HYDROGEN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00304 | TPSK-LSPA1-T-ME-00415
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2545 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2545 - DEMETHANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2546 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2546 - DEMETHANIZER BOTTOMS COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2548 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2548 - DEMETHANIZER BOTTOMS VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor |  | Class 2 | Purpose** | IFA | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00050 | TPSK-LSPA1-T-ME-00130
[6 empty] | Return Date | 2018-10-02 | 2018-10-26
[6 empty] | Owner Cmmt* | A3 | A3
| ME | OL1-2M03-2551 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2550 - EXPANDER SUCTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2555 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2555 - EXPANDER DISCHARGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2570 | Mechanical Equipment Data Sheet - Deethanizer |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00394
Return Date
Owner Cmmt*
| ME | OL1-2M03-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00310
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-2572 | Mechanical Equipment Data Sheet - Deethanizer Reflux Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00484
Return Date
Owner Cmmt*
| ME | OL1-2M03-2573 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2570 - DEETHANIZER REFLUX PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2574 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2575 - DEETHANIZER REBOILER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2575 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2575 - DEETHANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2576 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2576 - DEETHANIZER BOTTOMS COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2577 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2575 - DEETHANIZER REBOILER COND PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2580 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2580 - C2 TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2582 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2582 - C2 TOWER REFLUX COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2586 | Mechanical Equipment Datasheet - Ethane Recycle Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00413
Return Date
Owner Cmmt*
| ME | OL1-2M03-2591 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2856 - ETHYLENE PRODUCT SUBCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2600 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2600 - C3 HYDROG GUARD ADSORBER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2610 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2610 - C3 HYDROG ARSINE GUARD BED |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2620 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2620 - C3 HYDROG REACTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2621 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2620 - C3 HYDROG AFTERCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2622 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2620 - C3 HYDROG RECYCLE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2623 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2620 - C3 HYDROG RECYCLE PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2630 | Mechanical Equipment Data Sheet - Secondary Deethanizer |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00458
Return Date
Owner Cmmt*
| ME | OL1-2M03-2631 | Mechanical Equipment Data Sheet - 10-E-2630 - Secondary Deeth Condenser |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00455
Return Date
Owner Cmmt*
| ME | OL1-2M03-2632 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2630 - SECONDARY DEETH REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2633 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00487
Return Date
Owner Cmmt*
| ME | OL1-2M03-2635 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2635 - SECONDARY DEETH REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2636 | Mechanical Equipment Data Sheet - 10-E-2636 - Secondary Deeth Bottoms Cooler |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00465
Return Date
Owner Cmmt*
| ME | OL1-2M03-2640 | Mechanical Equipment Data Sheet - C3 Tower |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00415
Return Date
Owner Cmmt*
| ME | OL1-2M03-2644 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2645 - C3 TOWER REBOILER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00361
Return Date
Owner Cmmt*
| ME | OL1-2M03-2646 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2646 - PROPANE RECYCLE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2647 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2647 - HP PROPYLENE / OFF SPEC PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2660 | Mechanical Equipment Datasheet - Debutanizer |  | Class 2 | Purpose** | IFQ | IFQ | IFQ
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23 | 2018-11-08 | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00215 | TPSK-LSPA1-T-ME-00288 | TPSK-LSPA1-T-ME-00415
Return Date
Owner Cmmt*
| ME | OL1-2M03-2661 | Mechanical Equipment Data Sheet - 10-E-2660 - Debutanizer Condenser |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00465
Return Date
Owner Cmmt*
| ME | OL1-2M03-2662 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2660 - DEBUTANIZER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2663 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2660 - DEBUTANIZER REFLUX / PRODUCT PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2665 | Mechanical Equipment Data Sheet - 10-E-2665 AB - Debutanizer Reboilers |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00468
Return Date
Owner Cmmt*
| ME | OL1-2M03-2666 | Mechanical Equipment Data Sheet - 10-E-2666 - Debutanizer Bottoms Cooler |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00468
Return Date
Owner Cmmt*
| ME | OL1-2M03-2667 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2666 - C5 / PYGAS SURGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2668 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2666 - C5 / PYGAS PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00421
Return Date
Owner Cmmt*
| ME | OL1-2M03-2700 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2700 - GHU-1 REACTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2701 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2701 - GHU-1 FEED / EFFLUENT EXCHANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2702 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2702 - GHU-1 S/U HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2703 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2705 - GHU-1 RECYCLE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2704 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2705 - GHU-1 RECYCLE PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2705 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2705 - GHU-1 HOT SEPARATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2706 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2706 - GHU-1 COLD SEPARATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2707 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2706 - GHU-1 COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2710 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2710 - DEPENTANIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2711 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2710 -DEPENTANIZER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2712 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2710 - DEPENTANIZER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2713 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2710 - DEPENTANIZER REFLUX PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2714 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2714 - C5 CUT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2715 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2715 - DEPENTANIZER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2716 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2714 - C5 CUT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2718 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2720 - RERUN TOWER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2719 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2720 - RERUN TOWER REFLUX / PRODUCT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2720 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-2720 - RERUN TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2721 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2720 - RERUN TOWER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2722 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2722 - GHU-1 PRODUCT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2723 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2724 - WASH OIL CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2724 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2724 - WASH OIL DEGASSING DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2725 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2725 - RERUN TOWER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2726 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2726 - PYGAS FUEL OIL PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2727 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2726 - PYGAS FUEL OIL COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2728 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2724 - RECYCLE WASH OIL PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2730 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2730 - HYDROG REGEN HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2735 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2735 - REGEN HYDROG DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2750 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2750 - C4 / C5 HYDROG SURGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2751 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2750 - C4 / C5 HYDROG FEED PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2755 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2755 - C4 / C5 HYDROG S/U HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2760 | MECHANICAL EQUIPMENT DATA SHEET - 10-R-2760 - C4 / C5 HYDROG REACTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2761 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2761 - C4 / C5 HYDROG VENT CHILLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2762 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2760 - C4 / C5 HYDROG RECYCLE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2763 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2760 - C4 / C5 HYDROG VENT CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2764 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2760 - C4 / C5 HYDROG RECYCLE PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2765 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2765 - C4 / C5 HYDROG RECYCLE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2790 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2790 - LIGHT OIL DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2791 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2790 - LIGHT OIL DRAIN DRUM PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor |  | Class 2 | Purpose** | IFA | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00038 | TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date | 2018-09-28
[6 empty] | Owner Cmmt* | A3
| ME | OL1-2M03-2801 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2805 - PROPYLENE PRODUCT PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2805 | Mechanical Equipment Data Sheet - C3R Surge Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2806 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2805 - C3R CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2807 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2807 - C3 CHILLER NO. 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2809 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2809 - C3 CHILLER NO. 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2810 | Mechanical Equipment Data Sheet - C3R 1st Stage Suction Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2815 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2815 - C3R DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2816 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2815 - PROPYLENE REFRIG RECOVERY PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2820 | Mechanical Equipment Data Sheet - C3R 2nd Stage Suction Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2830 | Mechanical Equipment Data Sheet - C3R 3rd Stage Suction Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-2840 | Mechanical Equipment Data Sheet - C3R 4TH Stage Suction Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00460
Return Date
Owner Cmmt*
| ME | OL1-2M03-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor |  | Class 2 | Purpose** | IFA | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10 | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00038 | TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date | 2018-09-28 | 2018-10-26
[6 empty] | Owner Cmmt* | A3 | A3
| ME | OL1-2M03-2852 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2853 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2854 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2855 - C2R SURGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2855 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2855 - ETHYLENE PRODUCT PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00316
Return Date
Owner Cmmt*
| ME | OL1-2M03-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00312
Return Date
Owner Cmmt*
| ME | OL1-2M03-2858 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-2858 - HP ETHYLENE PRODUCT SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2860 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2860 - C2R 1ST STAGE SUCTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2865 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2865 - C2R DRAIN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2870 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-2870 - C2R 2ND STAGE SUCTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2880 | Mechanical Equipment Data Sheet - C2R 3RD Stage Suction Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00460
Return Date
Owner Cmmt*
| ME | OL1-2M03-2910 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-2910 - WASH OIL DAY TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-2911 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-2910 - WASH OIL INJECTION PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3000 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3000 - PREDISTILLATION TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3001 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3000 - PREDISTILLATION CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3002 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3002 - PREDISTILLATION FEED PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3003 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3000 - PREDISTILLATION REFLUX PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3004 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3004 - PREDISTILLATION TRIM REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3005 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3005 - PREDISTILLATION REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3006 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3000 - PREDISTILLATION REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3007 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3002 - PREDISTILLATION FEED DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3008 | MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3009 | MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3010 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3010 - C4 FEED DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3014 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3014 - C4 TRIM VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3015 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3015 - C4 VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3016 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3016 - HEAVY END DISCHARGE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3018 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3018 - SOLVENT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3020 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3020 - MAIN WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3021 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3020 - MAIN WASHER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3022 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3020 - MAIN WASHER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3023 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3020 - MAIN WASHER REFLUX PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3026 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3026 - MAIN WASHER BOTTOM PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3030 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3030 - AFTER WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3031 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3030 - AFTER WASHER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3032 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3030 - AFTER WASHER REFLUX PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3033 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3030 - AFTER WASHER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3036 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3036 - AFTER WASHER BOTTOM PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3040 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3040 - RECTIFIER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3044 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3044 - SOLVENT HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3045 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3045 - SOLVENT HEAT EXCHANGER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3046 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3046 - DEGASSER FEED PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3047 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3045 - RECTIFIER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3050 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3050 - DEGASSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3055 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3055 - DEGASSER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3056 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3056 - DEGASSER BOTTOM PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3060 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3060 - ACETYLENE WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3061 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3060 - ACETYLENE WASHER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3062 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3062 - ACETYLENE CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3063 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3060 - WASTE WATER PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3064 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3062 - C4 ACETYLENE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3065 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3061 - WASTE HC PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3066 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3062 - ACETYLENE ACCUMULATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3067 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3060 - C4 FEED DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3070 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3070 - DIRECT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3071 | MECHANICAL EQUIPMENT DATA SHEET - 10-C-3070 - RECYCLE GAS COMPRESSOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3073 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3070 - WATER / NMP COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3076 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3076 - DIRECT COOLER PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3080 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3080 - BUTADIENE TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3081 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3080 - BUTADIENE TOWER REFLUX DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3082 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3080 - BUTADIENE TOWER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3083 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3080 - BUTADIENE TOWER REFLUX PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3084 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3084 - BUTADIENE TOWER TRIM REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3085 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3085 - BUTADIENE TOWER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3086 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3086 - C4 / C5 HC PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3090 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3090 - BUTADIENE DRYING TOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3095 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3095 - BUTADIENE DRYING TOWER REBOILER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3096 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3096 - BUTADIENE PRODUCT COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3097 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3096 - BUTADIENE PRODUCT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3098 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3098 - BUTADIENE PRODUCT SUBCOOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3100 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3100 - SOLVENT REGEN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3110 | MECHANICAL EQUIPMENT DATA SHEET - 10-T-3110 - WATER WASHER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3111 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3110 - WATER WASHER ACCUMULATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3112 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3110 - WATER WASHER CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3113 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3110 - SOLVENT RETURN PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3120 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3120 - REGEN STEAM EJECTOR COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3126 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3126 - EJECTOR SEAL DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3127 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3126 - WASTE WATER RETURN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3150 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3150 - CONDENSATE HEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3151 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3150 - CONDENSATE FLASH DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3160 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-3160 - CONDENSATE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3161 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3160 - CONDENSATE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3162 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3160 - CONDENSATE RECYCLE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3180 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3180 - BLOWDOWN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3190 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3190 - NMP SLOP DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3191 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3190 - SOLVENT SLOP PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3900 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-3900 - NMP STORAGE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3901 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3900 - NMP STORAGE PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3902 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3902 - SOLVENT INHIBITOR DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3903 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3902 - SOLVENT INHIBITOR DOSING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3904 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3904 - PRODUCT INHIBITOR DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3905 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3904 - PRODUCT INHIBITOR DOSING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3906 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3906 - ANTI FOAM AGENT DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3907 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3906 - ANTIFOAM DOSING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3908 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-3908 - PREDISTILLATION INHIBITOR DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-3909 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-3908 - PREDISTILLATION INHIBITOR DOSING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-4001 | MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-4003 | MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5001 | MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5003 | MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5101 | Mechanical Equipment Data Sheet - SHP BFW Pumps |  | Class 2 | Purpose** | IFQ | IFQ | IFQ
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-27 | 2018-11-15 | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00322 | TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2018-11-19 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| ME | OL1-2M03-5102 | Mechanical Equipment Data Sheet - VLP BFW Pumps |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-27 | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00236 | TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2018-11-19
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-5103 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5100 - DEARATOR VENT CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5107 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5112 - SUSPECT CONDENSATE FLASH DRUM VENT CONDENSER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5108 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5110 - SUSPECT CONDENSATE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5109 | Mechanical Equipment Data Sheet - Condensate Pumps |  | Class 2 | Purpose** | IFQ | IFQ | IFQ
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26 | 2018-11-14 | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00235 | TPSK-LSPA1-T-ME-00317 | TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2018-11-19
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-5110 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5110 - CONDENSATE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5111 | Mechanical Equipment Datasheet - Suspect Condensate Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00341
Return Date
Owner Cmmt*
| ME | OL1-2M03-5112 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5112 - SUSPECT CONDENSATE FLASH DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5113 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5113 - FOUL CONDENSATE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5114 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5114 - LP CONDENSATE FLASH DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5120 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5120 - RAW CONDENSATE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5121 | Mechanical Equipment Datasheet - Raw Condensate Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00341
Return Date
Owner Cmmt*
| ME | OL1-2M03-5140 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5140 - INTERMITTENT BLOWDOWN DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5141 | Mechanical Equipment Datasheet - Intermittent Blowdown Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00335
Return Date
Owner Cmmt*
| ME | OL1-2M03-5150 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5150 - CONTINUOUS BLOWDOWN FLASH DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5200 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5200 - FUEL GAS DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5201 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5200 - MP ETHYLENE SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5210 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5210 - PILOT GAS VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5220 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5220 - PILOT GAS SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5350 | Mechanical Equipment Datasheet for Cooling Tower |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
Owner Cmmt*
| ME | OL1-2M03-5352 | Mechanical Equipment DataSheet - Olefins Cooling Water Pumps |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00210 | TPSK-LSPA1-T-ME-00388
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-5355 | Mechanical Equipment Datasheet for Side Stream Filter Package |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248
[6 empty] | Return Date | 2018-11-27
Owner Cmmt*
| ME | OL1-2M03-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps |  | Class 2 | Purpose** | IFQ | IFQ | IFQ
[6 empty] | Rev. | A | B | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23 | 2018-11-14 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00210 | TPSK-LSPA1-T-ME-00317 | TPSK-LSPA1-T-ME-00388
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2M03-5371 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5370 - CW FILTER BACKWASH PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5400 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5400 - INSTRUMENT AIR RECEIVER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5500 | Mechanical Equipment Data Sheet - Hot Flare Drum |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00483
Return Date
Owner Cmmt*
| ME | OL1-2M03-5501 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5500 - HOT BLOWDOWN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5510 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5510 - COLD FLARE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5511 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5510 - COLD FLARE BLOWDOWN VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5512 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5512 - COLD FLARE SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5513 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5513 - METHANOL VAPORIZER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5514 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5513 - METHANOL VAPROIZER COND POT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5515 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5515 - METHANOL MAKE-UP DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5520 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5520 - VENT COLLECTION DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5550 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5550 - HP FLARE KNOCK OUT DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5551 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5550 - HP FLARE KNOCK OUT DRUM PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5552 | MECHANICAL EQUIPMENT DATA SHEET - 10-D-5552 - LPG STORAGE DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5553 | MECHANICAL EQUIPMENT DATA SHEET - 10-E-5552 - LPG VAPORIZER / SUPERHEATER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5554 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5552 - LPG UNLOADING PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5565 | MECHANICAL EQUIPMENT DATA SHEET- 10-D-5565 - LLDPE LP FLARE KNOCK OUT DRUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5606 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5600 - PYGAS AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5607 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5601 - BUTADIENE AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5608 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5602 - QW AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5609 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5603 - CGC AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5611 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5610 - HYDROBLAST PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5612 | MECHANICAL EQUIPMENT DATA SHEET - 10-F-5610 - HYDROBLAST FILTER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5613 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5604 - REFRIG AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5614 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5605 - FURNACE AREA OILY WATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5616 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5615 - OLEFINS STORMWATER SUMP PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5621 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5621 - OLEFINS HOLDING BASIN SKIM OIL PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5622 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5620 - OLEFINS HOLDING BASIN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5635 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5630 - CT AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5636 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5631 - CWWT AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5637 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5632 - HP FLARE AREA OILY WASTEWATER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5638 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5633 - HP FLARE AREA STORMWATER SUMP PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5640 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5640 - OILY WASTEWATER EQUALIZATION TANKS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5641 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5641 - WASTEWATER EQ TANK SKIMMED OIL PUMP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5643 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5642 - COOLING WATER BD BASIN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5645 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5640 - OILY WASTEWATER EQ TANK PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5654 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5655 - EQUALIZATION PIT PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5657 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5656 - FINAL CHECK BASIN PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5674 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5675 - SLOP OIL TRANSFER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5675 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5675 - SLOP OIL TANKS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5676 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5676 - OILY SLUDGE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5677 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5676 - OILY SLUDGE TRANSFER PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5900 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5900 - SULFURIC ACID TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5901 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5900 - SULFURIC ACID PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5950 | MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5950 - SODIUM HYPOCHLORITE TANK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-5951 | MECHANICAL EQUIPMENT DATA SHEET - 10-P-5950 - SODIUM HYPOCHLORITE METERING PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-6001 | MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M03-6003 | MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: M06 Mechanical equipment drawing
| ME | OL1-2M06-1001 | USC 36M Recycle Furnace General Arrangement Cross Section Elevation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00327
Return Date
Owner Cmmt*
| ME | OL1-2M06-1002 | USC 36M Recycle Furnace General Arrangement Longitudinal Elevation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00327
Return Date
Owner Cmmt*
| ME | OL1-2M06-1003 | USC "36M" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1004 | USC "36M" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1101 | USC "36M" FURNACE REFRACTORY & INSULATION RADIANT SECTION DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1102 | USC "36M" FURNACE REFRACTORY & INSULATION CONVECTION SECTION DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1103 | USC "36M" FURNACE INSULATION INSTALLATION DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1104 | USC "36M" FURNACE REFRACTORY AND INSULATION ANCHOR DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1105 | USC "36M" FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1106 | USC "36M" FURNACE PEEP DOOR INSERT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1107 | USC "36M" FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1108 | USC "36M" FURNACE DECOKE NOZZLE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1109 | USC "36M" FURNACE SEAL BOOT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1110 | USC "36M" FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062 | TPSK-LSPA1-T-ME-00486
Return Date
Owner Cmmt*
| ME | OL1-2M06-1202 | USC 36M Recycle Furnace Transfer Line And Clean Out Details |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062 | TPSK-LSPA1-T-ME-00486
Return Date
Owner Cmmt*
| ME | OL1-2M06-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062 | TPSK-LSPA1-T-ME-00486
Return Date
Owner Cmmt*
| ME | OL1-2M06-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill Of Material |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00182
Return Date
Owner Cmmt*
| ME | OL1-2M06-1205 | USC "36M" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1206 | USC "36M" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1301 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00286
Return Date
Owner Cmmt*
| ME | OL1-2M06-1302 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00286
Return Date
Owner Cmmt*
| ME | OL1-2M06-1303 | USC "36M" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2001 | USC 132U Cracking Furnace General Arrangement Cross Section Elevation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00328
Return Date
Owner Cmmt*
| ME | OL1-2M06-2002 | USC 132U Cracking Furnace General Arrangement Longitudinal Elevation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00328
Return Date
Owner Cmmt*
| ME | OL1-2M06-2003 | USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2004 | USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2107 | USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2201 | USC 132U Cracking Furnace Radiant Coil Assembly and Details |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062 | TPSK-LSPA1-T-ME-00486
Return Date
Owner Cmmt*
| ME | OL1-2M06-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062 | TPSK-LSPA1-T-ME-00486
Return Date
Owner Cmmt*
| ME | OL1-2M06-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00062 | TPSK-LSPA1-T-ME-00486
Return Date
Owner Cmmt*
| ME | OL1-2M06-2204 | USC 132U Cracking Furnace Fabricatin Assembly of Convection Coils Finned Tubes and Bill of Material |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00182
Return Date
Owner Cmmt*
| ME | OL1-2M06-2205 | USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2206 | USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2207 | DILUTION STEAM MIXING TEE DRAWING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2301 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00289
Return Date
Owner Cmmt*
| ME | OL1-2M06-2302 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00289
Return Date
Owner Cmmt*
| ME | OL1-2M06-2303 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2554 | USC 132U Cracking Furnace Peep Door Details |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00422
Return Date
Owner Cmmt*
| ME | OL1-2M06-2555 | FURNACE PEEP DOOR DETAILS (LEFT HAND) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3001 | USC "132SU" FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3002 | USC "132SU" FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3003 | USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3004 | USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3107 | USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3201 | USC "132U" FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3202 | USC "132U" FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3203 | USC "132U" FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3204 | USC "132U" FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3205 | USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3206 | USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3301 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3302 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-3303 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4001 | USC "132SU" FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4002 | USC "132SU" FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4003 | USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4004 | USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4107 | USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4201 | USC "132U" FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4202 | USC "132U" FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4203 | USC "132U" FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4204 | USC "132U" FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4205 | USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4206 | USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4301 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4302 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-4303 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5001 | USC "132SU" FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5002 | USC "132SU" FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5003 | USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5004 | USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5107 | USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5201 | USC "132U" FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5202 | USC "132U" FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5203 | USC "132U" FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5204 | USC "132U" FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5205 | USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5206 | USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5301 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5302 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-5303 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6001 | USC "132SU" FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6002 | USC "132SU" FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6003 | USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6004 | USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6107 | USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6201 | USC "132U" FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6202 | USC "132U" FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6203 | USC "132U" FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6204 | USC "132U" FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6205 | USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6206 | USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6301 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6302 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-6303 | USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: M55
| ME | OL1-2M55-0002 | MR API CENTRIFUGAL PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0003 | Material Requisition for Cooling Water Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00319
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M55-0004 | MR HIGH SPEED PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0005 | MR SUBMERSIBLE PUMPS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0007 | MR MECH.SEALS & FLUSHING CONSOLES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0008 | Material Requisition For Centrifugal Compressors Steam Turbine Driven |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00136
[6 empty] | Return Date | 2018-10-26
Owner Cmmt*
| ME | OL1-2M55-0010 | MR RECYCLE GAS SCREW COMPRESSOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0011 | MR VENT GAS BLOWER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0012 | Material Requisition For Residue Gas Expander/Recompressor |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00139
[6 empty] | Return Date | 2018-10-26
Owner Cmmt*
| ME | OL1-2M55-0013 | MR AGITATORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0014 | Material Requisition For Integrally Geared Decoking Air Compressors |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | 2018-11-07
Owner Cmmt*
| ME | OL1-2M55-0015 | Material Requisition For API Centrifugal Pumps - LLI |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00257
[6 empty] | Return Date | 2018-11-27
Owner Cmmt*
| ME | OL1-2M55-0050 | MR FOR SHOP ASSEMBLED REACTORS AND THICKER VESSELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0051 | MR FOR REACTORS TRAYS (BY AXENS) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0052 | MR FOR SHOP ASS. LARGE COLUMNS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0053 | MR FOR SHOP ASS. COLUMNS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0054 | MR FOR SHOP ASS. COLUMNS (BUTADIENE UNIT BY LURGI) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0055 | Material Requisition For Trays For Columns Requisition For Inquiry |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00300
[6 empty] | Return Date | 2018-12-06
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M55-0056 | MR FOR COLUMNS TRAYS (RIPPLE TYPE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0057 | MR FOR COLUMNS TRAYS & INTERN. (BUTADIENE BY LURGI) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0058 | Material Requisition For Wieland Tubes (Solo Source) Requisition For Inquiry |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00377
Return Date
Owner Cmmt*
| ME | OL1-2M55-0059 | MR FOR S&T HEAT EXCHANGERS (LARGE) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0060 | MR FOR C.S. S&T HEAT EXCHANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0061 | MR FOR C.S. CLAD, S.S. AND LOW ALLOY S&T HEAT EXCHANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0062 | MR FOR C.S. S&T HEAT EXCHANGERS (BUTADIENE BY LURGI) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0063 | MR FOR HAIRPIN H.E. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0064 | Material Requisition For Plate And Frame Heat Exchangers Requisition For Inquiry |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00124
[6 empty] | Return Date | 2018-10-24
Owner Cmmt*
| ME | OL1-2M55-0065 | MR FOR HEAT RECOVERY SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0066 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03 | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00125 | TPSK-LSPA1-T-ME-00153
[6 empty] | Return Date | 2018-10-24 | 2018-11-02
Owner Cmmt*
| ME | OL1-2M55-0068 | MR FOR SHOP ASSEMBLED C.S. LARGE DRUMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0069 | MR FOR SHOP ASSEMBLED C.S. VESSELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0070 | MR FOR SHOP ASSEMBLED C.S. CLAD, LOW ALLOY & S.S. VESSELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0071 | MR FOR SHOP ASSEMBLED C.S. DRUMS (BUTADIENE BY LURGI) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0072 | MR FOR SHOP ASSEMBLED VESSELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0073 | MR FOR FIXED OR FLOATING ROOF TANKS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0074 | MR FOR S&T HEAT EXCHANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0075 | Material Requisition for High Efficiency Internals for Columns |  | Class 2 | Purpose** | IFQ | IMP
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2018-11-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00278 | TPSK-LSPA1-T-ME-00314
[6 empty] | Return Date | 2018-11-29
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M55-0100 | MR DEMINERALIZATION AND POLISHING PACKAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0101 | MR CONDENSATE CARBON FILTER PACKAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0102 | MR COMPLEX WASTE WATER TREATMENT PACKAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0103 | Material Requisition for Wet Air Oxidation Package |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00367
Return Date
Owner Cmmt*
| ME | OL1-2M55-0104 | Material Requisition for Cooling Tower |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
Owner Cmmt*
| ME | OL1-2M55-0105 | MR SILENCERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0106 | MR FILTERS AND COALESCERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0107 | MR QUENCH OIL FILTERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0108 | Material Requisition for Deareator |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00270
[6 empty] | Return Date | 2018-11-29
Owner Cmmt*
| ME | OL1-2M55-0109 | Material Requisition for Side Stream Filter Package |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248
[6 empty] | Return Date | 2018-11-27
Owner Cmmt*
| ME | OL1-2M55-0110 | MR EJECTORS & STATIC MIXERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0112 | MR CHEMICAL DOSING SYSTEMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0113 | MR CRANES (BRIDGE, GANTRY ETC.) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0114 | Material Requisition for Hydrogen Production Unit |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00271
Return Date
Owner Cmmt*
| ME | OL1-2M55-0115 | MR SANITARY WATER PACKAGE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-0116 | MR HP FLARE SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2001 | Material Requisition for Convection Tubes |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00450
Return Date
Owner Cmmt*
| ME | OL1-2M55-2002 | Material Requisition for Furnace Convection Fittings |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00207
Return Date
Owner Cmmt*
| ME | OL1-2M55-2003 | Material Requisition for Quench Exchangers |  | Class 2 | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00233 | TPSK-LSPA1-T-ME-00466
Return Date
Owner Cmmt*
| ME | OL1-2M55-2004 | Material Requisition for Radiant Coil Assemblies |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00063
Return Date
Owner Cmmt*
| ME | OL1-2M55-2005 | Material Requisition for Furnace ID Fans |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00269
Return Date
Owner Cmmt*
| ME | OL1-2M55-2006 | Material Requisition for Furnace Burners |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00313
Return Date
Owner Cmmt*
| ME | OL1-2M55-2007 | Material Requisition for Cast Intermediate Tube Supports |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00329
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M55-2008 | MATERIAL REQUISITION FOR PEEP DOOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2009 | MATERIAL REQUISITION FOR ELEVATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2010 | MATERIAL REQUISITION FOR MOV |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2011 | MATERIAL REQUISITION FOR ATTEMPERATOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2012 | MATERIAL REQUISITION FOR CONVECTION FINNING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2013 | MATERIAL REQUISITION FOR RADIANT REFRACTORY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2014 | MATERIAL REQUISITION FOR RADIANT STEEL PANEL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2015 | MATERIAL REQUISITION FOR CONVECTION FABRICATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2016 | MATERIAL REQUISITION FOR UTILITY STEEL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2017 | MATERIAL REQUISITION FOR PIPING SPRING SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M55-2018 | Material Requisition for Furnace Steam Drums |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00263
Return Date
Owner Cmmt*
| ME | OL1-4M55-2001 | Material Requisition for Convection Tubes |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00044
Return Date
Owner Cmmt*
Category Code: M57
| ME | OL1-2M57-0003 | Particular Technical Specification for Cooling Water Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00319
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M57-0008 | Particular Technical Specification For Centrifugal Compressors Steam Turbine Driven |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00136
[6 empty] | Return Date | 2018-10-26
Owner Cmmt*
| ME | OL1-2M57-0012 | Particular Technical Specification For Residue Gas Expander/Recompressor |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00139
[6 empty] | Return Date | 2018-10-26
Owner Cmmt*
| ME | OL1-2M57-0014 | Particular Technical Specification for Integrally Geared Decoking Air Compressors |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | 2018-11-07
Owner Cmmt*
| ME | OL1-2M57-0015 | Particular Technical Specification For API Centrifugal Pumps - LLI |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00257
[6 empty] | Return Date | 2018-11-27
Owner Cmmt*
| ME | OL1-2M57-0055 | Particular Technical Specification For Trays For Columns |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00300
[6 empty] | Return Date | 2018-12-06
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M57-0058 | Particular Technical Specification For Wieland Tubes (Solo Source) |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00377
Return Date
Owner Cmmt*
| ME | OL1-2M57-0064 | Particular Technical Specification For Plate And Frame Heat Exchangers |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00124
[6 empty] | Return Date | 2018-10-24
Owner Cmmt*
| ME | OL1-2M57-0066 | Particular Technical Specification For Cold Box And Core Exchangers |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00125
[6 empty] | Return Date | 2018-10-24
Owner Cmmt*
| ME | OL1-2M57-0075 | Particular Technical Specification for High Efficiency Internals for Columns |  | Class 2 | Purpose** | IFQ | IMP
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07 | 2018-11-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00278 | TPSK-LSPA1-T-ME-00314
[6 empty] | Return Date | 2018-11-29
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M57-0103 | Particular Technical Specification for Wet Air Oxidation Package |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00390
Return Date
Owner Cmmt*
| ME | OL1-2M57-0104 | Particular Technical Specification for Cooling Tower |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
Owner Cmmt*
| ME | OL1-2M57-0108 | Particular Technical Specification For Deaerator |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00270
[6 empty] | Return Date | 2018-11-29
Owner Cmmt*
| ME | OL1-2M57-0109 | Particular Technical Specification for Side Steam Filter Package |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248
[6 empty] | Return Date | 2018-11-27
Owner Cmmt*
| ME | OL1-2M57-0114 | Particular Technical Specification For Hydrogen Production Unit |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00271
Return Date
Owner Cmmt*
| ME | OL1-2M57-2001 | Particular Technical Specification for Convection Tubes |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00450
Return Date
Owner Cmmt*
| ME | OL1-2M57-2002 | Particular Technical Specification for Furnace Convection Fittings |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00207
Return Date
Owner Cmmt*
| ME | OL1-2M57-2003 | Particular Techanical Specification for Quench Exchangers |  | Class 2 | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00233 | TPSK-LSPA1-T-ME-00466
Return Date
Owner Cmmt*
| ME | OL1-2M57-2004 | Particular Technical Specification For Radiant Coil Assemblies |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00063
Return Date
Owner Cmmt*
| ME | OL1-2M57-2005 | Particular Technical Specification for Furnace ID Fans |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00269
Return Date
Owner Cmmt*
| ME | OL1-2M57-2006 | Particular Technical Specification for Furnace Burners |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00313
Return Date
Owner Cmmt*
| ME | OL1-2M57-2007 | Particular Technical Specification for Cast Intermediate Tube Supports |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00329
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2M57-2018 | Particular Technical Specification for Furnace Steam Drums |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00263
Return Date
Owner Cmmt*
Category Code: M91 Index/List
| ME | OL1-2M91-1001 | Approved Vendor List for 36M and 132U Furnace |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00211
Return Date
Owner Cmmt*
Category Code: M92 Procedures & Standards
| ME | OL1-2M92-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00470
Return Date
Owner Cmmt*
| ME | OL1-2M92-2002 | Project Specification for Statically Cast Fittings For Radiant Coils and Transfer Lines in Cracking Furnaces |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00471
Return Date
Owner Cmmt*
| ME | OL1-2M92-2003 | Project Specification for Cast Intermediate Tube Supports |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00232
Return Date
Owner Cmmt*
| ME | OL1-2M92-2004 | SPECIFICATION FOR FABRICATION OF CONVECTION COILS FOR CRACKING FURNACES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M92-2005 | SPECIFICATION FOR SUPPLY & INSTALLATION OF CERAMIC FIBER BLANKET & CF MODULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M92-2006 | SPECIFICATION FOR SUPPLY & INSTALLATION OF REFRACTORY INSULATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M92-2007 | Project Specification For SLE and USX Exchangers |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00427
Return Date
Owner Cmmt*
| ME | OL1-2M92-2008 | Project Specification For Transfer Line Exchangers |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00428
Return Date
Owner Cmmt*
| ME | OL1-2M92-2009 | Project Specification for Furnace Burners |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00231
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| ME | OL1-4M92-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00037
[6 empty] | Return Date | 2018-09-25
[6 empty] | Owner Cmmt* | R2
| ME | OL1-4M92-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00037
[6 empty] | Return Date | 2018-09-25
[6 empty] | Owner Cmmt* | R2
| ME | OL1-4M92-2007 | Project Specification For SLE and USX Exchangers |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00067
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R2
| ME | OL1-4M92-2008 | Project Specification For Transfer Line Exchangers |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00067
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R2
Category Code: O01 Precommissioning Plan and Schedule
| PE | OL1-2O01-0001 | PCC&SU SCHEDULE (LEVEL 1) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O01-0002 | PCC&SU SCHEDULE (LEVEL 2) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O01-0003 | PCC&SU SCHEDULE (LEVEL 3) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O01-0004 | PCC&SU MANPOWER SCHEDULE (INCLUDING RECRUITING) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O01-0005 | VENDORS AND LICENSORS FOR PCC&SU SUPPORT - SCHEDULE FOR EPCC PHASE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O01-0006 | CUO 107 - TRAINING SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O01-0007 | RAW MATERIAL, CHEMICALS AND UTILITIES SUPPLY PLAN & SCHEDULE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O04 Performance Test Plan and Schedule
| PE | OL1-2O04-1004 | PERFORMANCE TEST PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O06
| PE | OL1-2O06-0001 | CUO 107 - OPERATING MANUALS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O07
| PE | OL1-2O07-0001 | CUO 110 - PLANT MAINTENANCE MANUAL - COOLING WATER UNIT - S02 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0002 | CUO 110 - PLANT MAINTENANCE MANUAL - OFFSITES - S04 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0003 | CUO 110 - PLANT MAINTENANCE MANUAL - WASTE WATER TREATMENT - S05 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0004 | CUO 110 - PLANT MAINTENANCE MANUAL - FURNACES - S06 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0005 | CUO 110 - PLANT MAINTENANCE MANUAL - FRACTIONATION #1 & #2 - S07 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0006 | CUO 110 - PLANT MAINTENANCE MANUAL - FRACTIONATION #3 & BUTADIENE EXTRACTION & AMINE TREATEMENT - S08 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O08
| PE | OL1-2O08-0001 | START-UP DELIVERABLE LIST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O08-0002 | START-UP PACKAGE LIST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O08-0003 | PROJECT SYSTEM LIST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O08-0004 | SPECIAL ACTIVITIES DOSSIER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O08-0005 | SYSTEM COMPONENT LIST WITH MARKED-UP DWGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O08-0007 | CUO 110 - OPERATING SPARE PARTS STATUS REPORT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O09
| PE | OL1-2O09-0001 | RESPONSABILITY MATRIX - DEFINITION OF MECHANICAL COMPLET./PRE-COMMISSIONING TPIT-SUBCONTRACTOR |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O09-0002 | DEFINITION OF SCOPE OF WORK - TPIT - SPECIALIZED COMPANY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O10
| PE | OL1-2O10-0001 | SYSTEMIZATION PHILOSOPHY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O10-0002 | CUO 110 - MAINTENANCE PHILOSOPHY DURING INTERIM MAINTENANCE MANAGEMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O20 Precommissioning Form and Checksheet
| PE | OL1-2O20-0001 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - PIPING - ( 51 ÷ 99 ) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0002 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - INSTRUMENTATION - ( 51 ÷ 99 ) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0003 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - ELECTRICAL - ( 51 ÷ 99 ) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0004 | PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - MECHANICAL - ( 51 ÷ 99 ) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O67 List of set point and controller parameter
| PE | OL1-2O67-1001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-2001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-3001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-4001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-5001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O67-6001 | ALARM & SETPOINT SUMMARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O71 Commissioning Procedure
| PE | OL1-2O71-0001 | JOB START UP SPECIFICATION FOR WATER FLUSHING OF PIPING & EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0002 | JOB START UP SPECIFICATION FOR AIR BLOWING OF PIPING & EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0003 | JOB START UP SPECIFICATION FOR DRYING OF PIPING & EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0004 | JOB START UP SPECIFICATION FOR GROSS LEAK TEST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0005 | JOB START UP SPECIFICATION FOR TIGHTNESS TEST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0006 | JOB START UP SPECIFICATION FOR STEAM BLOWING OF PIPING & EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0007 | JOB START UP SPECIFICATION FOR CHEMICAL CLEANING OF CS OF PIPING & EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0008 | JOB START UP SPECIFICATION FOR CHEMICAL CLEANING OF SS OF PIPING & EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0009 | JOB START UP SPECIFICATION FOR NITROGEN PURGING OF PIPING & EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0010 | JOB START UP SPECIFICATION FOR HYDRO-JETTING OF PIPING & EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0011 | JOB START UP SPECIFICATION FOR OIL FLUSHING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0012 | JOB START UP SPECIFICATION FOR MANUAL CLEANING FOR LARGE BORE PIPING PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0013 | JOB START UP SPECIFICATION FOR PIPING INSPECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0014 | JOB START UP SPECIFICATION FOR RELIEF VALVE MANAGEMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0015 | JOB START UP SPECIFICATION FOR SPRING HANGER SETTING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0016 | JOB START UP SPECIFICATION FOR TIGHTNESS TEST WITH NITROGEN & HELIUM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0017 | JOB START UP SPECIFICATION FOR LOOP CHECK MANAGEMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0018 | JOB START UP SPECIFICATION FOR LOOP FOLDER MANAGEMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0019 | JOB START UP SPECIFICATION FOR ELECTRICAL MOTOR SOLO RUN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0020 | JOB START UP SPECIFICATION FOR ELECTRICAL SUBSTATION ENERGIZATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0021 | JOB START UP SPECIFICATION FOR PUMP ALIGNMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0022 | JOB START UP SPECIFICATION FOR VESSELS/EQUIPMENT INSPECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0023 | CUO 110 - JOB START UP SPECIF.FOR MTL PRESERVATION DURING CONSTRUCTION, PRECOMM., COMMISS. AND STARTUP |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0024 | SITE PCC&SU ORGANIZATION CHART |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0025 | OVERALL PCC&SU EXECUTION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0026 | RESPONSIBILITY MATRIX - DEFINIT.OF MECH.COMPLET./PRE-COMM./COMM./START UP/OPERAT.TPIT-OWNER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0027 | HANDOVER PROCEDURE (INLUDING PUNCH LIST MANAGEMENT & INDEX DOSSIER) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0029 | JOB START SPECIFICATION FOR FUNCTIONAL TEST MANAGEMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0030 | GOVERNANCE FOR INTEGRATED TEAM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0032 | PLANT OPERATION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0033 | CUO 107 - GUIDELINES FOR SUPERVISORY AND COMPREHENSIVE OPERATING MANUALS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0034 | GUIDELINES FOR OTP PREPARATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0036 | CUO 107 - TRAINING PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0037 | CUO 107 - PLAN OF INSTRUCTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0039 | CUO 107 - TRAINING MANUAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-1001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-2001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-3001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-4001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-5001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-6001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O75 Operation Work instruction
| PE | OL1-2O75-0001 | OPERATIONAL TEST PROCEDURE (OTP) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-1001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-2001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-3001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-4001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-5001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-6001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O80 Lab, Product QA and QC
| PE | OL1-2O80-1003 | SAMPLING AND ANALYTICAL MANUAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O92 Procedures & Standards
| PE | OL1-2O92-0001 | INSTRUCTIONS TO SUPPLIER FOR FILLING-UP OF SPARE PARTS AND INTERCHANGEABILITY RECORD (SPIR FORM) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P03 Piping datasheet
| MP | OL1-2P03-1101 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1201 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1202 | SP/RO DATASHEETS - MIXING T |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1203 | SP/RO DATASHEETS - ANGLE VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1204 | SP/RO DATASHEETS - SAMPLE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1205 | SP/RO DATASHEETS - ISOKINETIC NOZZLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1206 | SP/RO DATASHEETS - SILENCER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1301 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1401 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1501 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-1601 | PIPING SPECIALTY ITEM - DATA SHEETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXA | AREA 30 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXB | AREA 53 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXC | AREA 55 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXD | AREA 56 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P03-XXXX | SP ITEM DATA SHEETS, OLEFINS UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P05 Piping calculation sheet / report
| MP | OL1-2P05-0002 | CRITICAL LINE LIST - COOLING WATER UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0003 | CRITICAL LINE LIST - MAIN PIPE RACK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0004 | CRITICAL LINE LIST - OFF-SITES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0005 | CRITICAL LINE LIST - WASTE WATER TREATMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0006 | CRITICAL LINE LIST - FURNACES UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0007 | CRITICAL LINE LIST - FRACTIONATION #1 & #2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0008 | CRITICAL LINE LIST - FRACTIONATION #3 & BUTADIENE EXTRACTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1101 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1102 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1103 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1104 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1105 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1106 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1107 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1108 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1109 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1110 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1111 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1112 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1113 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1114 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1115 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1116 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1117 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1118 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1119 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1120 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1121 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1122 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1123 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1124 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1201 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1202 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1203 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1204 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1205 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1206 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1207 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1208 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1209 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1210 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1211 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1212 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1213 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1214 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1215 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1216 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1217 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1218 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1219 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1220 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1221 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1222 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1223 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1224 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1301 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1302 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1303 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1304 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1305 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1306 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1307 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1308 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1309 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1310 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1311 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1312 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1313 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1314 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1315 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1316 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1317 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1318 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1319 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1320 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1321 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1322 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1323 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1324 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1401 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1402 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1403 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1404 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1405 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1406 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1407 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1408 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1409 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1410 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1411 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1412 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1413 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1414 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1415 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1416 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1417 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1418 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1419 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1420 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1421 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1422 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1423 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1424 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1501 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1502 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1503 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1504 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1505 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1506 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1507 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1508 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1509 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1510 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1511 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1512 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1513 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1514 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1515 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1516 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1517 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1518 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1519 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1520 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1521 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1522 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1523 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1524 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1601 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1602 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1603 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1604 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1605 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1606 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1607 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1608 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1609 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1610 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1611 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1612 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1613 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1614 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1615 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1616 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1617 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1618 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1619 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1620 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1621 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1622 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1623 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1624 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2000 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 0C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2500 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 5T |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5T |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-3000 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 0P |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-3001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0P |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4000 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 5R |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5R |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4500 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 5F |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5F |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-5000 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 5W |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-5001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5W |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-6000 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 1B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-6001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 1B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7000 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 2A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7200 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 2B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7201 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7400 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 2D |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7401 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2D |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7600 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 2E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7601 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7800 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 5U |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7801 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5U |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8000 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 2C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8500 | COMPUTER STRESS ANAL.CALC.LIST - ZONE 3A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 3A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P06 Piping drawing
| MP | OL1-2P06-0001 | GENERAL PLOT PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0002 | DETAIL PLOT PLAN METERING STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0003 | DETAIL PLOT-PLAN MAIN PIPE RACK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0004 | DETAIL PLOT-PLAN ELECTRICAL SUB-STATION & FAR E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0005 | DETAIL PLOT PLAN FURNACES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0006 | DETAIL PLOT PLAN FURNACES AND AUXILIARIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0007 | DETAIL PLOT PLAN QUENCH |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0008 | DETAIL PLOT PLAN C3 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0009 | DETAIL PLOT PLAN HOT FRACTIONATION / GHU UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0010 | DETAIL PLOT PLAN PROCESS COLD COMPRESSORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0011 | DETAIL PLOT PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0012 | DETAIL PLOT PLAN BUTADIENE EXTRACTION UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0013 | DETAIL PLOT-PLAN ELECTRICAL SUB-STATION & FAR C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0014 | DETAIL PLOT PLAN FLARE UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0015 | DETAIL PLOT PLAN COOLING WATER UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0016 | DETAIL PLOT PLAN UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0017 | DETAIL PLOT PLAN WASTE WATER TREATMENT UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0020 | GENERAL KEY-PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0021 | DETAIL KEY-PLAN METERING STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0022 | DETAIL KEY-PLAN MAIN PIPE RACK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0023 | DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0024 | DETAIL KEY-PLAN FURNACES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0025 | DETAIL KEY-PLAN FURNACES AUXILIARIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0026 | DETAIL KEY-PLAN QUENCH |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0027 | DETAIL KEY-PLAN C3 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0028 | DETAIL KEY-PLAN HOT FRACTIONATION / GHU DETAIL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0029 | DETAIL KEY-PLAN COLD COMPRESSORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0030 | DETAIL KEY-PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0031 | DETAIL KEY-PLAN BUTADIENE EXTRACTION DETAIL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0032 | DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0033 | DETAIL KEY-PLAN FLARE DETAIL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0034 | DETAIL KEY-PLAN COOLING WATER DETAIL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0035 | DETAIL KEY-PLAN UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0036 | DETAIL KEY-PLAN WASTE WATER TREATMENT DETAIL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0040 | UTILITY STATION PLOT PLAN MAIN PIPE RACK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0041 | UTILITY STATION PLOT PLAN FURNACES AUXILIARIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0042 | UTILITY STATION PLOT PLAN QUENCH |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0043 | UTILITY STATION PLOT PLAN C3 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0044 | UTILITY STATION PLOT PLAN HOT FRACTIONATION / GHU UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0045 | UTILITY STATION PLOT PLAN COLD COMPRESSORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0046 | UTILITY STATION PLOT PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0047 | UTILITY STATION PLOT PLAN BUTADIENE EXTRACTION UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0048 | UTILITY STATION PLOT PLAN FLARE UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0049 | UTILITY STATION PLOT PLAN COOLING WATER UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0050 | UTILITY STATION PLOT PLAN UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0051 | UTILITY STATION PLOT PLAN WASTE WATER TREATMENT UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0060 | STEAM TRACING MANIFOLDS LOCATION PLAN MAIN PIPE RACK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0061 | STEAM TRACING MANIFOLDS LOCATION PLAN QUENCH |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0062 | STEAM TRACING MANIFOLDS LOCATION PLAN C3 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0063 | STEAM TRACING MANIFOLDS LOCATION PLAN HOT FRACTIONATION / GHU UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0064 | STEAM TRACING MANIFOLDS LOCATION PLAN COLD COMPRESSORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0065 | STEAM TRACING MANIFOLDS LOCATION PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0066 | STEAM TRACING MANIFOLDS LOCATION PLAN BUTADIENE EXTRACTION UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0070 | GAD KEY-PLAN MAIN PIPE RACK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0071 | GAD KEY-PLAN METERING STATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0072 | GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0073 | GAD KEY-PLAN FURNACES AUXILIARIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0074 | GAD KEY-PLAN QUENCH |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0075 | GAD KEY-PLAN C3 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0076 | GAD KEY-PLAN HOT FRACTIONATION / GHU UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0077 | GAD KEY-PLAN COLD COMPRESSORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0078 | GAD KEY-PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0079 | GAD KEY-PLAN BUTADIENE EXTRACTION UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0080 | GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0081 | GAD KEY-PLAN FLARE UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0082 | GAD KEY-PLAN FLARE LINES ROUTING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0083 | GAD KEY-PLAN COOLING WATER UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0084 | GAD KEY-PLAN UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0085 | STD.AUX.PIPE SUPPORTS COLLECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0086 | GAD KEY-PLAN WASTE WATER TREATMENT UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5T |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2901 | MISC ENGINEERED SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0P |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3901 | MISC ENGINEERED SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5R |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5F |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4901 | MISC ENGINEERED SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2C |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 3A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5901 | MISC ENGINEERED SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 1B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6901 | MISC ENGINEERED SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7200 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2B |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7400 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2D |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7600 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2E |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7800 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5U |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-8000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5W |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-XXXX | FIRE AND GAS DETECTOR LOCATION PLAN, OLEFINS UNIT - PRELIMINARY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P10 Insulation Material Take-off (MTO)
| MP | OL1-2P10-10XX | FURNACE 10-H-1100 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 LARGE BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-10YY | FURNACE 10-H-1100 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 SMALL BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-20XX | FURNACE 10-H-1200 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 LARGE BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-20YY | FURNACE 10-H-1200 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 SMALL BORE ISOMETRIC DRAWINGS) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-30XX | FURNACE 10-H-1300 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1300 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-40XX | FURNACE 10-H-1400 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1400 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-50XX | FURNACE 10-H-1500 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1500 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-60XX | FURNACE 10-H-1600 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1600 ISOMETRIC DRAWINGS) |  | Class 3 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P20 Aboveground Piping General Arrangement Drawings
| MP | OL1-2P20-0100 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0101 | GAD BATTERY LIMIT OL1-A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0200 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0300 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0400 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-1000 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2100 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2200 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2300 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2301 | GAD BATTERY LIMIT OU1-A |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2400 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2500 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-3000 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5100 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5200 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5300 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5400 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5500 | GAD (N...) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P30 3D Model Review File
| MP | OL1-2P30-0002 | AUX.PIPE SUPP.LIST & BILL OF MTL - COOLING WATER UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0003 | AUX.PIPE SUPP.LIST & BILL OF MTL - MAIN PIPE RACK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0004 | AUX.PIPE SUPP.LIST & BILL OF MTL - OFF-SITES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0005 | AUX.PIPE SUPP.LIST & BILL OF MTL - WASTE WATER TREATMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0006 | AUX.PIPE SUPP.LIST & BILL OF MTL - FURNACES UTILITIES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0007 | AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION #1 & #2 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0008 | AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION #3 & BUTADIENE EXTRACTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P40
| MP | OL1-2P40-0007 | TIE-INS / INTERFACE POINTS LIST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P40-0008 | STEAM TRACING MANIFOLD LIST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P54
| MP | OL1-2P54-2001 | PIPING MTO |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P55
| MP | OL1-2P55-0001 | MR GATE GLOBE & CHECK FORGED VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0002 | MR GATE GLOBE & CHECK CAST VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0003 | MR BUTTERFLY VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0004 | MR PLUG VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0005 | MR BALL VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0006 | MR DUAL PLATE CHECK VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0007 | MR SPRING-ASSISTED CHECK VALVES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0008 | MR CARBON STEEL SEAMLESS PIPE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0009 | MR CARBON STEEL WELDED PIPE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0010 | MR ALLOY STEEL SEAMLESS PIPE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0011 | MR ALLOY STEEL WELDED PIPE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0012 | MR STAINLESS STEEL SEAMLESS PIPE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0013 | MR STAINLESS STEEL WELDED PIPE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0014 | MR FIBERGLASS REINFORCED PLASTIC PIPING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0015 | MR PE & PVC PIPING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0016 | MR BUTTWELDING FITTINGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0017 | MR FORGED FITTINGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0018 | MR FLANGES BLINDS & DRIP RINGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0019 | MR GASKETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0020 | MR BOLTING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0021 | MR STEAM TRAPS AND MANIFOLDS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0022 | MR HOSE CONNECTIONS AND FLEXIBLE HOSES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0023 | MR STRAINERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0024 | MR SIGHT FLOW INDICATORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0025 | MR SAMPLING PANELS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0026 | MR INTERLOCKS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0027 | MR FOR CRYOGENIC SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0028 | MR FOR ITEMIZED SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-0029 | MR FOR EXPANSION JNTS. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-2101 | REQUISITION - ANGLE VALVE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-2102 | REQUISITION - SAMPLE COOLER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-2103 | REQUISITION - STRAINER |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P55-2104 | REQUISITION - ISOKINETIC SAMPLING NOZZLE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P91 Index/List
| MP | OL1-2P91-1001 | LINE LIST - OLEFINS PROCESS AREA 10 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1101 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1201 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1301 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1401 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1501 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-1601 | LINE DESIGNATION TABLE - FURNACE AREA |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2001 | LINE LIST - OLEFINS PROCESS AREA 20 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2101 | LINE LIST - OLEFINS PROCESS AREA 21 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2201 | LINE LIST - OLEFINS PROCESS AREA 22 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2301 | LINE LIST - OLEFINS PROCESS AREA 23 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2401 | LINE LIST - OLEFINS PROCESS AREA 24 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2501 | LINE LIST - OLEFINS PROCESS AREA 25 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2601 | LINE LIST - OLEFINS PROCESS AREA 26 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2701 | LINE LIST - OLEFINS PROCESS AREA 27 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2801 | LINE LIST - OLEFINS PROCESS AREA 28 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-2901 | LINE LIST - OLEFINS PROCESS AREA 29 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-3001 | LINE LIST - OLEFINS PROCESS AREA 30 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-5001 | LINE LIST - OLEFINS UTILITY AREA 50 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-5301 | LINE LIST - OLEFINS UTILITY AREA 53 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-5501 | LINE LIST - OLEFINS UTILITY AREA 55 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P91-5601 | LINE LIST - OLEFINS UTILITY AREA 56 |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P92 Procedures & Standards
| MP | OL1-2P92-0001 | PIPING STANDARD ASSEMBLY COLLECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P92-0002 | PIPING DESIGN STANDARD DRAWINGS |  | Class 2 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08 | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00012 | TPSK-LSPA1-T-MP-00325
[6 empty] | Return Date | 2018-09-26 | 2018-12-07
[6 empty] | Owner Cmmt* | A4 | R1
| MP | OL1-2P92-0003 | PIPING STANDARD CONSTRUCTION DRAWINGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P92-0004 | JOB CONSTRUCTION SPECIFICATION FOR BOLTED FLANGED JOINT ASSEMBLY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P92-0007 | CONSTRUCTION SPECIFICATION FOR PIPING PREFABRICATION, ERECTION AND NON DESTRUCTIVE TESTING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P92-0008 | HYDROSTATIC LEAK TESTING FOR PIPING SYSTEMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P92-0012 | SPECIAL TECH.SPEC.PIP.PREFAB. & ERE. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P92-0050 | Piping Standard Construction Drawings |  | Class 2 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08 | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00012 | TPSK-LSPA1-T-MP-00325
[6 empty] | Return Date | 2018-09-26 | 2018-12-07
[6 empty] | Owner Cmmt* | A4 | R1
Category Code: Q92 Procedures & Standards
| QM | OL1-2Q92-0001 | OVERALL PROJECT QUALITY PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0002 | CONFIDENTIALITY PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: R02 Civil Specification (CV)
| CV | OL1-2R02-0001 | Job Design Specification For Underground Systems |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00087
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2R02-0002 | JOB DESIGN SPECIFICATION FOR GEOTECHNICAL RECOMMENDATIONS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0003 | JOB DESIGN SPECIFICATION FOR PILES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0004 | Job Design Specification For Foundations And Structures |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00087
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2R02-0005 | Buildings Design And Construction |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00158
Return Date
Owner Cmmt*
| CV | OL1-2R02-0006 | JOB SUPPLY SPEC.FOR STEEL STRUCT. |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0007 | TEKLA STRUCTURE MANAGEMENT FOR LSP COMPLEX PROJECT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0008 | GUIDELINE FOR MTO SUMMARY FOR STEEL STRUCTURES WITH USE OF “TEKLA STRUCTURE” REPORT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0009 | U/G AND A/G CIVIL MODEL MANAGEMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0010 | 3D MODELING PROCEDURE FOR CIVIL DESIGNERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: R03 Mechanical Specification (ME)
| ME | OL1-2R03-0001 | Jo b Specification For Weldings and NDE Of Pressure Vessels And Heat Exchangers |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00029
[6 empty] | Return Date | 2018-09-19
[6 empty] | Owner Cmmt* | A4
| ME | OL1-2R03-0002 | Job Specification For Materials In Sour Services |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00029
[6 empty] | Return Date | 2018-09-19
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0003 | Job Specification For Supply Positive Alloy Material Identification Of Equipment And Piping |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00029
[6 empty] | Return Date | 2018-09-19
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0004 | Job Specification For Welding And NDE Storage Tanks |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00029
[6 empty] | Return Date | 2018-09-19
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0005 | ME-005 Double Jacket Pipe Heat Exchangers for 36M and 132U Furnace |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00212
Return Date
Owner Cmmt*
| ME | OL1-2R03-0006 | Plate Heat Exchanger |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00042
Return Date
Owner Cmmt*
| ME | OL1-2R03-0010 | ME-010 Centrifugal Pump |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00078
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0013 | ME-013 Diesel Engine |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00196
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0014 | ME-014 Centrifugal Compressor |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00065
[6 empty] | Return Date | 2018-10-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0016 | ME-016 Centrifugal Compressor For PA/IA Servise |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00164
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0017 | ME-017 Root Blower |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00334
Return Date
Owner Cmmt*
| ME | OL1-2R03-0018 | ME-018 General Purpose Steam Turbines |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00078
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0019 | ME-019 Lube Oil Unit And Seal Oil System |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00065
[6 empty] | Return Date | 2018-10-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0020 | ME-020 Special Purpose Steam Tturbines |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00078
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0021 | ME-021 Flare System |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00429
Return Date
Owner Cmmt*
| ME | OL1-2R03-0022 | ME-022 Special Purpose Gear |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00166
[6 empty] | Return Date | 2018-11-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-0028 | ME-028 Mechanical Seal |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00057
Return Date
Owner Cmmt*
| ME | OL1-2R03-0029 | ME-029 Centrifugal Blower for 36M and 132U Furnace |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00185
[6 empty] | Return Date | 2018-11-05
Owner Cmmt*
| ME | OL1-2R03-0047 | ME-047 Dry Screw Compressor for Hydrocarbon Services |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00429
Return Date
Owner Cmmt*
| ME | OL1-2R03-0050 | Job Specification For Design Of Pressure & Atmospheric Static Equipment |  | Class 2 | Purpose** | IFR | IFR | IMP
[6 empty] | Rev. | A | B | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-09-25 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00017 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00245
[6 empty] | Return Date | 2018-08-27 | 2018-10-24 | 2018-11-26
[6 empty] | Owner Cmmt* | A3 | R1
| ME | OL1-2R03-0051 | Job Specification For Supply Of Pressure Vessels |  | Class 2 | Purpose** | IFR | IFR | IMP
[6 empty] | Rev. | A | B | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-13 | 2018-09-25 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00021 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00249
[6 empty] | Return Date | 2018-08-27 | 2018-10-24 | 2018-11-27
[6 empty] | Owner Cmmt* | A4 | R1
| ME | OL1-2R03-0052 | Job Specification For Supply Of Column Internals |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00017 | TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | 2018-08-27 | 2018-10-24
[6 empty] | Owner Cmmt* | A3
| ME | OL1-2R03-0053 | Job Specification For Supply Of Equipment Ladders And Platforms |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00017 | TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | 2018-08-27 | 2018-10-24
[6 empty] | Owner Cmmt* | A4
| ME | OL1-2R03-0054 | Construction Standards For Pressure Equipment |  | Class 2 | Purpose** | IFR | IFR | IMP
[6 empty] | Rev. | A | B | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-09-25 | 2018-10-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00018 | TPSK-LSPA1-T-ME-00084 | TPSK-LSPA1-T-ME-00256
[6 empty] | Return Date | 2018-08-27 | 2018-10-24 | 2018-11-27
[6 empty] | Owner Cmmt* | A3 | R1
| ME | OL1-2R03-0055 | Construction Standards For Ladders & Platforms Attached To Pressure Equipment |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00120
[6 empty] | Return Date | 2018-10-24
Owner Cmmt*
| ME | OL1-2R03-0102 | Marking For Vessel & Heat Exchanger |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00042
Return Date
Owner Cmmt*
| ME | OL1-2R03-0104 | ME-008 Cooling Water |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276
Return Date
Owner Cmmt*
| ME | OL1-2R03-0500 | ME-050 Centrifugal Pump (Non API) |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00308
[6 empty] | Return Date | 2018-12-06
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R03-055 | Construction Standards For Ladders And Platforms Attached To Pressure Equipment |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00027
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2R03-1001 | ME-001 Pressure Vessel for 36M and 132U Furnace |  | Class 2 | Purpose** | IFE
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00262
Return Date
Owner Cmmt*
| ME | OL1-2R03-1004 | ME-004 Shell and Tube Heat Exchangers for 36M and 132U Furnace |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00221
Return Date
Owner Cmmt*
Category Code: R04 Piping Specification (PIP)
| MP | OL1-2R04-0001 | PIPING CLASSES SUMMARY & PIPING CLASSES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0002 | Job Specification For Detail Design Piping |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08 | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00012 | TPSK-LSPA1-T-MP-00012
[6 empty] | Return Date | 2018-09-26 | 2018-12-07
[6 empty] | Owner Cmmt* | A4 | R1
| MP | OL1-2R04-0003 | Job design specification for thermal insulation (hot service) |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00024
[6 empty] | Return Date | 2018-09-12
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0004 | Job Design Specification For Thermal Insulation (Cold Service) |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00024
[6 empty] | Return Date | 2018-09-12
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0005 | Job Design Specification For Painting |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00024
[6 empty] | Return Date | 2018-09-12
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0006 | General Supply Specification For Piping Material |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27 | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2R04-0007 | PIP-007 Marking of Piping Material for 36M and 132U Furnace |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00213
Return Date
Owner Cmmt*
| MP | OL1-2R04-0008 | Job Supply Specification For Butterfly Valves |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00352
Return Date
Owner Cmmt*
| MP | OL1-2R04-0009 | Job Supply Specification For Plug Valves |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00352
Return Date
Owner Cmmt*
| MP | OL1-2R04-0010 | Job Supply Specification For Ball Valves |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00352
Return Date
Owner Cmmt*
| MP | OL1-2R04-0011 | Job Supply Specification For Pipes |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27 | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2R04-0012 | Pipe Support |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00324
Return Date
Owner Cmmt*
| MP | OL1-2R04-0013 | Job Supply Specification For Buttwelding Fittings |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27 | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0014 | Job Supply Specification For Forged Fittings |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27 | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0015 | Job Supply Specification For Flanges |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-27 | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00028 | TPSK-LSPA1-T-MP-00342
[6 empty] | Return Date | 2018-09-18
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0016 | JOB SUPPLY SPECIFICATION FOR GASKETS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0017 | JOB SUPPLY SPECIFICATION FOR BOLTING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0018 | JOB SUPPLY SPECIFICATION FOR REINFORCED THERMOSETTING RESIN PLASTIC PIPING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0030 | Piping Flexibility |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00336
[6 empty] | Return Date | 2018-12-07
[6 empty] | Owner Cmmt* | R1
| MP | OL1-2R04-0031 | A1 Scope Annex C– Ppiping Specification PIP-006 Steam Tracing Piping |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-08 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00012 | TPSK-LSPA1-T-MP-00292
[6 empty] | Return Date | 2018-09-26
[6 empty] | Owner Cmmt* | A4
| MP | OL1-2R04-0032 | JSD For Piping Stress Analysis |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00324
Return Date
Owner Cmmt*
| MP | OL1-2R04-0033 | JSD for piping loads on PRK SLW STR IS |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00324
Return Date
Owner Cmmt*
| MP | OL1-2R04-0034 | JSD For Auxiliary Piping Supports |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00324
Return Date
Owner Cmmt*
| MP | OL1-2R04-0035 | JSS AUXILIARY PIPING SUPPORTS MATERIALS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0036 | JSS CRYOGENIC SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0037 | JSS FOR ROD & SPRING HANGERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0038 | JSS SLIDING PLATES |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0039 | JSS DYNAMIC PIPING SUPPORTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0040 | JSS METALLIC EXPANSION JOINTS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2R04-0041 | Job Supply Specification For Valves (Gate - Globe - Check) |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00356
Return Date
Owner Cmmt*
| MP | OL1-2R04-1004 | PIP-004 Piping Welding Specification for 36M and 132U Furnace |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00184
Return Date
Owner Cmmt*
Category Code: R05 Electrical Specification (EE)
| EE | OL1-2R05-0001 | General Electrical Design |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0002 | Electrical System Design |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0003 | Oil Filled Distribution Transformer |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0004 | PROTECTIVE RELAY AND CONTROL UNIT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0005 | Substation Monitoring And Control System |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0006 | Medium Voltage Switchgear |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0007 | Low Voltage Distribution Panel |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00309
Return Date
Owner Cmmt*
| EE | OL1-2R05-0008 | Low Voltage Switchgear And Motor Control Center |  | Class 2 | Purpose** | IFE
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00309
Return Date
Owner Cmmt*
| EE | OL1-2R05-0010 | Electrical Motos Up To 300 kW |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00079
Return Date
Owner Cmmt*
| EE | OL1-2R05-0011 | Electrical Motors Greater Than 300 kW |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00293
Return Date
Owner Cmmt*
| EE | OL1-2R05-0012 | Uninterruptible Power Supplies |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0013 | Intercom/Paging/Audible Alarm System |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00403
Return Date
Owner Cmmt*
| EE | OL1-2R05-0014 | LIGHTING SYSTEM |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0015 | Earthing And Lightning Protection |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0016 | Cathodic Protection |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0017 | Diesel Engine Generator |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0018 | Power Control And Fiber Optic Cables |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0019 | Safety Supervisory System |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00403
Return Date
Owner Cmmt*
| EE | OL1-2R05-0021 | Power Capacitors |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0022 | Miscellaneous Equipment |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0023 | Low Voltage Variable Voltage Variable Frequency System |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0024 | SUBSTATION DESIGN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0027 | Neutral Grounding Resistor |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0028 | TELECOM NUMBERING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0029 | Functional and Schematic Diagram |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0036 | Document Template |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0037 | Electrical Heat Tracing |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00079
Return Date
Owner Cmmt*
| EE | OL1-2R05-0038 | Low Voltage Bus Duct |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0040 | Medium Voltage Variable Voltage Variable Frequency System |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0041 | NUMBERING SYSTEM FOR ELECTRICAL EQUIPMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0042 | GENERAL DESIGN RULE FOR PACKAGE EQUIPMENT ELECTRICAL SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0043 | GENERAL DESIGN RULE FOR SMARTPLANT ELECTRICAL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0044 | Coordination Procedure For Smartplant Electrical |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2018-08-24
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2R05-0045 | Coordination Procedure For ETAP |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | 2018-08-24
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2R05-1001 | INTERCOM/PAGING / AUDIBLE ALARM SYSTEM EXTENT OF SUPPLY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-1002 | SAFETY SUPERVISORY SYSTEM EXTENT OF SUPPLY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: R06 Instrument Specification (INS)
| IE | OL1-2R06-0001 | Instrument General Design |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0003 | Flow Measurement |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0005 | LEVEL MEASUREMENT |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0006 | PRESSURE MEASUREMENT |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0007 | TEMPERATURE MEASUREMENT |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0008 | Final Control Element |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0010 | Instrument Construction Material |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0011 | Instrument Air Supply |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00357
Return Date
Owner Cmmt*
| IE | OL1-2R06-0012 | GROUNDING SYSTEM FOR INSTRUMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2R06-0013 | Machinery Monitoring System |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0015 | Integrated Control And Safety System |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00357
Return Date
Owner Cmmt*
| IE | OL1-2R06-0016 | Instrument Cabinet |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0017 | Integrated Turbine And Compressor Control System |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00148
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2R06-0021 | Pressure Safety Valve |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0022 | Instrument Numbering |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date | 2018-10-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2R06-0023 | Instrument Inspection And Test Plan |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0024 | General Design Rules For SmartPlant Instrumentation Setup |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28 | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00109 | TPSK-LSPA1-T-IE-00291
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2R06-0035 | General Design Rules For Instrumentation And Control Of Packaged Equipment |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-17 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00056 | TPSK-LSPA1-T-IE-00393
[6 empty] | Return Date | 2018-10-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2R06-1002 | SPEC. FOR ALARM MANAGEMENT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2R06-1025 | JSD FOR CTRL & SAFETY PHILOSOPHY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2R06-1026 | JSD FOR AUTOMATION SYSTEM AVAILABILITY |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2R06-1301 | Progammable Logic Controller |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00291
Return Date
Owner Cmmt*
| IE | OL1-2R06-2003 | PROCESS ONLINE ANALYZER AND ANALYZER HOUSING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2R06-3101 | Custody Transfer System |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00357
Return Date
Owner Cmmt*
Category Code: R07 Project Specification (SP)
| ME | OL1-2R07-0001 | TAGGING PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2R07-0010 | EQUIPMENT PRESERVATION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2R07-0018 | Units Of Measurement |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00080
[6 empty] | Return Date | 2018-10-24
Owner Cmmt*
| ME | OL1-2R07-0020 | Electrical And Instrument Interface Philosophy |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00121
[6 empty] | Return Date | 2018-10-09
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2R07-0023 | DRAFTING PROCEDURE FOR 2D DRAWINGS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2R07-0024 | 3D MODELING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2R07-0025 | REQUIREMENTS FOR EQIPMENT SUPPLIER 3D MODEL |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2R07-0026 | Project Design Basis |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00110
[6 empty] | Return Date | 2018-10-24
Owner Cmmt*
| ME | OL1-2R07-0027 | 3D MODELING PROCEDURE FOR PIPING DESIGNERS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: R08 Construction Specification (CON)
| CON | OL1-2R08-0001 | SPECIAL TEC.SP.FOR ERECT |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CON | OL1-2R08-0003 | Instrument Installation |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
Category Code: R93 Policy , Guidelines & Memo
| CON | OL1-2R93-2001 | GUIDELINE FOR CRACKING FURNACE CONSTRUCTION / ERECTION |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: S08
| ES | OL1-2S08-0001 | Environmental Protection Design Criteria |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ES-00473
Return Date
Owner Cmmt*
Category Code: S92 Procedures & Standards
| ES | OL1-2S92-0001 | PROJECT HSSE PLAN |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ES | OL1-2S92-0002 | INCIDENT INVESTIGATION AND REPORTING PROCEDURE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T11 Intercom/Paging/Audible Alarm system schematic diagram
| EE | OL1-2T11-0001 | TELECOMM.SYST ARCHITECTURE OF INTERCOM, PAGING AND AUDIBLE ALARM SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T12 Intercom/Paging/Audible Alarm aystem layout
| EE | OL1-2T12-0002 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT COMMON AREA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0003 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT METERING |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0004 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT MAIN PIPE RACK |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0005 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT AREA SUBSTATION E & FAR E |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0006 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT AREA SUBSTATION C & FAR C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0007 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT FURNACES UTILITY |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0008 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT QUENCH |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0009 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS 20B |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0010 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS 20C |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0011 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS COLD COMPRESSORS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0012 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS CGC |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0013 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT BUTADIENE |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0014 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT COOLING WATER UNIT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0015 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT UTILITIES |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0016 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT WASTE WATER TREATMENT |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0017 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT FLARE AREA |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T13 Intercom/Paging/Audible Alarm aystem wiring layout
| EE | OL1-2T13-1001 | TELECOM WIRING DRAWINGS FOR FAR-E SYSTEMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1002 | TELECOM WIRING DRAWINGS FOR FAR-C SYSTEMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1003 | TELECOM WIRING DRAWINGS FOR FAR-FL SYSTEMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1004 | TELECOM WIRING DRAWINGS FOR CCB SYSTEMS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T16 Connection List for Intercom/Paging/Audible Alarm aystem
| EE | OL1-2T16-1001 | TELECOM CABLE LIST FOR FAR C SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1002 | TELECOM CABLE LIST FOR FAR E SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1003 | TELECOM CABLE LIST FOR FAR FL SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1004 | TELECOM CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T17 Bill of quantities for Intercom/Paging/Audible Alarm aystem
| EE | OL1-2T17-0001 | TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T17-0002 | TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST FOR OTHER CONTRACTORS |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T26 Connection List for Computer Network (LAN) and Telephone system
| EE | OL1-2T26-0001 | FIBRE OPTIC TERMINATION DRAWINGS |  | Class 1 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T92 Procedures & Standards
| EE | OL1-2T92-0001 | JSS FOR INTERCOM/PAGING/AUDIBLE ALARM SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T92-0002 | JSS FOR SAFETY SUPERVISORY SYSTEM |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: V92 Procedures & Standards
| IF | OL1-2V92-0014 | INTERFACE MANAGEMENT PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: W90
| PC | OL1-2W90-0001 | Fire Fighting Basic Design Report For Package A1 |  | Class 2 | Purpose** | IFI | IFI
[6 empty] | Rev. | 0 | 1
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-08-10 | 2018-10-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00020 | TPSK-LSPA1-T-PM-00187
[6 empty] | Return Date | 2018-08-20
[6 empty] | Owner Cmmt* | R2
Category Code: W91 Index/List
| PC | OL1-2W91-0001 | Master Document Index (MDI) |  | Class 2 | Purpose** | IFI | IFI
[6 empty] | Rev. | 0 | 1
Issue Plan
Revised Plan
[6 empty] | Issue Actual | 2018-10-17 | 2018-11-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PM-00186 | TPSK-LSPA1-T-PC-00354
Return Date
Owner Cmmt*
Category Code: W92 Procedures & Standards
| PC | OL1-2W92-0001 | COORDINATION PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0003 | PROJECT DOCUMENT CODING |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0004 | DOCUMENT MANAGEMENT PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0005 | REQUIREMENTS FOR VENDOR DOCUMENTATION AND EXCHANGE OF CORRESPONDENCE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0006 | TPSK PROJECT DIRECTORATE ORGANIZATION CHART |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0007 | TPSK ROC ORGANIZATION CHART |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0009 | CRITICALITY RATING PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0010 | PRESCRIPTIONS FOR PREPARATION OF VENDOR DATA BOOK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0011 | TPSK HOC ORGANIZATION CHART |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0012 | ITC PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0013 | PROJECT EXECUTION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0015 | PRESCRIPTIONS FOR PREPARATION OF MANUFACTURING DATA RECORD BOOK |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0016 | REPORTING PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0018 | ENGINEERING EXECUTION PLAN |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0019 | PROJECT CONTROL PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0020 | TPSK SOC ORGANIZATION CHART |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-0021 | TPSK KLOC ORGANIZATION CHART |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PC | OL1-2W92-2122 | PROJECT ENGINEERING PLAN - PACKAGE A1 - FURNACES - HOUSTON SCOPE (INTERNAL ONLY) |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: X01
| PC | OL1-2X01-0001 | PAYMENT AND INVOICING PROCEDURE |  | Class 2 | Purpose**
Rev.
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: