## Document
Document Reference | Document Title | Revision Number | Revision Date | Document Revision Object | Document Client Reference | Discipline | Transmittal Date | Transmittal Reference | Specific Transmittal Number | Required Action | Response Due Date | Actual Response Date | Document Status | Client Transmittal Ref Number | Remarks | Fake Rev
036909C-1000-DI-0007-0001 | Process Design Basis | A | 2018-07-20 | IFA | OL1-2G02-0001 | PE | 2018-07-30 | 036909C-JVD-TRN-00002 | 036909C-JVD-TRN-00002 | IFA | 2018-08-10 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00002 |  | A
036909C-1000-DI-0007-0002 | Equipment Basis Of Design | A | 2018-07-24 | IFA | OL1-2G02-0002 | PE | 2018-07-30 | 036909C-JVD-TRN-00002 | 036909C-JVD-TRN-00002 | IFA | 2018-08-10 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00002 |  | A
036909C-1050-DI-0007-5001 | Area Basis of Design - 50 ISBL Supporting Utilities | A | 2018-07-25 | IFA | OL1-2G05-5001 | PE | 2018-07-31 | 036909C-JVD-TRN-00003 | 036909C-JVD-TRN-00003 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00003 |  | A
036909C-1053-DI-0007-5301 | Area Basis of Design - 53 Cooling Tower System | A | 2018-07-25 | IFA | OL1-2G05-5301 | PE | 2018-07-31 | 036909C-JVD-TRN-00003 | 036909C-JVD-TRN-00003 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00003 |  | A
036909C-1000-DI-0007-0006 | Furnace Process Basis of Design | A | 2018-07-26 | IFA | OL1-2G02-0006 | PE | 2018-07-31 | 036909C-JVD-TRN-00004 | 036909C-JVD-TRN-00004 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00004 |  | A
036909C-1000-JSD-0000-03 | JSD for P&ID Preparation | A | 2018-07-31 | IFA | OL1-2G01-0001 | PE | 2018-07-31 | 036909C-JVD-TRN-00006 | 036909C-JVD-TRN-00006 | IFR | 2018-08-13 | 2018-08-21 | Transmitted | TPSK-LSPA1-T-PE-00006 |  | A
036909C-1000-JSD-1600-003 | General Design Rule For Package Equipment Electrical System | A | 2018-08-03 | IFR | OL1-2R05-0042 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | A
036909C-1000-JSD-1600-008 | General Design Rule For Smartplant Electrical | A | 2018-08-03 | IFR | OL1-2R05-0043 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | A
036909C-1000-PP-1600-001 | Coordination Procedure For Smartplant Electrical | A | 2018-08-03 | IFR | OL1-2R05-0044 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | A
036909C-1000-PP-1600-003 | Coordination Procedure For ETAP | A | 2018-08-03 | IFI | OL1-2R05-0045 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | A
036909C-1000-NM-0001-1001 | Overall Material Balance | A | 2018-08-03 | IFI | OL1-2G44-1001 | PE | 2018-08-06 | 036909C-JVD-TRN-00009 | 036909C-JVD-TRN-00009 | IFI |  | 2018-08-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-00009 |  | A
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | A | 2018-08-03 | IFA | OL1-2G05-5601 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | A
036909C-1010-DI-0007-1001 | Area Basis of Design - 10 Feed Preparation | A | 2018-08-06 | IFA | OL1-2G05-1001 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | A
036909C-1020-DI-0007-2001 | Area Basis of Design - 20-21 Quench and Dilution Steam | A | 2018-08-06 | IFA | OL1-2G05-2001 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | A
036909C-1025-DI-0007-2501 | Area Basis of Design - 25 Cold Fractionation | A | 2018-08-06 | IFA | OL1-2G05-2501 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | A
036909C-1000-STD-1380-0001 | Piping Design Standard Drawings | A | 2018-08-07 | IFR | OL1-2P92-0002 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | A
036909C-1000-STC-1390-0001 | Piping Construction Drawing | A | 2018-08-07 | IFR | OL1-2P92-0003 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | A
036909C-1000-JSD-1300-0002 | Piping Design Specification | A | 2018-08-07 | IFR | OL1-2R04-0002 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | A
036909C-1000-JSD-1300-0003 | Job Design Specification For Steam Tracing | A | 2018-08-07 | IFR | OL1-2R04-0031 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | A
036909C-1023-DI-0007-2301 | Area Basis of Design - 23 Caustic and Spent Caustic Pretreatment | A | 2018-08-08 | IFA | OL1-2G05-2301 | PE | 2018-08-08 | 036909C-JVD-TRN-00014 | 036909C-JVD-TRN-00014 | IFA | 2018-08-22 | 2018-08-31 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00014 |  | A
036909C-1026-DI-0007-2601 | Area Basis of Design - 26 Hot Fractionation | A | 2018-08-07 | IFA | OL1-2G05-2601 | PE | 2018-08-08 | 036909C-JVD-TRN-00014 | 036909C-JVD-TRN-00014 | IFA | 2018-08-22 | 2018-08-31 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00014 |  | A
036909C-1000-JSS-1820-01 | Job Specification For Supply Of Equipment Ladders And Platforms | A | 2018-08-09 | IFR | OL1-2R03-0053 | ME | 2018-08-10 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00017 |  | A
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | A | 2018-08-09 | IFR | OL1-2R03-0050 | ME | 2018-08-10 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00017 |  | A
036909C-1000-JSS-0570-01 | Job Specification For Supply Of Column Internals | A | 2018-08-09 | IFR | OL1-2R03-0052 | ME | 2018-08-10 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00017 |  | A
036909C-1055-DI-0007-5501 | Area Basis of Design - 55 Flare System | A | 2018-08-09 | IFA | OL1-2G05-5501 | PE | 2018-08-09 | 036909C-JVD-TRN-00016 | 036909C-JVD-TRN-00016 | IFA | 2018-08-23 | 2018-08-29 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00016 |  | A
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | A | 2018-08-10 | IFR | OL1-2R03-0054 | ME | 2018-08-10 | 036909C-JVD-TRN-00018 | 036909C-JVD-TRN-00018 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00018 |  | A
036909C-1000-JSS-0400-01 | Job Specification for Supply of Pressure Vessels | A | 2018-08-10 | IFR | OL1-2R03-0051 | ME | 2018-08-13 | 036909C-JVD-TRN-00021 | 036909C-JVD-TRN-00021 | IFR | 2018-08-27 | 2018-08-27 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00021 |  | A
036909C-1022-DI-0007-2201 | Area Basis of Design - 22-24 Compresssion Train | A | 2018-08-09 | IFA | OL1-2G05-2201 | PE | 2018-08-13 | 036909C-JVD-TRN-00022 | 036909C-JVD-TRN-00022 | IFA | 2018-08-27 | 2018-09-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00022 |  | A
036909C-1028-DI-0007-2801 | Area Basis of Design - 28 Refrigeration | A | 2018-08-09 | IFA | OL1-2G05-2801 | PE | 2018-08-13 | 036909C-JVD-TRN-00022 | 036909C-JVD-TRN-00022 | IFA | 2018-08-27 | 2018-09-05 | A1-Approved without comments | TPSK-LSPA1-T-PE-00022 |  | A
036909C-1000-JSD-2200-01 | Job design specification for thermal insulation (hot service) | A | 2018-08-22 | IFR | OL1-2R04-0003 | MP | 2018-08-22 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | A
036909C-1000-JSD-2200-02 | Job Design Specification For Thermal Insulation (Cold Service) | A | 2018-08-22 | IFR | OL1-2R04-0004 | MP | 2018-08-22 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | A
036909C-1000-JSD-2300-01 | Job Design Specification For Painting | A | 2018-08-22 | IFR | OL1-2R04-0005 | MP | 2018-08-22 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | A
036909C-1022-PDS-1000-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | A | 2018-08-22 | IFA | OL1-2G30-2200 | PE | 2018-08-22 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | A
036909C-1028-PDS-1000-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | A | 2018-08-22 | IFA | OL1-2G30-2800 | PE | 2018-08-22 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | A
036909C-1028-PDS-1000-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | A | 2018-08-22 | IFA | OL1-2G30-2850 | PE | 2018-08-22 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | A
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | A | 2018-08-22 | IFR | OL1-2R04-0006 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-JSS-1320-01 | Job Supply Specification For Pipes | A | 2018-08-22 | IFR | OL1-2R04-0011 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-JSS-1330-01 | Job Supply Specification For Butt Welding Fittings | A | 2018-08-22 | IFR | OL1-2R04-0013 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-JSS-1340-01 | Job Supply Specification For Forged Fittings | A | 2018-08-22 | IFR | OL1-2R04-0014 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | A | 2018-08-23 | IFA | OL1-2G40-0010 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | A | 2018-08-23 | IFA | OL1-2G41-0001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | A | 2018-08-23 | IFA | OL1-2G41-0002 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | 2018-08-23 | IFA | OL1-2G41-1001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | 2018-08-23 | IFA | OL1-2G41-1003 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | A | 2018-08-23 | IFA | OL1-2G41-1101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | 2018-08-23 | IFA | OL1-2G41-1201 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | 2018-08-23 | IFA | OL1-2G41-1901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-1902 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | 2018-08-23 | IFA | OL1-2G41-2001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-08-23 | IFA | OL1-2G41-2002 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | 2018-08-23 | IFA | OL1-2G41-2101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | 2018-08-23 | IFA | OL1-2G41-2102 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | 2018-08-23 | IFA | OL1-2G41-2103 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | 2018-08-23 | IFA | OL1-2G41-2201 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | 2018-08-23 | IFA | OL1-2G41-2301 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | 2018-08-23 | IFA | OL1-2G41-2302 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | 2018-08-23 | IFA | OL1-2G41-2303 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | 2018-08-23 | IFA | OL1-2G41-2304 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | 2018-08-23 | IFA | OL1-2G41-2305 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | 2018-08-23 | IFA | OL1-2G41-2401 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | 2018-08-23 | IFA | OL1-2G41-2402 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | 2018-08-23 | IFA | OL1-2G41-2403 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2404 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | 2018-08-23 | IFA | OL1-2G41-2405 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | 2018-08-23 | IFA | OL1-2G41-2501 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | 2018-08-23 | IFA | OL1-2G41-2502 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | 2018-08-23 | IFA | OL1-2G41-2503 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | 2018-08-23 | IFA | OL1-2G41-2504 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | 2018-08-23 | IFA | OL1-2G41-2505 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | 2018-08-23 | IFA | OL1-2G41-2506 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2601 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | 2018-08-23 | IFA | OL1-2G41-2602 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | 2018-08-23 | IFA | OL1-2G41-2603 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | 2018-08-23 | IFA | OL1-2G41-2604 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | A | 2018-08-23 | IFA | OL1-2G41-2701 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | A | 2018-08-23 | IFA | OL1-2G41-2702 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | A | 2018-08-23 | IFA | OL1-2G41-2703 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2704 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | 2018-08-23 | IFA | OL1-2G41-2801 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | 2018-08-23 | IFA | OL1-2G41-2802 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | 2018-08-23 | IFA | OL1-2G41-2803 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | 2018-08-23 | IFA | OL1-2G41-2804 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-2901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | A | 2018-08-23 | IFA | OL1-2G41-3001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | A | 2018-08-23 | IFA | OL1-2G41-3002 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | A | 2018-08-23 | IFA | OL1-2G41-3003 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | A | 2018-08-23 | IFA | OL1-2G41-3004 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | A | 2018-08-23 | IFA | OL1-2G41-3005 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | A | 2018-08-23 | IFA | OL1-2G41-3101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam And Condensate System | A | 2018-08-23 | IFA | OL1-2G41-3102 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-3901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable And Demin Water Systems | A | 2018-08-23 | IFA | OL1-2G42-5001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | A | 2018-08-23 | IFA | OL1-2G42-5101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate And Boiler Feedwater Systems | A | 2018-08-23 | IFA | OL1-2G42-5102 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | A | 2018-08-23 | IFA | OL1-2G42-5103 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | A | 2018-08-23 | IFA | OL1-2G42-5104 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | A | 2018-08-23 | IFA | OL1-2G42-5201 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | A | 2018-08-23 | IFA | OL1-2G42-5301 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | A | 2018-08-23 | IFA | OL1-2G42-5311 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air And Nitrogen Systems | A | 2018-08-23 | IFA | OL1-2G42-5401 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare And Blowdown System | A | 2018-08-23 | IFA | OL1-2G42-5501 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | A | 2018-08-23 | IFA | OL1-2G42-5502 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | A | 2018-08-23 | IFA | OL1-2G42-5511 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | A | 2018-08-23 | IFA | OL1-2G42-5512 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5601 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | A | 2018-08-23 | IFA | OL1-2G42-5602 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | A | 2018-08-23 | IFA | OL1-2G42-5603 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5604 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | A | 2018-08-23 | IFA | OL1-2G42-5610 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5611 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | A | 2018-08-23 | IFA | OL1-2G42-5612 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | A | 2018-08-23 | IFA | OL1-2G42-5613 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | A | 2018-08-23 | IFA | OL1-2G42-5614 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | A | 2018-08-23 | IFA | OL1-2G42-5615 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | A | 2018-08-23 | IFA | OL1-2G42-5616 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | A | 2018-08-23 | IFA | OL1-2G42-5617 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G42-5901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | A | 2018-08-23 | IFA | OL1-2G42-5911 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1000-JSS-1350-01 | Job Supply Specification For Flanges | A | 2018-08-24 | IFR | OL1-2R04-0015 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-JSS-6300-02 | Jo b Specification For Weldings and NDE Of Pressure Vessels And Heat Exchangers | A | 2018-08-24 | IFR | OL1-2R03-0001 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00029 |  | A
036909C-1000-JSS-6300-03 | Job Specification For Materials In Sour Services | A | 2018-08-24 | IFR | OL1-2R03-0002 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | A
036909C-1000-JSS-6300-04 | Job Specification For Supply Positive Alloy Material Identification Of Equipment And Piping | A | 2018-08-24 | IFR | OL1-2R03-0003 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | A
036909C-1000-JSS-6300-05 | Job Specification For Welding And NDE Storage Tanks | A | 2018-08-24 | IFR | OL1-2R03-0004 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | A
036909C-1000-STC-1890-080 | Construction Standards For Ladders And Platforms Attached To Pressure Equipment | A | 2018-08-23 | IFR | OL1-2R03-055 | ME | 2018-08-27 | 036909C-JVD-TRN-00027 | 036909C-JVD-TRN-00027 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-00027 |  | A
036909C-1019-PDS-1000-1950 | Process Equipment Data Sheet - 10-PK-1950 - Decoke Air Compressor Package | A | 2018-08-29 | IFA | OL1-2G30-1950 | PE | 2018-08-29 | 036909C-JVD-TRN-00031 | 036909C-JVD-TRN-00031 | IFA |  | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00031 |  | A
036909C-1025-PDS-1000-2550 | Process Equipment Data Sheet - 10-C-TX-2550 - Residue Gas Expander - Recompressor | A | 2018-08-29 | IFA | OL1-2G30-2550 | PE | 2018-08-29 | 036909C-JVD-TRN-00031 | 036909C-JVD-TRN-00031 | IFA |  | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00031 |  | A
036909C-1000-NM-0001-1002 | Heat & Material Balance - Design Case 6 | A | 2018-08-30 | IFI | OL1-2G44-1002 | PE | 2018-08-31 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | A
036909C-1000-NM-0001-1003 | Heat & Material Balance - Design Case 8 | A | 2018-08-30 | IFI | OL1-2G44-1003 | PE | 2018-08-31 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | A
036909C-1000-NM-0001-1004 | Heat & Material Balance - Design Case 9 | A | 2018-08-30 | IFI | OL1-2G44-1004 | PE | 2018-08-31 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | A
036909C-1000-DI-0007-0003 | Flare and Blowdown System Design Basis | A | 2018-09-06 | IFA | OL1-2G02-0003 | PE | 2018-09-06 | 036909C-JVD-TRN-00034 | 036909C-JVD-TRN-00034 | IFA | 2018-09-20 | 2018-09-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00034 |  | A
036909C-1021-PDS-0600-2101 | Process Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | A | 2018-09-07 | IFA | OL1-2G30-2101 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2502 | Process Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | A | 2018-09-07 | IFA | OL1-2G30-2502 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2503 | Process Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | A | 2018-09-07 | IFA | OL1-2G30-2503 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2505 | Process Equipment Data Sheet - 10-E-2506 & 2508 - Demeth Prefrac Feed Cooler No 3 & No 4 | A | 2018-09-06 | IFA | OL1-2G30-2505 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2511 | Process Equipment Data Sheet - 10-E-2510 - Demeth Prefrac Condenser | A | 2018-09-06 | IFA | OL1-2G30-2511 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2521 | Process Equipment Data Sheet - 10-E-2520 - Rectifier Condenser | A | 2018-09-06 | IFA | OL1-2G30-2521 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2526 | Process Equipment Data Sheet - 10-E-2525 - Hydrogen Core Exchanger | A | 2018-09-06 | IFA | OL1-2G30-2526 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2531 | Process Equipment Data Sheet - 10-E-2530 - Demeth Feed Cooler | A | 2018-09-06 | IFA | OL1-2G30-2531 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2541 | Process Equipment Data Sheet - 10-E-2540 - Demethanizer Condenser | A | 2018-09-06 | IFA | OL1-2G30-2541 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2571 | Process Equipment Data Sheet - 10-E-2570 Deethanizer Condenser | A | 2018-09-07 | IFA | OL1-2G30-2571 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2585 | Process Equipment Data Sheet - 10-E-2585 - C2 Tower Bottoms Reboiler | A | 2018-09-06 | IFA | OL1-2G30-2585 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2587 | Process Equipment Data Sheet - 10-E-2587 - C2 Tower Side Reboiler | A | 2018-09-06 | IFA | OL1-2G30-2587 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1028-PDS-0600-2882 | Process Equipment Data Sheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | A | 2018-09-06 | IFA | OL1-2G30-2882 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1028-PDS-0600-2884 | Process Equipment Data Sheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | A | 2018-09-06 | IFA | OL1-2G30-2884 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1012-JSS-0122-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces | A | 2018-09-10 | IFR | OL1-4M92-2001 | ME | 2018-09-10 | 036909C-JVD-TRN-00037 | 036909C-JVD-TRN-00037 | IFR | 2018-09-24 | 2018-09-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00037 |  | A
036909C-1012-JSS-0122-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces | A | 2018-09-10 | IFR | OL1-4M92-2002 | ME | 2018-09-10 | 036909C-JVD-TRN-00037 | 036909C-JVD-TRN-00037 | IFR | 2018-09-24 | 2018-09-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00037 |  | A
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | A | 2018-09-06 | IFA | OL1-2M03-2200 | ME | 2018-09-10 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | A
036909C-1028-SP-1011-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | A | 2018-09-06 | IFA | OL1-2M03-2800 | ME | 2018-09-10 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | A
036909C-1028-SP-1011-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | A | 2018-09-06 | IFA | OL1-2M03-2850 | ME | 2018-09-10 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | A
036909C-1025-PDS-0600-2500 | Process Equipment Data Sheet - 10-E-2500 - Propylene Refrig Subcooler | A | 2018-09-10 | IFA | OL1-2G30-2500 | PE | 2018-09-11 | 036909C-JVD-TRN-00039 | 036909C-JVD-TRN-00039 | IFA | 2018-09-25 | 2018-09-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00039 |  | A
036909C-1028-PDS-0600-2856 | Process Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | 2018-09-10 | IFA | OL1-2G30-2856 | PE | 2018-09-11 | 036909C-JVD-TRN-00039 | 036909C-JVD-TRN-00039 | IFA | 2018-09-25 | 2018-09-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00039 |  | A
036909C-1026-PDS-0600-2645 | Process Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | A | 2018-09-11 | IFA | OL1-2G30-2645 | PE | 2018-09-12 | 036909C-JVD-TRN-00041 | 036909C-JVD-TRN-00041 | IFA | 2018-09-26 | 2018-10-01 | A1-Approved without comments | TPSK-LSPA1-T-PE-00041 |  | A
036909C-1028-PDS-0600-2857 | Process Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | 2018-09-11 | IFA | OL1-2G30-2857 | PE | 2018-09-12 | 036909C-JVD-TRN-00041 | 036909C-JVD-TRN-00041 | IFA | 2018-09-26 | 2018-10-01 | A1-Approved without comments | TPSK-LSPA1-T-PE-00041 |  | A
036909C-1012-JSS-0000-9999 | General Supply Rules for Supplier Documentation | A | 2018-09-12 | IFI | OL1-2C93-0001 | PL | 2018-09-12 | 036909C-JVD-TRN-00043 | 036909C-JVD-TRN-00043 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00043 |  | A
036909C-1012-TEN-0127-2001 | Technical Notes for Convection Tubes Material Requisition | A | 2018-09-06 | IFQ | OL1-4M57-2001 | ME | 2018-09-12 | 036909C-JVD-TRN-00044 | 036909C-JVD-TRN-00044 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00044 |  | A
036909C-1012-MR-0127-2001 | Material Requisition for Convection Tubes | A | 2018-09-06 | IFQ | OL1-4M55-2001 | ME | 2018-09-12 | 036909C-JVD-TRN-00044 | 036909C-JVD-TRN-00044 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00044 |  | A
036909C-1000-NM-0003-1008 | Fuel Balance | A | 2018-09-12 | IFI | OL1-2G62-1008 | PE | 2018-09-13 | 036909C-JVD-TRN-00049 | 036909C-JVD-TRN-00049 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00049 |  | A
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet for Decoking Air Compressor Package | A | 2018-09-13 | IFA | OL1-2M03-1950 | ME | 2018-09-13 | 036909C-JVD-TRN-00050 | 036909C-JVD-TRN-00050 | IFA | 2018-09-27 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00050 |  | A
036909C-1025-SP-1011-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | A | 2018-09-13 | IFA | OL1-2M03-2550 | ME | 2018-09-13 | 036909C-JVD-TRN-00050 | 036909C-JVD-TRN-00050 | IFA | 2018-09-27 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00050 |  | A
036909C-1024-PDS-0500-2440 | Process Equipment Data Sheet - 10-T-2440 - HP Depropanizer | A | 2018-09-13 | IFA | OL1-2G30-2440 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | A
036909C-1024-PDS-0500-2450 | Process Equipment Data Sheet - 10-T-2450 - LP Depropanizer | A | 2018-09-13 | IFA | OL1-2G30-2450 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | A
036909C-1026-PDS-0500-2630 | Process Equipment Data Sheet - 10-T-2630 - Secondary Deethanizer | A | 2018-09-13 | IFA | OL1-2G30-2630 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | A
036909C-1026-PDS-0500-2660 | Process Equipment Data Sheet - 10-T-2660 - Debutanizer | A | 2018-09-13 | IFA | OL1-2G30-2660 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | A
036909C-1000-NM-0003-1006 | Cooling Water Balance | A | 2018-09-14 | IFI | OL1-2G62-1006 | PE | 2018-09-17 | 036909C-JVD-TRN-00054 | 036909C-JVD-TRN-00054 | IFI | 2018-10-08 | 2018-10-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00054 |  | A
036909C-1000-JSD-1580-0003 | General Design Rules For Instrumentation And Control Of Packaged Equipment | A | 2018-09-14 | IFR | OL1-2R06-0035 | IE | 2018-09-17 | 036909C-JVD-TRN-00056 | 036909C-JVD-TRN-00056 | IFR | 2018-10-01 | 2018-10-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-00056 |  | A
036909C-1021-TDS-0661-2101 | Mechanical Data Sheet - 10-E-2100 - Quench Water Cooler | A | 2018-09-14 | IFA | OL1-2M03-2101 | ME | 2018-09-17 | 036909C-JVD-TRN-00058 | 036909C-JVD-TRN-00058 | IFA | 2018-10-01 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00058 |  | A
036909C-1000-NM-0003-1001 | Steam Balance | A | 2018-09-17 | IFI | OL1-2G62-1001 | PE | 2018-09-17 | 036909C-JVD-TRN-00059 | 036909C-JVD-TRN-00059 | IFI | 2018-10-01 | 2018-10-04 | Transmitted | TPSK-LSPA1-T-PE-00059 |  | A
036909C-1023-PDS-0500-2300 | Process Equipment Data Sheet - 10-T-2300 - Caustic Tower | A | 2018-09-17 | IFA | OL1-2G30-2300 | PE | 2018-09-18 | 036909C-JVD-TRN-00060 | 036909C-JVD-TRN-00060 | IFA | 2018-10-02 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00060 |  | A
036909C-1012-MR-0122-2004 | Material Requisition for Radiant Coil Assemblies | A | 2018-09-12 | IFQ | OL1-2M55-2004 | ME | 2018-09-18 | 036909C-JVD-TRN-00063 | 036909C-JVD-TRN-00063 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00063 |  | A
036909C-1011-DW-0122-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details | A | 2018-09-11 | IFR | OL1-2M06-1201 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1011-DW-0122-1202 | USC 36M Recycle Furnace Transfer Line and Clean-Out Details | A | 2018-09-11 | IFR | OL1-2M06-1202 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1011-DW-0122-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details | A | 2018-09-11 | IFR | OL1-2M06-1203 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1012-DW-0122-2201 | USC 132U Furnace Radiant Coil Assembly and Details | A | 2018-09-11 | IFR | OL1-2M06-2201 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1012-DW-0122-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details | A | 2018-09-11 | IFR | OL1-2M06-2202 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1012-DW-0122-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | A | 2018-09-11 | IFR | OL1-2M06-2203 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1000-JSS-1011-0001 | ME-014 Centrifugal Compressor | A | 2018-09-18 | IFR | OL1-2R03-0014 | ME | 2018-09-18 | 036909C-JVD-TRN-00065 | 036909C-JVD-TRN-00065 | IFR | 2018-10-03 | 2018-10-10 | R1-No comments | TPSK-LSPA1-T-ME-00065 |  | A
036909C-1000-JSS-1061-0001 | ME-019 Lube Oil Unit And Seal Oil System | A | 2018-09-18 | IFR | OL1-2R03-0019 | ME | 2018-09-18 | 036909C-JVD-TRN-00065 | 036909C-JVD-TRN-00065 | IFR | 2018-10-03 | 2018-10-10 | R1-No comments | TPSK-LSPA1-T-ME-00065 |  | A
036909C-1011-PDS-0610-1009 | See document number 036909C-1011-PDS-0610-1109 or OL1-2G30-1109 | A | 2018-09-17 | IFR | OL1-4G30-1009 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1011-PDS-0610-1010 | See document number 036909C-1011-PDS-0610-1110 or OL1-2G30-1110 | A | 2018-09-17 | IFR | OL1-4G30-1010 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1011-PDS-0630-1008 | See document number 036909C-1011-PDS-0630-1108 or OL1-2G30-1108 | A | 2018-09-17 | IFR | OL1-4G30-1008 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1012-PDS-0610-2009 | See document number 036909C-1012-PDS-0610-1209 or OL1-2G30-1209 | A | 2018-09-17 | IFR | OL1-4G30-2009 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1012-PDS-0630-2008 | See document number 036909C-1012-PDS-0630-1208 or OL1-2G30-1208 | A | 2018-09-17 | IFR | OL1-4G30-2008 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1012-JSS-0154-2007 | Project Specification For SLE and USX Exchangers | A | 2018-09-20 | IFR | OL1-4M92-2007 | ME | 2018-09-20 | 036909C-JVD-TRN-00067 | 036909C-JVD-TRN-00067 | IFR | 2018-10-04 | 2018-10-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00067 |  | A
036909C-1012-JSS-0154-2008 | Project Specification For Transfer Line Exchangers | A | 2018-09-20 | IFR | OL1-4M92-2008 | ME | 2018-09-20 | 036909C-JVD-TRN-00067 | 036909C-JVD-TRN-00067 | IFR | 2018-10-04 | 2018-10-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00067 |  | A
036909C-1023-PDS-2500-2320 | Process Equipment Data Sheet - 10-TK-2320 - Spent Caustic Storage Tank | A | 2018-09-20 | IFA | OL1-2G30-2320 | PE | 2018-09-20 | 036909C-JVD-TRN-00068 | 036909C-JVD-TRN-00068 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00068 |  | A
036909C-1021-PDS-0900-2146 | Process Equipment Datasheet 10-P-2146 DSG Feed Pumps | A | 2018-09-20 | IFA | OL1-2G30-2146 | PE | 2018-09-20 | 036909C-JVD-TRN-00069 | 036909C-JVD-TRN-00069 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00069 |  | A
036909C-1021-PDS-0900-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-2106 | PE | 2018-09-20 | 036909C-JVD-TRN-00070 | 036909C-JVD-TRN-00070 | IFA | 2018-10-04 | 2018-10-09 | A1-Approved without comments | TPSK-LSPA1-T-PE-00070 |  | A
036909C-1020-PDS-0900-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | A | 2018-09-20 | IFA | OL1-2G30-2006 | PE | 2018-09-20 | 036909C-JVD-TRN-00071 | 036909C-JVD-TRN-00071 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00071 |  | A
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | A | 2018-09-20 | IFA | OL1-2G30-2330 | PE | 2018-09-24 | 036909C-JVD-TRN-00073 | 036909C-JVD-TRN-00073 | IFA | 2018-10-08 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00073 |  | A
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 and 10-D-2540 - Demethanizer and Reflux Drum | A | 2018-09-20 | IFA | OL1-2G30-2540 | PE | 2018-09-24 | 036909C-JVD-TRN-00073 | 036909C-JVD-TRN-00073 | IFA | 2018-10-08 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00073 |  | A
036909C-1026-PDS-0600-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | A | 2018-09-20 | IFA | OL1-2G30-2631 | PE | 2018-09-24 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | A
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | A | 2018-09-20 | IFA | OL1-2G30-2635 | PE | 2018-09-24 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | A
036909C-1026-PDS-0600-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | A | 2018-09-20 | IFA | OL1-2G30-2636 | PE | 2018-09-24 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | A
036909C-1053-PDS-0900-5352 | Process Equipment Data Sheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-5352 | PE | 2018-09-24 | 036909C-JVD-TRN-00075 | 036909C-JVD-TRN-00075 | IFA | 2018-10-08 |  | Transmitted | TPSK-LSPA1-T-PE-00075 |  | A
036909C-1053-PDS-0900-5361 | Process Equipment Data Sheet - 10-P-5360 A-C - CTU Cooling Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-5361 | PE | 2018-09-24 | 036909C-JVD-TRN-00075 | 036909C-JVD-TRN-00075 | IFA | 2018-10-08 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00075 |  | A
036909C-1000-JSS-0910-0001 | ME-010 Centrifugal Pump | A | 2018-09-20 | IFR | OL1-2R03-0010 | ME | 2018-09-24 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | A
036909C-1000-JSS-1111-0001 | ME-018 General Purpose Steam Turbines | A | 2018-09-20 | IFR | OL1-2R03-0018 | ME | 2018-09-24 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | A
036909C-1000-JSS-1112-0001 | ME-020 Special Purpose Steam Tturbines | A | 2018-09-20 | IFR | OL1-2R03-0020 | ME | 2018-09-24 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | A
036909C-1053-PDS-0300-5350 | Process Equipment Data Sheet - 10-PK-5350 - Cooling Tower | A | 2018-09-24 | IFA | OL1-2G30-5350 | PE | 2018-09-25 | 036909C-JVD-TRN-00082 | 036909C-JVD-TRN-00082 | IFA | 2018-10-09 | 2018-10-13 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00082 |  | A
036909C-1053-PDS-0300-5355 | Process Equipment Data Sheet - 10-PK-5355 - Side Stream Filter Package | A | 2018-09-24 | IFA | OL1-2G30-5355 | PE | 2018-09-25 | 036909C-JVD-TRN-00082 | 036909C-JVD-TRN-00082 | IFA | 2018-10-09 | 2018-10-13 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00082 |  | A
036909C-1000-DW-1402-0001 | General Notes For Underground Works | A | 2018-09-18 | IFR | OL1-2K92-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | A
036909C-1000-DW-1702-0001 | General Notes For Concrete Works | A | 2018-09-19 | IFR | OL1-2K92-0003 | CV | 2018-09-25 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | A
036909C-1000-DW-1802-0001 | General Notes For Steel Structures | A | 2018-09-19 | IFR | OL1-2K92-0004 | CV | 2018-09-25 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | A
036909C-1000-JSD-1400-0001 | Job Design Specification For Underground Systems | A | 2018-09-18 | IFR | OL1-2R02-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00087 | 036909C-JVD-TRN-00087 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00087 |  | A
036909C-1000-JSD-1700-0001 | Job Design Specification For Foundations And Structures | A | 2018-09-19 | IFR | OL1-2R02-0004 | CV | 2018-09-25 | 036909C-JVD-TRN-00087 | 036909C-JVD-TRN-00087 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00087 |  | A
036909C-1000-STC-1790-0001 | Construction Standards for Reinforced Concrete Works | A | 2018-09-19 | IFR | OL1-2K20-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | A
036909C-1000-STC-1890-0001 | Construction Standards For Steel Structures | A | 2018-09-19 | IFR | OL1-2K21-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | A
036909C-1000-STC-1490-0001 | Standard Construction Drawings For Underground Systems | A | 2018-09-18 | IFR | OL1-2K23-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | A
036909C-1011-PDS-1040-1011 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | A | 2018-09-25 | IFR | OL1-4G30-1011 | PE | 2018-09-26 | 036909C-JVD-TRN-00090 | 036909C-JVD-TRN-00090 | IFR | 2018-10-10 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00090 |  | A
036909C-1012-PDS-1040-2011 | Process Equipment Data sheet - 10-C-1200-1600 - USC 132U Induced Draft Fan | A | 2018-09-25 | IFR | OL1-4G30-2011 | PE | 2018-09-26 | 036909C-JVD-TRN-00090 | 036909C-JVD-TRN-00090 | IFR | 2018-10-10 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00090 |  | A
036909C-1025-PDS-0500-2510 | Process Equipment Datasheet - 10-T-2510 and 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | A | 2018-09-26 | IFA | OL1-2G30-2510 | PE | 2018-09-26 | 036909C-JVD-TRN-00092 | 036909C-JVD-TRN-00092 | IFA | 2018-10-09 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00092 |  | A
036909C-1025-PDS-0600-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | A | 2018-09-26 | IFA | OL1-2G30-2575 | PE | 2018-09-26 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | A
036909C-1026-PDS-0600-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | A | 2018-09-26 | IFA | OL1-2G30-2661 | PE | 2018-09-26 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | A
036909C-1025-PDS-0600-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | A | 2018-09-26 | IFA | OL1-2G30-2576 | PE | 2018-09-26 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | A
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | A | 2018-09-27 | IFR | OL1-2R06-0024 | IE | 2018-09-28 | 036909C-JVD-TRN-00109 | 036909C-JVD-TRN-00109 | IFR | 2018-10-11 | 2018-10-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-00109 |  | A
036909C-1026-PDS-0600-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | A | 2018-09-27 | IFA | OL1-2G30-2665 | PE | 2018-09-27 | 036909C-JVD-TRN-00101 | 036909C-JVD-TRN-00101 | IFA | 2018-10-11 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00101 |  | A
036909C-1023-PDS-0800-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum | A | 2018-09-27 | IFA | OL1-2G30-2309 | PE | 2018-09-27 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | A
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | A | 2018-09-27 | IFA | OL1-2G30-2390 | PE | 2018-09-27 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | A
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 Spent Caustic Drain Drum | A | 2018-09-27 | IFA | OL1-2G30-2392 | PE | 2018-09-27 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | A
036909C-1023-PDS-0800-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum | A | 2018-09-27 | IFA | OL1-2G30-2322 | PE | 2018-09-28 | 036909C-JVD-TRN-00111 | 036909C-JVD-TRN-00111 | IFA | 2018-10-12 |  | Transmitted | TPSK-LSPA1-T-PE-00111 |  | A
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | A | 2018-09-27 | IFA | OL1-2G30-2666 | PE | 2018-09-28 | 036909C-JVD-TRN-00112 | 036909C-JVD-TRN-00112 | IFA | 2018-10-12 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00112 |  | A
036909C-1028-PDS-0600-2806 | Process Equipment Datasheet - 10-E-2805 - C3 Refrig Condensers | A | 2018-09-28 | IFA | OL1-2G30-2806 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1028-PDS-0600-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | A | 2018-09-28 | IFA | OL1-2G30-2807 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1028-PDS-0600-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | A | 2018-09-28 | IFA | OL1-2G30-2809 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1028-PDS-0600-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | A | 2018-09-28 | IFA | OL1-2G30-2852 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1028-PDS-0600-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | A | 2018-09-28 | IFA | OL1-2G30-2853 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1021-PDS-0800-2160 | Process Equipment Datasheet - 10-D-2160 - Dilution Steam Generator | A | 2018-09-28 | IFA | OL1-2G30-2160 | PE | 2018-09-28 | 036909C-JVD-TRN-00115 | 036909C-JVD-TRN-00115 | IFA | 2018-10-12 | 2018-11-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00115 |  | A
036909C-1000-NM-0001-1011 | Heat & Material Balance - Cooling Water System | A | 2018-09-28 | IFI | OL1-2G44-1011 | PE | 2018-10-01 | 036909C-JVD-TRN-00116 | 036909C-JVD-TRN-00116 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00116 |  | A
036909C-1012-PDS-0117-2001 | Process Equipment Datasheet - USC 132U Cracking Furnace Yields | A | 2018-09-28 | IFR | OL1-4G30-2001 | PE | 2018-10-01 | 036909C-JVD-TRN-00117 | 036909C-JVD-TRN-00117 | IFR | 2018-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-00117 |  | A
036909C-1011-PDS-0117-1001 | Process Equipment Datasheet - USC 36M Cracking Furnace Yields | A | 2018-09-28 | IFR | OL1-4G30-1001 | PE | 2018-10-01 | 036909C-JVD-TRN-00117 | 036909C-JVD-TRN-00117 | IFR | 2018-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-00117 |  | A
036909C-1000-JSD-0000-0004 | Cold Box Design Specification | A | 2018-10-01 | IFR | OL1-2G01-0002 | PE | 2018-10-03 | 036909C-JVD-TRN-00123 | 036909C-JVD-TRN-00123 | IFR | 2018-10-17 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00123 |  | A
036909C-1000-JSD-1540-0001 | Instrument General Design | A | 2018-09-28 | IFR | OL1-2R06-0001 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-SP-0662-0002 | Particular Technical Specification For Cold Box And Core Exchangers | A | 2018-10-01 | IFQ | OL1-2M57-0066 | ME | 2018-10-03 | 036909C-JVD-TRN-00125 | 036909C-JVD-TRN-00125 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00125 |  | A
036909C-1000-SP-0661-0001 | Particular Technical Specification For Plate And Frame Heat Exchangers | A | 2018-10-01 | IFQ | OL1-2M57-0064 | ME | 2018-10-03 | 036909C-JVD-TRN-00124 | 036909C-JVD-TRN-00124 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00124 |  | A
036909C-1000-JSD-1552-0001 | LEVEL MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0005 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1553-0001 | PRESSURE MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0006 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1554-0001 | TEMPERATURE MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0007 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1511-0001 | Instrument Cabinet | A | 2018-09-28 | IFR | OL1-2R06-0016 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1515-0004 | Machinery Monitoring System | A | 2018-09-28 | IFR | OL1-2R06-0013 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1522-0001 | Electrical And Instrument Interface Philosophy | A | 2018-09-28 | IFR | OL1-2R07-0020 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1541-0001 | Final Control Element | A | 2018-09-28 | IFR | OL1-2R06-0008 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-0000-0005 | Plate-Fin Exchanger Design Specification | A | 2018-10-01 | IFR | OL1-2G01-0003 | PE | 2018-10-03 | 036909C-JVD-TRN-00123 | 036909C-JVD-TRN-00123 | IFR | 2018-10-17 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00123 |  | A
036909C-1000-MR-0661-0001 | Material Requisition For Plate And Frame Heat Exchangers Requisition For Inquiry | A | 2018-10-01 | IFQ | OL1-2M55-0064 | ME | 2018-10-03 | 036909C-JVD-TRN-00124 | 036909C-JVD-TRN-00124 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00124 |  | A
036909C-1000-MR-0662-0002 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry | A | 2018-10-01 | IFQ | OL1-2M55-0066 | ME | 2018-10-03 | 036909C-JVD-TRN-00125 | 036909C-JVD-TRN-00125 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00125 |  | A
036909C-1000-NM-0001-1010 | Heat and Material Balance - ISBL Supporting Utilities | A | 2018-10-03 | IFI | OL1-2G44-1010 | PE | 2018-10-03 | 036909C-JVD-TRN-00128 | 036909C-JVD-TRN-00128 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00128 |  | A
036909C-1000-DW-1702-0002 | General Notes For Precast Concrete Works | A | 2018-10-04 | IFR | OL1-2K92-0002 | CV | 2018-10-08 | 036909C-JVD-TRN-00137 | 036909C-JVD-TRN-00137 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-CV-00137 |  | A
036909C-1000-JSD-1501-0001 | Instrument Numbering | A | 2018-10-03 | IFR | OL1-2R06-0022 | IE | 2018-10-05 | 036909C-JVD-TRN-00132 | 036909C-JVD-TRN-00132 | IFR | 2018-10-19 | 2018-10-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00131 |  | A
036909C-1000-PLG-302 | 90 Days Look-Head Schedule | A | 2018-10-04 | IFR | OL1-2B92-0002 | PC | 2018-10-05 | 036909C-JVD-TRN-00133 | 036909C-JVD-TRN-00133 | IFR | 2018-10-19 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-PC-00133 |  | A
036909C-1000-SP-1011-0001 | Particular Technical Specification For Centrifugal Compressors Steam Turbine Driven | A | 2018-10-04 | IFQ | OL1-2M57-0008 | ME | 2018-10-08 | 036909C-JVD-TRN-00136 | 036909C-JVD-TRN-00136 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00136 |  | A
036909C-1000-MR-1011-0001 | Material Requisition For Centrifugal Compressors Steam Turbine Driven | A | 2018-10-04 | IFQ | OL1-2M55-0008 | ME | 2018-10-08 | 036909C-JVD-TRN-00136 | 036909C-JVD-TRN-00136 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00136 |  | A
036909C-1000-PLG-305 | Engineering And Procurement Level 3 Schedule | A | 2018-10-05 | IFR | OL1-2B01-0001 | PC | 2018-10-05 | 036909C-JVD-TRN-00135 | 036909C-JVD-TRN-00135 | IFR | 2018-10-19 | 2018-10-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PC-00135 |  | A
036909C-1000-SP-1130-0001 | Particular Technical Specification For Residue Gas Expander/Recompressor | A | 2018-10-05 | IFQ | OL1-2M57-0012 | ME | 2018-10-09 | 036909C-JVD-TRN-00139 | 036909C-JVD-TRN-00139 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00139 |  | A
036909C-1000-MR-1130-0001 | Material Requisition For Residue Gas Expander/Recompressor | A | 2018-10-05 | IFQ | OL1-2M55-0012 | ME | 2018-10-09 | 036909C-JVD-TRN-00139 | 036909C-JVD-TRN-00139 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00139 |  | A
036909C-1051-PDS-0900-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | A | 2018-10-04 | IFR | OL1-2G30-5101 | PE | 2018-10-08 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | A
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | A | 2018-10-04 | IFR | OL1-2G30-5102 | PE | 2018-10-08 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | A
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | A | 2018-10-04 | IFR | OL1-2G30-5109 | PE | 2018-10-08 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | A
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | A | 2018-10-04 | IFR | OL1-2G30-5550 | PE | 2018-10-08 | 036909C-JVD-TRN-00142 | 036909C-JVD-TRN-00142 | IFR | 2018-10-22 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00142 |  | A
036909C-1022-PDS-0800-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2210 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2220 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1022-PDS-0800-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2230 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1028-PDS-0800-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2810 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1028-PDS-0800-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2820 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1028-PDS-0800-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2830 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1028-PDS-0800-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2840 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1000-DW-1422-0001 | Soil Investigation Plan | A | 2018-10-04 | IFR | OL1-2K43-0004 | CV | 2018-10-10 | 036909C-JVD-TRN-00145 | 036909C-JVD-TRN-00145 | IFR | 2018-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-00145 |  | A
036909C-1000-MS-1422-0001 | Technical Specification For Geotechnical Investigation | A | 2018-10-04 | IFR | OL1-2K43-0002 | CV | 2018-10-10 | 036909C-JVD-TRN-00147 | 036909C-JVD-TRN-00147 | IFR | 2018-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-00147 |  | A
036909C-1000-PS-1422-0001 | Price List For Geotechnical Investigation | A | 2018-10-04 | IFR | OL1-2K43-0003 | CV | 2018-10-10 | 036909C-JVD-TRN-00147 | 036909C-JVD-TRN-00147 | IFR | 2018-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-00147 |  | A
036909C-1000-JSD-1580-0001 | Integrated Turbine And Compressor Control System | A | 2018-10-08 | IFR | OL1-2R06-0017 | IE | 2018-10-10 | 036909C-JVD-TRN-00148 | 036909C-JVD-TRN-00148 | IFR | 2018-10-24 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-IE-00148 |  | A
036909C-1030-DI-0007-3001 | Area Basis of Design - 30 BDU | A | 2018-10-09 | IFA | OL1-2G05-3001 | PE | 2018-10-09 | 036909C-JVD-TRN-00150 | 036909C-JVD-TRN-00150 | IFA | 2018-10-23 |  | Transmitted | TPSK-LSPA1-T-PE-00150 |  | A
036909C-1051-PDS-0800-5100 | Process Equipment Data Sheet - 10-D-5100 - Deaerator | A | 2018-10-09 | IFR | OL1-2G30-5100 | PE | 2018-10-09 | 036909C-JVD-TRN-00151 | 036909C-JVD-TRN-00151 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00151 |  | A
036909C-1000-JSS-1013-0001 | ME-016 Centrifugal Compressor For PA/IA Servise | A | 2018-10-09 | IFR | OL1-2R03-0016 | ME | 2018-10-12 | 036909C-JVD-TRN-00164 | 036909C-JVD-TRN-00164 | IFR | 2018-10-26 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00164 |  | A
036909C-1000-JSD-2000-0001 | Buildings Design And Construction | A | 2018-10-10 | IFR | OL1-2R02-0005 | CV | 2018-10-11 | 036909C-JVD-TRN-00158 | 036909C-JVD-TRN-00158 | IFR | 2018-10-25 |  | Transmitted | TPSK-LSPA1-T-CV-00158 |  | A
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - 36M Cracking Furnace Steam Drum | A | 2018-10-11 | IFR | OL1-2G30-1107 | PE | 2018-10-11 | 036909C-JVD-TRN-00159 | 036909C-JVD-TRN-00159 | IFR | 2018-10-25 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00159 |  | A
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200-1600 - 132U Cracking Furnace Steam Drum | A | 2018-10-11 | IFR | OL1-2G30-1207 | PE | 2018-10-11 | 036909C-JVD-TRN-00159 | 036909C-JVD-TRN-00159 | IFR | 2018-10-25 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00159 |  | A
036909C-1020-PDS-0500-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower | A | 2018-10-11 | IFR | OL1-2G30-2000 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162 |  | A
036909C-1020-PDS-0500-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper | A | 2018-10-11 | IFR | OL1-2G30-2040 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162 |  | A
036909C-1025-PDS-0500-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower | A | 2018-10-11 | IFR | OL1-2G30-2580 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-10-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162 |  | A
036909C-1000-JSD-3400-0001 | Air Conditioning Ventilating And Ducting Design | A | 2018-10-12 | IFR | OL1-2H03-0001 | EE | 2018-10-12 | 036909C-JVD-TRN-00165 | 036909C-JVD-TRN-00165 | IFR | 2018-10-26 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-EE-00165 |  | A
036909C-1000-JSS-1160-0001 | ME-022 Special Purpose Gear | A | 2018-10-12 | IFR | OL1-2R03-0022 | ME | 2018-10-12 | 036909C-JVD-TRN-00166 | 036909C-JVD-TRN-00166 | IFR | 2018-10-26 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00166 |  | A
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | A | 2018-10-12 | IFR | OL1-2G30-5500 | PE | 2018-10-12 | 036909C-JVD-TRN-00168 | 036909C-JVD-TRN-00168 | IFR | 2018-10-26 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00168 |  | A
036909C-1025-PDS-0500-2520 | Process Equipment Datasheet - 10-T-2520 and 10-D-2520 - Residue Gas Rectifier & Reflux Drum | A | 2018-10-12 | IFR | OL1-2G30-2520 | PE | 2018-10-15 | 036909C-JVD-TRN-00172 | 036909C-JVD-TRN-00172 | IFR | 2018-10-29 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00172 |  | A
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | A | 2018-10-12 | IFR | OL1-2G30-2301 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00173 |  | A
036909C-1023-PDS-4200-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer | A | 2018-10-12 | IFR | OL1-2G30-2308 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00173 |  | A
036909C-1023-PDS-4200-2313 | Process Equipment Datasheet - 10-X-2312 - Spent Wash Oil Mixer | A | 2018-10-12 | IFR | OL1-2G30-2313 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00173 |  | A
036909C-1023-PDS-4200-2315 | Process Equipment Datasheet - 10-X-2310 - Spent Caustic Mixer | A | 2018-10-12 | IFR | OL1-2G30-2315 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00173 |  | A
036909C-1023-PDS-0900-2302 | Process Equipment Datasheet - 10-P-2302 A-B - Strong Caustic Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2302 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00174 |  | A
036909C-1023-PDS-0900-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump | A | 2018-10-12 | IFR | OL1-2G30-2304 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00174 |  | A
036909C-1023-PDS-0900-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2306 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00174 |  | A
036909C-1023-PDS-0900-2311 | Process Equipment Datasheet - 10-P-2310 A-B - Wash Oil Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2311 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00174 |  | A
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | A | 2018-10-12 | IFR | OL1-2G30-2331 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175 |  | A
036909C-1023-PDS-0800-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum | A | 2018-10-12 | IFR | OL1-2G30-2316 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175 |  | A
036909C-1022-PDS-0800-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum | A | 2018-10-12 | IFR | OL1-2G30-2240 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175 |  | A
036909C-1010-PDS-0600-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater | A | 2018-10-15 | IFR | OL1-2G30-1015 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176 |  | A
036909C-1010-PDS-0600-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater | A | 2018-10-15 | IFR | OL1-2G30-1005 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176 |  | A
036909C-1010-PDS-0600-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer | A | 2018-10-15 | IFR | OL1-2G30-1001 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176 |  | A
036909C-1010-PDS-0600-1003 | Process Equipment Datasheet - 10-E-1001 - LPG Steam Vaporizer | A | 2018-10-15 | IFR | OL1-2G30-1003 | PE | 2018-10-16 | 036909C-JVD-TRN-00179 | 036909C-JVD-TRN-00179 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-PE-00179 |  | A
036909C-1023-PDS-4100-2350 | Process Equipment Datasheet - 10-PK-2350 - Wet Air Oxidation Pkg | A | 2018-10-15 | IFR | OL1-2G30-2350 | PE | 2018-10-16 | 036909C-JVD-TRN-00180 | 036909C-JVD-TRN-00180 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-PE-00180 |  | A
036909C-1029-PDS-2600-2914 | Process Equipment Datasheet - 10-PK-2914 - Neutralization Injection Pkg | A | 2018-10-15 | IFR | OL1-2G30-2914 | PE | 2018-10-16 | 036909C-JVD-TRN-00181 | 036909C-JVD-TRN-00181 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-PE-00181 |  | A
036909C-1011-DW-0127-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill Of Material | A | 2018-10-12 | IFR | OL1-2M06-1204 | ME | 2018-10-16 | 036909C-JVD-TRN-00182 | 036909C-JVD-TRN-00182 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-00182 |  | A
036909C-1012-DW-0127-2204 | USC 132U Cracking Furnace Fabricatin Assembly of Convection Coils Finned Tubes and Bill of Material | A | 2018-10-12 | IFR | OL1-2M06-2204 | ME | 2018-10-16 | 036909C-JVD-TRN-00182 | 036909C-JVD-TRN-00182 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-00182 |  | A
036909C-1024-SP-0510-2450 | Mechanical Equipment Datasheet LP Depropanizer | A | 2018-10-15 | IFQ | OL1-2M03-2450 | ME | 2018-10-16 | 036909C-JVD-TRN-00183 | 036909C-JVD-TRN-00183 | IFR | 2018-10-30 | 2018-11-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00183 |  | A
036909C-1012-SP-0122-2004 | Particular Technical Specification For Radiant Coil Assemblies | A | 2018-09-10 | IFI | OL1-2M57-2004 | ME | 2018-09-18 | 036909C-JVD-TRN-00063 | 036909C-JVD-TRN-00063 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00063 |  | A
036909C-1021-PDS-0500-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper | A | 2018-10-17 | IFR | OL1-2G30-2140 | PE | 2018-10-17 | 036909C-JVD-TRN-00189 | 036909C-JVD-TRN-00189 | IFR | 2018-10-31 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00189 |  | A
036909C-1025-PDS-4100-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit | A | 2018-10-17 | IFR | OL1-2G30-2560 | PE | 2018-10-17 | 036909C-JVD-TRN-00190 | 036909C-JVD-TRN-00190 | IFR | 2018-10-31 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00190 |  | A
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | A | 2018-10-17 | IFR | OL1-2G30-2570 | PE | 2018-10-17 | 036909C-JVD-TRN-00191 | 036909C-JVD-TRN-00191 | IFR | 2018-10-31 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00191 |  | A
036909C-1021-PDS-0600-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater | A | 2018-10-17 | IFR | OL1-2G30-2137 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1021-PDS-0600-2145 | Process Equipment Datasheet - 10-E-2145 - Process Water Stripper Reboiler | A | 2018-10-17 | IFR | OL1-2G30-2145 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 |  | Transmitted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1021-PDS-0600-2147 | Process Equipment Datasheet - 10-E-2146 - DSG Feed Heater | A | 2018-10-17 | IFR | OL1-2G30-2147 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 |  | Transmitted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1021-PDS-0600-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater | A | 2018-10-17 | IFR | OL1-2G30-2161 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1021-PDS-0600-2165 | Process Equipment Datasheet - 10-E-2165 A-D DSG Reboilers | A | 2018-10-17 | IFR | OL1-2G30-2165 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1000-MR-1013-0001 | Material Requisition For Integrally Geared Decoking Air Compressors | A | 2018-10-18 | IFQ | OL1-2M55-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00198 | 036909C-JVD-TRN-00198 | IFR | 2018-11-02 | 2018-11-07 | Transmitted | TPSK-LSPA1-T-ME-00198 |  | A
036909C-1000-SP-1013-0001 | Particular Technical Specification for Integrally Geared Decoking Air Compressors | A | 2018-10-18 | IFQ | OL1-2M57-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00198 | 036909C-JVD-TRN-00198 | IFR | 2018-11-02 | 2018-11-07 | Transmitted | TPSK-LSPA1-T-ME-00198 |  | A
036909C-1026-PDS-0500-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower | A | 2018-10-18 | IFR | OL1-2G30-2640 | PE | 2018-10-22 | 036909C-JVD-TRN-00201 | 036909C-JVD-TRN-00201 | IFR | 2018-11-05 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00201 |  | A
036909C-1012-PDS-0117-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields | A | 2018-10-15 | IFR | OL1-2G30-1201 | PE | 2018-10-22 | 036909C-JVD-TRN-00204 | 036909C-JVD-TRN-00204 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00204 |  | A
036909C-1011-PDS-0117-1101 | Process Equipment Datasheet - 10-H-1100 - 36M Cracking Furnace Yields | A | 2018-10-15 | IFR | OL1-2G30-1101 | PE | 2018-10-22 | 036909C-JVD-TRN-00204 | 036909C-JVD-TRN-00204 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00204 |  | A
036909C-1023-PDS-0840-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters | A | 2018-10-18 | IFR | OL1-2G30-2307 | PE | 2018-10-22 | 036909C-JVD-TRN-00205 | 036909C-JVD-TRN-00205 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00205 |  | A
036909C-1023-PDS-0840-2314 | Process Equipment Datasheet - 10-F-2310 A-B - Wash Oil Circulating Filter | A | 2018-10-18 | IFR | OL1-2G30-2314 | PE | 2018-10-22 | 036909C-JVD-TRN-00205 | 036909C-JVD-TRN-00205 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00205 |  | A
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | A | 2018-10-18 | IFR | OL1-2G30-1020 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1022-PDS-0600-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercoolers | A | 2018-10-18 | IFR | OL1-2G30-2221 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1010-PDS-0600-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater | A | 2018-10-18 | IFR | OL1-2G30-1051 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1022-PDS-0600-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler | A | 2018-10-18 | IFR | OL1-2G30-2231 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1022-PDS-0600-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler | A | 2018-10-18 | IFR | OL1-2G30-2241 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1012-MR-0127-2002 | Material Requisition for Furnace Convection Fittings | A | 2018-10-16 | IFQ | OL1-2M55-2002 | ME | 2018-10-22 | 036909C-JVD-TRN-00207 | 036909C-JVD-TRN-00207 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00207 |  | A
036909C-1012-SP-0127-2002 | Particular Technical Specification for Furnace Convection Fittings | A | 2018-10-16 | IFQ | OL1-2M57-2002 | ME | 2018-10-22 | 036909C-JVD-TRN-00207 | 036909C-JVD-TRN-00207 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00207 |  | A
036909C-1000-JSS-1140-0001 | ME-013 Diesel Engine | A | 2018-10-22 | IFR | OL1-2R03-0013 | ME | 2018-10-18 | 036909C-JVD-TRN-00196 | 036909C-JVD-TRN-00196 | IFR | 2018-11-06 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-ME-00196 |  | A
036909C-1021-PDS-0600-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler | A | 2018-10-22 | IFR | OL1-2G30-2166 | PE | 2018-10-23 | 036909C-JVD-TRN-00209 | 036909C-JVD-TRN-00209 | IFR | 2018-11-06 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00209 |  | A
036909C-1028-PDS-0800-2860 | Process Equipment Datasheet - 10-D-2860 - C2R 1st Stage Suction Drum | A | 2018-10-22 | IFR | OL1-2G30-2860 | PE | 2018-10-23 | 036909C-JVD-TRN-00208 | 036909C-JVD-TRN-00208 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-PE-00208 |  | A
036909C-1028-PDS-0800-2880 | Process Equipment Datasheet - 10-D-2880 - C2R 3rd Stage Suction Drum | A | 2018-10-22 | IFR | OL1-2G30-2880 | PE | 2018-10-23 | 036909C-JVD-TRN-00208 | 036909C-JVD-TRN-00208 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-PE-00208 |  | A
036909C-1053-SP-0910-5352 | Mechanical Equipment Data Sheet for Olefins Cooling Water Pumps 10-P-5350 A-H | A | 2018-10-22 | IFQ | OL1-2M03-5352 | ME | 2018-10-23 | 036909C-JVD-TRN-00210 | 036909C-JVD-TRN-00210 | IFR | 2018-11-06 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00210 |  | A
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet for CTU Cooling Water Pumps 10-P-5360 A-B-C | A | 2018-10-22 | IFQ | OL1-2M03-5361 | ME | 2018-10-23 | 036909C-JVD-TRN-00210 | 036909C-JVD-TRN-00210 | IFR | 2018-11-06 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00210 |  | A
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet for HP Depropanizer | A | 2018-10-23 | IFQ | OL1-2M03-2440 | ME | 2018-10-23 | 036909C-JVD-TRN-00215 | 036909C-JVD-TRN-00215 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-ME-00215 |  | A
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet for Debutanizer | A | 2018-10-23 | IFQ | OL1-2M03-2660 | ME | 2018-10-23 | 036909C-JVD-TRN-00215 | 036909C-JVD-TRN-00215 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-ME-00215 |  | A
036909C-1025-PDS-0600-2515 | Process Equipment Datasheet - 10-E-2515 - Demeth Prefrac Reboiler | A | 2018-10-23 | IFR | OL1-2G30-2515 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1025-PDS-0600-2545 | Process Equipment Datasheet - 10-E-2545 - Demethanizer Reboiler | A | 2018-10-23 | IFR | OL1-2G30-2545 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1025-PDS-0600-2546 | Process Equipment Datasheet - 10-E-2546 - Demethanizer Bottoms Cooler | A | 2018-10-23 | IFR | OL1-2G30-2546 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1025-PDS-0600-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | A | 2018-10-23 | IFR | OL1-2G30-2548 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1025-PDS-0600-2591 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler | A | 2018-10-23 | IFR | OL1-2G30-2591 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1025-PDS-0800-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | A | 2018-10-23 | IFR | OL1-2G30-2504 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217 |  | A
036909C-1025-PDS-0800-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | A | 2018-10-23 | IFR | OL1-2G30-2506 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217 |  | A
036909C-1025-PDS-0800-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | A | 2018-10-23 | IFR | OL1-2G30-2508 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217 |  | A
036909C-1025-PDS-0800-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum | A | 2018-10-23 | IFR | OL1-2G30-2525 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1025-PDS-0800-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum | A | 2018-10-23 | IFR | OL1-2G30-2551 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1025-PDS-0800-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum | A | 2018-10-23 | IFR | OL1-2G30-2555 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1028-PDS-0800-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum | A | 2018-10-23 | IFR | OL1-2G30-2805 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1028-PDS-0800-2854 | Process Equipment Datasheet - 10-D-2855 - C2R Surge Drum | A | 2018-10-23 | IFR | OL1-2G30-2854 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1028-PDS-0800-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum | A | 2018-10-23 | IFR | OL1-2G30-2870 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1051-PDS-0900-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps | A | 2018-10-23 | IFR | OL1-2G30-5111 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219 |  | A
036909C-1051-PDS-0900-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps | A | 2018-10-23 | IFR | OL1-2G30-5121 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219 |  | A
036909C-1051-PDS-0900-5141 | Process Equipment Datasheet - 10-P-5140 A-B - Intermittent Blowdown Pumps | A | 2018-10-23 | IFR | OL1-2G30-5141 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219 |  | A
036909C-1028-PDS-0600-2858 | Process Equipment Datasheet - 10-E-2858 - HP Ethylene Product Superheater | A | 2018-10-23 | IFR | OL1-2G30-2858 | PE | 2018-10-24 | 036909C-JVD-TRN-00223 | 036909C-JVD-TRN-00223 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00223 |  | A
036909C-1010-PDS-0800-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum | A | 2018-10-25 | IFR | OL1-2G30-1000 | PE | 2018-10-25 | 036909C-JVD-TRN-00227 | 036909C-JVD-TRN-00227 | IFR | 2018-11-08 | 2018-12-05 | R1-No comments | TPSK-LSPA1-T-PE-00227 |  | A
036909C-1025-PDS-0800-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum | A | 2018-10-24 | IFR | OL1-2G30-2572 | PE | 2018-10-25 | 036909C-JVD-TRN-00227 | 036909C-JVD-TRN-00227 | IFR | 2018-11-08 | 2018-12-05 | R1-No comments | TPSK-LSPA1-T-PE-00227 |  | A
036909C-1024-PDS-0600-2455 | Process Equipment Datasheet - 10-E-2455 A-B - LP Depropanizer Reboilers | A | 2018-10-24 | IFR | OL1-2G30-2455 | PE | 2018-10-25 | 036909C-JVD-TRN-00228 | 036909C-JVD-TRN-00228 | IFR | 2018-11-08 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00228 |  | A
036909C-1000-NM-0014-0001 | Flare Load Summary | A | 2018-10-23 | IFR | OL1-2G22-0001 | PE | 2018-10-25 | 036909C-JVD-TRN-00229 | 036909C-JVD-TRN-00229 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00229 |  | A
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | A | 2018-10-25 | IFR | OL1-2G30-5113 | PE | 2018-10-25 | 036909C-JVD-TRN-00230 | 036909C-JVD-TRN-00230 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00230 |  | A
036909C-1051-PDS-0600-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | A | 2018-10-25 | IFR | OL1-2G30-5103 | PE | 2018-10-25 | 036909C-JVD-TRN-00230 | 036909C-JVD-TRN-00230 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00230 |  | A
036909C-1012-JSS-0191-2009 | Project Specification for Furnace Burners | A | 2018-10-15 | IFR | OL1-2M92-2009 | ME | 2018-10-25 | 036909C-JVD-TRN-00231 | 036909C-JVD-TRN-00231 | IFR | 2018-11-08 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00231 |  | A
036909C-1012-MR-0154-2003 | Material Requisition for Quench Exchangers | A | 2018-10-18 | IFQ | OL1-2M55-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00233 | 036909C-JVD-TRN-00233 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00233 |  | A
036909C-1012-SP-0154-2003 | Particular Techanical Specification for Quench Exchangers | A | 2018-10-18 | IFQ | OL1-2M57-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00233 | 036909C-JVD-TRN-00233 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00233 |  | A
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps 10-P-5110 A-B | A | 2018-10-25 | IFQ | OL1-2M03-5109 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235 |  | A
036909C-1021-SP-0910-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps 10-P-2146 A-B | A | 2018-10-25 | IFQ | OL1-2M03-2146 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235 |  | A
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet Quench Oil Pump 10-P-2006 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-2006 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235 |  | A
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps - 10-P-2106 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-2106 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236 |  | A
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet SHP BFW Pumps - 10-P-5100 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-5101 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236 |  | A
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet VLP BFW Pumps - 10-P-5102 A-B | A | 2018-10-25 | IFQ | OL1-2M03-5102 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236 |  | A
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1109 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1110 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1011-PDS-0630-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1108 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1209 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1012-PDS-0630-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1208 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1020-PDS-0500-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper | A | 2018-10-26 | IFR | OL1-2G30-2020 | PE | 2018-10-29 | 036909C-JVD-TRN-00238 | 036909C-JVD-TRN-00238 | IFR | 2018-11-12 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00238 |  | A
036909C-1021-PDS-0500-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | A | 2018-10-26 | IFR | OL1-2G30-2100 | PE | 2018-10-29 | 036909C-JVD-TRN-00238 | 036909C-JVD-TRN-00238 | IFR | 2018-11-12 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00238 |  | A
036909C-1024-PDS-0600-2406 | Process Equipment Datasheet - 10-E-2405 - Gas Dryer Feed Chiller | A | 2018-10-26 | IFR | OL1-2G30-2406 | PE | 2018-10-30 | 036909C-JVD-TRN-00239 | 036909C-JVD-TRN-00239 | IFR | 2018-11-12 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00239 |  | A
036909C-1024-PDS-0600-2412 | Process Equipment Datasheet - 10-E-2412 - HP Depropanizer Feed Chiller | A | 2018-10-26 | IFR | OL1-2G30-2412 | PE | 2018-10-30 | 036909C-JVD-TRN-00239 | 036909C-JVD-TRN-00239 | IFR | 2018-11-12 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00239 |  | A
036909C-1011-PDS-0191-1106 | Process Equipment Datasheet - 10-H-1100 - USC 36M Burner | A | 2018-10-26 | IFR | OL1-2G30-1106 | PE | 2018-10-30 | 036909C-JVD-TRN-00241 | 036909C-JVD-TRN-00241 | IFR | 2018-11-12 |  | Transmitted | TPSK-LSPA1-T-PE-00241 |  | A
036909C-1012-PDS-0191-1206 | Process Equipment Datasheet - 10-H-1200 - 1600 - USC 132U Burner | A | 2018-10-26 | IFR | OL1-2G30-1206 | PE | 2018-10-30 | 036909C-JVD-TRN-00241 | 036909C-JVD-TRN-00241 | IFR | 2018-11-12 |  | Transmitted | TPSK-LSPA1-T-PE-00241 |  | A
036909C-1051-PDS-0600-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler | A | 2018-10-29 | IFR | OL1-2G30-5108 | PE | 2018-10-30 | 036909C-JVD-TRN-00243 | 036909C-JVD-TRN-00243 | IFR | 2018-11-12 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00243 |  | A
036909C-1051-PDS-0600-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | A | 2018-10-26 | IFR | OL1-2G30-5107 | PE | 2018-10-30 | 036909C-JVD-TRN-00243 | 036909C-JVD-TRN-00243 | IFR | 2018-11-12 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00243 |  | A
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet Caustic Tower 10-T-2300 | A | 2018-10-26 | IFQ | OL1-2M03-2300 | ME | 2018-10-31 | 036909C-JVD-TRN-00246 | 036909C-JVD-TRN-00246 | IFR | 2018-11-13 | 2018-11-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00246 |  | A
036909C-1011-SP-1040-1001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 36M | A | 2018-10-30 | IFR | OL1-2M03-1001 | ME | 2018-10-31 | 036909C-JVD-TRN-00247 | 036909C-JVD-TRN-00247 | IFR | 2018-11-13 |  | Transmitted | TPSK-LSPA1-T-ME-00247 |  | A
036909C-1012-SP-1040-2001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 132U | A | 2018-10-29 | IFR | OL1-2M03-2001 | ME | 2018-10-31 | 036909C-JVD-TRN-00247 | 036909C-JVD-TRN-00247 | IFR | 2018-11-13 |  | Transmitted | TPSK-LSPA1-T-ME-00247 |  | A
036909C-1000-MR-4234-0001 | Material Requisition for Side Stream Filter Package | A | 2018-10-29 | IFQ | OL1-2M55-0109 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248 |  | A
036909C-1000-SP-4234-0001 | Particular Technical Specification for Side Steam Filter Package | A | 2018-10-29 | IFQ | OL1-2M57-0109 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248 |  | A
036909C-1000-SP-0910-0001 | Particular Technical Specification For API Centrifugal Pumps - LLI | A | 2018-10-30 | IFQ | OL1-2M57-0015 | ME | 2018-10-31 | 036909C-JVD-TRN-00257 | 036909C-JVD-TRN-00257 | IFR | 2018-11-20 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00257 |  | A
036909C-1024-PDS-0600-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | A | 2018-10-30 | IFR | OL1-2G30-2413 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser | A | 2018-10-30 | IFR | OL1-2G30-2439 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | A | 2018-10-30 | IFR | OL1-2G30-2441 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 | A | 2018-10-30 | IFR | OL1-2G30-2442 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler | A | 2018-10-30 | IFR | OL1-2G30-2446 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler | A | 2018-10-30 | IFR | OL1-2G30-2461 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1023-PDS-0900-2321 | Process Equipment Datasheet - 10-P-2320 A-B - Spent Caustic Pumps | A | 2018-10-29 | IFR | OL1-2G30-2321 | PE | 2018-10-31 | 036909C-JVD-TRN-00252 | 036909C-JVD-TRN-00252 | IFR | 2018-11-14 |  | Transmitted | TPSK-LSPA1-T-PE-00252 |  | A
036909C-1023-PDS-0900-2393 | Process Equipment Datasheet - 10-P-2392 - Spent Caustic Drain Drum Pump | A | 2018-10-29 | IFR | OL1-2G30-2393 | PE | 2018-10-31 | 036909C-JVD-TRN-00252 | 036909C-JVD-TRN-00252 | IFR | 2018-11-14 |  | Transmitted | TPSK-LSPA1-T-PE-00252 |  | A
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | A | 2018-10-29 | IFR | OL1-2G30-2120 | PE | 2018-10-31 | 036909C-JVD-TRN-00253 | 036909C-JVD-TRN-00253 | IFR | 2018-11-14 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00253 |  | A
036909C-1023-PDS-0800-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum | A | 2018-10-29 | IFR | OL1-2G30-2310 | PE | 2018-10-31 | 036909C-JVD-TRN-00254 | 036909C-JVD-TRN-00254 | IFR | 2018-11-14 |  | Transmitted | TPSK-LSPA1-T-PE-00254 |  | A
036909C-1023-PDS-0840-2319 | Process Equipment Datasheet - 10-F-2320 A-B - Spent Caustic Pump Discharge Filters | A | 2018-10-29 | IFR | OL1-2G30-2319 | PE | 2018-10-31 | 036909C-JVD-TRN-00255 | 036909C-JVD-TRN-00255 | IFR | 2018-11-14 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00255 |  | A
036909C-1000-SP-0845-0001 | Particular Technical Specification For Deaerator | A | 2018-10-29 | IFQ | OL1-2M57-0108 | ME | 2018-11-06 | 036909C-JVD-TRN-00270 | 036909C-JVD-TRN-00270 | IFR | 2018-11-20 | 2018-11-29 | Transmitted | TPSK-LSPA1-T-ME-00270 |  | A
036909C-1000-MR-0910-0001 | Material Requisition For API Centrifugal Pumps - LLI | A | 2018-10-30 | IFQ | OL1-2M55-0015 | ME | 2018-10-31 | 036909C-JVD-TRN-00257 | 036909C-JVD-TRN-00257 | IFR | 2018-11-20 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00257 |  | A
036909C-1023-PDS-0600-2305 | Process Equipment Datasheet - 10-E-2305 - Caustic Tower Feed Heater | A | 2018-10-31 | IFR | OL1-2G30-2305 | PE | 2018-10-31 | 036909C-JVD-TRN-00259 | 036909C-JVD-TRN-00259 | IFR | 2018-11-14 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00259 |  | A
036909C-1024-PDS-0600-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser | A | 2018-10-31 | IFR | OL1-2G30-2451 | PE | 2018-10-31 | 036909C-JVD-TRN-00259 | 036909C-JVD-TRN-00259 | IFR | 2018-11-14 | 2018-11-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-00259 |  | A
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator and Reflux Drum | A | 2018-10-29 | IFQ | OL1-2M03-2510 | ME | 2018-10-31 | 036909C-JVD-TRN-00260 | 036909C-JVD-TRN-00260 | IFR | 2018-11-14 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00260 |  | A
036909C-1012-MR-0155-2018 | Material Requisition for Furnace Steam Drums | A | 2018-11-01 | IFQ | OL1-2M55-2018 | ME | 2018-11-01 | 036909C-JVD-TRN-00263 | 036909C-JVD-TRN-00263 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00263 |  | A
036909C-1012-SP-0155-2018 | Particular Technical Specification for Furnace Steam Drums | A | 2018-11-01 | IFQ | OL1-2M57-2018 | ME | 2018-11-01 | 036909C-JVD-TRN-00263 | 036909C-JVD-TRN-00263 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00263 |  | A
036909C-1022-PDS-0800-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum | A | 2018-10-31 | IFR | OL1-2G30-2245 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00264 |  | A
036909C-1024-PDS-0800-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum | A | 2018-10-31 | IFR | OL1-2G30-2438 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-PE-00264 |  | A
036909C-1021-PDS-0600-2125 | Process Equipment Datasheet - 10-E-2125 - Distillate Stripper Reboiler | A | 2018-11-01 | IFR | OL1-2G30-2125 | PE | 2018-11-01 | 036909C-JVD-TRN-00265 | 036909C-JVD-TRN-00265 | IFR | 2018-11-15 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00265 |  | A
036909C-1024-PDS-0800-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum | A | 2018-10-31 | IFR | OL1-2G30-2452 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-PE-00264 |  | A
036909C-1025-PDS-0600-2582 | Process Equipment Datasheet - 10-E-2582 - C2 Tower Reflux Cooler | A | 2018-11-01 | IFR | OL1-2G30-2582 | PE | 2018-11-01 | 036909C-JVD-TRN-00265 | 036909C-JVD-TRN-00265 | IFR | 2018-11-15 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00265 |  | A
036909C-1022-PDS-0600-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | A | 2018-11-01 | IFR | OL1-2G30-2211 | PE | 2018-11-01 | 036909C-JVD-TRN-00266 | 036909C-JVD-TRN-00266 | IFR | 2018-11-15 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00266 |  | A
036909C-1024-PDS-0600-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers | A | 2018-11-01 | IFR | OL1-2G30-2445 | PE | 2018-11-01 | 036909C-JVD-TRN-00267 | 036909C-JVD-TRN-00267 | IFR | 2018-11-15 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00267 |  | A
036909C-1000-SP-4111-0001 | Particular Technical Specification For Hydrogen Production Unit | A | 2018-10-26 | IFQ | OL1-2M57-0114 | ME | 2018-11-06 | 036909C-JVD-TRN-00271 | 036909C-JVD-TRN-00271 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-ME-00271 |  | A
036909C-1000-SP-0570-0004 | Particular Technical Specification For MD Trays For Columns | A | 2018-10-31 | IFQ | OL1-2M57-0075 | ME | 2018-11-07 | 036909C-JVD-TRN-00278 | 036909C-JVD-TRN-00278 | IFR | 2018-11-21 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00278 |  | A
036909C-1012-MR-1040-2005 | Material Requisition for Furnace ID Fans | A | 2018-11-01 | IFQ | OL1-2M55-2005 | ME | 2018-11-05 | 036909C-JVD-TRN-00269 | 036909C-JVD-TRN-00269 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00269 |  | A
036909C-1012-SP-1040-2005 | Particular Technical Specification for Furnace ID Fans | A | 2018-11-01 | IFQ | OL1-2M57-2005 | ME | 2018-11-05 | 036909C-JVD-TRN-00269 | 036909C-JVD-TRN-00269 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00269 |  | A
036909C-1000-MR-4111-0001 | Material Requisition for Hydrogen Production Unit | A | 2018-10-26 | IFQ | OL1-2M55-0114 | ME | 2018-11-06 | 036909C-JVD-TRN-00271 | 036909C-JVD-TRN-00271 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-ME-00271 |  | A
036909C-1000-MR-0845-0001 | Material Requisition for Deareator | A | 2018-10-29 | IFQ | OL1-2M55-0108 | ME | 2018-11-06 | 036909C-JVD-TRN-00270 | 036909C-JVD-TRN-00270 | IFR | 2018-11-20 | 2018-11-29 | Transmitted | TPSK-LSPA1-T-ME-00270 |  | A
036909C-1051-PDS-0800-5112 | Process Equipment Datasheet - 10-D-5112 - Suspect Condensate Flash Drum | A | 2018-11-05 | IFR | OL1-2G30-5112 | PE | 2018-11-05 | 036909C-JVD-TRN-00274 | 036909C-JVD-TRN-00274 | IFR | 2018-11-21 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00274 |  | A
036909C-1051-PDS-0800-5114 | Process Equipment Datasheet - 10-D-5114 - LP Condensate Flash Drum | A | 2018-11-05 | IFR | OL1-2G30-5114 | PE | 2018-11-05 | 036909C-JVD-TRN-00274 | 036909C-JVD-TRN-00274 | IFR | 2018-11-21 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00274 |  | A
036909C-1052-PDS-0600-5201 | Process Equipment Datasheet - 10-E-5200 - MP Ethylene Superheater | A | 2018-11-05 | IFR | OL1-2G30-5201 | PE | 2018-11-05 | 036909C-JVD-TRN-00275 | 036909C-JVD-TRN-00275 | IFR | 2018-11-19 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-PE-00275 |  | A
036909C-1000-JSS-0310-0001 | ME-008 Cooling Water | A | 2018-10-30 | IFQ | OL1-2R03-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 |  | Transmitted | TPSK-LSPA1-T-ME-00276 |  | A
036909C-1000-MR-0310-0001 | Material Requisition for Cooling Tower | A | 2018-10-30 | IFQ | OL1-2M55-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 |  | Transmitted | TPSK-LSPA1-T-ME-00276 |  | A
036909C-1000-SP-0310-0001 | Particular Technical Specification for Cooling Tower | A | 2018-10-30 | IFQ | OL1-2M57-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 |  | Transmitted | TPSK-LSPA1-T-ME-00276 |  | A
036909C-1026-PDS-0900-2633 | Process Equipment Datasheet - 10-P-2630 A-B - Secondary Deeth Reflux Pumps | A | 2018-11-05 | IFR | OL1-2G30-2633 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-PE-00277 |  | A
036909C-1026-PDS-0900-2646 | Process Equipment Datasheet - 10-P-2646 A-B - Propane Recycle Pumps | A | 2018-11-05 | IFR | OL1-2G30-2646 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-PE-00277 |  | A
036909C-1028-PDS-0900-2801 | Process Equipment Datasheet - 10-P-2805 A-B - Propylene Product Pumps | A | 2018-11-05 | IFR | OL1-2G30-2801 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-PE-00277 |  | A
036909C-1000-MR-0570-0004 | Material Requisition For MD Trays For Columns Requisition For Inquiry | A | 2018-10-31 | IFQ | OL1-2M55-0075 | ME | 2018-11-07 | 036909C-JVD-TRN-00278 | 036909C-JVD-TRN-00278 | IFR | 2018-11-21 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00278 |  | A
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | A | 2018-11-06 | IFR | OL1-2G30-5644 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281 |  | A
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | A | 2018-11-06 | IFR | OL1-2G30-5650 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281 |  | A
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | A | 2018-11-06 | IFR | OL1-2G30-5653 | PE | 2018-11-06 | 036909C-JVD-TRN-00282 | 036909C-JVD-TRN-00282 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00282 |  | A
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | A | 2018-11-06 | IFR | OL1-2G30-5670 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281 |  | A
036909C-1000-SP-0570-0001 | Particular Technical Specification For Trays For Columns | A | 2018-11-06 | IFQ | OL1-2M57-0055 | ME | 2018-11-09 | 036909C-JVD-TRN-00300 | 036909C-JVD-TRN-00300 | IFR | 2018-11-26 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00300 |  | A
036909C-1020-PDS-0900-2024 | Process Equipment Datasheet - 10-P-2026 A-B - Light Fuel Oil Pumps | A | 2018-11-06 | IFR | OL1-2G30-2024 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1020-PDS-0900-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps | A | 2018-11-06 | IFR | OL1-2G30-2046 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1021-PDS-0900-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps | A | 2018-11-06 | IFR | OL1-2G30-2105 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1022-PDS-0900-2212 | Process Equipment Datasheet - 10-P-2210 A-B - CG 1st Stage Condensate Pumps | A | 2018-11-06 | IFR | OL1-2G30-2212 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1022-PDS-0900-2222 | Process Equipment Datasheet - 10-P-2220 A-B - CG 2nd Stage Condensed HC Pumps | A | 2018-11-06 | IFR | OL1-2G30-2222 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1024-PDS-0900-2416 | Process Equipment Datasheet - 10-P-2415 A-B - CG Liquid Dryer Feed Pumps | A | 2018-11-06 | IFR | OL1-2G30-2416 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1024-PDS-0900-2453 | Process Equipment Datasheet - 10-P-2450 A-B - LP Depropanizer Reflux-Product Pump | A | 2018-11-06 | IFR | OL1-2G30-2453 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1000-MSD-0011-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes | A | 2018-11-02 | IFA | OL1-2G74-0001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1010-MSD-0011-1001 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | 2018-11-02 | IFA | OL1-2G74-1001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1010-MSD-0011-1003 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | 2018-11-02 | IFA | OL1-2G74-1003 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1011-MSD-0011-1101 | Material Selection Diagram - Olefins Unit 10 - 11 - Furnaces - Gas Cracking Furnace | A | 2018-11-02 | IFA | OL1-2G74-1101 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1012-MSD-0011-1201 | Material Selection Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | 2018-11-02 | IFA | OL1-2G74-1201 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1019-MSD-0011-1901 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | 2018-11-02 | IFA | OL1-2G74-1901 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1019-MSD-0011-1902 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | 2018-11-02 | IFA | OL1-2G74-1902 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1020-MSD-0011-2001 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | 2018-11-02 | IFA | OL1-2G74-2001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1020-MSD-0011-2002 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-11-02 | IFA | OL1-2G74-2002 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1021-MSD-0011-2101 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | 2018-11-02 | IFA | OL1-2G74-2101 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1021-MSD-0011-2102 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | 2018-11-02 | IFA | OL1-2G74-2102 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1021-MSD-0011-2103 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | 2018-11-02 | IFA | OL1-2G74-2103 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1022-MSD-0011-2201 | Material Selection Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | 2018-11-02 | IFA | OL1-2G74-2201 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2301 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | 2018-11-02 | IFA | OL1-2G74-2301 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2302 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | 2018-11-02 | IFA | OL1-2G74-2302 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2303 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | 2018-11-02 | IFA | OL1-2G74-2303 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2304 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | 2018-11-02 | IFA | OL1-2G74-2304 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2305 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | 2018-11-02 | IFA | OL1-2G74-2305 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2401 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | 2018-11-02 | IFA | OL1-2G74-2401 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2402 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | 2018-11-02 | IFA | OL1-2G74-2402 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2403 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | 2018-11-02 | IFA | OL1-2G74-2403 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2404 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | 2018-11-02 | IFA | OL1-2G74-2404 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2405 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | 2018-11-02 | IFA | OL1-2G74-2405 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2501 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | 2018-11-02 | IFA | OL1-2G74-2501 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2502 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | 2018-11-02 | IFA | OL1-2G74-2502 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2503 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | 2018-11-02 | IFA | OL1-2G74-2503 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2504 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | 2018-11-02 | IFA | OL1-2G74-2504 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2505 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | 2018-11-02 | IFA | OL1-2G74-2505 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2506 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | 2018-11-02 | IFA | OL1-2G74-2506 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1026-MSD-0011-2601 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | 2018-11-02 | IFA | OL1-2G74-2601 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1026-MSD-0011-2602 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | 2018-11-02 | IFA | OL1-2G74-2602 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1026-MSD-0011-2603 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | 2018-11-02 | IFA | OL1-2G74-2603 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1026-MSD-0011-2604 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | 2018-11-02 | IFA | OL1-2G74-2604 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1028-MSD-0011-2801 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | 2018-11-02 | IFA | OL1-2G74-2801 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1028-MSD-0011-2802 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | 2018-11-02 | IFA | OL1-2G74-2802 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1028-MSD-0011-2803 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | 2018-11-02 | IFA | OL1-2G74-2803 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1028-MSD-0011-2804 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | 2018-11-02 | IFA | OL1-2G74-2804 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1029-MSD-0011-2901 | Material Selection Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | 2018-11-02 | IFA | OL1-2G74-2901 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1026-PDS-0800-2662 | Process Equipment Datasheet - 10-D-2660 - Debutanizer Reflux Drum | A | 2018-11-07 | IFR | OL1-2G30-2662 | PE | 2018-11-07 | 036909C-JVD-TRN-00287 | 036909C-JVD-TRN-00287 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00287 |  | A
036909C-1026-PDS-0800-2632 | Process Equipment Datasheet - 10-D-2630 - Secondary Deeth Reflux Drum | A | 2018-11-07 | IFR | OL1-2G30-2632 | PE | 2018-11-07 | 036909C-JVD-TRN-00287 | 036909C-JVD-TRN-00287 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00287 |  | A
036909C-1000-JSD-1580-0002 | Progammable Logic Controller | A | 2018-11-07 | IFR | OL1-2R06-1301 | IE | 2018-11-08 | 036909C-JVD-TRN-00291 | 036909C-JVD-TRN-00291 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-IE-00291 |  | A
036909C-1000-MR-0570-0001 | Material Requisition For Trays For Columns Requisition For Inquiry | A | 2018-11-06 | IFQ | OL1-2M55-0055 | ME | 2018-11-09 | 036909C-JVD-TRN-00300 | 036909C-JVD-TRN-00300 | IFR | 2018-11-26 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00300 |  | A
036909C-1024-SP-0910-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux-Product Pump | A | 2018-11-08 | IFQ | OL1-2M03-2453 | ME | 2018-11-08 | 036909C-JVD-TRN-00294 | 036909C-JVD-TRN-00294 | IFR | 2018-11-22 |  | Transmitted | TPSK-LSPA1-T-ME-00294 |  | A
036909C-1020-PDS-0600-2026 | Process Equipment Datasheet - 10-E-2026 - FO Product Cooler | A | 2018-11-08 | IFR | OL1-2G30-2026 | PE | 2018-11-09 | 036909C-JVD-TRN-00298 | 036909C-JVD-TRN-00298 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PE-00298 |  | A
036909C-1020-PDS-0600-2048 | Process Equipment Datasheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | A | 2018-11-08 | IFR | OL1-2G30-2048 | PE | 2018-11-09 | 036909C-JVD-TRN-00298 | 036909C-JVD-TRN-00298 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PE-00298 |  | A
036909C-1024-PDS-0400-2470 | Process Equipment Datasheet - 10-R-2470 A-C - C2 Hydrog Reactor | A | 2018-11-08 | IFR | OL1-2G30-2470 | PE | 2018-11-09 | 036909C-JVD-TRN-00299 | 036909C-JVD-TRN-00299 | IFR | 2018-11-23 | 2018-11-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-00299 |  | A
036909C-1024-PDS-0800-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer | A | 2018-11-08 | IFR | OL1-2G30-2420 | PE | 2018-11-09 | 036909C-JVD-TRN-00301 | 036909C-JVD-TRN-00301 | IFR | 2018-11-23 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00301 |  | A
036909C-1026-PDS-0900-2647 | Process Equipment Datasheet - 10-P-2647 - HP Propylene - Off Spec Pumps | A | 2018-11-08 | IFR | OL1-2G30-2647 | PE | 2018-11-09 | 036909C-JVD-TRN-00302 | 036909C-JVD-TRN-00302 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PE-00302 |  | A
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum | A | 2018-11-09 | IFQ | OL1-2M03-2540 | ME | 2018-11-09 | 036909C-JVD-TRN-00304 | 036909C-JVD-TRN-00304 | IFR | 2018-11-23 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00304 |  | A
036909C-1020-PDS-0600-2015 | Process Equipment Datasheet - 10-E-2008 A-C - LS2 Steam Generators | A | 2018-11-09 | IFR | OL1-2G30-2015 | PE | 2018-11-09 | 036909C-JVD-TRN-00305 | 036909C-JVD-TRN-00305 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PE-00305 |  | A
036909C-1026-DI-0007-2602 | Area Basis of Design - 262 C3 Hydrogenation | A | 2018-11-09 | IFA | OL1-2G05-2602 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307 | IFA | 2018-11-26 |  | Transmitted | TPSK-LSPA1-T-PE-00307 |  | A
036909C-1027-DI-0007-2702 | Area Basis of Design - Area 275 C4-C5 Hydrogenation | A | 2018-11-09 | IFA | OL1-2G05-2702 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307 | IFA | 2018-11-26 |  | Transmitted | TPSK-LSPA1-T-PE-00307 |  | A
036909C-1027-DI-0007-2701 | Area Basis of Design - 270 Gasoline Hydrogenation -GHU-1 | A | 2018-11-09 | IFA | OL1-2G05-2701 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307 | IFA | 2018-11-26 |  | Transmitted | TPSK-LSPA1-T-PE-00307 |  | A
036909C-1000-JSS-0910-0002 | ME-050 Centrifugal Pump (Non API) | A | 2018-10-25 | IFR | OL1-2R03-0500 | ME | 2018-11-12 | 036909C-JVD-TRN-00308 | 036909C-JVD-TRN-00308 | IFR | 2018-11-27 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00308 |  | A
036909C-1025-TDS-0610-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser | A | 2018-11-12 | IFQ | OL1-2M03-2571 | ME | 2018-11-13 | 036909C-JVD-TRN-00310 | 036909C-JVD-TRN-00310 | IFR | 2018-11-27 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00310 |  | A
036909C-1028-TDS-0610-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | 2018-11-13 | IFQ | OL1-2M03-2857 | ME | 2018-11-13 | 036909C-JVD-TRN-00312 | 036909C-JVD-TRN-00312 | IFR | 2018-11-27 |  | Transmitted | TPSK-LSPA1-T-ME-00312 |  | A
036909C-1012-MR-0191-2006 | Material Requisition for Furnace Burners | A | 2018-11-07 | IFQ | OL1-2M55-2006 | ME | 2018-11-13 | 036909C-JVD-TRN-00313 | 036909C-JVD-TRN-00313 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00313 |  | A
036909C-1012-SP-0191-2006 | Particular Technical Specification for Furnace Burners | A | 2018-11-07 | IFQ | OL1-2M57-2006 | ME | 2018-11-13 | 036909C-JVD-TRN-00313 | 036909C-JVD-TRN-00313 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00313 |  | A
036909C-1024-PDS-0800-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum | A | 2018-11-13 | IFR | OL1-2G30-2405 | PE | 2018-11-14 | 036909C-JVD-TRN-00315 | 036909C-JVD-TRN-00315 | IFR | 2018-11-28 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00315 |  | A
036909C-1028-TDS-0610-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | 2018-11-14 | IFQ | OL1-2M03-2856 | ME | 2018-11-14 | 036909C-JVD-TRN-00316 | 036909C-JVD-TRN-00316 | IFR | 2018-11-28 |  | Transmitted | TPSK-LSPA1-T-ME-00316 |  | A
036909C-1023-SP-0910-2302 | Mechanical Equipment Datasheet - Strong Caustic Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2302 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | A
036909C-1023-SP-0910-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump | A | 2018-11-13 | IFQ | OL1-2M03-2304 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | A
036909C-1023-SP-0910-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2306 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | A
036909C-1023-SP-0910-2311 | Mechanical Equipment Datasheet - Wash Oil Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2311 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | A
036909C-1000-MR-0910-0003 | Material Requisition for Cooling Water Pumps | A | 2018-11-14 | IFQ | OL1-2M55-0003 | ME | 2018-11-15 | 036909C-JVD-TRN-00319 | 036909C-JVD-TRN-00319 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00319 |  | A
036909C-1000-SP-0910-0003 | Particular Technical Specification for Cooling Water Pumps | A | 2018-11-14 | IFQ | OL1-2M57-0003 | ME | 2018-11-15 | 036909C-JVD-TRN-00319 | 036909C-JVD-TRN-00319 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00319 |  | A
036909C-1052-PDS-0600-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer | A | 2018-11-14 | IFR | OL1-2G30-5210 | PE | 2018-11-15 | 036909C-JVD-TRN-00321 | 036909C-JVD-TRN-00321 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00321 |  | A
036909C-1000-PID-0090-0001 | P&ID - Olefins Unit 10 - Common - Abbreviations And Numbering | A | 2018-11-15 | IFR | OL1-2G43-0001 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0002 | P&ID - Olefins Unit 10 - Common - Piping Symbols | A | 2018-11-15 | IFR | OL1-2G43-0002 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0003 | P&ID - Olefins Unit 10 - Common - Instrumentation Symbols | A | 2018-11-15 | IFR | OL1-2G43-0003 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0004 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 1 | A | 2018-11-15 | IFR | OL1-2G43-0004 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0005 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 2 | A | 2018-11-15 | IFR | OL1-2G43-0005 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0010 | P&ID - Olefins Unit 10 - Common - Instrument Details | A | 2018-11-15 | IFR | OL1-2G43-0010 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0011 | P&ID - Olefins Unit 10 - Common - EIV Block Valves Typical | A | 2018-11-15 | IFR | OL1-2G43-0011 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1101 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1105 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1106 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1107 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1108 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1109 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed-Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1110 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1111 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1112 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section | A | 2018-11-15 | IFR | OL1-2G43-1115 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1116 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1117 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1118 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1119 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1120 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1121 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers | A | 2018-11-15 | IFR | OL1-2G43-1125 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent And Decoke MOVs | A | 2018-11-15 | IFR | OL1-2G43-1126 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header | A | 2018-11-15 | IFR | OL1-2G43-1127 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - SHP Steam Drum | A | 2018-11-15 | IFR | OL1-2G43-1128 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers | A | 2018-11-15 | IFR | OL1-2G43-1129 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply Export Steam | A | 2018-11-15 | IFR | OL1-2G43-1130 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils | A | 2018-11-15 | IFR | OL1-2G43-1131 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1135 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners | A | 2018-11-15 | IFR | OL1-2G43-1140 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent | A | 2018-11-15 | IFR | OL1-2G43-1145 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas | A | 2018-11-15 | IFR | OL1-2G43-1150 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1201 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1202 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1205 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1206 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1207 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1208 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1209 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1210 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1211 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1212 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section | A | 2018-11-15 | IFR | OL1-2G43-1215 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1216 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1217 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1218 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1219 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1220 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1221 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger | A | 2018-11-15 | IFR | OL1-2G43-1225 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV's | A | 2018-11-15 | IFR | OL1-2G43-1226 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SLE Drain Header | A | 2018-11-15 | IFR | OL1-2G43-1227 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - VHP Steam Drum | A | 2018-11-15 | IFR | OL1-2G43-1228 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-SLE And TLX Risers | A | 2018-11-15 | IFR | OL1-2G43-1229 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply Export Steam | A | 2018-11-15 | IFR | OL1-2G43-1230 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils | A | 2018-11-15 | IFR | OL1-2G43-1231 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1235 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners | A | 2018-11-15 | IFR | OL1-2G43-1240 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas | A | 2018-11-15 | IFR | OL1-2G43-1245 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1250 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-JSD-1300-0008 | JSD For Piping Stress Analysis | A | 2018-11-12 | IFR | OL1-2R04-0032 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-MP-00324 |  | A
036909C-1000-JSD-1300-0009 | JSD for piping loads on PRK SLW STR IS | A | 2018-11-12 | IFR | OL1-2R04-0033 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-MP-00324 |  | A
036909C-1000-JSD-1300-0010 | JSD For Auxiliary Piping Supports | A | 2018-11-12 | IFR | OL1-2R04-0034 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-MP-00324 |  | A
036909C-1000-JSD-1300-0012 | Pipe Support | A | 2018-11-12 | IFR | OL1-2R04-0012 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-MP-00324 |  | A
036909C-1011-DW-0117-1001 | USC 36M Recycle Furnace General Arrangement Cross Section Elevation | A | 2018-11-15 | IFR | OL1-2M06-1001 | ME | 2018-11-16 | 036909C-JVD-TRN-00327 | 036909C-JVD-TRN-00327 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00327 |  | A
036909C-1011-DW-0117-1002 | USC 36M Recycle Furnace General Arrangement Longitudinal Elevation | A | 2018-11-15 | IFR | OL1-2M06-1002 | ME | 2018-11-16 | 036909C-JVD-TRN-00327 | 036909C-JVD-TRN-00327 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00327 |  | A
036909C-1012-DW-0117-2001 | USC 132U Cracking Furnace General Arrangement Cross Section Elevation | A | 2018-11-15 | IFR | OL1-2M06-2001 | ME | 2018-11-16 | 036909C-JVD-TRN-00328 | 036909C-JVD-TRN-00328 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00328 |  | A
036909C-1012-DW-0117-2002 | USC 132U Cracking Furnace General Arrangement Longitudinal Elevation | A | 2018-11-15 | IFR | OL1-2M06-2002 | ME | 2018-11-16 | 036909C-JVD-TRN-00328 | 036909C-JVD-TRN-00328 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00328 |  | A
036909C-1012-SP-0125-2007 | Particular Technical Specification for Cast Intermediate Tube Supports | A | 2018-11-12 | IFQ | OL1-2M57-2007 | ME | 2018-11-16 | 036909C-JVD-TRN-00329 | 036909C-JVD-TRN-00329 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00329 |  | A
036909C-1012-MR-0125-2007 | Material Requisition for Cast Intermediate Tube Supports | A | 2018-11-12 | IFQ | OL1-2M55-2007 | ME | 2018-11-16 | 036909C-JVD-TRN-00329 | 036909C-JVD-TRN-00329 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00329 |  | A
036909C-1011-PDS-0853-1112 | Process Equipment Datasheet - 10-M-1100 - USC 36M Attemperator | A | 2018-11-14 | IFR | OL1-2G30-1112 | PE | 2018-11-16 | 036909C-JVD-TRN-00330 | 036909C-JVD-TRN-00330 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-PE-00330 |  | A
036909C-1012-PDS-0853-1212 | Process Equipment Datasheet - 10-M-1200 1600 - USC 132U Attemperator | A | 2018-11-14 | IFR | OL1-2G30-1212 | PE | 2018-11-16 | 036909C-JVD-TRN-00330 | 036909C-JVD-TRN-00330 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-PE-00330 |  | A
036909C-1051-PDS-0800-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum | A | 2018-11-15 | IFR | OL1-2G30-5140 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331 |  | A
036909C-1051-PDS-0800-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum | A | 2018-11-15 | IFR | OL1-2G30-5150 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331 |  | A
036909C-1052-PDS-0800-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum | A | 2018-11-15 | IFR | OL1-2G30-5200 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331 |  | A
036909C-1055-PDS-1000-5521 | Process Equipment Datasheet - 10-PK-5520 - LP Vent Blower Pkg | A | 2018-11-15 | IFR | OL1-2G30-5521 | PE | 2018-11-19 | 036909C-JVD-TRN-00332 | 036909C-JVD-TRN-00332 | IFR | 2018-12-03 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-PE-00332 |  | A
036909C-1023-SP-0910-2321 | Mechanical Equipment Datasheet - Spent Caustic Pumps | A | 2018-11-16 | IFQ | OL1-2M03-2321 | ME | 2018-11-19 | 036909C-JVD-TRN-00335 | 036909C-JVD-TRN-00335 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-ME-00335 |  | A
036909C-1051-SP-0910-5141 | Mechanical Equipment Datasheet - Intermittent Blowdown Pumps | A | 2018-11-16 | IFQ | OL1-2M03-5141 | ME | 2018-11-19 | 036909C-JVD-TRN-00335 | 036909C-JVD-TRN-00335 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-ME-00335 |  | A
036909C-1000-JSD-1300-0011 | Piping Flexibility | A | 2018-11-19 | IFR | OL1-2R04-0030 | MP | 2018-11-20 | 036909C-JVD-TRN-00336 | 036909C-JVD-TRN-00336 | IFR | 2018-12-05 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00336 |  | A
036909C-1020-PDS-4200-2036 | Process Equipment Datasheet - 10-X-2036 - Quench Fitting | A | 2018-11-19 | IFR | OL1-2G30-2036 | PE | 2018-11-20 | 036909C-JVD-TRN-00338 | 036909C-JVD-TRN-00338 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-PE-00338 |  | A
036909C-1024-PDS-0800-2411 | Process Equipment Datasheet - 10-D-2411 - Cracked Gas Mercury Adsorber | A | 2018-11-19 | IFR | OL1-2G30-2411 | PE | 2018-11-20 | 036909C-JVD-TRN-00339 | 036909C-JVD-TRN-00339 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-PE-00339 |  | A
036909C-1024-PDS-0800-2415 | Process Equipment Datasheet - 10-D-2415 - CG Liquid Dryer Feed Coalescer | A | 2018-11-19 | IFR | OL1-2G30-2415 | PE | 2018-11-20 | 036909C-JVD-TRN-00339 | 036909C-JVD-TRN-00339 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-PE-00339 |  | A
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | A | 2018-11-14 | IFR | OL1-2G30-2663 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00340 |  | A
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | A | 2018-11-14 | IFR | OL1-2G30-2816 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340 |  | A
036909C-1025-PDS-0900-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps | A | 2018-11-14 | IFR | OL1-2G30-2573 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340 |  | A
036909C-1025-PDS-0900-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps | A | 2018-11-14 | IFR | OL1-2G30-2586 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340 |  | A
036909C-1051-SP-0910-5111 | Mechanical Equipment Datasheet - Suspect Condensate Pumps | A | 2018-11-20 | IFQ | OL1-2M03-5111 | ME | 2018-11-20 | 036909C-JVD-TRN-00341 | 036909C-JVD-TRN-00341 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-ME-00341 |  | A
036909C-1051-SP-0910-5121 | Mechanical Equipment Datasheet - Raw Condensate Pumps | A | 2018-11-20 | IFQ | OL1-2M03-5121 | ME | 2018-11-20 | 036909C-JVD-TRN-00341 | 036909C-JVD-TRN-00341 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-ME-00341 |  | A
036909C-1022-SP-0910-2222 | Mechanical Equipment Datasheet - CG 2nd Stage Condensed HC Pump | A | 2018-11-16 | IFQ | OL1-2M03-2222 | ME | 2018-11-20 | 036909C-JVD-TRN-00343 | 036909C-JVD-TRN-00343 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-ME-00343 |  | A
036909C-1030-PDS-1000-3073 | Process Equipment Data Sheet - 10-C-3070 - BDU Recycle Gas Compressor | A | 2018-11-20 | IFR | OL1-2G30-3073 | PE | 2018-11-20 | 036909C-JVD-TRN-00344 | 036909C-JVD-TRN-00344 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-PE-00344 |  | A
036909C-1026-PDS-0800-2610 | Process Equipment Datasheet - 10-D-2610 - C3 Hydrog Arsine Guard Bed | A | 2018-11-20 | IFR | OL1-2G30-2610 | PE | 2018-11-21 | 036909C-JVD-TRN-00345 | 036909C-JVD-TRN-00345 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00345 |  | A
036909C-1021-PDS-0900-2191 | Process Equipment Datasheet - 10-P-2190- Quench Water Drain Drum Pump | A | 2018-11-20 | IFR | OL1-2G30-2191 | PE | 2018-11-21 | 036909C-JVD-TRN-00346 | 036909C-JVD-TRN-00346 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00346 |  | A
036909C-1020-PDS-0840-2010 | Process Equipment Datasheet - 10-F-2008 A-C Quench Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2010 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1020-PDS-0840-2014 | Process Equipment Datasheet - 10-F-2009 A-B QO Pump Purge Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2014 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1020-PDS-0840-2025 | Process Equipment Datasheet - 10-F-2026 A-B Cracker Bottoms Product Filter | A | 2018-11-21 | IFR | OL1-2G30-2025 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1020-PDS-0840-2028 | Process Equipment Datasheet - 10-F-2028 A-B - FO Pump Purge Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2028 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1020-PDS-0840-2049 | Process Equipment Datasheet - 10-F-2048 A-B Heavy Fuel Oil Filters | A | 2018-11-21 | IFR | OL1-2G30-2049 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1021-PDS-0840-2104 | Process Equipment Datasheet - 10-F-2105 A-B Quench Oil Reflux Filter | A | 2018-11-21 | IFR | OL1-2G30-2104 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1021-PDS-0840-2138 | Process Equipment Datasheet - 10-F-2136 A-B Process Water Feed Filters | A | 2018-11-21 | IFR | OL1-2G30-2138 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1000-JSS-1310-0004 | Job Supply Specification For Butterfly Valves | A | 2018-11-20 | IFR | OL1-2R04-0008 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-MP-00352 |  | A
036909C-1000-JSS-1310-0006 | Job Supply Specification For Plug Valves | A | 2018-11-20 | IFR | OL1-2R04-0009 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-MP-00352 |  | A
036909C-1000-JSS-1310-0008 | Job Supply Specification For Ball Valves | A | 2018-11-20 | IFR | OL1-2R04-0010 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-MP-00352 |  | A
036909C-1000-JSS-1310-0001 | Job Supply Specification For Valves (Gate - Globe - Check) | A | 2018-11-20 | IFR | OL1-2R04-0041 | MP | 2018-11-26 | 036909C-JVD-TRN-00356 | 036909C-JVD-TRN-00356 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-MP-00356 |  | A
036909C-1000-JSD-1511-0002 | Integrated Control And Safety System | A | 2018-11-20 | IFR | OL1-2R06-0015 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-IE-00357 |  | A
036909C-1000-JSD-1572-0003 | Instrument Air Supply | A | 2018-11-20 | IFR | OL1-2R06-0011 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-IE-00357 |  | A
036909C-1000-JSD-1584-0001 | Custody Transfer System | A | 2018-11-20 | IFR | OL1-2R06-3101 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-IE-00357 |  | A
036909C-1000-SP-1691-0001 | Particular Technical Specification For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E57-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00359 | 036909C-JVD-TRN-00359 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-EE-00359 |  | A
036909C-1000-SP-1691-0100 | Typical Data Sheet for LV Motors | A | 2018-11-16 | IFQ | OL1-2E05-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00358 | 036909C-JVD-TRN-00358 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-EE-00358 |  | A
036909C-1000-SP-1691-0500 | Typical Data Sheet For Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E05-3500 | EE | 2018-11-26 | 036909C-JVD-TRN-00358 | 036909C-JVD-TRN-00358 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-EE-00358 |  | A
036909C-1000-MR-1691-0001 | Material Requisition For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E55-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00359 | 036909C-JVD-TRN-00359 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-EE-00359 |  | A
036909C-1026-TDS-0610-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | A | 2018-11-19 | IFQ | OL1-2M03-2645 | ME | 2018-11-26 | 036909C-JVD-TRN-00361 | 036909C-JVD-TRN-00361 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-ME-00361 |  | A
036909C-1051-PDS-0200-5115 | Process Equipment Datasheet - 10-PK-5115 - Condensate Carbon Filter Pkg | A | 2018-11-16 | IFR | OL1-2G30-5115 | PE | 2018-11-26 | 036909C-JVD-TRN-00362 | 036909C-JVD-TRN-00362 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-PE-00362 |  | A
036909C-1051-PDS-2500-5120 | Process Equipment Datasheet - 10-TK-5120 - Raw Condensate Tank | A | 2018-11-16 | IFR | OL1-2G30-5120 | PE | 2018-11-26 | 036909C-JVD-TRN-00364 | 036909C-JVD-TRN-00364 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-PE-00364 |  | A
036909C-1055-PDS-0800-5520 | Process Equipment Datasheet - 10-D-5520 - Vent Collection Drum | A | 2018-11-16 | IFR | OL1-2G30-5520 | PE | 2018-11-26 | 036909C-JVD-TRN-00365 | 036909C-JVD-TRN-00365 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-PE-00365 |  | A
036909C-1059-PDS-2500-5900 | Process Equipment Datasheet - 10-TK-5900 - Sulfuric Acid Tank | A | 2018-11-16 | IFR | OL1-2G30-5900 | PE | 2018-11-26 | 036909C-JVD-TRN-00364 | 036909C-JVD-TRN-00364 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-PE-00364 |  | A
036909C-1000-MR-4100-0001 | Material Requisition for Wet Air Oxidation Package | A | 2018-11-22 | IFQ | OL1-2M55-0103 | ME | 2018-11-27 | 036909C-JVD-TRN-00367 | 036909C-JVD-TRN-00367 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-ME-00367 |  | A
036909C-1020-PDS-0800-2090 | Process Equipment Datasheet - 10-D-2090 - Quench Oil Drain Drum | A | 2018-11-26 | IFR | OL1-2G30-2090 | PE | 2018-11-27 | 036909C-JVD-TRN-00368 | 036909C-JVD-TRN-00368 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00368 |  | A
036909C-1021-PDS-0800-2190 | Process Equipment Datasheet - 10-D-2190 - Quench Water Drain Drum | A | 2018-11-26 | IFR | OL1-2G30-2190 | PE | 2018-11-27 | 036909C-JVD-TRN-00368 | 036909C-JVD-TRN-00368 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00368 |  | A
036909C-1020-PDS-0900-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps | A | 2018-11-26 | IFR | OL1-2G30-2091 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00371 |  | A
036909C-1021-PDS-0900-2126 | Process Equipment Datasheet - 10-P-2126 A-B - Distillate Stripper Bottom Pumps | A | 2018-11-26 | IFR | OL1-2G30-2126 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00371 |  | A
036909C-1026-PDS-0900-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps | A | 2018-11-26 | IFR | OL1-2G30-2669 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00371 |  | A
036909C-1051-PDS-0200-5125 | Process Equipment Datasheet - 10-PK-5125 - Condensate Polisher Pkg | A | 2018-11-27 | IFR | OL1-2G30-5125 | PE | 2018-11-27 | 036909C-JVD-TRN-00373 | 036909C-JVD-TRN-00373 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00373 |  | A
036909C-1051-PDS-2500-5110 | Process Equipment Datasheet - 10-TK-5110 - Condensate Tank | A | 2018-11-27 | IFR | OL1-2G30-5110 | PE | 2018-11-27 | 036909C-JVD-TRN-00374 | 036909C-JVD-TRN-00374 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00374 |  | A
036909C-1053-PDS-2600-5390 | Process Equipment Datasheet - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5390 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00375 |  | A
036909C-1053-PDS-2600-5392 | Process Equipment Datasheet - 10-PK-5392 - Mild Steel Corr Inhibitor Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5392 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00375 |  | A
036909C-1053-PDS-2600-5394 | Process Equipment Datasheet - 10-PK-5394 - Dispersant Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5394 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00375 |  | A
036909C-1053-PDS-2600-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5397 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00375 |  | A
036909C-1000-MR-0610-0001 | Material Requisition For Wieland Tubes (Solo Source) Requisition For Inquiry | A | 2018-11-27 | IFQ | OL1-2M55-0058 | ME | 2018-11-28 | 036909C-JVD-TRN-00377 | 036909C-JVD-TRN-00377 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00377 |  | A
036909C-1000-SP-0610-0001 | Particular Technical Specification For Wieland Tubes (Solo Source) | A | 2018-11-27 | IFQ | OL1-2M57-0058 | ME | 2018-11-28 | 036909C-JVD-TRN-00377 | 036909C-JVD-TRN-00377 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00377 |  | A
036909C-1028-PDS-0900-2855 | Process Equipment Datasheet - 10-P-2855 A-B - Ethylene Product Pumps | A | 2018-11-27 | IFR | OL1-2G30-2855 | PE | 2018-11-28 | 036909C-JVD-TRN-00379 | 036909C-JVD-TRN-00379 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-PE-00379 |  | A
036909C-1022-PDS-0600-2206 | Process Equipment Datasheet - 10-E-2206 - Wash Water Cooler | A | 2018-11-27 | IFR | OL1-2G30-2206 | PE | 2018-11-28 | 036909C-JVD-TRN-00381 | 036909C-JVD-TRN-00381 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-PE-00381 |  | A
036909C-1023-PDS-0600-2326 | Process Equipment Datasheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | A | 2018-11-27 | IFR | OL1-2G30-2326 | PE | 2018-11-28 | 036909C-JVD-TRN-00381 | 036909C-JVD-TRN-00381 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-PE-00381 |  | A
036909C-1024-PDS-0800-2480 | Process Equipment Datasheet - 10-D-2480 - CG Secondary Dryer | A | 2018-11-28 | IFR | OL1-2G30-2480 | PE | 2018-11-28 | 036909C-JVD-TRN-00386 | 036909C-JVD-TRN-00386 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-PE-00386 |  | A
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | A | 2018-11-28 | IFQ | OL1-2M03-2040 | ME | 2018-11-28 | 036909C-JVD-TRN-00387 | 036909C-JVD-TRN-00387 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-ME-00387 |  | A
036909C-1025-TDS-0610-2503 | Mechanical Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | A | 2018-11-28 | IFQ | OL1-2M03-2503 | ME | 2018-11-28 | 036909C-JVD-TRN-00389 | 036909C-JVD-TRN-00389 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-ME-00389 |  | A
036909C-1000-SP-4100-0001 | Particular Technical Specification for Wet Air Oxidation Package | A | 2018-11-26 | IFQ | OL1-2M57-0103 | ME | 2018-11-29 | 036909C-JVD-TRN-00390 | 036909C-JVD-TRN-00390 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00390 |  | A
036909C-1023-SP-4100-0002 | Mechanical Equipment Datasheet for Wet Air Oxidation Package | A | 2018-11-27 | IFQ | OL1-2M03-2350 | ME | 2018-11-29 | 036909C-JVD-TRN-00390 | 036909C-JVD-TRN-00390 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00390 |  | A
036909C-1024-PDS-0600-2465 | Process Equipment Datasheet - 10-E-2465 - C2 Hydrog Feed Heater | A | 2018-11-28 | IFR | OL1-2G30-2465 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00391 |  | A
036909C-1024-PDS-0600-2471 | Process Equipment Datasheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | A | 2018-11-28 | IFR | OL1-2G30-2471 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00391 |  | A
036909C-1024-PDS-0600-2472 | Process Equipment Datasheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | A | 2018-11-28 | IFR | OL1-2G30-2472 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00391 |  | A
036909C-1024-PDS-0600-2474 | Process Equipment Datasheet - 10-E-2474 - C2 Hydrog Aftercooler | A | 2018-11-28 | IFR | OL1-2G30-2474 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00391 |  | A
036909C-1025-SP-0510-2570 | Mechanical Equipment Data Sheet - Deethanizer | A | 2018-11-28 | IFQ | OL1-2M03-2570 | ME | 2018-11-29 | 036909C-JVD-TRN-00394 | 036909C-JVD-TRN-00394 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00394 |  | A
036909C-1055-PDS-0800-5510 | Process Equipment Datasheet - 10-D-5510 - Cold Flare Drum | A | 2018-11-29 | IFR | OL1-2G30-5510 | PE | 2018-11-29 | 036909C-JVD-TRN-00397 | 036909C-JVD-TRN-00397 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00397 |  | A
036909C-1055-PDS-0180-5560 | Process Equipment Datasheet - 10-PK-5560 - HP - Polyolefins Flare Pkg | A | 2018-11-29 | IFR | OL1-2G30-5560 | PE | 2018-11-29 | 036909C-JVD-TRN-00398 | 036909C-JVD-TRN-00398 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00398 |  | A
036909C-1053-MSD-0011-5301 | Material Selection Diagram - Olefins Unit 10 - 53 Cooling Water System Cooling Water Diagram | A | 2018-11-16 | IFA | OL1-2G74-5301 | ME | 2018-11-29 | 036909C-JVD-TRN-00399 | 036909C-JVD-TRN-00399 | IFA | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00399 |  | A
036909C-1053-MSD-0011-5311 | Material Selection Diagram - Olefins Unit 10 - 53-Cooling Water System Cooling Tower | A | 2018-11-16 | IFA | OL1-2G74-5311 | ME | 2018-11-29 | 036909C-JVD-TRN-00399 | 036909C-JVD-TRN-00399 | IFA | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00399 |  | A
036909C-1021-SP-0910-2191 | Mechanical Equipment Datasheet - Quench Water Drain Drum Pump | A | 2018-11-28 | IFQ | OL1-2M03-2191 | ME | 2018-11-29 | 036909C-JVD-TRN-00400 | 036909C-JVD-TRN-00400 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00400 |  | A
036909C-1000-JSD-1530-0001 | Intercom/Paging/Audible Alarm System | A | 2018-11-30 | IFR | OL1-2R05-0013 | EE | 2018-12-04 | 036909C-JVD-TRN-00403 | 036909C-JVD-TRN-00403 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-EE-00403 |  | A
036909C-1000-JSD-1530-0002 | Safety Supervisory System | A | 2018-11-30 | IFR | OL1-2R05-0019 | EE | 2018-12-04 | 036909C-JVD-TRN-00403 | 036909C-JVD-TRN-00403 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-EE-00403 |  | A
036909C-1059-PDS-2500-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank | A | 2018-11-29 | IFR | OL1-2G30-5950 | PE | 2018-12-04 | 036909C-JVD-TRN-00406 | 036909C-JVD-TRN-00406 | IFR | 2018-12-17 |  | Transmitted | TPSK-LSPA1-T-PE-00406 |  | A
036909C-1024-PDS-0900-2457 | Process Equipment Datasheet - 10-P-2455 A-B - LP Deprop Reboiler Cond Pump | A | 2018-12-03 | IFR | OL1-2G30-2457 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 |  | Transmitted | TPSK-LSPA1-T-PE-00408 |  | A
036909C-1025-PDS-0900-2577 | Process Equipment Datasheet - 10-P-2575 A-B - Deethanizer Reboiler Cond Pumps | A | 2018-12-03 | IFR | OL1-2G30-2577 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 |  | Transmitted | TPSK-LSPA1-T-PE-00408 |  | A
036909C-1024-PDS-0900-2443 | Process Equipment Datasheet - 10-P-2445 A-B - HP Deprop Reboiler Cond Pump | A | 2018-12-03 | IFR | OL1-2G30-2443 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 |  | Transmitted | TPSK-LSPA1-T-PE-00408 |  | A
036909C-1021-SP-0910-2126 | Mechanical Equipment Datasheet - Distillate Stripper Bottom Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2126 | ME | 2018-12-05 | 036909C-JVD-TRN-00410 | 036909C-JVD-TRN-00410 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00410 |  | A
036909C-1022-SP-0910-2212 | Mechanical Equipment Datasheet - CG 1st Stage Condensate Pumps | A | 2018-12-04 | IFQ | OL1-2M03-2212 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00413 |  | A
036909C-1024-SP-0910-2416 | Mechanical Equipment Datasheet - CG Liquid Dryer Feed Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2416 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00413 |  | A
036909C-1025-SP-0910-2586 | Mechanical Equipment Datasheet - Ethane Recycle Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2586 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00413 |  | A
036909C-1026-SP-0510-2640 | Mechanical Equipment Data Sheet - C3 Tower | A | 2018-11-30 | IFQ | OL1-2M03-2640 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00415 |  | A
036909C-1020-SP-0510-2000 | Mechanical Equipment Data Sheet - Quench Oil Tower | A | 2018-12-04 | IFQ | OL1-2M03-2000 | ME | 2018-12-04 | 036909C-JVD-TRN-00420 | 036909C-JVD-TRN-00420 | IFR | 2018-12-18 |  | Transmitted | TPSL-LSPA1-T-ME-00420 |  | A
036909C-1026-SP-0910-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2669 | ME | 2018-12-04 | 036909C-JVD-TRN-00421 | 036909C-JVD-TRN-00421 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00421 |  | A
036909C-1000-JSS-0184-0001 | ME-021 Flare System | A | 2018-11-29 | IFR | OL1-2R03-0021 | ME | 2018-12-06 | 036909C-JVD-TRN-00429 | 036909C-JVD-TRN-00429 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-ME-00429 |  | A
036909C-1000-JSS-1031-0001 | ME-047 Dry Screw Compressor for Hydrocarbon Services | A | 2018-11-30 | IFR | OL1-2R03-0047 | ME | 2018-12-06 | 036909C-JVD-TRN-00429 | 036909C-JVD-TRN-00429 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-ME-00429 |  | A
036909C-1012-PDS-1542-1213 | Process Equipment Datasheet - 10-M-1201 - 1601 A-F - USC 132U Dilution Steam Mixing Tee | A | 2018-12-04 | IFR | OL1-2G30-1213 | PE | 2018-12-07 | 036909C-JVD-TRN-00434 | 036909C-JVD-TRN-00434 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00434 |  | A
036909C-1024-PDS-0800-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer | A | 2018-12-06 | IFR | OL1-2G30-2410 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00439 |  | A
036909C-1026-PDS-0800-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber | A | 2018-12-05 | IFR | OL1-2G30-2600 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00439 |  | A
036909C-1028-PDS-0800-2815 | Process Equipment Datasheet - 10-D-2815 - C3R Drain Drum | A | 2018-12-04 | IFR | OL1-2G30-2815 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00439 |  | A
036909C-1055-PDS-0800-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum | A | 2018-12-05 | IFR | OL1-2G30-5552 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00439 |  | A
036909C-1021-SP-0510-2100 | Mechanical Equipment Data Sheet - Quench Water Tower | A | 2018-12-06 | IFQ | OL1-2M03-2100 | ME | 2018-12-07 | 036909C-JVD-TRN-00443 | 036909C-JVD-TRN-00443 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-ME-00443 |  | A
036909C-1023-PDS-0900-2391 | Process Equipment Datasheet - 10-P-2390 - Caustic Drain Drum Pump | A | 2018-12-06 | IFR | OL1-2G30-2391 | PE | 2018-12-07 | 036909C-JVD-TRN-00444 | 036909C-JVD-TRN-00444 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00444 |  | A
036909C-1028-PDS-0800-2865 | Process Equipment Datasheet - 10-D-2865 - C2R Drain Drum | A | 2018-12-06 | IFR | OL1-2G30-2865 | PE | 2018-12-07 | 036909C-JVD-TRN-00445 | 036909C-JVD-TRN-00445 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00445 |  | A
036909C-1020-SP-0510-2020 | Mechanical Equipment Data Sheet - Light Fuel Oil Stripper | A | 2018-12-07 | IFQ | OL1-2M03-2020 | ME | 2018-12-10 | 036909C-JVD-TRN-00447 | 036909C-JVD-TRN-00447 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00447 |  | A
036909C-1021-PDS-0800-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum | A | 2018-12-06 | IFR | OL1-2G30-2110 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00453 |  | A
036909C-1021-PDS-0800-2136 | Process Equipment Datasheet - 10-D-2136 - Process Water Feed Coalescer | A | 2018-12-06 | IFR | OL1-2G30-2136 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00453 |  | A
036909C-1024-PDS-0800-2460 | Process Equipment Datasheet - 10-D-2460 - C2 Hydrog Arsine Guard Bed | A | 2018-12-06 | IFR | OL1-2G30-2460 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00453 |  | A
036909C-1056-PDS-0840-5612 | Process Equipment Datasheet - 10-F-5610 - Hydroblast Filter | A | 2018-12-06 | IFR | OL1-2G30-5612 | PE | 2018-12-10 | 036909C-JVD-TRN-00454 | 036909C-JVD-TRN-00454 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00454 |  | A
036909C-1026-TDS-0610-2631 | Mechanical Equipment Data Sheet - 10-E-2630 - Secondary Deeth Condenser | A | 2018-12-06 | IFQ | OL1-2M03-2631 | ME | 2018-12-10 | 036909C-JVD-TRN-00455 | 036909C-JVD-TRN-00455 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00455 |  | A
036909C-1021-SP-0510-2140 | Mechanical Equipment Data Sheet - Process Water Stripper | A | 2018-12-05 | IFQ | OL1-2M03-2140 | ME | 2018-12-10 | 036909C-JVD-TRN-00458 | 036909C-JVD-TRN-00458 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00458 |  | A
036909C-1026-SP-0510-2630 | Mechanical Equipment Data Sheet - Secondary Deethanizer | A | 2018-12-05 | IFQ | OL1-2M03-2630 | ME | 2018-12-10 | 036909C-JVD-TRN-00458 | 036909C-JVD-TRN-00458 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00458 |  | A
036909C-1020-SP-0910-2024 | Mechanical Equipment Datasheet - Light Fuel Oil Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2024 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00457 |  | A
036909C-1020-SP-0910-2046 | Mechanical Equipment Datasheet - Heavy Fuel Oil Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2046 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00457 |  | A
036909C-1021-SP-0910-2105 | Mechanical Equipment Datasheet - Quench Oil Reflux Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2105 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00457 |  | A
036909C-1023-SP-0910-2393 | Mechanical Equipment Datasheet - Spent Caustic Drain Drum Pump | A | 2018-12-05 | IFQ | OL1-2M03-2393 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00457 |  | A
036909C-1059-PDS-2600-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg | A | 2018-12-07 | IFR | OL1-2G30-5910 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00456 |  | A
036909C-1059-PDS-2600-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | A | 2018-12-07 | IFR | OL1-2G30-5912 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00456 |  | A
036909C-1059-PDS-2600-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg | A | 2018-12-07 | IFR | OL1-2G30-5914 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00456 |  | A
036909C-1028-SP-0810-2840 | Mechanical Equipment Data Sheet - C3R 4TH Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2840 | ME | 2018-12-10 | 036909C-JVD-TRN-00460 | 036909C-JVD-TRN-00460 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00460 |  | A
036909C-1028-SP-0810-2880 | Mechanical Equipment Data Sheet - C2R 3RD Stage Suction Drum | A | 2018-12-04 | IFQ | OL1-2M03-2880 | ME | 2018-12-10 | 036909C-JVD-TRN-00460 | 036909C-JVD-TRN-00460 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00460 |  | A
036909C-1025-TDS-0610-2502 | Mechanical Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | A | 2018-12-06 | IFQ | OL1-2M03-2502 | ME | 2018-12-10 | 036909C-JVD-TRN-00461 | 036909C-JVD-TRN-00461 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00461 |  | A
036909C-1023-SP-0510-2330 | Mechanical Equipment Data Sheet - Spent Caustic Stripper | A | 2018-12-06 | IFQ | OL1-2M03-2330 | ME | 2018-12-10 | 036909C-JVD-TRN-00462 | 036909C-JVD-TRN-00462 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00462 |  | A
036909C-1026-TDS-0610-2636 | Mechanical Equipment Data Sheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | A | 2018-12-07 | IFQ | OL1-2M03-2636 | ME | 2018-12-10 | 036909C-JVD-TRN-00465 | 036909C-JVD-TRN-00465 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00465 |  | A
036909C-1026-TDS-0610-2661 | Mechanical Equipment Data Sheet - 10-E-2660 - Debutanizer Condenser | A | 2018-12-07 | IFQ | OL1-2M03-2661 | ME | 2018-12-10 | 036909C-JVD-TRN-00465 | 036909C-JVD-TRN-00465 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00465 |  | A
036909C-1026-TDS-0610-2665 | Mechanical Equipment Data Sheet - 10-E-2665 AB - Debutanizer Reboilers | A | 2018-12-07 | IFQ | OL1-2M03-2665 | ME | 2018-12-10 | 036909C-JVD-TRN-00468 | 036909C-JVD-TRN-00468 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00468 |  | A
036909C-1026-TDS-0610-2666 | Mechanical Equipment Data Sheet - 10-E-2666 - Debutanizer Bottoms Cooler | A | 2018-12-07 | IFQ | OL1-2M03-2666 | ME | 2018-12-10 | 036909C-JVD-TRN-00468 | 036909C-JVD-TRN-00468 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00468 |  | A
036909C-1000-JSD-6200-0001 | Environmental Protection Design Criteria | A | 2018-12-05 | IFR | OL1-2S08-0001 | ES | 2018-12-11 | 036909C-JVD-TRN-00473 | 036909C-JVD-TRN-00472, 036909C-JVD-TRN-00473 | IFR | 2018-12-27 |  | Transmitted | TPSK-LSPA1-T-ES-00473 |  | A
036909C-1000-JSD-6000-0001 | Noise Control | A | 2018-12-05 | IFR | OL1-2L10-0001 | SE | 2018-12-11 | 036909C-JVD-TRN-00472 | 036909C-JVD-TRN-00472, 036909C-JVD-TRN-00473 | IFR | 2018-12-27 |  | Transmitted | TPSK-LSPA1-T-SE-00472 |  | A
036909C-1024-PDS-0800-2444 | Process Equipment Datasheet - 10-D-2445 - HP Deprop Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2444 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 |  | Transmitted | TPSK-LSPA1-T-PE-00474 |  | A
036909C-1024-PDS-0800-2456 | Process Equipment Datasheet - 10-D-2455 - LP Deprop Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2456 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 |  | Transmitted | TPSK-LSPA1-T-PE-00474 |  | A
036909C-1025-PDS-0800-2574 | Process Equipment Datasheet - 10-D-2575 - Deethanizer Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2574 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 |  | Transmitted | TPSK-LSPA1-T-PE-00474 |  | A
036909C-1000-SP-1652-0001 | Particular Technical Specification for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E57-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | A
036909C-1000-SP-1652-1100 | Typical Data Sheet for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E05-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | A
036909C-1000-MR-1652-0001 | Material Requisition for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E55-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | A
036909C-1027-PDS-0800-2790 | Process Equipment Datasheet - 10-D-2790 - Light Oil Drain Drum | A | 2018-12-10 | IFR | OL1-2G30-2790 | PE | 2018-12-12 | 036909C-JVD-TRN-00482 | 036909C-JVD-TRN-00482 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-PE-00482 |  | A
036909C-1010-SP-0810-1000 | Mechanical Equipment Data Sheet - LPG Drum | A | 2018-12-05 | IFQ | OL1-2M03-1000 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1021-SP-0810-2160 | Mechanical Equipment Data Sheet - Dilution Steam Generator | A | 2018-12-05 | IFQ | OL1-2M03-2160 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1022-SP-0810-2220 | Mechanical Equipment Data Sheet - CG 2nd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2220 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1022-SP-0810-2230 | Mechanical Equipment Data Sheet - CG 3rd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2230 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1022-SP-0810-2240 | Mechanical Equipment Data Sheet - CG 4th Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2240 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1023-SP-0810-2322 | Mechanical Equipment Data Sheet - Skim Oil Drum | A | 2018-12-10 | IFQ | OL1-2M03-2322 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1025-SP-0810-2504 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 1 | A | 2018-12-06 | IFQ | OL1-2M03-2504 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1028-SP-0810-2805 | Mechanical Equipment Data Sheet - C3R Surge Drum | A | 2018-12-05 | IFQ | OL1-2M03-2805 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1028-SP-0810-2820 | Mechanical Equipment Data Sheet - C3R 2nd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2820 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1028-SP-0810-2830 | Mechanical Equipment Data Sheet - C3R 3rd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2830 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1055-SP-0810-5500 | Mechanical Equipment Data Sheet - Hot Flare Drum | A | 2018-12-07 | IFQ | OL1-2M03-5500 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1028-SP-0810-2810 | Mechanical Equipment Data Sheet - C3R 1st Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2810 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1023-SP-0810-2309 | Mechanical Equipment Data Sheet - Yellow Oil Drum | A | 2018-12-10 | IFQ | OL1-2M03-2309 | ME | 2018-12-12 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00484 |  | A
036909C-1024-SP-0810-2438 | Mechanical Equipment Data Sheet - HP Depropanizer Reflux Drum | A | 2018-12-04 | IFQ | OL1-2M03-2438 | ME | 2018-12-12 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00484 |  | A
036909C-1025-SP-0810-2572 | Mechanical Equipment Data Sheet - Deethanizer Reflux Drum | A | 2018-12-10 | IFQ | OL1-2M03-2572 | ME | 2018-12-12 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00484 |  | A
036909C-1054-PDS-0800-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver | A | 2018-12-11 | IFR | OL1-2G30-5400 | PE | 2018-12-12 | 036909C-JVD-TRN-00485 | 036909C-JVD-TRN-00485 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-PE-00485 |  | A
036909C-1026-SP-0910-2633 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Pumps | A | 2018-11-19 | IFQ | OL1-2M03-2633 | ME | 2018-12-12 | 036909C-JVD-TRN-00487 | 036909C-JVD-TRN-00487 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00487 |  | A
036909C-1050-PID-0031-5010 | P&ID - Olefins Unit 10 - Water System Treated Potable Demin - Supporting Utilities Auxiliaries Treated Water | A | 2018-12-11 | IFR | OL1-2G43-5010 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5301 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 1 | A | 2018-12-11 | IFR | OL1-2G43-5301 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5302 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 2 | A | 2018-12-11 | IFR | OL1-2G43-5302 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5303 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 3 | A | 2018-12-11 | IFR | OL1-2G43-5303 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5305 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 1 | A | 2018-12-11 | IFR | OL1-2G43-5305 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5306 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 2 | A | 2018-12-11 | IFR | OL1-2G43-5306 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5307 | P&ID - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply Pumps | A | 2018-12-11 | IFR | OL1-2G43-5307 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5310 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply | A | 2018-12-11 | IFR | OL1-2G43-5310 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5311 | P&ID - Olefins Unit 10 - Cooling Water - Ctu Cooling Water Supply | A | 2018-12-11 | IFR | OL1-2G43-5311 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5315 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package | A | 2018-12-11 | IFR | OL1-2G43-5315 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5317 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Filter Backwash | A | 2018-12-11 | IFR | OL1-2G43-5317 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5320 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 01 | A | 2018-12-11 | IFR | OL1-2G43-5320 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5321 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 02 | A | 2018-12-11 | IFR | OL1-2G43-5321 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5322 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 03 | A | 2018-12-11 | IFR | OL1-2G43-5322 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5323 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 04 | A | 2018-12-11 | IFR | OL1-2G43-5323 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5324 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 05 | A | 2018-12-11 | IFR | OL1-2G43-5324 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5325 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 06 | A | 2018-12-11 | IFR | OL1-2G43-5325 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5326 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 07 | A | 2018-12-11 | IFR | OL1-2G43-5326 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5351 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5351 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5352 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection | A | 2018-12-11 | IFR | OL1-2G43-5352 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1059-PID-0031-5903 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - CW Hypochlorite Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5903 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1059-PID-0031-5904 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5904 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1059-PID-0031-5932 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Pumps | A | 2018-12-11 | IFR | OL1-2G43-5932 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1028-PDS-1000-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | B | 2018-09-14 | IFD | OL1-2G30-2800 | PE | 2018-09-17 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | B
036909C-1028-PDS-1000-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | B | 2018-09-14 | IFD | OL1-2G30-2850 | PE | 2018-09-17 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | B
036909C-1022-PDS-1000-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | B | 2018-09-14 | IFD | OL1-2G30-2200 | PE | 2018-09-17 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | B
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | B | 2018-09-20 | IFR | OL1-2R03-0050 | ME | 2018-09-25 | 036909C-JVD-TRN-00084 | 036909C-JVD-TRN-00084 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | B
036909C-1000-JSS-0400-01 | Job Specification For Supply Of Pressure Vessels | B | 2018-09-20 | IFR | OL1-2R03-0051 | ME | 2018-09-25 | 036909C-JVD-TRN-00084 | 036909C-JVD-TRN-00084 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | B
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | B | 2018-09-20 | IFR | OL1-2R03-0054 | ME | 2018-09-25 | 036909C-JVD-TRN-00085 | 036909C-JVD-TRN-00085 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | B
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | B | 2018-09-13 | IFD | OL1-2G05-5601 | PE | 2018-09-26 | 036909C-JVD-TRN-00091 | 036909C-JVD-TRN-00091 | IFI |  | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | B
036909C-1053-DI-0007-5301 | Area Basis of Design - 53 Cooling Tower System | B | 2018-09-24 | IFD | OL1-2G05-5301 | PE | 2018-09-26 | 036909C-JVD-TRN-00093 | 036909C-JVD-TRN-00093 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00003 |  | B
036909C-1019-PDS-1000-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | B | 2018-09-28 | IFD | OL1-2G30-1950 | PE | 2018-09-28 | 036909C-JVD-TRN-00114 | 036909C-JVD-TRN-00114 | IFI |  | 2018-10-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00114 |  | B
036909C-1025-PDS-1000-2550 | Process Equipment Datasheet - 10-TX-2550 - 10-C-2550 - Residue Gas Expander - Recompressor | B | 2018-09-28 | IFD | OL1-2G30-2550 | PE | 2018-09-28 | 036909C-JVD-TRN-00114 | 036909C-JVD-TRN-00114 | IFI |  | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-PE-00114 |  | B
036909C-1028-SP-1011-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2850 | ME | 2018-10-03 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  | 2018-10-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00127 |  | B
036909C-1000-JSD-1600-003 | General Design Rule for Package Equipment Electrical System | B | 2018-10-20 | IFR | OL1-2E04-6000 | EE | 2018-10-04 | 036909C-JVD-TRN-00126 | 036909C-JVD-TRN-00126 | IFR | 2018-10-18 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-EE-00126 | Ex Document Client Reference OL1-2R05-0042 | B
036909C-1028-SP-1011-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2800 | ME | 2018-10-03 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00127 |  | B
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2200 | ME | 2018-10-03 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00127 |  | B
036909C-1025-SP-1011-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | B | 2018-10-04 | IFQ | OL1-2M03-2550 | ME | 2018-10-05 | 036909C-JVD-TRN-00130 | 036909C-JVD-TRN-00130 | IFI |  | 2018-10-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00130 |  | B
036909C-1025-PDS-0600-2500 | Process Equipment Datasheet - 10-E-2500 - Propylene Refrig Subcooler | B | 2018-10-03 | IFD | OL1-2G30-2500 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2505 | Process Equipment Datasheet - 10-E2506 and 10-E2508 - Demeth Prefrac Feed Cooler No 3 and No 4 | B | 2018-10-03 | IFD | OL1-2G30-2505 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2541 | Process Equipment Datasheet - 10-E-2540 - Demethanizer Condenser | B | 2018-10-03 | IFD | OL1-2G30-2541 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2587 | Process Equipment Datasheet - 10-E-2587 - C2 Tower Side Reboiler | B | 2018-10-03 | IFD | OL1-2G30-2587 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2521 | Process Equipment Datasheet - 10-E-2520 - Rectifier Condenser | B | 2018-10-03 | IFD | OL1-2G30-2521 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2526 | Process Equipment Datasheet - 10-E-2525 - Hydrogen Core Exchanger | B | 2018-10-03 | IFD | OL1-2G30-2526 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2585 | Process Equipment Datasheet - 10-E-2585 - C2 Tower Bottoms Reboiler | B | 2018-10-03 | IFD | OL1-2G30-2585 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1028-PDS-0600-2882 | Process Equipment Datasheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | B | 2018-10-03 | IFD | OL1-2G30-2882 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2531 | Process Equipment Datasheet - 10-E-2530 - Demeth Feed Cooler | B | 2018-10-03 | IFD | OL1-2G30-2531 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2511 | Process Equipment Datasheet - 10-E-2510 - Demeth Prefrac Condenser | B | 2018-10-03 | IFD | OL1-2G30-2511 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1028-PDS-0600-2884 | Process Equipment Datasheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | B | 2018-10-03 | IFD | OL1-2G30-2884 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1021-PDS-0600-2101 | Process Equipment Datasheet - 10-E-2100 A-F - Quench Water Cooler | B | 2018-10-04 | IFD | OL1-2G30-2101 | PE | 2018-10-08 | 036909C-JVD-TRN-00143 | 036909C-JVD-TRN-00143 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00143 |  | B
036909C-1000-MR-0662-0002 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry | B | 2018-10-09 | IFQ | OL1-2M55-0066 | ME | 2018-10-10 | 036909C-JVD-TRN-00153 | 036909C-JVD-TRN-00153 | IFR | 2018-10-24 | 2018-11-02 | Transmitted | TPSK-LSPA1-T-ME-00153 |  | B
036909C-1021-TDS-0661-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | B | 2018-10-09 | IFQ | OL1-2M03-2101 | ME | 2018-10-10 | 036909C-JVD-TRN-00154 | 036909C-JVD-TRN-00154 | IFI |  | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00154 |  | B
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | B | 2018-10-09 | IFD | OL1-2G40-0010 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | B | 2018-10-09 | IFD | OL1-2G41-0001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | B | 2018-10-09 | IFD | OL1-2G41-0002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | B | 2018-10-09 | IFD | OL1-2G41-1001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | B | 2018-10-09 | IFD | OL1-2G41-1003 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | B | 2018-10-09 | IFD | OL1-2G41-1101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | B | 2018-10-09 | IFD | OL1-2G41-1201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | B | 2018-10-09 | IFD | OL1-2G41-1901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-1902 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | B | 2018-10-09 | IFD | OL1-2G41-2001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | B | 2018-10-09 | IFD | OL1-2G41-2002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | B | 2018-10-09 | IFD | OL1-2G41-2101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | B | 2018-10-09 | IFD | OL1-2G41-2102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | B | 2018-10-09 | IFD | OL1-2G41-2103 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | B | 2018-10-09 | IFD | OL1-2G41-2201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | B | 2018-10-09 | IFD | OL1-2G41-2301 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | B | 2018-10-09 | IFD | OL1-2G41-2302 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | B | 2018-10-09 | IFD | OL1-2G41-2303 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | B | 2018-10-09 | IFD | OL1-2G41-2304 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | B | 2018-10-09 | IFD | OL1-2G41-2305 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | B | 2018-10-09 | IFD | OL1-2G41-2401 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | B | 2018-10-09 | IFD | OL1-2G41-2402 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | B | 2018-10-09 | IFD | OL1-2G41-2403 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2404 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | B | 2018-10-09 | IFD | OL1-2G41-2405 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | B | 2018-10-09 | IFD | OL1-2G41-2501 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | B | 2018-10-09 | IFD | OL1-2G41-2502 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | B | 2018-10-09 | IFD | OL1-2G41-2503 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | B | 2018-10-09 | IFD | OL1-2G41-2504 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | B | 2018-10-09 | IFD | OL1-2G41-2505 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | B | 2018-10-09 | IFD | OL1-2G41-2506 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2601 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | B | 2018-10-09 | IFD | OL1-2G41-2602 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | B | 2018-10-09 | IFD | OL1-2G41-2603 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | B | 2018-10-09 | IFD | OL1-2G41-2604 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | B | 2018-10-09 | IFD | OL1-2G41-2701 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | B | 2018-10-09 | IFD | OL1-2G41-2702 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | B | 2018-10-09 | IFD | OL1-2G41-2703 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2704 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | B | 2018-10-09 | IFD | OL1-2G41-2801 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | B | 2018-10-09 | IFD | OL1-2G41-2802 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | B | 2018-10-09 | IFD | OL1-2G41-2803 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | B | 2018-10-09 | IFD | OL1-2G41-2804 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-2901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | B | 2018-10-09 | IFD | OL1-2G41-3001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | B | 2018-10-09 | IFD | OL1-2G41-3002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | B | 2018-10-09 | IFD | OL1-2G41-3003 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | B | 2018-10-09 | IFD | OL1-2G41-3004 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | B | 2018-10-09 | IFD | OL1-2G41-3005 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | B | 2018-10-09 | IFD | OL1-2G41-3101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam and Condensate System | B | 2018-10-09 | IFD | OL1-2G41-3102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-3901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable and Demin Water Systems | B | 2018-10-09 | IFD | OL1-2G42-5001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | B | 2018-10-09 | IFD | OL1-2G42-5101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate and Boiler Feedwater Systems | B | 2018-10-09 | IFD | OL1-2G42-5102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | B | 2018-10-09 | IFD | OL1-2G42-5103 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | B | 2018-10-09 | IFD | OL1-2G42-5104 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | B | 2018-10-09 | IFD | OL1-2G42-5201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | B | 2018-10-09 | IFD | OL1-2G42-5301 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | B | 2018-10-09 | IFD | OL1-2G42-5311 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air and Nitrogen Systems | B | 2018-10-09 | IFD | OL1-2G42-5401 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare and Blowdown System | B | 2018-10-09 | IFD | OL1-2G42-5501 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | B | 2018-10-09 | IFD | OL1-2G42-5502 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | B | 2018-10-09 | IFD | OL1-2G42-5511 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | B | 2018-10-09 | IFD | OL1-2G42-5512 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5601 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | B | 2018-10-09 | IFD | OL1-2G42-5602 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | B | 2018-10-09 | IFD | OL1-2G42-5603 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5604 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | B | 2018-10-09 | IFD | OL1-2G42-5610 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5611 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | B | 2018-10-09 | IFD | OL1-2G42-5612 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | B | 2018-10-09 | IFD | OL1-2G42-5613 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | B | 2018-10-09 | IFD | OL1-2G42-5614 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | B | 2018-10-09 | IFD | OL1-2G42-5615 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | B | 2018-10-09 | IFD | OL1-2G42-5616 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | B | 2018-10-09 | IFD | OL1-2G42-5617 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G42-5901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | B | 2018-10-09 | IFD | OL1-2G42-5911 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1000-DW-1422-0001 | Soil Investigation Plan | B | 2018-10-10 | IFR | OL1-2K43-0004 | CV | 2018-10-12 | 036909C-JVD-TRN-00163 | 036909C-JVD-TRN-00163 | IFR | 2018-10-26 |  | Transmitted | TPSK-LSPA1-T-CV-00163 |  | B
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | B | 2018-10-10 | IFA | OL1-2G30-2330 | PE | 2018-10-11 | 036909C-JVD-TRN-00160 | 036909C-JVD-TRN-00160 | IFA | 2018-10-25 |  | Transmitted | TPSK-LSPA1-T-PE-00160 |  | B
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet for Decoke Air Compressor Package | B | 2018-10-10 | IFQ | OL1-2M03-1950 | ME | 2018-10-11 | 036909C-JVD-TRN-00161 | 036909C-JVD-TRN-00161 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00161 |  | B
036909C-1024-PDS-0500-2440 | Process Equipment Datasheet - 10-T-2440 - HP Depropanizer | B | 2018-10-11 | IFD | OL1-2G30-2440 | PE | 2018-10-12 | 036909C-JVD-TRN-00167 | 036909C-JVD-TRN-00167 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00167 |  | B
036909C-1024-PDS-0500-2450 | Process Equipment Datasheet - 10-T-2450 - LP Depropanizer | B | 2018-10-11 | IFD | OL1-2G30-2450 | PE | 2018-10-12 | 036909C-JVD-TRN-00167 | 036909C-JVD-TRN-00167 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00167 |  | B
036909C-1026-PDS-0500-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer | B | 2018-10-12 | IFD | OL1-2G30-2630 | PE | 2018-10-12 | 036909C-JVD-TRN-00169 | 036909C-JVD-TRN-00169 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00169 |  | B
036909C-1026-PDS-0500-2660 | Process Equipment Datasheet - 10-T-2660 - Debutanizer | B | 2018-10-12 | IFD | OL1-2G30-2660 | PE | 2018-10-12 | 036909C-JVD-TRN-00169 | 036909C-JVD-TRN-00169 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00169 |  | B
036909C-1000-MS-1422-0001 | Technical Specification for Geotechnical Investigation | B | 2018-10-15 | IFR | OL1-2K43-0002 | CV | 2018-10-17 | 036909C-JVD-TRN-00188 | 036909C-JVD-TRN-00188 | IFR | 2018-11-05 | 2018-11-01 | R1-No comments | TPSK-LSPA1-T-CV-00188 |  | B
036909C-1000-PS-1422-0001 | Price List for Geotechnical Investigation | B | 2018-10-15 | IFR | OL1-2K43-0003 | CV | 2018-10-17 | 036909C-JVD-TRN-00188 | 036909C-JVD-TRN-00188 | IFR | 2018-11-05 | 2018-11-01 | R1-No comments | TPSK-LSPA1-T-CV-00188 |  | B
036909C-1020-PDS-0900-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | B | 2018-10-18 | IFD | OL1-2G30-2006 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202 |  | B
036909C-1021-PDS-0900-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | B | 2018-10-18 | IFD | OL1-2G30-2106 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202 |  | B
036909C-1021-PDS-0900-2146 | Process Equipment Datasheet - 10-P-2146 A-B - DSG Feed Pumps | B | 2018-10-18 | IFD | OL1-2G30-2146 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202 |  | B
036909C-1023-PDS-2500-2320 | Process Equipment Datasheet - 10-TK-2320 - Spent Caustic Storage Tank | B | 2018-10-18 | IFD | OL1-2G30-2320 | PE | 2018-10-22 | 036909C-JVD-TRN-00203 | 036909C-JVD-TRN-00203 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00203 |  | B
036909C-1011-PDS-1040-1111 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | B | 2018-10-23 | IFD | OL1-2G30-1111 | PE | 2018-10-24 | 036909C-JVD-TRN-00222 | 036909C-JVD-TRN-00222 | IFI | 2018-11-08 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00222 |  | B
036909C-1012-PDS-1040-1211 | Process Equipment Datasheet - 10-C-1200 1600 - USC 132U Induced Draft Fan | B | 2018-10-23 | IFD | OL1-2G30-1211 | PE | 2018-10-24 | 036909C-JVD-TRN-00222 | 036909C-JVD-TRN-00222 | IFI | 2018-11-08 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00222 |  | B
036909C-1053-PDS-0300-5350 | Process Equipment Datasheet - 10-PK-5350 - Cooling Tower | B | 2018-10-24 | IFD | OL1-2G30-5350 | PE | 2018-10-24 | 036909C-JVD-TRN-00226 | 036909C-JVD-TRN-00226 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00226 |  | B
036909C-1053-PDS-0900-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | B | 2018-10-24 | IFD | OL1-2G30-5352 | PE | 2018-10-24 | 036909C-JVD-TRN-00225 | 036909C-JVD-TRN-00225 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00225 |  | B
036909C-1053-PDS-0300-5355 | Process Equipment Datasheet - 10-PK-5355 - Side Stream Filter Pkg | B | 2018-10-24 | IFD | OL1-2G30-5355 | PE | 2018-10-24 | 036909C-JVD-TRN-00226 | 036909C-JVD-TRN-00226 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00226 |  | B
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | B | 2018-10-24 | IFD | OL1-2G30-5361 | PE | 2018-10-24 | 036909C-JVD-TRN-00225 | 036909C-JVD-TRN-00225 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00225 |  | B
036909C-1053-SP-4234-0002 | Mechanical Equipment Datasheet for Side Stream Filter Package | B | 2018-10-29 | IFQ | OL1-2M03-5355 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248 |  | B
036909C-1051-PDS-0900-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | B | 2018-10-30 | IFD | OL1-2G30-5101 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00251 |  | B
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | B | 2018-10-30 | IFD | OL1-2G30-5102 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00251 |  | B
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | B | 2018-10-30 | IFD | OL1-2G30-5109 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00251 |  | B
036909C-1028-PDS-0600-2856 | Process Equipment Datasheet - 10-E-2855 - C2R Condenser | B | 2018-11-01 | IFD | OL1-2G30-2856 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | B | 2018-11-01 | IFD | OL1-2G30-2853 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2857 | Process Equipment Datasheet - 10-E-2857 - HP Ethylene Product Vaporizer | B | 2018-11-01 | IFD | OL1-2G30-2857 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | B | 2018-11-01 | IFD | OL1-2G30-2852 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | B | 2018-11-01 | IFD | OL1-2G30-2807 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2806 | Process Equipment Datasheet - 10-E-2805 A-B - C3 Refrig Condensers | B | 2018-11-01 | IFD | OL1-2G30-2806 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0600-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | B | 2018-11-01 | IFD | OL1-2G30-2665 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0600-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | B | 2018-11-01 | IFD | OL1-2G30-2661 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0600-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers | B | 2018-11-01 | IFD | OL1-2G30-2645 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0600-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | B | 2018-11-01 | IFD | OL1-2G30-2636 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | B | 2018-11-01 | IFD | OL1-2G30-2635 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0600-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | B | 2018-11-01 | IFD | OL1-2G30-2631 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0600-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | B | 2018-11-01 | IFD | OL1-2G30-2576 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0600-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | B | 2018-11-01 | IFD | OL1-2G30-2575 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0600-2571 | Process Equipment Datasheet - 10-E-2570 - Deethanizer Condenser | B | 2018-11-01 | IFD | OL1-2G30-2571 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0600-2503 | Process Equipment Datasheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | B | 2018-11-01 | IFD | OL1-2G30-2503 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0600-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | B | 2018-11-01 | IFD | OL1-2G30-2502 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | B | 2018-11-01 | IFD | OL1-2G30-2809 | PE | 2018-11-05 | 036909C-JVD-TRN-00273 | 036909C-JVD-TRN-00273 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00273 |  | B
036909C-1053-SP-0310-0002 | Mechanical Equipment Datasheet for Cooling Tower | B | 2018-10-30 | IFQ | OL1-2M03-5350 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 |  | Transmitted | TPSK-LSPA1-T-ME-00276 |  | B
036909C-1024-SP-0510-2450 | Mechanical Equipment Datasheet - LP Depropanizer | B | 2018-11-06 | IFQ | OL1-2M03-2450 | ME | 2018-11-06 | 036909C-JVD-TRN-00283 | 036909C-JVD-TRN-00283 | IFI |  | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-ME-00283 |  | B
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | B | 2018-11-07 | IFQ | OL1-2M03-2660 | ME | 2018-11-08 | 036909C-JVD-TRN-00288 | 036909C-JVD-TRN-00288 | IFR | 2018-11-22 |  | Transmitted | TPSK-LSPA1-T-ME-00288 |  | B
036909C-1023-PDS-0500-2300 | Process Equipment Datasheet - 10-T-2300 - Caustic Tower | B | 2018-11-08 | IFD | OL1-2G30-2300 | PE | 2018-11-08 | 036909C-JVD-TRN-00290 | 036909C-JVD-TRN-00290 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00290 |  | B
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | B | 2018-10-24 | IFR | OL1-2R06-0024 | IE | 2018-11-08 | 036909C-JVD-TRN-00291 | 036909C-JVD-TRN-00291 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-IE-00291 |  | B
036909C-1000-JSD-1300-0003 | A1 Scope Annex C– Ppiping Specification PIP-006 Steam Tracing Piping | B | 2018-11-06 | IFR | OL1-2R04-0031 | MP | 2018-11-09 | 036909C-JVD-TRN-00292 | 036909C-JVD-TRN-00292 | IFR | 2018-11-26 |  | Transmitted | TPSK-LSPA1-T-MP-00292 |  | B
036909C-1025-PDS-0800-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | B | 2018-11-08 | IFD | OL1-2G30-2504 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303 |  | B
036909C-1025-PDS-0800-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | B | 2018-11-08 | IFD | OL1-2G30-2506 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303 |  | B
036909C-1025-PDS-0800-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | B | 2018-11-08 | IFD | OL1-2G30-2508 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303 |  | B
036909C-1025-PDS-0500-2510 | Process Equipment Datasheet - 10-T-2510 - 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | B | 2018-11-09 | IFD | OL1-2G30-2510 | PE | 2018-11-09 | 036909C-JVD-TRN-00306 | 036909C-JVD-TRN-00306 | IFI |  | 2018-11-29 | A1-Approved without comments | TPSK-LSPA1-T-PE-00306 |  | B
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum | B | 2018-11-09 | IFD | OL1-2G30-2540 | PE | 2018-11-09 | 036909C-JVD-TRN-00306 | 036909C-JVD-TRN-00306 | IFI |  | 2018-11-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00306 |  | B
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet for SHP BFW Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5101 | ME | 2018-11-15 | 036909C-JVD-TRN-00322 | 036909C-JVD-TRN-00322 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00322 |  | B
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5109 | ME | 2018-11-14 | 036909C-JVD-TRN-00317 | 036909C-JVD-TRN-00317 | IFR | 2018-11-28 |  | Transmitted | TPSK-LSPA1-T-ME-00317 |  | B
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5361 | ME | 2018-11-14 | 036909C-JVD-TRN-00317 | 036909C-JVD-TRN-00317 | IFR | 2018-11-28 |  | Transmitted | TPSK-LSPA1-T-ME-00317 |  | B
036909C-1000-MR-0570-0004 | Material Requisition for High Efficiency Internals for Columns | B | 2018-11-12 | IMP | OL1-2M55-0075 | ME | 2018-11-14 | 036909C-JVD-TRN-00314 | 036909C-JVD-TRN-00314 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-ME-00314 |  | B
036909C-1000-SP-0570-0004 | Particular Technical Specification for High Efficiency Internals for Columns | B | 2018-11-12 | IMP | OL1-2M57-0075 | ME | 2018-11-14 | 036909C-JVD-TRN-00314 | 036909C-JVD-TRN-00314 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-ME-00314 |  | B
036909C-1051-PDS-0800-5100 | Process Equipment Datasheet - 10-D-5100 - Deaerator | B | 2018-11-14 | IFD | OL1-2G30-5100 | PE | 2018-11-14 | 036909C-JVD-TRN-00318 | 036909C-JVD-TRN-00318 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00318 |  | B
036909C-1000-JSD-1300-0002 | Job Specification For Detail Design Piping | B | 2018-11-12 | IFR | OL1-2R04-0002 | MP | 2018-11-16 | 036909C-JVD-TRN-00326 | 036909C-JVD-TRN-00326 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00012 | Replaces doc. OL1-2P92-0002 (included as attachment to this doc.) | B
036909C-1011-PDS-0117-1101 | Process Equipment Datasheet - 10-H-1100 - USM 36M Cracking Furnace Yields | B | 2018-11-15 | IFD | OL1-2G30-1101 | PE | 2018-11-26 | 036909C-JVD-TRN-00360 | 036909C-JVD-TRN-00360 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00360 |  | B
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | B | 2018-11-19 | IFR | OL1-2R04-0006 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1000-JSS-1320-01 | Job Supply Specification For Pipes | B | 2018-11-19 | IFR | OL1-2R04-0011 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1000-JSS-1330-01 | Job Supply Specification For Buttwelding Fittings | B | 2018-11-19 | IFR | OL1-2R04-0013 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1000-JSS-1340-01 | Job Supply Specification For Forged Fittings | B | 2018-11-19 | IFR | OL1-2R04-0014 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1000-JSS-1350-01 | Job Supply Specification For Flanges | B | 2018-11-19 | IFR | OL1-2R04-0015 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1020-PDS-0500-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper | B | 2018-11-21 | IFD | OL1-2G30-2040 | PE | 2018-11-21 | 036909C-JVD-TRN-00347 | 036909C-JVD-TRN-00347 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00347 |  | B
036909C-1028-PDS-0800-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum | B | 2018-11-21 | IFD | OL1-2G30-2805 | PE | 2018-11-21 | 036909C-JVD-TRN-00348 | 036909C-JVD-TRN-00348 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00348 |  | B
036909C-1028-PDS-0800-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2810 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1028-PDS-0800-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2820 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1028-PDS-0800-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2830 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1028-PDS-0800-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2840 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1028-PDS-0800-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2870 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1051-PDS-0900-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps | B | 2018-11-16 | IFD | OL1-2G30-5111 | PE | 2018-11-26 | 036909C-JVD-TRN-00363 | 036909C-JVD-TRN-00363 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00363 |  | B
036909C-1051-PDS-0900-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps | B | 2018-11-16 | IFD | OL1-2G30-5121 | PE | 2018-11-26 | 036909C-JVD-TRN-00363 | 036909C-JVD-TRN-00363 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00363 |  | B
036909C-1051-PDS-0600-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | B | 2018-11-19 | IFD | OL1-2G30-5103 | PE | 2018-11-26 | 036909C-JVD-TRN-00366 | 036909C-JVD-TRN-00366 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00366 |  | B
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | B | 2018-11-19 | IFD | OL1-2G30-5113 | PE | 2018-11-26 | 036909C-JVD-TRN-00366 | 036909C-JVD-TRN-00366 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00366 |  | B
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | B | 2018-11-26 | IFD | OL1-2G30-2390 | PE | 2018-11-27 | 036909C-JVD-TRN-00369 | 036909C-JVD-TRN-00369 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00369 |  | B
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 - Spent Caustic Drain Drum | B | 2018-11-26 | IFD | OL1-2G30-2392 | PE | 2018-11-27 | 036909C-JVD-TRN-00369 | 036909C-JVD-TRN-00369 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00369 |  | B
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | B | 2018-11-26 | IFD | OL1-2G30-2666 | PE | 2018-11-27 | 036909C-JVD-TRN-00370 | 036909C-JVD-TRN-00370 | IFI |  | 2018-12-10 | A1-Approved without comments | TPSK-LSPA1-T-PE-00370 |  | B
036909C-1012-PDS-0117-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields | B | 2018-11-27 | IFD | OL1-2G30-1201 | PE | 2018-11-27 | 036909C-JVD-TRN-00372 | 036909C-JVD-TRN-00372 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00372 |  | B
036909C-1000-DI-0007-0006 | Furnace Process Basis of Design | B | 2018-11-27 | IFD | OL1-2G02-0006 | PE | 2018-11-27 | 036909C-JVD-TRN-00376 | 036909C-JVD-TRN-00376 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00376 |  | B
036909C-1023-PDS-0900-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump | B | 2018-11-27 | IFD | OL1-2G30-2304 | PE | 2018-11-28 | 036909C-JVD-TRN-00382 | 036909C-JVD-TRN-00382 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00382 |  | B
036909C-1023-PDS-0900-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps | B | 2018-11-27 | IFD | OL1-2G30-2306 | PE | 2018-11-28 | 036909C-JVD-TRN-00382 | 036909C-JVD-TRN-00382 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00382 |  | B
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | B | 2018-11-27 | IFD | OL1-2G30-2301 | PE | 2018-11-28 | 036909C-JVD-TRN-00383 | 036909C-JVD-TRN-00383 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00383 |  | B
036909C-1023-PDS-4200-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer | B | 2018-11-27 | IFD | OL1-2G30-2308 | PE | 2018-11-28 | 036909C-JVD-TRN-00383 | 036909C-JVD-TRN-00383 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00383 |  | B
036909C-1053-SP-0910-5352 | Mechanical Equipment DataSheet - Olefins Cooling Water Pumps | B | 2018-11-26 | IFQ | OL1-2M03-5352 | ME | 2018-11-28 | 036909C-JVD-TRN-00388 | 036909C-JVD-TRN-00388 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00388 |  | B
036909C-1024-PDS-0600-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | B | 2018-11-28 | IFD | OL1-2G30-2413 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0600-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser | B | 2018-11-28 | IFD | OL1-2G30-2439 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0600-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | B | 2018-11-28 | IFD | OL1-2G30-2441 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0600-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 | B | 2018-11-28 | IFD | OL1-2G30-2442 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0600-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler | B | 2018-11-28 | IFD | OL1-2G30-2446 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0600-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser | B | 2018-11-28 | IFD | OL1-2G30-2451 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0600-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler | B | 2018-11-28 | IFD | OL1-2G30-2461 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1021-PDS-0500-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper | B | 2018-11-29 | IFD | OL1-2G30-2140 | PE | 2018-11-29 | 036909C-JVD-TRN-00401 | 036909C-JVD-TRN-00401 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00401 |  | B
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | B | 2018-11-29 | IFD | OL1-2G30-2120 | PE | 2018-11-29 | 036909C-JVD-TRN-00401 | 036909C-JVD-TRN-00401 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00401 |  | B
036909C-1020-PDS-0500-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower | B | 2018-11-29 | IFD | OL1-2G30-2000 | PE | 2018-12-04 | 036909C-JVD-TRN-00402 | 036909C-JVD-TRN-00402 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00402 |  | B
036909C-1025-PDS-0500-2520 | Process Equipment Datasheet - 10-T-2520 - 10-D2520 - Residue Gas Rectifier & Reflux Drum | B | 2018-11-30 | IFD | OL1-2G30-2520 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | B
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | B | 2018-11-30 | IFD | OL1-2G30-2570 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | B
036909C-1025-PDS-0500-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower | B | 2018-11-30 | IFD | OL1-2G30-2580 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | B
036909C-1026-PDS-0500-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower | B | 2018-11-30 | IFD | OL1-2G30-2640 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | B
036909C-1023-SP-0910-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps | B | 2018-12-03 | IFQ | OL1-2M03-2306 | ME | 2018-12-05 | 036909C-JVD-TRN-00411 | 036909C-JVD-TRN-00411 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00411 |  | B
036909C-1023-SP-0910-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump | B | 2018-12-03 | IFQ | OL1-2M03-2304 | ME | 2018-12-05 | 036909C-JVD-TRN-00411 | 036909C-JVD-TRN-00411 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00411 |  | B
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator & Reflux Drum | B | 2018-11-30 | IFQ | OL1-2M03-2510 | ME | 2018-12-05 | 036909C-JVD-TRN-00414 | 036909C-JVD-TRN-00414 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00414 |  | B
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum | B | 2018-11-30 | IFQ | OL1-2M03-2540 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00415 |  | B
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet - HP Depropanizer | B | 2018-11-28 | IFQ | OL1-2M03-2440 | ME | 2018-12-05 | 036909C-JVD-TRN-00416 | 036909C-JVD-TRN-00416 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00416 |  | B
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | B | 2018-12-04 | IFD | OL1-2G30-5500 | PE | 2018-12-05 | 036909C-JVD-TRN-00417 | 036909C-JVD-TRN-00417 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00417 |  | B
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | B | 2018-12-04 | IFQ | OL1-2M03-2040 | ME | 2018-12-05 | 036909C-JVD-TRN-00418 | 036909C-JVD-TRN-00418 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00418 |  | B
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet - Caustic Tower | B | 2018-12-04 | IFQ | OL1-2M03-2300 | ME | 2018-12-05 | 036909C-JVD-TRN-00419 | 036909C-JVD-TRN-00419 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00419 |  | B
036909C-1024-PDS-0800-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum | B | 2018-12-04 | IFD | OL1-2G30-2438 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00430 |  | B
036909C-1025-PDS-0800-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum | B | 2018-12-04 | IFD | OL1-2G30-2525 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00430 |  | B
036909C-1024-PDS-0800-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum | B | 2018-12-04 | IFD | OL1-2G30-2452 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00430 |  | B
036909C-1025-PDS-0800-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum | B | 2018-12-04 | IFD | OL1-2G30-2555 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00430 |  | B
036909C-1010-PDS-0600-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater | B | 2018-12-04 | IFD | OL1-2G30-1015 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | B | 2018-12-04 | IFD | OL1-2G30-1020 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1021-PDS-0600-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler | B | 2018-12-04 | IFD | OL1-2G30-2166 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1022-PDS-0600-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2221 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1022-PDS-0600-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2231 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1011-PDS-0630-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger | B | 2018-12-05 | IFD | OL1-2G30-1108 | PE | 2018-12-07 | 036909C-JVD-TRN-00432 | 036909C-JVD-TRN-00432 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00432 |  | B
036909C-1012-PDS-0630-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger | B | 2018-12-05 | IFD | OL1-2G30-1208 | PE | 2018-12-07 | 036909C-JVD-TRN-00433 | 036909C-JVD-TRN-00433 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00433 |  | B
036909C-1010-PDS-0600-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater | B | 2018-12-04 | IFD | OL1-2G30-1051 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00436 |  | B
036909C-1020-PDS-0500-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper | B | 2018-12-05 | IFD | OL1-2G30-2020 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00437 |  | B
036909C-1021-PDS-0500-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | B | 2018-12-05 | IFD | OL1-2G30-2100 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00437 |  | B
036909C-1022-PDS-0600-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2241 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00436 |  | B
036909C-1024-PDS-0600-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers | B | 2018-12-04 | IFD | OL1-2G30-2445 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00436 |  | B
036909C-1025-PDS-0800-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum | B | 2018-12-04 | IFD | OL1-2G30-2551 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00440 |  | B
036909C-1051-PDS-0800-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum | B | 2018-12-05 | IFD | OL1-2G30-5150 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00440 |  | B
036909C-1052-PDS-0800-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum | B | 2018-12-05 | IFD | OL1-2G30-5200 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00440 |  | B
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | B | 2018-12-05 | IFD | OL1-2G30-5550 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00440 |  | B
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | B | 2018-12-05 | IFD | OL1-2G30-5653 | PE | 2018-12-07 | 036909C-JVD-TRN-00441 | 036909C-JVD-TRN-00441 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00441 |  | B
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | B | 2018-12-05 | IFD | OL1-2G30-5644 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00442 |  | B
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | B | 2018-12-05 | IFD | OL1-2G30-5650 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00442 |  | B
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | B | 2018-12-05 | IFD | OL1-2G30-5670 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00442 |  | B
036909C-1025-PDS-0800-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum | B | 2018-12-06 | IFD | OL1-2G30-2572 | PE | 2018-12-07 | 036909C-JVD-TRN-00446 | 036909C-JVD-TRN-00446 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00446 |  | B
036909C-1022-PDS-0800-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2210 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00448 |  | B
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2220 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00448 |  | B
036909C-1022-PDS-0800-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2230 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00448 |  | B
036909C-1022-PDS-0800-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2240 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00448 |  | B
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1209 | PE | 2018-12-10 | 036909C-JVD-TRN-00449 | 036909C-JVD-TRN-00449 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00449 |  | B
036909C-1010-PDS-0600-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer | B | 2018-12-06 | IFD | OL1-2G30-1001 | PE | 2018-12-10 | 036909C-JVD-TRN-00451 | 036909C-JVD-TRN-00451 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00451 |  | B
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1109 | PE | 2018-12-10 | 036909C-JVD-TRN-00459 | 036909C-JVD-TRN-00459 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00459 |  | B
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1110 | PE | 2018-12-10 | 036909C-JVD-TRN-00459 | 036909C-JVD-TRN-00459 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00459 |  | B
036909C-1010-PDS-0800-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum | B | 2018-12-07 | IFD | OL1-2G30-1000 | PE | 2018-12-10 | 036909C-JVD-TRN-00463 | 036909C-JVD-TRN-00463 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00463 |  | B
036909C-1025-PDS-0600-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | B | 2018-12-07 | IFD | OL1-2G30-2548 | PE | 2018-12-10 | 036909C-JVD-TRN-00464 | 036909C-JVD-TRN-00464 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00464 |  | B
036909C-1021-PDS-0600-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater | B | 2018-12-07 | IFD | OL1-2G30-2137 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00467 |  | B
036909C-1021-PDS-0600-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater | B | 2018-12-07 | IFD | OL1-2G30-2161 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00467 |  | B
036909C-1021-PDS-0600-2165 | Process Equipment Datasheet - 10-E-2165 A-D - DSG Reboilers | B | 2018-12-07 | IFD | OL1-2G30-2165 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00467 |  | B
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet - Quench Oil Pump | B | 2018-11-28 | IFQ | OL1-2M03-2006 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | B
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps | B | 2018-11-28 | IFQ | OL1-2M03-2106 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | B
036909C-1021-SP-0910-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps | B | 2018-11-28 | IFQ | OL1-2M03-2146 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | B
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet - VLP BFW Pumps | B | 2018-11-28 | IFQ | OL1-2M03-5102 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | B
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - USC 36M Cracking Furnace Steam Drum | B | 2018-12-10 | IFD | OL1-2G30-1107 | PE | 2018-12-12 | 036909C-JVD-TRN-00478 | 036909C-JVD-TRN-00478 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00478 |  | B
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200-1600 - USC 132U Cracking Furnace Steam Drum | B | 2018-12-10 | IFD | OL1-2G30-1207 | PE | 2018-12-12 | 036909C-JVD-TRN-00478 | 036909C-JVD-TRN-00478 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00478 |  | B
036909C-1022-PDS-0600-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | B | 2018-12-10 | IFD | OL1-2G30-2211 | PE | 2018-12-12 | 036909C-JVD-TRN-00479 | 036909C-JVD-TRN-00479 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00479 |  | B
036909C-1022-PDS-0800-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum | B | 2018-12-10 | IFD | OL1-2G30-2245 | PE | 2018-12-12 | 036909C-JVD-TRN-00480 | 036909C-JVD-TRN-00480 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00480 |  | B
036909C-1024-PDS-0800-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum | B | 2018-12-10 | IFD | OL1-2G30-2405 | PE | 2018-12-12 | 036909C-JVD-TRN-00480 | 036909C-JVD-TRN-00480 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00480 |  | B
036909C-1025-PDS-0900-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps | B | 2018-12-10 | IFD | OL1-2G30-2573 | PE | 2018-12-12 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00481 |  | B
036909C-1025-PDS-0900-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps | B | 2018-12-10 | IFD | OL1-2G30-2586 | PE | 2018-12-12 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00481 |  | B
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | B | 2018-12-10 | IFD | OL1-2G30-2663 | PE | 2018-12-12 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00481 |  | B
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | B | 2018-12-10 | IFD | OL1-2G30-2816 | PE | 2018-12-12 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00481 |  | B
036909C-1053-PDS-0900-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | C | 2018-10-25 | IFD | OL1-2G30-5352 | PE | 2018-10-26 | 036909C-JVD-TRN-00234 | 036909C-JVD-TRN-00234 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00075 |  | C
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | C | 2018-10-25 | IFD | OL1-2G30-5361 | PE | 2018-10-26 | 036909C-JVD-TRN-00234 | 036909C-JVD-TRN-00234 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00075 |  | C
036909C-1019-PDS-1000-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | C | 2018-10-29 | IFD | OL1-2G30-1950 | PE | 2018-10-30 | 036909C-JVD-TRN-00242 | 036909C-JVD-TRN-00242 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00242 |  | C
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet - Decoking Air Compressor Package | C | 2018-10-31 | IFQ | OL1-2M03-1950 | ME | 2018-11-01 | 036909C-JVD-TRN-00261 | 036909C-JVD-TRN-00261 | IFI |  | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00261 |  | C
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | C | 2018-10-31 | IFQ | OL1-2M03-2200 | ME | 2018-11-06 | 036909C-JVD-TRN-00280 | 036909C-JVD-TRN-00280 | IFI |  | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-ME-00280 |  | C
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | C | 2018-11-27 | IFD | OL1-2G30-2330 | PE | 2018-11-28 | 036909C-JVD-TRN-00384 | 036909C-JVD-TRN-00384 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00384 |  | C
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps | C | 2018-11-26 | IFQ | OL1-2M03-5361 | ME | 2018-11-28 | 036909C-JVD-TRN-00388 | 036909C-JVD-TRN-00388 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00388 |  | C
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum | C | 2018-11-30 | IFD | OL1-2G30-2540 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | C
036909C-1026-PDS-0500-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer | C | 2018-11-30 | IFD | OL1-2G30-2630 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | C
036909C-1024-SP-0510-2450 | Mechanical Equipment Data Sheet - LP Depropanizer | C | 2018-11-30 | IFQ | OL1-2M03-2450 | ME | 2018-12-05 | 036909C-JVD-TRN-00412 | 036909C-JVD-TRN-00412 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00412 |  | C
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | C | 2018-11-30 | IFQ | OL1-2M03-2660 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00415 |  | C
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | C | 2018-12-04 | IFD | OL1-2G30-2635 | PE | 2018-12-07 | 036909C-JVD-TRN-00438 | 036909C-JVD-TRN-00438 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00438 |  | C
036909C-1026-PDS-0600-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers | C | 2018-12-04 | IFD | OL1-2G30-2645 | PE | 2018-12-07 | 036909C-JVD-TRN-00438 | 036909C-JVD-TRN-00438 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00438 |  | C
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | C | 2018-12-05 | IFD | OL1-2G30-2120 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00437 |  | C
036909C-1025-PDS-0600-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | C | 2018-12-07 | IFD | OL1-2G30-2502 | PE | 2018-12-11 | 036909C-JVD-TRN-00475 | 036909C-JVD-TRN-00475 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00475 |  | C
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | C | 2018-11-28 | IFQ | OL1-2M03-5109 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | C
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet - SHP BFW Pumps | C | 2018-11-28 | IFQ | OL1-2M03-5101 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | C
036909C-1000-RT-200 | Firefighting basic design report for package A1 | 0 | 2018-08-10 | IFI | OL1-2W90-0001 | PM | 2018-08-10 | 036909C-JVD-TRN-00020 | 036909C-JVD-TRN-00020 | IFI |  | 2018-08-20 | R2-Comments as noted | TPSK-LSPA1-T-PC-00020 |  | z0
036909C-1000-JSS-0400-02 | Marking For Vessel & Heat Exchanger | 0 | 2018-09-10 | IMP | OL1-2R03-0102 | ME | 2018-09-12 | 036909C-JVD-TRN-00042 | 036909C-JVD-TRN-00042 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00042 |  | z0
036909C-1000-JSS-0660-01 | Plate Heat Exchanger | 0 | 2018-09-10 | IMP | OL1-2R03-0006 | ME | 2018-09-12 | 036909C-JVD-TRN-00042 | 036909C-JVD-TRN-00042 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00042 |  | z0
036909C-1000-JSS-0900-0001 | ME-028 Mechanical Seal | 0 | 2018-09-14 | IMP | OL1-2R03-0028 | ME | 2018-09-17 | 036909C-JVD-TRN-00057 | 036909C-JVD-TRN-00057 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00057 |  | z0
036909C-1000-JSD-0001-0002 | Units Of Measurement | 0 | 2018-09-20 | IMP | OL1-2R07-0018 | ME | 2018-09-24 | 036909C-JVD-TRN-00080 | 036909C-JVD-TRN-00080 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00080 |  | z0
036909C-1000-JSS-1682-0001 | Electrical Heat Tracing | 0 | 2018-09-20 | IMP | OL1-2R05-0037 | EE | 2018-09-24 | 036909C-JVD-TRN-00079 | 036909C-JVD-TRN-00079 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00079 |  | z0
036909C-1000-JSS-1691-0001 | Electrical Motos Up To 300 kW | 0 | 2018-09-20 | IMP | OL1-2R05-0010 | EE | 2018-09-24 | 036909C-JVD-TRN-00079 | 036909C-JVD-TRN-00079 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00079 |  | z0
036909C-1000-JSS-0570-01 | Job Specification For Supply Of Column Internals | 0 | 2018-09-20 | IMP | OL1-2R03-0052 | ME | 2018-09-24 | 036909C-JVD-TRN-00081 | 036909C-JVD-TRN-00081 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00081 |  | z0
036909C-1000-JSS-1820-01 | Job Specification For Supply Of Equipment Ladders And Platforms | 0 | 2018-09-20 | IFR | OL1-2R03-0053 | ME | 2018-09-24 | 036909C-JVD-TRN-00081 | 036909C-JVD-TRN-00081 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00081 |  | z0
036909C-1000-PLG-313 | Six (6) Week Look-Head Schedule | 0 | 2018-09-26 | IFI | OL1-2B91-0001 | PC | 2018-09-27 | 036909C-JVD-TRN-00096 | 036909C-JVD-TRN-00096 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00096 |  | z0
036909C-1000-JSD-0001 | Project Design Basis | 0 | 2018-09-26 | IMP | OL1-2R07-0026 | ME | 2018-09-28 | 036909C-JVD-TRN-00110 | 036909C-JVD-TRN-00110 | IFR | 2018-10-11 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00110 |  | z0
036909C-1000-STC-1890-080 | Construction Standards For Ladders & Platforms Attached To Pressure Equipment | 0 | 2018-10-01 | IMP | OL1-2R03-0055 | ME | 2018-10-03 | 036909C-JVD-TRN-00120 | 036909C-JVD-TRN-00120 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00120 |  | z0
036909C-1000-JSD-1501-0003 | Instrument Inspection And Test Plan | 0 | 2018-09-28 | IMP | OL1-2R06-0023 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-JSD-1545-0001 | Pressure Safety Valve | 0 | 2018-09-28 | IMP | OL1-2R06-0021 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-JSD-1547-0001 | Flow Measurement | 0 | 2018-09-28 | IMP | OL1-2R06-0003 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-JSD-1572-0001 | Instrument Construction Material | 0 | 2018-09-28 | IMP | OL1-2R06-0010 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-JSD-1572-0004 | Instrument Installation | 0 | 2018-09-28 | IMP | OL1-2R08-0003 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-SL-0000-02 | Subvendor List For Compressor And Turboexpander - Abstract From Approved Vendor List | 0 | 2018-10-05 | IMP | OL1-2C01-0001 | PL | 2018-10-05 | 036909C-JVD-TRN-00134 | 036909C-JVD-TRN-00134 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00134 |  | z0
036909C-1006-JSS-0117-0029 | ME-029 Centrifugal Blower for 36M and 132U Furnace | 0 | 2018-10-16 | IMP | OL1-2R03-0029 | ME | 2018-10-17 | 036909C-JVD-TRN-00185 | 036909C-JVD-TRN-00185 | IFI |  | 2018-11-05 | Transmitted | TPSK-LSPA1-T-ME-00185 |  | z0
036909C-1006-JSS-0117-1004 | PIP-004 Piping Welding Specification for 36M and 132U Furnace | 0 | 2018-10-15 | IMP | OL1-2R04-1004 | ME | 2018-10-16 | 036909C-JVD-TRN-00184 | 036909C-JVD-TRN-00184 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00184 |  | z0
036909C-1000-NM-107 | Master Document Index (MDI) | 0 | 2018-10-16 | IFI | OL1-2W91-0001 | PC | 2018-10-17 | 036909C-JVD-TRN-00186 | 036909C-JVD-TRN-00186 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PM-00186 |  | z0
036909C-1006-JSS-0117-0005 | ME-005 Double Jacket Pipe Heat Exchangers for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R03-0005 | ME | 2018-10-23 | 036909C-JVD-TRN-00212 | 036909C-JVD-TRN-00212 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00212 |  | z0
036909C-1006-JSS-0117-0007 | PIP-007 Marking of Piping Material for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R04-0007 | ME | 2018-10-23 | 036909C-JVD-TRN-00213 | 036909C-JVD-TRN-00213 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00213 |  | z0
036909C-1006-JSS-0117-0009 | SP-009 Painting for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL-2R07-0009 | ME | 2018-10-23 | 036909C-JVD-TRN-00214 | 036909C-JVD-TRN-00214 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00214 |  | z0
036909C-1006-JSS-0117-1001 | Approved Vendor List for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2M91-1001 | ME | 2018-10-23 | 036909C-JVD-TRN-00211 | 036909C-JVD-TRN-00211 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00211 |  | z0
036909C-1006-JSS-0117-3004 | ME-004 Shell and Tube Heat Exchangers for 36M and 132U Furnace | 0 | 2018-10-18 | IFI | OL1-2R03-1004 | ME | 2018-10-24 | 036909C-JVD-TRN-00221 | 036909C-JVD-TRN-00221 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00221 |  | z0
036909C-1011-PDS-0117-1102 | Anticipated Operating Conditions - 10-H-1100 - USC 36M Gas Cracking Furnace | 0 | 2018-10-24 | IFI | OL1-2G30-1102 | PE | 2018-10-24 | 036909C-JVD-TRN-00224 | 036909C-JVD-TRN-00224 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00224 |  | z0
036909C-1012-PDS-0117-1202 | Anticipated Operating Conditions - 10-H-1200/1600 - USC 132U Liquid Cracking Furnace | 0 | 2018-10-24 | IFI | OL1-2G30-1202 | PE | 2018-10-24 | 036909C-JVD-TRN-00224 | 036909C-JVD-TRN-00224 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00224 |  | z0
036909C-1012-JSS-0125-2003 | Project Specification for Cast Intermediate Tube Supports | 0 | 2018-10-15 | IFI | OL1-2M92-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00232 | 036909C-JVD-TRN-00232 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00232 |  | z0
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | 0 | 2018-10-26 | IMP | OL1-2R03-0050 | ME | 2018-10-31 | 036909C-JVD-TRN-00245 | 036909C-JVD-TRN-00245 | IFR | 2018-11-14 | 2018-11-26 | Transmitted | TPSK-LSPA1-T-ME-00245 |  | z0
036909C-1000-JSS-0400-01 | Job Specification For Supply Of Pressure Vessels | 0 | 2018-10-26 | IMP | OL1-2R03-0051 | ME | 2018-10-31 | 036909C-JVD-TRN-00249 | 036909C-JVD-TRN-00249 | IFR | 2018-11-14 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00249 |  | z0
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | 0 | 2018-10-26 | IMP | OL1-2R03-0054 | ME | 2018-10-31 | 036909C-JVD-TRN-00256 | 036909C-JVD-TRN-00256 | IFR | 2018-11-14 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00256 |  | z0
036909C-1000-JSD-1600-0004 | LIGHTING SYSTEM | 0 | 2018-09-20 | IMP | OL1-2R05-0014 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258 |  | z0
036909C-1000-JSD-1600-0007 | Functional and Schematic Diagram | 0 | 2018-09-20 | IMP | OL1-2R05-0029 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258 |  | z0
036909C-1000-JSD-1600-0010 | Earthing And Lightning Protection | 0 | 2018-09-20 | IMP | OL1-2R05-0015 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258 |  | z0
036909C-1006-JSS-0117-3001 | ME-001 Pressure Vessel for 36M and 132U Furnace | 0 | 2018-10-18 | IFE | OL1-2R03-1001 | ME | 2018-11-07 | 036909C-JVD-TRN-00262 | 036909C-JVD-TRN-00262 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00262 |  | z0
036909C-1000-JSS-1622-0001 | Miscellaneous Equipment | 0 | 2018-09-20 | IMP | OL1-2R05-0022 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1641-0001 | Oil Filled Distribution Transformer | 0 | 2018-09-20 | IMP | OL1-2R05-0003 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1652-0001 | Medium Voltage Switchgear | 0 | 2018-09-20 | IMP | OL1-2R05-0006 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1655-0001 | Low Voltage Bus Duct | 0 | 2018-09-20 | IMP | OL1-2R05-0038 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1656-0001 | Power Capacitors | 0 | 2018-09-20 | IMP | OL1-2R05-0021 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1671-0001 | Uninterruptible Power Supplies | 0 | 2018-09-20 | IMP | OL1-2R05-0012 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1684-0001 | Cathodic Protection | 0 | 2018-09-20 | IMP | OL1-2R05-0016 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1693-0001 | Low Voltage Variable Voltage Variable Frequency System | 0 | 2018-09-20 | IMP | OL1-2R05-0023 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1694-0001 | Medium Voltage Variable Voltage Variable Frequency System | 0 | 2018-09-20 | IMP | OL1-2R05-0040 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-4123-0001 | Diesel Engine Generator | 0 | 2018-09-20 | IMP | OL1-2R05-0017 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1011-DW-0125-1301 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-1301 | ME | 2018-11-07 | 036909C-JVD-TRN-00286 | 036909C-JVD-TRN-00286 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00286 |  | z0
036909C-1011-DW-0125-1302 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-1302 | ME | 2018-11-07 | 036909C-JVD-TRN-00286 | 036909C-JVD-TRN-00286 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00286 |  | z0
036909C-1012-DW-0125-2302 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-2302 | ME | 2018-11-08 | 036909C-JVD-TRN-00289 | 036909C-JVD-TRN-00289 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00289 |  | z0
036909C-1012-DW-0125-2301 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-2301 | ME | 2018-11-08 | 036909C-JVD-TRN-00289 | 036909C-JVD-TRN-00289 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00289 |  | z0
036909C-1000-JSS-1692-0001 | Electrical Motors Greater Than 300 kW | 0 | 2018-09-20 | IMP | OL1-2R05-0011 | EE | 2018-11-08 | 036909C-JVD-TRN-00293 | 036909C-JVD-TRN-00293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00293 |  | z0
036909C-1000-JSS-1654-0001 | Low Voltage Switchgear And Motor Control Center | 0 | 2018-09-20 | IFE | OL1-2R05-0008 | EE | 2018-11-12 | 036909C-JVD-TRN-00309 | 036909C-JVD-TRN-00309 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00309 |  | z0
036909C-1000-JSS-1657-0001 | Low Voltage Distribution Panel | 0 | 2018-09-20 | IMP | OL1-2R05-0007 | EE | 2018-11-12 | 036909C-JVD-TRN-00309 | 036909C-JVD-TRN-00309 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00309 |  | z0
036909C-1000-STC-1390-0001 | Piping Standard Construction Drawings | 0 | 2018-11-12 | CAN | OL1-2P92-0003 | MP | 2018-11-16 | 036909C-JVD-TRN-00325 | 036909C-JVD-TRN-00325 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00325 | Replaced by doc. OL1-2P92-0050 (included as attachment) | z0
036909C-1000-STD-1380-0001 | Piping Design Standard Drawings | 0 | 2018-11-12 | CAN | OL1-2P92-0002 | MP | 2018-11-16 | 036909C-JVD-TRN-00325 | 036909C-JVD-TRN-00325 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00325 | Replaced by doc. OL1-2R04-0002 (included as attachment) | z0
036909C-1000-SL-0000-04 | Subvendor list for Pumps | 0 | 2018-11-16 | IMP | OL1-2C01-0003 | PL | 2018-11-19 | 036909C-JVD-TRN-00333 | 036909C-JVD-TRN-00333 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00333 |  | z0
036909C-1000-SL-0000-03 | Subvendor list for PSA/Deareator/Filter Package | 0 | 2018-11-15 | IMP | OL1-2C01-0002 | PL | 2018-11-19 | 036909C-JVD-TRN-00333 | 036909C-JVD-TRN-00333 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00333 |  | z0
036909C-1000-JSS-1040-0001 | ME-017 Root Blower | 0 | 2018-11-16 | IMP | OL1-2R03-0017 | ME | 2018-11-19 | 036909C-JVD-TRN-00334 | 036909C-JVD-TRN-00334 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00334 |  | z0
036909C-1000-JSD-1580-0003 | General Design Rules For Instrumentation And Control Of Packaged Equipment | 0 | 2018-11-29 | IMP | OL1-2R06-0035 | IE | 2018-11-29 | 036909C-JVD-TRN-00393 | 036909C-JVD-TRN-00393 | IFR | 2018-12-14 |  | Transmitted | TPSK-LSPA1-T-IE-00393 |  | z0
036909C-1000-JSD-1600-008 | General Design Rules For Smartplant Electrical | 0 | 2018-11-09 | IFI | OL1-2E92-0001 | EE | 2018-11-29 | 036909C-JVD-TRN-00396 | 036909C-JVD-TRN-00396 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00396 | Ex Document Client Reference: OL1-2R05-0043 | z0
036909C-1012-DW-0130-2554 | USC 132U Cracking Furnace Peep Door Details | 0 | 2018-12-04 | IFI | OL1-2M06-2554 | ME | 2018-12-04 | 036909C-JVD-TRN-00422 | 036909C-JVD-TRN-00422 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00422 |  | z0
036909C-1012-DW-0131-2546 | USC 132U Cracking Furnace Name Plate Details | 0 | 2018-12-04 | IFI | OL1-2K32-2546 | ME | 2018-12-04 | 036909C-JVD-TRN-00423 | 036909C-JVD-TRN-00423 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00423 |  | z0
036909C-1000-JSD-1600-0001 | General Electrical Design | 0 | 2018-12-03 | IMP | OL1-2R05-0001 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424 |  | z0
036909C-1000-JSD-1600-0002 | Electrical System Design | 0 | 2018-12-03 | IMP | OL1-2R05-0002 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424 |  | z0
036909C-1000-JSD-1600-0009 | Document Template | 0 | 2018-12-03 | IMP | OL1-2R05-0036 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424 |  | z0
036909C-1000-JSS-1621-0001 | Power Control And Fiber Optic Cables | 0 | 2018-12-03 | IMP | OL1-2R05-0018 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425 |  | z0
036909C-1000-JSS-1641-0002 | Neutral Grounding Resistor | 0 | 2018-12-03 | IMP | OL1-2R05-0027 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425 |  | z0
036909C-1012-JSS-0154-2007 | Project Specification For SLE and USX Exchangers | 0 | 2018-11-28 | IMP | OL1-2M92-2007 | ME | 2018-12-05 | 036909C-JVD-TRN-00427 | 036909C-JVD-TRN-00427 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00427 |  | z0
036909C-1012-JSS-0154-2008 | Project Specification For Transfer Line Exchangers | 0 | 2018-11-28 | IMP | OL1-2M92-2008 | ME | 2018-12-05 | 036909C-JVD-TRN-00428 | 036909C-JVD-TRN-00428 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00428 |  | z0
036909C-1012-SP-0127-2001 | Particular Technical Specification for Convection Tubes | 0 | 2018-12-04 | IFP | OL1-2M57-2001 | ME | 2018-12-10 | 036909C-JVD-TRN-00450 | 036909C-JVD-TRN-00450 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00450 |  | z0
036909C-1012-MR-0127-2001 | Material Requisition for Convection Tubes | 0 | 2018-12-06 | IFP | OL1-2M55-2001 | ME | 2018-12-10 | 036909C-JVD-TRN-00450 | 036909C-JVD-TRN-00450 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00450 |  | z0
036909C-1012-SP-0154-2003 | Particular Techanical Specification for Quench Exchangers | 0 | 2018-12-06 | IFP | OL1-2M57-2003 | ME | 2018-12-10 | 036909C-JVD-TRN-00466 | 036909C-JVD-TRN-00466 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00466 |  | z0
036909C-1012-MR-0154-2003 | Material Requisition for Quench Exchangers | 0 | 2018-12-07 | IFP | OL1-2M55-2003 | ME | 2018-12-10 | 036909C-JVD-TRN-00466 | 036909C-JVD-TRN-00466 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00466 |  | z0
036909C-1012-JSS-0122-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces | 0 | 2018-12-07 | IMP | OL1-2M92-2001 | ME | 2018-12-11 | 036909C-JVD-TRN-00470 | 036909C-JVD-TRN-00470 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00470 |  | z0
036909C-1012-JSS-0122-2002 | Project Specification for Statically Cast Fittings For Radiant Coils and Transfer Lines in Cracking Furnaces | 0 | 2018-12-07 | IMP | OL1-2M92-2002 | ME | 2018-12-11 | 036909C-JVD-TRN-00471 | 036909C-JVD-TRN-00471 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00471 |  | z0
036909C-1011-DW-0122-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details | 0 | 2018-12-10 | IMP | OL1-2M06-1201 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1011-DW-0122-1202 | USC 36M Recycle Furnace Transfer Line And Clean Out Details | 0 | 2018-12-11 | IMP | OL1-2M06-1202 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1011-DW-0122-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details | 0 | 2018-12-11 | IMP | OL1-2M06-1203 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1012-DW-0122-2201 | USC 132U Cracking Furnace Radiant Coil Assembly and Details | 0 | 2018-12-11 | IMP | OL1-2M06-2201 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1012-DW-0122-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details | 0 | 2018-12-11 | IMP | OL1-2M06-2202 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1012-DW-0122-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | 0 | 2018-12-11 | IMP | OL1-2M06-2203 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1000-JSS-1661-0001 | Substation Monitoring And Control System | 0 | 2018-12-03 | IMP | OL1-2R05-0005 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425 |  | z0
036909C-1000-RT-200 | Fire Fighting Basic Design Report For Package A1 | 1 | 2018-09-28 | IFI | OL1-2W90-0001 | PC | 2018-10-17 | 036909C-JVD-TRN-00187 | 036909C-JVD-TRN-00187 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PM-00187 |  | z1
036909C-1000-NM-107 | Master Document Index (MDI) | 1 | 2018-11-21 | IFI | OL1-2W91-0001 | PC | 2018-11-23 | 036909C-JVD-TRN-00354 | 036909C-JVD-TRN-00354 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00354 |  | z1

## Foglio1
rev | fake rev
a | a
a | a
b | b
c | c
0 | z0
1 | z1