## Document
Document Reference | Document Title | Revision Number | Revision Date | Document Revision Object | Document Client Reference | Discipline | Transmittal Date | Transmittal Reference | Specific Transmittal Number | Required Action | Response Due Date | Actual Response Date | Document Status | Client Transmittal Ref Number | Remarks | Fake Rev
036909C-1006-JSS-0117-0009 | SP-009 Painting for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL-2R07-0009 | ME | 2018-10-23 | 036909C-JVD-TRN-00214 | 036909C-JVD-TRN-00214 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00214 |  | z0
036909C-1012-JSS-0000-9999 | General Supply Rules for Supplier Documentation | A | 2018-09-12 | IFI | OL1-2C93-0001 | PL | 2018-09-12 | 036909C-JVD-TRN-00043 | 036909C-JVD-TRN-00043 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PL-00043 |  | A
036909C-1000-JSD-1600-003 | General Design Rule For Package Equipment Electrical System | A | 2018-08-03 | IFR | OL1-2E04-6000 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | A
036909C-1000-JSD-1600-003 | General Design Rule for Package Equipment Electrical System | B | 2018-10-20 | IFR | OL1-2E04-6000 | EE | 2018-10-04 | 036909C-JVD-TRN-00126 | 036909C-JVD-TRN-00126 | IFR | 2018-10-18 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-EE-00126 | Ex Document Client Reference OL1-2R05-0042 | B
036909C-1000-SP-1652-1100 | Typical Data Sheet for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E05-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | A
036909C-1000-SP-1691-0100 | Typical Data Sheet for LV Motors | A | 2018-11-16 | IFQ | OL1-2E05-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00358 | 036909C-JVD-TRN-00358 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-EE-00358 |  | A
036909C-1000-SP-1691-0500 | Typical Data Sheet For Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E05-3500 | EE | 2018-11-26 | 036909C-JVD-TRN-00358 | 036909C-JVD-TRN-00358 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-EE-00358 |  | A
036909C-1000-MR-1652-0001 | Material Requisition for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E55-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | A
036909C-1000-MR-1691-0001 | Material Requisition For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E55-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00359 | 036909C-JVD-TRN-00359 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-EE-00359 |  | A
036909C-1000-SP-1652-0001 | Particular Technical Specification for Medium Voltage Switchgears | A | 2018-12-07 | IFQ | OL1-2E57-1100 | EE | 2018-12-11 | 036909C-JVD-TRN-00477 | 036909C-JVD-TRN-00477 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | A
036909C-1000-SP-1691-0001 | Particular Technical Specification For Low Voltage Motors Low Voltage Variable Voltage Variable Frequency System | A | 2018-11-16 | IFQ | OL1-2E57-3001 | EE | 2018-11-26 | 036909C-JVD-TRN-00359 | 036909C-JVD-TRN-00359 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-EE-00359 |  | A
036909C-1000-JSD-1600-008 | General Design Rule For Smartplant Electrical | A | 2018-08-03 | IFR | OL1-2E92-0001 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | A
036909C-1000-JSD-1600-008 | General Design Rules For Smartplant Electrical | 0 | 2018-11-09 | IFI | OL1-2E92-0001 | EE | 2018-11-29 | 036909C-JVD-TRN-00396 | 036909C-JVD-TRN-00396 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00396 | Ex Document Client Reference: OL1-2R05-0043 | z0
036909C-1000-JSD-0000-03 | JSD for P&ID Preparation | A | 2018-07-31 | IFA | OL1-2G01-0001 | PE | 2018-07-31 | 036909C-JVD-TRN-00006 | 036909C-JVD-TRN-00006 | IFR | 2018-08-13 | 2018-08-21 | Transmitted | TPSK-LSPA1-T-PE-00006 |  | A
036909C-1000-JSD-0000-0004 | Cold Box Design Specification | A | 2018-10-01 | IFR | OL1-2G01-0002 | PE | 2018-10-03 | 036909C-JVD-TRN-00123 | 036909C-JVD-TRN-00123 | IFR | 2018-10-17 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00123 |  | A
036909C-1000-JSD-0000-0005 | Plate-Fin Exchanger Design Specification | A | 2018-10-01 | IFR | OL1-2G01-0003 | PE | 2018-10-03 | 036909C-JVD-TRN-00123 | 036909C-JVD-TRN-00123 | IFR | 2018-10-17 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00123 |  | A
036909C-1000-DI-0007-0001 | Process Design Basis | A | 2018-07-20 | IFA | OL1-2G02-0001 | PE | 2018-07-30 | 036909C-JVD-TRN-00002 | 036909C-JVD-TRN-00002 | IFA | 2018-08-10 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00002 |  | A
036909C-1000-DI-0007-0002 | Equipment Basis Of Design | A | 2018-07-24 | IFA | OL1-2G02-0002 | PE | 2018-07-30 | 036909C-JVD-TRN-00002 | 036909C-JVD-TRN-00002 | IFA | 2018-08-10 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00002 |  | A
036909C-1000-DI-0007-0003 | Flare and Blowdown System Design Basis | A | 2018-09-06 | IFA | OL1-2G02-0003 | PE | 2018-09-06 | 036909C-JVD-TRN-00034 | 036909C-JVD-TRN-00034 | IFA | 2018-09-20 | 2018-09-28 | R2-Comments as noted | TPSK-LSPA1-T-PE-00034 |  | A
036909C-1000-DI-0007-0006 | Furnace Process Basis of Design | A | 2018-07-26 | IFA | OL1-2G02-0006 | PE | 2018-07-31 | 036909C-JVD-TRN-00004 | 036909C-JVD-TRN-00004 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00004 |  | A
036909C-1000-DI-0007-0006 | Furnace Process Basis of Design | B | 2018-11-27 | IFD | OL1-2G02-0006 | PE | 2018-11-27 | 036909C-JVD-TRN-00376 | 036909C-JVD-TRN-00376 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00376 |  | B
036909C-1010-DI-0007-1001 | Area Basis of Design - 10 Feed Preparation | A | 2018-08-06 | IFA | OL1-2G05-1001 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | A
036909C-1020-DI-0007-2001 | Area Basis of Design - 20-21 Quench and Dilution Steam | A | 2018-08-06 | IFA | OL1-2G05-2001 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | A
036909C-1022-DI-0007-2201 | Area Basis of Design - 22-24 Compresssion Train | A | 2018-08-09 | IFA | OL1-2G05-2201 | PE | 2018-08-13 | 036909C-JVD-TRN-00022 | 036909C-JVD-TRN-00022 | IFA | 2018-08-27 | 2018-09-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00022 |  | A
036909C-1023-DI-0007-2301 | Area Basis of Design - 23 Caustic and Spent Caustic Pretreatment | A | 2018-08-08 | IFA | OL1-2G05-2301 | PE | 2018-08-08 | 036909C-JVD-TRN-00014 | 036909C-JVD-TRN-00014 | IFA | 2018-08-22 | 2018-08-31 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00014 |  | A
036909C-1025-DI-0007-2501 | Area Basis of Design - 25 Cold Fractionation | A | 2018-08-06 | IFA | OL1-2G05-2501 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | A
036909C-1026-DI-0007-2601 | Area Basis of Design - 26 Hot Fractionation | A | 2018-08-07 | IFA | OL1-2G05-2601 | PE | 2018-08-08 | 036909C-JVD-TRN-00014 | 036909C-JVD-TRN-00014 | IFA | 2018-08-22 | 2018-08-31 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00014 |  | A
036909C-1026-DI-0007-2602 | Area Basis of Design - 262 C3 Hydrogenation | A | 2018-11-09 | IFA | OL1-2G05-2602 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307 | IFA | 2018-11-26 |  | Transmitted | TPSK-LSPA1-T-PE-00307 |  | A
036909C-1027-DI-0007-2701 | Area Basis of Design - 270 Gasoline Hydrogenation -GHU-1 | A | 2018-11-09 | IFA | OL1-2G05-2701 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307 | IFA | 2018-11-26 |  | Transmitted | TPSK-LSPA1-T-PE-00307 |  | A
036909C-1027-DI-0007-2702 | Area Basis of Design - Area 275 C4-C5 Hydrogenation | A | 2018-11-09 | IFA | OL1-2G05-2702 | PE | 2018-11-12 | 036909C-JVD-TRN-00307 | 036909C-JVD-TRN-00307 | IFA | 2018-11-26 |  | Transmitted | TPSK-LSPA1-T-PE-00307 |  | A
036909C-1028-DI-0007-2801 | Area Basis of Design - 28 Refrigeration | A | 2018-08-09 | IFA | OL1-2G05-2801 | PE | 2018-08-13 | 036909C-JVD-TRN-00022 | 036909C-JVD-TRN-00022 | IFA | 2018-08-27 | 2018-09-05 | A1-Approved without comments | TPSK-LSPA1-T-PE-00022 |  | A
036909C-1030-DI-0007-3001 | Area Basis of Design - 30 BDU | A | 2018-10-09 | IFA | OL1-2G05-3001 | PE | 2018-10-09 | 036909C-JVD-TRN-00150 | 036909C-JVD-TRN-00150 | IFA | 2018-10-23 |  | Transmitted | TPSK-LSPA1-T-PE-00150 |  | A
036909C-1050-DI-0007-5001 | Area Basis of Design - 50 ISBL Supporting Utilities | A | 2018-07-25 | IFA | OL1-2G05-5001 | PE | 2018-07-31 | 036909C-JVD-TRN-00003 | 036909C-JVD-TRN-00003 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00003 |  | A
036909C-1053-DI-0007-5301 | Area Basis of Design - 53 Cooling Tower System | A | 2018-07-25 | IFA | OL1-2G05-5301 | PE | 2018-07-31 | 036909C-JVD-TRN-00003 | 036909C-JVD-TRN-00003 | IFA | 2018-08-13 | 2018-08-17 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00003 |  | A
036909C-1053-DI-0007-5301 | Area Basis of Design - 53 Cooling Tower System | B | 2018-09-24 | IFD | OL1-2G05-5301 | PE | 2018-09-26 | 036909C-JVD-TRN-00093 | 036909C-JVD-TRN-00093 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00003 |  | B
036909C-1055-DI-0007-5501 | Area Basis of Design - 55 Flare System | A | 2018-08-09 | IFA | OL1-2G05-5501 | PE | 2018-08-09 | 036909C-JVD-TRN-00016 | 036909C-JVD-TRN-00016 | IFA | 2018-08-23 | 2018-08-29 | A3-Not Approve Re-Submit For Re-Approval | TPSK-LSPA1-T-PE-00016 |  | A
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | A | 2018-08-03 | IFA | OL1-2G05-5601 | PE | 2018-08-07 | 036909C-JVD-TRN-00011 | 036909C-JVD-TRN-00011 | IFA | 2018-08-21 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | A
036909C-1056-DI-0007-5601 | Area Basis of Design - 56 Waste Water Treatment System | B | 2018-09-13 | IFD | OL1-2G05-5601 | PE | 2018-09-26 | 036909C-JVD-TRN-00091 | 036909C-JVD-TRN-00091 | IFI |  | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00011 |  | B
036909C-1000-NM-0014-0001 | Flare Load Summary | A | 2018-10-23 | IFR | OL1-2G22-0001 | PE | 2018-10-25 | 036909C-JVD-TRN-00229 | 036909C-JVD-TRN-00229 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00229 |  | A
036909C-1010-PDS-0800-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum | A | 2018-10-25 | IFR | OL1-2G30-1000 | PE | 2018-10-25 | 036909C-JVD-TRN-00227 | 036909C-JVD-TRN-00227 | IFR | 2018-11-08 | 2018-12-05 | R1-No comments | TPSK-LSPA1-T-PE-00227 |  | A
036909C-1010-PDS-0800-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum | B | 2018-12-07 | IFD | OL1-2G30-1000 | PE | 2018-12-10 | 036909C-JVD-TRN-00463 | 036909C-JVD-TRN-00463 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00463 |  | B
036909C-1010-PDS-0600-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer | A | 2018-10-15 | IFR | OL1-2G30-1001 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176 |  | A
036909C-1010-PDS-0600-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer | B | 2018-12-06 | IFD | OL1-2G30-1001 | PE | 2018-12-10 | 036909C-JVD-TRN-00451 | 036909C-JVD-TRN-00451 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00451 |  | B
036909C-1010-PDS-0600-1003 | Process Equipment Datasheet - 10-E-1001 - LPG Steam Vaporizer | A | 2018-10-15 | IFR | OL1-2G30-1003 | PE | 2018-10-16 | 036909C-JVD-TRN-00179 | 036909C-JVD-TRN-00179 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-PE-00179 |  | A
036909C-1010-PDS-0600-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater | A | 2018-10-15 | IFR | OL1-2G30-1005 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176 |  | A
036909C-1010-PDS-0600-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater | A | 2018-10-15 | IFR | OL1-2G30-1015 | PE | 2018-10-15 | 036909C-JVD-TRN-00176 | 036909C-JVD-TRN-00176 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00176 |  | A
036909C-1010-PDS-0600-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater | B | 2018-12-04 | IFD | OL1-2G30-1015 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | A | 2018-10-18 | IFR | OL1-2G30-1020 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1010-PDS-0600-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater | B | 2018-12-04 | IFD | OL1-2G30-1020 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1010-PDS-0600-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater | A | 2018-10-18 | IFR | OL1-2G30-1051 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1010-PDS-0600-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater | B | 2018-12-04 | IFD | OL1-2G30-1051 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00436 |  | B
036909C-1011-PDS-0117-1101 | Process Equipment Datasheet - 10-H-1100 - 36M Cracking Furnace Yields | A | 2018-10-15 | IFR | OL1-2G30-1101 | PE | 2018-10-22 | 036909C-JVD-TRN-00204 | 036909C-JVD-TRN-00204 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00204 |  | A
036909C-1011-PDS-0117-1101 | Process Equipment Datasheet - 10-H-1100 - USM 36M Cracking Furnace Yields | B | 2018-11-15 | IFD | OL1-2G30-1101 | PE | 2018-11-26 | 036909C-JVD-TRN-00360 | 036909C-JVD-TRN-00360 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00360 |  | B
036909C-1011-PDS-0117-1102 | Anticipated Operating Conditions - 10-H-1100 - USC 36M Gas Cracking Furnace | 0 | 2018-10-24 | IFI | OL1-2G30-1102 | PE | 2018-10-24 | 036909C-JVD-TRN-00224 | 036909C-JVD-TRN-00224 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00224 |  | z0
036909C-1011-PDS-0191-1106 | Process Equipment Datasheet - 10-H-1100 - USC 36M Burner | A | 2018-10-26 | IFR | OL1-2G30-1106 | PE | 2018-10-30 | 036909C-JVD-TRN-00241 | 036909C-JVD-TRN-00241 | IFR | 2018-11-12 |  | Transmitted | TPSK-LSPA1-T-PE-00241 |  | A
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - 36M Cracking Furnace Steam Drum | A | 2018-10-11 | IFR | OL1-2G30-1107 | PE | 2018-10-11 | 036909C-JVD-TRN-00159 | 036909C-JVD-TRN-00159 | IFR | 2018-10-25 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00159 |  | A
036909C-1011-PDS-0811-1107 | Process Equipment Datasheet - 10-D-1100 - USC 36M Cracking Furnace Steam Drum | B | 2018-12-10 | IFD | OL1-2G30-1107 | PE | 2018-12-12 | 036909C-JVD-TRN-00478 | 036909C-JVD-TRN-00478 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00478 |  | B
036909C-1011-PDS-0630-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1108 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1011-PDS-0630-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger | B | 2018-12-05 | IFD | OL1-2G30-1108 | PE | 2018-12-07 | 036909C-JVD-TRN-00432 | 036909C-JVD-TRN-00432 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00432 |  | B
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1109 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1011-PDS-0610-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1109 | PE | 2018-12-10 | 036909C-JVD-TRN-00459 | 036909C-JVD-TRN-00459 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00459 |  | B
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1110 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1011-PDS-0610-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1110 | PE | 2018-12-10 | 036909C-JVD-TRN-00459 | 036909C-JVD-TRN-00459 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00459 |  | B
036909C-1011-PDS-1040-1111 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | B | 2018-10-23 | IFD | OL1-2G30-1111 | PE | 2018-10-24 | 036909C-JVD-TRN-00222 | 036909C-JVD-TRN-00222 | IFI | 2018-11-08 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00222 |  | B
036909C-1011-PDS-0853-1112 | Process Equipment Datasheet - 10-M-1100 - USC 36M Attemperator | A | 2018-11-14 | IFR | OL1-2G30-1112 | PE | 2018-11-16 | 036909C-JVD-TRN-00330 | 036909C-JVD-TRN-00330 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-PE-00330 |  | A
036909C-1012-PDS-0117-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields | A | 2018-10-15 | IFR | OL1-2G30-1201 | PE | 2018-10-22 | 036909C-JVD-TRN-00204 | 036909C-JVD-TRN-00204 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00204 |  | A
036909C-1012-PDS-0117-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields | B | 2018-11-27 | IFD | OL1-2G30-1201 | PE | 2018-11-27 | 036909C-JVD-TRN-00372 | 036909C-JVD-TRN-00372 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00372 |  | B
036909C-1012-PDS-0117-1202 | Anticipated Operating Conditions - 10-H-1200/1600 - USC 132U Liquid Cracking Furnace | 0 | 2018-10-24 | IFI | OL1-2G30-1202 | PE | 2018-10-24 | 036909C-JVD-TRN-00224 | 036909C-JVD-TRN-00224 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00224 |  | z0
036909C-1012-PDS-0191-1206 | Process Equipment Datasheet - 10-H-1200 - 1600 - USC 132U Burner | A | 2018-10-26 | IFR | OL1-2G30-1206 | PE | 2018-10-30 | 036909C-JVD-TRN-00241 | 036909C-JVD-TRN-00241 | IFR | 2018-11-12 |  | Transmitted | TPSK-LSPA1-T-PE-00241 |  | A
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200-1600 - 132U Cracking Furnace Steam Drum | A | 2018-10-11 | IFR | OL1-2G30-1207 | PE | 2018-10-11 | 036909C-JVD-TRN-00159 | 036909C-JVD-TRN-00159 | IFR | 2018-10-25 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00159 |  | A
036909C-1012-PDS-0811-1207 | Process Equipment Datasheet - 10-D-1200-1600 - USC 132U Cracking Furnace Steam Drum | B | 2018-12-10 | IFD | OL1-2G30-1207 | PE | 2018-12-12 | 036909C-JVD-TRN-00478 | 036909C-JVD-TRN-00478 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00478 |  | B
036909C-1012-PDS-0630-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1208 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1012-PDS-0630-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger | B | 2018-12-05 | IFD | OL1-2G30-1208 | PE | 2018-12-07 | 036909C-JVD-TRN-00433 | 036909C-JVD-TRN-00433 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00433 |  | B
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger | A | 2018-10-25 | IFR | OL1-2G30-1209 | PE | 2018-10-29 | 036909C-JVD-TRN-00237 | 036909C-JVD-TRN-00237 | IFR | 2018-11-12 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00237 |  | A
036909C-1012-PDS-0610-1209 | Process Equipment Datasheet - 10-E-1210 - 10-E-1610 - USC 132U TLX Quench Exchanger | B | 2018-12-06 | IFD | OL1-2G30-1209 | PE | 2018-12-10 | 036909C-JVD-TRN-00449 | 036909C-JVD-TRN-00449 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00449 |  | B
036909C-1012-PDS-1040-1211 | Process Equipment Datasheet - 10-C-1200 1600 - USC 132U Induced Draft Fan | B | 2018-10-23 | IFD | OL1-2G30-1211 | PE | 2018-10-24 | 036909C-JVD-TRN-00222 | 036909C-JVD-TRN-00222 | IFI | 2018-11-08 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00222 |  | B
036909C-1012-PDS-0853-1212 | Process Equipment Datasheet - 10-M-1200 1600 - USC 132U Attemperator | A | 2018-11-14 | IFR | OL1-2G30-1212 | PE | 2018-11-16 | 036909C-JVD-TRN-00330 | 036909C-JVD-TRN-00330 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-PE-00330 |  | A
036909C-1012-PDS-1542-1213 | Process Equipment Datasheet - 10-M-1201 - 1601 A-F - USC 132U Dilution Steam Mixing Tee | A | 2018-12-04 | IFR | OL1-2G30-1213 | PE | 2018-12-07 | 036909C-JVD-TRN-00434 | 036909C-JVD-TRN-00434 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00434 |  | A
036909C-1019-PDS-1000-1950 | Process Equipment Data Sheet - 10-PK-1950 - Decoke Air Compressor Package | A | 2018-08-29 | IFA | OL1-2G30-1950 | PE | 2018-08-29 | 036909C-JVD-TRN-00031 | 036909C-JVD-TRN-00031 | IFA |  | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00031 |  | A
036909C-1019-PDS-1000-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | B | 2018-09-28 | IFD | OL1-2G30-1950 | PE | 2018-09-28 | 036909C-JVD-TRN-00114 | 036909C-JVD-TRN-00114 | IFI |  | 2018-10-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00114 |  | B
036909C-1019-PDS-1000-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg | C | 2018-10-29 | IFD | OL1-2G30-1950 | PE | 2018-10-30 | 036909C-JVD-TRN-00242 | 036909C-JVD-TRN-00242 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00242 |  | C
036909C-1020-PDS-0500-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower | A | 2018-10-11 | IFR | OL1-2G30-2000 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162 |  | A
036909C-1020-PDS-0500-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower | B | 2018-11-29 | IFD | OL1-2G30-2000 | PE | 2018-12-04 | 036909C-JVD-TRN-00402 | 036909C-JVD-TRN-00402 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00402 |  | B
036909C-1020-PDS-0900-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | A | 2018-09-20 | IFA | OL1-2G30-2006 | PE | 2018-09-20 | 036909C-JVD-TRN-00071 | 036909C-JVD-TRN-00071 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00071 |  | A
036909C-1020-PDS-0900-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps | B | 2018-10-18 | IFD | OL1-2G30-2006 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202 |  | B
036909C-1020-PDS-0840-2010 | Process Equipment Datasheet - 10-F-2008 A-C Quench Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2010 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1020-PDS-0840-2014 | Process Equipment Datasheet - 10-F-2009 A-B QO Pump Purge Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2014 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1020-PDS-0600-2015 | Process Equipment Datasheet - 10-E-2008 A-C - LS2 Steam Generators | A | 2018-11-09 | IFR | OL1-2G30-2015 | PE | 2018-11-09 | 036909C-JVD-TRN-00305 | 036909C-JVD-TRN-00305 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PE-00305 |  | A
036909C-1020-PDS-0500-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper | A | 2018-10-26 | IFR | OL1-2G30-2020 | PE | 2018-10-29 | 036909C-JVD-TRN-00238 | 036909C-JVD-TRN-00238 | IFR | 2018-11-12 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00238 |  | A
036909C-1020-PDS-0500-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper | B | 2018-12-05 | IFD | OL1-2G30-2020 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00437 |  | B
036909C-1020-PDS-0900-2024 | Process Equipment Datasheet - 10-P-2026 A-B - Light Fuel Oil Pumps | A | 2018-11-06 | IFR | OL1-2G30-2024 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1020-PDS-0840-2025 | Process Equipment Datasheet - 10-F-2026 A-B Cracker Bottoms Product Filter | A | 2018-11-21 | IFR | OL1-2G30-2025 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1020-PDS-0600-2026 | Process Equipment Datasheet - 10-E-2026 - FO Product Cooler | A | 2018-11-08 | IFR | OL1-2G30-2026 | PE | 2018-11-09 | 036909C-JVD-TRN-00298 | 036909C-JVD-TRN-00298 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PE-00298 |  | A
036909C-1020-PDS-0840-2028 | Process Equipment Datasheet - 10-F-2028 A-B - FO Pump Purge Oil Filter | A | 2018-11-21 | IFR | OL1-2G30-2028 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1020-PDS-4200-2036 | Process Equipment Datasheet - 10-X-2036 - Quench Fitting | A | 2018-11-19 | IFR | OL1-2G30-2036 | PE | 2018-11-20 | 036909C-JVD-TRN-00338 | 036909C-JVD-TRN-00338 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-PE-00338 |  | A
036909C-1020-PDS-0500-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper | A | 2018-10-11 | IFR | OL1-2G30-2040 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162 |  | A
036909C-1020-PDS-0500-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper | B | 2018-11-21 | IFD | OL1-2G30-2040 | PE | 2018-11-21 | 036909C-JVD-TRN-00347 | 036909C-JVD-TRN-00347 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00347 |  | B
036909C-1020-PDS-0900-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps | A | 2018-11-06 | IFR | OL1-2G30-2046 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1020-PDS-0600-2048 | Process Equipment Datasheet - 10-E-2048 - Heavy Fuel Oil Product Cooler | A | 2018-11-08 | IFR | OL1-2G30-2048 | PE | 2018-11-09 | 036909C-JVD-TRN-00298 | 036909C-JVD-TRN-00298 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PE-00298 |  | A
036909C-1020-PDS-0840-2049 | Process Equipment Datasheet - 10-F-2048 A-B Heavy Fuel Oil Filters | A | 2018-11-21 | IFR | OL1-2G30-2049 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1020-PDS-0800-2090 | Process Equipment Datasheet - 10-D-2090 - Quench Oil Drain Drum | A | 2018-11-26 | IFR | OL1-2G30-2090 | PE | 2018-11-27 | 036909C-JVD-TRN-00368 | 036909C-JVD-TRN-00368 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00368 |  | A
036909C-1020-PDS-0900-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps | A | 2018-11-26 | IFR | OL1-2G30-2091 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00371 |  | A
036909C-1021-PDS-0500-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | A | 2018-10-26 | IFR | OL1-2G30-2100 | PE | 2018-10-29 | 036909C-JVD-TRN-00238 | 036909C-JVD-TRN-00238 | IFR | 2018-11-12 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00238 |  | A
036909C-1021-PDS-0500-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower | B | 2018-12-05 | IFD | OL1-2G30-2100 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00437 |  | B
036909C-1021-PDS-0600-2101 | Process Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | A | 2018-09-07 | IFA | OL1-2G30-2101 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1021-PDS-0600-2101 | Process Equipment Datasheet - 10-E-2100 A-F - Quench Water Cooler | B | 2018-10-04 | IFD | OL1-2G30-2101 | PE | 2018-10-08 | 036909C-JVD-TRN-00143 | 036909C-JVD-TRN-00143 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00143 |  | B
036909C-1021-PDS-0840-2104 | Process Equipment Datasheet - 10-F-2105 A-B Quench Oil Reflux Filter | A | 2018-11-21 | IFR | OL1-2G30-2104 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1021-PDS-0900-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps | A | 2018-11-06 | IFR | OL1-2G30-2105 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1021-PDS-0900-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-2106 | PE | 2018-09-20 | 036909C-JVD-TRN-00070 | 036909C-JVD-TRN-00070 | IFA | 2018-10-04 | 2018-10-09 | A1-Approved without comments | TPSK-LSPA1-T-PE-00070 |  | A
036909C-1021-PDS-0900-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps | B | 2018-10-18 | IFD | OL1-2G30-2106 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202 |  | B
036909C-1021-PDS-0800-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum | A | 2018-12-06 | IFR | OL1-2G30-2110 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00453 |  | A
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | A | 2018-10-29 | IFR | OL1-2G30-2120 | PE | 2018-10-31 | 036909C-JVD-TRN-00253 | 036909C-JVD-TRN-00253 | IFR | 2018-11-14 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00253 |  | A
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | B | 2018-11-29 | IFD | OL1-2G30-2120 | PE | 2018-11-29 | 036909C-JVD-TRN-00401 | 036909C-JVD-TRN-00401 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00401 |  | B
036909C-1021-PDS-0500-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper | C | 2018-12-05 | IFD | OL1-2G30-2120 | PE | 2018-12-07 | 036909C-JVD-TRN-00437 | 036909C-JVD-TRN-00437 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00437 |  | C
036909C-1021-PDS-0600-2125 | Process Equipment Datasheet - 10-E-2125 - Distillate Stripper Reboiler | A | 2018-11-01 | IFR | OL1-2G30-2125 | PE | 2018-11-01 | 036909C-JVD-TRN-00265 | 036909C-JVD-TRN-00265 | IFR | 2018-11-15 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00265 |  | A
036909C-1021-PDS-0900-2126 | Process Equipment Datasheet - 10-P-2126 A-B - Distillate Stripper Bottom Pumps | A | 2018-11-26 | IFR | OL1-2G30-2126 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00371 |  | A
036909C-1021-PDS-0800-2136 | Process Equipment Datasheet - 10-D-2136 - Process Water Feed Coalescer | A | 2018-12-06 | IFR | OL1-2G30-2136 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00453 |  | A
036909C-1021-PDS-0600-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater | A | 2018-10-17 | IFR | OL1-2G30-2137 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1021-PDS-0600-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater | B | 2018-12-07 | IFD | OL1-2G30-2137 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00467 |  | B
036909C-1021-PDS-0840-2138 | Process Equipment Datasheet - 10-F-2136 A-B Process Water Feed Filters | A | 2018-11-21 | IFR | OL1-2G30-2138 | PE | 2018-11-21 | 036909C-JVD-TRN-00350 | 036909C-JVD-TRN-00350 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00350 |  | A
036909C-1021-PDS-0500-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper | A | 2018-10-17 | IFR | OL1-2G30-2140 | PE | 2018-10-17 | 036909C-JVD-TRN-00189 | 036909C-JVD-TRN-00189 | IFR | 2018-10-31 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00189 |  | A
036909C-1021-PDS-0500-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper | B | 2018-11-29 | IFD | OL1-2G30-2140 | PE | 2018-11-29 | 036909C-JVD-TRN-00401 | 036909C-JVD-TRN-00401 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00401 |  | B
036909C-1021-PDS-0600-2145 | Process Equipment Datasheet - 10-E-2145 - Process Water Stripper Reboiler | A | 2018-10-17 | IFR | OL1-2G30-2145 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 |  | Transmitted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1021-PDS-0900-2146 | Process Equipment Datasheet 10-P-2146 DSG Feed Pumps | A | 2018-09-20 | IFA | OL1-2G30-2146 | PE | 2018-09-20 | 036909C-JVD-TRN-00069 | 036909C-JVD-TRN-00069 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00069 |  | A
036909C-1021-PDS-0900-2146 | Process Equipment Datasheet - 10-P-2146 A-B - DSG Feed Pumps | B | 2018-10-18 | IFD | OL1-2G30-2146 | PE | 2018-10-22 | 036909C-JVD-TRN-00202 | 036909C-JVD-TRN-00202 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00202 |  | B
036909C-1021-PDS-0600-2147 | Process Equipment Datasheet - 10-E-2146 - DSG Feed Heater | A | 2018-10-17 | IFR | OL1-2G30-2147 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 |  | Transmitted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1021-PDS-0800-2160 | Process Equipment Datasheet - 10-D-2160 - Dilution Steam Generator | A | 2018-09-28 | IFA | OL1-2G30-2160 | PE | 2018-09-28 | 036909C-JVD-TRN-00115 | 036909C-JVD-TRN-00115 | IFA | 2018-10-12 | 2018-11-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00115 |  | A
036909C-1021-PDS-0600-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater | A | 2018-10-17 | IFR | OL1-2G30-2161 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1021-PDS-0600-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater | B | 2018-12-07 | IFD | OL1-2G30-2161 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00467 |  | B
036909C-1021-PDS-0600-2165 | Process Equipment Datasheet - 10-E-2165 A-D DSG Reboilers | A | 2018-10-17 | IFR | OL1-2G30-2165 | PE | 2018-10-18 | 036909C-JVD-TRN-00194 | 036909C-JVD-TRN-00194 | IFR | 2018-11-01 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00194 |  | A
036909C-1021-PDS-0600-2165 | Process Equipment Datasheet - 10-E-2165 A-D - DSG Reboilers | B | 2018-12-07 | IFD | OL1-2G30-2165 | PE | 2018-12-10 | 036909C-JVD-TRN-00467 | 036909C-JVD-TRN-00467 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00467 |  | B
036909C-1021-PDS-0600-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler | A | 2018-10-22 | IFR | OL1-2G30-2166 | PE | 2018-10-23 | 036909C-JVD-TRN-00209 | 036909C-JVD-TRN-00209 | IFR | 2018-11-06 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00209 |  | A
036909C-1021-PDS-0600-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler | B | 2018-12-04 | IFD | OL1-2G30-2166 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1021-PDS-0800-2190 | Process Equipment Datasheet - 10-D-2190 - Quench Water Drain Drum | A | 2018-11-26 | IFR | OL1-2G30-2190 | PE | 2018-11-27 | 036909C-JVD-TRN-00368 | 036909C-JVD-TRN-00368 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00368 |  | A
036909C-1021-PDS-0900-2191 | Process Equipment Datasheet - 10-P-2190- Quench Water Drain Drum Pump | A | 2018-11-20 | IFR | OL1-2G30-2191 | PE | 2018-11-21 | 036909C-JVD-TRN-00346 | 036909C-JVD-TRN-00346 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00346 |  | A
036909C-1022-PDS-1000-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | A | 2018-08-22 | IFA | OL1-2G30-2200 | PE | 2018-08-22 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | A
036909C-1022-PDS-1000-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor | B | 2018-09-14 | IFD | OL1-2G30-2200 | PE | 2018-09-17 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | B
036909C-1022-PDS-0600-2206 | Process Equipment Datasheet - 10-E-2206 - Wash Water Cooler | A | 2018-11-27 | IFR | OL1-2G30-2206 | PE | 2018-11-28 | 036909C-JVD-TRN-00381 | 036909C-JVD-TRN-00381 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-PE-00381 |  | A
036909C-1022-PDS-0800-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2210 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1022-PDS-0800-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2210 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00448 |  | B
036909C-1022-PDS-0600-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | A | 2018-11-01 | IFR | OL1-2G30-2211 | PE | 2018-11-01 | 036909C-JVD-TRN-00266 | 036909C-JVD-TRN-00266 | IFR | 2018-11-15 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00266 |  | A
036909C-1022-PDS-0600-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers | B | 2018-12-10 | IFD | OL1-2G30-2211 | PE | 2018-12-12 | 036909C-JVD-TRN-00479 | 036909C-JVD-TRN-00479 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00479 |  | B
036909C-1022-PDS-0900-2212 | Process Equipment Datasheet - 10-P-2210 A-B - CG 1st Stage Condensate Pumps | A | 2018-11-06 | IFR | OL1-2G30-2212 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2220 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1022-PDS-0800-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2220 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00448 |  | B
036909C-1022-PDS-0600-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercoolers | A | 2018-10-18 | IFR | OL1-2G30-2221 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1022-PDS-0600-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2221 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1022-PDS-0900-2222 | Process Equipment Datasheet - 10-P-2220 A-B - CG 2nd Stage Condensed HC Pumps | A | 2018-11-06 | IFR | OL1-2G30-2222 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1022-PDS-0800-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2230 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1022-PDS-0800-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2230 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00448 |  | B
036909C-1022-PDS-0600-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler | A | 2018-10-18 | IFR | OL1-2G30-2231 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1022-PDS-0600-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2231 | PE | 2018-12-07 | 036909C-JVD-TRN-00431 | 036909C-JVD-TRN-00431 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00431 |  | B
036909C-1022-PDS-0800-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum | A | 2018-10-12 | IFR | OL1-2G30-2240 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175 |  | A
036909C-1022-PDS-0800-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum | B | 2018-12-06 | IFD | OL1-2G30-2240 | PE | 2018-12-10 | 036909C-JVD-TRN-00448 | 036909C-JVD-TRN-00448 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00448 |  | B
036909C-1022-PDS-0600-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler | A | 2018-10-18 | IFR | OL1-2G30-2241 | PE | 2018-10-22 | 036909C-JVD-TRN-00206 | 036909C-JVD-TRN-00206 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00206 |  | A
036909C-1022-PDS-0600-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler | B | 2018-12-04 | IFD | OL1-2G30-2241 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00436 |  | B
036909C-1022-PDS-0800-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum | A | 2018-10-31 | IFR | OL1-2G30-2245 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00264 |  | A
036909C-1022-PDS-0800-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum | B | 2018-12-10 | IFD | OL1-2G30-2245 | PE | 2018-12-12 | 036909C-JVD-TRN-00480 | 036909C-JVD-TRN-00480 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00480 |  | B
036909C-1023-PDS-0500-2300 | Process Equipment Data Sheet - 10-T-2300 - Caustic Tower | A | 2018-09-17 | IFA | OL1-2G30-2300 | PE | 2018-09-18 | 036909C-JVD-TRN-00060 | 036909C-JVD-TRN-00060 | IFA | 2018-10-02 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00060 |  | A
036909C-1023-PDS-0500-2300 | Process Equipment Datasheet - 10-T-2300 - Caustic Tower | B | 2018-11-08 | IFD | OL1-2G30-2300 | PE | 2018-11-08 | 036909C-JVD-TRN-00290 | 036909C-JVD-TRN-00290 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00290 |  | B
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | A | 2018-10-12 | IFR | OL1-2G30-2301 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00173 |  | A
036909C-1023-PDS-4200-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer | B | 2018-11-27 | IFD | OL1-2G30-2301 | PE | 2018-11-28 | 036909C-JVD-TRN-00383 | 036909C-JVD-TRN-00383 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00383 |  | B
036909C-1023-PDS-0900-2302 | Process Equipment Datasheet - 10-P-2302 A-B - Strong Caustic Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2302 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00174 |  | A
036909C-1023-PDS-0900-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump | A | 2018-10-12 | IFR | OL1-2G30-2304 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00174 |  | A
036909C-1023-PDS-0900-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump | B | 2018-11-27 | IFD | OL1-2G30-2304 | PE | 2018-11-28 | 036909C-JVD-TRN-00382 | 036909C-JVD-TRN-00382 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00382 |  | B
036909C-1023-PDS-0600-2305 | Process Equipment Datasheet - 10-E-2305 - Caustic Tower Feed Heater | A | 2018-10-31 | IFR | OL1-2G30-2305 | PE | 2018-10-31 | 036909C-JVD-TRN-00259 | 036909C-JVD-TRN-00259 | IFR | 2018-11-14 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00259 |  | A
036909C-1023-PDS-0900-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2306 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00174 |  | A
036909C-1023-PDS-0900-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps | B | 2018-11-27 | IFD | OL1-2G30-2306 | PE | 2018-11-28 | 036909C-JVD-TRN-00382 | 036909C-JVD-TRN-00382 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00382 |  | B
036909C-1023-PDS-0840-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters | A | 2018-10-18 | IFR | OL1-2G30-2307 | PE | 2018-10-22 | 036909C-JVD-TRN-00205 | 036909C-JVD-TRN-00205 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00205 |  | A
036909C-1023-PDS-4200-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer | A | 2018-10-12 | IFR | OL1-2G30-2308 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00173 |  | A
036909C-1023-PDS-4200-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer | B | 2018-11-27 | IFD | OL1-2G30-2308 | PE | 2018-11-28 | 036909C-JVD-TRN-00383 | 036909C-JVD-TRN-00383 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00383 |  | B
036909C-1023-PDS-0800-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum | A | 2018-09-27 | IFA | OL1-2G30-2309 | PE | 2018-09-27 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | A
036909C-1023-PDS-0800-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum | A | 2018-10-29 | IFR | OL1-2G30-2310 | PE | 2018-10-31 | 036909C-JVD-TRN-00254 | 036909C-JVD-TRN-00254 | IFR | 2018-11-14 |  | Transmitted | TPSK-LSPA1-T-PE-00254 |  | A
036909C-1023-PDS-0900-2311 | Process Equipment Datasheet - 10-P-2310 A-B - Wash Oil Circulating Pumps | A | 2018-10-12 | IFR | OL1-2G30-2311 | PE | 2018-10-15 | 036909C-JVD-TRN-00174 | 036909C-JVD-TRN-00174 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00174 |  | A
036909C-1023-PDS-4200-2313 | Process Equipment Datasheet - 10-X-2312 - Spent Wash Oil Mixer | A | 2018-10-12 | IFR | OL1-2G30-2313 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00173 |  | A
036909C-1023-PDS-0840-2314 | Process Equipment Datasheet - 10-F-2310 A-B - Wash Oil Circulating Filter | A | 2018-10-18 | IFR | OL1-2G30-2314 | PE | 2018-10-22 | 036909C-JVD-TRN-00205 | 036909C-JVD-TRN-00205 | IFR | 2018-11-05 | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-PE-00205 |  | A
036909C-1023-PDS-4200-2315 | Process Equipment Datasheet - 10-X-2310 - Spent Caustic Mixer | A | 2018-10-12 | IFR | OL1-2G30-2315 | PE | 2018-10-15 | 036909C-JVD-TRN-00173 | 036909C-JVD-TRN-00173 | IFR | 2018-10-29 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00173 |  | A
036909C-1023-PDS-0800-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum | A | 2018-10-12 | IFR | OL1-2G30-2316 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175 |  | A
036909C-1023-PDS-0840-2319 | Process Equipment Datasheet - 10-F-2320 A-B - Spent Caustic Pump Discharge Filters | A | 2018-10-29 | IFR | OL1-2G30-2319 | PE | 2018-10-31 | 036909C-JVD-TRN-00255 | 036909C-JVD-TRN-00255 | IFR | 2018-11-14 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00255 |  | A
036909C-1023-PDS-2500-2320 | Process Equipment Data Sheet - 10-TK-2320 - Spent Caustic Storage Tank | A | 2018-09-20 | IFA | OL1-2G30-2320 | PE | 2018-09-20 | 036909C-JVD-TRN-00068 | 036909C-JVD-TRN-00068 | IFA | 2018-10-04 | 2018-10-09 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00068 |  | A
036909C-1023-PDS-2500-2320 | Process Equipment Datasheet - 10-TK-2320 - Spent Caustic Storage Tank | B | 2018-10-18 | IFD | OL1-2G30-2320 | PE | 2018-10-22 | 036909C-JVD-TRN-00203 | 036909C-JVD-TRN-00203 | IFI |  | 2018-11-30 | A1-Approved without comments | TPSK-LSPA1-T-PE-00203 |  | B
036909C-1023-PDS-0900-2321 | Process Equipment Datasheet - 10-P-2320 A-B - Spent Caustic Pumps | A | 2018-10-29 | IFR | OL1-2G30-2321 | PE | 2018-10-31 | 036909C-JVD-TRN-00252 | 036909C-JVD-TRN-00252 | IFR | 2018-11-14 |  | Transmitted | TPSK-LSPA1-T-PE-00252 |  | A
036909C-1023-PDS-0800-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum | A | 2018-09-27 | IFA | OL1-2G30-2322 | PE | 2018-09-28 | 036909C-JVD-TRN-00111 | 036909C-JVD-TRN-00111 | IFA | 2018-10-12 |  | Transmitted | TPSK-LSPA1-T-PE-00111 |  | A
036909C-1023-PDS-0600-2326 | Process Equipment Datasheet - 10-E-2326 - Spent Caustic Stripper Feed Heater | A | 2018-11-27 | IFR | OL1-2G30-2326 | PE | 2018-11-28 | 036909C-JVD-TRN-00381 | 036909C-JVD-TRN-00381 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-PE-00381 |  | A
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | A | 2018-09-20 | IFA | OL1-2G30-2330 | PE | 2018-09-24 | 036909C-JVD-TRN-00073 | 036909C-JVD-TRN-00073 | IFA | 2018-10-08 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00073 |  | A
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | B | 2018-10-10 | IFA | OL1-2G30-2330 | PE | 2018-10-11 | 036909C-JVD-TRN-00160 | 036909C-JVD-TRN-00160 | IFA | 2018-10-25 |  | Transmitted | TPSK-LSPA1-T-PE-00160 |  | B
036909C-1023-PDS-0500-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper | C | 2018-11-27 | IFD | OL1-2G30-2330 | PE | 2018-11-28 | 036909C-JVD-TRN-00384 | 036909C-JVD-TRN-00384 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00384 |  | C
036909C-1023-PDS-0800-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum | A | 2018-10-12 | IFR | OL1-2G30-2331 | PE | 2018-10-15 | 036909C-JVD-TRN-00175 | 036909C-JVD-TRN-00175 | IFR | 2018-10-29 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00175 |  | A
036909C-1023-PDS-4100-2350 | Process Equipment Datasheet - 10-PK-2350 - Wet Air Oxidation Pkg | A | 2018-10-15 | IFR | OL1-2G30-2350 | PE | 2018-10-16 | 036909C-JVD-TRN-00180 | 036909C-JVD-TRN-00180 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-PE-00180 |  | A
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | A | 2018-09-27 | IFA | OL1-2G30-2390 | PE | 2018-09-27 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | A
036909C-1023-PDS-0800-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum | B | 2018-11-26 | IFD | OL1-2G30-2390 | PE | 2018-11-27 | 036909C-JVD-TRN-00369 | 036909C-JVD-TRN-00369 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00369 |  | B
036909C-1023-PDS-0900-2391 | Process Equipment Datasheet - 10-P-2390 - Caustic Drain Drum Pump | A | 2018-12-06 | IFR | OL1-2G30-2391 | PE | 2018-12-07 | 036909C-JVD-TRN-00444 | 036909C-JVD-TRN-00444 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00444 |  | A
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 Spent Caustic Drain Drum | A | 2018-09-27 | IFA | OL1-2G30-2392 | PE | 2018-09-27 | 036909C-JVD-TRN-00102 | 036909C-JVD-TRN-00102 | IFA | 2018-10-11 | 2018-11-14 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00102 |  | A
036909C-1023-PDS-0800-2392 | Process Equipment Datasheet - 10-D-2392 - Spent Caustic Drain Drum | B | 2018-11-26 | IFD | OL1-2G30-2392 | PE | 2018-11-27 | 036909C-JVD-TRN-00369 | 036909C-JVD-TRN-00369 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00369 |  | B
036909C-1023-PDS-0900-2393 | Process Equipment Datasheet - 10-P-2392 - Spent Caustic Drain Drum Pump | A | 2018-10-29 | IFR | OL1-2G30-2393 | PE | 2018-10-31 | 036909C-JVD-TRN-00252 | 036909C-JVD-TRN-00252 | IFR | 2018-11-14 |  | Transmitted | TPSK-LSPA1-T-PE-00252 |  | A
036909C-1024-PDS-0800-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum | A | 2018-11-13 | IFR | OL1-2G30-2405 | PE | 2018-11-14 | 036909C-JVD-TRN-00315 | 036909C-JVD-TRN-00315 | IFR | 2018-11-28 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00315 |  | A
036909C-1024-PDS-0800-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum | B | 2018-12-10 | IFD | OL1-2G30-2405 | PE | 2018-12-12 | 036909C-JVD-TRN-00480 | 036909C-JVD-TRN-00480 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00480 |  | B
036909C-1024-PDS-0600-2406 | Process Equipment Datasheet - 10-E-2405 - Gas Dryer Feed Chiller | A | 2018-10-26 | IFR | OL1-2G30-2406 | PE | 2018-10-30 | 036909C-JVD-TRN-00239 | 036909C-JVD-TRN-00239 | IFR | 2018-11-12 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00239 |  | A
036909C-1024-PDS-0800-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer | A | 2018-12-06 | IFR | OL1-2G30-2410 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00439 |  | A
036909C-1024-PDS-0800-2411 | Process Equipment Datasheet - 10-D-2411 - Cracked Gas Mercury Adsorber | A | 2018-11-19 | IFR | OL1-2G30-2411 | PE | 2018-11-20 | 036909C-JVD-TRN-00339 | 036909C-JVD-TRN-00339 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-PE-00339 |  | A
036909C-1024-PDS-0600-2412 | Process Equipment Datasheet - 10-E-2412 - HP Depropanizer Feed Chiller | A | 2018-10-26 | IFR | OL1-2G30-2412 | PE | 2018-10-30 | 036909C-JVD-TRN-00239 | 036909C-JVD-TRN-00239 | IFR | 2018-11-12 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00239 |  | A
036909C-1024-PDS-0600-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | A | 2018-10-30 | IFR | OL1-2G30-2413 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger | B | 2018-11-28 | IFD | OL1-2G30-2413 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0800-2415 | Process Equipment Datasheet - 10-D-2415 - CG Liquid Dryer Feed Coalescer | A | 2018-11-19 | IFR | OL1-2G30-2415 | PE | 2018-11-20 | 036909C-JVD-TRN-00339 | 036909C-JVD-TRN-00339 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-PE-00339 |  | A
036909C-1024-PDS-0900-2416 | Process Equipment Datasheet - 10-P-2415 A-B - CG Liquid Dryer Feed Pumps | A | 2018-11-06 | IFR | OL1-2G30-2416 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1024-PDS-0800-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer | A | 2018-11-08 | IFR | OL1-2G30-2420 | PE | 2018-11-09 | 036909C-JVD-TRN-00301 | 036909C-JVD-TRN-00301 | IFR | 2018-11-23 | 2018-11-30 | R2-Comments as noted | TPSK-LSPA1-T-PE-00301 |  | A
036909C-1024-PDS-0800-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum | A | 2018-10-31 | IFR | OL1-2G30-2438 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-PE-00264 |  | A
036909C-1024-PDS-0800-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum | B | 2018-12-04 | IFD | OL1-2G30-2438 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00430 |  | B
036909C-1024-PDS-0600-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser | A | 2018-10-30 | IFR | OL1-2G30-2439 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser | B | 2018-11-28 | IFD | OL1-2G30-2439 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0500-2440 | Process Equipment Data Sheet - 10-T-2440 - HP Depropanizer | A | 2018-09-13 | IFA | OL1-2G30-2440 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | A
036909C-1024-PDS-0500-2440 | Process Equipment Datasheet - 10-T-2440 - HP Depropanizer | B | 2018-10-11 | IFD | OL1-2G30-2440 | PE | 2018-10-12 | 036909C-JVD-TRN-00167 | 036909C-JVD-TRN-00167 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00167 |  | B
036909C-1024-PDS-0600-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | A | 2018-10-30 | IFR | OL1-2G30-2441 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 | B | 2018-11-28 | IFD | OL1-2G30-2441 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0600-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 | A | 2018-10-30 | IFR | OL1-2G30-2442 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 | B | 2018-11-28 | IFD | OL1-2G30-2442 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0900-2443 | Process Equipment Datasheet - 10-P-2445 A-B - HP Deprop Reboiler Cond Pump | A | 2018-12-03 | IFR | OL1-2G30-2443 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 |  | Transmitted | TPSK-LSPA1-T-PE-00408 |  | A
036909C-1024-PDS-0800-2444 | Process Equipment Datasheet - 10-D-2445 - HP Deprop Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2444 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 |  | Transmitted | TPSK-LSPA1-T-PE-00474 |  | A
036909C-1024-PDS-0600-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers | A | 2018-11-01 | IFR | OL1-2G30-2445 | PE | 2018-11-01 | 036909C-JVD-TRN-00267 | 036909C-JVD-TRN-00267 | IFR | 2018-11-15 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00267 |  | A
036909C-1024-PDS-0600-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers | B | 2018-12-04 | IFD | OL1-2G30-2445 | PE | 2018-12-07 | 036909C-JVD-TRN-00436 | 036909C-JVD-TRN-00436 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00436 |  | B
036909C-1024-PDS-0600-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler | A | 2018-10-30 | IFR | OL1-2G30-2446 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler | B | 2018-11-28 | IFD | OL1-2G30-2446 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0500-2450 | Process Equipment Data Sheet - 10-T-2450 - LP Depropanizer | A | 2018-09-13 | IFA | OL1-2G30-2450 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | A
036909C-1024-PDS-0500-2450 | Process Equipment Datasheet - 10-T-2450 - LP Depropanizer | B | 2018-10-11 | IFD | OL1-2G30-2450 | PE | 2018-10-12 | 036909C-JVD-TRN-00167 | 036909C-JVD-TRN-00167 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00167 |  | B
036909C-1024-PDS-0600-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser | A | 2018-10-31 | IFR | OL1-2G30-2451 | PE | 2018-10-31 | 036909C-JVD-TRN-00259 | 036909C-JVD-TRN-00259 | IFR | 2018-11-14 | 2018-11-20 | R2-Comments as noted | TPSK-LSPA1-T-PE-00259 |  | A
036909C-1024-PDS-0600-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser | B | 2018-11-28 | IFD | OL1-2G30-2451 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0800-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum | A | 2018-10-31 | IFR | OL1-2G30-2452 | PE | 2018-11-01 | 036909C-JVD-TRN-00264 | 036909C-JVD-TRN-00264 | IFR | 2018-11-15 | 2018-11-27 | R1-No comments | TPSK-LSPA1-T-PE-00264 |  | A
036909C-1024-PDS-0800-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum | B | 2018-12-04 | IFD | OL1-2G30-2452 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00430 |  | B
036909C-1024-PDS-0900-2453 | Process Equipment Datasheet - 10-P-2450 A-B - LP Depropanizer Reflux-Product Pump | A | 2018-11-06 | IFR | OL1-2G30-2453 | PE | 2018-11-07 | 036909C-JVD-TRN-00285 | 036909C-JVD-TRN-00285 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00285 |  | A
036909C-1024-PDS-0600-2455 | Process Equipment Datasheet - 10-E-2455 A-B - LP Depropanizer Reboilers | A | 2018-10-24 | IFR | OL1-2G30-2455 | PE | 2018-10-25 | 036909C-JVD-TRN-00228 | 036909C-JVD-TRN-00228 | IFR | 2018-11-08 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00228 |  | A
036909C-1024-PDS-0800-2456 | Process Equipment Datasheet - 10-D-2455 - LP Deprop Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2456 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 |  | Transmitted | TPSK-LSPA1-T-PE-00474 |  | A
036909C-1024-PDS-0900-2457 | Process Equipment Datasheet - 10-P-2455 A-B - LP Deprop Reboiler Cond Pump | A | 2018-12-03 | IFR | OL1-2G30-2457 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 |  | Transmitted | TPSK-LSPA1-T-PE-00408 |  | A
036909C-1024-PDS-0800-2460 | Process Equipment Datasheet - 10-D-2460 - C2 Hydrog Arsine Guard Bed | A | 2018-12-06 | IFR | OL1-2G30-2460 | PE | 2018-12-10 | 036909C-JVD-TRN-00453 | 036909C-JVD-TRN-00453 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00453 |  | A
036909C-1024-PDS-0600-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler | A | 2018-10-30 | IFR | OL1-2G30-2461 | PE | 2018-10-31 | 036909C-JVD-TRN-00250 | 036909C-JVD-TRN-00250 | IFR | 2018-11-14 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00250 |  | A
036909C-1024-PDS-0600-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler | B | 2018-11-28 | IFD | OL1-2G30-2461 | PE | 2018-11-29 | 036909C-JVD-TRN-00392 | 036909C-JVD-TRN-00392 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00392 |  | B
036909C-1024-PDS-0600-2465 | Process Equipment Datasheet - 10-E-2465 - C2 Hydrog Feed Heater | A | 2018-11-28 | IFR | OL1-2G30-2465 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00391 |  | A
036909C-1024-PDS-0400-2470 | Process Equipment Datasheet - 10-R-2470 A-C - C2 Hydrog Reactor | A | 2018-11-08 | IFR | OL1-2G30-2470 | PE | 2018-11-09 | 036909C-JVD-TRN-00299 | 036909C-JVD-TRN-00299 | IFR | 2018-11-23 | 2018-11-29 | R2-Comments as noted | TPSK-LSPA1-T-PE-00299 |  | A
036909C-1024-PDS-0600-2471 | Process Equipment Datasheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler | A | 2018-11-28 | IFR | OL1-2G30-2471 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00391 |  | A
036909C-1024-PDS-0600-2472 | Process Equipment Datasheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler | A | 2018-11-28 | IFR | OL1-2G30-2472 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00391 |  | A
036909C-1024-PDS-0600-2474 | Process Equipment Datasheet - 10-E-2474 - C2 Hydrog Aftercooler | A | 2018-11-28 | IFR | OL1-2G30-2474 | PE | 2018-11-29 | 036909C-JVD-TRN-00391 | 036909C-JVD-TRN-00391 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00391 |  | A
036909C-1024-PDS-0800-2480 | Process Equipment Datasheet - 10-D-2480 - CG Secondary Dryer | A | 2018-11-28 | IFR | OL1-2G30-2480 | PE | 2018-11-28 | 036909C-JVD-TRN-00386 | 036909C-JVD-TRN-00386 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-PE-00386 |  | A
036909C-1025-PDS-0600-2500 | Process Equipment Data Sheet - 10-E-2500 - Propylene Refrig Subcooler | A | 2018-09-10 | IFA | OL1-2G30-2500 | PE | 2018-09-11 | 036909C-JVD-TRN-00039 | 036909C-JVD-TRN-00039 | IFA | 2018-09-25 | 2018-09-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00039 |  | A
036909C-1025-PDS-0600-2500 | Process Equipment Datasheet - 10-E-2500 - Propylene Refrig Subcooler | B | 2018-10-03 | IFD | OL1-2G30-2500 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2502 | Process Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | A | 2018-09-07 | IFA | OL1-2G30-2502 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | B | 2018-11-01 | IFD | OL1-2G30-2502 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0600-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | C | 2018-12-07 | IFD | OL1-2G30-2502 | PE | 2018-12-11 | 036909C-JVD-TRN-00475 | 036909C-JVD-TRN-00475 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00475 |  | C
036909C-1025-PDS-0600-2503 | Process Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | A | 2018-09-07 | IFA | OL1-2G30-2503 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2503 | Process Equipment Datasheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | B | 2018-11-01 | IFD | OL1-2G30-2503 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0800-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | A | 2018-10-23 | IFR | OL1-2G30-2504 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217 |  | A
036909C-1025-PDS-0800-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 | B | 2018-11-08 | IFD | OL1-2G30-2504 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303 |  | B
036909C-1025-PDS-0600-2505 | Process Equipment Data Sheet - 10-E-2506 & 2508 - Demeth Prefrac Feed Cooler No 3 & No 4 | A | 2018-09-06 | IFA | OL1-2G30-2505 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2505 | Process Equipment Datasheet - 10-E2506 and 10-E2508 - Demeth Prefrac Feed Cooler No 3 and No 4 | B | 2018-10-03 | IFD | OL1-2G30-2505 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0800-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | A | 2018-10-23 | IFR | OL1-2G30-2506 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217 |  | A
036909C-1025-PDS-0800-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 | B | 2018-11-08 | IFD | OL1-2G30-2506 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303 |  | B
036909C-1025-PDS-0800-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | A | 2018-10-23 | IFR | OL1-2G30-2508 | PE | 2018-10-24 | 036909C-JVD-TRN-00217 | 036909C-JVD-TRN-00217 | IFR | 2018-11-07 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-PE-00217 |  | A
036909C-1025-PDS-0800-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 | B | 2018-11-08 | IFD | OL1-2G30-2508 | PE | 2018-11-09 | 036909C-JVD-TRN-00303 | 036909C-JVD-TRN-00303 | IFI |  | 2018-11-26 | R1-No comments | TPSK-LSPA1-T-PE-00303 |  | B
036909C-1025-PDS-0500-2510 | Process Equipment Datasheet - 10-T-2510 and 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | A | 2018-09-26 | IFA | OL1-2G30-2510 | PE | 2018-09-26 | 036909C-JVD-TRN-00092 | 036909C-JVD-TRN-00092 | IFA | 2018-10-09 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00092 |  | A
036909C-1025-PDS-0500-2510 | Process Equipment Datasheet - 10-T-2510 - 10-D-2510 - Demethanizer Prefractionator & Reflux Drum | B | 2018-11-09 | IFD | OL1-2G30-2510 | PE | 2018-11-09 | 036909C-JVD-TRN-00306 | 036909C-JVD-TRN-00306 | IFI |  | 2018-11-29 | A1-Approved without comments | TPSK-LSPA1-T-PE-00306 |  | B
036909C-1025-PDS-0600-2511 | Process Equipment Data Sheet - 10-E-2510 - Demeth Prefrac Condenser | A | 2018-09-06 | IFA | OL1-2G30-2511 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2511 | Process Equipment Datasheet - 10-E-2510 - Demeth Prefrac Condenser | B | 2018-10-03 | IFD | OL1-2G30-2511 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2515 | Process Equipment Datasheet - 10-E-2515 - Demeth Prefrac Reboiler | A | 2018-10-23 | IFR | OL1-2G30-2515 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1025-PDS-0500-2520 | Process Equipment Datasheet - 10-T-2520 and 10-D-2520 - Residue Gas Rectifier & Reflux Drum | A | 2018-10-12 | IFR | OL1-2G30-2520 | PE | 2018-10-15 | 036909C-JVD-TRN-00172 | 036909C-JVD-TRN-00172 | IFR | 2018-10-29 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00172 |  | A
036909C-1025-PDS-0500-2520 | Process Equipment Datasheet - 10-T-2520 - 10-D2520 - Residue Gas Rectifier & Reflux Drum | B | 2018-11-30 | IFD | OL1-2G30-2520 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | B
036909C-1025-PDS-0600-2521 | Process Equipment Data Sheet - 10-E-2520 - Rectifier Condenser | A | 2018-09-06 | IFA | OL1-2G30-2521 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2521 | Process Equipment Datasheet - 10-E-2520 - Rectifier Condenser | B | 2018-10-03 | IFD | OL1-2G30-2521 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0800-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum | A | 2018-10-23 | IFR | OL1-2G30-2525 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1025-PDS-0800-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum | B | 2018-12-04 | IFD | OL1-2G30-2525 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00430 |  | B
036909C-1025-PDS-0600-2526 | Process Equipment Data Sheet - 10-E-2525 - Hydrogen Core Exchanger | A | 2018-09-06 | IFA | OL1-2G30-2526 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2526 | Process Equipment Datasheet - 10-E-2525 - Hydrogen Core Exchanger | B | 2018-10-03 | IFD | OL1-2G30-2526 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2531 | Process Equipment Data Sheet - 10-E-2530 - Demeth Feed Cooler | A | 2018-09-06 | IFA | OL1-2G30-2531 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2531 | Process Equipment Datasheet - 10-E-2530 - Demeth Feed Cooler | B | 2018-10-03 | IFD | OL1-2G30-2531 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 and 10-D-2540 - Demethanizer and Reflux Drum | A | 2018-09-20 | IFA | OL1-2G30-2540 | PE | 2018-09-24 | 036909C-JVD-TRN-00073 | 036909C-JVD-TRN-00073 | IFA | 2018-10-08 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00073 |  | A
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum | B | 2018-11-09 | IFD | OL1-2G30-2540 | PE | 2018-11-09 | 036909C-JVD-TRN-00306 | 036909C-JVD-TRN-00306 | IFI |  | 2018-11-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00306 |  | B
036909C-1025-PDS-0500-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum | C | 2018-11-30 | IFD | OL1-2G30-2540 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | C
036909C-1025-PDS-0600-2541 | Process Equipment Data Sheet - 10-E-2540 - Demethanizer Condenser | A | 2018-09-06 | IFA | OL1-2G30-2541 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2541 | Process Equipment Datasheet - 10-E-2540 - Demethanizer Condenser | B | 2018-10-03 | IFD | OL1-2G30-2541 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2545 | Process Equipment Datasheet - 10-E-2545 - Demethanizer Reboiler | A | 2018-10-23 | IFR | OL1-2G30-2545 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1025-PDS-0600-2546 | Process Equipment Datasheet - 10-E-2546 - Demethanizer Bottoms Cooler | A | 2018-10-23 | IFR | OL1-2G30-2546 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1025-PDS-0600-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | A | 2018-10-23 | IFR | OL1-2G30-2548 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1025-PDS-0600-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer | B | 2018-12-07 | IFD | OL1-2G30-2548 | PE | 2018-12-10 | 036909C-JVD-TRN-00464 | 036909C-JVD-TRN-00464 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00464 |  | B
036909C-1025-PDS-1000-2550 | Process Equipment Data Sheet - 10-C-TX-2550 - Residue Gas Expander - Recompressor | A | 2018-08-29 | IFA | OL1-2G30-2550 | PE | 2018-08-29 | 036909C-JVD-TRN-00031 | 036909C-JVD-TRN-00031 | IFA |  | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00031 |  | A
036909C-1025-PDS-1000-2550 | Process Equipment Datasheet - 10-TX-2550 - 10-C-2550 - Residue Gas Expander - Recompressor | B | 2018-09-28 | IFD | OL1-2G30-2550 | PE | 2018-09-28 | 036909C-JVD-TRN-00114 | 036909C-JVD-TRN-00114 | IFI |  | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-PE-00114 |  | B
036909C-1025-PDS-0800-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum | A | 2018-10-23 | IFR | OL1-2G30-2551 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1025-PDS-0800-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum | B | 2018-12-04 | IFD | OL1-2G30-2551 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00440 |  | B
036909C-1025-PDS-0800-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum | A | 2018-10-23 | IFR | OL1-2G30-2555 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1025-PDS-0800-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum | B | 2018-12-04 | IFD | OL1-2G30-2555 | PE | 2018-12-07 | 036909C-JVD-TRN-00430 | 036909C-JVD-TRN-00430 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00430 |  | B
036909C-1025-PDS-4100-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit | A | 2018-10-17 | IFR | OL1-2G30-2560 | PE | 2018-10-17 | 036909C-JVD-TRN-00190 | 036909C-JVD-TRN-00190 | IFR | 2018-10-31 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00190 |  | A
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | A | 2018-10-17 | IFR | OL1-2G30-2570 | PE | 2018-10-17 | 036909C-JVD-TRN-00191 | 036909C-JVD-TRN-00191 | IFR | 2018-10-31 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00191 |  | A
036909C-1025-PDS-0500-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer | B | 2018-11-30 | IFD | OL1-2G30-2570 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | B
036909C-1025-PDS-0600-2571 | Process Equipment Data Sheet - 10-E-2570 Deethanizer Condenser | A | 2018-09-07 | IFA | OL1-2G30-2571 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2571 | Process Equipment Datasheet - 10-E-2570 - Deethanizer Condenser | B | 2018-11-01 | IFD | OL1-2G30-2571 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0800-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum | A | 2018-10-24 | IFR | OL1-2G30-2572 | PE | 2018-10-25 | 036909C-JVD-TRN-00227 | 036909C-JVD-TRN-00227 | IFR | 2018-11-08 | 2018-12-05 | R1-No comments | TPSK-LSPA1-T-PE-00227 |  | A
036909C-1025-PDS-0800-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum | B | 2018-12-06 | IFD | OL1-2G30-2572 | PE | 2018-12-07 | 036909C-JVD-TRN-00446 | 036909C-JVD-TRN-00446 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00446 |  | B
036909C-1025-PDS-0900-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps | A | 2018-11-14 | IFR | OL1-2G30-2573 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340 |  | A
036909C-1025-PDS-0900-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps | B | 2018-12-10 | IFD | OL1-2G30-2573 | PE | 2018-12-12 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00481 |  | B
036909C-1025-PDS-0800-2574 | Process Equipment Datasheet - 10-D-2575 - Deethanizer Reboiler Cond Pot | A | 2018-12-07 | IFR | OL1-2G30-2574 | PE | 2018-12-11 | 036909C-JVD-TRN-00474 | 036909C-JVD-TRN-00474 | IFR | 2018-12-24 |  | Transmitted | TPSK-LSPA1-T-PE-00474 |  | A
036909C-1025-PDS-0600-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | A | 2018-09-26 | IFA | OL1-2G30-2575 | PE | 2018-09-26 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | A
036909C-1025-PDS-0600-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler | B | 2018-11-01 | IFD | OL1-2G30-2575 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0600-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | A | 2018-09-26 | IFA | OL1-2G30-2576 | PE | 2018-09-26 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | A
036909C-1025-PDS-0600-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler | B | 2018-11-01 | IFD | OL1-2G30-2576 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1025-PDS-0900-2577 | Process Equipment Datasheet - 10-P-2575 A-B - Deethanizer Reboiler Cond Pumps | A | 2018-12-03 | IFR | OL1-2G30-2577 | PE | 2018-12-04 | 036909C-JVD-TRN-00408 | 036909C-JVD-TRN-00408 | IFR | 2018-12-17 |  | Transmitted | TPSK-LSPA1-T-PE-00408 |  | A
036909C-1025-PDS-0500-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower | A | 2018-10-11 | IFR | OL1-2G30-2580 | PE | 2018-10-12 | 036909C-JVD-TRN-00162 | 036909C-JVD-TRN-00162 | IFR | 2018-10-26 | 2018-10-31 | R2-Comments as noted | TPSK-LSPA1-T-PE-00162 |  | A
036909C-1025-PDS-0500-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower | B | 2018-11-30 | IFD | OL1-2G30-2580 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | B
036909C-1025-PDS-0600-2582 | Process Equipment Datasheet - 10-E-2582 - C2 Tower Reflux Cooler | A | 2018-11-01 | IFR | OL1-2G30-2582 | PE | 2018-11-01 | 036909C-JVD-TRN-00265 | 036909C-JVD-TRN-00265 | IFR | 2018-11-15 | 2018-11-20 | R1-No comments | TPSK-LSPA1-T-PE-00265 |  | A
036909C-1025-PDS-0600-2585 | Process Equipment Data Sheet - 10-E-2585 - C2 Tower Bottoms Reboiler | A | 2018-09-06 | IFA | OL1-2G30-2585 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2585 | Process Equipment Datasheet - 10-E-2585 - C2 Tower Bottoms Reboiler | B | 2018-10-03 | IFD | OL1-2G30-2585 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0900-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps | A | 2018-11-14 | IFR | OL1-2G30-2586 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340 |  | A
036909C-1025-PDS-0900-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps | B | 2018-12-10 | IFD | OL1-2G30-2586 | PE | 2018-12-12 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00481 |  | B
036909C-1025-PDS-0600-2587 | Process Equipment Data Sheet - 10-E-2587 - C2 Tower Side Reboiler | A | 2018-09-06 | IFA | OL1-2G30-2587 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A1-Approved without comments | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1025-PDS-0600-2587 | Process Equipment Datasheet - 10-E-2587 - C2 Tower Side Reboiler | B | 2018-10-03 | IFD | OL1-2G30-2587 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1025-PDS-0600-2591 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler | A | 2018-10-23 | IFR | OL1-2G30-2591 | PE | 2018-10-24 | 036909C-JVD-TRN-00216 | 036909C-JVD-TRN-00216 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00216 |  | A
036909C-1026-PDS-0800-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber | A | 2018-12-05 | IFR | OL1-2G30-2600 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00439 |  | A
036909C-1026-PDS-0800-2610 | Process Equipment Datasheet - 10-D-2610 - C3 Hydrog Arsine Guard Bed | A | 2018-11-20 | IFR | OL1-2G30-2610 | PE | 2018-11-21 | 036909C-JVD-TRN-00345 | 036909C-JVD-TRN-00345 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-PE-00345 |  | A
036909C-1026-PDS-0500-2630 | Process Equipment Data Sheet - 10-T-2630 - Secondary Deethanizer | A | 2018-09-13 | IFA | OL1-2G30-2630 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | A
036909C-1026-PDS-0500-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer | B | 2018-10-12 | IFD | OL1-2G30-2630 | PE | 2018-10-12 | 036909C-JVD-TRN-00169 | 036909C-JVD-TRN-00169 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00169 |  | B
036909C-1026-PDS-0500-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer | C | 2018-11-30 | IFD | OL1-2G30-2630 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | C
036909C-1026-PDS-0600-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | A | 2018-09-20 | IFA | OL1-2G30-2631 | PE | 2018-09-24 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | A
036909C-1026-PDS-0600-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser | B | 2018-11-01 | IFD | OL1-2G30-2631 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0800-2632 | Process Equipment Datasheet - 10-D-2630 - Secondary Deeth Reflux Drum | A | 2018-11-07 | IFR | OL1-2G30-2632 | PE | 2018-11-07 | 036909C-JVD-TRN-00287 | 036909C-JVD-TRN-00287 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00287 |  | A
036909C-1026-PDS-0900-2633 | Process Equipment Datasheet - 10-P-2630 A-B - Secondary Deeth Reflux Pumps | A | 2018-11-05 | IFR | OL1-2G30-2633 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-PE-00277 |  | A
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | A | 2018-09-20 | IFA | OL1-2G30-2635 | PE | 2018-09-24 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | A
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | B | 2018-11-01 | IFD | OL1-2G30-2635 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0600-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler | C | 2018-12-04 | IFD | OL1-2G30-2635 | PE | 2018-12-07 | 036909C-JVD-TRN-00438 | 036909C-JVD-TRN-00438 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00438 |  | C
036909C-1026-PDS-0600-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | A | 2018-09-20 | IFA | OL1-2G30-2636 | PE | 2018-09-24 | 036909C-JVD-TRN-00074 | 036909C-JVD-TRN-00074 | IFA | 2018-10-08 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00074 |  | A
036909C-1026-PDS-0600-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | B | 2018-11-01 | IFD | OL1-2G30-2636 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0500-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower | A | 2018-10-18 | IFR | OL1-2G30-2640 | PE | 2018-10-22 | 036909C-JVD-TRN-00201 | 036909C-JVD-TRN-00201 | IFR | 2018-11-05 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00201 |  | A
036909C-1026-PDS-0500-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower | B | 2018-11-30 | IFD | OL1-2G30-2640 | PE | 2018-12-04 | 036909C-JVD-TRN-00407 | 036909C-JVD-TRN-00407 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00407 |  | B
036909C-1026-PDS-0600-2645 | Process Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | A | 2018-09-11 | IFA | OL1-2G30-2645 | PE | 2018-09-12 | 036909C-JVD-TRN-00041 | 036909C-JVD-TRN-00041 | IFA | 2018-09-26 | 2018-10-01 | A1-Approved without comments | TPSK-LSPA1-T-PE-00041 |  | A
036909C-1026-PDS-0600-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers | B | 2018-11-01 | IFD | OL1-2G30-2645 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0600-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers | C | 2018-12-04 | IFD | OL1-2G30-2645 | PE | 2018-12-07 | 036909C-JVD-TRN-00438 | 036909C-JVD-TRN-00438 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00438 |  | C
036909C-1026-PDS-0900-2646 | Process Equipment Datasheet - 10-P-2646 A-B - Propane Recycle Pumps | A | 2018-11-05 | IFR | OL1-2G30-2646 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-PE-00277 |  | A
036909C-1026-PDS-0900-2647 | Process Equipment Datasheet - 10-P-2647 - HP Propylene - Off Spec Pumps | A | 2018-11-08 | IFR | OL1-2G30-2647 | PE | 2018-11-09 | 036909C-JVD-TRN-00302 | 036909C-JVD-TRN-00302 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-PE-00302 |  | A
036909C-1026-PDS-0500-2660 | Process Equipment Data Sheet - 10-T-2660 - Debutanizer | A | 2018-09-13 | IFA | OL1-2G30-2660 | PE | 2018-09-14 | 036909C-JVD-TRN-00053 | 036909C-JVD-TRN-00053 | IFA | 2018-09-28 | 2018-10-03 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00053 |  | A
036909C-1026-PDS-0500-2660 | Process Equipment Datasheet - 10-T-2660 - Debutanizer | B | 2018-10-12 | IFD | OL1-2G30-2660 | PE | 2018-10-12 | 036909C-JVD-TRN-00169 | 036909C-JVD-TRN-00169 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00169 |  | B
036909C-1026-PDS-0600-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | A | 2018-09-26 | IFA | OL1-2G30-2661 | PE | 2018-09-26 | 036909C-JVD-TRN-00094 | 036909C-JVD-TRN-00094 | IFA | 2018-10-10 | 2018-10-12 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00094 |  | A
036909C-1026-PDS-0600-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser | B | 2018-11-01 | IFD | OL1-2G30-2661 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0800-2662 | Process Equipment Datasheet - 10-D-2660 - Debutanizer Reflux Drum | A | 2018-11-07 | IFR | OL1-2G30-2662 | PE | 2018-11-07 | 036909C-JVD-TRN-00287 | 036909C-JVD-TRN-00287 | IFR | 2018-11-21 |  | Transmitted | TPSK-LSPA1-T-PE-00287 |  | A
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | A | 2018-11-14 | IFR | OL1-2G30-2663 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00340 |  | A
036909C-1026-PDS-0900-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps | B | 2018-12-10 | IFD | OL1-2G30-2663 | PE | 2018-12-12 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00481 |  | B
036909C-1026-PDS-0600-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | A | 2018-09-27 | IFA | OL1-2G30-2665 | PE | 2018-09-27 | 036909C-JVD-TRN-00101 | 036909C-JVD-TRN-00101 | IFA | 2018-10-11 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00101 |  | A
036909C-1026-PDS-0600-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers | B | 2018-11-01 | IFD | OL1-2G30-2665 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | A | 2018-09-27 | IFA | OL1-2G30-2666 | PE | 2018-09-28 | 036909C-JVD-TRN-00112 | 036909C-JVD-TRN-00112 | IFA | 2018-10-12 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00112 |  | A
036909C-1026-PDS-0600-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler | B | 2018-11-26 | IFD | OL1-2G30-2666 | PE | 2018-11-27 | 036909C-JVD-TRN-00370 | 036909C-JVD-TRN-00370 | IFI |  | 2018-12-10 | A1-Approved without comments | TPSK-LSPA1-T-PE-00370 |  | B
036909C-1026-PDS-0900-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps | A | 2018-11-26 | IFR | OL1-2G30-2669 | PE | 2018-11-27 | 036909C-JVD-TRN-00371 | 036909C-JVD-TRN-00371 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00371 |  | A
036909C-1027-PDS-0800-2790 | Process Equipment Datasheet - 10-D-2790 - Light Oil Drain Drum | A | 2018-12-10 | IFR | OL1-2G30-2790 | PE | 2018-12-12 | 036909C-JVD-TRN-00482 | 036909C-JVD-TRN-00482 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-PE-00482 |  | A
036909C-1028-PDS-1000-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | A | 2018-08-22 | IFA | OL1-2G30-2800 | PE | 2018-08-22 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | A
036909C-1028-PDS-1000-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor | B | 2018-09-14 | IFD | OL1-2G30-2800 | PE | 2018-09-17 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | B
036909C-1028-PDS-0900-2801 | Process Equipment Datasheet - 10-P-2805 A-B - Propylene Product Pumps | A | 2018-11-05 | IFR | OL1-2G30-2801 | PE | 2018-11-06 | 036909C-JVD-TRN-00277 | 036909C-JVD-TRN-00277 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-PE-00277 |  | A
036909C-1028-PDS-0800-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum | A | 2018-10-23 | IFR | OL1-2G30-2805 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1028-PDS-0800-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum | B | 2018-11-21 | IFD | OL1-2G30-2805 | PE | 2018-11-21 | 036909C-JVD-TRN-00348 | 036909C-JVD-TRN-00348 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00348 |  | B
036909C-1028-PDS-0600-2806 | Process Equipment Datasheet - 10-E-2805 - C3 Refrig Condensers | A | 2018-09-28 | IFA | OL1-2G30-2806 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1028-PDS-0600-2806 | Process Equipment Datasheet - 10-E-2805 A-B - C3 Refrig Condensers | B | 2018-11-01 | IFD | OL1-2G30-2806 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | A | 2018-09-28 | IFA | OL1-2G30-2807 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1028-PDS-0600-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 | B | 2018-11-01 | IFD | OL1-2G30-2807 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | A | 2018-09-28 | IFA | OL1-2G30-2809 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1028-PDS-0600-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 | B | 2018-11-01 | IFD | OL1-2G30-2809 | PE | 2018-11-05 | 036909C-JVD-TRN-00273 | 036909C-JVD-TRN-00273 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00273 |  | B
036909C-1028-PDS-0800-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2810 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1028-PDS-0800-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2810 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1028-PDS-0800-2815 | Process Equipment Datasheet - 10-D-2815 - C3R Drain Drum | A | 2018-12-04 | IFR | OL1-2G30-2815 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00439 |  | A
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | A | 2018-11-14 | IFR | OL1-2G30-2816 | PE | 2018-11-20 | 036909C-JVD-TRN-00340 | 036909C-JVD-TRN-00340 | IFR | 2018-12-04 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00340 |  | A
036909C-1028-PDS-0900-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump | B | 2018-12-10 | IFD | OL1-2G30-2816 | PE | 2018-12-12 | 036909C-JVD-TRN-00481 | 036909C-JVD-TRN-00481 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00481 |  | B
036909C-1028-PDS-0800-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2820 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1028-PDS-0800-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2820 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1028-PDS-0800-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2830 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1028-PDS-0800-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2830 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1028-PDS-0800-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum | A | 2018-10-08 | IFR | OL1-2G30-2840 | PE | 2018-10-09 | 036909C-JVD-TRN-00144 | 036909C-JVD-TRN-00144 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00144 |  | A
036909C-1028-PDS-0800-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2840 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1028-PDS-1000-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | A | 2018-08-22 | IFA | OL1-2G30-2850 | PE | 2018-08-22 | 036909C-JVD-TRN-00025 | 036909C-JVD-TRN-00025 | IFA | 2018-09-05 | 2018-09-11 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00025 |  | A
036909C-1028-PDS-1000-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor | B | 2018-09-14 | IFD | OL1-2G30-2850 | PE | 2018-09-17 | 036909C-JVD-TRN-00055 | 036909C-JVD-TRN-00055 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00055 |  | B
036909C-1028-PDS-0600-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | A | 2018-09-28 | IFA | OL1-2G30-2852 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1028-PDS-0600-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 | B | 2018-11-01 | IFD | OL1-2G30-2852 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | A | 2018-09-28 | IFA | OL1-2G30-2853 | PE | 2018-09-28 | 036909C-JVD-TRN-00113 | 036909C-JVD-TRN-00113 | IFA | 2018-10-12 | 2018-10-12 | A1-Approved without comments | TPSK-LSPA1-T-PE-00113 |  | A
036909C-1028-PDS-0600-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 | B | 2018-11-01 | IFD | OL1-2G30-2853 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0800-2854 | Process Equipment Datasheet - 10-D-2855 - C2R Surge Drum | A | 2018-10-23 | IFR | OL1-2G30-2854 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R1-No comments | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1028-PDS-0900-2855 | Process Equipment Datasheet - 10-P-2855 A-B - Ethylene Product Pumps | A | 2018-11-27 | IFR | OL1-2G30-2855 | PE | 2018-11-28 | 036909C-JVD-TRN-00379 | 036909C-JVD-TRN-00379 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-PE-00379 |  | A
036909C-1028-PDS-0600-2856 | Process Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | 2018-09-10 | IFA | OL1-2G30-2856 | PE | 2018-09-11 | 036909C-JVD-TRN-00039 | 036909C-JVD-TRN-00039 | IFA | 2018-09-25 | 2018-09-28 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-PE-00039 |  | A
036909C-1028-PDS-0600-2856 | Process Equipment Datasheet - 10-E-2855 - C2R Condenser | B | 2018-11-01 | IFD | OL1-2G30-2856 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2857 | Process Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | 2018-09-11 | IFA | OL1-2G30-2857 | PE | 2018-09-12 | 036909C-JVD-TRN-00041 | 036909C-JVD-TRN-00041 | IFA | 2018-09-26 | 2018-10-01 | A1-Approved without comments | TPSK-LSPA1-T-PE-00041 |  | A
036909C-1028-PDS-0600-2857 | Process Equipment Datasheet - 10-E-2857 - HP Ethylene Product Vaporizer | B | 2018-11-01 | IFD | OL1-2G30-2857 | PE | 2018-11-05 | 036909C-JVD-TRN-00272 | 036909C-JVD-TRN-00272 | IFI |  | 2018-11-26 | A1-Approved without comments | TPSK-LSPA1-T-PE-00272 |  | B
036909C-1028-PDS-0600-2858 | Process Equipment Datasheet - 10-E-2858 - HP Ethylene Product Superheater | A | 2018-10-23 | IFR | OL1-2G30-2858 | PE | 2018-10-24 | 036909C-JVD-TRN-00223 | 036909C-JVD-TRN-00223 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00223 |  | A
036909C-1028-PDS-0800-2860 | Process Equipment Datasheet - 10-D-2860 - C2R 1st Stage Suction Drum | A | 2018-10-22 | IFR | OL1-2G30-2860 | PE | 2018-10-23 | 036909C-JVD-TRN-00208 | 036909C-JVD-TRN-00208 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-PE-00208 |  | A
036909C-1028-PDS-0800-2865 | Process Equipment Datasheet - 10-D-2865 - C2R Drain Drum | A | 2018-12-06 | IFR | OL1-2G30-2865 | PE | 2018-12-07 | 036909C-JVD-TRN-00445 | 036909C-JVD-TRN-00445 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00445 |  | A
036909C-1028-PDS-0800-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum | A | 2018-10-23 | IFR | OL1-2G30-2870 | PE | 2018-10-24 | 036909C-JVD-TRN-00218 | 036909C-JVD-TRN-00218 | IFR | 2018-11-07 | 2018-11-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00218 |  | A
036909C-1028-PDS-0800-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum | B | 2018-11-21 | IFD | OL1-2G30-2870 | PE | 2018-11-21 | 036909C-JVD-TRN-00349 | 036909C-JVD-TRN-00349 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00349 |  | B
036909C-1028-PDS-0800-2880 | Process Equipment Datasheet - 10-D-2880 - C2R 3rd Stage Suction Drum | A | 2018-10-22 | IFR | OL1-2G30-2880 | PE | 2018-10-23 | 036909C-JVD-TRN-00208 | 036909C-JVD-TRN-00208 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-PE-00208 |  | A
036909C-1028-PDS-0600-2882 | Process Equipment Data Sheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | A | 2018-09-06 | IFA | OL1-2G30-2882 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1028-PDS-0600-2882 | Process Equipment Datasheet - 10-E-2882 - LP Ethylene Product Cooler No 1 | B | 2018-10-03 | IFD | OL1-2G30-2882 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1028-PDS-0600-2884 | Process Equipment Data Sheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | A | 2018-09-06 | IFA | OL1-2G30-2884 | PE | 2018-09-10 | 036909C-JVD-TRN-00036 | 036909C-JVD-TRN-00036 | IFA | 2018-09-24 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00036 |  | A
036909C-1028-PDS-0600-2884 | Process Equipment Datasheet - 10-E-2884 - LP Ethylene Product Cooler No 2 | B | 2018-10-03 | IFD | OL1-2G30-2884 | PE | 2018-10-04 | 036909C-JVD-TRN-00131 | 036909C-JVD-TRN-00131 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00131 |  | B
036909C-1029-PDS-2600-2914 | Process Equipment Datasheet - 10-PK-2914 - Neutralization Injection Pkg | A | 2018-10-15 | IFR | OL1-2G30-2914 | PE | 2018-10-16 | 036909C-JVD-TRN-00181 | 036909C-JVD-TRN-00181 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-PE-00181 |  | A
036909C-1030-PDS-1000-3073 | Process Equipment Data Sheet - 10-C-3070 - BDU Recycle Gas Compressor | A | 2018-11-20 | IFR | OL1-2G30-3073 | PE | 2018-11-20 | 036909C-JVD-TRN-00344 | 036909C-JVD-TRN-00344 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-PE-00344 |  | A
036909C-1051-PDS-0800-5100 | Process Equipment Data Sheet - 10-D-5100 - Deaerator | A | 2018-10-09 | IFR | OL1-2G30-5100 | PE | 2018-10-09 | 036909C-JVD-TRN-00151 | 036909C-JVD-TRN-00151 | IFR | 2018-10-23 | 2018-11-05 | R2-Comments as noted | TPSK-LSPA1-T-PE-00151 |  | A
036909C-1051-PDS-0800-5100 | Process Equipment Datasheet - 10-D-5100 - Deaerator | B | 2018-11-14 | IFD | OL1-2G30-5100 | PE | 2018-11-14 | 036909C-JVD-TRN-00318 | 036909C-JVD-TRN-00318 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00318 |  | B
036909C-1051-PDS-0900-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | A | 2018-10-04 | IFR | OL1-2G30-5101 | PE | 2018-10-08 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | A
036909C-1051-PDS-0900-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps | B | 2018-10-30 | IFD | OL1-2G30-5101 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00251 |  | B
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | A | 2018-10-04 | IFR | OL1-2G30-5102 | PE | 2018-10-08 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | A
036909C-1051-PDS-0900-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps | B | 2018-10-30 | IFD | OL1-2G30-5102 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00251 |  | B
036909C-1051-PDS-0600-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | A | 2018-10-25 | IFR | OL1-2G30-5103 | PE | 2018-10-25 | 036909C-JVD-TRN-00230 | 036909C-JVD-TRN-00230 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00230 |  | A
036909C-1051-PDS-0600-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser | B | 2018-11-19 | IFD | OL1-2G30-5103 | PE | 2018-11-26 | 036909C-JVD-TRN-00366 | 036909C-JVD-TRN-00366 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00366 |  | B
036909C-1051-PDS-0600-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser | A | 2018-10-26 | IFR | OL1-2G30-5107 | PE | 2018-10-30 | 036909C-JVD-TRN-00243 | 036909C-JVD-TRN-00243 | IFR | 2018-11-12 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00243 |  | A
036909C-1051-PDS-0600-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler | A | 2018-10-29 | IFR | OL1-2G30-5108 | PE | 2018-10-30 | 036909C-JVD-TRN-00243 | 036909C-JVD-TRN-00243 | IFR | 2018-11-12 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00243 |  | A
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | A | 2018-10-04 | IFR | OL1-2G30-5109 | PE | 2018-10-08 | 036909C-JVD-TRN-00141 | 036909C-JVD-TRN-00141 | IFR | 2018-10-22 | 2018-10-26 | R1-No comments | TPSK-LSPA1-T-PE-00141 |  | A
036909C-1051-PDS-0900-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps | B | 2018-10-30 | IFD | OL1-2G30-5109 | PE | 2018-10-31 | 036909C-JVD-TRN-00251 | 036909C-JVD-TRN-00251 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00251 |  | B
036909C-1051-PDS-2500-5110 | Process Equipment Datasheet - 10-TK-5110 - Condensate Tank | A | 2018-11-27 | IFR | OL1-2G30-5110 | PE | 2018-11-27 | 036909C-JVD-TRN-00374 | 036909C-JVD-TRN-00374 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00374 |  | A
036909C-1051-PDS-0900-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps | A | 2018-10-23 | IFR | OL1-2G30-5111 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219 |  | A
036909C-1051-PDS-0900-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps | B | 2018-11-16 | IFD | OL1-2G30-5111 | PE | 2018-11-26 | 036909C-JVD-TRN-00363 | 036909C-JVD-TRN-00363 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00363 |  | B
036909C-1051-PDS-0800-5112 | Process Equipment Datasheet - 10-D-5112 - Suspect Condensate Flash Drum | A | 2018-11-05 | IFR | OL1-2G30-5112 | PE | 2018-11-05 | 036909C-JVD-TRN-00274 | 036909C-JVD-TRN-00274 | IFR | 2018-11-21 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00274 |  | A
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | A | 2018-10-25 | IFR | OL1-2G30-5113 | PE | 2018-10-25 | 036909C-JVD-TRN-00230 | 036909C-JVD-TRN-00230 | IFR | 2018-11-08 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00230 |  | A
036909C-1051-PDS-0600-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler | B | 2018-11-19 | IFD | OL1-2G30-5113 | PE | 2018-11-26 | 036909C-JVD-TRN-00366 | 036909C-JVD-TRN-00366 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-PE-00366 |  | B
036909C-1051-PDS-0800-5114 | Process Equipment Datasheet - 10-D-5114 - LP Condensate Flash Drum | A | 2018-11-05 | IFR | OL1-2G30-5114 | PE | 2018-11-05 | 036909C-JVD-TRN-00274 | 036909C-JVD-TRN-00274 | IFR | 2018-11-21 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-PE-00274 |  | A
036909C-1051-PDS-0200-5115 | Process Equipment Datasheet - 10-PK-5115 - Condensate Carbon Filter Pkg | A | 2018-11-16 | IFR | OL1-2G30-5115 | PE | 2018-11-26 | 036909C-JVD-TRN-00362 | 036909C-JVD-TRN-00362 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-PE-00362 |  | A
036909C-1051-PDS-2500-5120 | Process Equipment Datasheet - 10-TK-5120 - Raw Condensate Tank | A | 2018-11-16 | IFR | OL1-2G30-5120 | PE | 2018-11-26 | 036909C-JVD-TRN-00364 | 036909C-JVD-TRN-00364 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-PE-00364 |  | A
036909C-1051-PDS-0900-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps | A | 2018-10-23 | IFR | OL1-2G30-5121 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219 |  | A
036909C-1051-PDS-0900-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps | B | 2018-11-16 | IFD | OL1-2G30-5121 | PE | 2018-11-26 | 036909C-JVD-TRN-00363 | 036909C-JVD-TRN-00363 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00363 |  | B
036909C-1051-PDS-0200-5125 | Process Equipment Datasheet - 10-PK-5125 - Condensate Polisher Pkg | A | 2018-11-27 | IFR | OL1-2G30-5125 | PE | 2018-11-27 | 036909C-JVD-TRN-00373 | 036909C-JVD-TRN-00373 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00373 |  | A
036909C-1051-PDS-0800-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum | A | 2018-11-15 | IFR | OL1-2G30-5140 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331 |  | A
036909C-1051-PDS-0900-5141 | Process Equipment Datasheet - 10-P-5140 A-B - Intermittent Blowdown Pumps | A | 2018-10-23 | IFR | OL1-2G30-5141 | PE | 2018-10-24 | 036909C-JVD-TRN-00219 | 036909C-JVD-TRN-00219 | IFR | 2018-11-07 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00219 |  | A
036909C-1051-PDS-0800-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum | A | 2018-11-15 | IFR | OL1-2G30-5150 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331 |  | A
036909C-1051-PDS-0800-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum | B | 2018-12-05 | IFD | OL1-2G30-5150 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00440 |  | B
036909C-1052-PDS-0800-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum | A | 2018-11-15 | IFR | OL1-2G30-5200 | PE | 2018-11-19 | 036909C-JVD-TRN-00331 | 036909C-JVD-TRN-00331 | IFR | 2018-12-03 | 2018-12-04 | R2-Comments as noted | TPSK-LSPA1-T-PE-00331 |  | A
036909C-1052-PDS-0800-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum | B | 2018-12-05 | IFD | OL1-2G30-5200 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00440 |  | B
036909C-1052-PDS-0600-5201 | Process Equipment Datasheet - 10-E-5200 - MP Ethylene Superheater | A | 2018-11-05 | IFR | OL1-2G30-5201 | PE | 2018-11-05 | 036909C-JVD-TRN-00275 | 036909C-JVD-TRN-00275 | IFR | 2018-11-19 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-PE-00275 |  | A
036909C-1052-PDS-0600-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer | A | 2018-11-14 | IFR | OL1-2G30-5210 | PE | 2018-11-15 | 036909C-JVD-TRN-00321 | 036909C-JVD-TRN-00321 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00321 |  | A
036909C-1053-PDS-0300-5350 | Process Equipment Data Sheet - 10-PK-5350 - Cooling Tower | A | 2018-09-24 | IFA | OL1-2G30-5350 | PE | 2018-09-25 | 036909C-JVD-TRN-00082 | 036909C-JVD-TRN-00082 | IFA | 2018-10-09 | 2018-10-13 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00082 |  | A
036909C-1053-PDS-0300-5350 | Process Equipment Datasheet - 10-PK-5350 - Cooling Tower | B | 2018-10-24 | IFD | OL1-2G30-5350 | PE | 2018-10-24 | 036909C-JVD-TRN-00226 | 036909C-JVD-TRN-00226 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00226 |  | B
036909C-1053-PDS-0900-5352 | Process Equipment Data Sheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-5352 | PE | 2018-09-24 | 036909C-JVD-TRN-00075 | 036909C-JVD-TRN-00075 | IFA | 2018-10-08 |  | Transmitted | TPSK-LSPA1-T-PE-00075 |  | A
036909C-1053-PDS-0900-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | B | 2018-10-24 | IFD | OL1-2G30-5352 | PE | 2018-10-24 | 036909C-JVD-TRN-00225 | 036909C-JVD-TRN-00225 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00225 |  | B
036909C-1053-PDS-0900-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps | C | 2018-10-25 | IFD | OL1-2G30-5352 | PE | 2018-10-26 | 036909C-JVD-TRN-00234 | 036909C-JVD-TRN-00234 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00075 |  | C
036909C-1053-PDS-0300-5355 | Process Equipment Data Sheet - 10-PK-5355 - Side Stream Filter Package | A | 2018-09-24 | IFA | OL1-2G30-5355 | PE | 2018-09-25 | 036909C-JVD-TRN-00082 | 036909C-JVD-TRN-00082 | IFA | 2018-10-09 | 2018-10-13 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00082 |  | A
036909C-1053-PDS-0300-5355 | Process Equipment Datasheet - 10-PK-5355 - Side Stream Filter Pkg | B | 2018-10-24 | IFD | OL1-2G30-5355 | PE | 2018-10-24 | 036909C-JVD-TRN-00226 | 036909C-JVD-TRN-00226 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00226 |  | B
036909C-1053-PDS-0900-5361 | Process Equipment Data Sheet - 10-P-5360 A-C - CTU Cooling Water Pumps | A | 2018-09-20 | IFA | OL1-2G30-5361 | PE | 2018-09-24 | 036909C-JVD-TRN-00075 | 036909C-JVD-TRN-00075 | IFA | 2018-10-08 | 2018-10-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00075 |  | A
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | B | 2018-10-24 | IFD | OL1-2G30-5361 | PE | 2018-10-24 | 036909C-JVD-TRN-00225 | 036909C-JVD-TRN-00225 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00225 |  | B
036909C-1053-PDS-0900-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps | C | 2018-10-25 | IFD | OL1-2G30-5361 | PE | 2018-10-26 | 036909C-JVD-TRN-00234 | 036909C-JVD-TRN-00234 | IFI |  | 2018-11-14 | A1-Approved without comments | TPSK-LSPA1-T-PE-00075 |  | C
036909C-1053-PDS-2600-5390 | Process Equipment Datasheet - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5390 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00375 |  | A
036909C-1053-PDS-2600-5392 | Process Equipment Datasheet - 10-PK-5392 - Mild Steel Corr Inhibitor Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5392 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00375 |  | A
036909C-1053-PDS-2600-5394 | Process Equipment Datasheet - 10-PK-5394 - Dispersant Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5394 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00375 |  | A
036909C-1053-PDS-2600-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg | A | 2018-11-27 | IFR | OL1-2G30-5397 | PE | 2018-11-27 | 036909C-JVD-TRN-00375 | 036909C-JVD-TRN-00375 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-PE-00375 |  | A
036909C-1054-PDS-0800-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver | A | 2018-12-11 | IFR | OL1-2G30-5400 | PE | 2018-12-12 | 036909C-JVD-TRN-00485 | 036909C-JVD-TRN-00485 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-PE-00485 |  | A
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | A | 2018-10-12 | IFR | OL1-2G30-5500 | PE | 2018-10-12 | 036909C-JVD-TRN-00168 | 036909C-JVD-TRN-00168 | IFR | 2018-10-26 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-PE-00168 |  | A
036909C-1055-PDS-0800-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum | B | 2018-12-04 | IFD | OL1-2G30-5500 | PE | 2018-12-05 | 036909C-JVD-TRN-00417 | 036909C-JVD-TRN-00417 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00417 |  | B
036909C-1055-PDS-0800-5510 | Process Equipment Datasheet - 10-D-5510 - Cold Flare Drum | A | 2018-11-29 | IFR | OL1-2G30-5510 | PE | 2018-11-29 | 036909C-JVD-TRN-00397 | 036909C-JVD-TRN-00397 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00397 |  | A
036909C-1055-PDS-0800-5520 | Process Equipment Datasheet - 10-D-5520 - Vent Collection Drum | A | 2018-11-16 | IFR | OL1-2G30-5520 | PE | 2018-11-26 | 036909C-JVD-TRN-00365 | 036909C-JVD-TRN-00365 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-PE-00365 |  | A
036909C-1055-PDS-1000-5521 | Process Equipment Datasheet - 10-PK-5520 - LP Vent Blower Pkg | A | 2018-11-15 | IFR | OL1-2G30-5521 | PE | 2018-11-19 | 036909C-JVD-TRN-00332 | 036909C-JVD-TRN-00332 | IFR | 2018-12-03 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-PE-00332 |  | A
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | A | 2018-10-04 | IFR | OL1-2G30-5550 | PE | 2018-10-08 | 036909C-JVD-TRN-00142 | 036909C-JVD-TRN-00142 | IFR | 2018-10-22 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00142 |  | A
036909C-1055-PDS-0800-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum | B | 2018-12-05 | IFD | OL1-2G30-5550 | PE | 2018-12-07 | 036909C-JVD-TRN-00440 | 036909C-JVD-TRN-00440 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00440 |  | B
036909C-1055-PDS-0800-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum | A | 2018-12-05 | IFR | OL1-2G30-5552 | PE | 2018-12-07 | 036909C-JVD-TRN-00439 | 036909C-JVD-TRN-00439 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-PE-00439 |  | A
036909C-1055-PDS-0180-5560 | Process Equipment Datasheet - 10-PK-5560 - HP - Polyolefins Flare Pkg | A | 2018-11-29 | IFR | OL1-2G30-5560 | PE | 2018-11-29 | 036909C-JVD-TRN-00398 | 036909C-JVD-TRN-00398 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-PE-00398 |  | A
036909C-1056-PDS-0840-5612 | Process Equipment Datasheet - 10-F-5610 - Hydroblast Filter | A | 2018-12-06 | IFR | OL1-2G30-5612 | PE | 2018-12-10 | 036909C-JVD-TRN-00454 | 036909C-JVD-TRN-00454 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00454 |  | A
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | A | 2018-11-06 | IFR | OL1-2G30-5644 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281 |  | A
036909C-1056-PDS-2600-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package | B | 2018-12-05 | IFD | OL1-2G30-5644 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00442 |  | B
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | A | 2018-11-06 | IFR | OL1-2G30-5650 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281 |  | A
036909C-1056-PDS-2600-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg | B | 2018-12-05 | IFD | OL1-2G30-5650 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00442 |  | B
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | A | 2018-11-06 | IFR | OL1-2G30-5653 | PE | 2018-11-06 | 036909C-JVD-TRN-00282 | 036909C-JVD-TRN-00282 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00282 |  | A
036909C-1056-PDS-0200-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg | B | 2018-12-05 | IFD | OL1-2G30-5653 | PE | 2018-12-07 | 036909C-JVD-TRN-00441 | 036909C-JVD-TRN-00441 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00441 |  | B
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | A | 2018-11-06 | IFR | OL1-2G30-5670 | PE | 2018-11-06 | 036909C-JVD-TRN-00281 | 036909C-JVD-TRN-00281 | IFR | 2018-11-20 | 2018-11-26 | R2-Comments as noted | TPSK-LSPA1-T-PE-00281 |  | A
036909C-1056-PDS-2600-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg | B | 2018-12-05 | IFD | OL1-2G30-5670 | PE | 2018-12-07 | 036909C-JVD-TRN-00442 | 036909C-JVD-TRN-00442 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00442 |  | B
036909C-1059-PDS-2500-5900 | Process Equipment Datasheet - 10-TK-5900 - Sulfuric Acid Tank | A | 2018-11-16 | IFR | OL1-2G30-5900 | PE | 2018-11-26 | 036909C-JVD-TRN-00364 | 036909C-JVD-TRN-00364 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-PE-00364 |  | A
036909C-1059-PDS-2600-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg | A | 2018-12-07 | IFR | OL1-2G30-5910 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00456 |  | A
036909C-1059-PDS-2600-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg | A | 2018-12-07 | IFR | OL1-2G30-5912 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00456 |  | A
036909C-1059-PDS-2600-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg | A | 2018-12-07 | IFR | OL1-2G30-5914 | PE | 2018-12-10 | 036909C-JVD-TRN-00456 | 036909C-JVD-TRN-00456 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-PE-00456 |  | A
036909C-1059-PDS-2500-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank | A | 2018-11-29 | IFR | OL1-2G30-5950 | PE | 2018-12-04 | 036909C-JVD-TRN-00406 | 036909C-JVD-TRN-00406 | IFR | 2018-12-17 |  | Transmitted | TPSK-LSPA1-T-PE-00406 |  | A
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | A | 2018-08-23 | IFA | OL1-2G40-0010 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1000-PFD-0010-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme | B | 2018-10-09 | IFD | OL1-2G40-0010 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | A | 2018-08-23 | IFA | OL1-2G41-0001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1000-PFD-0010-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols | B | 2018-10-09 | IFD | OL1-2G41-0001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | A | 2018-08-23 | IFA | OL1-2G41-0002 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1000-PFD-0010-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index | B | 2018-10-09 | IFD | OL1-2G41-0002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | 2018-08-23 | IFA | OL1-2G41-1001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1010-PFD-0010-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | B | 2018-10-09 | IFD | OL1-2G41-1001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | 2018-08-23 | IFA | OL1-2G41-1003 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1010-PFD-0010-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | B | 2018-10-09 | IFD | OL1-2G41-1003 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | A | 2018-08-23 | IFA | OL1-2G41-1101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1011-PFD-0010-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace | B | 2018-10-09 | IFD | OL1-2G41-1101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | 2018-08-23 | IFA | OL1-2G41-1201 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1012-PFD-0010-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | B | 2018-10-09 | IFD | OL1-2G41-1201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | 2018-08-23 | IFA | OL1-2G41-1901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1019-PFD-0010-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | B | 2018-10-09 | IFD | OL1-2G41-1901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-1902 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1019-PFD-0010-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-1902 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | 2018-08-23 | IFA | OL1-2G41-2001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1020-PFD-0010-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | B | 2018-10-09 | IFD | OL1-2G41-2001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-08-23 | IFA | OL1-2G41-2002 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1020-PFD-0010-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | B | 2018-10-09 | IFD | OL1-2G41-2002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | 2018-08-23 | IFA | OL1-2G41-2101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1021-PFD-0010-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | B | 2018-10-09 | IFD | OL1-2G41-2101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | 2018-08-23 | IFA | OL1-2G41-2102 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1021-PFD-0010-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | B | 2018-10-09 | IFD | OL1-2G41-2102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | 2018-08-23 | IFA | OL1-2G41-2103 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1021-PFD-0010-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | B | 2018-10-09 | IFD | OL1-2G41-2103 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | 2018-08-23 | IFA | OL1-2G41-2201 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1022-PFD-0010-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | B | 2018-10-09 | IFD | OL1-2G41-2201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | 2018-08-23 | IFA | OL1-2G41-2301 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | B | 2018-10-09 | IFD | OL1-2G41-2301 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | 2018-08-23 | IFA | OL1-2G41-2302 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | B | 2018-10-09 | IFD | OL1-2G41-2302 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | 2018-08-23 | IFA | OL1-2G41-2303 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | B | 2018-10-09 | IFD | OL1-2G41-2303 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | 2018-08-23 | IFA | OL1-2G41-2304 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | B | 2018-10-09 | IFD | OL1-2G41-2304 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | 2018-08-23 | IFA | OL1-2G41-2305 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1023-PFD-0010-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | B | 2018-10-09 | IFD | OL1-2G41-2305 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | 2018-08-23 | IFA | OL1-2G41-2401 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | B | 2018-10-09 | IFD | OL1-2G41-2401 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | 2018-08-23 | IFA | OL1-2G41-2402 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | B | 2018-10-09 | IFD | OL1-2G41-2402 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | 2018-08-23 | IFA | OL1-2G41-2403 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | B | 2018-10-09 | IFD | OL1-2G41-2403 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2404 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2404 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | 2018-08-23 | IFA | OL1-2G41-2405 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1024-PFD-0010-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | B | 2018-10-09 | IFD | OL1-2G41-2405 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | 2018-08-23 | IFA | OL1-2G41-2501 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | B | 2018-10-09 | IFD | OL1-2G41-2501 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | 2018-08-23 | IFA | OL1-2G41-2502 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | B | 2018-10-09 | IFD | OL1-2G41-2502 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | 2018-08-23 | IFA | OL1-2G41-2503 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | B | 2018-10-09 | IFD | OL1-2G41-2503 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | 2018-08-23 | IFA | OL1-2G41-2504 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | B | 2018-10-09 | IFD | OL1-2G41-2504 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | 2018-08-23 | IFA | OL1-2G41-2505 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | B | 2018-10-09 | IFD | OL1-2G41-2505 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | 2018-08-23 | IFA | OL1-2G41-2506 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1025-PFD-0010-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | B | 2018-10-09 | IFD | OL1-2G41-2506 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2601 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1026-PFD-0010-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2601 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | 2018-08-23 | IFA | OL1-2G41-2602 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1026-PFD-0010-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | B | 2018-10-09 | IFD | OL1-2G41-2602 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | 2018-08-23 | IFA | OL1-2G41-2603 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1026-PFD-0010-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | B | 2018-10-09 | IFD | OL1-2G41-2603 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | 2018-08-23 | IFA | OL1-2G41-2604 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1026-PFD-0010-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | B | 2018-10-09 | IFD | OL1-2G41-2604 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | A | 2018-08-23 | IFA | OL1-2G41-2701 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1027-PFD-0010-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer | B | 2018-10-09 | IFD | OL1-2G41-2701 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | A | 2018-08-23 | IFA | OL1-2G41-2702 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1027-PFD-0010-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower | B | 2018-10-09 | IFD | OL1-2G41-2702 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | A | 2018-08-23 | IFA | OL1-2G41-2703 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1027-PFD-0010-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System | B | 2018-10-09 | IFD | OL1-2G41-2703 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | A | 2018-08-23 | IFA | OL1-2G41-2704 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1027-PFD-0010-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation | B | 2018-10-09 | IFD | OL1-2G41-2704 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | 2018-08-23 | IFA | OL1-2G41-2801 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1028-PFD-0010-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | B | 2018-10-09 | IFD | OL1-2G41-2801 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | 2018-08-23 | IFA | OL1-2G41-2802 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1028-PFD-0010-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | B | 2018-10-09 | IFD | OL1-2G41-2802 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | 2018-08-23 | IFA | OL1-2G41-2803 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1028-PFD-0010-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | B | 2018-10-09 | IFD | OL1-2G41-2803 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | 2018-08-23 | IFA | OL1-2G41-2804 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1028-PFD-0010-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | B | 2018-10-09 | IFD | OL1-2G41-2804 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-2901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1029-PFD-0010-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-2901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | A | 2018-08-23 | IFA | OL1-2G41-3001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation | B | 2018-10-09 | IFD | OL1-2G41-3001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | A | 2018-08-23 | IFA | OL1-2G41-3002 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation | B | 2018-10-09 | IFD | OL1-2G41-3002 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | A | 2018-08-23 | IFA | OL1-2G41-3003 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier | B | 2018-10-09 | IFD | OL1-2G41-3003 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | A | 2018-08-23 | IFA | OL1-2G41-3004 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing | B | 2018-10-09 | IFD | OL1-2G41-3004 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | A | 2018-08-23 | IFA | OL1-2G41-3005 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1030-PFD-0010-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation | B | 2018-10-09 | IFD | OL1-2G41-3005 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | A | 2018-08-23 | IFA | OL1-2G41-3101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1031-PFD-0010-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration | B | 2018-10-09 | IFD | OL1-2G41-3101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam And Condensate System | A | 2018-08-23 | IFA | OL1-2G41-3102 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1031-PFD-0010-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam and Condensate System | B | 2018-10-09 | IFD | OL1-2G41-3102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | A | 2018-08-23 | IFA | OL1-2G41-3901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1039-PFD-0010-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage | B | 2018-10-09 | IFD | OL1-2G41-3901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable And Demin Water Systems | A | 2018-08-23 | IFA | OL1-2G42-5001 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1050-PFD-0030-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable and Demin Water Systems | B | 2018-10-09 | IFD | OL1-2G42-5001 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | A | 2018-08-23 | IFA | OL1-2G42-5101 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1051-PFD-0030-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram | B | 2018-10-09 | IFD | OL1-2G42-5101 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate And Boiler Feedwater Systems | A | 2018-08-23 | IFA | OL1-2G42-5102 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1051-PFD-0030-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate and Boiler Feedwater Systems | B | 2018-10-09 | IFD | OL1-2G42-5102 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | A | 2018-08-23 | IFA | OL1-2G42-5103 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1051-PFD-0030-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System | B | 2018-10-09 | IFD | OL1-2G42-5103 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | A | 2018-08-23 | IFA | OL1-2G42-5104 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1051-PFD-0030-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System | B | 2018-10-09 | IFD | OL1-2G42-5104 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | A | 2018-08-23 | IFA | OL1-2G42-5201 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1052-PFD-0030-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System | B | 2018-10-09 | IFD | OL1-2G42-5201 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | A | 2018-08-23 | IFA | OL1-2G42-5301 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1053-PFD-0030-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram | B | 2018-10-09 | IFD | OL1-2G42-5301 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | A | 2018-08-23 | IFA | OL1-2G42-5311 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1053-PFD-0030-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower | B | 2018-10-09 | IFD | OL1-2G42-5311 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air And Nitrogen Systems | A | 2018-08-23 | IFA | OL1-2G42-5401 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1054-PFD-0030-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air and Nitrogen Systems | B | 2018-10-09 | IFD | OL1-2G42-5401 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare And Blowdown System | A | 2018-08-23 | IFA | OL1-2G42-5501 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1055-PFD-0030-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare and Blowdown System | B | 2018-10-09 | IFD | OL1-2G42-5501 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | A | 2018-08-23 | IFA | OL1-2G42-5502 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1055-PFD-0030-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection | B | 2018-10-09 | IFD | OL1-2G42-5502 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | A | 2018-08-23 | IFA | OL1-2G42-5511 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1055-PFD-0030-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare | B | 2018-10-09 | IFD | OL1-2G42-5511 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | A | 2018-08-23 | IFA | OL1-2G42-5512 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1055-PFD-0030-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare | B | 2018-10-09 | IFD | OL1-2G42-5512 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5601 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5601 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | A | 2018-08-23 | IFA | OL1-2G42-5602 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection | B | 2018-10-09 | IFD | OL1-2G42-5602 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | A | 2018-08-23 | IFA | OL1-2G42-5603 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin | B | 2018-10-09 | IFD | OL1-2G42-5603 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5604 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5604 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | A | 2018-08-23 | IFA | OL1-2G42-5610 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection | B | 2018-10-09 | IFD | OL1-2G42-5610 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | A | 2018-08-23 | IFA | OL1-2G42-5611 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection | B | 2018-10-09 | IFD | OL1-2G42-5611 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | A | 2018-08-23 | IFA | OL1-2G42-5612 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank | B | 2018-10-09 | IFD | OL1-2G42-5612 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | A | 2018-08-23 | IFA | OL1-2G42-5613 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages | B | 2018-10-09 | IFD | OL1-2G42-5613 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | A | 2018-08-23 | IFA | OL1-2G42-5614 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package | B | 2018-10-09 | IFD | OL1-2G42-5614 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | A | 2018-08-23 | IFA | OL1-2G42-5615 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin | B | 2018-10-09 | IFD | OL1-2G42-5615 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | A | 2018-08-23 | IFA | OL1-2G42-5616 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package | B | 2018-10-09 | IFD | OL1-2G42-5616 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | A | 2018-08-23 | IFA | OL1-2G42-5617 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1056-PFD-0030-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge | B | 2018-10-09 | IFD | OL1-2G42-5617 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | A | 2018-08-23 | IFA | OL1-2G42-5901 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1059-PFD-0030-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage | B | 2018-10-09 | IFD | OL1-2G42-5901 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | A | 2018-08-23 | IFA | OL1-2G42-5911 | PE | 2018-08-23 | 036909C-JVD-TRN-00026 | 036909C-JVD-TRN-00026 | IFA | 2018-09-06 | 2018-10-29 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-PE-00026 |  | A
036909C-1059-PFD-0030-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage | B | 2018-10-09 | IFD | OL1-2G42-5911 | PE | 2018-10-10 | 036909C-JVD-TRN-00155 | 036909C-JVD-TRN-00155 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00155 |  | B
036909C-1000-PID-0090-0001 | P&ID - Olefins Unit 10 - Common - Abbreviations And Numbering | A | 2018-11-15 | IFR | OL1-2G43-0001 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0002 | P&ID - Olefins Unit 10 - Common - Piping Symbols | A | 2018-11-15 | IFR | OL1-2G43-0002 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0003 | P&ID - Olefins Unit 10 - Common - Instrumentation Symbols | A | 2018-11-15 | IFR | OL1-2G43-0003 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0004 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 1 | A | 2018-11-15 | IFR | OL1-2G43-0004 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0005 | P&ID - Olefins Unit 10 - Common - Equipment Symbols 2 | A | 2018-11-15 | IFR | OL1-2G43-0005 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0010 | P&ID - Olefins Unit 10 - Common - Instrument Details | A | 2018-11-15 | IFR | OL1-2G43-0010 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1000-PID-0090-0011 | P&ID - Olefins Unit 10 - Common - EIV Block Valves Typical | A | 2018-11-15 | IFR | OL1-2G43-0011 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1101 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1105 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1106 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1107 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1108 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1109 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed-Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1110 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1111 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1112 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section | A | 2018-11-15 | IFR | OL1-2G43-1115 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1116 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1117 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1118 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1119 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1120 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1121 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers | A | 2018-11-15 | IFR | OL1-2G43-1125 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent And Decoke MOVs | A | 2018-11-15 | IFR | OL1-2G43-1126 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header | A | 2018-11-15 | IFR | OL1-2G43-1127 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - SHP Steam Drum | A | 2018-11-15 | IFR | OL1-2G43-1128 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers | A | 2018-11-15 | IFR | OL1-2G43-1129 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply Export Steam | A | 2018-11-15 | IFR | OL1-2G43-1130 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils | A | 2018-11-15 | IFR | OL1-2G43-1131 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1135 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners | A | 2018-11-15 | IFR | OL1-2G43-1140 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent | A | 2018-11-15 | IFR | OL1-2G43-1145 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1011-PID-0021-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas | A | 2018-11-15 | IFR | OL1-2G43-1150 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1201 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1202 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1205 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header | A | 2018-11-15 | IFR | OL1-2G43-1206 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1207 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1208 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1209 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1210 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1211 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1212 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section | A | 2018-11-15 | IFR | OL1-2G43-1215 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 | A | 2018-11-15 | IFR | OL1-2G43-1216 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 | A | 2018-11-15 | IFR | OL1-2G43-1217 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 | A | 2018-11-15 | IFR | OL1-2G43-1218 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 | A | 2018-11-15 | IFR | OL1-2G43-1219 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 | A | 2018-11-15 | IFR | OL1-2G43-1220 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 | A | 2018-11-15 | IFR | OL1-2G43-1221 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger | A | 2018-11-15 | IFR | OL1-2G43-1225 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV's | A | 2018-11-15 | IFR | OL1-2G43-1226 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SLE Drain Header | A | 2018-11-15 | IFR | OL1-2G43-1227 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - VHP Steam Drum | A | 2018-11-15 | IFR | OL1-2G43-1228 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-SLE And TLX Risers | A | 2018-11-15 | IFR | OL1-2G43-1229 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply Export Steam | A | 2018-11-15 | IFR | OL1-2G43-1230 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils | A | 2018-11-15 | IFR | OL1-2G43-1231 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1235 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners | A | 2018-11-15 | IFR | OL1-2G43-1240 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas | A | 2018-11-15 | IFR | OL1-2G43-1245 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1012-PID-0021-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas | A | 2018-11-15 | IFR | OL1-2G43-1250 | PE | 2018-11-15 | 036909C-JVD-TRN-00323 | 036909C-JVD-TRN-00323 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-PE-00323 |  | A
036909C-1050-PID-0031-5010 | P&ID - Olefins Unit 10 - Water System Treated Potable Demin - Supporting Utilities Auxiliaries Treated Water | A | 2018-12-11 | IFR | OL1-2G43-5010 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5301 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 1 | A | 2018-12-11 | IFR | OL1-2G43-5301 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5302 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 2 | A | 2018-12-11 | IFR | OL1-2G43-5302 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5303 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Tower-Sheet 3 | A | 2018-12-11 | IFR | OL1-2G43-5303 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5305 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 1 | A | 2018-12-11 | IFR | OL1-2G43-5305 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5306 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 2 | A | 2018-12-11 | IFR | OL1-2G43-5306 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5307 | P&ID - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply Pumps | A | 2018-12-11 | IFR | OL1-2G43-5307 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5310 | P&ID - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply | A | 2018-12-11 | IFR | OL1-2G43-5310 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5311 | P&ID - Olefins Unit 10 - Cooling Water - Ctu Cooling Water Supply | A | 2018-12-11 | IFR | OL1-2G43-5311 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5315 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package | A | 2018-12-11 | IFR | OL1-2G43-5315 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5317 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Filter Backwash | A | 2018-12-11 | IFR | OL1-2G43-5317 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5320 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 01 | A | 2018-12-11 | IFR | OL1-2G43-5320 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5321 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 02 | A | 2018-12-11 | IFR | OL1-2G43-5321 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5322 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 03 | A | 2018-12-11 | IFR | OL1-2G43-5322 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5323 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 04 | A | 2018-12-11 | IFR | OL1-2G43-5323 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5324 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 05 | A | 2018-12-11 | IFR | OL1-2G43-5324 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5325 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 06 | A | 2018-12-11 | IFR | OL1-2G43-5325 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5326 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 07 | A | 2018-12-11 | IFR | OL1-2G43-5326 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5351 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5351 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1053-PID-0031-5352 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection | A | 2018-12-11 | IFR | OL1-2G43-5352 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1059-PID-0031-5903 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - CW Hypochlorite Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5903 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1059-PID-0031-5904 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Chemical Injection | A | 2018-12-11 | IFR | OL1-2G43-5904 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1059-PID-0031-5932 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - 98 percent Sulfuric Acid Pumps | A | 2018-12-11 | IFR | OL1-2G43-5932 | PE | 2018-12-12 | 036909C-JVD-TRN-00491 | 036909C-JVD-TRN-00491 | IFR | 2018-12-26 |  | Transmitted | TPSK-LSPA1-T-PE-00491 |  | A
036909C-1000-NM-0001-1001 | Overall Material Balance | A | 2018-08-03 | IFI | OL1-2G44-1001 | PE | 2018-08-06 | 036909C-JVD-TRN-00009 | 036909C-JVD-TRN-00009 | IFI |  | 2018-08-23 | R2-Comments as noted | TPSK-LSPA1-T-PE-00009 |  | A
036909C-1000-NM-0001-1002 | Heat & Material Balance - Design Case 6 | A | 2018-08-30 | IFI | OL1-2G44-1002 | PE | 2018-08-31 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | A
036909C-1000-NM-0001-1003 | Heat & Material Balance - Design Case 8 | A | 2018-08-30 | IFI | OL1-2G44-1003 | PE | 2018-08-31 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | A
036909C-1000-NM-0001-1004 | Heat & Material Balance - Design Case 9 | A | 2018-08-30 | IFI | OL1-2G44-1004 | PE | 2018-08-31 | 036909C-JVD-TRN-00032 | 036909C-JVD-TRN-00032 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00032 |  | A
036909C-1000-NM-0001-1010 | Heat and Material Balance - ISBL Supporting Utilities | A | 2018-10-03 | IFI | OL1-2G44-1010 | PE | 2018-10-03 | 036909C-JVD-TRN-00128 | 036909C-JVD-TRN-00128 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00128 |  | A
036909C-1000-NM-0001-1011 | Heat & Material Balance - Cooling Water System | A | 2018-09-28 | IFI | OL1-2G44-1011 | PE | 2018-10-01 | 036909C-JVD-TRN-00116 | 036909C-JVD-TRN-00116 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00116 |  | A
036909C-1000-NM-0003-1001 | Steam Balance | A | 2018-09-17 | IFI | OL1-2G62-1001 | PE | 2018-09-17 | 036909C-JVD-TRN-00059 | 036909C-JVD-TRN-00059 | IFI | 2018-10-01 | 2018-10-04 | Transmitted | TPSK-LSPA1-T-PE-00059 |  | A
036909C-1000-NM-0003-1006 | Cooling Water Balance | A | 2018-09-14 | IFI | OL1-2G62-1006 | PE | 2018-09-17 | 036909C-JVD-TRN-00054 | 036909C-JVD-TRN-00054 | IFI | 2018-10-08 | 2018-10-09 | R2-Comments as noted | TPSK-LSPA1-T-PE-00054 |  | A
036909C-1000-NM-0003-1008 | Fuel Balance | A | 2018-09-12 | IFI | OL1-2G62-1008 | PE | 2018-09-13 | 036909C-JVD-TRN-00049 | 036909C-JVD-TRN-00049 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PE-00049 |  | A
036909C-1000-MSD-0011-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes | A | 2018-11-02 | IFA | OL1-2G74-0001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1010-MSD-0011-1001 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat | A | 2018-11-02 | IFA | OL1-2G74-1001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1010-MSD-0011-1003 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution | A | 2018-11-02 | IFA | OL1-2G74-1003 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1011-MSD-0011-1101 | Material Selection Diagram - Olefins Unit 10 - 11 - Furnaces - Gas Cracking Furnace | A | 2018-11-02 | IFA | OL1-2G74-1101 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1012-MSD-0011-1201 | Material Selection Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces | A | 2018-11-02 | IFA | OL1-2G74-1201 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1019-MSD-0011-1901 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor | A | 2018-11-02 | IFA | OL1-2G74-1901 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1019-MSD-0011-1902 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage | A | 2018-11-02 | IFA | OL1-2G74-1902 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1020-MSD-0011-2001 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower | A | 2018-11-02 | IFA | OL1-2G74-2001 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1020-MSD-0011-2002 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper | A | 2018-11-02 | IFA | OL1-2G74-2002 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1021-MSD-0011-2101 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower | A | 2018-11-02 | IFA | OL1-2G74-2101 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1021-MSD-0011-2102 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit | A | 2018-11-02 | IFA | OL1-2G74-2102 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1021-MSD-0011-2103 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation | A | 2018-11-02 | IFA | OL1-2G74-2103 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1022-MSD-0011-2201 | Material Selection Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression | A | 2018-11-02 | IFA | OL1-2G74-2201 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2301 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower | A | 2018-11-02 | IFA | OL1-2G74-2301 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2302 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling | A | 2018-11-02 | IFA | OL1-2G74-2302 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2303 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage | A | 2018-11-02 | IFA | OL1-2G74-2303 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2304 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment | A | 2018-11-02 | IFA | OL1-2G74-2304 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1023-MSD-0011-2305 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation | A | 2018-11-02 | IFA | OL1-2G74-2305 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2401 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration | A | 2018-11-02 | IFA | OL1-2G74-2401 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2402 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration | A | 2018-11-02 | IFA | OL1-2G74-2402 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2403 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer | A | 2018-11-02 | IFA | OL1-2G74-2403 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2404 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation | A | 2018-11-02 | IFA | OL1-2G74-2404 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1024-MSD-0011-2405 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer | A | 2018-11-02 | IFA | OL1-2G74-2405 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2501 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator | A | 2018-11-02 | IFA | OL1-2G74-2501 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2502 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System | A | 2018-11-02 | IFA | OL1-2G74-2502 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2503 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer | A | 2018-11-02 | IFA | OL1-2G74-2503 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2504 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer | A | 2018-11-02 | IFA | OL1-2G74-2504 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2505 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation | A | 2018-11-02 | IFA | OL1-2G74-2505 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1025-MSD-0011-2506 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification | A | 2018-11-02 | IFA | OL1-2G74-2506 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1026-MSD-0011-2601 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation | A | 2018-11-02 | IFA | OL1-2G74-2601 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1026-MSD-0011-2602 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer | A | 2018-11-02 | IFA | OL1-2G74-2602 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1026-MSD-0011-2603 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation | A | 2018-11-02 | IFA | OL1-2G74-2603 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1026-MSD-0011-2604 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer | A | 2018-11-02 | IFA | OL1-2G74-2604 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1028-MSD-0011-2801 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 | A | 2018-11-02 | IFA | OL1-2G74-2801 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1028-MSD-0011-2802 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 | A | 2018-11-02 | IFA | OL1-2G74-2802 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1028-MSD-0011-2803 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 | A | 2018-11-02 | IFA | OL1-2G74-2803 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1028-MSD-0011-2804 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 | A | 2018-11-02 | IFA | OL1-2G74-2804 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1029-MSD-0011-2901 | Material Selection Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage | A | 2018-11-02 | IFA | OL1-2G74-2901 | ME | 2018-11-09 | 036909C-JVD-TRN-00295 | 036909C-JVD-TRN-00295 | IFA | 2018-11-23 | 2018-12-10 | A2-Approved with comments, re-submit is not required. | TPSK-LSPA1-T-ME-00295 |  | A
036909C-1053-MSD-0011-5301 | Material Selection Diagram - Olefins Unit 10 - 53 Cooling Water System Cooling Water Diagram | A | 2018-11-16 | IFA | OL1-2G74-5301 | ME | 2018-11-29 | 036909C-JVD-TRN-00399 | 036909C-JVD-TRN-00399 | IFA | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00399 |  | A
036909C-1053-MSD-0011-5311 | Material Selection Diagram - Olefins Unit 10 - 53-Cooling Water System Cooling Tower | A | 2018-11-16 | IFA | OL1-2G74-5311 | ME | 2018-11-29 | 036909C-JVD-TRN-00399 | 036909C-JVD-TRN-00399 | IFA | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00399 |  | A
036909C-1000-JSD-3400-0001 | Air Conditioning Ventilating And Ducting Design | A | 2018-10-12 | IFR | OL1-2H03-0001 | EE | 2018-10-12 | 036909C-JVD-TRN-00165 | 036909C-JVD-TRN-00165 | IFR | 2018-10-26 | 2018-10-26 | R2-Comments as noted | TPSK-LSPA1-T-EE-00165 |  | A
036909C-1000-STC-1790-0001 | Construction Standards for Reinforced Concrete Works | A | 2018-09-19 | IFR | OL1-2K20-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | A
036909C-1000-STC-1890-0001 | Construction Standards For Steel Structures | A | 2018-09-19 | IFR | OL1-2K21-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | A
036909C-1000-STC-1490-0001 | Standard Construction Drawings For Underground Systems | A | 2018-09-18 | IFR | OL1-2K23-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00088 | 036909C-JVD-TRN-00088 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00088 |  | A
036909C-1012-DW-0131-2546 | USC 132U Cracking Furnace Name Plate Details | 0 | 2018-12-04 | IFI | OL1-2K32-2546 | ME | 2018-12-04 | 036909C-JVD-TRN-00423 | 036909C-JVD-TRN-00423 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00423 |  | z0
036909C-1000-MS-1422-0001 | Technical Specification For Geotechnical Investigation | A | 2018-10-04 | IFR | OL1-2K43-0002 | CV | 2018-10-10 | 036909C-JVD-TRN-00147 | 036909C-JVD-TRN-00147 | IFR | 2018-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-00147 |  | A
036909C-1000-MS-1422-0001 | Technical Specification for Geotechnical Investigation | B | 2018-10-15 | IFR | OL1-2K43-0002 | CV | 2018-10-17 | 036909C-JVD-TRN-00188 | 036909C-JVD-TRN-00188 | IFR | 2018-11-05 | 2018-11-01 | R1-No comments | TPSK-LSPA1-T-CV-00188 |  | B
036909C-1000-PS-1422-0001 | Price List For Geotechnical Investigation | A | 2018-10-04 | IFR | OL1-2K43-0003 | CV | 2018-10-10 | 036909C-JVD-TRN-00147 | 036909C-JVD-TRN-00147 | IFR | 2018-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-00147 |  | A
036909C-1000-PS-1422-0001 | Price List for Geotechnical Investigation | B | 2018-10-15 | IFR | OL1-2K43-0003 | CV | 2018-10-17 | 036909C-JVD-TRN-00188 | 036909C-JVD-TRN-00188 | IFR | 2018-11-05 | 2018-11-01 | R1-No comments | TPSK-LSPA1-T-CV-00188 |  | B
036909C-1000-DW-1422-0001 | Soil Investigation Plan | A | 2018-10-04 | IFR | OL1-2K43-0004 | CV | 2018-10-10 | 036909C-JVD-TRN-00145 | 036909C-JVD-TRN-00145 | IFR | 2018-10-24 |  | Transmitted | TPSK-LSPA1-T-CV-00145 |  | A
036909C-1000-DW-1422-0001 | Soil Investigation Plan | B | 2018-10-10 | IFR | OL1-2K43-0004 | CV | 2018-10-12 | 036909C-JVD-TRN-00163 | 036909C-JVD-TRN-00163 | IFR | 2018-10-26 |  | Transmitted | TPSK-LSPA1-T-CV-00163 |  | B
036909C-1000-DW-1402-0001 | General Notes For Underground Works | A | 2018-09-18 | IFR | OL1-2K92-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | A
036909C-1000-DW-1702-0002 | General Notes For Precast Concrete Works | A | 2018-10-04 | IFR | OL1-2K92-0002 | CV | 2018-10-08 | 036909C-JVD-TRN-00137 | 036909C-JVD-TRN-00137 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-CV-00137 |  | A
036909C-1000-DW-1702-0001 | General Notes For Concrete Works | A | 2018-09-19 | IFR | OL1-2K92-0003 | CV | 2018-09-25 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | A
036909C-1000-DW-1802-0001 | General Notes For Steel Structures | A | 2018-09-19 | IFR | OL1-2K92-0004 | CV | 2018-09-25 | 036909C-JVD-TRN-00086 | 036909C-JVD-TRN-00086 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00086 |  | A
036909C-1000-JSD-6000-0001 | Noise Control | A | 2018-12-05 | IFR | OL1-2L10-0001 | SE | 2018-12-11 | 036909C-JVD-TRN-00472 | 036909C-JVD-TRN-00472, 036909C-JVD-TRN-00473 | IFR | 2018-12-27 |  | Transmitted | TPSK-LSPA1-T-SE-00472 |  | A
036909C-1010-SP-0810-1000 | Mechanical Equipment Data Sheet - LPG Drum | A | 2018-12-05 | IFQ | OL1-2M03-1000 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1011-SP-1040-1001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 36M | A | 2018-10-30 | IFR | OL1-2M03-1001 | ME | 2018-10-31 | 036909C-JVD-TRN-00247 | 036909C-JVD-TRN-00247 | IFR | 2018-11-13 |  | Transmitted | TPSK-LSPA1-T-ME-00247 |  | A
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet for Decoking Air Compressor Package | A | 2018-09-13 | IFA | OL1-2M03-1950 | ME | 2018-09-13 | 036909C-JVD-TRN-00050 | 036909C-JVD-TRN-00050 | IFA | 2018-09-27 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00050 |  | A
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet for Decoke Air Compressor Package | B | 2018-10-10 | IFQ | OL1-2M03-1950 | ME | 2018-10-11 | 036909C-JVD-TRN-00161 | 036909C-JVD-TRN-00161 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00161 |  | B
036909C-1019-SP-1013-1950 | Mechanical Equipment Datasheet - Decoking Air Compressor Package | C | 2018-10-31 | IFQ | OL1-2M03-1950 | ME | 2018-11-01 | 036909C-JVD-TRN-00261 | 036909C-JVD-TRN-00261 | IFI |  | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00261 |  | C
036909C-1020-SP-0510-2000 | Mechanical Equipment Data Sheet - Quench Oil Tower | A | 2018-12-04 | IFQ | OL1-2M03-2000 | ME | 2018-12-04 | 036909C-JVD-TRN-00420 | 036909C-JVD-TRN-00420 | IFR | 2018-12-18 |  | Transmitted | TPSL-LSPA1-T-ME-00420 |  | A
036909C-1012-SP-1040-2001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 132U | A | 2018-10-29 | IFR | OL1-2M03-2001 | ME | 2018-10-31 | 036909C-JVD-TRN-00247 | 036909C-JVD-TRN-00247 | IFR | 2018-11-13 |  | Transmitted | TPSK-LSPA1-T-ME-00247 |  | A
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet Quench Oil Pump 10-P-2006 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-2006 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235 |  | A
036909C-1020-SP-0910-2006 | Mechanical Equipment Data Sheet - Quench Oil Pump | B | 2018-11-28 | IFQ | OL1-2M03-2006 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | B
036909C-1020-SP-0510-2020 | Mechanical Equipment Data Sheet - Light Fuel Oil Stripper | A | 2018-12-07 | IFQ | OL1-2M03-2020 | ME | 2018-12-10 | 036909C-JVD-TRN-00447 | 036909C-JVD-TRN-00447 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00447 |  | A
036909C-1020-SP-0910-2024 | Mechanical Equipment Datasheet - Light Fuel Oil Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2024 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00457 |  | A
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | A | 2018-11-28 | IFQ | OL1-2M03-2040 | ME | 2018-11-28 | 036909C-JVD-TRN-00387 | 036909C-JVD-TRN-00387 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-ME-00387 |  | A
036909C-1020-SP-0510-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper | B | 2018-12-04 | IFQ | OL1-2M03-2040 | ME | 2018-12-05 | 036909C-JVD-TRN-00418 | 036909C-JVD-TRN-00418 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00418 |  | B
036909C-1020-SP-0910-2046 | Mechanical Equipment Datasheet - Heavy Fuel Oil Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2046 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00457 |  | A
036909C-1021-SP-0510-2100 | Mechanical Equipment Data Sheet - Quench Water Tower | A | 2018-12-06 | IFQ | OL1-2M03-2100 | ME | 2018-12-07 | 036909C-JVD-TRN-00443 | 036909C-JVD-TRN-00443 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-ME-00443 |  | A
036909C-1021-TDS-0661-2101 | Mechanical Data Sheet - 10-E-2100 - Quench Water Cooler | A | 2018-09-14 | IFA | OL1-2M03-2101 | ME | 2018-09-17 | 036909C-JVD-TRN-00058 | 036909C-JVD-TRN-00058 | IFA | 2018-10-01 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00058 |  | A
036909C-1021-TDS-0661-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler | B | 2018-10-09 | IFQ | OL1-2M03-2101 | ME | 2018-10-10 | 036909C-JVD-TRN-00154 | 036909C-JVD-TRN-00154 | IFI |  | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00154 |  | B
036909C-1021-SP-0910-2105 | Mechanical Equipment Datasheet - Quench Oil Reflux Pumps | A | 2018-11-23 | IFQ | OL1-2M03-2105 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00457 |  | A
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps - 10-P-2106 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-2106 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236 |  | A
036909C-1021-SP-0910-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps | B | 2018-11-28 | IFQ | OL1-2M03-2106 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | B
036909C-1021-SP-0910-2126 | Mechanical Equipment Datasheet - Distillate Stripper Bottom Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2126 | ME | 2018-12-05 | 036909C-JVD-TRN-00410 | 036909C-JVD-TRN-00410 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00410 |  | A
036909C-1021-SP-0510-2140 | Mechanical Equipment Data Sheet - Process Water Stripper | A | 2018-12-05 | IFQ | OL1-2M03-2140 | ME | 2018-12-10 | 036909C-JVD-TRN-00458 | 036909C-JVD-TRN-00458 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00458 |  | A
036909C-1021-SP-0910-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps 10-P-2146 A-B | A | 2018-10-25 | IFQ | OL1-2M03-2146 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235 |  | A
036909C-1021-SP-0910-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps | B | 2018-11-28 | IFQ | OL1-2M03-2146 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | B
036909C-1021-SP-0810-2160 | Mechanical Equipment Data Sheet - Dilution Steam Generator | A | 2018-12-05 | IFQ | OL1-2M03-2160 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1021-SP-0910-2191 | Mechanical Equipment Datasheet - Quench Water Drain Drum Pump | A | 2018-11-28 | IFQ | OL1-2M03-2191 | ME | 2018-11-29 | 036909C-JVD-TRN-00400 | 036909C-JVD-TRN-00400 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00400 |  | A
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | A | 2018-09-06 | IFA | OL1-2M03-2200 | ME | 2018-09-10 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | A
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2200 | ME | 2018-10-03 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00127 |  | B
036909C-1022-SP-1011-2200 | Mechanical Equipment Data Sheet for Cracked Gas Compressor | C | 2018-10-31 | IFQ | OL1-2M03-2200 | ME | 2018-11-06 | 036909C-JVD-TRN-00280 | 036909C-JVD-TRN-00280 | IFI |  | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-ME-00280 |  | C
036909C-1022-SP-0910-2212 | Mechanical Equipment Datasheet - CG 1st Stage Condensate Pumps | A | 2018-12-04 | IFQ | OL1-2M03-2212 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00413 |  | A
036909C-1022-SP-0810-2220 | Mechanical Equipment Data Sheet - CG 2nd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2220 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1022-SP-0910-2222 | Mechanical Equipment Datasheet - CG 2nd Stage Condensed HC Pump | A | 2018-11-16 | IFQ | OL1-2M03-2222 | ME | 2018-11-20 | 036909C-JVD-TRN-00343 | 036909C-JVD-TRN-00343 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-ME-00343 |  | A
036909C-1022-SP-0810-2230 | Mechanical Equipment Data Sheet - CG 3rd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2230 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1022-SP-0810-2240 | Mechanical Equipment Data Sheet - CG 4th Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2240 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet Caustic Tower 10-T-2300 | A | 2018-10-26 | IFQ | OL1-2M03-2300 | ME | 2018-10-31 | 036909C-JVD-TRN-00246 | 036909C-JVD-TRN-00246 | IFR | 2018-11-13 | 2018-11-27 | R2-Comments as noted | TPSK-LSPA1-T-ME-00246 |  | A
036909C-1023-SP-0510-2300 | Mechanical Equipment Data Sheet - Caustic Tower | B | 2018-12-04 | IFQ | OL1-2M03-2300 | ME | 2018-12-05 | 036909C-JVD-TRN-00419 | 036909C-JVD-TRN-00419 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00419 |  | B
036909C-1023-SP-0910-2302 | Mechanical Equipment Datasheet - Strong Caustic Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2302 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | A
036909C-1023-SP-0910-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump | A | 2018-11-13 | IFQ | OL1-2M03-2304 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | A
036909C-1023-SP-0910-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump | B | 2018-12-03 | IFQ | OL1-2M03-2304 | ME | 2018-12-05 | 036909C-JVD-TRN-00411 | 036909C-JVD-TRN-00411 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00411 |  | B
036909C-1023-SP-0910-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2306 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | A
036909C-1023-SP-0910-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps | B | 2018-12-03 | IFQ | OL1-2M03-2306 | ME | 2018-12-05 | 036909C-JVD-TRN-00411 | 036909C-JVD-TRN-00411 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00411 |  | B
036909C-1023-SP-0810-2309 | Mechanical Equipment Data Sheet - Yellow Oil Drum | A | 2018-12-10 | IFQ | OL1-2M03-2309 | ME | 2018-12-12 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00484 |  | A
036909C-1023-SP-0910-2311 | Mechanical Equipment Datasheet - Wash Oil Circulating Pumps | A | 2018-11-13 | IFQ | OL1-2M03-2311 | ME | 2018-11-15 | 036909C-JVD-TRN-00320 | 036909C-JVD-TRN-00320 | IFR | 2018-11-29 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00320 |  | A
036909C-1023-SP-0910-2321 | Mechanical Equipment Datasheet - Spent Caustic Pumps | A | 2018-11-16 | IFQ | OL1-2M03-2321 | ME | 2018-11-19 | 036909C-JVD-TRN-00335 | 036909C-JVD-TRN-00335 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-ME-00335 |  | A
036909C-1023-SP-0810-2322 | Mechanical Equipment Data Sheet - Skim Oil Drum | A | 2018-12-10 | IFQ | OL1-2M03-2322 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1023-SP-0510-2330 | Mechanical Equipment Data Sheet - Spent Caustic Stripper | A | 2018-12-06 | IFQ | OL1-2M03-2330 | ME | 2018-12-10 | 036909C-JVD-TRN-00462 | 036909C-JVD-TRN-00462 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00462 |  | A
036909C-1023-SP-4100-0002 | Mechanical Equipment Datasheet for Wet Air Oxidation Package | A | 2018-11-27 | IFQ | OL1-2M03-2350 | ME | 2018-11-29 | 036909C-JVD-TRN-00390 | 036909C-JVD-TRN-00390 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00390 |  | A
036909C-1023-SP-0910-2393 | Mechanical Equipment Datasheet - Spent Caustic Drain Drum Pump | A | 2018-12-05 | IFQ | OL1-2M03-2393 | ME | 2018-12-10 | 036909C-JVD-TRN-00457 | 036909C-JVD-TRN-00457 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00457 |  | A
036909C-1024-SP-0910-2416 | Mechanical Equipment Datasheet - CG Liquid Dryer Feed Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2416 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00413 |  | A
036909C-1024-SP-0810-2438 | Mechanical Equipment Data Sheet - HP Depropanizer Reflux Drum | A | 2018-12-04 | IFQ | OL1-2M03-2438 | ME | 2018-12-12 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00484 |  | A
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet for HP Depropanizer | A | 2018-10-23 | IFQ | OL1-2M03-2440 | ME | 2018-10-23 | 036909C-JVD-TRN-00215 | 036909C-JVD-TRN-00215 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-ME-00215 |  | A
036909C-1024-SP-0510-2440 | Mechanical Equipment Datasheet - HP Depropanizer | B | 2018-11-28 | IFQ | OL1-2M03-2440 | ME | 2018-12-05 | 036909C-JVD-TRN-00416 | 036909C-JVD-TRN-00416 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00416 |  | B
036909C-1024-SP-0510-2450 | Mechanical Equipment Datasheet LP Depropanizer | A | 2018-10-15 | IFQ | OL1-2M03-2450 | ME | 2018-10-16 | 036909C-JVD-TRN-00183 | 036909C-JVD-TRN-00183 | IFR | 2018-10-30 | 2018-11-05 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00183 |  | A
036909C-1024-SP-0510-2450 | Mechanical Equipment Datasheet - LP Depropanizer | B | 2018-11-06 | IFQ | OL1-2M03-2450 | ME | 2018-11-06 | 036909C-JVD-TRN-00283 | 036909C-JVD-TRN-00283 | IFI |  | 2018-11-30 | R1-No comments | TPSK-LSPA1-T-ME-00283 |  | B
036909C-1024-SP-0510-2450 | Mechanical Equipment Data Sheet - LP Depropanizer | C | 2018-11-30 | IFQ | OL1-2M03-2450 | ME | 2018-12-05 | 036909C-JVD-TRN-00412 | 036909C-JVD-TRN-00412 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00412 |  | C
036909C-1024-SP-0910-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux-Product Pump | A | 2018-11-08 | IFQ | OL1-2M03-2453 | ME | 2018-11-08 | 036909C-JVD-TRN-00294 | 036909C-JVD-TRN-00294 | IFR | 2018-11-22 |  | Transmitted | TPSK-LSPA1-T-ME-00294 |  | A
036909C-1025-TDS-0610-2502 | Mechanical Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 | A | 2018-12-06 | IFQ | OL1-2M03-2502 | ME | 2018-12-10 | 036909C-JVD-TRN-00461 | 036909C-JVD-TRN-00461 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00461 |  | A
036909C-1025-TDS-0610-2503 | Mechanical Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 | A | 2018-11-28 | IFQ | OL1-2M03-2503 | ME | 2018-11-28 | 036909C-JVD-TRN-00389 | 036909C-JVD-TRN-00389 | IFR | 2018-12-12 |  | Transmitted | TPSK-LSPA1-T-ME-00389 |  | A
036909C-1025-SP-0810-2504 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 1 | A | 2018-12-06 | IFQ | OL1-2M03-2504 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator and Reflux Drum | A | 2018-10-29 | IFQ | OL1-2M03-2510 | ME | 2018-10-31 | 036909C-JVD-TRN-00260 | 036909C-JVD-TRN-00260 | IFR | 2018-11-14 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00260 |  | A
036909C-1025-SP-0510-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator & Reflux Drum | B | 2018-11-30 | IFQ | OL1-2M03-2510 | ME | 2018-12-05 | 036909C-JVD-TRN-00414 | 036909C-JVD-TRN-00414 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00414 |  | B
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum | A | 2018-11-09 | IFQ | OL1-2M03-2540 | ME | 2018-11-09 | 036909C-JVD-TRN-00304 | 036909C-JVD-TRN-00304 | IFR | 2018-11-23 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00304 |  | A
036909C-1025-SP-0510-2540 | Mechanical Equipment Data Sheet - Demethanizer and Demethanizer Reflux Drum | B | 2018-11-30 | IFQ | OL1-2M03-2540 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00415 |  | B
036909C-1025-SP-1011-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | A | 2018-09-13 | IFA | OL1-2M03-2550 | ME | 2018-09-13 | 036909C-JVD-TRN-00050 | 036909C-JVD-TRN-00050 | IFA | 2018-09-27 | 2018-10-02 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00050 |  | A
036909C-1025-SP-1011-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor | B | 2018-10-04 | IFQ | OL1-2M03-2550 | ME | 2018-10-05 | 036909C-JVD-TRN-00130 | 036909C-JVD-TRN-00130 | IFI |  | 2018-10-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00130 |  | B
036909C-1025-SP-0510-2570 | Mechanical Equipment Data Sheet - Deethanizer | A | 2018-11-28 | IFQ | OL1-2M03-2570 | ME | 2018-11-29 | 036909C-JVD-TRN-00394 | 036909C-JVD-TRN-00394 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00394 |  | A
036909C-1025-TDS-0610-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser | A | 2018-11-12 | IFQ | OL1-2M03-2571 | ME | 2018-11-13 | 036909C-JVD-TRN-00310 | 036909C-JVD-TRN-00310 | IFR | 2018-11-27 | 2018-12-10 | R2-Comments as noted | TPSK-LSPA1-T-ME-00310 |  | A
036909C-1025-SP-0810-2572 | Mechanical Equipment Data Sheet - Deethanizer Reflux Drum | A | 2018-12-10 | IFQ | OL1-2M03-2572 | ME | 2018-12-12 | 036909C-JVD-TRN-00484 | 036909C-JVD-TRN-00484 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00484 |  | A
036909C-1025-SP-0910-2586 | Mechanical Equipment Datasheet - Ethane Recycle Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2586 | ME | 2018-12-05 | 036909C-JVD-TRN-00413 | 036909C-JVD-TRN-00413 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00413 |  | A
036909C-1026-SP-0510-2630 | Mechanical Equipment Data Sheet - Secondary Deethanizer | A | 2018-12-05 | IFQ | OL1-2M03-2630 | ME | 2018-12-10 | 036909C-JVD-TRN-00458 | 036909C-JVD-TRN-00458 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00458 |  | A
036909C-1026-TDS-0610-2631 | Mechanical Equipment Data Sheet - 10-E-2630 - Secondary Deeth Condenser | A | 2018-12-06 | IFQ | OL1-2M03-2631 | ME | 2018-12-10 | 036909C-JVD-TRN-00455 | 036909C-JVD-TRN-00455 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00455 |  | A
036909C-1026-SP-0910-2633 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Pumps | A | 2018-11-19 | IFQ | OL1-2M03-2633 | ME | 2018-12-12 | 036909C-JVD-TRN-00487 | 036909C-JVD-TRN-00487 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00487 |  | A
036909C-1026-TDS-0610-2636 | Mechanical Equipment Data Sheet - 10-E-2636 - Secondary Deeth Bottoms Cooler | A | 2018-12-07 | IFQ | OL1-2M03-2636 | ME | 2018-12-10 | 036909C-JVD-TRN-00465 | 036909C-JVD-TRN-00465 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00465 |  | A
036909C-1026-SP-0510-2640 | Mechanical Equipment Data Sheet - C3 Tower | A | 2018-11-30 | IFQ | OL1-2M03-2640 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00415 |  | A
036909C-1026-TDS-0610-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers | A | 2018-11-19 | IFQ | OL1-2M03-2645 | ME | 2018-11-26 | 036909C-JVD-TRN-00361 | 036909C-JVD-TRN-00361 | IFR | 2018-12-10 |  | Transmitted | TPSK-LSPA1-T-ME-00361 |  | A
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet for Debutanizer | A | 2018-10-23 | IFQ | OL1-2M03-2660 | ME | 2018-10-23 | 036909C-JVD-TRN-00215 | 036909C-JVD-TRN-00215 | IFR | 2018-11-06 |  | Transmitted | TPSK-LSPA1-T-ME-00215 |  | A
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | B | 2018-11-07 | IFQ | OL1-2M03-2660 | ME | 2018-11-08 | 036909C-JVD-TRN-00288 | 036909C-JVD-TRN-00288 | IFR | 2018-11-22 |  | Transmitted | TPSK-LSPA1-T-ME-00288 |  | B
036909C-1026-SP-0510-2660 | Mechanical Equipment Datasheet - Debutanizer | C | 2018-11-30 | IFQ | OL1-2M03-2660 | ME | 2018-12-05 | 036909C-JVD-TRN-00415 | 036909C-JVD-TRN-00415 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00415 |  | C
036909C-1026-TDS-0610-2661 | Mechanical Equipment Data Sheet - 10-E-2660 - Debutanizer Condenser | A | 2018-12-07 | IFQ | OL1-2M03-2661 | ME | 2018-12-10 | 036909C-JVD-TRN-00465 | 036909C-JVD-TRN-00465 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00465 |  | A
036909C-1026-TDS-0610-2665 | Mechanical Equipment Data Sheet - 10-E-2665 AB - Debutanizer Reboilers | A | 2018-12-07 | IFQ | OL1-2M03-2665 | ME | 2018-12-10 | 036909C-JVD-TRN-00468 | 036909C-JVD-TRN-00468 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00468 |  | A
036909C-1026-TDS-0610-2666 | Mechanical Equipment Data Sheet - 10-E-2666 - Debutanizer Bottoms Cooler | A | 2018-12-07 | IFQ | OL1-2M03-2666 | ME | 2018-12-10 | 036909C-JVD-TRN-00468 | 036909C-JVD-TRN-00468 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00468 |  | A
036909C-1026-SP-0910-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps | A | 2018-12-03 | IFQ | OL1-2M03-2669 | ME | 2018-12-04 | 036909C-JVD-TRN-00421 | 036909C-JVD-TRN-00421 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-ME-00421 |  | A
036909C-1028-SP-1011-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | A | 2018-09-06 | IFA | OL1-2M03-2800 | ME | 2018-09-10 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | A
036909C-1028-SP-1011-2800 | Mechanical Equipment Data Sheet for Propylene Refrigeration Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2800 | ME | 2018-10-03 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00127 |  | B
036909C-1028-SP-0810-2805 | Mechanical Equipment Data Sheet - C3R Surge Drum | A | 2018-12-05 | IFQ | OL1-2M03-2805 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1028-SP-0810-2810 | Mechanical Equipment Data Sheet - C3R 1st Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2810 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1028-SP-0810-2820 | Mechanical Equipment Data Sheet - C3R 2nd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2820 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1028-SP-0810-2830 | Mechanical Equipment Data Sheet - C3R 3rd Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2830 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1028-SP-0810-2840 | Mechanical Equipment Data Sheet - C3R 4TH Stage Suction Drum | A | 2018-12-05 | IFQ | OL1-2M03-2840 | ME | 2018-12-10 | 036909C-JVD-TRN-00460 | 036909C-JVD-TRN-00460 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00460 |  | A
036909C-1028-SP-1011-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | A | 2018-09-06 | IFA | OL1-2M03-2850 | ME | 2018-09-10 | 036909C-JVD-TRN-00038 | 036909C-JVD-TRN-00038 | IFA | 2018-09-24 | 2018-09-28 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00038 |  | A
036909C-1028-SP-1011-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor | B | 2018-10-02 | IFQ | OL1-2M03-2850 | ME | 2018-10-03 | 036909C-JVD-TRN-00127 | 036909C-JVD-TRN-00127 | IFI |  | 2018-10-26 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00127 |  | B
036909C-1028-TDS-0610-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser | A | 2018-11-14 | IFQ | OL1-2M03-2856 | ME | 2018-11-14 | 036909C-JVD-TRN-00316 | 036909C-JVD-TRN-00316 | IFR | 2018-11-28 |  | Transmitted | TPSK-LSPA1-T-ME-00316 |  | A
036909C-1028-TDS-0610-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer | A | 2018-11-13 | IFQ | OL1-2M03-2857 | ME | 2018-11-13 | 036909C-JVD-TRN-00312 | 036909C-JVD-TRN-00312 | IFR | 2018-11-27 |  | Transmitted | TPSK-LSPA1-T-ME-00312 |  | A
036909C-1028-SP-0810-2880 | Mechanical Equipment Data Sheet - C2R 3RD Stage Suction Drum | A | 2018-12-04 | IFQ | OL1-2M03-2880 | ME | 2018-12-10 | 036909C-JVD-TRN-00460 | 036909C-JVD-TRN-00460 | IFR | 2018-12-21 |  | Transmitted | TPSK-LSPA1-T-ME-00460 |  | A
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet SHP BFW Pumps - 10-P-5100 A-B-C | A | 2018-10-25 | IFQ | OL1-2M03-5101 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236 |  | A
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet for SHP BFW Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5101 | ME | 2018-11-15 | 036909C-JVD-TRN-00322 | 036909C-JVD-TRN-00322 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00322 |  | B
036909C-1051-SP-0910-5101 | Mechanical Equipment Data Sheet - SHP BFW Pumps | C | 2018-11-28 | IFQ | OL1-2M03-5101 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | C
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet VLP BFW Pumps - 10-P-5102 A-B | A | 2018-10-25 | IFQ | OL1-2M03-5102 | ME | 2018-10-27 | 036909C-JVD-TRN-00236 | 036909C-JVD-TRN-00236 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00236 |  | A
036909C-1051-SP-0910-5102 | Mechanical Equipment Data Sheet - VLP BFW Pumps | B | 2018-11-28 | IFQ | OL1-2M03-5102 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | B
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps 10-P-5110 A-B | A | 2018-10-25 | IFQ | OL1-2M03-5109 | ME | 2018-10-26 | 036909C-JVD-TRN-00235 | 036909C-JVD-TRN-00235 | IFR | 2018-11-09 | 2018-11-19 | R2-Comments as noted | TPSK-LSPA1-T-ME-00235 |  | A
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5109 | ME | 2018-11-14 | 036909C-JVD-TRN-00317 | 036909C-JVD-TRN-00317 | IFR | 2018-11-28 |  | Transmitted | TPSK-LSPA1-T-ME-00317 |  | B
036909C-1051-SP-0910-5109 | Mechanical Equipment Data Sheet - Condensate Pumps | C | 2018-11-28 | IFQ | OL1-2M03-5109 | ME | 2018-12-11 | 036909C-JVD-TRN-00476 | 036909C-JVD-TRN-00476 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00476 |  | C
036909C-1051-SP-0910-5111 | Mechanical Equipment Datasheet - Suspect Condensate Pumps | A | 2018-11-20 | IFQ | OL1-2M03-5111 | ME | 2018-11-20 | 036909C-JVD-TRN-00341 | 036909C-JVD-TRN-00341 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-ME-00341 |  | A
036909C-1051-SP-0910-5121 | Mechanical Equipment Datasheet - Raw Condensate Pumps | A | 2018-11-20 | IFQ | OL1-2M03-5121 | ME | 2018-11-20 | 036909C-JVD-TRN-00341 | 036909C-JVD-TRN-00341 | IFR | 2018-12-04 |  | Transmitted | TPSK-LSPA1-T-ME-00341 |  | A
036909C-1051-SP-0910-5141 | Mechanical Equipment Datasheet - Intermittent Blowdown Pumps | A | 2018-11-16 | IFQ | OL1-2M03-5141 | ME | 2018-11-19 | 036909C-JVD-TRN-00335 | 036909C-JVD-TRN-00335 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-ME-00335 |  | A
036909C-1053-SP-0310-0002 | Mechanical Equipment Datasheet for Cooling Tower | B | 2018-10-30 | IFQ | OL1-2M03-5350 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 |  | Transmitted | TPSK-LSPA1-T-ME-00276 |  | B
036909C-1053-SP-0910-5352 | Mechanical Equipment Data Sheet for Olefins Cooling Water Pumps 10-P-5350 A-H | A | 2018-10-22 | IFQ | OL1-2M03-5352 | ME | 2018-10-23 | 036909C-JVD-TRN-00210 | 036909C-JVD-TRN-00210 | IFR | 2018-11-06 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00210 |  | A
036909C-1053-SP-0910-5352 | Mechanical Equipment DataSheet - Olefins Cooling Water Pumps | B | 2018-11-26 | IFQ | OL1-2M03-5352 | ME | 2018-11-28 | 036909C-JVD-TRN-00388 | 036909C-JVD-TRN-00388 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00388 |  | B
036909C-1053-SP-4234-0002 | Mechanical Equipment Datasheet for Side Stream Filter Package | B | 2018-10-29 | IFQ | OL1-2M03-5355 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248 |  | B
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet for CTU Cooling Water Pumps 10-P-5360 A-B-C | A | 2018-10-22 | IFQ | OL1-2M03-5361 | ME | 2018-10-23 | 036909C-JVD-TRN-00210 | 036909C-JVD-TRN-00210 | IFR | 2018-11-06 | 2018-11-14 | R2-Comments as noted | TPSK-LSPA1-T-ME-00210 |  | A
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps | B | 2018-11-12 | IFQ | OL1-2M03-5361 | ME | 2018-11-14 | 036909C-JVD-TRN-00317 | 036909C-JVD-TRN-00317 | IFR | 2018-11-28 |  | Transmitted | TPSK-LSPA1-T-ME-00317 |  | B
036909C-1053-SP-0910-5361 | Mechanical Equipment Data Sheet - CTU Cooling Water Pumps | C | 2018-11-26 | IFQ | OL1-2M03-5361 | ME | 2018-11-28 | 036909C-JVD-TRN-00388 | 036909C-JVD-TRN-00388 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00388 |  | C
036909C-1055-SP-0810-5500 | Mechanical Equipment Data Sheet - Hot Flare Drum | A | 2018-12-07 | IFQ | OL1-2M03-5500 | ME | 2018-12-12 | 036909C-JVD-TRN-00483 | 036909C-JVD-TRN-00483 | IFR | 2018-12-25 |  | Transmitted | TPSK-LSPA1-T-ME-00483 |  | A
036909C-1011-DW-0117-1001 | USC 36M Recycle Furnace General Arrangement Cross Section Elevation | A | 2018-11-15 | IFR | OL1-2M06-1001 | ME | 2018-11-16 | 036909C-JVD-TRN-00327 | 036909C-JVD-TRN-00327 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00327 |  | A
036909C-1011-DW-0117-1002 | USC 36M Recycle Furnace General Arrangement Longitudinal Elevation | A | 2018-11-15 | IFR | OL1-2M06-1002 | ME | 2018-11-16 | 036909C-JVD-TRN-00327 | 036909C-JVD-TRN-00327 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00327 |  | A
036909C-1011-DW-0122-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details | A | 2018-09-11 | IFR | OL1-2M06-1201 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1011-DW-0122-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details | 0 | 2018-12-10 | IMP | OL1-2M06-1201 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1011-DW-0122-1202 | USC 36M Recycle Furnace Transfer Line and Clean-Out Details | A | 2018-09-11 | IFR | OL1-2M06-1202 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1011-DW-0122-1202 | USC 36M Recycle Furnace Transfer Line And Clean Out Details | 0 | 2018-12-11 | IMP | OL1-2M06-1202 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1011-DW-0122-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details | A | 2018-09-11 | IFR | OL1-2M06-1203 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1011-DW-0122-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details | 0 | 2018-12-11 | IMP | OL1-2M06-1203 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1011-DW-0127-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill Of Material | A | 2018-10-12 | IFR | OL1-2M06-1204 | ME | 2018-10-16 | 036909C-JVD-TRN-00182 | 036909C-JVD-TRN-00182 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-00182 |  | A
036909C-1011-DW-0125-1301 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-1301 | ME | 2018-11-07 | 036909C-JVD-TRN-00286 | 036909C-JVD-TRN-00286 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00286 |  | z0
036909C-1011-DW-0125-1302 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-1302 | ME | 2018-11-07 | 036909C-JVD-TRN-00286 | 036909C-JVD-TRN-00286 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00286 |  | z0
036909C-1012-DW-0117-2001 | USC 132U Cracking Furnace General Arrangement Cross Section Elevation | A | 2018-11-15 | IFR | OL1-2M06-2001 | ME | 2018-11-16 | 036909C-JVD-TRN-00328 | 036909C-JVD-TRN-00328 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00328 |  | A
036909C-1012-DW-0117-2002 | USC 132U Cracking Furnace General Arrangement Longitudinal Elevation | A | 2018-11-15 | IFR | OL1-2M06-2002 | ME | 2018-11-16 | 036909C-JVD-TRN-00328 | 036909C-JVD-TRN-00328 | IFR | 2018-11-30 |  | Transmitted | TPSK-LSPA1-T-ME-00328 |  | A
036909C-1012-DW-0122-2201 | USC 132U Furnace Radiant Coil Assembly and Details | A | 2018-09-11 | IFR | OL1-2M06-2201 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1012-DW-0122-2201 | USC 132U Cracking Furnace Radiant Coil Assembly and Details | 0 | 2018-12-11 | IMP | OL1-2M06-2201 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1012-DW-0122-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details | A | 2018-09-11 | IFR | OL1-2M06-2202 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1012-DW-0122-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details | 0 | 2018-12-11 | IMP | OL1-2M06-2202 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1012-DW-0122-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | A | 2018-09-11 | IFR | OL1-2M06-2203 | ME | 2018-10-08 | 036909C-JVD-TRN-00062 | 036909C-JVD-TRN-00062 | IFR | 2018-10-22 |  | Transmitted | TPSK-LSPA1-T-ME-00062 |  | A
036909C-1012-DW-0122-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details | 0 | 2018-12-11 | IMP | OL1-2M06-2203 | ME | 2018-12-12 | 036909C-JVD-TRN-00486 | 036909C-JVD-TRN-00486 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00486 |  | z0
036909C-1012-DW-0127-2204 | USC 132U Cracking Furnace Fabricatin Assembly of Convection Coils Finned Tubes and Bill of Material | A | 2018-10-12 | IFR | OL1-2M06-2204 | ME | 2018-10-16 | 036909C-JVD-TRN-00182 | 036909C-JVD-TRN-00182 | IFR | 2018-10-30 |  | Transmitted | TPSK-LSPA1-T-ME-00182 |  | A
036909C-1012-DW-0125-2301 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-2301 | ME | 2018-11-08 | 036909C-JVD-TRN-00289 | 036909C-JVD-TRN-00289 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00289 |  | z0
036909C-1012-DW-0125-2302 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details | 0 | 2018-11-06 | IFI | OL1-2M06-2302 | ME | 2018-11-08 | 036909C-JVD-TRN-00289 | 036909C-JVD-TRN-00289 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00289 |  | z0
036909C-1012-DW-0130-2554 | USC 132U Cracking Furnace Peep Door Details | 0 | 2018-12-04 | IFI | OL1-2M06-2554 | ME | 2018-12-04 | 036909C-JVD-TRN-00422 | 036909C-JVD-TRN-00422 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00422 |  | z0
036909C-1000-MR-0910-0003 | Material Requisition for Cooling Water Pumps | A | 2018-11-14 | IFQ | OL1-2M55-0003 | ME | 2018-11-15 | 036909C-JVD-TRN-00319 | 036909C-JVD-TRN-00319 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00319 |  | A
036909C-1000-MR-1011-0001 | Material Requisition For Centrifugal Compressors Steam Turbine Driven | A | 2018-10-04 | IFQ | OL1-2M55-0008 | ME | 2018-10-08 | 036909C-JVD-TRN-00136 | 036909C-JVD-TRN-00136 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00136 |  | A
036909C-1000-MR-1130-0001 | Material Requisition For Residue Gas Expander/Recompressor | A | 2018-10-05 | IFQ | OL1-2M55-0012 | ME | 2018-10-09 | 036909C-JVD-TRN-00139 | 036909C-JVD-TRN-00139 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00139 |  | A
036909C-1000-MR-1013-0001 | Material Requisition For Integrally Geared Decoking Air Compressors | A | 2018-10-18 | IFQ | OL1-2M55-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00198 | 036909C-JVD-TRN-00198 | IFR | 2018-11-02 | 2018-11-07 | Transmitted | TPSK-LSPA1-T-ME-00198 |  | A
036909C-1000-MR-0910-0001 | Material Requisition For API Centrifugal Pumps - LLI | A | 2018-10-30 | IFQ | OL1-2M55-0015 | ME | 2018-10-31 | 036909C-JVD-TRN-00257 | 036909C-JVD-TRN-00257 | IFR | 2018-11-20 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00257 |  | A
036909C-1000-MR-0570-0001 | Material Requisition For Trays For Columns Requisition For Inquiry | A | 2018-11-06 | IFQ | OL1-2M55-0055 | ME | 2018-11-09 | 036909C-JVD-TRN-00300 | 036909C-JVD-TRN-00300 | IFR | 2018-11-26 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00300 |  | A
036909C-1000-MR-0610-0001 | Material Requisition For Wieland Tubes (Solo Source) Requisition For Inquiry | A | 2018-11-27 | IFQ | OL1-2M55-0058 | ME | 2018-11-28 | 036909C-JVD-TRN-00377 | 036909C-JVD-TRN-00377 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00377 |  | A
036909C-1000-MR-0661-0001 | Material Requisition For Plate And Frame Heat Exchangers Requisition For Inquiry | A | 2018-10-01 | IFQ | OL1-2M55-0064 | ME | 2018-10-03 | 036909C-JVD-TRN-00124 | 036909C-JVD-TRN-00124 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00124 |  | A
036909C-1000-MR-0662-0002 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry | A | 2018-10-01 | IFQ | OL1-2M55-0066 | ME | 2018-10-03 | 036909C-JVD-TRN-00125 | 036909C-JVD-TRN-00125 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00125 |  | A
036909C-1000-MR-0662-0002 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry | B | 2018-10-09 | IFQ | OL1-2M55-0066 | ME | 2018-10-10 | 036909C-JVD-TRN-00153 | 036909C-JVD-TRN-00153 | IFR | 2018-10-24 | 2018-11-02 | Transmitted | TPSK-LSPA1-T-ME-00153 |  | B
036909C-1000-MR-0570-0004 | Material Requisition For MD Trays For Columns Requisition For Inquiry | A | 2018-10-31 | IFQ | OL1-2M55-0075 | ME | 2018-11-07 | 036909C-JVD-TRN-00278 | 036909C-JVD-TRN-00278 | IFR | 2018-11-21 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00278 |  | A
036909C-1000-MR-0570-0004 | Material Requisition for High Efficiency Internals for Columns | B | 2018-11-12 | IMP | OL1-2M55-0075 | ME | 2018-11-14 | 036909C-JVD-TRN-00314 | 036909C-JVD-TRN-00314 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-ME-00314 |  | B
036909C-1000-MR-4100-0001 | Material Requisition for Wet Air Oxidation Package | A | 2018-11-22 | IFQ | OL1-2M55-0103 | ME | 2018-11-27 | 036909C-JVD-TRN-00367 | 036909C-JVD-TRN-00367 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-ME-00367 |  | A
036909C-1000-MR-0310-0001 | Material Requisition for Cooling Tower | A | 2018-10-30 | IFQ | OL1-2M55-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 |  | Transmitted | TPSK-LSPA1-T-ME-00276 |  | A
036909C-1000-MR-0845-0001 | Material Requisition for Deareator | A | 2018-10-29 | IFQ | OL1-2M55-0108 | ME | 2018-11-06 | 036909C-JVD-TRN-00270 | 036909C-JVD-TRN-00270 | IFR | 2018-11-20 | 2018-11-29 | Transmitted | TPSK-LSPA1-T-ME-00270 |  | A
036909C-1000-MR-4234-0001 | Material Requisition for Side Stream Filter Package | A | 2018-10-29 | IFQ | OL1-2M55-0109 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248 |  | A
036909C-1000-MR-4111-0001 | Material Requisition for Hydrogen Production Unit | A | 2018-10-26 | IFQ | OL1-2M55-0114 | ME | 2018-11-06 | 036909C-JVD-TRN-00271 | 036909C-JVD-TRN-00271 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-ME-00271 |  | A
036909C-1012-MR-0127-2001 | Material Requisition for Convection Tubes | 0 | 2018-12-06 | IFP | OL1-2M55-2001 | ME | 2018-12-10 | 036909C-JVD-TRN-00450 | 036909C-JVD-TRN-00450 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00450 |  | z0
036909C-1012-MR-0127-2002 | Material Requisition for Furnace Convection Fittings | A | 2018-10-16 | IFQ | OL1-2M55-2002 | ME | 2018-10-22 | 036909C-JVD-TRN-00207 | 036909C-JVD-TRN-00207 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00207 |  | A
036909C-1012-MR-0154-2003 | Material Requisition for Quench Exchangers | A | 2018-10-18 | IFQ | OL1-2M55-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00233 | 036909C-JVD-TRN-00233 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00233 |  | A
036909C-1012-MR-0154-2003 | Material Requisition for Quench Exchangers | 0 | 2018-12-07 | IFP | OL1-2M55-2003 | ME | 2018-12-10 | 036909C-JVD-TRN-00466 | 036909C-JVD-TRN-00466 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00466 |  | z0
036909C-1012-MR-0122-2004 | Material Requisition for Radiant Coil Assemblies | A | 2018-09-12 | IFQ | OL1-2M55-2004 | ME | 2018-09-18 | 036909C-JVD-TRN-00063 | 036909C-JVD-TRN-00063 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00063 |  | A
036909C-1012-MR-1040-2005 | Material Requisition for Furnace ID Fans | A | 2018-11-01 | IFQ | OL1-2M55-2005 | ME | 2018-11-05 | 036909C-JVD-TRN-00269 | 036909C-JVD-TRN-00269 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00269 |  | A
036909C-1012-MR-0191-2006 | Material Requisition for Furnace Burners | A | 2018-11-07 | IFQ | OL1-2M55-2006 | ME | 2018-11-13 | 036909C-JVD-TRN-00313 | 036909C-JVD-TRN-00313 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00313 |  | A
036909C-1012-MR-0125-2007 | Material Requisition for Cast Intermediate Tube Supports | A | 2018-11-12 | IFQ | OL1-2M55-2007 | ME | 2018-11-16 | 036909C-JVD-TRN-00329 | 036909C-JVD-TRN-00329 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00329 |  | A
036909C-1012-MR-0155-2018 | Material Requisition for Furnace Steam Drums | A | 2018-11-01 | IFQ | OL1-2M55-2018 | ME | 2018-11-01 | 036909C-JVD-TRN-00263 | 036909C-JVD-TRN-00263 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00263 |  | A
036909C-1000-SP-0910-0003 | Particular Technical Specification for Cooling Water Pumps | A | 2018-11-14 | IFQ | OL1-2M57-0003 | ME | 2018-11-15 | 036909C-JVD-TRN-00319 | 036909C-JVD-TRN-00319 | IFR | 2018-11-29 | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00319 |  | A
036909C-1000-SP-1011-0001 | Particular Technical Specification For Centrifugal Compressors Steam Turbine Driven | A | 2018-10-04 | IFQ | OL1-2M57-0008 | ME | 2018-10-08 | 036909C-JVD-TRN-00136 | 036909C-JVD-TRN-00136 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00136 |  | A
036909C-1000-SP-1130-0001 | Particular Technical Specification For Residue Gas Expander/Recompressor | A | 2018-10-05 | IFQ | OL1-2M57-0012 | ME | 2018-10-09 | 036909C-JVD-TRN-00139 | 036909C-JVD-TRN-00139 | IFR | 2018-10-22 | 2018-10-26 | Transmitted | TPSK-LSPA1-T-ME-00139 |  | A
036909C-1000-SP-1013-0001 | Particular Technical Specification for Integrally Geared Decoking Air Compressors | A | 2018-10-18 | IFQ | OL1-2M57-0014 | ME | 2018-10-19 | 036909C-JVD-TRN-00198 | 036909C-JVD-TRN-00198 | IFR | 2018-11-02 | 2018-11-07 | Transmitted | TPSK-LSPA1-T-ME-00198 |  | A
036909C-1000-SP-0910-0001 | Particular Technical Specification For API Centrifugal Pumps - LLI | A | 2018-10-30 | IFQ | OL1-2M57-0015 | ME | 2018-10-31 | 036909C-JVD-TRN-00257 | 036909C-JVD-TRN-00257 | IFR | 2018-11-20 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00257 |  | A
036909C-1000-SP-0570-0001 | Particular Technical Specification For Trays For Columns | A | 2018-11-06 | IFQ | OL1-2M57-0055 | ME | 2018-11-09 | 036909C-JVD-TRN-00300 | 036909C-JVD-TRN-00300 | IFR | 2018-11-26 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00300 |  | A
036909C-1000-SP-0610-0001 | Particular Technical Specification For Wieland Tubes (Solo Source) | A | 2018-11-27 | IFQ | OL1-2M57-0058 | ME | 2018-11-28 | 036909C-JVD-TRN-00377 | 036909C-JVD-TRN-00377 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00377 |  | A
036909C-1000-SP-0661-0001 | Particular Technical Specification For Plate And Frame Heat Exchangers | A | 2018-10-01 | IFQ | OL1-2M57-0064 | ME | 2018-10-03 | 036909C-JVD-TRN-00124 | 036909C-JVD-TRN-00124 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00124 |  | A
036909C-1000-SP-0662-0002 | Particular Technical Specification For Cold Box And Core Exchangers | A | 2018-10-01 | IFQ | OL1-2M57-0066 | ME | 2018-10-03 | 036909C-JVD-TRN-00125 | 036909C-JVD-TRN-00125 | IFR | 2018-10-17 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00125 |  | A
036909C-1000-SP-0570-0004 | Particular Technical Specification For MD Trays For Columns | A | 2018-10-31 | IFQ | OL1-2M57-0075 | ME | 2018-11-07 | 036909C-JVD-TRN-00278 | 036909C-JVD-TRN-00278 | IFR | 2018-11-21 | 2018-11-29 | R1-No comments | TPSK-LSPA1-T-ME-00278 |  | A
036909C-1000-SP-0570-0004 | Particular Technical Specification for High Efficiency Internals for Columns | B | 2018-11-12 | IMP | OL1-2M57-0075 | ME | 2018-11-14 | 036909C-JVD-TRN-00314 | 036909C-JVD-TRN-00314 | IFR | 2018-11-29 |  | Transmitted | TPSK-LSPA1-T-ME-00314 |  | B
036909C-1000-SP-4100-0001 | Particular Technical Specification for Wet Air Oxidation Package | A | 2018-11-26 | IFQ | OL1-2M57-0103 | ME | 2018-11-29 | 036909C-JVD-TRN-00390 | 036909C-JVD-TRN-00390 | IFR | 2018-12-13 |  | Transmitted | TPSK-LSPA1-T-ME-00390 |  | A
036909C-1000-SP-0310-0001 | Particular Technical Specification for Cooling Tower | A | 2018-10-30 | IFQ | OL1-2M57-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 |  | Transmitted | TPSK-LSPA1-T-ME-00276 |  | A
036909C-1000-SP-0845-0001 | Particular Technical Specification For Deaerator | A | 2018-10-29 | IFQ | OL1-2M57-0108 | ME | 2018-11-06 | 036909C-JVD-TRN-00270 | 036909C-JVD-TRN-00270 | IFR | 2018-11-20 | 2018-11-29 | Transmitted | TPSK-LSPA1-T-ME-00270 |  | A
036909C-1000-SP-4234-0001 | Particular Technical Specification for Side Steam Filter Package | A | 2018-10-29 | IFQ | OL1-2M57-0109 | ME | 2018-10-31 | 036909C-JVD-TRN-00248 | 036909C-JVD-TRN-00248 | IFR | 2018-11-16 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00248 |  | A
036909C-1000-SP-4111-0001 | Particular Technical Specification For Hydrogen Production Unit | A | 2018-10-26 | IFQ | OL1-2M57-0114 | ME | 2018-11-06 | 036909C-JVD-TRN-00271 | 036909C-JVD-TRN-00271 | IFR | 2018-11-20 |  | Transmitted | TPSK-LSPA1-T-ME-00271 |  | A
036909C-1012-SP-0127-2001 | Particular Technical Specification for Convection Tubes | 0 | 2018-12-04 | IFP | OL1-2M57-2001 | ME | 2018-12-10 | 036909C-JVD-TRN-00450 | 036909C-JVD-TRN-00450 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00450 |  | z0
036909C-1012-SP-0127-2002 | Particular Technical Specification for Furnace Convection Fittings | A | 2018-10-16 | IFQ | OL1-2M57-2002 | ME | 2018-10-22 | 036909C-JVD-TRN-00207 | 036909C-JVD-TRN-00207 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00207 |  | A
036909C-1012-SP-0154-2003 | Particular Techanical Specification for Quench Exchangers | A | 2018-10-18 | IFQ | OL1-2M57-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00233 | 036909C-JVD-TRN-00233 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00233 |  | A
036909C-1012-SP-0154-2003 | Particular Techanical Specification for Quench Exchangers | 0 | 2018-12-06 | IFP | OL1-2M57-2003 | ME | 2018-12-10 | 036909C-JVD-TRN-00466 | 036909C-JVD-TRN-00466 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00466 |  | z0
036909C-1012-SP-0122-2004 | Particular Technical Specification For Radiant Coil Assemblies | A | 2018-09-10 | IFI | OL1-2M57-2004 | ME | 2018-09-18 | 036909C-JVD-TRN-00063 | 036909C-JVD-TRN-00063 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00063 |  | A
036909C-1012-SP-1040-2005 | Particular Technical Specification for Furnace ID Fans | A | 2018-11-01 | IFQ | OL1-2M57-2005 | ME | 2018-11-05 | 036909C-JVD-TRN-00269 | 036909C-JVD-TRN-00269 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00269 |  | A
036909C-1012-SP-0191-2006 | Particular Technical Specification for Furnace Burners | A | 2018-11-07 | IFQ | OL1-2M57-2006 | ME | 2018-11-13 | 036909C-JVD-TRN-00313 | 036909C-JVD-TRN-00313 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00313 |  | A
036909C-1012-SP-0125-2007 | Particular Technical Specification for Cast Intermediate Tube Supports | A | 2018-11-12 | IFQ | OL1-2M57-2007 | ME | 2018-11-16 | 036909C-JVD-TRN-00329 | 036909C-JVD-TRN-00329 | IFI |  | 2018-12-10 | R1-No comments | TPSK-LSPA1-T-ME-00329 |  | A
036909C-1012-SP-0155-2018 | Particular Technical Specification for Furnace Steam Drums | A | 2018-11-01 | IFQ | OL1-2M57-2018 | ME | 2018-11-01 | 036909C-JVD-TRN-00263 | 036909C-JVD-TRN-00263 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00263 |  | A
036909C-1006-JSS-0117-1001 | Approved Vendor List for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2M91-1001 | ME | 2018-10-23 | 036909C-JVD-TRN-00211 | 036909C-JVD-TRN-00211 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00211 |  | z0
036909C-1012-JSS-0122-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces | 0 | 2018-12-07 | IMP | OL1-2M92-2001 | ME | 2018-12-11 | 036909C-JVD-TRN-00470 | 036909C-JVD-TRN-00470 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00470 |  | z0
036909C-1012-JSS-0122-2002 | Project Specification for Statically Cast Fittings For Radiant Coils and Transfer Lines in Cracking Furnaces | 0 | 2018-12-07 | IMP | OL1-2M92-2002 | ME | 2018-12-11 | 036909C-JVD-TRN-00471 | 036909C-JVD-TRN-00471 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00471 |  | z0
036909C-1012-JSS-0125-2003 | Project Specification for Cast Intermediate Tube Supports | 0 | 2018-10-15 | IFI | OL1-2M92-2003 | ME | 2018-10-26 | 036909C-JVD-TRN-00232 | 036909C-JVD-TRN-00232 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00232 |  | z0
036909C-1012-JSS-0154-2007 | Project Specification For SLE and USX Exchangers | 0 | 2018-11-28 | IMP | OL1-2M92-2007 | ME | 2018-12-05 | 036909C-JVD-TRN-00427 | 036909C-JVD-TRN-00427 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00427 |  | z0
036909C-1012-JSS-0154-2008 | Project Specification For Transfer Line Exchangers | 0 | 2018-11-28 | IMP | OL1-2M92-2008 | ME | 2018-12-05 | 036909C-JVD-TRN-00428 | 036909C-JVD-TRN-00428 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00428 |  | z0
036909C-1012-JSS-0191-2009 | Project Specification for Furnace Burners | A | 2018-10-15 | IFR | OL1-2M92-2009 | ME | 2018-10-25 | 036909C-JVD-TRN-00231 | 036909C-JVD-TRN-00231 | IFR | 2018-11-08 | 2018-11-14 | R1-No comments | TPSK-LSPA1-T-PE-00231 |  | A
036909C-1000-STC-1390-0001 | Piping Construction Drawing | A | 2018-08-07 | IFR | OL1-2P92-0003 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | A
036909C-1000-STC-1390-0001 | Piping Standard Construction Drawings | 0 | 2018-11-12 | CAN | OL1-2P92-0003 | MP | 2018-11-16 | 036909C-JVD-TRN-00325 | 036909C-JVD-TRN-00325 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00325 | Replaced by doc. OL1-2P92-0050 (included as attachment) | z0
036909C-1000-JSD-1400-0001 | Job Design Specification For Underground Systems | A | 2018-09-18 | IFR | OL1-2R02-0001 | CV | 2018-09-25 | 036909C-JVD-TRN-00087 | 036909C-JVD-TRN-00087 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00087 |  | A
036909C-1000-JSD-1700-0001 | Job Design Specification For Foundations And Structures | A | 2018-09-19 | IFR | OL1-2R02-0004 | CV | 2018-09-25 | 036909C-JVD-TRN-00087 | 036909C-JVD-TRN-00087 | IFR | 2018-10-09 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-CV-00087 |  | A
036909C-1000-JSD-2000-0001 | Buildings Design And Construction | A | 2018-10-10 | IFR | OL1-2R02-0005 | CV | 2018-10-11 | 036909C-JVD-TRN-00158 | 036909C-JVD-TRN-00158 | IFR | 2018-10-25 |  | Transmitted | TPSK-LSPA1-T-CV-00158 |  | A
036909C-1000-JSS-6300-02 | Jo b Specification For Weldings and NDE Of Pressure Vessels And Heat Exchangers | A | 2018-08-24 | IFR | OL1-2R03-0001 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00029 |  | A
036909C-1000-JSS-6300-03 | Job Specification For Materials In Sour Services | A | 2018-08-24 | IFR | OL1-2R03-0002 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | A
036909C-1000-JSS-6300-04 | Job Specification For Supply Positive Alloy Material Identification Of Equipment And Piping | A | 2018-08-24 | IFR | OL1-2R03-0003 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | A
036909C-1000-JSS-6300-05 | Job Specification For Welding And NDE Storage Tanks | A | 2018-08-24 | IFR | OL1-2R03-0004 | MP | 2018-08-27 | 036909C-JVD-TRN-00029 | 036909C-JVD-TRN-00029 | IFR | 2018-09-10 | 2018-09-19 | R1-No comments | TPSK-LSPA1-T-ME-00029 |  | A
036909C-1006-JSS-0117-0005 | ME-005 Double Jacket Pipe Heat Exchangers for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R03-0005 | ME | 2018-10-23 | 036909C-JVD-TRN-00212 | 036909C-JVD-TRN-00212 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00212 |  | z0
036909C-1000-JSS-0660-01 | Plate Heat Exchanger | 0 | 2018-09-10 | IMP | OL1-2R03-0006 | ME | 2018-09-12 | 036909C-JVD-TRN-00042 | 036909C-JVD-TRN-00042 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00042 |  | z0
036909C-1000-JSS-0910-0001 | ME-010 Centrifugal Pump | A | 2018-09-20 | IFR | OL1-2R03-0010 | ME | 2018-09-24 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | A
036909C-1000-JSS-1140-0001 | ME-013 Diesel Engine | A | 2018-10-22 | IFR | OL1-2R03-0013 | ME | 2018-10-18 | 036909C-JVD-TRN-00196 | 036909C-JVD-TRN-00196 | IFR | 2018-11-06 | 2018-11-02 | R1-No comments | TPSK-LSPA1-T-ME-00196 |  | A
036909C-1000-JSS-1011-0001 | ME-014 Centrifugal Compressor | A | 2018-09-18 | IFR | OL1-2R03-0014 | ME | 2018-09-18 | 036909C-JVD-TRN-00065 | 036909C-JVD-TRN-00065 | IFR | 2018-10-03 | 2018-10-10 | R1-No comments | TPSK-LSPA1-T-ME-00065 |  | A
036909C-1000-JSS-1013-0001 | ME-016 Centrifugal Compressor For PA/IA Servise | A | 2018-10-09 | IFR | OL1-2R03-0016 | ME | 2018-10-12 | 036909C-JVD-TRN-00164 | 036909C-JVD-TRN-00164 | IFR | 2018-10-26 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00164 |  | A
036909C-1000-JSS-1040-0001 | ME-017 Root Blower | 0 | 2018-11-16 | IMP | OL1-2R03-0017 | ME | 2018-11-19 | 036909C-JVD-TRN-00334 | 036909C-JVD-TRN-00334 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00334 |  | z0
036909C-1000-JSS-1111-0001 | ME-018 General Purpose Steam Turbines | A | 2018-09-20 | IFR | OL1-2R03-0018 | ME | 2018-09-24 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | A
036909C-1000-JSS-1061-0001 | ME-019 Lube Oil Unit And Seal Oil System | A | 2018-09-18 | IFR | OL1-2R03-0019 | ME | 2018-09-18 | 036909C-JVD-TRN-00065 | 036909C-JVD-TRN-00065 | IFR | 2018-10-03 | 2018-10-10 | R1-No comments | TPSK-LSPA1-T-ME-00065 |  | A
036909C-1000-JSS-1112-0001 | ME-020 Special Purpose Steam Tturbines | A | 2018-09-20 | IFR | OL1-2R03-0020 | ME | 2018-09-24 | 036909C-JVD-TRN-00078 | 036909C-JVD-TRN-00078 | IFR | 2018-10-08 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-ME-00078 |  | A
036909C-1000-JSS-0184-0001 | ME-021 Flare System | A | 2018-11-29 | IFR | OL1-2R03-0021 | ME | 2018-12-06 | 036909C-JVD-TRN-00429 | 036909C-JVD-TRN-00429 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-ME-00429 |  | A
036909C-1000-JSS-1160-0001 | ME-022 Special Purpose Gear | A | 2018-10-12 | IFR | OL1-2R03-0022 | ME | 2018-10-12 | 036909C-JVD-TRN-00166 | 036909C-JVD-TRN-00166 | IFR | 2018-10-26 | 2018-11-07 | R1-No comments | TPSK-LSPA1-T-ME-00166 |  | A
036909C-1000-JSS-0900-0001 | ME-028 Mechanical Seal | 0 | 2018-09-14 | IMP | OL1-2R03-0028 | ME | 2018-09-17 | 036909C-JVD-TRN-00057 | 036909C-JVD-TRN-00057 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00057 |  | z0
036909C-1006-JSS-0117-0029 | ME-029 Centrifugal Blower for 36M and 132U Furnace | 0 | 2018-10-16 | IMP | OL1-2R03-0029 | ME | 2018-10-17 | 036909C-JVD-TRN-00185 | 036909C-JVD-TRN-00185 | IFI |  | 2018-11-05 | Transmitted | TPSK-LSPA1-T-ME-00185 |  | z0
036909C-1000-JSS-1031-0001 | ME-047 Dry Screw Compressor for Hydrocarbon Services | A | 2018-11-30 | IFR | OL1-2R03-0047 | ME | 2018-12-06 | 036909C-JVD-TRN-00429 | 036909C-JVD-TRN-00429 | IFR | 2018-12-20 |  | Transmitted | TPSK-LSPA1-T-ME-00429 |  | A
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | A | 2018-08-09 | IFR | OL1-2R03-0050 | ME | 2018-08-10 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00017 |  | A
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | B | 2018-09-20 | IFR | OL1-2R03-0050 | ME | 2018-09-25 | 036909C-JVD-TRN-00084 | 036909C-JVD-TRN-00084 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | B
036909C-1000-JSD-0400-01 | Job Specification For Design Of Pressure & Atmospheric Static Equipment | 0 | 2018-10-26 | IMP | OL1-2R03-0050 | ME | 2018-10-31 | 036909C-JVD-TRN-00245 | 036909C-JVD-TRN-00245 | IFR | 2018-11-14 | 2018-11-26 | Transmitted | TPSK-LSPA1-T-ME-00245 |  | z0
036909C-1000-JSS-0400-01 | Job Specification for Supply of Pressure Vessels | A | 2018-08-10 | IFR | OL1-2R03-0051 | ME | 2018-08-13 | 036909C-JVD-TRN-00021 | 036909C-JVD-TRN-00021 | IFR | 2018-08-27 | 2018-08-27 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00021 |  | A
036909C-1000-JSS-0400-01 | Job Specification For Supply Of Pressure Vessels | B | 2018-09-20 | IFR | OL1-2R03-0051 | ME | 2018-09-25 | 036909C-JVD-TRN-00084 | 036909C-JVD-TRN-00084 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | B
036909C-1000-JSS-0400-01 | Job Specification For Supply Of Pressure Vessels | 0 | 2018-10-26 | IMP | OL1-2R03-0051 | ME | 2018-10-31 | 036909C-JVD-TRN-00249 | 036909C-JVD-TRN-00249 | IFR | 2018-11-14 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00249 |  | z0
036909C-1000-JSS-0570-01 | Job Specification For Supply Of Column Internals | A | 2018-08-09 | IFR | OL1-2R03-0052 | ME | 2018-08-10 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00017 |  | A
036909C-1000-JSS-0570-01 | Job Specification For Supply Of Column Internals | 0 | 2018-09-20 | IMP | OL1-2R03-0052 | ME | 2018-09-24 | 036909C-JVD-TRN-00081 | 036909C-JVD-TRN-00081 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00081 |  | z0
036909C-1000-JSS-1820-01 | Job Specification For Supply Of Equipment Ladders And Platforms | A | 2018-08-09 | IFR | OL1-2R03-0053 | ME | 2018-08-10 | 036909C-JVD-TRN-00017 | 036909C-JVD-TRN-00017 | IFR | 2018-08-24 | 2018-08-27 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-ME-00017 |  | A
036909C-1000-JSS-1820-01 | Job Specification For Supply Of Equipment Ladders And Platforms | 0 | 2018-09-20 | IFR | OL1-2R03-0053 | ME | 2018-09-24 | 036909C-JVD-TRN-00081 | 036909C-JVD-TRN-00081 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00081 |  | z0
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | A | 2018-08-10 | IFR | OL1-2R03-0054 | ME | 2018-08-10 | 036909C-JVD-TRN-00018 | 036909C-JVD-TRN-00018 | IFR | 2018-08-24 | 2018-08-27 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-ME-00018 |  | A
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | B | 2018-09-20 | IFR | OL1-2R03-0054 | ME | 2018-09-25 | 036909C-JVD-TRN-00085 | 036909C-JVD-TRN-00085 | IFR | 2018-10-09 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-ME-00084 |  | B
036909C-1000-STC-0490-000 | Construction Standards For Pressure Equipment | 0 | 2018-10-26 | IMP | OL1-2R03-0054 | ME | 2018-10-31 | 036909C-JVD-TRN-00256 | 036909C-JVD-TRN-00256 | IFR | 2018-11-14 | 2018-11-27 | Transmitted | TPSK-LSPA1-T-ME-00256 |  | z0
036909C-1000-STC-1890-080 | Construction Standards For Ladders & Platforms Attached To Pressure Equipment | 0 | 2018-10-01 | IMP | OL1-2R03-0055 | ME | 2018-10-03 | 036909C-JVD-TRN-00120 | 036909C-JVD-TRN-00120 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00120 |  | z0
036909C-1000-JSS-0400-02 | Marking For Vessel & Heat Exchanger | 0 | 2018-09-10 | IMP | OL1-2R03-0102 | ME | 2018-09-12 | 036909C-JVD-TRN-00042 | 036909C-JVD-TRN-00042 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00042 |  | z0
036909C-1000-JSS-0310-0001 | ME-008 Cooling Water | A | 2018-10-30 | IFQ | OL1-2R03-0104 | ME | 2018-11-06 | 036909C-JVD-TRN-00276 | 036909C-JVD-TRN-00276 | IFR | 2018-11-19 |  | Transmitted | TPSK-LSPA1-T-ME-00276 |  | A
036909C-1000-JSS-0910-0002 | ME-050 Centrifugal Pump (Non API) | A | 2018-10-25 | IFR | OL1-2R03-0500 | ME | 2018-11-12 | 036909C-JVD-TRN-00308 | 036909C-JVD-TRN-00308 | IFR | 2018-11-27 | 2018-12-06 | R1-No comments | TPSK-LSPA1-T-ME-00308 |  | A
036909C-1000-STC-1890-080 | Construction Standards For Ladders And Platforms Attached To Pressure Equipment | A | 2018-08-23 | IFR | OL1-2R03-055 | ME | 2018-08-27 | 036909C-JVD-TRN-00027 | 036909C-JVD-TRN-00027 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-ME-00027 |  | A
036909C-1006-JSS-0117-3001 | ME-001 Pressure Vessel for 36M and 132U Furnace | 0 | 2018-10-18 | IFE | OL1-2R03-1001 | ME | 2018-11-07 | 036909C-JVD-TRN-00262 | 036909C-JVD-TRN-00262 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00262 |  | z0
036909C-1006-JSS-0117-3004 | ME-004 Shell and Tube Heat Exchangers for 36M and 132U Furnace | 0 | 2018-10-18 | IFI | OL1-2R03-1004 | ME | 2018-10-24 | 036909C-JVD-TRN-00221 | 036909C-JVD-TRN-00221 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00221 |  | z0
036909C-1000-STD-1380-0001 | Piping Design Standard Drawings | A | 2018-08-07 | IFR | OL1-2P92-0002 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | A
036909C-1000-JSD-1300-0002 | Piping Design Specification | A | 2018-08-07 | IFR | OL1-2R04-0002 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | A
036909C-1000-JSD-1300-0002 | Job Specification For Detail Design Piping | B | 2018-11-12 | IFR | OL1-2R04-0002 | MP | 2018-11-16 | 036909C-JVD-TRN-00326 | 036909C-JVD-TRN-00326 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00012 | Replaces doc. OL1-2P92-0002 (included as attachment to this doc.) | B
036909C-1000-STD-1380-0001 | Piping Design Standard Drawings | 0 | 2018-11-12 | CAN | OL1-2P92-0002 | MP | 2018-11-16 | 036909C-JVD-TRN-00325 | 036909C-JVD-TRN-00325 | IFR | 2018-12-03 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00325 | Replaced by doc. OL1-2R04-0002 (included as attachment) | z0
036909C-1000-JSD-2200-01 | Job design specification for thermal insulation (hot service) | A | 2018-08-22 | IFR | OL1-2R04-0003 | MP | 2018-08-22 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | A
036909C-1000-JSD-2200-02 | Job Design Specification For Thermal Insulation (Cold Service) | A | 2018-08-22 | IFR | OL1-2R04-0004 | MP | 2018-08-22 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | A
036909C-1000-JSD-2300-01 | Job Design Specification For Painting | A | 2018-08-22 | IFR | OL1-2R04-0005 | MP | 2018-08-22 | 036909C-JVD-TRN-00024 | 036909C-JVD-TRN-00024 | IFR | 2018-09-05 | 2018-09-12 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00024 |  | A
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | A | 2018-08-22 | IFR | OL1-2R04-0006 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-JSS-1300-01 | General Supply Specification For Piping Material | B | 2018-11-19 | IFR | OL1-2R04-0006 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1006-JSS-0117-0007 | PIP-007 Marking of Piping Material for 36M and 132U Furnace | 0 | 2018-10-18 | IMP | OL1-2R04-0007 | ME | 2018-10-23 | 036909C-JVD-TRN-00213 | 036909C-JVD-TRN-00213 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00213 |  | z0
036909C-1000-JSS-1310-0004 | Job Supply Specification For Butterfly Valves | A | 2018-11-20 | IFR | OL1-2R04-0008 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-MP-00352 |  | A
036909C-1000-JSS-1310-0006 | Job Supply Specification For Plug Valves | A | 2018-11-20 | IFR | OL1-2R04-0009 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-MP-00352 |  | A
036909C-1000-JSS-1310-0008 | Job Supply Specification For Ball Valves | A | 2018-11-20 | IFR | OL1-2R04-0010 | MP | 2018-11-26 | 036909C-JVD-TRN-00352 | 036909C-JVD-TRN-00352 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-MP-00352 |  | A
036909C-1000-JSS-1320-01 | Job Supply Specification For Pipes | A | 2018-08-22 | IFR | OL1-2R04-0011 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | R2-Comments as noted | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-JSS-1320-01 | Job Supply Specification For Pipes | B | 2018-11-19 | IFR | OL1-2R04-0011 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1000-JSD-1300-0012 | Pipe Support | A | 2018-11-12 | IFR | OL1-2R04-0012 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-MP-00324 |  | A
036909C-1000-JSS-1330-01 | Job Supply Specification For Butt Welding Fittings | A | 2018-08-22 | IFR | OL1-2R04-0013 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-JSS-1330-01 | Job Supply Specification For Buttwelding Fittings | B | 2018-11-19 | IFR | OL1-2R04-0013 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1000-JSS-1340-01 | Job Supply Specification For Forged Fittings | A | 2018-08-22 | IFR | OL1-2R04-0014 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-JSS-1340-01 | Job Supply Specification For Forged Fittings | B | 2018-11-19 | IFR | OL1-2R04-0014 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1000-JSS-1350-01 | Job Supply Specification For Flanges | A | 2018-08-24 | IFR | OL1-2R04-0015 | MP | 2018-08-27 | 036909C-JVD-TRN-00028 | 036909C-JVD-TRN-00028 | IFR | 2018-09-10 | 2018-09-18 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00028 |  | A
036909C-1000-JSS-1350-01 | Job Supply Specification For Flanges | B | 2018-11-19 | IFR | OL1-2R04-0015 | MP | 2018-11-20 | 036909C-JVD-TRN-00342 | 036909C-JVD-TRN-00342 | IFR | 2018-12-05 |  | Transmitted | TPSK-LSPA1-T-MP-00342 |  | B
036909C-1000-JSD-1300-0011 | Piping Flexibility | A | 2018-11-19 | IFR | OL1-2R04-0030 | MP | 2018-11-20 | 036909C-JVD-TRN-00336 | 036909C-JVD-TRN-00336 | IFR | 2018-12-05 | 2018-12-07 | R1-No comments | TPSK-LSPA1-T-MP-00336 |  | A
036909C-1000-JSD-1300-0003 | Job Design Specification For Steam Tracing | A | 2018-08-07 | IFR | OL1-2R04-0031 | MP | 2018-08-08 | 036909C-JVD-TRN-00012 | 036909C-JVD-TRN-00012 | IFR | 2018-08-22 | 2018-09-26 | A4-Not Approved, re-submit for approval | TPSK-LSPA1-T-MP-00012 |  | A
036909C-1000-JSD-1300-0003 | A1 Scope Annex C– Ppiping Specification PIP-006 Steam Tracing Piping | B | 2018-11-06 | IFR | OL1-2R04-0031 | MP | 2018-11-09 | 036909C-JVD-TRN-00292 | 036909C-JVD-TRN-00292 | IFR | 2018-11-26 |  | Transmitted | TPSK-LSPA1-T-MP-00292 |  | B
036909C-1000-JSD-1300-0008 | JSD For Piping Stress Analysis | A | 2018-11-12 | IFR | OL1-2R04-0032 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-MP-00324 |  | A
036909C-1000-JSD-1300-0009 | JSD for piping loads on PRK SLW STR IS | A | 2018-11-12 | IFR | OL1-2R04-0033 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-MP-00324 |  | A
036909C-1000-JSD-1300-0010 | JSD For Auxiliary Piping Supports | A | 2018-11-12 | IFR | OL1-2R04-0034 | MP | 2018-11-16 | 036909C-JVD-TRN-00324 | 036909C-JVD-TRN-00324 | IFR | 2018-12-03 |  | Transmitted | TPSK-LSPA1-T-MP-00324 |  | A
036909C-1000-JSS-1310-0001 | Job Supply Specification For Valves (Gate - Globe - Check) | A | 2018-11-20 | IFR | OL1-2R04-0041 | MP | 2018-11-26 | 036909C-JVD-TRN-00356 | 036909C-JVD-TRN-00356 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-MP-00356 |  | A
036909C-1006-JSS-0117-1004 | PIP-004 Piping Welding Specification for 36M and 132U Furnace | 0 | 2018-10-15 | IMP | OL1-2R04-1004 | ME | 2018-10-16 | 036909C-JVD-TRN-00184 | 036909C-JVD-TRN-00184 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00184 |  | z0
036909C-1000-JSD-1600-0001 | General Electrical Design | 0 | 2018-12-03 | IMP | OL1-2R05-0001 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424 |  | z0
036909C-1000-JSD-1600-0002 | Electrical System Design | 0 | 2018-12-03 | IMP | OL1-2R05-0002 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424 |  | z0
036909C-1000-JSS-1641-0001 | Oil Filled Distribution Transformer | 0 | 2018-09-20 | IMP | OL1-2R05-0003 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1661-0001 | Substation Monitoring And Control System | 0 | 2018-12-03 | IMP | OL1-2R05-0005 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425 |  | z0
036909C-1000-JSS-1652-0001 | Medium Voltage Switchgear | 0 | 2018-09-20 | IMP | OL1-2R05-0006 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1657-0001 | Low Voltage Distribution Panel | 0 | 2018-09-20 | IMP | OL1-2R05-0007 | EE | 2018-11-12 | 036909C-JVD-TRN-00309 | 036909C-JVD-TRN-00309 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00309 |  | z0
036909C-1000-JSS-1654-0001 | Low Voltage Switchgear And Motor Control Center | 0 | 2018-09-20 | IFE | OL1-2R05-0008 | EE | 2018-11-12 | 036909C-JVD-TRN-00309 | 036909C-JVD-TRN-00309 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00309 |  | z0
036909C-1000-JSS-1691-0001 | Electrical Motos Up To 300 kW | 0 | 2018-09-20 | IMP | OL1-2R05-0010 | EE | 2018-09-24 | 036909C-JVD-TRN-00079 | 036909C-JVD-TRN-00079 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00079 |  | z0
036909C-1000-JSS-1692-0001 | Electrical Motors Greater Than 300 kW | 0 | 2018-09-20 | IMP | OL1-2R05-0011 | EE | 2018-11-08 | 036909C-JVD-TRN-00293 | 036909C-JVD-TRN-00293 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00293 |  | z0
036909C-1000-JSS-1671-0001 | Uninterruptible Power Supplies | 0 | 2018-09-20 | IMP | OL1-2R05-0012 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSD-1530-0001 | Intercom/Paging/Audible Alarm System | A | 2018-11-30 | IFR | OL1-2R05-0013 | EE | 2018-12-04 | 036909C-JVD-TRN-00403 | 036909C-JVD-TRN-00403 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-EE-00403 |  | A
036909C-1000-JSD-1600-0004 | LIGHTING SYSTEM | 0 | 2018-09-20 | IMP | OL1-2R05-0014 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258 |  | z0
036909C-1000-JSD-1600-0010 | Earthing And Lightning Protection | 0 | 2018-09-20 | IMP | OL1-2R05-0015 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258 |  | z0
036909C-1000-JSS-1684-0001 | Cathodic Protection | 0 | 2018-09-20 | IMP | OL1-2R05-0016 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-4123-0001 | Diesel Engine Generator | 0 | 2018-09-20 | IMP | OL1-2R05-0017 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1621-0001 | Power Control And Fiber Optic Cables | 0 | 2018-12-03 | IMP | OL1-2R05-0018 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425 |  | z0
036909C-1000-JSD-1530-0002 | Safety Supervisory System | A | 2018-11-30 | IFR | OL1-2R05-0019 | EE | 2018-12-04 | 036909C-JVD-TRN-00403 | 036909C-JVD-TRN-00403 | IFR | 2018-12-18 |  | Transmitted | TPSK-LSPA1-T-EE-00403 |  | A
036909C-1000-JSS-1656-0001 | Power Capacitors | 0 | 2018-09-20 | IMP | OL1-2R05-0021 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1622-0001 | Miscellaneous Equipment | 0 | 2018-09-20 | IMP | OL1-2R05-0022 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1693-0001 | Low Voltage Variable Voltage Variable Frequency System | 0 | 2018-09-20 | IMP | OL1-2R05-0023 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1641-0002 | Neutral Grounding Resistor | 0 | 2018-12-03 | IMP | OL1-2R05-0027 | EE | 2018-12-05 | 036909C-JVD-TRN-00425 | 036909C-JVD-TRN-00425 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00425 |  | z0
036909C-1000-JSD-1600-0007 | Functional and Schematic Diagram | 0 | 2018-09-20 | IMP | OL1-2R05-0029 | EE | 2018-11-05 | 036909C-JVD-TRN-00258 | 036909C-JVD-TRN-00258 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00258 |  | z0
036909C-1000-JSD-1600-0009 | Document Template | 0 | 2018-12-03 | IMP | OL1-2R05-0036 | EE | 2018-12-05 | 036909C-JVD-TRN-00424 | 036909C-JVD-TRN-00424 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00424 |  | z0
036909C-1000-JSS-1682-0001 | Electrical Heat Tracing | 0 | 2018-09-20 | IMP | OL1-2R05-0037 | EE | 2018-09-24 | 036909C-JVD-TRN-00079 | 036909C-JVD-TRN-00079 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00079 |  | z0
036909C-1000-JSS-1655-0001 | Low Voltage Bus Duct | 0 | 2018-09-20 | IMP | OL1-2R05-0038 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-JSS-1694-0001 | Medium Voltage Variable Voltage Variable Frequency System | 0 | 2018-09-20 | IMP | OL1-2R05-0040 | EE | 2018-11-05 | 036909C-JVD-TRN-00268 | 036909C-JVD-TRN-00268 | IFI |  |  | Transmitted | TPSK-LSPA1-T-EE-00268 |  | z0
036909C-1000-PP-1600-001 | Coordination Procedure For Smartplant Electrical | A | 2018-08-03 | IFR | OL1-2R05-0044 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | A
036909C-1000-PP-1600-003 | Coordination Procedure For ETAP | A | 2018-08-03 | IFI | OL1-2R05-0045 | EE | 2018-08-06 | 036909C-JVD-TRN-00008 | 036909C-JVD-TRN-00008 | IFR | 2018-08-20 | 2018-08-24 | A3-Approved with comments, re-submit for review. | TPSK-LSPA1-T-EE-00008 |  | A
036909C-1000-JSD-1540-0001 | Instrument General Design | A | 2018-09-28 | IFR | OL1-2R06-0001 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1547-0001 | Flow Measurement | 0 | 2018-09-28 | IMP | OL1-2R06-0003 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-JSD-1552-0001 | LEVEL MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0005 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1553-0001 | PRESSURE MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0006 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1554-0001 | TEMPERATURE MEASUREMENT | A | 2018-09-28 | IFR | OL1-2R06-0007 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1541-0001 | Final Control Element | A | 2018-09-28 | IFR | OL1-2R06-0008 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1572-0001 | Instrument Construction Material | 0 | 2018-09-28 | IMP | OL1-2R06-0010 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-JSD-1572-0003 | Instrument Air Supply | A | 2018-11-20 | IFR | OL1-2R06-0011 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-IE-00357 |  | A
036909C-1000-JSD-1515-0004 | Machinery Monitoring System | A | 2018-09-28 | IFR | OL1-2R06-0013 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1511-0002 | Integrated Control And Safety System | A | 2018-11-20 | IFR | OL1-2R06-0015 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-IE-00357 |  | A
036909C-1000-JSD-1511-0001 | Instrument Cabinet | A | 2018-09-28 | IFR | OL1-2R06-0016 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-1580-0001 | Integrated Turbine And Compressor Control System | A | 2018-10-08 | IFR | OL1-2R06-0017 | IE | 2018-10-10 | 036909C-JVD-TRN-00148 | 036909C-JVD-TRN-00148 | IFR | 2018-10-24 | 2018-10-24 | R1-No comments | TPSK-LSPA1-T-IE-00148 |  | A
036909C-1000-JSD-1545-0001 | Pressure Safety Valve | 0 | 2018-09-28 | IMP | OL1-2R06-0021 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-JSD-1501-0001 | Instrument Numbering | A | 2018-10-03 | IFR | OL1-2R06-0022 | IE | 2018-10-05 | 036909C-JVD-TRN-00132 | 036909C-JVD-TRN-00132 | IFR | 2018-10-19 | 2018-10-24 | R2-Comments as noted | TPSK-LSPA1-T-PE-00131 |  | A
036909C-1000-JSD-1501-0003 | Instrument Inspection And Test Plan | 0 | 2018-09-28 | IMP | OL1-2R06-0023 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | A | 2018-09-27 | IFR | OL1-2R06-0024 | IE | 2018-09-28 | 036909C-JVD-TRN-00109 | 036909C-JVD-TRN-00109 | IFR | 2018-10-11 | 2018-10-09 | R2-Comments as noted | TPSK-LSPA1-T-IE-00109 |  | A
036909C-1000-JSD-1501-0002 | General Design Rules For SmartPlant Instrumentation Setup | B | 2018-10-24 | IFR | OL1-2R06-0024 | IE | 2018-11-08 | 036909C-JVD-TRN-00291 | 036909C-JVD-TRN-00291 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-IE-00291 |  | B
036909C-1000-JSD-1580-0003 | General Design Rules For Instrumentation And Control Of Packaged Equipment | A | 2018-09-14 | IFR | OL1-2R06-0035 | IE | 2018-09-17 | 036909C-JVD-TRN-00056 | 036909C-JVD-TRN-00056 | IFR | 2018-10-01 | 2018-10-02 | R2-Comments as noted | TPSK-LSPA1-T-IE-00056 |  | A
036909C-1000-JSD-1580-0003 | General Design Rules For Instrumentation And Control Of Packaged Equipment | 0 | 2018-11-29 | IMP | OL1-2R06-0035 | IE | 2018-11-29 | 036909C-JVD-TRN-00393 | 036909C-JVD-TRN-00393 | IFR | 2018-12-14 |  | Transmitted | TPSK-LSPA1-T-IE-00393 |  | z0
036909C-1000-JSD-1580-0002 | Progammable Logic Controller | A | 2018-11-07 | IFR | OL1-2R06-1301 | IE | 2018-11-08 | 036909C-JVD-TRN-00291 | 036909C-JVD-TRN-00291 | IFR | 2018-11-23 |  | Transmitted | TPSK-LSPA1-T-IE-00291 |  | A
036909C-1000-JSD-1584-0001 | Custody Transfer System | A | 2018-11-20 | IFR | OL1-2R06-3101 | IE | 2018-11-26 | 036909C-JVD-TRN-00357 | 036909C-JVD-TRN-00357 | IFR | 2018-12-11 |  | Transmitted | TPSK-LSPA1-T-IE-00357 |  | A
036909C-1000-JSD-0001-0002 | Units Of Measurement | 0 | 2018-09-20 | IMP | OL1-2R07-0018 | ME | 2018-09-24 | 036909C-JVD-TRN-00080 | 036909C-JVD-TRN-00080 | IFI |  | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00080 |  | z0
036909C-1000-JSD-1522-0001 | Electrical And Instrument Interface Philosophy | A | 2018-09-28 | IFR | OL1-2R07-0020 | IE | 2018-10-03 | 036909C-JVD-TRN-00121 | 036909C-JVD-TRN-00121 | IFR | 2018-10-17 | 2018-10-09 | R1-No comments | TPSK-LSPA1-T-IE-00121 |  | A
036909C-1000-JSD-0001 | Project Design Basis | 0 | 2018-09-26 | IMP | OL1-2R07-0026 | ME | 2018-09-28 | 036909C-JVD-TRN-00110 | 036909C-JVD-TRN-00110 | IFR | 2018-10-11 | 2018-10-24 | Transmitted | TPSK-LSPA1-T-ME-00110 |  | z0
036909C-1000-JSD-1572-0004 | Instrument Installation | 0 | 2018-09-28 | IMP | OL1-2R08-0003 | IE | 2018-10-03 | 036909C-JVD-TRN-00122 | 036909C-JVD-TRN-00122 | IFI |  |  | Transmitted | TPSK-LSPA1-T-IE-00122 |  | z0
036909C-1000-JSD-6200-0001 | Environmental Protection Design Criteria | A | 2018-12-05 | IFR | OL1-2S08-0001 | ES | 2018-12-11 | 036909C-JVD-TRN-00473 | 036909C-JVD-TRN-00472, 036909C-JVD-TRN-00473 | IFR | 2018-12-27 |  | Transmitted | TPSK-LSPA1-T-ES-00473 |  | A
036909C-1000-RT-200 | Firefighting basic design report for package A1 | 0 | 2018-08-10 | IFI | OL1-2W90-0001 | PM | 2018-08-10 | 036909C-JVD-TRN-00020 | 036909C-JVD-TRN-00020 | IFI |  | 2018-08-20 | R2-Comments as noted | TPSK-LSPA1-T-PC-00020 |  | z0
036909C-1000-RT-200 | Fire Fighting Basic Design Report For Package A1 | 1 | 2018-09-28 | IFI | OL1-2W90-0001 | PC | 2018-10-17 | 036909C-JVD-TRN-00187 | 036909C-JVD-TRN-00187 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PM-00187 |  | z1
036909C-1000-NM-107 | Master Document Index (MDI) | 0 | 2018-10-16 | IFI | OL1-2W91-0001 | PC | 2018-10-17 | 036909C-JVD-TRN-00186 | 036909C-JVD-TRN-00186 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PM-00186 |  | z0
036909C-1000-NM-107 | Master Document Index (MDI) | 1 | 2018-11-21 | IFI | OL1-2W91-0001 | PC | 2018-11-23 | 036909C-JVD-TRN-00354 | 036909C-JVD-TRN-00354 | IFI |  |  | Transmitted | TPSK-LSPA1-T-PC-00354 |  | z1
036909C-1011-PDS-0117-1001 | Process Equipment Datasheet - USC 36M Cracking Furnace Yields | A | 2018-09-28 | IFR | OL1-4G30-1001 | PE | 2018-10-01 | 036909C-JVD-TRN-00117 | 036909C-JVD-TRN-00117 | IFR | 2018-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-00117 |  | A
036909C-1011-PDS-0630-1008 | See document number 036909C-1011-PDS-0630-1108 or OL1-2G30-1108 | A | 2018-09-17 | IFR | OL1-4G30-1008 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1011-PDS-0610-1009 | See document number 036909C-1011-PDS-0610-1109 or OL1-2G30-1109 | A | 2018-09-17 | IFR | OL1-4G30-1009 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1011-PDS-0610-1010 | See document number 036909C-1011-PDS-0610-1110 or OL1-2G30-1110 | A | 2018-09-17 | IFR | OL1-4G30-1010 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1011-PDS-1040-1011 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan | A | 2018-09-25 | IFR | OL1-4G30-1011 | PE | 2018-09-26 | 036909C-JVD-TRN-00090 | 036909C-JVD-TRN-00090 | IFR | 2018-10-10 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00090 |  | A
036909C-1012-PDS-0117-2001 | Process Equipment Datasheet - USC 132U Cracking Furnace Yields | A | 2018-09-28 | IFR | OL1-4G30-2001 | PE | 2018-10-01 | 036909C-JVD-TRN-00117 | 036909C-JVD-TRN-00117 | IFR | 2018-10-15 |  | Transmitted | TPSK-LSPA1-T-PE-00117 |  | A
036909C-1012-PDS-0630-2008 | See document number 036909C-1012-PDS-0630-1208 or OL1-2G30-1208 | A | 2018-09-17 | IFR | OL1-4G30-2008 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1012-PDS-0610-2009 | See document number 036909C-1012-PDS-0610-1209 or OL1-2G30-1209 | A | 2018-09-17 | IFR | OL1-4G30-2009 | PE | 2018-09-19 | 036909C-JVD-TRN-00066 | 036909C-JVD-TRN-00066 | IFR |  |  | Transmitted | TPSK-LSPA1-T-PE-00066 |  | A
036909C-1012-PDS-1040-2011 | Process Equipment Data sheet - 10-C-1200-1600 - USC 132U Induced Draft Fan | A | 2018-09-25 | IFR | OL1-4G30-2011 | PE | 2018-09-26 | 036909C-JVD-TRN-00090 | 036909C-JVD-TRN-00090 | IFR | 2018-10-10 | 2018-10-12 | R1-No comments | TPSK-LSPA1-T-PE-00090 |  | A
036909C-1012-MR-0127-2001 | Material Requisition for Convection Tubes | A | 2018-09-06 | IFQ | OL1-4M55-2001 | ME | 2018-09-12 | 036909C-JVD-TRN-00044 | 036909C-JVD-TRN-00044 | IFI |  |  | Transmitted | TPSK-LSPA1-T-ME-00044 |  | A
036909C-1012-JSS-0122-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces | A | 2018-09-10 | IFR | OL1-4M92-2001 | ME | 2018-09-10 | 036909C-JVD-TRN-00037 | 036909C-JVD-TRN-00037 | IFR | 2018-09-24 | 2018-09-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00037 |  | A
036909C-1012-JSS-0122-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces | A | 2018-09-10 | IFR | OL1-4M92-2002 | ME | 2018-09-10 | 036909C-JVD-TRN-00037 | 036909C-JVD-TRN-00037 | IFR | 2018-09-24 | 2018-09-25 | R2-Comments as noted | TPSK-LSPA1-T-ME-00037 |  | A
036909C-1012-JSS-0154-2007 | Project Specification For SLE and USX Exchangers | A | 2018-09-20 | IFR | OL1-4M92-2007 | ME | 2018-09-20 | 036909C-JVD-TRN-00067 | 036909C-JVD-TRN-00067 | IFR | 2018-10-04 | 2018-10-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00067 |  | A
036909C-1012-JSS-0154-2008 | Project Specification For Transfer Line Exchangers | A | 2018-09-20 | IFR | OL1-4M92-2008 | ME | 2018-09-20 | 036909C-JVD-TRN-00067 | 036909C-JVD-TRN-00067 | IFR | 2018-10-04 | 2018-10-12 | R2-Comments as noted | TPSK-LSPA1-T-ME-00067 |  | A
| VARIATION ORDER PROCEDURE |  |  |  | OL1-2A92-0001 | CO | [6 empty] | Transmitted
| CAR & THIRD PARTY INSURANCE CLAIM PROCEDURE |  |  |  | OL1-2A92-0002 | CO | [6 empty] | Transmitted
| PLANNING SCHEDULING AND PROGRESS MEASUREMENT PROCEDURE |  |  |  | OL1-2B92-0001 | PC | [6 empty] | Transmitted
| PROJECT PROCUREMENT EXECUTION PLAN |  |  |  | OL1-2C92-0001 | PL | [6 empty] | Transmitted
| PROJECT QCS COORDINATION PROCEDURE |  |  |  | OL1-2C92-0002 | PL | [6 empty] | Transmitted
| PROJECT QCS REQUIREMENTS FOR SUPPLIERS |  |  |  | OL1-2C92-0005 | PL | [6 empty] | Transmitted
| PRESCRIPTIONS FOR PREPARATION OF DOCUMENTATION PACKAGE FOR TRANSPORTATION |  |  |  | OL1-2C92-0007 | PL | [6 empty] | Transmitted
| PROJECT QCS EXPEDITING PROCEDURE |  |  |  | OL1-2C92-0008 | PL | [6 empty] | Transmitted
| PROJECT QCS INSPECTION PROCEDURE |  |  |  | OL1-2C92-0009 | PL | [6 empty] | Transmitted
| SPARE PARTS & SPECIAL TOOLS INSTRUCTIONS |  |  |  | OL1-2C92-0013 | PL | [6 empty] | Transmitted
| PROJECT EXPEDITING AND INSPECTION LEVEL DEFINITION |  |  |  | OL1-2C92-0014 | PL | [6 empty] | Transmitted
| TRANSPORTATION PLAN |  |  |  | OL1-2C92-0015 | PL | [6 empty] | Transmitted
| PARKING MARKING AND SHIPPING INSTRUCTIONS |  |  |  | OL1-2C92-0016 | PL | [6 empty] | Transmitted
| PROJECT SITE SERVICES CONDITIONS FOR SUPPLIER SPECIALISTS |  |  |  | OL1-2C92-0017 | PL | [6 empty] | Transmitted
| CONSTRUCTION SUBCONTRACTING PLAN |  |  |  | OL1-2D92-0001 | CM | [6 empty] | Transmitted
| ELECTRICAL BASIS OF FURNACE DETAILED DESIGN |  |  |  | OL1-2E01-2001 | EE | [6 empty] | Transmitted
| ELECTRICAL DRAWINGS LEGEND AND SYMBOLS |  |  |  | OL1-2E02-0001 | EE | [6 empty] | Transmitted
| TYPICAL INSTALLATION STANDARDS FOR ELECTRICAL EQUIPMENT |  |  |  | OL1-2E03-0035 | EE | [6 empty] | Transmitted
| MEDIUM VOLTAGE (> 1 KV, ≤ 52 KV) SWITCHBOARD SCHEDULE FOR SUBSTATION E |  |  |  | OL1-2E08-0001 | EE | [6 empty] | Transmitted
| MEDIUM VOLTAGE (> 1 KV, ≤ 52 KV) SWITCHBOARD SCHEDULE FOR SUBSTATION C |  |  |  | OL1-2E08-0002 | EE | [6 empty] | Transmitted
| LOW VOLTAGE (≤ 1 KV) SWITCHBOARD SCHEDULE FOR SUBSTATION E |  |  |  | OL1-2E08-0003 | EE | [6 empty] | Transmitted
| LOW VOLTAGE (≤ 1 KV) SWITCHBOARD SCHEDULE FOR SUBSTATION C |  |  |  | OL1-2E08-0004 | EE | [6 empty] | Transmitted
| LOW VOLTAGE (≤ 1 KV) SWITCHBOARD SCHEDULE FOR SATELLITE SUBSTATION |  |  |  | OL1-2E08-0005 | EE | [6 empty] | Transmitted
| ELECTRICAL CABLE SIZING CALCULATION NOTES |  |  |  | OL1-2E10-0001 | EE | [6 empty] | Transmitted
| ELECTRICAL POWER BALANCE |  |  |  | OL1-2E10-0002 | EE | [6 empty] | Transmitted
| LIGHTING SYSTEM CALCULATION NOTES |  |  |  | OL1-2E10-0003 | EE | [6 empty] | Transmitted
| SHORT CIRCUIT ANALYSIS |  |  |  | OL1-2E10-0004 | EE | [6 empty] | Transmitted
| LOAD FLOW AND VOLTAGE DROP ANALYSIS |  |  |  | OL1-2E10-0005 | EE | [6 empty] | Transmitted
| MOTOR STARTING ANALYSIS |  |  |  | OL1-2E10-0006 | EE | [6 empty] | Transmitted
| REACCELERATION STUDY |  |  |  | OL1-2E10-0007 | EE | [6 empty] | Transmitted
| HARMONIC ANALYSIS |  |  |  | OL1-2E10-0008 | EE | [6 empty] | Transmitted
| EMC STUDY |  |  |  | OL1-2E10-0009 | EE | [6 empty] | Transmitted
| ELECTRICAL RELIABILITY ANALYSIS |  |  |  | OL1-2E10-0010 | EE | [6 empty] | Transmitted
| INSULATION COORDINATION STUDY |  |  |  | OL1-2E10-0011 | EE | [6 empty] | Transmitted
| FLASH PROTECTION STUDY |  |  |  | OL1-2E11-0001 | EE | [6 empty] | Transmitted
| PROTECTIVE RELAY SELECTIVITY STUDY |  |  |  | OL1-2E12-0001 | EE | [6 empty] | Transmitted
| POWER FACTOR IMPROVEMENT SYSTEM SIZING |  |  |  | OL1-2E13-0001 | EE | [6 empty] | Transmitted
| AC UPS SYSTEM SIZING |  |  |  | OL1-2E13-0002 | EE | [6 empty] | Transmitted
| DC SYSTEM SIZING |  |  |  | OL1-2E13-0003 | EE | [6 empty] | Transmitted
| KEY SINGLE LINE DIAGRAM |  |  |  | OL1-2E14-0001 | EE | [6 empty] | Transmitted
| INTERLOCKING SYSTEM PHYLOSOPHY DRAWING |  |  |  | OL1-2E14-0002 | EE | [6 empty] | Transmitted
| SUBSTATION E SINGLE LINE DIAGRAM (N...) |  |  |  | OL1-2E14-0003 | EE | [6 empty] | Transmitted
| SUBSTATION C SINGLE LINE DIAGRAM (N...) |  |  |  | OL1-2E14-0004 | EE | [6 empty] | Transmitted
| SATELLITE SUBSTATION SINGLE LINE DIAGRAM (N...) |  |  |  | OL1-2E14-0005 | EE | [6 empty] | Transmitted
| PRELIMINARY SINGLE LINE DIAGRAM - OLEFINS UNIT |  |  |  | OL1-2E14-1001 | EE | [6 empty] | Transmitted
| PRELIMINARY ELECTRICAL LOAD SCHEDULE - OLEFINS UNIT |  |  |  | OL1-2E15-0001 | EE | [6 empty] | Transmitted
| ELECTRICAL EQUIPMENT LIST |  |  |  | OL1-2E15-0002 | EE | [6 empty] | Transmitted
| EX-EQUIPMENT REGISTER LIST |  |  |  | OL1-2E15-0003 | EE | [6 empty] | Transmitted
| ELECTRICAL CONSUMERS LIST |  |  |  | OL1-2E15-0004 | EE | [6 empty] | Transmitted
| LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  |  | OL1-2E15-1001 | EE | [6 empty] | Transmitted
| LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  |  | OL1-2E15-2001 | EE | [6 empty] | Transmitted
| LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  |  | OL1-2E15-3001 | EE | [6 empty] | Transmitted
| LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  |  | OL1-2E15-4001 | EE | [6 empty] | Transmitted
| LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  |  | OL1-2E15-5001 | EE | [6 empty] | Transmitted
| LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  |  | OL1-2E15-6001 | EE | [6 empty] | Transmitted
| PRELIMINARY MOTOR LIST - OLEFINS UNIT |  |  |  | OL1-2E17-1001 | EE | [6 empty] | Transmitted
| SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SUBSTATION E |  |  |  | OL1-2E18-0001 | EE | [6 empty] | Transmitted
| SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SUBSTATION C |  |  |  | OL1-2E18-0002 | EE | [6 empty] | Transmitted
| SUBSTATION MONITORING AND CONTROL SYSTEM BLOCK DIAGRAM FOR SATELLITE SUBSTATION |  |  |  | OL1-2E18-0003 | EE | [6 empty] | Transmitted
| MEDIUM VOLTAGE PROTECTION DIAGRAMS |  |  |  | OL1-2E19-0001 | EE | [6 empty] | Transmitted
| LOW VOLTAGE PROTECTION DIAGRAMS |  |  |  | OL1-2E19-0002 | EE | [6 empty] | Transmitted
| SUBSTATION E EQUIPMENT LAYOUT |  |  |  | OL1-2E20-0001 | EE | [6 empty] | Transmitted
| SUBSTATION C EQUIPMENT LAYOUT |  |  |  | OL1-2E20-0002 | EE | [6 empty] | Transmitted
| SATELLITE ELECTRICAL / INSTRUMENT EQUIPMENT LAYOUT |  |  |  | OL1-2E20-0003 | EE | [6 empty] | Transmitted
| SUBSTATION E CABLE ROUTING LAYOUT (N…) |  |  |  | OL1-2E22-0001 | EE | [6 empty] | Transmitted
| SUBSTATION C CABLE ROUTING LAYOUT (N…) |  |  |  | OL1-2E22-0002 | EE | [6 empty] | Transmitted
| SATELLITE SUBSTATION CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E22-0003 | EE | [6 empty] | Transmitted
| ELECTRICAL INTERCONNECTION WIRING LIST FOR SUBSTATION E |  |  |  | OL1-2E23-0001 | EE | [6 empty] | Transmitted
| ELECTRICAL INTERCONNECTION WIRING LIST FOR SUBSTATION C |  |  |  | OL1-2E23-0002 | EE | [6 empty] | Transmitted
| ELECTRICAL INTERCONNECTION WIRING LIST FOR SATELLITE SUBSTATION |  |  |  | OL1-2E23-0003 | EE | [6 empty] | Transmitted
| OVERALL ELECTRICAL MAIN CABLE ROUTING LAYOUT |  |  |  | OL1-2E31-0001 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0002 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0003 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0004 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0005 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0006 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0007 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0008 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0009 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0010 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0011 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0012 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0013 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0014 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0015 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0016 | EE | [6 empty] | Transmitted
| ELECTRICAL MAIN CABLE ROUTING LAYOUT (N...) |  |  |  | OL1-2E31-0017 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-1001 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-1002 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-1003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-2001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-2002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-2003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-3001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-3002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-3003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-4001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-4002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-4003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-5001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-5002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-5003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-6001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-6002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  |  | OL1-2E31-6003 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0001 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0002 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0003 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0004 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0005 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0006 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0007 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0008 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0009 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0010 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0011 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0012 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0013 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0014 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0015 | EE | [6 empty] | Transmitted
| POWER LAYOUT (N...) |  |  |  | OL1-2E32-0016 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1100 |  |  |  | OL1-2E32-1001 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-1002 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-1003 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-1004 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-1005 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  |  | OL1-2E32-1006 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E32-1007 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E32-1008 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1100 |  |  |  | OL1-2E32-1009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1200 |  |  |  | OL1-2E32-2001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-2002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-2003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-2004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-2005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  |  | OL1-2E32-2006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E32-2007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E32-2008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1200 |  |  |  | OL1-2E32-2009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1300 |  |  |  | OL1-2E32-3001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-3002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-3003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-3004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-3005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  |  | OL1-2E32-3006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E32-3007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E32-3008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1300 |  |  |  | OL1-2E32-3009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1400 |  |  |  | OL1-2E32-4001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-4002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-4003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-4004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-4005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  |  | OL1-2E32-4006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E32-4007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E32-4008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1400 |  |  |  | OL1-2E32-4009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1500 |  |  |  | OL1-2E32-5001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-5002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-5003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-5004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-5005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  |  | OL1-2E32-5006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E32-5007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E32-5008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1500 |  |  |  | OL1-2E32-5009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1600 |  |  |  | OL1-2E32-6001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-6002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-6003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-6004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  |  | OL1-2E32-6005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  |  | OL1-2E32-6006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E32-6007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E32-6008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1600 |  |  |  | OL1-2E32-6009 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0001 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0002 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0003 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0004 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0005 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0006 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0007 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0008 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0009 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0010 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0011 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0012 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0013 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0014 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0015 | EE | [6 empty] | Transmitted
| CABLE ROUTING CROSS SECTIONS (N...) |  |  |  | OL1-2E34-0016 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0001 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0002 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0003 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0004 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0005 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0006 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0007 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0008 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0009 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0010 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0011 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0012 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0013 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0014 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0015 | EE | [6 empty] | Transmitted
| WELDING AND RECEPTACLES PANEL SCHEDULE |  |  |  | OL1-2E35-0016 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0001 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0002 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0003 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0004 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0005 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0006 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0007 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0008 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0009 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0010 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0011 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0012 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0013 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0014 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0015 | EE | [6 empty] | Transmitted
| POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  |  | OL1-2E36-0016 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0001 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0002 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0003 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0004 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0005 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0006 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0007 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0008 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0009 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0010 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0011 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0012 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0013 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0014 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0015 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  |  | OL1-2E42-0016 | EE | [6 empty] | Transmitted
| USC 36M FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1100 |  |  |  | OL1-2E42-1001 | EE | [6 empty] | Transmitted
| USC 36M FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1100 |  |  |  | OL1-2E42-1002 | EE | [6 empty] | Transmitted
| USC 36M FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1100 |  |  |  | OL1-2E42-1003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1200 |  |  |  | OL1-2E42-2001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1200 |  |  |  | OL1-2E42-2002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1200 |  |  |  | OL1-2E42-2003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1300 |  |  |  | OL1-2E42-3001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1300 |  |  |  | OL1-2E42-3002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1300 |  |  |  | OL1-2E42-3003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1400 |  |  |  | OL1-2E42-4001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1400 |  |  |  | OL1-2E42-4002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1400 |  |  |  | OL1-2E42-4003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1500 |  |  |  | OL1-2E42-5001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1500 |  |  |  | OL1-2E42-5002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1500 |  |  |  | OL1-2E42-5003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1600 |  |  |  | OL1-2E42-6001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1600 |  |  |  | OL1-2E42-6002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1600 |  |  |  | OL1-2E42-6003 | EE | [6 empty] | Transmitted
| STREET LIGHTING SYSTEM LAYOUT |  |  |  | OL1-2E43-0001 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0005 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0006 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0007 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0008 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0009 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0010 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0011 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0012 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0013 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0014 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0015 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0016 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0017 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0018 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0019 | EE | [6 empty] | Transmitted
| LIGHTING LAYOUT (N...) |  |  |  | OL1-2E43-0020 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  |  | OL1-2E43-1001 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1100 |  |  |  | OL1-2E43-1002 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1003 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1004 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1005 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1006 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1007 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1008 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1009 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1010 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1011 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1012 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1013 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1014 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E43-1015 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  |  | OL1-2E43-2001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1200 |  |  |  | OL1-2E43-2002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2010 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2011 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2012 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2013 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2014 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2015 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2016 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E43-2017 | EE | [6 empty] | Transmitted
| ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  |  |  | OL1-2E43-2018 | EE | [6 empty] | Transmitted
| ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  |  |  | OL1-2E43-2019 | EE | [6 empty] | Transmitted
| ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  |  |  | OL1-2E43-2020 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  |  | OL1-2E43-3001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1300 |  |  |  | OL1-2E43-3002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3010 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3011 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3012 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3013 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3014 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3015 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3016 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E43-3017 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  |  | OL1-2E43-4001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1400 |  |  |  | OL1-2E43-4002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4010 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4011 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4012 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4013 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4014 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4015 | EE | [6 empty] | Transmitted
| ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  |  |  | OL1-2E43-4016 | EE | [6 empty] | Transmitted
| ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  |  |  | OL1-2E43-4017 | EE | [6 empty] | Transmitted
| ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  |  |  | OL1-2E43-4018 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4019 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E43-4020 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  |  | OL1-2E43-5001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1500 |  |  |  | OL1-2E43-5002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5010 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5011 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5012 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5013 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5014 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5015 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5016 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E43-5017 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  |  | OL1-2E43-6001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1600 |  |  |  | OL1-2E43-6002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6004 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6005 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6006 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6007 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6008 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6009 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6010 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6011 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6012 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6013 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6014 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6015 | EE | [6 empty] | Transmitted
| ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  |  |  | OL1-2E43-6016 | EE | [6 empty] | Transmitted
| ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  |  |  | OL1-2E43-6017 | EE | [6 empty] | Transmitted
| ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  |  |  | OL1-2E43-6018 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6019 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E43-6020 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0001 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0002 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0003 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0004 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0005 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0006 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0007 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0008 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0009 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0010 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0011 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0012 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0013 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0014 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0015 | EE | [6 empty] | Transmitted
| LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  |  | OL1-2E44-0016 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING SYSTEM CALCULATION |  |  |  | OL1-2E50-0001 | EE | [6 empty] | Transmitted
| OVERALL EARTHING LAYOUT |  |  |  | OL1-2E52-0001 | EE | [6 empty] | Transmitted
| OVERALL LIGHTNING PROTECTION LAYOUT |  |  |  | OL1-2E52-0002 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0003 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0004 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0005 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0006 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0007 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0008 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0009 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0010 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0011 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0012 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0013 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0014 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0015 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0016 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0017 | EE | [6 empty] | Transmitted
| EARTHING AND LIGHTNING PROTECTION LAYOUT (N...) |  |  |  | OL1-2E52-0018 | EE | [6 empty] | Transmitted
| SUBSTATION E EARTHING LAYOUT |  |  |  | OL1-2E52-0021 | EE | [6 empty] | Transmitted
| SUBSTATION C EARTHING LAYOUT |  |  |  | OL1-2E52-0022 | EE | [6 empty] | Transmitted
| SATELLITE SUBSTATION EARTHING LAYOUT |  |  |  | OL1-2E52-0023 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  |  | OL1-2E52-1001 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E52-1002 | EE | [6 empty] | Transmitted
| USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  |  |  | OL1-2E52-1003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  |  | OL1-2E52-2001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E52-2002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  |  |  | OL1-2E52-2003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  |  | OL1-2E52-3001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E52-3002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  |  |  | OL1-2E52-3003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  |  | OL1-2E52-4001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E52-4002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  |  |  | OL1-2E52-4003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  |  | OL1-2E52-5001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E52-5002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  |  |  | OL1-2E52-5003 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  |  | OL1-2E52-6001 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E52-6002 | EE | [6 empty] | Transmitted
| USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  |  |  | OL1-2E52-6003 | EE | [6 empty] | Transmitted
| MR SAFETY SUPERVISORY SYSTEM |  |  |  | OL1-2E55-0030 | EE | [6 empty] | Transmitted
| MR INTERCOM/PAGING / AUDIBLE ALARM SYSTEM |  |  |  | OL1-2E55-0031 | EE | [6 empty] | Transmitted
| MR EMERGENCY DIESEL GENERATOR |  |  |  | OL1-2E55-0117 | EE | [6 empty] | Transmitted
| MR FOR LV SWITCHGEARS AND LV BUS DUCTS (≤ 1 KV) |  |  |  | OL1-2E55-1200 | EE | [6 empty] | Transmitted
| MR FOR TRANSFORMERS |  |  |  | OL1-2E55-1500 | EE | [6 empty] | Transmitted
| MR FOR POWER CAPACITOR BANKS |  |  |  | OL1-2E55-1600 | EE | [6 empty] | Transmitted
| MR FOR MV VARIABLE FREQUENCY DRIVES |  |  |  | OL1-2E55-1700 | EE | [6 empty] | Transmitted
| MR FOR SMCS SYSTEM |  |  |  | OL1-2E55-1800 | EE | [6 empty] | Transmitted
| MR FOR AC AND DC UPS SYSTEMS |  |  |  | OL1-2E55-2000 | EE | [6 empty] | Transmitted
| MR FOR MV ELECTRIC MOTORS AND D/S |  |  |  | OL1-2E55-3100 | EE | [6 empty] | Transmitted
| MR FOR POWER AND LIGHTING DISTRIBUTION PANELS |  |  |  | OL1-2E55-5300 | EE | [6 empty] | Transmitted
| MR FOR CATHODIC PROTECTION SYSTEM |  |  |  | OL1-2E55-8000 | EE | [6 empty] | Transmitted
| MR FOR ELECTRICAL HEAT TRACING SYSTEM |  |  |  | OL1-2E55-8100 | EE | [6 empty] | Transmitted
| MR FOR ELECTRICAL CABLES |  |  |  | OL1-2E55-9000 | EE | [6 empty] | Transmitted
| MR FOR POWER MATERIALS |  |  |  | OL1-2E55-9200 | EE | [6 empty] | Transmitted
| MR FOR GROUNDING AND LIGHTNING MATERIAL |  |  |  | OL1-2E55-9300 | EE | [6 empty] | Transmitted
| MR FOR LIGHTING MATERIALS |  |  |  | OL1-2E55-9301 | EE | [6 empty] | Transmitted
| MR FOR CABLE TRAYS |  |  |  | OL1-2E55-9400 | EE | [6 empty] | Transmitted
| MR FOR CONDUITS |  |  |  | OL1-2E55-9500 | EE | [6 empty] | Transmitted
| ELECTRICAL CABLE DRUM SCHEDULE |  |  |  | OL1-2E60-0001 | EE | [6 empty] | Transmitted
| ELECTRICAL CABLE SCHEDULE |  |  |  | OL1-2E61-0001 | EE | [6 empty] | Transmitted
| TECHNICAL SPECIFICATION FOR ELECTRICAL INSTALLATION |  |  |  | OL1-2E63-0002 | EE | [6 empty] | Transmitted
| ELECTRICAL BULK MATERIAL |  |  |  | OL1-2E63-1001 | EE | [6 empty] | Transmitted
| ELECTRICAL BULK MATERIAL |  |  |  | OL1-2E63-2001 | EE | [6 empty] | Transmitted
| ELECTRICAL BULK MATERIAL |  |  |  | OL1-2E63-3001 | EE | [6 empty] | Transmitted
| ELECTRICAL BULK MATERIAL |  |  |  | OL1-2E63-4001 | EE | [6 empty] | Transmitted
| ELECTRICAL BULK MATERIAL |  |  |  | OL1-2E63-5001 | EE | [6 empty] | Transmitted
| ELECTRICAL BULK MATERIAL |  |  |  | OL1-2E63-6001 | EE | [6 empty] | Transmitted
| COORDINATION PROCEDURE FOR SMARTPLANT ELECTRICAL |  |  |  | OL1-2E92-0002 | EE | [6 empty] | Transmitted
| COORDINATION PROCEDURE FOR ETAP |  |  |  | OL1-2E92-0003 | EE | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT COMMON AREA |  |  |  | OL1-2F40-5001 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT METERING |  |  |  | OL1-2F40-5002 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT MAIN PIPE RACK |  |  |  | OL1-2F40-5003 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT AREA SUBSTATION E & FAR E |  |  |  | OL1-2F40-5004 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT AREA SUBSTATION C & FAR C |  |  |  | OL1-2F40-5005 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT FURNACES UTILITY |  |  |  | OL1-2F40-5006 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT QUENCH |  |  |  | OL1-2F40-5007 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT PROCESS 20B |  |  |  | OL1-2F40-5008 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT PROCESS 20C |  |  |  | OL1-2F40-5009 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT PROCESS COLD COMPRESSORS |  |  |  | OL1-2F40-5010 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT PROCESS CGC |  |  |  | OL1-2F40-5011 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT BUTADIENE |  |  |  | OL1-2F40-5012 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT COOLING WATER UNIT |  |  |  | OL1-2F40-5013 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT UTILITIES |  |  |  | OL1-2F40-5014 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT WASTE WATER TREATMENT |  |  |  | OL1-2F40-5015 | FF | [6 empty] | Transmitted
| FIRE & GAS DEVICES LAYOUT FLARE AREA |  |  |  | OL1-2F40-5016 | FF | [6 empty] | Transmitted
| FIRE AND GAS CAUSE & EFFECT CHART FAR-E SYSTEM |  |  |  | OL1-2F41-5001 | FF | [6 empty] | Transmitted
| FIRE AND GAS CAUSE & EFFECT CHART FAR-C SYSTEM |  |  |  | OL1-2F41-5002 | FF | [6 empty] | Transmitted
| FIRE AND GAS CAUSE & EFFECT CHART CCB SYSTEM |  |  |  | OL1-2F41-5003 | FF | [6 empty] | Transmitted
| FIRE&GAS DETECTION SYSTEMS SPECIFICATION |  |  |  | OL1-2F94-0001 | FF | [6 empty] | Transmitted
| SIZING OF STEAM DRUM & SUPERHEATER PSVS |  |  |  | OL1-2G05-1101 | PE | [6 empty] | Transmitted
| SIZING OF STEAM DRUM & SUPERHEATER PSVS |  |  |  | OL1-2G05-1301 | PE | [6 empty] | Transmitted
| SIZING OF STEAM DRUM & SUPERHEATER PSVS |  |  |  | OL1-2G05-1501 | PE | [6 empty] | Transmitted
| SIZING OF STEAM DRUM & SUPERHEATER PSVS |  |  |  | OL1-2G05-2101 | PE | [6 empty] | Transmitted
| SIZING OF STEAM DRUM & SUPERHEATER PSVS |  |  |  | OL1-2G05-4001 | PE | [6 empty] | Transmitted
| SIZING OF STEAM DRUM & SUPERHEATER PSVS |  |  |  | OL1-2G05-6001 | PE | [6 empty] | Transmitted
| HYDRAULICS |  |  |  | OL1-2G21-11XX | PE | [6 empty] | Transmitted
| HYDRAULICS |  |  |  | OL1-2G21-12XX | PE | [6 empty] | Transmitted
| HYDRAULICS |  |  |  | OL1-2G21-13XX | PE | [6 empty] | Transmitted
| HYDRAULICS |  |  |  | OL1-2G21-14XX | PE | [6 empty] | Transmitted
| HYDRAULICS |  |  |  | OL1-2G21-15XX | PE | [6 empty] | Transmitted
| HYDRAULICS |  |  |  | OL1-2G21-16XX | PE | [6 empty] | Transmitted
| API FIRED HEATER DATA SHEET (36M FURNACE) |  |  |  | OL1-2G30-1105 | PE | [6 empty] | Transmitted
| USC 36M EFFLUENT MOV - DATA SHEET |  |  |  | OL1-2G30-1151 | PE | [6 empty] | Transmitted
| USC 36M DECOKE MOV - DATA SHEET |  |  |  | OL1-2G30-1152 | PE | [6 empty] | Transmitted
| USC 132SU EFFLUENT MOV - DATA SHEET |  |  |  | OL1-2G30-1251 | PE | [6 empty] | Transmitted
| USC 132SU DECOKE MOV - DATA SHEET |  |  |  | OL1-2G30-1252 | PE | [6 empty] | Transmitted
| AOCS PDS (132SU FURNACE) |  |  |  | OL1-2G30-1302 | PE | [6 empty] | Transmitted
| API FIRED HEATER DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-1305 | PE | [6 empty] | Transmitted
| BURNERS PDS (132SU FURNACE) |  |  |  | OL1-2G30-1306 | PE | [6 empty] | Transmitted
| STEAM DRUM PDS (132SU FURNACE) |  |  |  | OL1-2G30-1307 | PE | [6 empty] | Transmitted
| SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  |  |  | OL1-2G30-1308 | PE | [6 empty] | Transmitted
| TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  |  |  | OL1-2G30-1309 | PE | [6 empty] | Transmitted
| ID FAN DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-1311 | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-1312 | PE | [6 empty] | Transmitted
| MIXING TEE PDS (132SU FURNACE) |  |  |  | OL1-2G30-1313 | PE | [6 empty] | Transmitted
| USC 132SU EFFLUENT MOV - DATA SHEET |  |  |  | OL1-2G30-1351 | PE | [6 empty] | Transmitted
| USC 132SU DECOKE MOV - DATA SHEET |  |  |  | OL1-2G30-1352 | PE | [6 empty] | Transmitted
| BURNERS PDS (132SU FURNACE) |  |  |  | OL1-2G30-1406 | PE | [6 empty] | Transmitted
| STEAM DRUM PDS (132SU FURNACE) |  |  |  | OL1-2G30-1407 | PE | [6 empty] | Transmitted
| SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  |  |  | OL1-2G30-1408 | PE | [6 empty] | Transmitted
| TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  |  |  | OL1-2G30-1409 | PE | [6 empty] | Transmitted
| ID FAN DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-1411 | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-1412 | PE | [6 empty] | Transmitted
| MIXING TEE PDS (132SU FURNACE) |  |  |  | OL1-2G30-1413 | PE | [6 empty] | Transmitted
| USC 132SU EFFLUENT MOV - DATA SHEET |  |  |  | OL1-2G30-1451 | PE | [6 empty] | Transmitted
| USC 132SU DECOKE MOV - DATA SHEET |  |  |  | OL1-2G30-1452 | PE | [6 empty] | Transmitted
| BURNERS PDS (132SU FURNACE) |  |  |  | OL1-2G30-1506 | PE | [6 empty] | Transmitted
| STEAM DRUM PDS (132SU FURNACE) |  |  |  | OL1-2G30-1507 | PE | [6 empty] | Transmitted
| SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  |  |  | OL1-2G30-1508 | PE | [6 empty] | Transmitted
| TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  |  |  | OL1-2G30-1509 | PE | [6 empty] | Transmitted
| ID FAN DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-1511 | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-1512 | PE | [6 empty] | Transmitted
| MIXING TEE PDS (132SU FURNACE) |  |  |  | OL1-2G30-1513 | PE | [6 empty] | Transmitted
| USC 132SU EFFLUENT MOV - DATA SHEET |  |  |  | OL1-2G30-1551 | PE | [6 empty] | Transmitted
| USC 132SU DECOKE MOV - DATA SHEET |  |  |  | OL1-2G30-1552 | PE | [6 empty] | Transmitted
| BURNERS PDS (132SU FURNACE) |  |  |  | OL1-2G30-1606 | PE | [6 empty] | Transmitted
| STEAM DRUM PDS (132SU FURNACE) |  |  |  | OL1-2G30-1607 | PE | [6 empty] | Transmitted
| SLE QUENCH EXCHANGERS PDS (132SU FURNACE) |  |  |  | OL1-2G30-1608 | PE | [6 empty] | Transmitted
| TLX QUENCH EXCHANGER PDS (132SU FURNACE) |  |  |  | OL1-2G30-1609 | PE | [6 empty] | Transmitted
| ID FAN DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-1611 | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-1612 | PE | [6 empty] | Transmitted
| MIXING TEE PDS (132SU FURNACE) |  |  |  | OL1-2G30-1613 | PE | [6 empty] | Transmitted
| USC 132SU EFFLUENT MOV - DATA SHEET |  |  |  | OL1-2G30-1651 | PE | [6 empty] | Transmitted
| USC 132SU DECOKE MOV - DATA SHEET |  |  |  | OL1-2G30-1652 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-1910 - DMDS INJECTION PACKAGE |  |  |  | OL1-2G30-1910 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-1950 - DECOKE AIR RECEIVER |  |  |  | OL1-2G30-1951 | PE | [6 empty] | Transmitted
| AOCS PDS (132SU FURNACE) |  |  |  | OL1-2G30-2002 | PE | [6 empty] | Transmitted
| API FIRED HEATER DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-2005 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-F-2008 - QUENCH OIL FILTER |  |  |  | OL1-2G30-2007 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2008 - VLP STEAM GENERATORS |  |  |  | OL1-2G30-2008 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-F-2009 - QO PUMP PURGE OIL FILTER |  |  |  | OL1-2G30-2009 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-2090 - QUENCH OIL DRAIN SUMP EDUCTOR |  |  |  | OL1-2G30-2092 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2165 - DSG REBOILER COND POT |  |  |  | OL1-2G30-2164 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-2190 - QUENCH WATER DRAING SUMP EDUCTOR |  |  |  | OL1-2G30-2192 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2312 - SPENT WASH OIL DRUM |  |  |  | OL1-2G30-2312 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2316 - SPENT CAUSTIC DISCHARGE PUMP |  |  |  | OL1-2G30-2317 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-2322 - SKIM OIL SUMP EDUCTOR |  |  |  | OL1-2G30-2323 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND POT |  |  |  | OL1-2G30-2327 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND PUMP |  |  |  | OL1-2G30-2328 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-2390 - CAUSTIC DRAIN SUMP EDUCTOR |  |  |  | OL1-2G30-2389 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-2392 - SPENT CAUSTIC DRAIN SUMP EDUCTOR |  |  |  | OL1-2G30-2394 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2430 - REGEN GAS FEED HEATER |  |  |  | OL1-2G30-2430 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2432 - REGEN GAS SHP HEATER |  |  |  | OL1-2G30-2432 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2435 - REGEN GAS EFFLUENT COOLER |  |  |  | OL1-2G30-2434 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2435 - REGEN GAS SEPARATOR |  |  |  | OL1-2G30-2435 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2436 - MERCURY ADSORBER |  |  |  | OL1-2G30-2436 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2465 - C2 HYDROG FEED HEATER COND POT |  |  |  | OL1-2G30-2466 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2465 - C2 HYDROG FEED HEATER COND PUMP |  |  |  | OL1-2G30-2467 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-R-2620 - C3 HYDROG REACTOR |  |  |  | OL1-2G30-2620 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2620 - C3 HYDROG AFTERCOOLER |  |  |  | OL1-2G30-2621 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2620 - C3 HYDROG RECYCLE DRUM |  |  |  | OL1-2G30-2622 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2620 - C3 HYDROG RECYCLE PUMPS |  |  |  | OL1-2G30-2623 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2645 - C3 TOWER REBOILER COND POT |  |  |  | OL1-2G30-2644 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2666 - C5 / PYGAS SURGE DRUM |  |  |  | OL1-2G30-2667 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2666 - C5 / PYGAS PUMPS |  |  |  | OL1-2G30-2668 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-R-2700 - GHU-1 REACTOR |  |  |  | OL1-2G30-2700 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2701 - GHU-1 FEED / EFFLUENT EXCHANGERS |  |  |  | OL1-2G30-2701 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2702 - GHU-1 S/U HEATER |  |  |  | OL1-2G30-2702 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2705 - GHU-1 RECYCLE COOLER |  |  |  | OL1-2G30-2703 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2705 - GHU-1 RECYCLE PUMPS |  |  |  | OL1-2G30-2704 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2705 - GHU-1 HOT SEPARATOR |  |  |  | OL1-2G30-2705 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2706 - GHU-1 COLD SEPARATOR |  |  |  | OL1-2G30-2706 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2706 - GHU-1 COOLER |  |  |  | OL1-2G30-2707 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-2710 - DEPENTANIZER |  |  |  | OL1-2G30-2710 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2710 -DEPENTANIZER CONDENSER |  |  |  | OL1-2G30-2711 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2710 - DEPENTANIZER REFLUX DRUM |  |  |  | OL1-2G30-2712 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2710 - DEPENTANIZER REFLUX PUMPS |  |  |  | OL1-2G30-2713 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2714 - C5 CUT PUMPS |  |  |  | OL1-2G30-2714 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2715 - DEPENTANIZER REBOILER |  |  |  | OL1-2G30-2715 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2714 - C5 CUT COOLER |  |  |  | OL1-2G30-2716 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2720 - RERUN TOWER EDUCTOR PKG |  |  |  | OL1-2G30-2717 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2720 - RERUN TOWER REFLUX DRUM |  |  |  | OL1-2G30-2718 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2720 - RERUN TOWER REFLUX / PRODUCT PUMPS |  |  |  | OL1-2G30-2719 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-2720 - RERUN TOWER |  |  |  | OL1-2G30-2720 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2720 - RERUN TOWER CONDENSER |  |  |  | OL1-2G30-2721 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2722 - GHU-1 PRODUCT COOLER |  |  |  | OL1-2G30-2722 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2724 - WASH OIL CONDENSER |  |  |  | OL1-2G30-2723 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2724 - WASH OIL DEGASSING DRUM |  |  |  | OL1-2G30-2724 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2725 - RERUN TOWER REBOILER |  |  |  | OL1-2G30-2725 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2726 - PYGAS FUEL OIL PUMPS |  |  |  | OL1-2G30-2726 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2726 - PYGAS FUEL OIL COOLER |  |  |  | OL1-2G30-2727 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2724 - RECYCLE WASH OIL PUMPS |  |  |  | OL1-2G30-2728 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2730 - HYDROG REGEN HEATER |  |  |  | OL1-2G30-2730 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2735 - REGEN HYDROG DRUM |  |  |  | OL1-2G30-2735 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2750 - C4 / C5 HYDROG SURGE DRUM |  |  |  | OL1-2G30-2750 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2750 - C4 / C5 HYDROG FEED PUMPS |  |  |  | OL1-2G30-2751 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-X-2755 - C4 / C5 HYDROG MIXER |  |  |  | OL1-2G30-2754 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2755 - C4 / C5 HYDROG S/U HEATER |  |  |  | OL1-2G30-2755 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-R-2760 - C4 / C5 HYDROG REACTOR |  |  |  | OL1-2G30-2760 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2761 - C4 / C5 HYDROG VENT CHILLER |  |  |  | OL1-2G30-2761 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-2760 - C4 / C5 HYDROG RECYCLE DRUM |  |  |  | OL1-2G30-2762 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2760 - C4 / C5 HYDROG VENT CONDENSER |  |  |  | OL1-2G30-2763 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2760 - C4 / C5 HYDROG RECYCLE PUMPS |  |  |  | OL1-2G30-2764 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-2765 - C4 / C5 HYDROG RECYCLE COOLER |  |  |  | OL1-2G30-2765 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2790 - LIGHT OIL DRAIN DRUM PUMP |  |  |  | OL1-2G30-2791 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-2790 - LIGHT OIL DRAIN SUMP EDUCTOR |  |  |  | OL1-2G30-2792 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2900 - PH CTRL / CORROSION INHIBITOR INJ PKG |  |  |  | OL1-2G30-2900 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2902 - EMULSION BREAKER INJ PKG |  |  |  | OL1-2G30-2902 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2904 - WATER STRIPPER CHEMICAL INJ PKG |  |  |  | OL1-2G30-2904 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2906 - DSG ANTI-FOULANT INJ PKG |  |  |  | OL1-2G30-2906 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-TK-2910 - WASH OIL DAY TANK |  |  |  | OL1-2G30-2910 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-2910 - WASH OIL INJECTION PUMP |  |  |  | OL1-2G30-2911 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2912 - CAUSTIC TOWER ANTI-FOULANT INJ PKG |  |  |  | OL1-2G30-2912 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2920 - POLYMERIZATION INHIBITOR INJ PKG |  |  |  | OL1-2G30-2920 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2922 - CO INJECTION PACKAGE |  |  |  | OL1-2G30-2922 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2930 - METHANOL INJECTION PKG |  |  |  | OL1-2G30-2930 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-2940 - C4 POLYMER INHIBITOR INJECTION PKG |  |  |  | OL1-2G30-2940 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3000 - PREDISTILLATION TOWER |  |  |  | OL1-2G30-3000 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3000 - PREDISTILLATION CONDENSER |  |  |  | OL1-2G30-3001 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3002 - PREDISTILLATION FEED PUMP |  |  |  | OL1-2G30-3002 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3000 - PREDISTILLATION REFLUX PUMP |  |  |  | OL1-2G30-3003 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3004 - PREDISTILLATION TRIM REBOILER |  |  |  | OL1-2G30-3004 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3005 - PREDISTILLATION REBOILER |  |  |  | OL1-2G30-3005 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3000 - PREDISTILLATION REFLUX DRUM |  |  |  | OL1-2G30-3006 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3002 - PREDISTILLATION FEED DRUM |  |  |  | OL1-2G30-3007 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3010 - C4 FEED DRUM |  |  |  | OL1-2G30-3010 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3014 - C4 SOLVENT VAPORIZER |  |  |  | OL1-2G30-3014 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3015 - C4 VAPORIZER |  |  |  | OL1-2G30-3015 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3016 - HEAVY END DISCHARGE PUMP |  |  |  | OL1-2G30-3016 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3018 - SOLVENT COOLER |  |  |  | OL1-2G30-3018 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3020 - MAIN WASHER |  |  |  | OL1-2G30-3020 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3020 - MAIN WASHER REFLUX DRUM |  |  |  | OL1-2G30-3021 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3020 - MAIN WASHER REFLUX PUMP |  |  |  | OL1-2G30-3022 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3020 - MAIN WASHER CONDENSER |  |  |  | OL1-2G30-3023 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3026 - MAIN WASHER BOTTOM PUMP |  |  |  | OL1-2G30-3026 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3030 - AFTER WASHER |  |  |  | OL1-2G30-3030 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3030 - AFTER WASHER CONDENSER |  |  |  | OL1-2G30-3031 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3030 - AFTER WASHER REFLUX PUMP |  |  |  | OL1-2G30-3032 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3030 - AFTER WASHER REFLUX DRUM |  |  |  | OL1-2G30-3033 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3036 - AFTER WASHER BOTTOM PUMP |  |  |  | OL1-2G30-3036 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3040 - RECTIFIER |  |  |  | OL1-2G30-3040 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3044 - SOLVENT HEATER |  |  |  | OL1-2G30-3044 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3045 - SOLVENT HEAT EXCHANGER |  |  |  | OL1-2G30-3045 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3046 - DEGASSER FEED PUMP |  |  |  | OL1-2G30-3046 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3045 - RECTIFIER PUMPS |  |  |  | OL1-2G30-3047 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3050 - DEGASSER |  |  |  | OL1-2G30-3050 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3055 - DEGASSER REBOILER |  |  |  | OL1-2G30-3055 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3056 - DEGASSER BOTTOM PUMP |  |  |  | OL1-2G30-3056 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3060 - ACETYLENE WASHER |  |  |  | OL1-2G30-3060 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3060 - ACETYLENE WASHER CONDENSER |  |  |  | OL1-2G30-3061 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3062 - ACETYLENE CONDENSER |  |  |  | OL1-2G30-3062 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3060 - WWASTE WATER PUMP |  |  |  | OL1-2G30-3063 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3062 - C4 ACETYLENE PUMP |  |  |  | OL1-2G30-3064 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3061 - WASTE HC PUMP |  |  |  | OL1-2G30-3065 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3062 - ACETYLENE ACCUMULATOR |  |  |  | OL1-2G30-3066 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3060 - C4 FEED DRUM |  |  |  | OL1-2G30-3067 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3070 - DIRECT COOLER |  |  |  | OL1-2G30-3070 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-C-3070 - RECYCLE GAS COMPRESSOR |  |  |  | OL1-2G30-3071 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-3070 - RECYCLE GAS STEAM EJECTOR |  |  |  | OL1-2G30-3072 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3076 - DIRECT COOLER PUMP |  |  |  | OL1-2G30-3076 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3080 - BUTADIENE TOWER |  |  |  | OL1-2G30-3080 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3080 - BUTADIENE TOWER REFLUX DRUM |  |  |  | OL1-2G30-3081 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3080 - BUTADIENE TOWER CONDENSER |  |  |  | OL1-2G30-3082 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3084 - BUTADIENE TOWER TRIM REBOILER |  |  |  | OL1-2G30-3084 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3085 - BUTADIENE TOWER REBOILER |  |  |  | OL1-2G30-3085 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3086 - C4 / C5 HC PUMP |  |  |  | OL1-2G30-3086 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3080 - BUTADIENE TOWER REFLUX PUMPS |  |  |  | OL1-2G30-3087 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3090 - BUTADIENE DRYING TOWER |  |  |  | OL1-2G30-3090 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3095 - BUTADIENE DRYING TOWER REBOILER |  |  |  | OL1-2G30-3095 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3096 - BUTADIENE PRODUCT COOLER |  |  |  | OL1-2G30-3096 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3096 - BUTADIENE PRODUCT PUMPS |  |  |  | OL1-2G30-3097 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3098 - BUTADIENE PRODUCT SUBCOOLER |  |  |  | OL1-2G30-3098 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3100 - SOLVENT REGEN DRUM |  |  |  | OL1-2G30-3100 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-A-3100 - SOLVENT REGEN AGITATOR |  |  |  | OL1-2G30-3101 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-T-3110 - WATER WASHER |  |  |  | OL1-2G30-3110 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3110 - WATER WASHER ACCUMULATOR |  |  |  | OL1-2G30-3111 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3110 - WATER WASHER CONDENSER |  |  |  | OL1-2G30-3112 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3110 - SOLVENT RETURN PUMP |  |  |  | OL1-2G30-3113 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3120 - REGEN STEAM EJECTOR COOLER |  |  |  | OL1-2G30-3120 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-3121 - REGEN STEAM EJECTOR NO. 2 |  |  |  | OL1-2G30-3121 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-3120 - REGEN STEAM EJECTOR NO. 1 |  |  |  | OL1-2G30-3122 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-3120 - REGEN STEAM EJECTOR PKG |  |  |  | OL1-2G30-3123 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3126 - EJECTOR SEAL DRUM |  |  |  | OL1-2G30-3126 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3126 - WASTE WATER RETURN PUMPS |  |  |  | OL1-2G30-3127 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3150 - CONDENSATE HEATER |  |  |  | OL1-2G30-3150 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3150 - CONDENSATE FLASH DRUM |  |  |  | OL1-2G30-3151 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-3160 - CONDENSATE COOLER |  |  |  | OL1-2G30-3160 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3160 - CONDENSATE DRUM |  |  |  | OL1-2G30-3161 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3160 - CONDENSATE RECYCLE PUMP |  |  |  | OL1-2G30-3162 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3180 - BLOWDOWN DRUM |  |  |  | OL1-2G30-3180 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3190 - NMP SLOP DRUM |  |  |  | OL1-2G30-3190 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-EJ-3190 - NMP SLOP SUMP EDUCTOR |  |  |  | OL1-2G30-3191 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3190 - SOLVENT SLOP PUMP |  |  |  | OL1-2G30-3192 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-TK-3900 - NMP STORAGE TANK |  |  |  | OL1-2G30-3900 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3900 - NMP STORAGE PUMP |  |  |  | OL1-2G30-3901 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3902 - SOLVENT INHIBITOR DOSING PUMP |  |  |  | OL1-2G30-3902 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3902 - SOLVENT INHIBITOR DRUM |  |  |  | OL1-2G30-3903 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3904 - PRODUCT INHIBITOR DRUM |  |  |  | OL1-2G30-3904 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3904 - PRODUCT INHIBITOR DOSING PUMP |  |  |  | OL1-2G30-3905 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3906 - ANTI FOAM AGENT DRUM |  |  |  | OL1-2G30-3906 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3906 - ANTIFOAM DOSING PUMP |  |  |  | OL1-2G30-3907 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-3908 - PREDISTILLATION INHIBITOR DRUM |  |  |  | OL1-2G30-3908 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-3908 - PREDISTILLATION INHIBITOR DOSING PUMP |  |  |  | OL1-2G30-3909 | PE | [6 empty] | Transmitted
| AOCS PDS (132SU FURNACE) |  |  |  | OL1-2G30-4002 | PE | [6 empty] | Transmitted
| API FIRED HEATER DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-4005 | PE | [6 empty] | Transmitted
| AOCS PDS (132SU FURNACE) |  |  |  | OL1-2G30-5002 | PE | [6 empty] | Transmitted
| API FIRED HEATER DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-5005 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-5210 - PILOT GAS VAPORIZER COND POT |  |  |  | OL1-2G30-5211 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-5220 - PILOT GAS SUPERHEATER |  |  |  | OL1-2G30-5220 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5351 - OLEFINS CW PUMPS SUMP |  |  |  | OL1-2G30-5351 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5360 - CTU CW PUMPS SUMP |  |  |  | OL1-2G30-5360 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5370 - CW FILTER BACKWASH SUMP |  |  |  | OL1-2G30-5370 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5370 - CW FILTER BACKWASH PUMPS |  |  |  | OL1-2G30-5371 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-5398 - 98% SULFURIC ACID INJ PKG |  |  |  | OL1-2G30-5398 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5500 - HOT BLOWDOWN PUMPS |  |  |  | OL1-2G30-5501 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-5510 - COLD FLARE BLOWDOWN VAPORIZER |  |  |  | OL1-2G30-5511 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-5512 - COLD FLARE SUPERHEATER |  |  |  | OL1-2G30-5512 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-5513 - METHANOL VAPORIZER |  |  |  | OL1-2G30-5513 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-5513 - METHANOL VAPROIZER COND POT |  |  |  | OL1-2G30-5514 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-5515 - METHANOL MAKE-UP DRUM |  |  |  | OL1-2G30-5515 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5550 - HP FLARE KNOCK OUT DRUM PUMPS |  |  |  | OL1-2G30-5551 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-E-5552 - LPG VAPORIZER / SUPERHEATER |  |  |  | OL1-2G30-5553 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5552 - LPG UNLOADING PUMP |  |  |  | OL1-2G30-5554 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-D-5565 - LLDPE LP FLARE KNOCK OUT DRUM |  |  |  | OL1-2G30-5565 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-5570 - ENCLOSED GROUND FLARE PACKAGE |  |  |  | OL1-2G30-5570 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5600 - PYGAS AREA OILY WASTEWATER SUMP |  |  |  | OL1-2G30-5600 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5601 - BUTADIENE AREA OILY WASTEWATER SUMP |  |  |  | OL1-2G30-5601 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5602 - QW AREA OILY WASTEWATER SUMP |  |  |  | OL1-2G30-5602 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5603 - CGC AREA OILY WASTEWATER SUMP |  |  |  | OL1-2G30-5603 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5604 - REFRIG AREA OILY WASTEWATER SUMP |  |  |  | OL1-2G30-5604 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5605 - FURNACE AREA OILY WASTEWATER SUMP |  |  |  | OL1-2G30-5605 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5600 - PYGAS AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2G30-5606 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5601 - BUTADIENE AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2G30-5607 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5602 - QW AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2G30-5608 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5603 - CGC AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2G30-5609 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5610 - HYDROBLAST SUMP |  |  |  | OL1-2G30-5610 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5610 - HYDROBLAST PUMPS |  |  |  | OL1-2G30-5611 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5604 - REFRIG AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2G30-5613 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5605 - FURNACE AREA OILY WATER PUMPS |  |  |  | OL1-2G30-5614 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5615 - OLEFINS STORMWATER SUMP |  |  |  | OL1-2G30-5615 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5615 - OLEFINS STORMWATER SUMP PUMPS |  |  |  | OL1-2G30-5616 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5620 - OLEFINS HOLDING BASIN |  |  |  | OL1-2G30-5620 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5621 - OLEFINS HOLDING BASIN SKIM OIL PUMPS |  |  |  | OL1-2G30-5621 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5620 - OLEFINS HOLDING BASIN PUMPS |  |  |  | OL1-2G30-5622 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-5625 - SANITARY LIFT STATION IFAR 1 |  |  |  | OL1-2G30-5625 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-5626 - SANITARY LIFT STATION IFAR 2 |  |  |  | OL1-2G30-5626 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-5627 - SANITARY LIFT STATION WEST GATE HOUSE |  |  |  | OL1-2G30-5627 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-5628 - SANITARY LIFT STATION EAST GATE HOUSE |  |  |  | OL1-2G30-5628 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5630 - CT AREA OILY WASTEWATER SUMP |  |  |  | OL1-2G30-5630 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5631 - CWWT AREA OILY WASTEWATER SUMP |  |  |  | OL1-2G30-5631 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5632 - HP FLARE AREA OILY WASTEWATER SUMP |  |  |  | OL1-2G30-5632 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5633 - HP FLARE AREA STORMWATER SUMP |  |  |  | OL1-2G30-5633 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5630 - CT AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2G30-5635 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5631 - CWWT AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2G30-5636 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5632 - HP FLARE AREA OILY WASTEWATER SUMP PUMPS |  |  |  | OL1-2G30-5637 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5633 - HP FLARE AREA STORMWATER SUMP PUMPS |  |  |  | OL1-2G30-5638 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-TK-5640 - OILY WASTEWATER EQUALIZATION TANKS |  |  |  | OL1-2G30-5640 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5641 - WASTEWATER EQ TANK SKIMMED OIL PUMP |  |  |  | OL1-2G30-5641 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5642 - COOLING WATER BLOWDOWN BASIS |  |  |  | OL1-2G30-5642 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5642 - COOLING WATER BD BASIN PUMPS |  |  |  | OL1-2G30-5643 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5640 - OILY WASTEWATER EQ TANK PUMPS |  |  |  | OL1-2G30-5645 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5655 - EQUALIZATION PIT PUMPS |  |  |  | OL1-2G30-5654 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5655 - EQUALIZATION PIT |  |  |  | OL1-2G30-5655 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5656 - FINAL CHECK BASIN |  |  |  | OL1-2G30-5656 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5656 - FINAL CHECK BASIN PUMPS |  |  |  | OL1-2G30-5657 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PIT-5658 - FINAL CHECK PIT |  |  |  | OL1-2G30-5658 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5675 - SLOP OIL TRANSFER PUMPS |  |  |  | OL1-2G30-5674 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-TK-5675 - SLOP OIL TANKS |  |  |  | OL1-2G30-5675 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-TK-5676 - OILY SLUDGE TANK |  |  |  | OL1-2G30-5676 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5676 - OILY SLUDGE TRANSFER PUMPS |  |  |  | OL1-2G30-5677 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-5690 - SLOP TANK POLYMER INJECTION PKG |  |  |  | OL1-2G30-5690 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-PK-5692 - SLOP OIL TANK ACID INJECTION PKG |  |  |  | OL1-2G30-5692 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5900 - SULFURIC ACID PUMPS |  |  |  | OL1-2G30-5901 | PE | [6 empty] | Transmitted
| PROCESS EQUIPMENT DATA SHEET - 10-P-5950 - SODIUM HYPOCHLORITE METERING PUMPS |  |  |  | OL1-2G30-5951 | PE | [6 empty] | Transmitted
| AOCS PDS (132SU FURNACE) |  |  |  | OL1-2G30-6002 | PE | [6 empty] | Transmitted
| API FIRED HEATER DATA SHEET (132SU FURNACE) |  |  |  | OL1-2G30-6005 | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET |  |  |  | OL1-2G31-1112 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE DATA SHEETS |  |  |  | OL1-2G31-11YY | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET |  |  |  | OL1-2G31-1212 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE DATA SHEETS |  |  |  | OL1-2G31-12YY | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET |  |  |  | OL1-2G31-1312 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE DATA SHEETS |  |  |  | OL1-2G31-13YY | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET |  |  |  | OL1-2G31-1412 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE DATA SHEETS |  |  |  | OL1-2G31-14YY | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET |  |  |  | OL1-2G31-1512 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE DATA SHEETS |  |  |  | OL1-2G31-15YY | PE | [6 empty] | Transmitted
| ATTEMPERATOR DATA SHEET |  |  |  | OL1-2G31-1612 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE DATA SHEETS |  |  |  | OL1-2G31-16YY | PE | [6 empty] | Transmitted
| AREA 30 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2G31-XXXA | PE | [6 empty] | Transmitted
| AREA 53 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2G31-XXXB | PE | [6 empty] | Transmitted
| AREA 55 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2G31-XXXC | PE | [6 empty] | Transmitted
| AREA 56 RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2G31-XXXD | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2G31-XXXX | PE | [6 empty] | Transmitted
| PRESSURE RELIEF VALVE DATA SHEETS |  |  |  | OL1-2G32-11XX | PE | [6 empty] | Transmitted
| PRESSURE RELIEF VALVE DATA SHEETS |  |  |  | OL1-2G32-12XX | PE | [6 empty] | Transmitted
| PRESSURE RELIEF VALVE DATA SHEETS |  |  |  | OL1-2G32-13XX | PE | [6 empty] | Transmitted
| PRESSURE RELIEF VALVE DATA SHEETS |  |  |  | OL1-2G32-14XX | PE | [6 empty] | Transmitted
| PRESSURE RELIEF VALVE DATA SHEETS |  |  |  | OL1-2G32-15XX | PE | [6 empty] | Transmitted
| PRESSURE RELIEF VALVE DATA SHEETS |  |  |  | OL1-2G32-16XX | PE | [6 empty] | Transmitted
| AREA 30 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2G32-XXXA | PE | [6 empty] | Transmitted
| AREA 53 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2G32-XXXB | PE | [6 empty] | Transmitted
| AREA 55 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2G32-XXXC | PE | [6 empty] | Transmitted
| AREA 56 PSV DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2G32-XXXD | PE | [6 empty] | Transmitted
| PSV DATA SHEETS & INDEX & INDEX, OLEFINS UNIT |  |  |  | OL1-2G32-XXXE | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION - FURNACE LIQUID FEED |  |  |  | OL1-2G43-1001 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION - FURNACE LPG FEED HEATER |  |  |  | OL1-2G43-1002 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION - FURNACE LPG FEED VAPORIZER |  |  |  | OL1-2G43-1003 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION - FURNACE LPG FEED SUPERHEATER |  |  |  | OL1-2G43-1004 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION - C2 FEED SUPERHEATER |  |  |  | OL1-2G43-1023 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION - SHEET 1 |  |  |  | OL1-2G43-1030 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION - SHEET 2 |  |  |  | OL1-2G43-1031 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION (UTILITY) - SHEET 1 |  |  |  | OL1-2G43-1035 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION - CRACKING FURNACE DISTRIBUTION (UTILITY) - SHEET 2 |  |  |  | OL1-2G43-1036 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 UTILITY STATION |  |  |  | OL1-2G43-1160 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1100 UTILITY DISTRIBUTION |  |  |  | OL1-2G43-1170 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 UTILITY STATION |  |  |  | OL1-2G43-1260 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1200 UTILITY DISTRIBUTION |  |  |  | OL1-2G43-1261 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 CONVECTION SECTION |  |  |  | OL1-2G43-1315 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 1 |  |  |  | OL1-2G43-1316 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 2 |  |  |  | OL1-2G43-1317 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 3 |  |  |  | OL1-2G43-1318 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 4 |  |  |  | OL1-2G43-1319 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 5 |  |  |  | OL1-2G43-1320 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 6 |  |  |  | OL1-2G43-1321 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 TLX EXCHANGER |  |  |  | OL1-2G43-1325 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 INTERMITTENT BLOWDOWN HEADER |  |  |  | OL1-2G43-1327 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 VHP STEAM DRUM |  |  |  | OL1-2G43-1328 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM DRUM-USX AND TLX RISERS |  |  |  | OL1-2G43-1329 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM COILS |  |  |  | OL1-2G43-1331 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 BURNERS |  |  |  | OL1-2G43-1340 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 DECOKING EFFLUENT |  |  |  | OL1-2G43-1345 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 FLUE GAS |  |  |  | OL1-2G43-1350 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY STATION |  |  |  | OL1-2G43-1360 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY DISTRIBUTION |  |  |  | OL1-2G43-1361 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 CONVECTION SECTION |  |  |  | OL1-2G43-1415 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 1 |  |  |  | OL1-2G43-1416 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 2 |  |  |  | OL1-2G43-1417 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 3 |  |  |  | OL1-2G43-1418 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 4 |  |  |  | OL1-2G43-1419 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 5 |  |  |  | OL1-2G43-1420 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 6 |  |  |  | OL1-2G43-1421 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 TLX EXCHANGER |  |  |  | OL1-2G43-1425 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 INTERMITTENT BLOWDOWN HEADER |  |  |  | OL1-2G43-1427 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 VHP STEAM DRUM |  |  |  | OL1-2G43-1428 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM DRUM-USX AND TLX RISERS |  |  |  | OL1-2G43-1429 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM COILS |  |  |  | OL1-2G43-1431 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 BURNERS |  |  |  | OL1-2G43-1440 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 DECOKING EFFLUENT |  |  |  | OL1-2G43-1445 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 FLUE GAS |  |  |  | OL1-2G43-1450 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY STATION |  |  |  | OL1-2G43-1460 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY DISTRIBUTION |  |  |  | OL1-2G43-1461 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 CONVECTION SECTION |  |  |  | OL1-2G43-1515 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 1 |  |  |  | OL1-2G43-1516 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 2 |  |  |  | OL1-2G43-1517 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 3 |  |  |  | OL1-2G43-1518 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 4 |  |  |  | OL1-2G43-1519 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 5 |  |  |  | OL1-2G43-1520 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 6 |  |  |  | OL1-2G43-1521 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 TLX EXCHANGER |  |  |  | OL1-2G43-1525 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 INTERMITTENT BLOWDOWN HEADER |  |  |  | OL1-2G43-1527 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 VHP STEAM DRUM |  |  |  | OL1-2G43-1528 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM DRUM-USX AND TLX RISERS |  |  |  | OL1-2G43-1529 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM COILS |  |  |  | OL1-2G43-1531 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 BURNERS |  |  |  | OL1-2G43-1540 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 DECOKING EFFLUENT |  |  |  | OL1-2G43-1545 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 FLUE GAS |  |  |  | OL1-2G43-1550 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY STATION |  |  |  | OL1-2G43-1560 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY DISTRIBUTION |  |  |  | OL1-2G43-1561 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 CONVECTION SECTION |  |  |  | OL1-2G43-1615 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 1 |  |  |  | OL1-2G43-1616 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 2 |  |  |  | OL1-2G43-1617 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 3 |  |  |  | OL1-2G43-1618 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 4 |  |  |  | OL1-2G43-1619 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 5 |  |  |  | OL1-2G43-1620 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 6 |  |  |  | OL1-2G43-1621 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 TLX EXCHANGER |  |  |  | OL1-2G43-1625 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 INTERMITTENT BLOWDOWN HEADER |  |  |  | OL1-2G43-1627 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 VHP STEAM DRUM |  |  |  | OL1-2G43-1628 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM DRUM-USX AND TLX RISERS |  |  |  | OL1-2G43-1629 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM COILS |  |  |  | OL1-2G43-1631 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 BURNERS |  |  |  | OL1-2G43-1640 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 DECOKING EFFLUENT |  |  |  | OL1-2G43-1645 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 FLUE GAS |  |  |  | OL1-2G43-1650 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY STATION |  |  |  | OL1-2G43-1660 | PE | [6 empty] | Transmitted
| PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY DISTRIBUTION |  |  |  | OL1-2G43-1661 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION & FURNACES AUX - DMDS INJECTION SYSTEM |  |  |  | OL1-2G43-1901 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION & FURNACES AUX - DECOKE COMPRESSOR - SHEET 1 |  |  |  | OL1-2G43-1910 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION & FURNACES AUX - DECOKE COMPRESSOR - SHEET 2 |  |  |  | OL1-2G43-1911 | PE | [6 empty] | Transmitted
| P&ID - FEED PREPARATION & FURNACES AUX - DECOKE AIR RECEIVER |  |  |  | OL1-2G43-1915 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - QUENCH OIL FRACTIONATOR |  |  |  | OL1-2G43-2001 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - QUENCH OIL CIRCULATING PUMPS |  |  |  | OL1-2G43-2003 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - QUENCH OIL FILTRATION |  |  |  | OL1-2G43-2005 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - VLP STEAM GENERATION - SHEET 1 |  |  |  | OL1-2G43-2006 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - VLP STEAM GENERATION - SHEET 2 |  |  |  | OL1-2G43-2007 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - LIGHT FUEL OIL STRIPPER |  |  |  | OL1-2G43-2020 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - FUEL OIL PRODUCT COOLING |  |  |  | OL1-2G43-2021 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - FUEL OIL FILTRATION |  |  |  | OL1-2G43-2022 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - HEAVY FUEL OIL STRIPPER |  |  |  | OL1-2G43-2025 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - HEAVY FUEL OIL PUMPS |  |  |  | OL1-2G43-2026 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL - HEAVY FUEL OIL PRODUCT COOLING |  |  |  | OL1-2G43-2027 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL DRAIN COLLECTION |  |  |  | OL1-2G43-2040 | PE | [6 empty] | Transmitted
| P&ID - QUENCH OIL DRAIN DRUM |  |  |  | OL1-2G43-2042 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER |  |  |  | OL1-2G43-2101 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER TOWER OVERHEAD |  |  |  | OL1-2G43-2102 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - QUENCH OIL FRACTIONATOR REFLUX |  |  |  | OL1-2G43-2104 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER PUMPS |  |  |  | OL1-2G43-2106 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DISTRIBUTION |  |  |  | OL1-2G43-2108 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER COOLING |  |  |  | OL1-2G43-2110 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DRAIN DISTRIBUTION |  |  |  | OL1-2G43-2115 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - QUENCH WATER DRAIN DRUM |  |  |  | OL1-2G43-2117 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DISTILLATE STRIPPER |  |  |  | OL1-2G43-2120 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DISTILLATE STRIPPER REBOILER |  |  |  | OL1-2G43-2122 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - PROCESS WATER STRIPPER FEED |  |  |  | OL1-2G43-2123 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - PROCESS WATER STRIPPER |  |  |  | OL1-2G43-2125 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - PRCOESS WATER STRIPPER REBOILER |  |  |  | OL1-2G43-2126 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR FEED PUMPS |  |  |  | OL1-2G43-2127 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR FEED HEATING |  |  |  | OL1-2G43-2130 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR |  |  |  | OL1-2G43-2131 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 1 |  |  |  | OL1-2G43-2132 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 2 |  |  |  | OL1-2G43-2133 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 3 |  |  |  | OL1-2G43-2134 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM GENERATOR REBOILERS - SHEET 4 |  |  |  | OL1-2G43-2135 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM SUPERHEATING |  |  |  | OL1-2G43-2137 | PE | [6 empty] | Transmitted
| P&ID - QUENCH WATER / DILUTION STEAM - DILUTION STEAM BLOWDOWN COOLING |  |  |  | OL1-2G43-2138 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS 1ST STAGE SUCTION DRUM |  |  |  | OL1-2G43-2201 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 1ST AND 2ND STAGES |  |  |  | OL1-2G43-2203 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 1ST STAGE AFTERCOOLING |  |  |  | OL1-2G43-2204 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 2ND STAGE SUCTION DRUM |  |  |  | OL1-2G43-2206 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 2ND STAGE AFTERCOOLING |  |  |  | OL1-2G43-2208 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD STAGE SUCTION DRUM |  |  |  | OL1-2G43-2210 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD AND 4TH STAGES |  |  |  | OL1-2G43-2211 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 3RD STAGE AFTERCOOLING |  |  |  | OL1-2G43-2212 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE SUCTION DRUM |  |  |  | OL1-2G43-2214 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE AFTERCOOLING |  |  |  | OL1-2G43-2215 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - CRACKED GAS COMPRESSOR 4TH STAGE DISCHARGE DRUM |  |  |  | OL1-2G43-2217 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - WASH WATER COOLER |  |  |  | OL1-2G43-2220 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - WASH WATER INJECTION |  |  |  | OL1-2G43-2222 | PE | [6 empty] | Transmitted
| P&ID - CRACKED GAS COMPRESSION - WASH OIL INJECTION |  |  |  | OL1-2G43-2224 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC TOWER |  |  |  | OL1-2G43-2301 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - WEAK/INTERMEDIATE CAUSTIC CIRCULATION |  |  |  | OL1-2G43-2303 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - STRONG CAUSTIC CIRCULATION |  |  |  | OL1-2G43-2305 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - FRESH CAUSTIC STORAGE |  |  |  | OL1-2G43-2310 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DEOILING |  |  |  | OL1-2G43-2311 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DEGASSING |  |  |  | OL1-2G43-2313 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT WASH OIL DRUM |  |  |  | OL1-2G43-2315 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - CAUSTIC DRAIN SUMP |  |  |  | OL1-2G43-2316 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC DRAIN SUMP |  |  |  | OL1-2G43-2318 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SKIM OIL DRUM |  |  |  | OL1-2G43-2319 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STORAGE |  |  |  | OL1-2G43-2320 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER FEED HEATING |  |  |  | OL1-2G43-2325 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER |  |  |  | OL1-2G43-2326 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - SPENT CAUSTIC STRIPPER OVERHEAD |  |  |  | OL1-2G43-2328 | PE | [6 empty] | Transmitted
| P&ID - CAUSTIC & SPENT CAUSTIC TREATMENT - WAO PACKAGE |  |  |  | OL1-2G43-2329 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CAUSTIC TOWER OVERHEAD CHILLING |  |  |  | OL1-2G43-2401 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CAUSTIC TOWER OVERHEAD KO DRUM |  |  |  | OL1-2G43-2402 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIER FEED COALESCER |  |  |  | OL1-2G43-2404 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIERS - SHEET 1 |  |  |  | OL1-2G43-2406 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LIQUID DRIERS - SHEET 2 |  |  |  | OL1-2G43-2407 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 1 |  |  |  | OL1-2G43-2409 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 2 |  |  |  | OL1-2G43-2410 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS DEHYDRATION - SHEET 3 |  |  |  | OL1-2G43-2411 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION GAS HEATING |  |  |  | OL1-2G43-2412 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - REGENERATION GAS COOLING |  |  |  | OL1-2G43-2414 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - FUEL GAS MERCURY ABSORBER |  |  |  | OL1-2G43-2416 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS MERCURY ABSORBER |  |  |  | OL1-2G43-2419 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER FEED CHILLING |  |  |  | OL1-2G43-2420 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER |  |  |  | OL1-2G43-2422 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REBOILER |  |  |  | OL1-2G43-2423 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER |  |  |  | OL1-2G43-2425 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER REBOILER |  |  |  | OL1-2G43-2426 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER OVERHEAD |  |  |  | OL1-2G43-2427 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - LP DEPROPANIZER PRODUCT/REFLUX PUMPS |  |  |  | OL1-2G43-2428 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - 5TH STAGE CRACKED GAS COMPRESSION |  |  |  | OL1-2G43-2430 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CRACKED GAS COMPRESSOR 5TH STAGE AFTERCOOLING |  |  |  | OL1-2G43-2432 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION FEED ARSINE REMOVAL |  |  |  | OL1-2G43-2433 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION FEED HEATING |  |  |  | OL1-2G43-2435 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR A |  |  |  | OL1-2G43-2437 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR A INTERCOOLING |  |  |  | OL1-2G43-2438 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR B |  |  |  | OL1-2G43-2439 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR B INTERCOOLING |  |  |  | OL1-2G43-2440 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - C2 HYDROGENATION REACTOR C |  |  |  | OL1-2G43-2442 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - CG SECONDARY DEHYDRATOR |  |  |  | OL1-2G43-2444 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REFLUX CHILLING |  |  |  | OL1-2G43-2446 | PE | [6 empty] | Transmitted
| P&ID - DEHYDRATION / REGEN / DEPROP / C2 HYDROG - HP DEPROPANIZER REFLUX |  |  |  | OL1-2G43-2447 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED CHILLING |  |  |  | OL1-2G43-2501 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 1 |  |  |  | OL1-2G43-2503 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 2 |  |  |  | OL1-2G43-2505 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR FEED SEPARATOR NO. 3 |  |  |  | OL1-2G43-2507 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR |  |  |  | OL1-2G43-2511 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER PREFRACTIONATOR REBOILER |  |  |  | OL1-2G43-2513 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - RESIDUE GAS RECTIFIER CONDENSER |  |  |  | OL1-2G43-2515 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - RESIDUE GAS RECTIFIER |  |  |  | OL1-2G43-2517 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER FEED COOLING |  |  |  | OL1-2G43-2520 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER |  |  |  | OL1-2G43-2521 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER REBOILER |  |  |  | OL1-2G43-2522 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - RESIDUE GAS EXPANDER SUCTION/DISCHARGE DRUMS |  |  |  | OL1-2G43-2525 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - RESIDUE GAS EXPANDER/RECOMPRESSOR |  |  |  | OL1-2G43-2527 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - HYDROGEN RECOVERY |  |  |  | OL1-2G43-2529 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - PROPYLENE REFRIGERANT SUBCOOLER SHEET 1 |  |  |  | OL1-2G43-2530 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - PROPYLENE REFRIGERANT SUBCOOLER SHEET 2 |  |  |  | OL1-2G43-2531 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - PRESSURE SWING ABSORPTION UNIT |  |  |  | OL1-2G43-2532 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEETHANIZER |  |  |  | OL1-2G43-2541 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEETHANIZER REBOILER |  |  |  | OL1-2G43-2543 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEETHANIZER CONDENSER |  |  |  | OL1-2G43-2546 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEETHANIZER OVERHEAD |  |  |  | OL1-2G43-2547 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - DEMETHANIZER BOTTOMS |  |  |  | OL1-2G43-2551 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - C2 SPLITTER |  |  |  | OL1-2G43-2552 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - C2 SPLITTER BOTTOMS REBOILER |  |  |  | OL1-2G43-2553 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - C2 SPLITTER INTER-REBOILER |  |  |  | OL1-2G43-2554 | PE | [6 empty] | Transmitted
| P&ID - COLD FRACTIONATION - ETHANE RECYCLE PUMPS |  |  |  | OL1-2G43-2556 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 HYDROGENATION ARSINE GUARD BED |  |  |  | OL1-2G43-2601 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 GUARD ADSORBERS - SHEET 1 |  |  |  | OL1-2G43-2602 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 GUARD ADSORBERS - SHEET 2 |  |  |  | OL1-2G43-2603 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 HYDROGENATION REACTORS - SHEET 1 |  |  |  | OL1-2G43-2605 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 HYDROGENATION REACTORS - SHEET 2 |  |  |  | OL1-2G43-2606 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 HYDROGENATION AFTERCOOLING |  |  |  | OL1-2G43-2608 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 HYDROGENATION RECYCLE |  |  |  | OL1-2G43-2610 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - SECONDARY DEETHANIZER |  |  |  | OL1-2G43-2615 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - SECONDARY DEETHANIZER OVERHEAD |  |  |  | OL1-2G43-2616 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 SPLITTER |  |  |  | OL1-2G43-2620 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 SPLITTER REBOILERS |  |  |  | OL1-2G43-2621 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C3 SPLITTER BOTTOMS |  |  |  | OL1-2G43-2622 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - DEBUTANIZER |  |  |  | OL1-2G43-2625 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - DEBUTANIZER OVERHEAD |  |  |  | OL1-2G43-2627 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - DEBUTANIZER OVERHEAD PRODUCT/REFLUX |  |  |  | OL1-2G43-2628 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - DEBUTANIZER BOTTOMS COOLING |  |  |  | OL1-2G43-2629 | PE | [6 empty] | Transmitted
| P&ID - HOT FRACTIONATION - C5/PYGAS SURGE DRUM |  |  |  | OL1-2G43-2630 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU-1 FEED HEATING |  |  |  | OL1-2G43-2701 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU-1 REACTORS - SHEET 1 |  |  |  | OL1-2G43-2702 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU-1 REACTORS - SHEET 2 |  |  |  | OL1-2G43-2703 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU-1 HOT SEPARATOR |  |  |  | OL1-2G43-2704 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU-1 COLD SEPARATOR |  |  |  | OL1-2G43-2705 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU-1 DEPENTANIZER |  |  |  | OL1-2G43-2706 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU C5 CUT PUMPS |  |  |  | OL1-2G43-2707 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU-1 DEPENTANIZER OVERHEAD |  |  |  | OL1-2G43-2708 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER |  |  |  | OL1-2G43-2710 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER CONDENSER |  |  |  | OL1-2G43-2711 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU RERUN TOWER REFLUX/PRODUCT PUMP |  |  |  | OL1-2G43-2712 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU-1 PRODUCT COOLING |  |  |  | OL1-2G43-2713 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - GHU-1 RECYCLE WASH OIL |  |  |  | OL1-2G43-2715 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - PYGAS FUEL OIL PRODUCT |  |  |  | OL1-2G43-2716 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - REACTIVATION GAS HEATING |  |  |  | OL1-2G43-2720 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - REGENERATION DECOKE DRUM |  |  |  | OL1-2G43-2722 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED SURGE DRUM |  |  |  | OL1-2G43-2730 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED PUMP |  |  |  | OL1-2G43-2732 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION FEED HEATING |  |  |  | OL1-2G43-2733 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION REACTOR |  |  |  | OL1-2G43-2734 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION RECYCLE DRUM |  |  |  | OL1-2G43-2736 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION VENT CHILLER |  |  |  | OL1-2G43-2737 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION RECYCLE/PRODUCT COOLING |  |  |  | OL1-2G43-2738 | PE | [6 empty] | Transmitted
| P&ID - GHU & C4/C5 HYDROG - LIGHT OIL DRAIN DRUM |  |  |  | OL1-2G43-2740 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT COMPRESSOR SHEET 1 |  |  |  | OL1-2G43-2801 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT COMPRESSOR SHEET 2 |  |  |  | OL1-2G43-2802 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT CONDENSER |  |  |  | OL1-2G43-2803 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT RECEIVER |  |  |  | OL1-2G43-2804 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - HP C3 REFRIGERATION DISTRIBUTION |  |  |  | OL1-2G43-2805 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT 4TH STAGE SUCTION |  |  |  | OL1-2G43-2806 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT 3RD STAGE SUCTION |  |  |  | OL1-2G43-2808 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT 2ND STAGE SUCTION |  |  |  | OL1-2G43-2810 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT 1ST STAGE SUCTION |  |  |  | OL1-2G43-2812 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT DRAIN DRUM |  |  |  | OL1-2G43-2814 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C3 REFRIGERANT DRAIN COLLECTION HEADER |  |  |  | OL1-2G43-2815 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - PROPYLENE PRODUCT PUMP |  |  |  | OL1-2G43-2816 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - PROPYLENE PRODUCT CHILLING SHEET 1 |  |  |  | OL1-2G43-2818 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - PROPYLENE PRODUCT CHILLING SHEET 2 |  |  |  | OL1-2G43-2819 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - ETHYLENE REFRIGERANT COMPRESSOR SHEET 1 |  |  |  | OL1-2G43-2821 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - ETHYLENE REFRIGERANT COMPRESSOR SHEET 2 |  |  |  | OL1-2G43-2822 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C2 REFRIGERANT DESUPERHEATERS |  |  |  | OL1-2G43-2824 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C2 REFRIGERANT DESUPERHEATERS AND CONDENSING |  |  |  | OL1-2G43-2825 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - ETHYLENE REFRIGERANT SURGE DRUM |  |  |  | OL1-2G43-2828 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - HP ETHYLENE LIQUID PRODUCT CHILLER |  |  |  | OL1-2G43-2830 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - HP ETHYLENE VAPOR PRODUCT |  |  |  | OL1-2G43-2834 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 3RD STAGE SUCTION |  |  |  | OL1-2G43-2836 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 2ND STAGE SUCTION |  |  |  | OL1-2G43-2838 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - ETHYLENE REFRIGERANT 1ST STAGE SUCTION |  |  |  | OL1-2G43-2840 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - LP ETHYLENE PRODUCT COOLING |  |  |  | OL1-2G43-2842 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - C2 REFRIGERANT DRAIN COLLECTION HEADER |  |  |  | OL1-2G43-2844 | PE | [6 empty] | Transmitted
| P&ID - REFRIGERATION - ETHYLENE REFRIGERANT DRAIN DRUM |  |  |  | OL1-2G43-2846 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - EMULSION BREAKER INJECTION SYSTEM |  |  |  | OL1-2G43-2901 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - PH CONTROL INJECTION SYSTEM |  |  |  | OL1-2G43-2902 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - POLYMERIZATION INHIBITOR INJECTION SYSTEM |  |  |  | OL1-2G43-2903 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - PROCESS WATER STRIPPER CHEMICAL INJECTION SYSTEM |  |  |  | OL1-2G43-2904 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - CORROSION INHIBITOR INJECTION SYSTEM |  |  |  | OL1-2G43-2905 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - DSG ANTI-FOULANT INJECTION SYSTEM |  |  |  | OL1-2G43-2906 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - WASH OIL STORAGE |  |  |  | OL1-2G43-2915 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - QUENCH OIL PUMP TURBINE DETAILS |  |  |  | OL1-2G43-2920 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - QUENCH WATER PUMP TURBINE DETAILS |  |  |  | OL1-2G43-2922 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - DSG FEED PUMP TURBINE DETAILS |  |  |  | OL1-2G43-2924 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 1 |  |  |  | OL1-2G43-2930 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 2 |  |  |  | OL1-2G43-2932 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - CG COMP. TURBINE DETAILS - SHEET 3 |  |  |  | OL1-2G43-2934 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - EXPANDER/RECOMPRESSOR AUXILIARIES - SHEET 1 |  |  |  | OL1-2G43-2950 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - EXPANDER/RECOMPRESSOR AUXILIARIES - SHEET 2 |  |  |  | OL1-2G43-2951 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - EXPANDER/RECOMPRESSOR AUXILIARIES - SHEET 3 |  |  |  | OL1-2G43-2952 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 1 |  |  |  | OL1-2G43-2955 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 2 |  |  |  | OL1-2G43-2960 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - C3 REFRIGERANT COMP. TURBINE DETAILS - SHEET 3 |  |  |  | OL1-2G43-2965 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - C2 REFRIGERANT COMP. TURBINE DETAILS - SHEET 1 |  |  |  | OL1-2G43-2970 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - C2 REFRIGERANT COMP. TURBINE DETAILS - SHEET 2 |  |  |  | OL1-2G43-2975 | PE | [6 empty] | Transmitted
| P&ID - OLEFINS RECOVERY AUXILLARY - GHU RERUN TOWER EJECTOR PACKAGE |  |  |  | OL1-2G43-2980 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - PREDISTILLATION FEED DRUM |  |  |  | OL1-2G43-3001 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - PREDISTILLATION FEED PUMPS |  |  |  | OL1-2G43-3002 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - PREDISTILLATION TOWER |  |  |  | OL1-2G43-3003 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - PREDISTILLATION TOWER REBOILERS |  |  |  | OL1-2G43-3004 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - PREDISTILLATION TOWER OVERHEAD |  |  |  | OL1-2G43-3006 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - FEED VAPORIZER DRUM |  |  |  | OL1-2G43-3008 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - C4 EVAPORATORS |  |  |  | OL1-2G43-3010 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - MAIN WASHER |  |  |  | OL1-2G43-3012 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - MAIN WASHER OVERHEAD |  |  |  | OL1-2G43-3014 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - RECTIFIER |  |  |  | OL1-2G43-3016 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - RECTIFIER BOTTOMS |  |  |  | OL1-2G43-3017 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - AFTERWASHER |  |  |  | OL1-2G43-3018 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - AFTERWASHER OVERHEAD |  |  |  | OL1-2G43-3020 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - SOLVENT HEAT EXCHANGERS |  |  |  | OL1-2G43-3021 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - SOLVENT HEATING |  |  |  | OL1-2G43-3022 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - SOLVENT COOLING/DEGASSING |  |  |  | OL1-2G43-3024 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - DEGASSING TOWER |  |  |  | OL1-2G43-3025 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - DEGASSING TOWER REBOILERS |  |  |  | OL1-2G43-3026 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - ACETYLENE WASHER |  |  |  | OL1-2G43-3027 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - ACETYLENE CONDENSING |  |  |  | OL1-2G43-3028 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - HC/WATER SEPARATOR |  |  |  | OL1-2G43-3029 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - RECYCLE GAS COMPRESSION |  |  |  | OL1-2G43-3030 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - BUTADIENE TOWER |  |  |  | OL1-2G43-3032 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - BUTADIENE TOWER REBOILERS |  |  |  | OL1-2G43-3033 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - BUTADIENE TOWER OVERHEAD |  |  |  | OL1-2G43-3035 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - BUTADIENE DRYING COLUMN |  |  |  | OL1-2G43-3037 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - BUTADIENE PRODUCT PUMPS |  |  |  | OL1-2G43-3038 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - SOLVENT RECOVERY |  |  |  | OL1-2G43-3050 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - SOLVENT REGENERATION |  |  |  | OL1-2G43-3051 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - SOLVENT CONDENSING |  |  |  | OL1-2G43-3053 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - WASH WATER ACCUMULATOR |  |  |  | OL1-2G43-3054 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - WASTE WATER RECOVERY |  |  |  | OL1-2G43-3055 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - CONDENSATE FLASH DRUM |  |  |  | OL1-2G43-3060 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - CONDENSATE RECYCLE |  |  |  | OL1-2G43-3061 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - SOLVENT STORAGE |  |  |  | OL1-2G43-3901 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - SOLVENT INHIBITOR INJECTION SYSTEM |  |  |  | OL1-2G43-3903 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - PRODUCT INHIBITOR INJECTION SYSTEM |  |  |  | OL1-2G43-3905 | PE | [6 empty] | Transmitted
| P&ID - C4 UNIT - ANTI-FOAM AGENT INJECTION SYSTEM |  |  |  | OL1-2G43-3907 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - DEMINERALIZATION |  |  |  | OL1-2G43-5001 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - POTABLE WATER |  |  |  | OL1-2G43-5020 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - STEAM LETDOWN STATIONS - SHEET 1 |  |  |  | OL1-2G43-5101 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - STEAM LETDOWN STATIONS - SHEET 2 |  |  |  | OL1-2G43-5102 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - DEAERATOR |  |  |  | OL1-2G43-5105 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SHP BOILER FEEDWATER PUMPS |  |  |  | OL1-2G43-5110 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - BOILER FEEDWATER PUMPS |  |  |  | OL1-2G43-5111 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SHP BOILER FEEDWATER DISTRIBUTION |  |  |  | OL1-2G43-5113 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - BOILER FEEDWATER DISTRIBUTION |  |  |  | OL1-2G43-5114 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SUSPECT CONDENSATE FLASH DRUM |  |  |  | OL1-2G43-5115 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SUSPECT CONDENSATE COOLING |  |  |  | OL1-2G43-5118 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - CONDENSATE CARBON FILTERS |  |  |  | OL1-2G43-5120 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - RAW CONDENSATE TANK |  |  |  | OL1-2G43-5125 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - CONDENSATE POLISHER |  |  |  | OL1-2G43-5127 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - CONDENSATE TANK |  |  |  | OL1-2G43-5130 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LOW PRESSURE CONDENSATE FLASH DRUM |  |  |  | OL1-2G43-5132 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - INTERMITTENT FURNACE BLOWDOWN DRUM |  |  |  | OL1-2G43-5134 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SHP STEAM DISTRIBUTION |  |  |  | OL1-2G43-5140 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HP STEAM DISTRIBUTION - SHEET 1 |  |  |  | OL1-2G43-5143 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HP STEAM DISTRIBUTION - SHEET 2 |  |  |  | OL1-2G43-5144 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 1 |  |  |  | OL1-2G43-5150 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 2 |  |  |  | OL1-2G43-5151 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - MP STEAM DISTRIBUTION - SHEET 3 |  |  |  | OL1-2G43-5152 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 1 |  |  |  | OL1-2G43-5160 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 2 |  |  |  | OL1-2G43-5161 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 3 |  |  |  | OL1-2G43-5162 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 4 |  |  |  | OL1-2G43-5163 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 5 |  |  |  | OL1-2G43-5164 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LP STEAM DISTRIBUTION - SHEET 6 |  |  |  | OL1-2G43-5165 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SHP/HP CONDENSATE COLLECTION |  |  |  | OL1-2G43-5170 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - MP CONDENSATE COLLECTION |  |  |  | OL1-2G43-5172 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LP CONDENSATE COLLECTION - SHEET 1 |  |  |  | OL1-2G43-5175 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LP CONDENSATE COLLECTION - SHEET 2 |  |  |  | OL1-2G43-5176 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - VLP CONDENSATE COLLECTION |  |  |  | OL1-2G43-5179 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - FUEL GAS SYSTEM |  |  |  | OL1-2G43-5201 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - PILOT GAS VAPORIZER AND SUPERHEATER |  |  |  | OL1-2G43-5203 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - FUEL GAS DISTRIBUTION - SHEET 1 |  |  |  | OL1-2G43-5210 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - FUEL GAS DISTRIBUTION - SHEET 2 |  |  |  | OL1-2G43-5211 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COOLING WATER DISTRIBUTION - SHEET 8 |  |  |  | OL1-2G43-5327 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 1 |  |  |  | OL1-2G43-5401 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 2 |  |  |  | OL1-2G43-5402 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 3 |  |  |  | OL1-2G43-5403 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - PLANT AIR DISTRIBUTION - SHEET 4 |  |  |  | OL1-2G43-5404 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - INSTRUMENT AIR RECEIVER |  |  |  | OL1-2G43-5410 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - INSTRUMENT AIR DISTRIBUTION - SHEET 1 |  |  |  | OL1-2G43-5411 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - INSTRUMENT AIR DISTRIBUTION - SHEET 2 |  |  |  | OL1-2G43-5412 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 1 |  |  |  | OL1-2G43-5420 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 2 |  |  |  | OL1-2G43-5421 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 3 |  |  |  | OL1-2G43-5422 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 4 |  |  |  | OL1-2G43-5423 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 5 |  |  |  | OL1-2G43-5424 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - NITROGEN DISTRIBUTION - SHEET 6 |  |  |  | OL1-2G43-5425 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HOT FLARE KO DRUM |  |  |  | OL1-2G43-5501 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COLD FLARE KO DRUM |  |  |  | OL1-2G43-5502 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 1 |  |  |  | OL1-2G43-5510 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 2 |  |  |  | OL1-2G43-5511 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 3 |  |  |  | OL1-2G43-5512 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 4 |  |  |  | OL1-2G43-5513 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 5 |  |  |  | OL1-2G43-5514 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - WET FLARE HEADER - SHEET 6 |  |  |  | OL1-2G43-5515 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 1 |  |  |  | OL1-2G43-5520 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 2 |  |  |  | OL1-2G43-5521 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 3 |  |  |  | OL1-2G43-5522 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COLD FLARE HEADER - SHEET 4 |  |  |  | OL1-2G43-5523 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - PROPYLENE BLOWDOWN HEADER - SHEET 1 |  |  |  | OL1-2G43-5526 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - PROPYLENE BLOWDOWN HEADER - SHEET 2 |  |  |  | OL1-2G43-5527 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 1 |  |  |  | OL1-2G43-5530 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 2 |  |  |  | OL1-2G43-5531 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 3 |  |  |  | OL1-2G43-5532 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HOT BLOWDOWN HEADER - SHEET 4 |  |  |  | OL1-2G43-5533 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 1 |  |  |  | OL1-2G43-5536 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 2 |  |  |  | OL1-2G43-5537 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 3 |  |  |  | OL1-2G43-5538 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COLD BLOWDOWN HEADER - SHEET 4 |  |  |  | OL1-2G43-5539 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - VOC VENT COLLECTION SYSTEM |  |  |  | OL1-2G43-5540 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HP FLARE KO DRUM |  |  |  | OL1-2G43-5551 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HP FLARE PILOT GAS |  |  |  | OL1-2G43-5553 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - HP FLARE |  |  |  | OL1-2G43-5555 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - ENCLOSED GROUND FLARE |  |  |  | OL1-2G43-5565 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - LLDPE FLARE |  |  |  | OL1-2G43-5575 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 1 |  |  |  | OL1-2G43-5601 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 2 |  |  |  | OL1-2G43-5602 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 3 |  |  |  | OL1-2G43-5603 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 4 |  |  |  | OL1-2G43-5604 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 5 |  |  |  | OL1-2G43-5605 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 6 |  |  |  | OL1-2G43-5606 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - ISBL OILY WATER COLLECTION - SHEET 7 |  |  |  | OL1-2G43-5607 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - OLEFINS STORM WATER COLLECTION |  |  |  | OL1-2G43-5620 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - OLEFINS HOLDING BASIN |  |  |  | OL1-2G43-5630 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SANITARY LIFT STATION - SHEET 1 |  |  |  | OL1-2G43-5640 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SANITARY LIFT STATION - SHEET 2 |  |  |  | OL1-2G43-5641 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 1 |  |  |  | OL1-2G43-5651 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 2 |  |  |  | OL1-2G43-5652 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - OSBL OILY WATER COLLECTION - SHEET 3 |  |  |  | OL1-2G43-5653 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COOLING WATER CHEMICAL INJECTION |  |  |  | OL1-2G43-5901 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COOLING WATER CORROSION INHIBITOR |  |  |  | OL1-2G43-5902 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - NEUTRALIZING AMINE INJECTION SYSTEM |  |  |  | OL1-2G43-5905 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - OXYGEN SCAVENGER INJECTION SYSTEM |  |  |  | OL1-2G43-5907 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - COOLING WATER SUPPLY PUMP TURBINES |  |  |  | OL1-2G43-5920 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SHP BFW PUMP TURBINE DETAILS |  |  |  | OL1-2G43-5925 | PE | [6 empty] | Transmitted
| P&ID - UTILITY SYSTEMS - SHP BFW LUBE OIL PUMP TURBINE DETAILS |  |  |  | OL1-2G43-5930 | PE | [6 empty] | Transmitted
| HEAT & MATERIAL BALANCE - AREA-55 (FLARE SYSTEM) |  |  |  | OL1-2G44-1012 | PE | [6 empty] | Transmitted
| HEAT & MATERIAL BALANCE - AREA-56 (WWT SYSTEM) |  |  |  | OL1-2G44-1013 | PE | [6 empty] | Transmitted
| SHUTDOWN INTERLOCK NARRATIVE (36M FURNACE) |  |  |  | OL1-2G50-1001 | PE | [6 empty] | Transmitted
| SHUTDOWN INTERLOCK NARRATIVE |  |  |  | OL1-2G50-2001 | PE | [6 empty] | Transmitted
| SHUTDOWN INTERLOCK NARRATIVE |  |  |  | OL1-2G50-3001 | PE | [6 empty] | Transmitted
| SHUTDOWN INTERLOCK NARRATIVE |  |  |  | OL1-2G50-4001 | PE | [6 empty] | Transmitted
| SHUTDOWN INTERLOCK NARRATIVE |  |  |  | OL1-2G50-5001 | PE | [6 empty] | Transmitted
| SHUTDOWN INTERLOCK NARRATIVE |  |  |  | OL1-2G50-6001 | PE | [6 empty] | Transmitted
| BATTERY LIMIT SUMMARY |  |  |  | OL1-2G60-0001 | PE | [6 empty] | Transmitted
| TIE-IN SUMMARY - FURNACE AREA 10-H-1100 |  |  |  | OL1-2G60-1101 | PE | [6 empty] | Transmitted
| TIE-IN SUMMARY - FURNACE AREA 10-H-1200 |  |  |  | OL1-2G60-1201 | PE | [6 empty] | Transmitted
| TIE-IN SUMMARY - FURNACE AREA 10-H-1300 |  |  |  | OL1-2G60-1301 | PE | [6 empty] | Transmitted
| TIE-IN SUMMARY - FURNACE AREA 10-H-1400 |  |  |  | OL1-2G60-1401 | PE | [6 empty] | Transmitted
| TIE-IN SUMMARY - FURNACE AREA 10-H-1500 |  |  |  | OL1-2G60-1501 | PE | [6 empty] | Transmitted
| TIE-IN SUMMARY - FURNACE AREA 10-H-1600 |  |  |  | OL1-2G60-1601 | PE | [6 empty] | Transmitted
| EQUIPMENT LIST - OLEFINS UNIT 10 |  |  |  | OL1-2G61-9001 | PE | [6 empty] | Transmitted
| OFF-DESIGN STEAM BALANCE - DESIGN CASES |  |  |  | OL1-2G62-1002 | PE | [6 empty] | Transmitted
| AIR & NITROGEN BALANCES |  |  |  | OL1-2G62-1010 | PE | [6 empty] | Transmitted
| ELECTRICAL LOAD SUMMARY |  |  |  | OL1-2G62-1011 | PE | [6 empty] | Transmitted
| EFFLUENT SUMMARY |  |  |  | OL1-2G63-1001 | PE | [6 empty] | Transmitted
| CATALYST & CHEMICAL SUMMARY |  |  |  | OL1-2G64-1001 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 REACTOR & DEPENTANIZER |  |  |  | OL1-2G74-2701 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - GHU-1 RERUN TOWER |  |  |  | OL1-2G74-2702 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - HYDROG REACTIVATION GAS SYSTEM |  |  |  | OL1-2G74-2703 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 27 GHU & C4/C5 HYDROG - C4/C5 HYDROGENATION |  |  |  | OL1-2G74-2704 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU PREDISTILLATION |  |  |  | OL1-2G74-3001 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU EVAPORATION |  |  |  | OL1-2G74-3002 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU RECTIFIER |  |  |  | OL1-2G74-3003 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU DEGASSING |  |  |  | OL1-2G74-3004 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 30 C4 UNIT - BDU FRACTIONATION |  |  |  | OL1-2G74-3005 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU SOLVENT REGENERATION |  |  |  | OL1-2G74-3101 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 31 C4 UNIT UTILITIES - BDU STEAM AND CONDENSATE SYSTEM |  |  |  | OL1-2G74-3102 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 39 C4 UNIT AUX - BDU CHEMICAL STORAGE |  |  |  | OL1-2G74-3901 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 50 WATER SYSTEMS - TREATED, POTABLE, AND DEMIN WATER SYSTEMS |  |  |  | OL1-2G74-5001 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - STEAM BALANCE DIAGRAM |  |  |  | OL1-2G74-5101 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE AND BOILER FEEDWATER SYSTEMS |  |  |  | OL1-2G74-5102 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - CONDENSATE TREATMENT SYSTEM |  |  |  | OL1-2G74-5103 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 51 BFW, STEAM, COND SYSTEMS - FURNACE BLOWDOWN SYSTEM |  |  |  | OL1-2G74-5104 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 52 FUEL SYSTEM - FUEL GAS SYSTEM |  |  |  | OL1-2G74-5201 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 54 AIR AND NITROGEN SYSTEM - PLANT AIR, INSTRUMENT AIR, AND NITROGEN SYSTEMS |  |  |  | OL1-2G74-5401 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - FLARE AND BLOWDOWN SYSTEM |  |  |  | OL1-2G74-5501 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - PROCESS VENT GAS COLLECTION |  |  |  | OL1-2G74-5502 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP FLARE |  |  |  | OL1-2G74-5511 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 55 VENT GAS AND FLARE SYSTEM - HP FLARE AREA |  |  |  | OL1-2G74-5512 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER COLLECTION |  |  |  | OL1-2G74-5601 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SURFACE RUNOFF COLLECTION |  |  |  | OL1-2G74-5602 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CRACKER HOLDING BASIN |  |  |  | OL1-2G74-5603 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - DOMESTIC WASTEWATER COLLECTION |  |  |  | OL1-2G74-5604 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OSBL OILY WASTEWATER COLLECTION |  |  |  | OL1-2G74-5611 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - OILY WASTEWATER EQUILIZATION TANK |  |  |  | OL1-2G74-5612 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CPI & IGF PACKAGES |  |  |  | OL1-2G74-5613 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - BIOTREATMENT PACKAGE |  |  |  | OL1-2G74-5614 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - CHECK BASIN |  |  |  | OL1-2G74-5615 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLUDGE DEWATERING PACKAGE |  |  |  | OL1-2G74-5616 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 56 WASTEWATER - SLOP AND OIL SLUDGE |  |  |  | OL1-2G74-5617 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - CHEMICAL STORAGE |  |  |  | OL1-2G74-5901 | PE | [6 empty] | Transmitted
| MATERIAL SELECTION DIAGRAM - OLEFINS UNIT 10 - 59 UTILITIES AUX - COMPLEX U & O CHEMICAL STORAGE |  |  |  | OL1-2G74-5911 | PE | [6 empty] | Transmitted
| BALANCE OF PLANT SUPERVISORY OPERATING MANUAL |  |  |  | OL1-2G76-1002 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 10 |  |  |  | OL1-2G91-1001 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 10 |  |  |  | OL1-2G91-1002 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 10 |  |  |  | OL1-2G91-1003 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX |  |  |  | OL1-2G91-1101 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX |  |  |  | OL1-2G91-1201 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX |  |  |  | OL1-2G91-1301 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX |  |  |  | OL1-2G91-1401 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX |  |  |  | OL1-2G91-1501 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX |  |  |  | OL1-2G91-1601 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 20 |  |  |  | OL1-2G91-2001 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 20 |  |  |  | OL1-2G91-2002 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 20 |  |  |  | OL1-2G91-2003 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 21 |  |  |  | OL1-2G91-2101 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 21 |  |  |  | OL1-2G91-2102 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 21 |  |  |  | OL1-2G91-2103 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 22 |  |  |  | OL1-2G91-2201 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 22 |  |  |  | OL1-2G91-2202 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 22 |  |  |  | OL1-2G91-2203 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 23 |  |  |  | OL1-2G91-2301 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 23 |  |  |  | OL1-2G91-2302 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 23 |  |  |  | OL1-2G91-2303 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 24 |  |  |  | OL1-2G91-2401 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 24 |  |  |  | OL1-2G91-2402 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 24 |  |  |  | OL1-2G91-2403 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 25 |  |  |  | OL1-2G91-2501 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 25 |  |  |  | OL1-2G91-2502 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 25 |  |  |  | OL1-2G91-2503 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 26 |  |  |  | OL1-2G91-2601 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 26 |  |  |  | OL1-2G91-2602 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 26 |  |  |  | OL1-2G91-2603 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 27 |  |  |  | OL1-2G91-2701 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 27 |  |  |  | OL1-2G91-2702 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 27 |  |  |  | OL1-2G91-2703 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 28 |  |  |  | OL1-2G91-2801 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 28 |  |  |  | OL1-2G91-2802 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 28 |  |  |  | OL1-2G91-2803 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 29 |  |  |  | OL1-2G91-2901 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 29 |  |  |  | OL1-2G91-2902 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 29 |  |  |  | OL1-2G91-2903 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS PROCESS AREA 30 |  |  |  | OL1-2G91-3001 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS PROCESS AREA 30 |  |  |  | OL1-2G91-3002 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS PROCESS AREA 30 |  |  |  | OL1-2G91-3003 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 50 |  |  |  | OL1-2G91-5001 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 50 |  |  |  | OL1-2G91-5002 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 50 |  |  |  | OL1-2G91-5003 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 53 |  |  |  | OL1-2G91-5301 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 53 |  |  |  | OL1-2G91-5302 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 53 |  |  |  | OL1-2G91-5303 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 55 |  |  |  | OL1-2G91-5501 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 55 |  |  |  | OL1-2G91-5502 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 55 |  |  |  | OL1-2G91-5503 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM INDEX - OLEFINS UTILITY AREA 56 |  |  |  | OL1-2G91-5601 | PE | [6 empty] | Transmitted
| PRESSURE SAFETY VALVE INDEX - OLEFINS UTILITY AREA 56 |  |  |  | OL1-2G91-5602 | PE | [6 empty] | Transmitted
| RESTRICTION ORIFICE INDEX - OLEFINS UTILITY AREA 56 |  |  |  | OL1-2G91-5603 | PE | [6 empty] | Transmitted
| JOB SUPPLY SPEC. FOR HVAC SYSTEMS |  |  |  | OL1-2H03-0002 | EE | [6 empty] | Transmitted
| HVAC THERMAL CALC. - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  |  |  | OL1-2H10-0001 | EE | [6 empty] | Transmitted
| HVAC THERMAL CALC. - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  |  |  | OL1-2H10-0002 | EE | [6 empty] | Transmitted
| HVAC THERMAL CALC. - GATEHOUSE |  |  |  | OL1-2H10-0003 | EE | [6 empty] | Transmitted
| HVAC THERMAL CALC. - OPERATION TOOL ROOM |  |  |  | OL1-2H10-0004 | EE | [6 empty] | Transmitted
| HVAC PROCESS FLOW DIAGRAM - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  |  |  | OL1-2H20-0001 | EE | [6 empty] | Transmitted
| HVAC PROCESS FLOW DIAGRAM - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  |  |  | OL1-2H20-0003 | EE | [6 empty] | Transmitted
| HVAC PROCESS FLOW DIAGRAM - GATEHOUSE |  |  |  | OL1-2H20-0005 | EE | [6 empty] | Transmitted
| HVAC PROCESS FLOW DIAGRAM - OPERATION TOOL ROOM |  |  |  | OL1-2H20-0007 | EE | [6 empty] | Transmitted
| HVAC LAYOUT- ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  |  |  | OL1-2H21-0001 | EE | [6 empty] | Transmitted
| HVAC LAYOUT- ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  |  |  | OL1-2H21-0005 | EE | [6 empty] | Transmitted
| HVAC LAYOUT- GATEHOUSE |  |  |  | OL1-2H21-0010 | EE | [6 empty] | Transmitted
| HVAC LAYOUT- OPERATION TOOL ROOM |  |  |  | OL1-2H21-0015 | EE | [6 empty] | Transmitted
| MR HVAC SYSTEMS |  |  |  | OL1-2H55-0001 | EE | [6 empty] | Transmitted
| D/S MECHANICAL RESTRICTION ORIFICE AND ORIFICE |  |  |  | OL1-2I20-0101 | IE | [6 empty] | Transmitted
| DATA SHEET FOR PITOT TUBE |  |  |  | OL1-2I20-0102 | IE | [6 empty] | Transmitted
| D/S MECHANICAL ELECTROMAGNETIC FLOW METER |  |  |  | OL1-2I20-0103 | IE | [6 empty] | Transmitted
| D/S MECHANICAL ROTAMETERS |  |  |  | OL1-2I20-0104 | IE | [6 empty] | Transmitted
| D/S MECHANICAL MASS FLOW MET.CORIOLIS EFFECT |  |  |  | OL1-2I20-0106 | IE | [6 empty] | Transmitted
| D/S MECHANICAL VENTURI |  |  |  | OL1-2I20-0107 | IE | [6 empty] | Transmitted
| D/S MECHANICAL ULTRASONIC FLOW METER |  |  |  | OL1-2I20-0108 | IE | [6 empty] | Transmitted
| D/S MECHANICAL TURBINE METER |  |  |  | OL1-2I20-0111 | IE | [6 empty] | Transmitted
| D/S MECHANICAL VORTEX METER |  |  |  | OL1-2I20-0112 | IE | [6 empty] | Transmitted
| DATA SHEET FOR CUSTODY TRANSFER METERING |  |  |  | OL1-2I20-0120 | IE | [6 empty] | Transmitted
| D/S MECHANICAL MAGNETIC LEVEL GAUGE |  |  |  | OL1-2I20-0202 | IE | [6 empty] | Transmitted
| D/S MECHANICAL RADAR LEVEL INSTRUMENTS |  |  |  | OL1-2I20-0203 | IE | [6 empty] | Transmitted
| D/S MECHANICAL SPECIAL LEVEL TRANSMITTERS |  |  |  | OL1-2I20-0211 | IE | [6 empty] | Transmitted
| D/S MECHANICAL LEVEL GLASS |  |  |  | OL1-2I20-0212 | IE | [6 empty] | Transmitted
| D/S MECHANICAL PRESSURE & DIFFER.PRESS.GAUGE |  |  |  | OL1-2I20-0301 | IE | [6 empty] | Transmitted
| D/S MECHANICAL CONTROL VALVES |  |  |  | OL1-2I20-0501 | IE | [6 empty] | Transmitted
| D/S MECHANICAL SPECIAL CONTROL VALVE |  |  |  | OL1-2I20-0503 | IE | [6 empty] | Transmitted
| D/S MECHANICAL SEVERE SERVICE CONTROL VALVE |  |  |  | OL1-2I20-0504 | IE | [6 empty] | Transmitted
| D/S ANTISURGE VALVES |  |  |  | OL1-2I20-0505 | IE | [6 empty] | Transmitted
| D/S MECHANICAL DESUPERHEATER VALVES |  |  |  | OL1-2I20-0506 | IE | [6 empty] | Transmitted
| D/S MECHANICAL PNEUMATIC ON OFF VALVES |  |  |  | OL1-2I20-0606 | IE | [6 empty] | Transmitted
| D/S MECHANICAL SPECIAL ON OFF VALVES |  |  |  | OL1-2I20-0608 | IE | [6 empty] | Transmitted
| D/S MECHANICAL ELECTRIC OPERATED VALVES |  |  |  | OL1-2I20-0609 | IE | [6 empty] | Transmitted
| D/S MECHANICAL SAFETY RELIEF VALVE & RUPTURE DISKS |  |  |  | OL1-2I20-0701 | IE | [6 empty] | Transmitted
| D/S MECHANICAL ELECTRONIC TRANSMITTER |  |  |  | OL1-2I20-0801 | IE | [6 empty] | Transmitted
| CONTROL VALVE DATASHEETS |  |  |  | OL1-2I20-1001 | IE | [6 empty] | Transmitted
| INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  |  |  | OL1-2I20-1002 | IE | [6 empty] | Transmitted
| VENTURI TUBE DATASHEETS |  |  |  | OL1-2I20-1003 | IE | [6 empty] | Transmitted
| ORIFICE PLATE DATASHEET |  |  |  | OL1-2I20-1004 | IE | [6 empty] | Transmitted
| INSTRUMENT LEVEL GAUGE DATASHEET |  |  |  | OL1-2I20-1005 | IE | [6 empty] | Transmitted
| D/P LEVEL TRANSMITTERS |  |  |  | OL1-2I20-1006 | IE | [6 empty] | Transmitted
| DATA SHEET FOR PRESSURE GAUGES |  |  |  | OL1-2I20-1007 | IE | [6 empty] | Transmitted
| DATA SHEET FOR DRAFT PRESSURE GAUGES |  |  |  | OL1-2I20-1008 | IE | [6 empty] | Transmitted
| PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-1009 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  |  |  | OL1-2I20-1010 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  |  |  | OL1-2I20-1011 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  |  |  | OL1-2I20-1012 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  |  |  | OL1-2I20-1013 | IE | [6 empty] | Transmitted
| TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-1014 | IE | [6 empty] | Transmitted
| INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  |  |  | OL1-2I20-1015 | IE | [6 empty] | Transmitted
| O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  |  |  | OL1-2I20-1016 | IE | [6 empty] | Transmitted
| FLAME SCANNER DATA SHEETS CRACKING FURNACE |  |  |  | OL1-2I20-1017 | IE | [6 empty] | Transmitted
| CONTROL VALVE DATASHEETS |  |  |  | OL1-2I20-2001 | IE | [6 empty] | Transmitted
| INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  |  |  | OL1-2I20-2002 | IE | [6 empty] | Transmitted
| VENTURI TUBE DATASHEETS |  |  |  | OL1-2I20-2003 | IE | [6 empty] | Transmitted
| ORIFICE PLATE DATASHEET |  |  |  | OL1-2I20-2004 | IE | [6 empty] | Transmitted
| INSTRUMENT LEVEL GAUGE DATASHEET |  |  |  | OL1-2I20-2005 | IE | [6 empty] | Transmitted
| D/P LEVEL TRANSMITTERS |  |  |  | OL1-2I20-2006 | IE | [6 empty] | Transmitted
| DATA SHEET FOR PRESSURE GAUGES |  |  |  | OL1-2I20-2007 | IE | [6 empty] | Transmitted
| DATA SHEET FOR DRAFT PRESSURE GAUGES |  |  |  | OL1-2I20-2008 | IE | [6 empty] | Transmitted
| PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-2009 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  |  |  | OL1-2I20-2010 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  |  |  | OL1-2I20-2011 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  |  |  | OL1-2I20-2012 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  |  |  | OL1-2I20-2013 | IE | [6 empty] | Transmitted
| TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-2014 | IE | [6 empty] | Transmitted
| INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  |  |  | OL1-2I20-2015 | IE | [6 empty] | Transmitted
| O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  |  |  | OL1-2I20-2016 | IE | [6 empty] | Transmitted
| FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  |  |  | OL1-2I20-2017 | IE | [6 empty] | Transmitted
| DATA SHEET FOR FIRE AND GAS DEVICES |  |  |  | OL1-2I20-2601 | IE | [6 empty] | Transmitted
| CONTROL VALVE DATASHEETS |  |  |  | OL1-2I20-3001 | IE | [6 empty] | Transmitted
| INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  |  |  | OL1-2I20-3002 | IE | [6 empty] | Transmitted
| VENTURI TUBE DATASHEETS |  |  |  | OL1-2I20-3003 | IE | [6 empty] | Transmitted
| ORIFICE PLATE DATASHEET |  |  |  | OL1-2I20-3004 | IE | [6 empty] | Transmitted
| INSTRUMENT LEVEL GAUGE DATASHEET |  |  |  | OL1-2I20-3005 | IE | [6 empty] | Transmitted
| D/P LEVEL TRANSMITTERS |  |  |  | OL1-2I20-3006 | IE | [6 empty] | Transmitted
| DATA SHEET FOR PRESSURE GAUGES |  |  |  | OL1-2I20-3007 | IE | [6 empty] | Transmitted
| DATA SHEET FOR DRAFT PRESSURE GAUGES |  |  |  | OL1-2I20-3008 | IE | [6 empty] | Transmitted
| PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-3009 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  |  |  | OL1-2I20-3010 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  |  |  | OL1-2I20-3011 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  |  |  | OL1-2I20-3012 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  |  |  | OL1-2I20-3013 | IE | [6 empty] | Transmitted
| TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-3014 | IE | [6 empty] | Transmitted
| INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  |  |  | OL1-2I20-3015 | IE | [6 empty] | Transmitted
| O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  |  |  | OL1-2I20-3016 | IE | [6 empty] | Transmitted
| FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  |  |  | OL1-2I20-3017 | IE | [6 empty] | Transmitted
| CONTROL VALVE DATASHEETS |  |  |  | OL1-2I20-4001 | IE | [6 empty] | Transmitted
| INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  |  |  | OL1-2I20-4002 | IE | [6 empty] | Transmitted
| VENTURI TUBE DATASHEETS |  |  |  | OL1-2I20-4003 | IE | [6 empty] | Transmitted
| ORIFICE PLATE DATASHEET |  |  |  | OL1-2I20-4004 | IE | [6 empty] | Transmitted
| INSTRUMENT LEVEL GAUGE DATASHEET |  |  |  | OL1-2I20-4005 | IE | [6 empty] | Transmitted
| D/P LEVEL TRANSMITTERS |  |  |  | OL1-2I20-4006 | IE | [6 empty] | Transmitted
| DATA SHEET FOR PRESSURE GAUGES |  |  |  | OL1-2I20-4007 | IE | [6 empty] | Transmitted
| DATA SHEET FOR DRAFT PRESSURE GAUGES |  |  |  | OL1-2I20-4008 | IE | [6 empty] | Transmitted
| PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-4009 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  |  |  | OL1-2I20-4010 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  |  |  | OL1-2I20-4011 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  |  |  | OL1-2I20-4012 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  |  |  | OL1-2I20-4013 | IE | [6 empty] | Transmitted
| TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-4014 | IE | [6 empty] | Transmitted
| INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  |  |  | OL1-2I20-4015 | IE | [6 empty] | Transmitted
| O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  |  |  | OL1-2I20-4016 | IE | [6 empty] | Transmitted
| FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  |  |  | OL1-2I20-4017 | IE | [6 empty] | Transmitted
| CONTROL VALVE DATASHEETS |  |  |  | OL1-2I20-5001 | IE | [6 empty] | Transmitted
| INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  |  |  | OL1-2I20-5002 | IE | [6 empty] | Transmitted
| VENTURI TUBE DATASHEETS |  |  |  | OL1-2I20-5003 | IE | [6 empty] | Transmitted
| ORIFICE PLATE DATASHEET |  |  |  | OL1-2I20-5004 | IE | [6 empty] | Transmitted
| INSTRUMENT LEVEL GAUGE DATASHEET |  |  |  | OL1-2I20-5005 | IE | [6 empty] | Transmitted
| D/P LEVEL TRANSMITTERS |  |  |  | OL1-2I20-5006 | IE | [6 empty] | Transmitted
| DATA SHEET FOR PRESSURE GAUGES |  |  |  | OL1-2I20-5007 | IE | [6 empty] | Transmitted
| DATA SHEET FOR DRAFT PRESSURE GAUGES |  |  |  | OL1-2I20-5008 | IE | [6 empty] | Transmitted
| PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-5009 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  |  |  | OL1-2I20-5010 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  |  |  | OL1-2I20-5011 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  |  |  | OL1-2I20-5012 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  |  |  | OL1-2I20-5013 | IE | [6 empty] | Transmitted
| TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-5014 | IE | [6 empty] | Transmitted
| INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  |  |  | OL1-2I20-5015 | IE | [6 empty] | Transmitted
| O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  |  |  | OL1-2I20-5016 | IE | [6 empty] | Transmitted
| FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  |  |  | OL1-2I20-5017 | IE | [6 empty] | Transmitted
| CONTROL VALVE DATASHEETS |  |  |  | OL1-2I20-6001 | IE | [6 empty] | Transmitted
| INSTRUMENT MOTOR OPERATED VALVE DATASHEETS |  |  |  | OL1-2I20-6002 | IE | [6 empty] | Transmitted
| VENTURI TUBE DATASHEETS |  |  |  | OL1-2I20-6003 | IE | [6 empty] | Transmitted
| ORIFICE PLATE DATASHEET |  |  |  | OL1-2I20-6004 | IE | [6 empty] | Transmitted
| INSTRUMENT LEVEL GAUGE DATASHEET |  |  |  | OL1-2I20-6005 | IE | [6 empty] | Transmitted
| D/P LEVEL TRANSMITTERS |  |  |  | OL1-2I20-6006 | IE | [6 empty] | Transmitted
| DATA SHEET FOR PRESSURE GAUGES |  |  |  | OL1-2I20-6007 | IE | [6 empty] | Transmitted
| DATA SHEET FOR DRAFT PRESSURE GAUGES |  |  |  | OL1-2I20-6008 | IE | [6 empty] | Transmitted
| PRESSURE INDICATING TRANSMITTERS & FLOW INDICATING D/P TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-6009 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR FURNACE PROFILE DATA SHEET |  |  |  | OL1-2I20-6010 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR COIL OUTLET DATA SHEETS |  |  |  | OL1-2I20-6011 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR THERMOCOUPLES WITH WELL DATASHEETS |  |  |  | OL1-2I20-6012 | IE | [6 empty] | Transmitted
| TEMPERATURE ELEMENTS FOR RTD WITH WELL DATASHEETS |  |  |  | OL1-2I20-6013 | IE | [6 empty] | Transmitted
| TEMPERATURE INDICATING TRANSMITTERS DATASHEETS |  |  |  | OL1-2I20-6014 | IE | [6 empty] | Transmitted
| INSTRUMENT PH AND CONDUCTIVITY ANALYZER DATASHEETS |  |  |  | OL1-2I20-6015 | IE | [6 empty] | Transmitted
| O2 / COMBUSTIBLES ANALYZERS DATASHEETS |  |  |  | OL1-2I20-6016 | IE | [6 empty] | Transmitted
| FLAME SCANNER DATA SHEETS RECYCLE FURNACE |  |  |  | OL1-2I20-6017 | IE | [6 empty] | Transmitted
| FLOW ELEMENT CALCULATION SHEET |  |  |  | OL1-2I21-0100 | IE | [6 empty] | Transmitted
| INTRINSIC SAFETY LOOP CALCULATION |  |  |  | OL1-2I21-1001 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 10 |  |  |  | OL1-2I30-1001 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 10 |  |  |  | OL1-2I30-1003 | IE | [6 empty] | Transmitted
| DCS INTERLOCK AND SEQUENCES DIAGRAMS |  |  |  | OL1-2I30-1101 | IE | [6 empty] | Transmitted
| ESD INTERLOCK LOGIC DIAGRAMS |  |  |  | OL1-2I30-1102 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 20 |  |  |  | OL1-2I30-2001 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 20 |  |  |  | OL1-2I30-2003 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 21 |  |  |  | OL1-2I30-2101 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 21 |  |  |  | OL1-2I30-2103 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 22 |  |  |  | OL1-2I30-2201 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 22 |  |  |  | OL1-2I30-2203 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 23 |  |  |  | OL1-2I30-2301 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 23 |  |  |  | OL1-2I30-2303 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 24 |  |  |  | OL1-2I30-2401 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 24 |  |  |  | OL1-2I30-2403 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 25 |  |  |  | OL1-2I30-2501 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 25 |  |  |  | OL1-2I30-2503 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 26 |  |  |  | OL1-2I30-2601 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 26 |  |  |  | OL1-2I30-2603 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 27 |  |  |  | OL1-2I30-2701 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 27 |  |  |  | OL1-2I30-2703 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 28 |  |  |  | OL1-2I30-2801 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 28 |  |  |  | OL1-2I30-2803 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 29 |  |  |  | OL1-2I30-2901 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 29 |  |  |  | OL1-2I30-2903 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 30 |  |  |  | OL1-2I30-3001 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 30 |  |  |  | OL1-2I30-3003 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 50 |  |  |  | OL1-2I30-5001 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 50 |  |  |  | OL1-2I30-5003 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 53 |  |  |  | OL1-2I30-5301 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 53 |  |  |  | OL1-2I30-5303 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 55 |  |  |  | OL1-2I30-5501 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 55 |  |  |  | OL1-2I30-5503 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS - AREA 56 |  |  |  | OL1-2I30-5601 | IE | [6 empty] | Transmitted
| INSTRUMENT INTERLOCK DESCRIPTIONS - AREA 56 |  |  |  | OL1-2I30-5603 | IE | [6 empty] | Transmitted
| INSTR.SUPPORTS TYPICAL MOUNT.DETAILS |  |  |  | OL1-2I31-0001 | IE | [6 empty] | Transmitted
| LEVEL INSTRUMENT DESIGN, ISBL UNITS |  |  |  | OL1-2I31-0200 | IE | [6 empty] | Transmitted
| LEVEL INSTRUMENT DESIGN, OSBL UNITS |  |  |  | OL1-2I31-0201 | IE | [6 empty] | Transmitted
| FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-1003 | IE | [6 empty] | Transmitted
| PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-1005 | IE | [6 empty] | Transmitted
| PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-1012 | IE | [6 empty] | Transmitted
| FLOW TRANSMITTER - LIQUID SERVICE #900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-1019 | IE | [6 empty] | Transmitted
| PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-1020 | IE | [6 empty] | Transmitted
| LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  |  |  | OL1-2I31-1021 | IE | [6 empty] | Transmitted
| PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-1022 | IE | [6 empty] | Transmitted
| O2 COMBUSTIBLE ANALYZER PROCESS CONNECTION DETAIL |  |  |  | OL1-2I31-2001 | IE | [6 empty] | Transmitted
| O2 COMBUSTIBLE ANALYZER INSTRUMENT ELECTRICAL CONNECTION DETAIL |  |  |  | OL1-2I31-2002 | IE | [6 empty] | Transmitted
| FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-2003 | IE | [6 empty] | Transmitted
| PRESSURE GAUGE - GAS SERVICE DRAFT REMOTE MOUNTING |  |  |  | OL1-2I31-2004 | IE | [6 empty] | Transmitted
| PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-2005 | IE | [6 empty] | Transmitted
| EYE-HYE LEVEL COMPONENTS ON STEAM DRUM ELECTRICAL CONNECTION |  |  |  | OL1-2I31-2006 | IE | [6 empty] | Transmitted
| COT INSERTION WELL T-C CONNECTION DETAIL |  |  |  | OL1-2I31-2007 | IE | [6 empty] | Transmitted
| INSTRUMENT SUPPORT DETAIL EYE-HYE LEVEL CONTROL UNIT |  |  |  | OL1-2I31-2008 | IE | [6 empty] | Transmitted
| INSTRUMENT PROCESS DETAILS DRAFT D-P TRANSMITTER GAS SERVICE REMOTE MOUNTED |  |  |  | OL1-2I31-2009 | IE | [6 empty] | Transmitted
| INSTRUMENT SUPPORT DETAILS DUAL STAND 4FT-4IN OUTSIDE HANDRAIL |  |  |  | OL1-2I31-2010 | IE | [6 empty] | Transmitted
| INSTRUMENT SUPPORT DETAILS TRIPLE STAND 4FT-4IN OUTSIDE HANDRAIL |  |  |  | OL1-2I31-2011 | IE | [6 empty] | Transmitted
| PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-2012 | IE | [6 empty] | Transmitted
| THERMOCOUPLE HEAD ELECTRICAL CONNECTION DETAIL 3-4IN CONDUIT |  |  |  | OL1-2I31-2013 | IE | [6 empty] | Transmitted
| TEMPERATURE TRANSMITTER ELECTRICAL CONNECTION DETAIL |  |  |  | OL1-2I31-2014 | IE | [6 empty] | Transmitted
| LUBE OIL VENDOR JUNCTION BOX TO FIE CHARM BOX ELECTRICAL CONNECTION |  |  |  | OL1-2I31-2015 | IE | [6 empty] | Transmitted
| INSTRUMENT SUPPORT DETAIL EYE-HYE MINIATURE LEVEL INDICATOR |  |  |  | OL1-2I31-2016 | IE | [6 empty] | Transmitted
| PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  |  |  | OL1-2I31-2017 | IE | [6 empty] | Transmitted
| PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  |  |  | OL1-2I31-2018 | IE | [6 empty] | Transmitted
| FLOW TRANSMITTER - LIQUID SERVICE #900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-2019 | IE | [6 empty] | Transmitted
| PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-2020 | IE | [6 empty] | Transmitted
| LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  |  |  | OL1-2I31-2021 | IE | [6 empty] | Transmitted
| PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  |  | OL1-2I31-2022 | IE | [6 empty] | Transmitted
| LEVEL GAUGE - STEAM SERVICE DIRECT MTD W ELECTRIC TRACED |  |  |  | OL1-2I31-2023 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING COMMON AREA |  |  |  | OL1-2I34-0001 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING METERING |  |  |  | OL1-2I34-0002 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING MAIN PIPE RACK |  |  |  | OL1-2I34-0003 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING AREA SUBSTATION E & FAR E |  |  |  | OL1-2I34-0004 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING AREA SUBSTATION C & FAR C |  |  |  | OL1-2I34-0005 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING FURNACES UTILITY |  |  |  | OL1-2I34-0006 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING QUENCH |  |  |  | OL1-2I34-0007 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING PROCESS 20B |  |  |  | OL1-2I34-0008 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING PROCESS 20C |  |  |  | OL1-2I34-0009 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING PROCESS COLD COMPRESSORS |  |  |  | OL1-2I34-0010 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING PROCESS CGC |  |  |  | OL1-2I34-0011 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING BUTADIENE |  |  |  | OL1-2I34-0012 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING COOLING WATER UNIT |  |  |  | OL1-2I34-0013 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING UTILITIES |  |  |  | OL1-2I34-0014 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING WASTE WATER TREATMENT |  |  |  | OL1-2I34-0015 | IE | [6 empty] | Transmitted
| INSTR.MAIN CABLE ROUTING FLARE AREA |  |  |  | OL1-2I34-0016 | IE | [6 empty] | Transmitted
| INSTR.OVERALL CABLE ROUTING |  |  |  | OL1-2I34-0017 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT COMMON AREA |  |  |  | OL1-2I35-0001 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT METERING |  |  |  | OL1-2I35-0002 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT MAIN PIPE RACK |  |  |  | OL1-2I35-0003 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT AREA SUBSTATION E & FAR E |  |  |  | OL1-2I35-0004 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT AREA SUBSTATION E & FAR C |  |  |  | OL1-2I35-0005 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT FURNACES UTILITY |  |  |  | OL1-2I35-0006 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT QUENCH |  |  |  | OL1-2I35-0007 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT PROCESS 20B |  |  |  | OL1-2I35-0008 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT PROCESS 20C |  |  |  | OL1-2I35-0009 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT PROCESS COLD COMPRESSORS |  |  |  | OL1-2I35-0010 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT PROCESS CGC |  |  |  | OL1-2I35-0011 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT BUTADIENE |  |  |  | OL1-2I35-0012 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT COOLING WATER UNIT |  |  |  | OL1-2I35-0013 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT UTILITIES |  |  |  | OL1-2I35-0014 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT WASTE WATER TREATMENT |  |  |  | OL1-2I35-0015 | IE | [6 empty] | Transmitted
| INSTRUMENT LAYOUT FLARE AREA |  |  |  | OL1-2I35-0016 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT COMMON AREA |  |  |  | OL1-2I35-0020 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT METERING |  |  |  | OL1-2I35-0021 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT MAIN PIPE RACK |  |  |  | OL1-2I35-0022 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION E & FAR E |  |  |  | OL1-2I35-0023 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION C & FAR C |  |  |  | OL1-2I35-0024 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT FURNACES UTILITY |  |  |  | OL1-2I35-0025 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT QUENCH |  |  |  | OL1-2I35-0026 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20B |  |  |  | OL1-2I35-0027 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20C |  |  |  | OL1-2I35-0028 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS COLD COMPRESSORS |  |  |  | OL1-2I35-0029 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS CGC |  |  |  | OL1-2I35-0030 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT BUTADIENE |  |  |  | OL1-2I35-0031 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT COOLING WATER UNIT |  |  |  | OL1-2I35-0032 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT UTILITIES |  |  |  | OL1-2I35-0033 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT WASTE WATER TREATMENT |  |  |  | OL1-2I35-0034 | IE | [6 empty] | Transmitted
| INSTRUMENT AIR DISTRIBUTION LAYOUT FLARE AREA |  |  |  | OL1-2I35-0035 | IE | [6 empty] | Transmitted
| INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-E SYSTEMS |  |  |  | OL1-2I42-0001 | IE | [6 empty] | Transmitted
| INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-C SYSTEMS |  |  |  | OL1-2I42-0002 | IE | [6 empty] | Transmitted
| INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR FL SYSTEMS |  |  |  | OL1-2I42-0003 | IE | [6 empty] | Transmitted
| INSTRUMENT AND F&G WIRING DRAWINGS FOR CCB AND OTHER BUILDINGS SYSTEMS |  |  |  | OL1-2I42-0004 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT GRADE TO EL AAFT-AIN |  |  |  | OL1-2I42-1001 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100- AT EL AAFT-AIN TO EL BBFT-BIN |  |  |  | OL1-2I42-1002 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1100 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  |  | OL1-2I42-1003 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL CCFT-CIN TO EL DDFT-DIN |  |  |  | OL1-2I42-1004 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL DDFT-DIN TO EL. EEFT-E |  |  |  | OL1-2I42-1005 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL EEFT-EIN TO EL FF1FT -F |  |  |  | OL1-2I42-1006 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL FFFT-FIN TO EL GGFT-GIN |  |  |  | OL1-2I42-1007 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  |  | OL1-2I42-1008 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL HHFT-HIN TO EL IIFT-IIN |  |  |  | OL1-2I42-1009 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1100 AT EL IIFT-IIN TO EL JJFT-JIN |  |  |  | OL1-2I42-1010 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL JJFT - JIN TO EL KKFT-KIN |  |  |  | OL1-2I42-1011 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL KKFT - KIN TO EL LLFT-LIN |  |  |  | OL1-2I42-1012 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT GRADE TO EL AAFT-AIN |  |  |  | OL1-2I42-2001 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200- AT EL AAFT-AIN TO EL BBFT-BIN |  |  |  | OL1-2I42-2002 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1200 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  |  | OL1-2I42-2003 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL CCFT-CIN TO EL DDFT-DIN |  |  |  | OL1-2I42-2004 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL DDFT-DIN TO EL. EEFT-E |  |  |  | OL1-2I42-2005 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL EEFT-EIN TO EL FF1FT -F |  |  |  | OL1-2I42-2006 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL FFFT-FIN TO EL GGFT-GIN |  |  |  | OL1-2I42-2007 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  |  | OL1-2I42-2008 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL HHFT-HIN TO EL IIFT-IIN |  |  |  | OL1-2I42-2009 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1200 AT EL IIFT-IIN TO EL JJFT-JIN |  |  |  | OL1-2I42-2010 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL JJFT - JIN TO EL KKFT-KIN |  |  |  | OL1-2I42-2011 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL KKFT - KIN TO EL LLFT-LIN |  |  |  | OL1-2I42-2012 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT GRADE TO EL AAFT-AIN |  |  |  | OL1-2I42-3001 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300- AT EL AAFT-AIN TO EL BBFT-BIN |  |  |  | OL1-2I42-3002 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1300 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  |  | OL1-2I42-3003 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL CCFT-CIN TO EL DDFT-DIN |  |  |  | OL1-2I42-3004 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL DDFT-DIN TO EL. EEFT-E |  |  |  | OL1-2I42-3005 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL EEFT-EIN TO EL FF1FT -F |  |  |  | OL1-2I42-3006 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL FFFT-FIN TO EL GGFT-GIN |  |  |  | OL1-2I42-3007 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  |  | OL1-2I42-3008 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL HHFT-HIN TO EL IIFT-IIN |  |  |  | OL1-2I42-3009 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1300 AT EL IIFT-IIN TO EL JJFT-JIN |  |  |  | OL1-2I42-3010 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL JJFT - JIN TO EL KKFT-KIN |  |  |  | OL1-2I42-3011 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL KKFT - KIN TO EL LLFT-LIN |  |  |  | OL1-2I42-3012 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT GRADE TO EL AAFT-AIN |  |  |  | OL1-2I42-4001 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400- AT EL AAFT-AIN TO EL BBFT-BIN |  |  |  | OL1-2I42-4002 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1400 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  |  | OL1-2I42-4003 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL CCFT-CIN TO EL DDFT-DIN |  |  |  | OL1-2I42-4004 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL DDFT-DIN TO EL. EEFT-E |  |  |  | OL1-2I42-4005 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL EEFT-EIN TO EL FF1FT -F |  |  |  | OL1-2I42-4006 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL FFFT-FIN TO EL GGFT-GIN |  |  |  | OL1-2I42-4007 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  |  | OL1-2I42-4008 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL HHFT-HIN TO EL IIFT-IIN |  |  |  | OL1-2I42-4009 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1400 AT EL IIFT-IIN TO EL JJFT-JIN |  |  |  | OL1-2I42-4010 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL JJFT - JIN TO EL KKFT-KIN |  |  |  | OL1-2I42-4011 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL KKFT - KIN TO EL LLFT-LIN |  |  |  | OL1-2I42-4012 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT GRADE TO EL AAFT-AIN |  |  |  | OL1-2I42-5001 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500- AT EL AAFT-AIN TO EL BBFT-BIN |  |  |  | OL1-2I42-5002 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1500 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  |  | OL1-2I42-5003 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL CCFT-CIN TO EL DDFT-DIN |  |  |  | OL1-2I42-5004 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL DDFT-DIN TO EL. EEFT-E |  |  |  | OL1-2I42-5005 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL EEFT-EIN TO EL FF1FT -F |  |  |  | OL1-2I42-5006 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL FFFT-FIN TO EL GGFT-GIN |  |  |  | OL1-2I42-5007 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  |  | OL1-2I42-5008 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL HHFT-HIN TO EL IIFT-IIN |  |  |  | OL1-2I42-5009 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1500 AT EL IIFT-IIN TO EL JJFT-JIN |  |  |  | OL1-2I42-5010 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL JJFT - JIN TO EL KKFT-KIN |  |  |  | OL1-2I42-5011 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL KKFT - KIN TO EL LLFT-LIN |  |  |  | OL1-2I42-5012 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT GRADE TO EL AAFT-AIN |  |  |  | OL1-2I42-6001 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600- AT EL AAFT-AIN TO EL BBFT-BIN |  |  |  | OL1-2I42-6002 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1600 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  |  | OL1-2I42-6003 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL CCFT-CIN TO EL DDFT-DIN |  |  |  | OL1-2I42-6004 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL DDFT-DIN TO EL. EEFT-E |  |  |  | OL1-2I42-6005 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL EEFT-EIN TO EL FF1FT -F |  |  |  | OL1-2I42-6006 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL FFFT-FIN TO EL GGFT-GIN |  |  |  | OL1-2I42-6007 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  |  | OL1-2I42-6008 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL HHFT-HIN TO EL IIFT-IIN |  |  |  | OL1-2I42-6009 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1600 AT EL IIFT-IIN TO EL JJFT-JIN |  |  |  | OL1-2I42-6010 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL JJFT - JIN TO EL KKFT-KIN |  |  |  | OL1-2I42-6011 | IE | [6 empty] | Transmitted
| INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL KKFT - KIN TO EL LLFT-LIN |  |  |  | OL1-2I42-6012 | IE | [6 empty] | Transmitted
| INSTRUMENT CABLE LIST FOR FAR C SYSTEMS |  |  |  | OL1-2I43-0001 | IE | [6 empty] | Transmitted
| INSTRUMENT CABLE LIST FOR FAR E SYSTEMS |  |  |  | OL1-2I43-0002 | IE | [6 empty] | Transmitted
| INSTRUMENT CABLE LIST FOR FAR FL SYSTEMS |  |  |  | OL1-2I43-0003 | IE | [6 empty] | Transmitted
| INSTRUMENT CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  |  |  | OL1-2I43-0004 | IE | [6 empty] | Transmitted
| INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR C SYSTEMS |  |  |  | OL1-2I43-0011 | IE | [6 empty] | Transmitted
| INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR E SYSTEMS |  |  |  | OL1-2I43-0012 | IE | [6 empty] | Transmitted
| INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR FL SYSTEMS |  |  |  | OL1-2I43-0013 | IE | [6 empty] | Transmitted
| INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FORCCB AND OTHER BULDINGS SYSTEMS |  |  |  | OL1-2I43-0014 | IE | [6 empty] | Transmitted
| INST.POW.SUP.DISTRIBUTION FOR CCB |  |  |  | OL1-2I44-1001 | IE | [6 empty] | Transmitted
| INST.POW.SUP.DISTRIBUTION FOR FAR C |  |  |  | OL1-2I44-1002 | IE | [6 empty] | Transmitted
| INST.POW.SUP.DISTRIBUTION FOR FAR E |  |  |  | OL1-2I44-1003 | IE | [6 empty] | Transmitted
| INST.POW.SUP.DISTRIBUTION FOR FAR FL |  |  |  | OL1-2I44-1004 | IE | [6 empty] | Transmitted
| CONTROL & TECH.ROOM LAYOUT, CENTRAL CONTROL BUILDING |  |  |  | OL1-2I46-1001 | IE | [6 empty] | Transmitted
| FAR C INSTRUMENT EQUIPMENT LAYOUT |  |  |  | OL1-2I46-1002 | IE | [6 empty] | Transmitted
| FAR E INSTRUMENT EQUIPMENT LAYOUT |  |  |  | OL1-2I46-1003 | IE | [6 empty] | Transmitted
| FAR FL INSTRUMENT EQUIPMENT LAYOUT |  |  |  | OL1-2I46-1004 | IE | [6 empty] | Transmitted
| MAINTENANCE BUILDING INSTRUMENT EQUIPMENT LAYOUT |  |  |  | OL1-2I46-1005 | IE | [6 empty] | Transmitted
| EMERGENCY CENTER BUILDING INSTRUMENT EQUIPMENT LAYOUT |  |  |  | OL1-2I46-1006 | IE | [6 empty] | Transmitted
| FAR E INSTRUMENT CABLE ROUTING |  |  |  | OL1-2I47-1001 | IE | [6 empty] | Transmitted
| FAR C INSTRUMENT CABLE ROUTING |  |  |  | OL1-2I47-1002 | IE | [6 empty] | Transmitted
| FAR FL INSTRUMENT CABLE ROUTING |  |  |  | OL1-2I47-1003 | IE | [6 empty] | Transmitted
| INSTRUMENT CABLE ROUTING CENTRAL CONTROL BUILDING AND OTHER BUILDINGS |  |  |  | OL1-2I47-1004 | IE | [6 empty] | Transmitted
| CCB INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT PACKAGE A1 |  |  |  | OL1-2I47-1005 | IE | [6 empty] | Transmitted
| FAR E INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  |  | OL1-2I47-1006 | IE | [6 empty] | Transmitted
| FAR C INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  |  | OL1-2I47-1007 | IE | [6 empty] | Transmitted
| FAR FL INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  |  | OL1-2I47-1008 | IE | [6 empty] | Transmitted
| TELECOM LOCATION AND CABLE ROUTING FAR E |  |  |  | OL1-2I47-1021 | IE | [6 empty] | Transmitted
| TELECOM LOCATION AND CABLE ROUTING FAR C |  |  |  | OL1-2I47-1022 | IE | [6 empty] | Transmitted
| TELECOM LOCATION AND CABLE ROUTING FAR FL |  |  |  | OL1-2I47-1023 | IE | [6 empty] | Transmitted
| TELECOM LOCATION AND CABLE ROUTING CENTRAL CONTROL BUILDING |  |  |  | OL1-2I47-1024 | IE | [6 empty] | Transmitted
| SUB E INSTRUMENT CABLE ROUTING |  |  |  | OL1-2I47-1050 | IE | [6 empty] | Transmitted
| SUB C INSTRUMENT CABLE ROUTING |  |  |  | OL1-2I47-1051 | IE | [6 empty] | Transmitted
| INSTRUMENT & TELECOM GROUNDING PHILOSOPHY DIAGRAM |  |  |  | OL1-2I48-1001 | IE | [6 empty] | Transmitted
| INSTRUMENT / TELECOM EARTHING LAYOUT CENTRAL CONTROL BUILDING |  |  |  | OL1-2I48-1002 | IE | [6 empty] | Transmitted
| INSTRUMENT / TELECOM EARTHING LAYOUT FAR E AND SUB E |  |  |  | OL1-2I48-1003 | IE | [6 empty] | Transmitted
| INSTRUMENT / TELECOM EARTHING LAYOUT FAR C AND SUB C |  |  |  | OL1-2I48-1004 | IE | [6 empty] | Transmitted
| INSTRUMENT / TELECOM EARTHING LAYOUT FAR FL |  |  |  | OL1-2I48-1005 | IE | [6 empty] | Transmitted
| INSTRUMENT / TELECOM EARTHING LAYOUT OTHER BUILDINGS |  |  |  | OL1-2I48-1006 | IE | [6 empty] | Transmitted
| INSTRUMENT/TELECOM AND FIBRE OPTIC CABLES MATERIALTAKE-OFF |  |  |  | OL1-2I49-4101 | IE | [6 empty] | Transmitted
| CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  |  |  | OL1-2I49-4201 | IE | [6 empty] | Transmitted
| SECONDARY CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  |  |  | OL1-2I49-4203 | IE | [6 empty] | Transmitted
| JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES MATERIAL TAKE-OFF |  |  |  | OL1-2I49-4301 | IE | [6 empty] | Transmitted
| CABLE GLANDS MAT.TAKE-OFF |  |  |  | OL1-2I49-4303 | IE | [6 empty] | Transmitted
| MAIN CABLE TRANSIT (MCT) & ACCESSORIES MATERIAL TAKE OFF |  |  |  | OL1-2I49-4304 | IE | [6 empty] | Transmitted
| INSTRUMENT HOOK-UP DRAWINGS ISBL UNITS |  |  |  | OL1-2I50-0001 | IE | [6 empty] | Transmitted
| INSTRUMENT TYPICAL HOOK -UP |  |  |  | OL1-2I51-0001 | IE | [6 empty] | Transmitted
| INSTRUMENT HOOK-UP DRAWINGS OSBL UNITS |  |  |  | OL1-2I52-0001 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - FURNACES UTILITY |  |  |  | OL1-2I53-0001 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - QUENCH |  |  |  | OL1-2I53-0002 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20B |  |  |  | OL1-2I53-0003 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20C |  |  |  | OL1-2I53-0004 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS COLD COMPRESSORS |  |  |  | OL1-2I53-0005 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS CGC |  |  |  | OL1-2I53-0006 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E- METERING |  |  |  | OL1-2I53-0007 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION E & FAR E |  |  |  | OL1-2I53-0008 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION C & FAR C |  |  |  | OL1-2I53-0009 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - BUTADIENE |  |  |  | OL1-2I53-0010 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - COOLING WATER UNIT |  |  |  | OL1-2I53-0011 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - UTILITIES |  |  |  | OL1-2I53-0012 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - WASTE WATER TREATMENT |  |  |  | OL1-2I53-0013 | IE | [6 empty] | Transmitted
| INSTRUMENT LOOP DRAWINGS FAR-FL DCS, ESD, FGS - FLARE |  |  |  | OL1-2I53-0014 | IE | [6 empty] | Transmitted
| MR ORIFICE AND RESTRICTION ORIFICE |  |  |  | OL1-2I55-0101 | IE | [6 empty] | Transmitted
| MR PITOT TUBE |  |  |  | OL1-2I55-0102 | IE | [6 empty] | Transmitted
| MR ELECTROMAGNETIC FLOW METER |  |  |  | OL1-2I55-0103 | IE | [6 empty] | Transmitted
| MR ROTAMETERS |  |  |  | OL1-2I55-0104 | IE | [6 empty] | Transmitted
| MR MASS FLOW MET.CORIOLIS EFFECT |  |  |  | OL1-2I55-0106 | IE | [6 empty] | Transmitted
| MR VENTURI |  |  |  | OL1-2I55-0107 | IE | [6 empty] | Transmitted
| MR ULTRASONIC FLOW METER |  |  |  | OL1-2I55-0108 | IE | [6 empty] | Transmitted
| MR TURBINE METER |  |  |  | OL1-2I55-0111 | IE | [6 empty] | Transmitted
| MR VORTEX METER |  |  |  | OL1-2I55-0112 | IE | [6 empty] | Transmitted
| MR CUSTODY TRANSFER SYSTEM |  |  |  | OL1-2I55-0120 | IE | [6 empty] | Transmitted
| MR MAGNETIC LEVEL GAUGE |  |  |  | OL1-2I55-0202 | IE | [6 empty] | Transmitted
| MR RADAR LEVEL INSTRUMENTS |  |  |  | OL1-2I55-0203 | IE | [6 empty] | Transmitted
| MR SPECIAL LEVEL TRANSMITTERS |  |  |  | OL1-2I55-0211 | IE | [6 empty] | Transmitted
| MR LEVEL GLASS |  |  |  | OL1-2I55-0212 | IE | [6 empty] | Transmitted
| MR LEVEL GLASS FOR STEAM DRUM |  |  |  | OL1-2I55-0213 | IE | [6 empty] | Transmitted
| MR THERMOCOUPLE/RTD WITH WELL |  |  |  | OL1-2I55-0302 | IE | [6 empty] | Transmitted
| MR THERMOMETER WITH WELL |  |  |  | OL1-2I55-0304 | IE | [6 empty] | Transmitted
| MR MULTIPLE THERMOCOUPLE / RTD |  |  |  | OL1-2I55-0305 | IE | [6 empty] | Transmitted
| MR PRESSURE & DIFFER.PRESS.GAUGE |  |  |  | OL1-2I55-0402 | IE | [6 empty] | Transmitted
| MR CONTROL VALVES |  |  |  | OL1-2I55-0501 | IE | [6 empty] | Transmitted
| MR SPECIAL CONTROL VALVE |  |  |  | OL1-2I55-0503 | IE | [6 empty] | Transmitted
| MR SEVERE SERVICE CONTROL VALVE |  |  |  | OL1-2I55-0504 | IE | [6 empty] | Transmitted
| MR ANTISURGE VALVES |  |  |  | OL1-2I55-0505 | IE | [6 empty] | Transmitted
| MR DESUPERHEATER VALVES |  |  |  | OL1-2I55-0506 | IE | [6 empty] | Transmitted
| MR PNEUMATIC ON OFF VALVE |  |  |  | OL1-2I55-0606 | IE | [6 empty] | Transmitted
| MR SPECIAL ON OFF VALVES |  |  |  | OL1-2I55-0608 | IE | [6 empty] | Transmitted
| MR ELECTRIC OPERATED VALVES |  |  |  | OL1-2I55-0609 | IE | [6 empty] | Transmitted
| MR FOR PNEUMATIC ACTUATORS |  |  |  | OL1-2I55-0610 | IE | [6 empty] | Transmitted
| MR SAFETY RELIEF VALVE & RUPTURE DISKS |  |  |  | OL1-2I55-0701 | IE | [6 empty] | Transmitted
| MR ELECTRONIC TRANSMITTER |  |  |  | OL1-2I55-0801 | IE | [6 empty] | Transmitted
| MR INTEGRATED CONTROL AND SAFETY SYSTEMS |  |  |  | OL1-2I55-1001 | IE | [6 empty] | Transmitted
| MR MACHINE MONITORING SYSTEM |  |  |  | OL1-2I55-1701 | IE | [6 empty] | Transmitted
| MR ANALYSER HOUSE PACKAGE |  |  |  | OL1-2I55-2001 | IE | [6 empty] | Transmitted
| MR CEMS / O2 FLUE GAS |  |  |  | OL1-2I55-2002 | IE | [6 empty] | Transmitted
| INLINE INSTRUMENT REQUISITION - VORTEX FLOW ELEMENT |  |  |  | OL1-2I55-2004 | IE | [6 empty] | Transmitted
| INLINE INSTRUMENT REQUISITION - CONTROL VALVES |  |  |  | OL1-2I55-2201 | IE | [6 empty] | Transmitted
| INLINE INSTRUMENT REQUISITION - PRESSURE & SAFETY RELIEF VAVLE |  |  |  | OL1-2I55-2202 | IE | [6 empty] | Transmitted
| INLINE INSTRUMENT REQUISITION - RESTRICTION ORIFICE |  |  |  | OL1-2I55-2203 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - FLAME SCANNER |  |  |  | OL1-2I55-2205 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - GAUGES - GLASS/LEVEL GAUGES CLARK RELIANCE |  |  |  | OL1-2I55-2206 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - LEVEL TRANSMITTER |  |  |  | OL1-2I55-2207 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - O2 & COMBUSTIBLE ANALYZER |  |  |  | OL1-2I55-2208 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - PH/CONDUCTIVITY ANALYZER |  |  |  | OL1-2I55-2209 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - PRESSURE & DIFF PRESSURE TRANSMITTER |  |  |  | OL1-2I55-2210 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - PRESSURE GAUGES/DRAFT GAUGES |  |  |  | OL1-2I55-2211 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - TEMPERATURE TRANSMITTER |  |  |  | OL1-2I55-2212 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE FOR FURNACE PROFILE |  |  |  | OL1-2I55-2213 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE TYPE K / RTD WITH WELL |  |  |  | OL1-2I55-2214 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - THERMOCOUPLE WITH COT |  |  |  | OL1-2I55-2215 | IE | [6 empty] | Transmitted
| OFFLINE INSTRUMENT REQUISITION - LEVEL GAUGES - REFLUX TYPE |  |  |  | OL1-2I55-2216 | IE | [6 empty] | Transmitted
| MR SIMPLE SPECIFIC COMPONENT AND PROPERTY ANALYZERS |  |  |  | OL1-2I55-2301 | IE | [6 empty] | Transmitted
| MR WATER ANALYZERS |  |  |  | OL1-2I55-2401 | IE | [6 empty] | Transmitted
| MR FIRE AND GAS DEVICES |  |  |  | OL1-2I55-2601 | IE | [6 empty] | Transmitted
| MR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  |  |  | OL1-2I55-4101 | IE | [6 empty] | Transmitted
| MR CABLE TRAY AND ACCESSORIES |  |  |  | OL1-2I55-4201 | IE | [6 empty] | Transmitted
| MR FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  |  |  | OL1-2I55-4301 | IE | [6 empty] | Transmitted
| MR CABLE GLANDS |  |  |  | OL1-2I55-4302 | IE | [6 empty] | Transmitted
| MR MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  |  | OL1-2I55-4501 | IE | [6 empty] | Transmitted
| MR SUNSHADES |  |  |  | OL1-2I55-4502 | IE | [6 empty] | Transmitted
| MOUNTING ACCESSORIES (TUBING & FITTINGS) MATERIALTAKE-OFF |  |  |  | OL1-2I55-4503 | IE | [6 empty] | Transmitted
| MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) TAKE-OFF |  |  |  | OL1-2I55-4505 | IE | [6 empty] | Transmitted
| STEAM & ELECTRICALTRACING MAT.TAKE-OFF |  |  |  | OL1-2I55-4507 | IE | [6 empty] | Transmitted
| MR MAIN CABLE TRANSIT (MCT) & ACCESSORIES |  |  |  | OL1-2I55-4510 | IE | [6 empty] | Transmitted
| MR FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  |  |  | OL1-2I55-4511 | IE | [6 empty] | Transmitted
| ICSS EXTENT OF SUPPLY |  |  |  | OL1-2I57-1001 | IE | [6 empty] | Transmitted
| MACHINE MONITORING SYSTEM EXTENT OF SUPPLY |  |  |  | OL1-2I57-1701 | IE | [6 empty] | Transmitted
| PARTICULAR TECNICAL SPECIFICATION FOR MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  |  | OL1-2I57-4501 | IE | [6 empty] | Transmitted
| SIS IMPLEMENTATION CALCULATION NOTES |  |  |  | OL1-2I61-1101 | IE | [6 empty] | Transmitted
| GENERAL SIS SAFETY REQUIREMENTS SPECIFICATION |  |  |  | OL1-2I61-1102 | IE | [6 empty] | Transmitted
| PARTICULAR SIS SAFETY REQUIREMENTS SPECIFICATION |  |  |  | OL1-2I61-1103 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 10 |  |  |  | OL1-2I71-1001 | IE | [6 empty] | Transmitted
| COMPLEX CONTROL NARRATIVES (36M FURNACE) |  |  |  | OL1-2I71-1101 | IE | [6 empty] | Transmitted
| COMPLEX CONTROL NARRATIVES |  |  |  | OL1-2I71-1201 | IE | [6 empty] | Transmitted
| COMPLEX CONTROL NARRATIVES |  |  |  | OL1-2I71-1301 | IE | [6 empty] | Transmitted
| COMPLEX CONTROL NARRATIVES |  |  |  | OL1-2I71-1501 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 20 |  |  |  | OL1-2I71-2001 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 21 |  |  |  | OL1-2I71-2101 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 22 |  |  |  | OL1-2I71-2201 | IE | [6 empty] | Transmitted
| SEQUENCE NARRATIVES - AREA 22 |  |  |  | OL1-2I71-2202 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 23 |  |  |  | OL1-2I71-2301 | IE | [6 empty] | Transmitted
| SEQUENCE NARRATIVES - AREA 23 |  |  |  | OL1-2I71-2302 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 24 |  |  |  | OL1-2I71-2401 | IE | [6 empty] | Transmitted
| SEQUENCE NARRATIVES - AREA 24 |  |  |  | OL1-2I71-2402 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 25 |  |  |  | OL1-2I71-2501 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 26 |  |  |  | OL1-2I71-2601 | IE | [6 empty] | Transmitted
| SEQUENCE NARRATIVES - AREA 26 |  |  |  | OL1-2I71-2602 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 27 |  |  |  | OL1-2I71-2701 | IE | [6 empty] | Transmitted
| SEQUENCE NARRATIVES - AREA 27 |  |  |  | OL1-2I71-2702 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 28 |  |  |  | OL1-2I71-2801 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 29 |  |  |  | OL1-2I71-2901 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 30 |  |  |  | OL1-2I71-3001 | IE | [6 empty] | Transmitted
| COMPLEX CONTROL NARRATIVES |  |  |  | OL1-2I71-4001 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 50 |  |  |  | OL1-2I71-5001 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 53 |  |  |  | OL1-2I71-5301 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 55 |  |  |  | OL1-2I71-5501 | IE | [6 empty] | Transmitted
| COMPLEX LOOP NARRATIVES - AREA 56 |  |  |  | OL1-2I71-5601 | IE | [6 empty] | Transmitted
| COMPLEX CONTROL NARRATIVES |  |  |  | OL1-2I71-6001 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  |  |  | OL1-2I72-1001 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  |  |  | OL1-2I72-2001 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  |  |  | OL1-2I72-3001 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  |  |  | OL1-2I72-4001 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  |  |  | OL1-2I72-5001 | IE | [6 empty] | Transmitted
| CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  |  |  | OL1-2I72-6001 | IE | [6 empty] | Transmitted
| CTRL & SAFETY SYST.CONNECTION DIAG. |  |  |  | OL1-2I81-1001 | IE | [6 empty] | Transmitted
| CTRL & SAFETY SYST.ARCHITECTURE |  |  |  | OL1-2I81-1002 | IE | [6 empty] | Transmitted
| ELECTRIC.INSTRUMENT INTERF. |  |  |  | OL1-2I81-1003 | IE | [6 empty] | Transmitted
| GRAPHIC DISLAYS |  |  |  | OL1-2I81-1004 | IE | [6 empty] | Transmitted
| OPERATOR TREND DISPLAY DEFINITION |  |  |  | OL1-2I81-1005 | IE | [6 empty] | Transmitted
| ANALYZER SYST.BLOCK DIAGRAM |  |  |  | OL1-2I84-2001 | IE | [6 empty] | Transmitted
| ANALYZER SHELTER LAYOUT |  |  |  | OL1-2I84-2002 | IE | [6 empty] | Transmitted
| ANALYZER SAMPLE LOOP ARRANGEMENT |  |  |  | OL1-2I84-2003 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST |  |  |  | OL1-2I91-0001 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - SUBSTATION E & FAR E |  |  |  | OL1-2I91-0002 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - SUBSTATION C & FAR C |  |  |  | OL1-2I91-0003 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - FURNACES UTILITY |  |  |  | OL1-2I91-0004 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - QUENCH |  |  |  | OL1-2I91-0005 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - PROCESS 20B |  |  |  | OL1-2I91-0006 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - PROCESS 20C |  |  |  | OL1-2I91-0007 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - PROCESS COLD COMPRESSORS |  |  |  | OL1-2I91-0008 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - PROCESS CGC |  |  |  | OL1-2I91-0009 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - BUTADIENE |  |  |  | OL1-2I91-0010 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - COOLING WATER UNIT |  |  |  | OL1-2I91-0011 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - UTILITIES |  |  |  | OL1-2I91-0012 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - WASTE WATER TREATMENT |  |  |  | OL1-2I91-0013 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - FLARE |  |  |  | OL1-2I91-0014 | IE | [6 empty] | Transmitted
| INSTRUMENT CLASSES |  |  |  | OL1-2I91-0020 | IE | [6 empty] | Transmitted
| INSTRUMENT CONTROL SYSTEMS EQUIPMENT LIST |  |  |  | OL1-2I91-0100 | IE | [6 empty] | Transmitted
| ICSS DATA BASE |  |  |  | OL1-2I91-0102 | IE | [6 empty] | Transmitted
| INSTRUMENT RANGE, ALARM & TRIP LIST |  |  |  | OL1-2I91-0103 | IE | [6 empty] | Transmitted
| INSTRUMENT LIST - METERING |  |  |  | OL1-2I91-0104 | IE | [6 empty] | Transmitted
| IN/OUT SUMMARY |  |  |  | OL1-2I91-1001 | IE | [6 empty] | Transmitted
| INSTRUMENT INDEX |  |  |  | OL1-2I91-1002 | IE | [6 empty] | Transmitted
| FURNACE ANALYZER LIST |  |  |  | OL1-2I91-1003 | IE | [6 empty] | Transmitted
| ANALYZER LIST |  |  |  | OL1-2I91-2000 | IE | [6 empty] | Transmitted
| INSTRUMENT INDEX |  |  |  | OL1-2I91-2002 | IE | [6 empty] | Transmitted
| FURNACE ANALYZER LIST - FURNACES 10-H-1200 - 10-H-1500 |  |  |  | OL1-2I91-2003 | IE | [6 empty] | Transmitted
| INSTRUMENT INDEX |  |  |  | OL1-2I91-3002 | IE | [6 empty] | Transmitted
| FURNACE ANALYZER LIST - FURNACES 10-H-1300 |  |  |  | OL1-2I91-3003 | IE | [6 empty] | Transmitted
| INSTRUMENT INDEX |  |  |  | OL1-2I91-4002 | IE | [6 empty] | Transmitted
| FURNACE ANALYZER LIST - FURNACES 10-H-1400 |  |  |  | OL1-2I91-4003 | IE | [6 empty] | Transmitted
| INSTRUMENT INDEX |  |  |  | OL1-2I91-5002 | IE | [6 empty] | Transmitted
| FURNACE ANALYZER LIST - FURNACES 10-H-1500 |  |  |  | OL1-2I91-5003 | IE | [6 empty] | Transmitted
| INSTRUMENT INDEX |  |  |  | OL1-2I91-6002 | IE | [6 empty] | Transmitted
| FURNACE ANALYZER LIST - FURNACES 10-H-1600 |  |  |  | OL1-2I91-6003 | IE | [6 empty] | Transmitted
| JSS FOR ANALYSER SYSTEMS & HOUSES |  |  |  | OL1-2I92-0050 | IE | [6 empty] | Transmitted
| JSS MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  |  | OL1-2I92-0051 | IE | [6 empty] | Transmitted
| JSS CABLE TRAY AND ACCESSORIES |  |  |  | OL1-2I92-0052 | IE | [6 empty] | Transmitted
| JSS FOR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  |  |  | OL1-2I92-0053 | IE | [6 empty] | Transmitted
| JSS FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  |  |  | OL1-2I92-0054 | IE | [6 empty] | Transmitted
| JSS FOR CABLE GLANDS AND ACCESSORIES |  |  |  | OL1-2I92-0055 | IE | [6 empty] | Transmitted
| JSS FOR SUNSHADES |  |  |  | OL1-2I92-0056 | IE | [6 empty] | Transmitted
| JSS FOR CUSTODY TRANSFER SYSTEM |  |  |  | OL1-2I92-0057 | IE | [6 empty] | Transmitted
| JSS FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  |  |  | OL1-2I92-0058 | IE | [6 empty] | Transmitted
| JSS FOR MAIN CABLE TRANSIT & ACCESSORIES |  |  |  | OL1-2I92-0059 | IE | [6 empty] | Transmitted
| JSS FOR FIRE AND GAS DEVICES |  |  |  | OL1-2I92-0060 | IE | [6 empty] | Transmitted
| JSS FOR FLOW METER |  |  |  | OL1-2I92-0100 | IE | [6 empty] | Transmitted
| JSS DIFFERENTIAL PRESSURE FLOW ELEMENTS |  |  |  | OL1-2I92-0101 | IE | [6 empty] | Transmitted
| JSS LEVEL INSTRUMENTS |  |  |  | OL1-2I92-0200 | IE | [6 empty] | Transmitted
| JSS FOR SURGE PROTECTION DEVICES |  |  |  | OL1-2I92-0201 | IE | [6 empty] | Transmitted
| JSS TEMPERATURE INSTRUMENTS |  |  |  | OL1-2I92-0300 | IE | [6 empty] | Transmitted
| JSS FOR PRESSURE & DIFF.PRESSURE INSTRUMENTS |  |  |  | OL1-2I92-0301 | IE | [6 empty] | Transmitted
| JSS ANTISURGE VALVES |  |  |  | OL1-2I92-0404 | IE | [6 empty] | Transmitted
| JSS DESUPERHEATERS VALVES |  |  |  | OL1-2I92-0405 | IE | [6 empty] | Transmitted
| JSS CONTROL VALVES |  |  |  | OL1-2I92-0501 | IE | [6 empty] | Transmitted
| JSS SPECIAL CONTROL VALVE |  |  |  | OL1-2I92-0503 | IE | [6 empty] | Transmitted
| JSS SEVERE SERVICE CONTROL VALVE |  |  |  | OL1-2I92-0504 | IE | [6 empty] | Transmitted
| JSS FOR ELECTRIC OPERATED VALVES |  |  |  | OL1-2I92-0602 | IE | [6 empty] | Transmitted
| JSS FOR SPECIAL ON OFF VALVES |  |  |  | OL1-2I92-0603 | IE | [6 empty] | Transmitted
| JSS FOR ACTUATORS |  |  |  | OL1-2I92-0604 | IE | [6 empty] | Transmitted
| JSS FOR PNEUMATIC ON OFF VALVES |  |  |  | OL1-2I92-0606 | IE | [6 empty] | Transmitted
| JSS FOR SAFETY RELIEF VALVE & RUPTURE DISKS |  |  |  | OL1-2I92-0701 | IE | [6 empty] | Transmitted
| JSS ELECTRONIC TRANSMITER |  |  |  | OL1-2I92-0801 | IE | [6 empty] | Transmitted
| JSS FOR MACHINE MONITORING SYST. |  |  |  | OL1-2I92-1701 | IE | [6 empty] | Transmitted
| EMPLOYEE GRIEVANCE MANAGEMENT PLAN |  |  |  | OL1-2J92-0002 | HR | [6 empty] | Transmitted
| HUMAN RESOURCE POLICY AND PROCEDURES |  |  |  | OL1-2J93-0004 | HR | [6 empty] | Transmitted
| WORKER CODE OF CONDUCT DECLARATION FORM |  |  |  | OL1-2J94-0002 | HR | [6 empty] | Transmitted
| CHILD LABOR RISK ASSESSMENT CHECKLIST |  |  |  | OL1-2J94-0004 | HR | [6 empty] | Transmitted
| FORCED LABOR RISK ASSESSMENT CHECKLIST |  |  |  | OL1-2J94-0005 | HR | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CALC. |  |  |  | OL1-2K10-0001 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-E - TRANSFORMERS & WALLS STRUCTURAL CALC. |  |  |  | OL1-2K10-0002 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CALC. |  |  |  | OL1-2K10-0003 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-C - TRANSFORMERS & WALLS STRUCTURAL CALC.STRUCTURAL CALC. |  |  |  | OL1-2K10-0004 | CV | [6 empty] | Transmitted
| GATEHOUSE - STRUCTURAL CALC. |  |  |  | OL1-2K10-0005 | CV | [6 empty] | Transmitted
| OPERATION TOOL ROOM - STRUCTURAL CALC. |  |  |  | OL1-2K10-0006 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PILES |  |  |  | OL1-2K11-0001 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR ROAD AND PAVING THICKNESS |  |  |  | OL1-2K12-0001 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-H-1100 |  |  |  | OL1-2K13-0001 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-H-1200/1600 |  |  |  | OL1-2K13-0002 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-1950 |  |  |  | OL1-2K13-0003 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5200 |  |  |  | OL1-2K13-0004 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-5200 |  |  |  | OL1-2K13-0005 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-5210 |  |  |  | OL1-2K13-0006 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2120 |  |  |  | OL1-2K13-0007 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2140 |  |  |  | OL1-2K13-0008 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2110 |  |  |  | OL1-2K13-0009 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5150 |  |  |  | OL1-2K13-0010 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2160 |  |  |  | OL1-2K13-0011 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2165 |  |  |  | OL1-2K13-0012 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2136 |  |  |  | OL1-2K13-0013 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2160 |  |  |  | OL1-2K13-0014 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2125A |  |  |  | OL1-2K13-0015 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2136 |  |  |  | OL1-2K13-0016 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2165A/D |  |  |  | OL1-2K13-0017 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2166 |  |  |  | OL1-2K13-0018 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2145 |  |  |  | OL1-2K13-0019 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2146 |  |  |  | OL1-2K13-0020 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2026 |  |  |  | OL1-2K13-0021 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2048 |  |  |  | OL1-2K13-0022 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-P-5102A/B |  |  |  | OL1-2K13-0023 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION PUMPS 10-P-2026A/B, 10-P-2126A/B, 10-P-2046A/B, 10-P-5140A/B, 10-P-2146A/B |  |  |  | OL1-2K13-0024 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-P-2105A/B AND 10-P-2006A/B/C |  |  |  | OL1-2K13-0025 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2105A/B |  |  |  | OL1-2K13-0026 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2009A/B |  |  |  | OL1-2K13-0027 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2008A/B/C |  |  |  | OL1-2K13-0028 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2026A/B |  |  |  | OL1-2K13-0029 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2028A/B |  |  |  | OL1-2K13-0030 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2136A/B |  |  |  | OL1-2K13-0031 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-X-2755 |  |  |  | OL1-2K13-0032 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-X-2036 |  |  |  | OL1-2K13-0033 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2440 |  |  |  | OL1-2K13-0034 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2450 |  |  |  | OL1-2K13-0035 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2300 |  |  |  | OL1-2K13-0036 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2330 |  |  |  | OL1-2K13-0037 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2410A/B/C |  |  |  | OL1-2K13-0038 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2435 |  |  |  | OL1-2K13-0039 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2436 |  |  |  | OL1-2K13-0040 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2240 |  |  |  | OL1-2K13-0041 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2245 |  |  |  | OL1-2K13-0042 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2445 |  |  |  | OL1-2K13-0043 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2455 |  |  |  | OL1-2K13-0044 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2220 |  |  |  | OL1-2K13-0045 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2210 |  |  |  | OL1-2K13-0046 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2230 |  |  |  | OL1-2K13-0047 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2405 |  |  |  | OL1-2K13-0048 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2415 |  |  |  | OL1-2K13-0049 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2310 |  |  |  | OL1-2K13-0050 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2312 |  |  |  | OL1-2K13-0051 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2316 |  |  |  | OL1-2K13-0052 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2326 |  |  |  | OL1-2K13-0053 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2330 |  |  |  | OL1-2K13-0054 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2411 |  |  |  | OL1-2K13-0055 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-2910 |  |  |  | OL1-2K13-0056 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2435 |  |  |  | OL1-2K13-0057 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2230A/B |  |  |  | OL1-2K13-0058 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2412 |  |  |  | OL1-2K13-0059 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2413 |  |  |  | OL1-2K13-0060 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2432 |  |  |  | OL1-2K13-0061 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2445A/B |  |  |  | OL1-2K13-0062 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2446 |  |  |  | OL1-2K13-0063 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2455A/B |  |  |  | OL1-2K13-0064 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2450 |  |  |  | OL1-2K13-0065 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2470 |  |  |  | OL1-2K13-0066 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2206 |  |  |  | OL1-2K13-0067 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2210A/B |  |  |  | OL1-2K13-0068 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2220A/B |  |  |  | OL1-2K13-0069 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2240A/B |  |  |  | OL1-2K13-0070 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2305 |  |  |  | OL1-2K13-0071 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2630 |  |  |  | OL1-2K13-0072 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2326 |  |  |  | OL1-2K13-0073 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2320A/B |  |  |  | OL1-2K13-0074 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2310A/B |  |  |  | OL1-2K13-0075 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2306A/B |  |  |  | OL1-2K13-0076 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  |  |  | OL1-2K13-0077 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  |  |  | OL1-2K13-0078 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-5112A/B, 10-P-2714A/B, 10-P-2710A/B, 10-P-2720A/B, 10-P-2721A/B, 10-P-2910 |  |  |  | OL1-2K13-0079 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-2724A/B, 10-P-2726A/B, 10-P-2750A/B, 10-P-2760A/B/C, 10-P-2705A/B |  |  |  | OL1-2K13-0080 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-P-5100A/B/C |  |  |  | OL1-2K13-0081 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-2900/2902/2906 |  |  |  | OL1-2K13-0082 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-2920 |  |  |  | OL1-2K13-0083 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-1920 |  |  |  | OL1-2K13-0084 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-2350 |  |  |  | OL1-2K13-0085 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5555 |  |  |  | OL1-2K13-0086 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-2048A/B |  |  |  | OL1-2K13-0087 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2580 |  |  |  | OL1-2K13-0088 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2640 |  |  |  | OL1-2K13-0089 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2570 |  |  |  | OL1-2K13-0090 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2510, 10-D-2510 AND 10-E-2510 |  |  |  | OL1-2K13-0091 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2540, 10-D-2540 AND 10-E-2540 |  |  |  | OL1-2K13-0092 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2520 AND 10-D-2520 |  |  |  | OL1-2K13-0093 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2480A |  |  |  | OL1-2K13-0094 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2465 |  |  |  | OL1-2K13-0095 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2840 |  |  |  | OL1-2K13-0096 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2830 |  |  |  | OL1-2K13-0097 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2815 |  |  |  | OL1-2K13-0098 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2820 |  |  |  | OL1-2K13-0099 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2810 |  |  |  | OL1-2K13-0100 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2645 |  |  |  | OL1-2K13-0101 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2555 |  |  |  | OL1-2K13-0102 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2550 |  |  |  | OL1-2K13-0103 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5628, 10-PIT-5628, P-10-5628A/B |  |  |  | OL1-2K13-0104 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2575 |  |  |  | OL1-2K13-0105 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2880 |  |  |  | OL1-2K13-0106 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2870 |  |  |  | OL1-2K13-0107 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2860 |  |  |  | OL1-2K13-0108 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2865 |  |  |  | OL1-2K13-0109 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5632 |  |  |  | OL1-2K13-0110 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2587 |  |  |  | OL1-2K13-0111 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2850, 10-E-2850 |  |  |  | OL1-2K13-0112 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2305 |  |  |  | OL1-2K13-0113 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2575 |  |  |  | OL1-2K13-0114 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2576 |  |  |  | OL1-2K13-0115 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2645A/B |  |  |  | OL1-2K13-0116 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2502 |  |  |  | OL1-2K13-0117 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2515 |  |  |  | OL1-2K13-0118 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2546 |  |  |  | OL1-2K13-0119 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2548 |  |  |  | OL1-2K13-0120 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2545 |  |  |  | OL1-2K13-0121 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2805A/B |  |  |  | OL1-2K13-0122 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2807 |  |  |  | OL1-2K13-0123 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2809 |  |  |  | OL1-2K13-0124 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2857 |  |  |  | OL1-2K13-0125 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2858 |  |  |  | OL1-2K13-0126 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2856 |  |  |  | OL1-2K13-0127 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2855 |  |  |  | OL1-2K13-0128 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2853 |  |  |  | OL1-2K13-0129 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2852 |  |  |  | OL1-2K13-0130 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2582 |  |  |  | OL1-2K13-0132 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2504 |  |  |  | OL1-2K13-0133 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF PSA PACKAGE 10-PK-2560, 10-D-2560A/F, 10-D-2565 |  |  |  | OL1-2K13-0134 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-2570A/B, 10-P-2575A/B, 10-P-2586A/B, 10-P-2647, 10-P-2646A/B |  |  |  | OL1-2K13-0135 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-2801A/B, 10-P-2805A/B, 10-P-2815, 10-P-2855A/B |  |  |  | OL1-2K13-0136 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-2930, 10-D-2930 AND 10-P-2930 |  |  |  | OL1-2K13-0137 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-R-2700A/B |  |  |  | OL1-2K13-0138 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-R-2760 |  |  |  | OL1-2K13-0139 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2620 |  |  |  | OL1-2K13-0140 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2666 |  |  |  | OL1-2K13-0141 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2665A/B |  |  |  | OL1-2K13-0142 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2660 |  |  |  | OL1-2K13-0143 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2710 |  |  |  | OL1-2K13-0144 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2720 |  |  |  | OL1-2K13-0145 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2660 |  |  |  | OL1-2K13-0146 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2630 |  |  |  | OL1-2K13-0147 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-R-2470A/B/C |  |  |  | OL1-2K13-0148 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2610 |  |  |  | OL1-2K13-0149 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2600A/B |  |  |  | OL1-2K13-0150 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2460 |  |  |  | OL1-2K13-0151 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2440 |  |  |  | OL1-2K13-0152 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-1000 |  |  |  | OL1-2K13-0153 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2635 |  |  |  | OL1-2K13-0154 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2636 |  |  |  | OL1-2K13-0155 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2472 |  |  |  | OL1-2K13-0156 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2474 |  |  |  | OL1-2K13-0157 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2465 |  |  |  | OL1-2K13-0158 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2460 |  |  |  | OL1-2K13-0159 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2440/2441/2442 |  |  |  | OL1-2K13-0160 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-1020 |  |  |  | OL1-2K13-0161 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-1015 |  |  |  | OL1-2K13-0162 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-1001A/B |  |  |  | OL1-2K13-0163 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-1000 |  |  |  | OL1-2K13-0164 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-1005 |  |  |  | OL1-2K13-0165 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-2912 |  |  |  | OL1-2K13-0166 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-2922 |  |  |  | OL1-2K13-0167 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-2940 |  |  |  | OL1-2K13-0168 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2705 |  |  |  | OL1-2K13-0169 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2706 |  |  |  | OL1-2K13-0170 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2735 |  |  |  | OL1-2K13-0171 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2724 |  |  |  | OL1-2K13-0172 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2730 |  |  |  | OL1-2K13-0173 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2722 |  |  |  | OL1-2K13-0174 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2755 |  |  |  | OL1-2K13-0175 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2725A/B |  |  |  | OL1-2K13-0176 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2726 |  |  |  | OL1-2K13-0177 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2702 |  |  |  | OL1-2K13-0179 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2701 |  |  |  | OL1-2K13-0180 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2706 |  |  |  | OL1-2K13-0181 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2008A/B/C |  |  |  | OL1-2K13-0182 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2710 |  |  |  | OL1-2K13-0183 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2720 |  |  |  | OL1-2K13-0184 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2720 |  |  |  | OL1-2K13-0185 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2724 |  |  |  | OL1-2K13-0186 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2714 |  |  |  | OL1-2K13-0187 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2882 AND 10-D-2882 |  |  |  | OL1-2K13-0188 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2884 AND 10-D-2884 |  |  |  | OL1-2K13-0189 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2715A/B |  |  |  | OL1-2K13-0190 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2100A/B/C/D/E/F |  |  |  | OL1-2K13-0191 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-2705 |  |  |  | OL1-2K13-0192 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-2320 |  |  |  | OL1-2K13-0193 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-1050 |  |  |  | OL1-2K13-0194 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-1910 |  |  |  | OL1-2K13-0195 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5910 |  |  |  | OL1-2K13-0196 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5914 |  |  |  | OL1-2K13-0197 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5912 |  |  |  | OL1-2K13-0198 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-2914 |  |  |  | OL1-2K13-0199 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF IGNITION SYSTEM |  |  |  | OL1-2K13-0200 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION FOR 10-C-3070 |  |  |  | OL1-2K13-0201 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-3900 |  |  |  | OL1-2K13-0202 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-3000 |  |  |  | OL1-2K13-0203 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-3040 |  |  |  | OL1-2K13-0204 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-3020 |  |  |  | OL1-2K13-0205 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-3010 |  |  |  | OL1-2K13-0206 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-3030 |  |  |  | OL1-2K13-0207 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-3050 |  |  |  | OL1-2K13-0208 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-3060 |  |  |  | OL1-2K13-0209 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-3080 |  |  |  | OL1-2K13-0210 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-3090 |  |  |  | OL1-2K13-0211 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-3070 |  |  |  | OL1-2K13-0212 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-3100, 10-A-3100 |  |  |  | OL1-2K13-0213 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-3126 |  |  |  | OL1-2K13-0214 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-3908 |  |  |  | OL1-2K13-0215 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-3902 |  |  |  | OL1-2K13-0216 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-3904 |  |  |  | OL1-2K13-0217 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-3906 |  |  |  | OL1-2K13-0218 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-3180 |  |  |  | OL1-2K13-0219 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-3110 |  |  |  | OL1-2K13-0220 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3004A/B |  |  |  | OL1-2K13-0221 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3014A/B |  |  |  | OL1-2K13-0222 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3015 |  |  |  | OL1-2K13-0223 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3084 |  |  |  | OL1-2K13-0224 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3085A/B |  |  |  | OL1-2K13-0225 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3095 |  |  |  | OL1-2K13-0226 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3096 |  |  |  | OL1-2K13-0227 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3098 |  |  |  | OL1-2K13-0228 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3055A/B |  |  |  | OL1-2K13-0229 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3045A/B/C/D |  |  |  | OL1-2K13-0230 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3044 |  |  |  | OL1-2K13-0231 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2585 |  |  |  | OL1-2K13-0232 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3150 |  |  |  | OL1-2K13-0233 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3160 |  |  |  | OL1-2K13-0234 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3005 |  |  |  | OL1-2K13-0235 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-3070 |  |  |  | OL1-2K13-0236 | CV | [6 empty] | Transmitted
| CALCULATION FOR FOUNDATION OF METERING STATION |  |  |  | OL1-2K13-0237 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-2765 |  |  |  | OL1-2K13-0238 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5560 |  |  |  | OL1-2K13-0239 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5560 |  |  |  | OL1-2K13-0240 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5394 |  |  |  | OL1-2K13-0241 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5398 |  |  |  | OL1-2K13-0242 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5355 |  |  |  | OL1-2K13-0243 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5392 |  |  |  | OL1-2K13-0244 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5390 |  |  |  | OL1-2K13-0245 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5396 |  |  |  | OL1-2K13-0246 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5550 |  |  |  | OL1-2K13-0247 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5500 |  |  |  | OL1-2K13-0248 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5510 |  |  |  | OL1-2K13-0249 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5513 |  |  |  | OL1-2K13-0250 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5515 |  |  |  | OL1-2K13-0251 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5520 |  |  |  | OL1-2K13-0252 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-C-5520A/B |  |  |  | OL1-2K13-0253 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-5510 |  |  |  | OL1-2K13-0254 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-5513 |  |  |  | OL1-2K13-0255 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-5640 |  |  |  | OL1-2K13-0256 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-5675A/B |  |  |  | OL1-2K13-0257 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-5676 |  |  |  | OL1-2K13-0258 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TX/C-2550 |  |  |  | OL1-2K13-0259 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-C-5650A/B |  |  |  | OL1-2K13-0260 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2800, 10-E-2800 |  |  |  | OL1-2K13-0261 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-C-2850, 10-E-2850 |  |  |  | OL1-2K13-0262 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-C-2200, 10-E-2200 |  |  |  | OL1-2K13-0263 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5627, 10-PIT-5627, P-10-5627A/B |  |  |  | OL1-2K13-0264 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5397 |  |  |  | OL1-2K13-0265 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5692 |  |  |  | OL1-2K13-0266 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5693 |  |  |  | OL1-2K13-0267 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5694 |  |  |  | OL1-2K13-0268 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5671 |  |  |  | OL1-2K13-0269 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5672 |  |  |  | OL1-2K13-0270 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5697 |  |  |  | OL1-2K13-0271 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5690 |  |  |  | OL1-2K13-0272 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5691 |  |  |  | OL1-2K13-0273 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5670 |  |  |  | OL1-2K13-0274 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-P-5670A/B, 10-P-5671A/B, 10-P-5644A/B, 10-P-5645A/B, 10-P-5646A/B, 10-P-5647A/B, 10-P-5675, 10-P-5676 |  |  |  | OL1-2K13-0275 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5646 AND 10-X-5646 |  |  |  | OL1-2K13-0276 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5644 |  |  |  | OL1-2K13-0277 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5644 |  |  |  | OL1-2K13-0278 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5653 |  |  |  | OL1-2K13-0279 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5650 |  |  |  | OL1-2K13-0280 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-5110 |  |  |  | OL1-2K13-0281 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-5120 |  |  |  | OL1-2K13-0282 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-5130 |  |  |  | OL1-2K13-0283 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5552 |  |  |  | OL1-2K13-0284 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5565 |  |  |  | OL1-2K13-0285 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-1950, 10-C-1950A/B, 10-E-1951A/B |  |  |  | OL1-2K13-0286 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5140 |  |  |  | OL1-2K13-0287 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5400 |  |  |  | OL1-2K13-0288 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5114 |  |  |  | OL1-2K13-0289 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-D-5112, 10-E-5112 |  |  |  | OL1-2K13-0290 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-5520 |  |  |  | OL1-2K13-0291 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-5113 |  |  |  | OL1-2K13-0292 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-5220 |  |  |  | OL1-2K13-0293 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-F-5610 |  |  |  | OL1-2K13-0294 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-5552 |  |  |  | OL1-2K13-0295 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-E-5110 |  |  |  | OL1-2K13-0296 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5191 |  |  |  | OL1-2K13-0297 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5192 |  |  |  | OL1-2K13-0298 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5115, 10-F-5115A/B/C |  |  |  | OL1-2K13-0299 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5125, 10-D-5125A/B, 10-F-5125A/B |  |  |  | OL1-2K13-0300 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-P-2106A/B/C |  |  |  | OL1-2K13-0301 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR SKID 10-P-2201A/B |  |  |  | OL1-2K13-0302 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-P-5360A/B/C |  |  |  | OL1-2K13-0303 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-5670 |  |  |  | OL1-2K13-0304 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5695 |  |  |  | OL1-2K13-0305 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-5900A/B, 10-P-5950A/B |  |  |  | OL1-2K13-0306 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-P-5350 A/B/C/D/E/F/G/H |  |  |  | OL1-2K13-0307 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-3080A/B, 10-P-3030A/B, 10-P-3000A/B, 10-P-3020A/B, 10-P-3061A/B, 10-P-3060A/B, 10-P-3062A/B, 10-P-3002A/B, 10-P-3902A/B, 10-P-3904A/B |  |  |  | OL1-2K13-0308 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-3096A/B, 10-P-3086A/B, 10-P-3036A/B, 10-P-3016A/B, 10-P-3900, 10-P-3160A/B, 10-P-3076A/B, 10-P-3906A/B, 10-P-3908A/B, 10-P-3110A/B, 10-P-3126A/B |  |  |  | OL1-2K13-0309 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-3046A/B |  |  |  | OL1-2K13-0310 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-3045A/B |  |  |  | OL1-2K13-0311 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-3026A/B |  |  |  | OL1-2K13-0312 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-3056A/B |  |  |  | OL1-2K13-0313 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-R-2620A |  |  |  | OL1-2K13-0314 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2450A/B, 10-P-2455A/B, 10-P-2620A/B, 10-P-2666A/B, 10-P-2660A/B |  |  |  | OL1-2K13-0315 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2630A/B, 10-P-2310A/B, 10-P-2316A/B, 10-P-2326A/B, 10-P-2320A/B |  |  |  | OL1-2K13-0316 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-2302A/B, 10-P-2415A/B, 10-P-2445A/B, 10-P-2304, 10-P-2306A/B |  |  |  | OL1-2K13-0317 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-2200A/B, 10-P-2220A/B, 10-P-2210A/B |  |  |  | OL1-2K13-0318 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 |  |  |  | OL1-2K13-0319 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-5550A/B, 10-P-5552 |  |  |  | OL1-2K13-0320 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B |  |  |  | OL1-2K13-0321 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2000 |  |  |  | OL1-2K13-0322 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2020 |  |  |  | OL1-2K13-0323 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-T-2100 |  |  |  | OL1-2K13-0324 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR CONCRETE STRUCTURE OF 10-T-2040 |  |  |  | OL1-2K13-0325 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5605 |  |  |  | OL1-2K13-0326 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5610 |  |  |  | OL1-2K13-0327 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2390 |  |  |  | OL1-2K13-0328 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5603 |  |  |  | OL1-2K13-0329 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5604 |  |  |  | OL1-2K13-0330 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2090 |  |  |  | OL1-2K13-0331 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2190 |  |  |  | OL1-2K13-0332 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2790 |  |  |  | OL1-2K13-0333 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2322 |  |  |  | OL1-2K13-0334 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-3190 |  |  |  | OL1-2K13-0335 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5601 |  |  |  | OL1-2K13-0336 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5600 |  |  |  | OL1-2K13-0337 | CV | [6 empty] | Transmitted
| CALCULATION OF BASIN FOR COOLING TOWER 10-PIT-5350 |  |  |  | OL1-2K13-0338 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5370 |  |  |  | OL1-2K13-0339 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5602 |  |  |  | OL1-2K13-0340 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-2392 |  |  |  | OL1-2K13-0341 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5658 |  |  |  | OL1-2K13-0342 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5615 |  |  |  | OL1-2K13-0343 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5656 |  |  |  | OL1-2K13-0344 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5620A/B/C |  |  |  | OL1-2K13-0345 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5630 |  |  |  | OL1-2K13-0346 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5633 |  |  |  | OL1-2K13-0347 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5631 |  |  |  | OL1-2K13-0348 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5671 |  |  |  | OL1-2K13-0349 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5650A/B |  |  |  | OL1-2K13-0350 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5655 |  |  |  | OL1-2K13-0351 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-5696 |  |  |  | OL1-2K13-0352 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF CLARIFIER 10-TK-5651A/B |  |  |  | OL1-2K13-0353 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-X-2310 |  |  |  | OL1-2K13-0354 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF SUPPORTS |  |  |  | OL1-2K13-0355 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0356 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0357 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0358 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0359 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0360 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0361 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0362 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0363 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0364 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0365 | CV | [6 empty] | Transmitted
| CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5900 |  |  |  | OL1-2K13-0366 | CV | [6 empty] | Transmitted
| CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5950 |  |  |  | OL1-2K13-0367 | CV | [6 empty] | Transmitted
| CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2320 |  |  |  | OL1-2K13-0368 | CV | [6 empty] | Transmitted
| CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2910 |  |  |  | OL1-2K13-0369 | CV | [6 empty] | Transmitted
| CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-3900 |  |  |  | OL1-2K13-0370 | CV | [6 empty] | Transmitted
| CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-PK-1910 |  |  |  | OL1-2K13-0371 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS FLARE UNIT |  |  |  | OL1-2K13-0372 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0373 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0374 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0375 | CV | [6 empty] | Transmitted
| CALCULATION FOR FOUNDATION OF SUPPORTS |  |  |  | OL1-2K13-0376 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0377 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR 10-SLW-5T02 |  |  |  | OL1-2K13-0378 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR 10-SLW-5T01 |  |  |  | OL1-2K13-0379 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR 10-SLW-0C01 |  |  |  | OL1-2K13-0380 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR 10-SLW-5W01 |  |  |  | OL1-2K13-0381 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR 10-SLW-5F01 |  |  |  | OL1-2K13-0382 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0383 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0384 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0385 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0386 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0387 | CV | [6 empty] | Transmitted
| CALCULATION FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0388 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0389 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K13-0390 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K13-0391 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF PLATFORMS |  |  |  | OL1-2K13-0392 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-5900 |  |  |  | OL1-2K13-0393 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-TK-5950 |  |  |  | OL1-2K13-0394 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-X-2312 |  |  |  | OL1-2K13-0395 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR SKID 10-P-2801A/B |  |  |  | OL1-2K13-0396 | CV | [6 empty] | Transmitted
| CALCULATION FOR BASIN 10-PIT-5642 |  |  |  | OL1-2K13-0398 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-PK-2904 |  |  |  | OL1-2K13-0399 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P01 |  |  |  | OL1-2K14-0001 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P01 |  |  |  | OL1-2K14-0002 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P02 |  |  |  | OL1-2K14-0003 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P02 |  |  |  | OL1-2K14-0004 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-3A01 |  |  |  | OL1-2K14-0005 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-3A01 |  |  |  | OL1-2K14-0006 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5U01 |  |  |  | OL1-2K14-0007 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-5U01 |  |  |  | OL1-2K14-0008 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2D01 |  |  |  | OL1-2K14-0009 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2D01 |  |  |  | OL1-2K14-0010 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2E01 |  |  |  | OL1-2K14-0011 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2E01 |  |  |  | OL1-2K14-0012 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2A01 |  |  |  | OL1-2K14-0013 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2A01 |  |  |  | OL1-2K14-0014 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2B01 |  |  |  | OL1-2K14-0015 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2B01 |  |  |  | OL1-2K14-0016 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2C01 |  |  |  | OL1-2K14-0017 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2C01 |  |  |  | OL1-2K14-0018 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5T01 |  |  |  | OL1-2K14-0019 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-0P03 |  |  |  | OL1-2K14-0020 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5F01 |  |  |  | OL1-2K14-0021 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-5F01 |  |  |  | OL1-2K14-0022 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2E01 |  |  |  | OL1-2K14-0023 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D01 |  |  |  | OL1-2K14-0024 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D02 |  |  |  | OL1-2K14-0025 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D03 |  |  |  | OL1-2K14-0026 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D04 |  |  |  | OL1-2K14-0027 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A06 |  |  |  | OL1-2K14-0028 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATIONOF 10-STR-3A03 |  |  |  | OL1-2K14-0029 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A05 |  |  |  | OL1-2K14-0030 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A04 |  |  |  | OL1-2K14-0031 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A02 |  |  |  | OL1-2K14-0032 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A01 |  |  |  | OL1-2K14-0033 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-SHT-3A01 |  |  |  | OL1-2K14-0034 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T01 |  |  |  | OL1-2K14-0035 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T02 |  |  |  | OL1-2K14-0036 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-5U01 |  |  |  | OL1-2K14-0037 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E01 |  |  |  | OL1-2K14-0038 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  |  |  | OL1-2K14-0039 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E03 |  |  |  | OL1-2K14-0040 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E04 |  |  |  | OL1-2K14-0041 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D05 |  |  |  | OL1-2K14-0042 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-0P01 |  |  |  | OL1-2K14-0043 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A01 |  |  |  | OL1-2K14-0044 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A02 |  |  |  | OL1-2K14-0045 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A03 |  |  |  | OL1-2K14-0046 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B01 |  |  |  | OL1-2K14-0047 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B02 |  |  |  | OL1-2K14-0048 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B03 |  |  |  | OL1-2K14-0049 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B04 |  |  |  | OL1-2K14-0050 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B05 |  |  |  | OL1-2K14-0051 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B06 |  |  |  | OL1-2K14-0052 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2D01 |  |  |  | OL1-2K14-0053 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2D02 |  |  |  | OL1-2K14-0054 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C01 |  |  |  | OL1-2K14-0055 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C02 |  |  |  | OL1-2K14-0056 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C03 |  |  |  | OL1-2K14-0057 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C04 |  |  |  | OL1-2K14-0058 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C05 |  |  |  | OL1-2K14-0059 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2B01 |  |  |  | OL1-2K14-0060 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-SHT-1B01 |  |  |  | OL1-2K14-0061 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF WASTE STORAGE BUILDING |  |  |  | OL1-2K14-0062 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF LUBRIFICATION OIL & GREASE STORAGE |  |  |  | OL1-2K14-0063 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF GAS CYLINDER STORAGE |  |  |  | OL1-2K14-0064 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF TOOL ROOM OPERATION |  |  |  | OL1-2K14-0065 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-0P03 |  |  |  | OL1-2K14-0066 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2B02 |  |  |  | OL1-2K14-0067 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-2B02 |  |  |  | OL1-2K14-0068 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE ARCK 10-PRK-2C02 |  |  |  | OL1-2K14-0069 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T03 |  |  |  | OL1-2K14-0070 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR FOUNDATION OF STORAGE SHELTER FOR CHENICALS |  |  |  | OL1-2K14-0071 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2C02 |  |  |  | OL1-2K14-0169 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P01 |  |  |  | OL1-2K15-0001 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P02 |  |  |  | OL1-2K15-0002 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-3A01 |  |  |  | OL1-2K15-0003 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-5U01 |  |  |  | OL1-2K15-0004 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2D01 |  |  |  | OL1-2K15-0005 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2E01 |  |  |  | OL1-2K15-0006 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2A01 |  |  |  | OL1-2K15-0007 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2B01 |  |  |  | OL1-2K15-0008 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2C01 |  |  |  | OL1-2K15-0009 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-5T01 |  |  |  | OL1-2K15-0010 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL 10-PRK-5F01 |  |  |  | OL1-2K15-0011 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL OF 10-SHT-2E01 |  |  |  | OL1-2K15-0012 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E01 |  |  |  | OL1-2K15-0013 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E02 |  |  |  | OL1-2K15-0014 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E03 |  |  |  | OL1-2K15-0015 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E04 |  |  |  | OL1-2K15-0016 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-2D05 |  |  |  | OL1-2K15-0017 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B01 |  |  |  | OL1-2K15-0018 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B02 |  |  |  | OL1-2K15-0019 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B03 |  |  |  | OL1-2K15-0020 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B04 |  |  |  | OL1-2K15-0021 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B05 |  |  |  | OL1-2K15-0022 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B06 |  |  |  | OL1-2K15-0023 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2D01 |  |  |  | OL1-2K15-0024 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2D02 |  |  |  | OL1-2K15-0025 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C01 |  |  |  | OL1-2K15-0026 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C02 |  |  |  | OL1-2K15-0027 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C03 |  |  |  | OL1-2K15-0028 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C04 |  |  |  | OL1-2K15-0029 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C05 |  |  |  | OL1-2K15-0030 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-2B01 |  |  |  | OL1-2K15-0031 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-1B01 |  |  |  | OL1-2K15-0032 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-0P01 |  |  |  | OL1-2K15-0033 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A01 |  |  |  | OL1-2K15-0034 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A02 |  |  |  | OL1-2K15-0035 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A03 |  |  |  | OL1-2K15-0036 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-2D01 |  |  |  | OL1-2K15-0037 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-2D02 |  |  |  | OL1-2K15-0038 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-2D03 |  |  |  | OL1-2K15-0039 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-2D04 |  |  |  | OL1-2K15-0040 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL FOR WASTE STORAGE BUILDING |  |  |  | OL1-2K15-0041 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL FOR LUBRIFICATION OIL & GREASE STORAGE |  |  |  | OL1-2K15-0042 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL FOR GAS CYLINDER STORAGE |  |  |  | OL1-2K15-0043 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL FOR TOOL ROOM OPERATION |  |  |  | OL1-2K15-0044 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-0P03 |  |  |  | OL1-2K15-0045 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-3A06 |  |  |  | OL1-2K15-0046 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-3A03 |  |  |  | OL1-2K15-0047 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-3A05 |  |  |  | OL1-2K15-0048 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-3A04 |  |  |  | OL1-2K15-0049 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-3A02 |  |  |  | OL1-2K15-0050 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-STR-3A01 |  |  |  | OL1-2K15-0051 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-SHT-3A01 |  |  |  | OL1-2K15-0052 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-SHT-5T01 |  |  |  | OL1-2K15-0053 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-SHT-5T02 |  |  |  | OL1-2K15-0054 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-5U01 |  |  |  | OL1-2K15-0055 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2B02 |  |  |  | OL1-2K15-0056 | CV | [6 empty] | Transmitted
| CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2C02 |  |  |  | OL1-2K15-0057 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL FOR STORAGE SHELTER FOR CHENICALS |  |  |  | OL1-2K15-0058 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL STRUCTURE 10-SHT-5T03 |  |  |  | OL1-2K15-0059 | CV | [6 empty] | Transmitted
| UNDERGROUND CALCULATION NOTES |  |  |  | OL1-2K16-0001 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE OF 10-C-2200, 10-E-2200 |  |  |  | OL1-2K18-0001 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE OF 10-C-2800, 10-E-2800 |  |  |  | OL1-2K18-0002 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE OF 10-T-2040 |  |  |  | OL1-2K18-0003 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL COOLING TOWER 5350 |  |  |  | OL1-2K18-0004 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0005 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0006 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0007 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0008 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0009 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0010 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0011 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0012 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0013 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0014 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS FLARE UNIT |  |  |  | OL1-2K18-0015 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0016 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0017 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0018 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0019 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0020 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0021 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0022 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0023 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0024 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0025 | CV | [6 empty] | Transmitted
| CALCULATION FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0026 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0027 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL SUPPORTS |  |  |  | OL1-2K18-0028 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL STRUCTURE OF 10-C-2850, 10-E-2850 |  |  |  | OL1-2K18-0029 | CV | [6 empty] | Transmitted
| CALCULATION NOTE FOR STEEL PLATFORMS |  |  |  | OL1-2K18-0128 | CV | [6 empty] | Transmitted
| KEY PLAN FOR INSTALLATION DWGS |  |  |  | OL1-2K25-0001 | CV | [6 empty] | Transmitted
| KEY PLAN FOR STRUCTURES |  |  |  | OL1-2K25-0002 | CV | [6 empty] | Transmitted
| ROADS, PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0001 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0002 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0003 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0004 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0005 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0006 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0007 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0008 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0009 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0010 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0011 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0012 | CV | [6 empty] | Transmitted
| ROADS , PAVING AND FINISHING LAYOUT |  |  |  | OL1-2K27-0013 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS |  |  |  | OL1-2K29-0001 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - TRANSFORMERS BAY CONSTR. DWGS |  |  |  | OL1-2K29-0020 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS |  |  |  | OL1-2K29-0030 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - TRANSFORMERS BAY CONSTR. DWGS |  |  |  | OL1-2K29-0060 | CV | [6 empty] | Transmitted
| GATEHOUSE - STRUCTURAL CONSTR. DWGS |  |  |  | OL1-2K29-0070 | CV | [6 empty] | Transmitted
| OPERATION TOOL ROOM - STRUCTURAL CONSTR. DWGS |  |  |  | OL1-2K29-0080 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - ARCHITECTURAL CONSTR. DWGS |  |  |  | OL1-2K30-0001 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - PLUMBING DWGS |  |  |  | OL1-2K30-0010 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - ARCHITECTURAL CONSTR. DWGS |  |  |  | OL1-2K30-0015 | CV | [6 empty] | Transmitted
| ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - PLUMBING DWGS |  |  |  | OL1-2K30-0025 | CV | [6 empty] | Transmitted
| GATEHOUSE - ARCHITECTURAL CONSTR. DWGS |  |  |  | OL1-2K30-0030 | CV | [6 empty] | Transmitted
| GATEHOUSE - PLUMBING |  |  |  | OL1-2K30-0035 | CV | [6 empty] | Transmitted
| OPERATION TOOL ROOM - ARCHITECTURAL CONSTR. DWGS |  |  |  | OL1-2K30-0040 | CV | [6 empty] | Transmitted
| OPERATION TOOL ROOM - PLUMBING |  |  |  | OL1-2K30-0045 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P01 |  |  |  | OL1-2K31-1000 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P01 |  |  |  | OL1-2K31-1020 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P02 |  |  |  | OL1-2K31-1040 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P02 |  |  |  | OL1-2K31-1060 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-0P03 |  |  |  | OL1-2K31-1080 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-0P03 |  |  |  | OL1-2K31-1100 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-3A01 |  |  |  | OL1-2K31-1120 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 |  |  |  | OL1-2K31-1140 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-5U01 |  |  |  | OL1-2K31-1160 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-5U01 |  |  |  | OL1-2K31-1180 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2D01 |  |  |  | OL1-2K31-1200 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2D01 |  |  |  | OL1-2K31-1220 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2E01 |  |  |  | OL1-2K31-1240 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2E01 |  |  |  | OL1-2K31-1260 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2A01 |  |  |  | OL1-2K31-1280 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2A01 |  |  |  | OL1-2K31-1300 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2B01 |  |  |  | OL1-2K31-1320 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2B02 |  |  |  | OL1-2K31-1340 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2B01 |  |  |  | OL1-2K31-1360 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2B02 |  |  |  | OL1-2K31-1380 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2C01 |  |  |  | OL1-2K31-1400 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2C02 |  |  |  | OL1-2K31-1420 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2C01 |  |  |  | OL1-2K31-1440 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-2C02 |  |  |  | OL1-2K31-1480 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-5T01 |  |  |  | OL1-2K31-1500 | CV | [6 empty] | Transmitted
| PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-5F01 |  |  |  | OL1-2K31-1520 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PRK-5F01 |  |  |  | OL1-2K31-1540 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2E01 |  |  |  | OL1-2K31-1560 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  |  |  | OL1-2K31-1580 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2E03 |  |  |  | OL1-2K31-1600 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2E04 |  |  |  | OL1-2K31-1620 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D05 |  |  |  | OL1-2K31-1640 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2B01 |  |  |  | OL1-2K31-1660 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2B02 |  |  |  | OL1-2K31-1680 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2B03 |  |  |  | OL1-2K31-1700 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2B04 |  |  |  | OL1-2K31-1720 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2B05 |  |  |  | OL1-2K31-1740 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2B06 |  |  |  | OL1-2K31-1760 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-SHT-2D01 |  |  |  | OL1-2K31-1780 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-SHT-2D02 |  |  |  | OL1-2K31-1800 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2C01 |  |  |  | OL1-2K31-1820 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2C02 |  |  |  | OL1-2K31-1840 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2C03 |  |  |  | OL1-2K31-1860 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2C04 |  |  |  | OL1-2K31-1880 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2C05 |  |  |  | OL1-2K31-1900 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-SHT-2B01 |  |  |  | OL1-2K31-1920 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-SHT-1B01 |  |  |  | OL1-2K31-1940 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-0P01 |  |  |  | OL1-2K31-1960 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2A01 |  |  |  | OL1-2K31-1980 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2A02 |  |  |  | OL1-2K31-2000 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-2A03 |  |  |  | OL1-2K31-2020 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR WASTE STORAGE BUILDING |  |  |  | OL1-2K31-2040 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STORAGE SHELTER FOR CHENICALS |  |  |  | OL1-2K31-2060 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR LUBRIFICATION OIL & GREASE STORAGE |  |  |  | OL1-2K31-2080 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR GAS CYLINDER STORAGE |  |  |  | OL1-2K31-2100 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR TOOL ROOM OPERATION |  |  |  | OL1-2K31-2120 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-SHT-2E01 |  |  |  | OL1-2K31-2140 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 |  |  |  | OL1-2K31-2160 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D02 |  |  |  | OL1-2K31-2180 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D03 |  |  |  | OL1-2K31-2200 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D04 |  |  |  | OL1-2K31-2220 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A06 |  |  |  | OL1-2K31-2240 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A03 |  |  |  | OL1-2K31-2260 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A05 |  |  |  | OL1-2K31-2280 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A04 |  |  |  | OL1-2K31-2300 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A02 |  |  |  | OL1-2K31-2320 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 |  |  |  | OL1-2K31-2340 | CV | [6 empty] | Transmitted
| FOUNDATION FOR STRUCTURE 10-SHT-3A01 |  |  |  | OL1-2K31-2360 | CV | [6 empty] | Transmitted
| FOUNDATION FOR STRUCTURE 10-SHT-5T01 |  |  |  | OL1-2K31-2380 | CV | [6 empty] | Transmitted
| FOUNDATION FOR STRUCTURE 10-SHT-5T02 |  |  |  | OL1-2K31-2400 | CV | [6 empty] | Transmitted
| FOUNDATION FOR STRUCTURE 10-SHT-5T03 |  |  |  | OL1-2K31-2420 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-STR-5U01 |  |  |  | OL1-2K31-2440 | CV | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (36M FURNACE) |  |  |  | OL1-2K32-1001 | CV | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (36M FURNACE) |  |  |  | OL1-2K32-1003 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-3A01 |  |  |  | OL1-2K32-1060 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-5U01 |  |  |  | OL1-2K32-1080 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-2D01 |  |  |  | OL1-2K32-1100 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-2E01 |  |  |  | OL1-2K32-1120 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-2A01 |  |  |  | OL1-2K32-1140 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-2B01 |  |  |  | OL1-2K32-1160 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-2B02 |  |  |  | OL1-2K32-1180 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-2C01 |  |  |  | OL1-2K32-1200 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-2C02 |  |  |  | OL1-2K32-1220 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-5T01 |  |  |  | OL1-2K32-1240 | CV | [6 empty] | Transmitted
| STEEL FOR 10-PRK-5F01 |  |  |  | OL1-2K32-1260 | CV | [6 empty] | Transmitted
| STEEL FOR 10-SHT-2E01 |  |  |  | OL1-2K32-1280 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2E01 |  |  |  | OL1-2K32-1300 | CV | [6 empty] | Transmitted
| FURNACE STEEL END WALL TUBE SHEET DETAILS |  |  |  | OL1-2K32-1304 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2E02 |  |  |  | OL1-2K32-1320 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2E03 |  |  |  | OL1-2K32-1340 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2E04 |  |  |  | OL1-2K32-1360 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2D05 |  |  |  | OL1-2K32-1380 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2B01 |  |  |  | OL1-2K32-1400 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2B02 |  |  |  | OL1-2K32-1420 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2B03 |  |  |  | OL1-2K32-1440 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2B04 |  |  |  | OL1-2K32-1460 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2B05 |  |  |  | OL1-2K32-1480 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2B06 |  |  |  | OL1-2K32-1500 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  |  |  | OL1-2K32-1511 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  |  |  | OL1-2K32-1512 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  |  |  | OL1-2K32-1513 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  |  |  | OL1-2K32-1514 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  |  |  | OL1-2K32-1515 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL SHADOW BOX DETAILS |  |  |  | OL1-2K32-1516 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-1517 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-1518 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-1519 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  |  |  | OL1-2K32-1520 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  |  |  | OL1-2K32-1521 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  |  |  | OL1-2K32-1522 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL END WALL TUBE SHEET ELEVATION |  |  |  | OL1-2K32-1523 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL END WALL TUBE SHEET DETAILS |  |  |  | OL1-2K32-1524 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL END WALL TUBE SHEET DETAILS |  |  |  | OL1-2K32-1525 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CONVECTION SECTION HEADER BOX ELEVATIONS |  |  |  | OL1-2K32-1526 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CONVECTION SECTION HEADER BOX DETAILS |  |  |  | OL1-2K32-1527 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  |  |  | OL1-2K32-1528 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  |  |  | OL1-2K32-1529 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  |  |  | OL1-2K32-1530 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  |  |  | OL1-2K32-1531 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  |  |  | OL1-2K32-1532 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  |  |  | OL1-2K32-1533 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  |  |  | OL1-2K32-1534 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  |  |  | OL1-2K32-1535 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  |  |  | OL1-2K32-1536 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  |  |  | OL1-2K32-1537 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CONVECTION SECTIONS AND DETAILS |  |  |  | OL1-2K32-1538 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  |  |  | OL1-2K32-1539 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-1540 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-1541 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-1542 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-1543 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-1544 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-1545 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL NAME PLATE |  |  |  | OL1-2K32-1546 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STACK AND DETAILS |  |  |  | OL1-2K32-1550 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  |  |  | OL1-2K32-1551 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  |  |  | OL1-2K32-1552 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  |  |  | OL1-2K32-1553 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-1560 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-1561 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL BREECHING PLAN AND ELEVATIONS |  |  |  | OL1-2K32-1580 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL BREECHING SECTIONS AND DETAILS |  |  |  | OL1-2K32-1581 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL DUCT PLAN AND ELEVATIONS |  |  |  | OL1-2K32-1582 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  |  |  | OL1-2K32-1583 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  |  |  | OL1-2K32-1584 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  |  |  | OL1-2K32-1585 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  |  |  | OL1-2K32-1586 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  |  |  | OL1-2K32-1587 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2C03 |  |  |  | OL1-2K32-1600 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  |  |  | OL1-2K32-1601 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  |  |  | OL1-2K32-1602 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  |  |  | OL1-2K32-1603 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  |  |  | OL1-2K32-1604 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  |  |  | OL1-2K32-1605 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  |  |  | OL1-2K32-1606 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  |  |  | OL1-2K32-1607 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-1608 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  |  |  | OL1-2K32-1609 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  |  |  | OL1-2K32-1610 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-1611 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  |  |  | OL1-2K32-1612 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  |  |  | OL1-2K32-1613 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  |  |  | OL1-2K32-1614 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  |  |  | OL1-2K32-1615 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  |  |  | OL1-2K32-1616 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  |  |  | OL1-2K32-1617 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-1618 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-1619 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-1620 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-1621 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-1622 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-1623 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-1631 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-1632 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2C05 |  |  |  | OL1-2K32-1640 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL ID FAN BOLTING PLAN |  |  |  | OL1-2K32-1641 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  |  |  | OL1-2K32-1651 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-SHT-2B01 |  |  |  | OL1-2K32-1660 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-SHT-1B01 |  |  |  | OL1-2K32-1680 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-0P01 |  |  |  | OL1-2K32-1700 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-1701 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-1702 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-1703 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-1704 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-1705 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-1706 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  |  |  | OL1-2K32-1707 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  |  |  | OL1-2K32-1708 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2A01 |  |  |  | OL1-2K32-1720 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2A02 |  |  |  | OL1-2K32-1740 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2A03 |  |  |  | OL1-2K32-1760 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2D01 |  |  |  | OL1-2K32-1780 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2D02 |  |  |  | OL1-2K32-1800 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2D03 |  |  |  | OL1-2K32-1820 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2D04 |  |  |  | OL1-2K32-1840 | CV | [6 empty] | Transmitted
| STEEL FOR WASTE STORAGE BUILDING |  |  |  | OL1-2K32-1860 | CV | [6 empty] | Transmitted
| STEEL FOR STORAGE SHELTER FOR CHEMICALS |  |  |  | OL1-2K32-1880 | CV | [6 empty] | Transmitted
| STEEL FOR LUBRIFICATION OIL & GREASE STORAGE |  |  |  | OL1-2K32-1900 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  |  |  | OL1-2K32-1901 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  |  |  | OL1-2K32-1902 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  |  |  | OL1-2K32-1903 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  |  |  | OL1-2K32-1904 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  |  |  | OL1-2K32-1905 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  |  |  | OL1-2K32-1906 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL CABLE TRAY SUPPORTS |  |  |  | OL1-2K32-1907 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-1908 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-1909 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  |  |  | OL1-2K32-1910 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-1911 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-1912 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-1913 | CV | [6 empty] | Transmitted
| USC "36M" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-1914 | CV | [6 empty] | Transmitted
| STEEL FOR GAS CYLINDER STORAGE |  |  |  | OL1-2K32-1920 | CV | [6 empty] | Transmitted
| STEEL FOR TOOL ROOM OPERATION |  |  |  | OL1-2K32-1940 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-3A06 |  |  |  | OL1-2K32-1960 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-3A03 |  |  |  | OL1-2K32-1980 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-3A05 |  |  |  | OL1-2K32-2000 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-3A04 |  |  |  | OL1-2K32-2020 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-3A02 |  |  |  | OL1-2K32-2040 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-3A01 |  |  |  | OL1-2K32-2060 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-SHT-3A01 |  |  |  | OL1-2K32-2080 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-SHT-2D01 |  |  |  | OL1-2K32-2100 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-SHT-2D02 |  |  |  | OL1-2K32-2120 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2C01 |  |  |  | OL1-2K32-2140 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2C02 |  |  |  | OL1-2K32-2160 | CV | [6 empty] | Transmitted
| FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-2161 | CV | [6 empty] | Transmitted
| FURNACE STEEL MOMENT CONNECTION DETAIL AND MISCELLANEOUS DETAILS |  |  |  | OL1-2K32-2162 | CV | [6 empty] | Transmitted
| FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-2163 | CV | [6 empty] | Transmitted
| FURNACE STEEL STANDARD FLOOR - TOE PLATE DETAILS |  |  |  | OL1-2K32-2164 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-2C04 |  |  |  | OL1-2K32-2180 | CV | [6 empty] | Transmitted
| FURNACE STEEL END WALL TUBE SHEET DETAILS |  |  |  | OL1-2K32-2304 | CV | [6 empty] | Transmitted
| USC "132U" & "36M" FURNACE GENERAL NOTES & ABBREVIATIONS |  |  |  | OL1-2K32-2500 | CV | [6 empty] | Transmitted
| USC "132U" & "36M" FURNACE STEEL FOUNDATION PLAN & LOADING DIAGRAM |  |  |  | OL1-2K32-2501 | CV | [6 empty] | Transmitted
| USC "132U" & "36M" FURNACE STEEL BASE PLATE DETAILS |  |  |  | OL1-2K32-2502 | CV | [6 empty] | Transmitted
| USC "132U" & "36M" FURNACE STEEL MISCELLANEOUS FOUNDATION PLAN & LOADING DIAGRAM |  |  |  | OL1-2K32-2503 | CV | [6 empty] | Transmitted
| USC "132U" & "36M" FURNACE STEEL MISCELLANEOUS FOUNDATION PLAN & LOADING DIAGRAM |  |  |  | OL1-2K32-2504 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  |  |  | OL1-2K32-2511 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  |  |  | OL1-2K32-2512 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  |  |  | OL1-2K32-2513 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  |  |  | OL1-2K32-2514 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  |  |  | OL1-2K32-2515 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  |  |  | OL1-2K32-2516 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-2517 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-2518 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-2519 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  |  |  | OL1-2K32-2520 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  |  |  | OL1-2K32-2521 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  |  |  | OL1-2K32-2522 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-2540 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-2541 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-2542 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-2543 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-2544 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-2545 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STACK AND DETAILS |  |  |  | OL1-2K32-2550 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  |  |  | OL1-2K32-2551 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  |  |  | OL1-2K32-2552 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  |  |  | OL1-2K32-2553 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-2560 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-2561 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  |  |  | OL1-2K32-2583 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  |  |  | OL1-2K32-2584 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  |  |  | OL1-2K32-2585 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  |  |  | OL1-2K32-2586 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  |  |  | OL1-2K32-2587 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  |  |  | OL1-2K32-2601 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  |  |  | OL1-2K32-2602 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  |  |  | OL1-2K32-2603 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  |  |  | OL1-2K32-2604 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  |  |  | OL1-2K32-2605 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  |  |  | OL1-2K32-2606 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  |  |  | OL1-2K32-2607 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-2608 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  |  |  | OL1-2K32-2609 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  |  |  | OL1-2K32-2610 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-2611 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  |  |  | OL1-2K32-2612 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  |  |  | OL1-2K32-2613 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  |  |  | OL1-2K32-2614 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  |  |  | OL1-2K32-2615 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  |  |  | OL1-2K32-2616 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  |  |  | OL1-2K32-2617 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-2618 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-2619 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-2620 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-2621 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-2622 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-2623 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-2631 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-2632 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  |  |  | OL1-2K32-2651 | CV | [6 empty] | Transmitted
| USC "132U" & "36M" FURNACE STEEL MOMENT CONNECTION DETAIL & MISCELLANEOUS DETAILS |  |  |  | OL1-2K32-2659 | CV | [6 empty] | Transmitted
| USC "132U" & "36M" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-2660 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-2701 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-2702 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-2703 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-2704 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-2705 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-2706 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  |  |  | OL1-2K32-2707 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  |  |  | OL1-2K32-2708 | CV | [6 empty] | Transmitted
| USC FURNACE STEEL ELEVATOR ACCESS PLATFORM |  |  |  | OL1-2K32-2801 | CV | [6 empty] | Transmitted
| USC FURNACE STEEL ELEVATOR PLANS |  |  |  | OL1-2K32-2802 | CV | [6 empty] | Transmitted
| USC FURNACE STEEL ELEVATOR PLANS |  |  |  | OL1-2K32-2803 | CV | [6 empty] | Transmitted
| USC FURNACE STEEL ELEVATOR PLANS |  |  |  | OL1-2K32-2804 | CV | [6 empty] | Transmitted
| USC FURNACE STEEL ELEVATOR PLANS |  |  |  | OL1-2K32-2805 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-2908 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-2909 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  |  |  | OL1-2K32-2910 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-2911 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-2912 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-2913 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-2914 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-SHT-5T01 |  |  |  | OL1-2K32-3000 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-SHT-5T02 |  |  |  | OL1-2K32-3020 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-SHT-5T03 |  |  |  | OL1-2K32-3040 | CV | [6 empty] | Transmitted
| STEEL FOR STRUCTURE 10-STR-5U01 |  |  |  | OL1-2K32-3060 | CV | [6 empty] | Transmitted
| FURNACE STEEL END WALL TUBE SHEET DETAILS |  |  |  | OL1-2K32-3304 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  |  |  | OL1-2K32-3511 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  |  |  | OL1-2K32-3512 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  |  |  | OL1-2K32-3513 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  |  |  | OL1-2K32-3514 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  |  |  | OL1-2K32-3515 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  |  |  | OL1-2K32-3516 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-3517 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-3518 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-3519 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  |  |  | OL1-2K32-3520 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  |  |  | OL1-2K32-3521 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  |  |  | OL1-2K32-3522 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-3540 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-3541 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-3542 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-3543 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-3544 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-3545 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL NAME PLATE |  |  |  | OL1-2K32-3546 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STACK AND DETAILS |  |  |  | OL1-2K32-3550 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  |  |  | OL1-2K32-3551 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  |  |  | OL1-2K32-3552 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  |  |  | OL1-2K32-3553 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-3560 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-3561 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  |  |  | OL1-2K32-3583 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  |  |  | OL1-2K32-3584 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  |  |  | OL1-2K32-3585 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  |  |  | OL1-2K32-3586 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  |  |  | OL1-2K32-3587 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  |  |  | OL1-2K32-3601 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  |  |  | OL1-2K32-3602 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  |  |  | OL1-2K32-3603 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  |  |  | OL1-2K32-3604 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  |  |  | OL1-2K32-3605 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  |  |  | OL1-2K32-3606 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  |  |  | OL1-2K32-3607 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-3608 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  |  |  | OL1-2K32-3609 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  |  |  | OL1-2K32-3610 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-3611 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  |  |  | OL1-2K32-3612 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  |  |  | OL1-2K32-3613 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  |  |  | OL1-2K32-3614 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  |  |  | OL1-2K32-3615 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  |  |  | OL1-2K32-3616 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  |  |  | OL1-2K32-3617 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-3618 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-3619 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-3620 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-3621 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-3622 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-3623 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-3631 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-3632 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  |  |  | OL1-2K32-3651 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-3701 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-3702 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-3703 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-3704 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-3705 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-3706 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  |  |  | OL1-2K32-3707 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  |  |  | OL1-2K32-3708 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-3908 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-3909 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  |  |  | OL1-2K32-3910 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-3911 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-3912 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-3913 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-3914 | CV | [6 empty] | Transmitted
| FURNACE STEEL END WALL TUBE SHEET DETAILS |  |  |  | OL1-2K32-4304 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  |  |  | OL1-2K32-4511 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  |  |  | OL1-2K32-4512 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  |  |  | OL1-2K32-4513 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  |  |  | OL1-2K32-4514 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  |  |  | OL1-2K32-4515 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  |  |  | OL1-2K32-4516 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-4517 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-4518 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-4519 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  |  |  | OL1-2K32-4520 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  |  |  | OL1-2K32-4521 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  |  |  | OL1-2K32-4522 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-4540 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-4541 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-4542 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-4543 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-4544 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-4545 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL NAME PLATE |  |  |  | OL1-2K32-4546 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STACK AND DETAILS |  |  |  | OL1-2K32-4550 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  |  |  | OL1-2K32-4551 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  |  |  | OL1-2K32-4552 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  |  |  | OL1-2K32-4553 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-4560 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-4561 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  |  |  | OL1-2K32-4583 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  |  |  | OL1-2K32-4584 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  |  |  | OL1-2K32-4585 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  |  |  | OL1-2K32-4586 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  |  |  | OL1-2K32-4587 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  |  |  | OL1-2K32-4601 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  |  |  | OL1-2K32-4602 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  |  |  | OL1-2K32-4603 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  |  |  | OL1-2K32-4604 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  |  |  | OL1-2K32-4605 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  |  |  | OL1-2K32-4606 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  |  |  | OL1-2K32-4607 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-4608 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  |  |  | OL1-2K32-4609 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  |  |  | OL1-2K32-4610 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-4611 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  |  |  | OL1-2K32-4612 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  |  |  | OL1-2K32-4613 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  |  |  | OL1-2K32-4614 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  |  |  | OL1-2K32-4615 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  |  |  | OL1-2K32-4616 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  |  |  | OL1-2K32-4617 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-4618 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-4619 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-4620 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-4621 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-4622 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-4623 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-4631 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-4632 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  |  |  | OL1-2K32-4651 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-4701 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-4702 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-4703 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-4704 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-4705 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-4706 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  |  |  | OL1-2K32-4707 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  |  |  | OL1-2K32-4708 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-4908 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-4909 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  |  |  | OL1-2K32-4910 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-4911 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-4912 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-4913 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-4914 | CV | [6 empty] | Transmitted
| FURNACE STEEL END WALL TUBE SHEET DETAILS |  |  |  | OL1-2K32-5304 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  |  |  | OL1-2K32-5511 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  |  |  | OL1-2K32-5512 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  |  |  | OL1-2K32-5513 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  |  |  | OL1-2K32-5514 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  |  |  | OL1-2K32-5515 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  |  |  | OL1-2K32-5516 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-5517 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-5518 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-5519 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  |  |  | OL1-2K32-5520 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  |  |  | OL1-2K32-5521 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  |  |  | OL1-2K32-5522 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-5540 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-5541 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-5542 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-5543 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-5544 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-5545 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL NAME PLATE |  |  |  | OL1-2K32-5546 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STACK AND DETAILS |  |  |  | OL1-2K32-5550 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL INSTRUMENT CONNECTION DETAILS |  |  |  | OL1-2K32-5551 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  |  |  | OL1-2K32-5552 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  |  |  | OL1-2K32-5553 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-5560 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-5561 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  |  |  | OL1-2K32-5583 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  |  |  | OL1-2K32-5584 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  |  |  | OL1-2K32-5585 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  |  |  | OL1-2K32-5586 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  |  |  | OL1-2K32-5587 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  |  |  | OL1-2K32-5601 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  |  |  | OL1-2K32-5602 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  |  |  | OL1-2K32-5603 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  |  |  | OL1-2K32-5604 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  |  |  | OL1-2K32-5605 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  |  |  | OL1-2K32-5606 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  |  |  | OL1-2K32-5607 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-5608 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  |  |  | OL1-2K32-5609 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  |  |  | OL1-2K32-5610 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-5611 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  |  |  | OL1-2K32-5612 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  |  |  | OL1-2K32-5613 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  |  |  | OL1-2K32-5614 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  |  |  | OL1-2K32-5615 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  |  |  | OL1-2K32-5616 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  |  |  | OL1-2K32-5617 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-5618 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-5619 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-5620 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-5621 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-5622 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-5623 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-5631 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-5632 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  |  |  | OL1-2K32-5651 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-5701 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-5702 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-5703 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-5704 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-5705 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-5706 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  |  |  | OL1-2K32-5707 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  |  |  | OL1-2K32-5708 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-5908 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-5909 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  |  |  | OL1-2K32-5910 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-5911 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-5912 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-5913 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-5914 | CV | [6 empty] | Transmitted
| FURNACE STEEL END WALL TUBE SHEET DETAILS |  |  |  | OL1-2K32-6304 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT FLOOR & RADIANT ARCH PLANS |  |  |  | OL1-2K32-6511 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D1 |  |  |  | OL1-2K32-6512 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SIDE WALL AT COL LINE A1 AND D2 |  |  |  | OL1-2K32-6513 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT END WALL AT COL LINE 1 AND 5 |  |  |  | OL1-2K32-6514 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRANSITION FLOOR PLAN & SECTIONS |  |  |  | OL1-2K32-6515 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SHADOW BOX DETAILS |  |  |  | OL1-2K32-6516 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-6517 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-6518 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT SECTIONS & DETAILS |  |  |  | OL1-2K32-6519 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COL LINE B1 |  |  |  | OL1-2K32-6520 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL VIEW OF CONVECTION SIDE WALL AT COLUMN LINE C1 |  |  |  | OL1-2K32-6521 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL MATCH BOLTING PLANS FOR FIELD SPLICE AT EL 148'-2 1/2" & EL 221'-10" |  |  |  | OL1-2K32-6522 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-6540 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-6541 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-6542 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-6543 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-6544 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL SECTIONS AND DETAILS |  |  |  | OL1-2K32-6545 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL NAME PLATE |  |  |  | OL1-2K32-6546 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STACK AND DETAILS |  |  |  | OL1-2K32-6550 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT COIL REMOVAL / ACCESS DOOR DETAILS |  |  |  | OL1-2K32-6552 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL RADIANT TUBE REMOVAL DOOR PANEL |  |  |  | OL1-2K32-6553 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-6560 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  |  | OL1-2K32-6561 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  |  |  | OL1-2K32-6583 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  |  |  | OL1-2K32-6584 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  |  |  | OL1-2K32-6585 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  |  |  | OL1-2K32-6586 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  |  |  | OL1-2K32-6587 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. AA |  |  |  | OL1-2K32-6601 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. BB |  |  |  | OL1-2K32-6602 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. CC |  |  |  | OL1-2K32-6603 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL.DD |  |  |  | OL1-2K32-6604 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  |  |  | OL1-2K32-6605 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  |  |  | OL1-2K32-6606 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  |  |  | OL1-2K32-6607 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-6608 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  |  |  | OL1-2K32-6609 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  |  |  | OL1-2K32-6610 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  |  | OL1-2K32-6611 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  |  |  | OL1-2K32-6612 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  |  |  | OL1-2K32-6613 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  |  |  | OL1-2K32-6614 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  |  |  | OL1-2K32-6615 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  |  |  | OL1-2K32-6616 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  |  |  | OL1-2K32-6617 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-6618 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-6619 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-6620 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-6621 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-6622 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  |  | OL1-2K32-6623 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-6631 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL PIPE SUPPORT & DETAILS |  |  |  | OL1-2K32-6632 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  |  |  | OL1-2K32-6651 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-6701 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER ELEVATION VIEWS |  |  |  | OL1-2K32-6702 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-6703 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-6704 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-6705 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER PLANS |  |  |  | OL1-2K32-6706 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  |  |  | OL1-2K32-6707 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  |  |  | OL1-2K32-6708 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-6908 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  |  | OL1-2K32-6909 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  |  |  | OL1-2K32-6910 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-6911 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-6912 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-6913 | CV | [6 empty] | Transmitted
| USC "132U" FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  |  | OL1-2K32-6914 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-0P01 |  |  |  | OL1-2K32-7000 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-0P02 |  |  |  | OL1-2K32-7100 | CV | [6 empty] | Transmitted
| STEEL FOR PIPE RACK 10-PRK-0P03 |  |  |  | OL1-2K32-7200 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-5670 |  |  |  | OL1-2K34-0001 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5628, 10-PIT-5628, P-10-5628A/B |  |  |  | OL1-2K34-0002 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-1950, 10-C-1950A/B, 10-E-1951A/B |  |  |  | OL1-2K34-0003 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2765 |  |  |  | OL1-2K34-0004 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2585 |  |  |  | OL1-2K34-0005 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SKID 10-P-2801A/B |  |  |  | OL1-2K34-0006 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5200 |  |  |  | OL1-2K34-0007 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-5200 |  |  |  | OL1-2K34-0008 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-5210 |  |  |  | OL1-2K34-0009 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-5220 |  |  |  | OL1-2K34-0010 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-5610 |  |  |  | OL1-2K34-0011 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2120 |  |  |  | OL1-2K34-0012 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2140 |  |  |  | OL1-2K34-0013 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2110 |  |  |  | OL1-2K34-0014 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5150 |  |  |  | OL1-2K34-0015 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2160 |  |  |  | OL1-2K34-0016 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2165 |  |  |  | OL1-2K34-0017 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2136 |  |  |  | OL1-2K34-0018 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2125A |  |  |  | OL1-2K34-0019 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2136 |  |  |  | OL1-2K34-0020 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2160 |  |  |  | OL1-2K34-0021 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2165A/D |  |  |  | OL1-2K34-0022 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2166 |  |  |  | OL1-2K34-0023 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2146 |  |  |  | OL1-2K34-0024 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2145 |  |  |  | OL1-2K34-0025 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2026 |  |  |  | OL1-2K34-0026 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2048 |  |  |  | OL1-2K34-0027 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-P-2106A/B/C |  |  |  | OL1-2K34-0028 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-2026A/B, 10-P-2126A/B, 10-P-2046A/B, 10-P-5140A/B, 10-P-2146A/B |  |  |  | OL1-2K34-0029 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-P-2105A/B AND 10-P-2006A/B/C |  |  |  | OL1-2K34-0030 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2105A/B |  |  |  | OL1-2K34-0031 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2009A/B |  |  |  | OL1-2K34-0032 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2008A/B/C |  |  |  | OL1-2K34-0033 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2026A/B |  |  |  | OL1-2K34-0034 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2028A/B |  |  |  | OL1-2K34-0035 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2136A/B |  |  |  | OL1-2K34-0036 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-X-2755 |  |  |  | OL1-2K34-0037 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-X-2036 |  |  |  | OL1-2K34-0038 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2450 |  |  |  | OL1-2K34-0039 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2300 |  |  |  | OL1-2K34-0040 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2440 |  |  |  | OL1-2K34-0041 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2330 |  |  |  | OL1-2K34-0042 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2410A/B/C |  |  |  | OL1-2K34-0043 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2435 |  |  |  | OL1-2K34-0044 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2436 |  |  |  | OL1-2K34-0045 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2240 |  |  |  | OL1-2K34-0046 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2245 |  |  |  | OL1-2K34-0047 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2445 |  |  |  | OL1-2K34-0048 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2455 |  |  |  | OL1-2K34-0049 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2220 |  |  |  | OL1-2K34-0050 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2210 |  |  |  | OL1-2K34-0051 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2230 |  |  |  | OL1-2K34-0052 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2405 |  |  |  | OL1-2K34-0053 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2415 |  |  |  | OL1-2K34-0054 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2310 |  |  |  | OL1-2K34-0055 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2312 |  |  |  | OL1-2K34-0056 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2316 |  |  |  | OL1-2K34-0057 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2326 |  |  |  | OL1-2K34-0058 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2330 |  |  |  | OL1-2K34-0059 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-2910 |  |  |  | OL1-2K34-0060 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2435 |  |  |  | OL1-2K34-0061 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2230A/B |  |  |  | OL1-2K34-0062 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2412 |  |  |  | OL1-2K34-0063 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2413 |  |  |  | OL1-2K34-0064 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2445A/B |  |  |  | OL1-2K34-0065 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2446 |  |  |  | OL1-2K34-0066 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2455A/B |  |  |  | OL1-2K34-0067 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2450 |  |  |  | OL1-2K34-0068 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2470 |  |  |  | OL1-2K34-0069 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2206 |  |  |  | OL1-2K34-0070 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2210A/B |  |  |  | OL1-2K34-0071 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2220A/B |  |  |  | OL1-2K34-0072 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2240A/B |  |  |  | OL1-2K34-0073 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2305 |  |  |  | OL1-2K34-0074 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2305 |  |  |  | OL1-2K34-0075 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2630 |  |  |  | OL1-2K34-0076 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2326 |  |  |  | OL1-2K34-0077 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-2302A/B, 10-P-2415A/B, 10-P-2445A/B, 10-P-2304, 10-P-2306A/B |  |  |  | OL1-2K34-0078 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-2200A/B, 10-P-2220A/B, 10-P-10-P-2210A/B |  |  |  | OL1-2K34-0079 | CV | [6 empty] | Transmitted
| FOUNDATION PUMPS FOR 10-P-2450A/B, 10-P-2455A/B, 10-P-2620A/B, 10-P-2666A/B, 10-P-2660A/B |  |  |  | OL1-2K34-0080 | CV | [6 empty] | Transmitted
| FOUNDATION PUMPS FOR 10-P-2630A/B, 10-P-2310A/B, 10-P-2316A/B, 10-P-2326A/B, 10-P-2320A/B |  |  |  | OL1-2K34-0081 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2320A/B |  |  |  | OL1-2K34-0082 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2310A/B |  |  |  | OL1-2K34-0083 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2306A/B |  |  |  | OL1-2K34-0084 | CV | [6 empty] | Transmitted
| FOUNDATION FOR ANALYZER HOUSE |  |  |  | OL1-2K34-0085 | CV | [6 empty] | Transmitted
| FOUNDATION FOR ANALYZER HOUSE |  |  |  | OL1-2K34-0086 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-2900/2902/2906 |  |  |  | OL1-2K34-0087 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-2920 |  |  |  | OL1-2K34-0088 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-1920 |  |  |  | OL1-2K34-0089 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-2350 |  |  |  | OL1-2K34-0090 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5555 |  |  |  | OL1-2K34-0091 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SKID 10-P-2201A/B |  |  |  | OL1-2K34-0092 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-F-2048A/B |  |  |  | OL1-2K34-0093 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2580 |  |  |  | OL1-2K34-0094 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2640 |  |  |  | OL1-2K34-0095 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2570 |  |  |  | OL1-2K34-0096 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2510, 10-D-2510 AND 10-E-2510 |  |  |  | OL1-2K34-0097 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2540, 10-D-2540 AND 10-E-2540 |  |  |  | OL1-2K34-0098 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2520 AND 10-D-2520 |  |  |  | OL1-2K34-0099 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2411 |  |  |  | OL1-2K34-0100 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2480A |  |  |  | OL1-2K34-0101 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2465 |  |  |  | OL1-2K34-0102 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2840 |  |  |  | OL1-2K34-0103 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2830 |  |  |  | OL1-2K34-0104 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2815 |  |  |  | OL1-2K34-0105 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2820 |  |  |  | OL1-2K34-0106 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2810 |  |  |  | OL1-2K34-0107 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2645 |  |  |  | OL1-2K34-0108 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2555 |  |  |  | OL1-2K34-0109 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2550 |  |  |  | OL1-2K34-0110 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2575 |  |  |  | OL1-2K34-0112 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2880 |  |  |  | OL1-2K34-0113 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2870 |  |  |  | OL1-2K34-0114 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2860 |  |  |  | OL1-2K34-0115 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2865 |  |  |  | OL1-2K34-0116 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2587 |  |  |  | OL1-2K34-0117 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2432 |  |  |  | OL1-2K34-0120 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2575 |  |  |  | OL1-2K34-0121 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2576 |  |  |  | OL1-2K34-0122 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2645A/B |  |  |  | OL1-2K34-0123 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2502 |  |  |  | OL1-2K34-0124 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2515 |  |  |  | OL1-2K34-0125 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2546 |  |  |  | OL1-2K34-0126 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2548 |  |  |  | OL1-2K34-0127 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2545 |  |  |  | OL1-2K34-0128 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2805A/B |  |  |  | OL1-2K34-0129 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2807 |  |  |  | OL1-2K34-0130 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2809 |  |  |  | OL1-2K34-0131 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2857 |  |  |  | OL1-2K34-0132 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2858 |  |  |  | OL1-2K34-0133 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2856 |  |  |  | OL1-2K34-0134 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2855 |  |  |  | OL1-2K34-0135 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2853 |  |  |  | OL1-2K34-0136 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2852 |  |  |  | OL1-2K34-0137 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2582 |  |  |  | OL1-2K34-0139 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2504 |  |  |  | OL1-2K34-0140 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-2930, 10-D-2930 AND 10-P-2930 |  |  |  | OL1-2K34-0142 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-R-2700A/B |  |  |  | OL1-2K34-0143 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-R-2620A |  |  |  | OL1-2K34-0144 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-R-2760 |  |  |  | OL1-2K34-0145 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2620 |  |  |  | OL1-2K34-0146 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2666 |  |  |  | OL1-2K34-0147 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2665A/B |  |  |  | OL1-2K34-0148 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2660 |  |  |  | OL1-2K34-0149 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2710 |  |  |  | OL1-2K34-0150 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2720 |  |  |  | OL1-2K34-0151 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2660 |  |  |  | OL1-2K34-0152 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2630 |  |  |  | OL1-2K34-0153 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-R-2470A/B/C |  |  |  | OL1-2K34-0154 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2610 |  |  |  | OL1-2K34-0155 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2600A/B |  |  |  | OL1-2K34-0156 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2460 |  |  |  | OL1-2K34-0157 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2440 |  |  |  | OL1-2K34-0158 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-1000 |  |  |  | OL1-2K34-0159 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2635 |  |  |  | OL1-2K34-0160 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2636 |  |  |  | OL1-2K34-0161 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2472 |  |  |  | OL1-2K34-0162 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2474 |  |  |  | OL1-2K34-0163 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2465 |  |  |  | OL1-2K34-0164 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2460 |  |  |  | OL1-2K34-0165 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2440/2441/2442 |  |  |  | OL1-2K34-0166 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-1020 |  |  |  | OL1-2K34-0167 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-1015 |  |  |  | OL1-2K34-0168 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-1001A/B |  |  |  | OL1-2K34-0169 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-1000 |  |  |  | OL1-2K34-0170 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-1005 |  |  |  | OL1-2K34-0171 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-5112A/B, 10-P-2714A/B, 10-P-2710A/B, 10-P-2720A/B, 10-P-2721A/B, 10-P-2910 |  |  |  | OL1-2K34-0172 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-2724A/B, 10-P-2726A/B, 10-P-2750A/B, 10-P-2760A/B/C, 10-P-2705A/B |  |  |  | OL1-2K34-0173 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-2912 |  |  |  | OL1-2K34-0174 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-2922 |  |  |  | OL1-2K34-0175 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-2940 |  |  |  | OL1-2K34-0176 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2705 |  |  |  | OL1-2K34-0177 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2705 |  |  |  | OL1-2K34-0178 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2706 |  |  |  | OL1-2K34-0179 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2735 |  |  |  | OL1-2K34-0180 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2724 |  |  |  | OL1-2K34-0181 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2730 |  |  |  | OL1-2K34-0182 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2722 |  |  |  | OL1-2K34-0183 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2755 |  |  |  | OL1-2K34-0184 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2725A/B |  |  |  | OL1-2K34-0185 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2726 |  |  |  | OL1-2K34-0186 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2702 |  |  |  | OL1-2K34-0188 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2701 |  |  |  | OL1-2K34-0189 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2706 |  |  |  | OL1-2K34-0190 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2008A/B/C |  |  |  | OL1-2K34-0191 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2710 |  |  |  | OL1-2K34-0192 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-2720 |  |  |  | OL1-2K34-0193 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2720 |  |  |  | OL1-2K34-0194 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2724 |  |  |  | OL1-2K34-0195 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2715A/B |  |  |  | OL1-2K34-0196 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2714 |  |  |  | OL1-2K34-0197 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2882 AND 10-D-2882 |  |  |  | OL1-2K34-0198 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2884 AND 10-D-2884 |  |  |  | OL1-2K34-0199 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-2100A/B/C/D/E/F |  |  |  | OL1-2K34-0200 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-2320 |  |  |  | OL1-2K34-0201 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-1050 |  |  |  | OL1-2K34-0202 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-1910 |  |  |  | OL1-2K34-0203 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5910 |  |  |  | OL1-2K34-0204 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5914 |  |  |  | OL1-2K34-0205 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5912 |  |  |  | OL1-2K34-0206 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-2914 |  |  |  | OL1-2K34-0207 | CV | [6 empty] | Transmitted
| FOUNDATION FOR IGNITION SYSTEM |  |  |  | OL1-2K34-0208 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-C-3070 |  |  |  | OL1-2K34-0209 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-3900 |  |  |  | OL1-2K34-0210 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-3000 |  |  |  | OL1-2K34-0211 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-3040 |  |  |  | OL1-2K34-0212 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-3020 |  |  |  | OL1-2K34-0213 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-3010 |  |  |  | OL1-2K34-0214 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-3030 |  |  |  | OL1-2K34-0215 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-3050 |  |  |  | OL1-2K34-0216 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-3060 |  |  |  | OL1-2K34-0217 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-3090 |  |  |  | OL1-2K34-0218 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-3080 |  |  |  | OL1-2K34-0219 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-3070 |  |  |  | OL1-2K34-0220 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-3100, 10-A-3100 |  |  |  | OL1-2K34-0221 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-3908 |  |  |  | OL1-2K34-0222 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-3902 |  |  |  | OL1-2K34-0223 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-3904 |  |  |  | OL1-2K34-0224 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-3906 |  |  |  | OL1-2K34-0225 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-3180 |  |  |  | OL1-2K34-0226 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-3110 |  |  |  | OL1-2K34-0227 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3004A/B |  |  |  | OL1-2K34-0228 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3014A/B |  |  |  | OL1-2K34-0229 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3015 |  |  |  | OL1-2K34-0230 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3084 |  |  |  | OL1-2K34-0231 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3085A/B |  |  |  | OL1-2K34-0232 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3095 |  |  |  | OL1-2K34-0233 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3096 |  |  |  | OL1-2K34-0234 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3098 |  |  |  | OL1-2K34-0235 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3055A/B |  |  |  | OL1-2K34-0236 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3045A/B/C/D |  |  |  | OL1-2K34-0237 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3044 |  |  |  | OL1-2K34-0238 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3150 |  |  |  | OL1-2K34-0239 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3160 |  |  |  | OL1-2K34-0240 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3005 |  |  |  | OL1-2K34-0241 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-3070 |  |  |  | OL1-2K34-0242 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-2570A/B, 10-P-2575A/B, 10-P-2586A/B, 10-P-2647, 10-P-2646A/B |  |  |  | OL1-2K34-0243 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-2802A/B, 10-P-2805A/B, 10-P-2815, 10-P-2855A/B |  |  |  | OL1-2K34-0244 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-3046A/B |  |  |  | OL1-2K34-0245 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-3045A/B |  |  |  | OL1-2K34-0246 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-3026A/B |  |  |  | OL1-2K34-0247 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-3056A/B |  |  |  | OL1-2K34-0248 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-3080A/B, 10-P-3030A/B, 10-P-3000A/B, 10-P-3020A/B, 10-P-3061A/B, 10-P-3060A/B, 10-P-3062A/B, 10-P-3002A/B, 10-P-3902A/B, 10-P-3904A/B |  |  |  | OL1-2K34-0249 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-3096A/B, 10-P-3086A/B, 10-P-3036A/B, 10-P-3016A/B, 10-P-3900, 10-P-3160A/B, 10-P-3076A/B, 10-P-3906A/B, 10-P-3908A/B, 10-P-3110A/B, 10-P-3126A/B |  |  |  | OL1-2K34-0250 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-5900A/B, 10-P-5950A/B |  |  |  | OL1-2K34-0252 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-5360A/B/C |  |  |  | OL1-2K34-0253 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-5350 A/B/C/D/E/F/G/H |  |  |  | OL1-2K34-0254 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-2904 |  |  |  | OL1-2K34-0256 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5560 |  |  |  | OL1-2K34-0257 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5560 |  |  |  | OL1-2K34-0258 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5355 |  |  |  | OL1-2K34-0259 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5394 |  |  |  | OL1-2K34-0260 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5398 |  |  |  | OL1-2K34-0261 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5397 |  |  |  | OL1-2K34-0262 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5392 |  |  |  | OL1-2K34-0263 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5390 |  |  |  | OL1-2K34-0264 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5396 |  |  |  | OL1-2K34-0265 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-3126 |  |  |  | OL1-2K34-0266 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5550 |  |  |  | OL1-2K34-0267 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5500 |  |  |  | OL1-2K34-0268 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5510 |  |  |  | OL1-2K34-0269 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5513 |  |  |  | OL1-2K34-0270 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5515 |  |  |  | OL1-2K34-0271 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5520 |  |  |  | OL1-2K34-0272 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-C-5520A/B |  |  |  | OL1-2K34-0273 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5125, 10-D-5125A/B, 10-F-5125A/B |  |  |  | OL1-2K34-0274 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-5513 |  |  |  | OL1-2K34-0275 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-5550A/B, 10-P-5552 |  |  |  | OL1-2K34-0276 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B |  |  |  | OL1-2K34-0277 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-5640 |  |  |  | OL1-2K34-0278 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-5675A/B |  |  |  | OL1-2K34-0279 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-5676 |  |  |  | OL1-2K34-0280 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 |  |  |  | OL1-2K34-0281 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TX/C-2550 |  |  |  | OL1-2K34-0282 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-C-5650A/B |  |  |  | OL1-2K34-0283 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5627, 10-PIT-5627, P-10-5627A/B |  |  |  | OL1-2K34-0287 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5692 |  |  |  | OL1-2K34-0288 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5693 |  |  |  | OL1-2K34-0289 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5694 |  |  |  | OL1-2K34-0290 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5671 |  |  |  | OL1-2K34-0291 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5672 |  |  |  | OL1-2K34-0292 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5697 |  |  |  | OL1-2K34-0293 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5690 |  |  |  | OL1-2K34-0294 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5691 |  |  |  | OL1-2K34-0295 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5670 |  |  |  | OL1-2K34-0296 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-P-5670A/B, 10-P-5671A/B, 10-P-5644A/B, 10-P-5645A/B, 10-P-5646A/B, 10-P-5647A/B, 10-P-5675, 10-P-5676 |  |  |  | OL1-2K34-0297 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5646 AND 10-X-5646 |  |  |  | OL1-2K34-0298 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5644 |  |  |  | OL1-2K34-0299 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5644 |  |  |  | OL1-2K34-0300 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5653 |  |  |  | OL1-2K34-0301 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5650 |  |  |  | OL1-2K34-0302 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-5110 |  |  |  | OL1-2K34-0303 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-5120 |  |  |  | OL1-2K34-0304 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-5130 |  |  |  | OL1-2K34-0305 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5140 |  |  |  | OL1-2K34-0306 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5400 |  |  |  | OL1-2K34-0307 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5114 |  |  |  | OL1-2K34-0308 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5112, 10-E-5112 |  |  |  | OL1-2K34-0309 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5552 |  |  |  | OL1-2K34-0310 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-D-5565 |  |  |  | OL1-2K34-0311 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-5520 |  |  |  | OL1-2K34-0312 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-5113 |  |  |  | OL1-2K34-0313 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-5552 |  |  |  | OL1-2K34-0314 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-E-5110 |  |  |  | OL1-2K34-0315 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-P-5100A/B/C |  |  |  | OL1-2K34-0316 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-P-5102A/B |  |  |  | OL1-2K34-0317 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5191 |  |  |  | OL1-2K34-0318 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5192 |  |  |  | OL1-2K34-0319 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5115, 10-F-5115A/B/C |  |  |  | OL1-2K34-0320 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5125, 10-D-5125A/B |  |  |  | OL1-2K34-0321 | CV | [6 empty] | Transmitted
| FOUNDATION OF 10-D-1950 |  |  |  | OL1-2K34-0322 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-5900 |  |  |  | OL1-2K34-0323 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-TK-5950 |  |  |  | OL1-2K34-0324 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5695 |  |  |  | OL1-2K34-0325 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-PK-5696 |  |  |  | OL1-2K34-0326 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-X-2310 |  |  |  | OL1-2K34-0327 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-X-2312 |  |  |  | OL1-2K34-0328 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5900 |  |  |  | OL1-2K34-0329 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-5950 |  |  |  | OL1-2K34-0330 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2320 |  |  |  | OL1-2K34-0331 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-2910 |  |  |  | OL1-2K34-0332 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-TK-3900 |  |  |  | OL1-2K34-0333 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-PK-1910 |  |  |  | OL1-2K34-0334 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2000 |  |  |  | OL1-2K34-1000 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2020 |  |  |  | OL1-2K34-1020 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-T-2100 |  |  |  | OL1-2K34-1040 | CV | [6 empty] | Transmitted
| CONCRETE STRUCTURE FOR 10-T-2040 |  |  |  | OL1-2K34-1060 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-H-1100 |  |  |  | OL1-2K34-1080 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-H-1200/1600 |  |  |  | OL1-2K34-1100 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PSA PACKAGE 10-PK-2560, 10-D-2560A/F, 10-D-2565 |  |  |  | OL1-2K34-1120 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5605 |  |  |  | OL1-2K34-1140 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5610 |  |  |  | OL1-2K34-1160 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-2390 |  |  |  | OL1-2K34-1180 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5603 |  |  |  | OL1-2K34-1200 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5604 |  |  |  | OL1-2K34-1220 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-2090 |  |  |  | OL1-2K34-1240 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-2190 |  |  |  | OL1-2K34-1260 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-2790 |  |  |  | OL1-2K34-1280 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-2322 |  |  |  | OL1-2K34-1300 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-3190 |  |  |  | OL1-2K34-1320 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5601 |  |  |  | OL1-2K34-1340 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5600 |  |  |  | OL1-2K34-1360 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5370 |  |  |  | OL1-2K34-1400 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5602 |  |  |  | OL1-2K34-1420 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-2392 |  |  |  | OL1-2K34-1440 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5658 |  |  |  | OL1-2K34-1460 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5615 |  |  |  | OL1-2K34-1480 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5656 |  |  |  | OL1-2K34-1500 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5620A/B/C |  |  |  | OL1-2K34-1520 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5630 |  |  |  | OL1-2K34-1540 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5633 |  |  |  | OL1-2K34-1560 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5631 |  |  |  | OL1-2K34-1580 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5671 |  |  |  | OL1-2K34-1600 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5650A/B |  |  |  | OL1-2K34-1620 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5655 |  |  |  | OL1-2K34-1640 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-C-2200, 10-E-2200 |  |  |  | OL1-2K34-1660 | CV | [6 empty] | Transmitted
| FOUNDATION FOR CLARIFIER 10-TK-5651A/B |  |  |  | OL1-2K34-1680 | CV | [6 empty] | Transmitted
| FOUNDATION FOR METERING STATION |  |  |  | OL1-2K34-1700 | CV | [6 empty] | Transmitted
| FOUNDATION FOR BASIN 10-PIT-5642 |  |  |  | OL1-2K34-1720 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-C-2800, 10-E-2800 |  |  |  | OL1-2K34-1740 | CV | [6 empty] | Transmitted
| FOUNDATION AND ELEVATION FOR 10-C-2850, 10-E-2850 |  |  |  | OL1-2K34-1760 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-1780 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-1820 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-1840 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-1860 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-1880 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-1900 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-1920 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-1940 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-1960 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-1980 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2000 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-2020 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2040 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS FLARE UNIT |  |  |  | OL1-2K34-2060 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-2080 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2100 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2120 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2140 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-2160 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2180 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2200 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-2220 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2240 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-2260 | CV | [6 empty] | Transmitted
| FOUNDATION FOR PLATFORMS |  |  |  | OL1-2K34-2280 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-SLW-5T02 |  |  |  | OL1-2K34-2300 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-SLW-5T01 |  |  |  | OL1-2K34-2320 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-SLW-0C01 |  |  |  | OL1-2K34-2340 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-SLW-5W01 |  |  |  | OL1-2K34-2360 | CV | [6 empty] | Transmitted
| FOUNDATION FOR 10-SLW-5F01 |  |  |  | OL1-2K34-2380 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2400 | CV | [6 empty] | Transmitted
| FOUNDATION FOR SUPPORTS |  |  |  | OL1-2K34-2420 | CV | [6 empty] | Transmitted
| FOUNDATION FOR LIFTING STATION 10-PIT-5632 |  |  |  | OL1-2K34-2440 | CV | [6 empty] | Transmitted
| BASIN FOR COOLING TOWER 10-PIT-5350 |  |  |  | OL1-2K34-2500 | CV | [6 empty] | Transmitted
| STEEL STRUCTURE FOR 10-T-2040 |  |  |  | OL1-2K35-0001 | CV | [6 empty] | Transmitted
| STEEL STRUCTURE FOR 10-C-2200, 10-E-2200 |  |  |  | OL1-2K35-1000 | CV | [6 empty] | Transmitted
| STEEL STRUCTURE FOR 10-C-2800, 10-E-2800 |  |  |  | OL1-2K35-1020 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2390 |  |  |  | OL1-2K35-1040 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2090 |  |  |  | OL1-2K35-1060 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2190 |  |  |  | OL1-2K35-1080 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2790 |  |  |  | OL1-2K35-1100 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2322 |  |  |  | OL1-2K35-1120 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-3190 |  |  |  | OL1-2K35-1140 | CV | [6 empty] | Transmitted
| STEEL PLATF. FOR COOLING TOWER 5350 |  |  |  | OL1-2K35-1160 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-2392 |  |  |  | OL1-2K35-1180 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5658 |  |  |  | OL1-2K35-1200 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5615 |  |  |  | OL1-2K35-1220 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5656 |  |  |  | OL1-2K35-1240 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5620A/B/C |  |  |  | OL1-2K35-1260 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5655 |  |  |  | OL1-2K35-1280 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1300 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1320 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1340 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1360 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1380 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1400 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1420 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1440 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1460 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1480 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1500 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS FLARE UNIT |  |  |  | OL1-2K35-1520 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1540 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1560 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1580 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1600 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1620 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1640 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1660 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1680 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1700 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1720 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1740 | CV | [6 empty] | Transmitted
| STEEL FOR PLATFORMS |  |  |  | OL1-2K35-1760 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5642 |  |  |  | OL1-2K35-1800 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5602 |  |  |  | OL1-2K35-1820 | CV | [6 empty] | Transmitted
| STEEL STRUCTURE FOR 10-C-2850, 10-E-2850 |  |  |  | OL1-2K35-1840 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5633 |  |  |  | OL1-2K35-1860 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5650A/B |  |  |  | OL1-2K35-1880 | CV | [6 empty] | Transmitted
| STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5671 |  |  |  | OL1-2K35-1900 | CV | [6 empty] | Transmitted
| STEEL FOR SUPPORTS |  |  |  | OL1-2K35-1920 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0001 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0002 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0003 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0004 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0005 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0006 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0007 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0008 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0009 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0010 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0011 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0012 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-0013 | CV | [6 empty] | Transmitted
| OVERALL UNDERGROUND INTERFACE POINTS LOCATION |  |  |  | OL1-2K36-0020 | CV | [6 empty] | Transmitted
| MAJOR UNDERGROUND PIPING LAYOUT |  |  |  | OL1-2K36-1000 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1020 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1040 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1060 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1080 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1100 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1120 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1140 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1160 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1180 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1200 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1220 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1240 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1260 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1280 | CV | [6 empty] | Transmitted
| GRADING UNDERGROUND AND FOUNDATION PLAN |  |  |  | OL1-2K37-1300 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0002 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0003 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0004 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0005 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0006 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0007 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0008 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0009 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0010 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0011 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0012 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0013 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0014 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0015 | CV | [6 empty] | Transmitted
| INSTALLATION DWG-DETAILS |  |  |  | OL1-2K38-0016 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1040 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1060 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1080 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1100 | CV | [6 empty] | Transmitted
| TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  |  | OL1-2K38-1120 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1140 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1160 | CV | [6 empty] | Transmitted
| TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  |  | OL1-2K38-1180 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1200 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1220 | CV | [6 empty] | Transmitted
| TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  |  | OL1-2K38-1240 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1260 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1280 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1300 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1320 | CV | [6 empty] | Transmitted
| TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  |  | OL1-2K38-1340 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1360 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1380 | CV | [6 empty] | Transmitted
| TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  |  | OL1-2K38-1400 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1420 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1440 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1460 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1480 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1500 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1520 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1540 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1560 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1580 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1600 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1620 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1640 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1660 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1680 | CV | [6 empty] | Transmitted
| CHANNELS |  |  |  | OL1-2K38-1700 | CV | [6 empty] | Transmitted
| TRENCHES/DUCT BANK |  |  |  | OL1-2K38-1720 | CV | [6 empty] | Transmitted
| BUILDING 3D MODEL VIEWS - SUB-E & FAR-1 |  |  |  | OL1-2K39-0001 | CV | [6 empty] | Transmitted
| BUILDING 3D MODEL VIEWS - SUB-C & FAR-2 |  |  |  | OL1-2K39-0003 | CV | [6 empty] | Transmitted
| BUILDING 3D MODEL VIEWS - GATEHOUSE |  |  |  | OL1-2K39-0005 | CV | [6 empty] | Transmitted
| BUILDING 3D MODEL VIEWS - OPERATION TOOL ROOM |  |  |  | OL1-2K39-0007 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1020 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1040 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1060 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1080 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1100 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1120 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1140 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1160 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1180 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1200 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1220 | CV | [6 empty] | Transmitted
| PILING PLAN |  |  |  | OL1-2K44-1240 | CV | [6 empty] | Transmitted
| CIVIL WORKS MTL QTY SUMMARY |  |  |  | OL1-2K52-0001 | CV | [6 empty] | Transmitted
| STEEL STRUCTURES MTL QTY SUMMARY |  |  |  | OL1-2K53-0001 | CV | [6 empty] | Transmitted
| BUILDINGS QUANTITIES - ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 |  |  |  | OL1-2K54-0001 | CV | [6 empty] | Transmitted
| BUILDINGS QUANTITIES - ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 |  |  |  | OL1-2K54-0002 | CV | [6 empty] | Transmitted
| BUILDINGS QUANTITIES - GATEHOUSE |  |  |  | OL1-2K54-0003 | CV | [6 empty] | Transmitted
| BUILDINGS QUANTITIES - OPERATION TOOL ROOM |  |  |  | OL1-2K54-0004 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 101B |  |  |  | OL1-2K60-0002 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 102A |  |  |  | OL1-2K60-0003 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 102B |  |  |  | OL1-2K60-0004 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 102C |  |  |  | OL1-2K60-0005 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 102D |  |  |  | OL1-2K60-0006 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 102E |  |  |  | OL1-2K60-0007 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 103A |  |  |  | OL1-2K60-0008 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 100C |  |  |  | OL1-2K60-0009 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 103S |  |  |  | OL1-2K60-0010 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 100M |  |  |  | OL1-2K60-0011 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 105F |  |  |  | OL1-2K60-0012 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 105T |  |  |  | OL1-2K60-0013 | CV | [6 empty] | Transmitted
| ISO PRESSUREDWG UNIT 105U |  |  |  | OL1-2K60-0014 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 105W |  |  |  | OL1-2K60-0015 | CV | [6 empty] | Transmitted
| ISO PRESSURE DWG UNIT 100S |  |  |  | OL1-2K60-0016 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 101B |  |  |  | OL1-2K61-0002 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 102A |  |  |  | OL1-2K61-0003 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 102B |  |  |  | OL1-2K61-0004 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 102C |  |  |  | OL1-2K61-0005 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 102D |  |  |  | OL1-2K61-0006 | CV | [6 empty] | Transmitted
| ISO GRAVITYDWG UNIT 102E |  |  |  | OL1-2K61-0007 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 103A |  |  |  | OL1-2K61-0008 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 100C |  |  |  | OL1-2K61-0009 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 103S |  |  |  | OL1-2K61-0010 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 100M |  |  |  | OL1-2K61-0011 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 105F |  |  |  | OL1-2K61-0012 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 105T |  |  |  | OL1-2K61-0013 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 105U |  |  |  | OL1-2K61-0014 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 105W |  |  |  | OL1-2K61-0015 | CV | [6 empty] | Transmitted
| ISO GRAVITY DWG UNIT 100S |  |  |  | OL1-2K61-0016 | CV | [6 empty] | Transmitted
| GENERAL NOTES FOR PILES |  |  |  | OL1-2K92-0005 | CV | [6 empty] | Transmitted
| TECHNICAL SPECIFICATION FOR PILES |  |  |  | OL1-2K96-0001 | CV | [6 empty] | Transmitted
| TECH. SPEC. CONCRETE WORKS |  |  |  | OL1-2K96-0002 | CV | [6 empty] | Transmitted
| TECH. SPEC. PRECAST CONCRETE WORKS |  |  |  | OL1-2K96-0003 | CV | [6 empty] | Transmitted
| TECH. SPEC. STEEL STRUCT.EREC. |  |  |  | OL1-2K96-0004 | CV | [6 empty] | Transmitted
| FIREFIGHTING SYSTEM SPECIFICATION |  |  |  | OL1-2L01-0001 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION SPECIFICATION |  |  |  | OL1-2L01-0002 | SE | [6 empty] | Transmitted
| DATASHEET FOR FIREFIGHTING EQUIPMENT |  |  |  | OL1-2L02-0001 | SE | [6 empty] | Transmitted
| DATASHEET FOR DELUGE VALVES |  |  |  | OL1-2L02-0011 | SE | [6 empty] | Transmitted
| DATASHEET FOR CLEAN AGENT FIRE EXTINGUISHING SYSTEM |  |  |  | OL1-2L02-0021 | SE | [6 empty] | Transmitted
| DATASHEET FOR STEAM CURTAIN SYSTEM |  |  |  | OL1-2L02-0031 | SE | [6 empty] | Transmitted
| DATASHEET FOR SPRINKLER SYSTEM |  |  |  | OL1-2L02-0041 | SE | [6 empty] | Transmitted
| DATASHEET FOR SAFETY & LIFE SAVING EQUIPMENT |  |  |  | OL1-2L02-0051 | SE | [6 empty] | Transmitted
| ACUSTIC INSULATION SPECIFICATION |  |  |  | OL1-2L10-0003 | SE | [6 empty] | Transmitted
| NOISE STUDY (NOISE MAP) |  |  |  | OL1-2L11-0001 | SE | [6 empty] | Transmitted
| FIRE WATER DEMAND CALCULATION AND HYDRAULIC STUDY FOR FW NETWORK |  |  |  | OL1-2L20-0001 | SE | [6 empty] | Transmitted
| HYDRAULIC CALCULATION FOR FIREWATER DELUGE/WATER SPRAY SYSTEM |  |  |  | OL1-2L20-0002 | SE | [6 empty] | Transmitted
| DELUGE NOZZLES ARRANGEMENT CALCULATION NOTE |  |  |  | OL1-2L20-0003 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - SUBSTATION & FAR E |  |  |  | OL1-2L40-0001 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - SUBSTATION & FAR C |  |  |  | OL1-2L40-0002 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - COOLING WATER UNIT |  |  |  | OL1-2L40-0003 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - WASTE WATER TREATMENT UNIT |  |  |  | OL1-2L40-0004 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - UTILITIES |  |  |  | OL1-2L40-0005 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - FLARE UNIT |  |  |  | OL1-2L40-0006 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - METERING STATION |  |  |  | OL1-2L40-0007 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - FURNACES |  |  |  | OL1-2L40-0008 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - FURNACES AND AUXILIARIES |  |  |  | OL1-2L40-0009 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - QUENCH |  |  |  | OL1-2L40-0010 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - C3 HYDROGENATION |  |  |  | OL1-2L40-0011 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - PROCESS COLD COMPRESSORS |  |  |  | OL1-2L40-0012 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  |  |  | OL1-2L40-0013 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - BUTADIENE EXTRACT UNIT |  |  |  | OL1-2L40-0014 | SE | [6 empty] | Transmitted
| FIRE PROTECTION & FIREFIGHTING LAYOUT DRAWING - HOT FRACTIONATION / GHU UNIT |  |  |  | OL1-2L40-0015 | SE | [6 empty] | Transmitted
| OVERALL FIRE WATER NETWORK DRAWING |  |  |  | OL1-2L40-1000 | SE | [6 empty] | Transmitted
| FIREWATER P&ID (MAIN NETWORK / DISTRIBUTION / DELUGE / SPRINKLER) |  |  |  | OL1-2L40-1001 | SE | [6 empty] | Transmitted
| FIREWATER PIPING LINE LIST (PLL) |  |  |  | OL1-2L40-2001 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - SUBSTATION & FAR E |  |  |  | OL1-2L41-0001 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - SUBSTATION & FAR C |  |  |  | OL1-2L41-0002 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - COOLING WATER UNIT |  |  |  | OL1-2L41-0003 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - WASTE WATER TREATMENT UNIT |  |  |  | OL1-2L41-0004 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - UTILITIES |  |  |  | OL1-2L41-0005 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - FLARE UNIT |  |  |  | OL1-2L41-0006 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - METERING STATION |  |  |  | OL1-2L41-0007 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - FURNACES |  |  |  | OL1-2L41-0008 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - FURNACES AND AUXILIARIES |  |  |  | OL1-2L41-0009 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - QUENCH |  |  |  | OL1-2L41-0010 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - C3 HYDROGENATION |  |  |  | OL1-2L41-0011 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - PROCESS COLD COMPRESSORS |  |  |  | OL1-2L41-0012 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  |  |  | OL1-2L41-0013 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - BUTADIENE EXTRACT UNIT |  |  |  | OL1-2L41-0014 | SE | [6 empty] | Transmitted
| PASSIVE FIRE PROTECTION DRAWING - HOT FRACTIONATION / GHU UNIT |  |  |  | OL1-2L41-0015 | SE | [6 empty] | Transmitted
| OVERALL PASSIVE FIRE PROTECTION DRAWING |  |  |  | OL1-2L41-1000 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING, OLEFINS UNIT |  |  |  | OL1-2L42-0002 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING |  |  |  | OL1-2L42-0003 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - COOLING WATER UNIT |  |  |  | OL1-2L42-0005 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - WASTE WATER TREATMENT UNIT |  |  |  | OL1-2L42-0006 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - UTILITIES |  |  |  | OL1-2L42-0007 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - FLARE UNIT |  |  |  | OL1-2L42-0008 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - METERING STATION |  |  |  | OL1-2L42-0009 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - FURNACES |  |  |  | OL1-2L42-0010 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - FURNACES AND AUXILIARIES |  |  |  | OL1-2L42-0011 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - QUENCH |  |  |  | OL1-2L42-0012 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - C3 HYDROGENATION |  |  |  | OL1-2L42-0013 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - PROCESS COLD COMPRESSORS |  |  |  | OL1-2L42-0014 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  |  |  | OL1-2L42-0015 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - BUTADIENE EXTRACT UNIT |  |  |  | OL1-2L42-0016 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING - HOT FRACTIONATION / GHU UNIT |  |  |  | OL1-2L42-0017 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION DRAWING |  |  |  | OL1-2L42-0018 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - SUBSTATION & FAR E |  |  |  | OL1-2L44-0001 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - SUBSTATION & FAR C |  |  |  | OL1-2L44-0002 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - COOLING WATER UNIT |  |  |  | OL1-2L44-0003 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - WASTE WATER TREATMENT UNIT |  |  |  | OL1-2L44-0004 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - UTILITIES |  |  |  | OL1-2L44-0005 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - FLARE UNIT |  |  |  | OL1-2L44-0006 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - METERING STATION |  |  |  | OL1-2L44-0007 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - FURNACES |  |  |  | OL1-2L44-0008 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - FURNACES AND AUXILIARIES |  |  |  | OL1-2L44-0009 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - QUENCH |  |  |  | OL1-2L44-0010 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - C3 HYDROGENATION |  |  |  | OL1-2L44-0011 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - PROCESS COLD COMPRESSORS |  |  |  | OL1-2L44-0012 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - CRACKED GAS COMPRESSOR / DE-PROPANIZER / C2 HYDROGENATION |  |  |  | OL1-2L44-0013 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - BUTADIENE EXTRACT UNIT |  |  |  | OL1-2L44-0014 | SE | [6 empty] | Transmitted
| LIFESAVING EQ. & ESCAPE ROUTE DRAWING - HOT FRACTIONATION / GHU UNIT |  |  |  | OL1-2L44-0015 | SE | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR FIREFIGHTING EQUIPMENT |  |  |  | OL1-2L50-0001 | SE | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR DELUGE VALVES |  |  |  | OL1-2L51-0001 | SE | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR CLEAN AGENT FIRE EXTINGUISHING SYSTEM |  |  |  | OL1-2L51-0002 | SE | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR STEAM CURTAIN SYSTEM |  |  |  | OL1-2L51-0003 | SE | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR SPRINKLER SYSTEM |  |  |  | OL1-2L51-0004 | SE | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR SAFETY & LIFE SAVING EQUIPMENT |  |  |  | OL1-2L52-0001 | SE | [6 empty] | Transmitted
| HAZARD & OPERABILITY STUDY (FEED) REPORT |  |  |  | OL1-2L60-0001 | SE | [6 empty] | Transmitted
| HAZARD & OPERABILITY STUDY (DETAIL DESIGN) REPORT |  |  |  | OL1-2L60-1001 | SE | [6 empty] | Transmitted
| HAZARD & OPERABILITY STUDY (DETAIL DESIGN) REPORT |  |  |  | OL1-2L60-2001 | SE | [6 empty] | Transmitted
| SIL CLASSIFICATION REPORT |  |  |  | OL1-2L60-3001 | SE | [6 empty] | Transmitted
| SIL CLASSIFICATION REPORT |  |  |  | OL1-2L60-4001 | SE | [6 empty] | Transmitted
| HAZARD & OPERABILITY STUDY (FEED) CLOSEOUT REPORT |  |  |  | OL1-2L62-0001 | SE | [6 empty] | Transmitted
| HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  |  |  | OL1-2L62-1001 | SE | [6 empty] | Transmitted
| HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  |  |  | OL1-2L62-2001 | SE | [6 empty] | Transmitted
| HAZARDOUS AREA CLASSIFICATION SOURCE LIST, OLEFINS UNIT |  |  |  | OL1-2L65-0050 | SE | [6 empty] | Transmitted
| REGISTER FOR SAFETY DEVICES |  |  |  | OL1-2L66-0001 | SE | [6 empty] | Transmitted
| PROCESS HAZARD ANALYSIS PROCEDURE |  |  |  | OL1-2L72-0001 | SE | [6 empty] | Transmitted
| SIL CLASSIFICATION PROCEDURE |  |  |  | OL1-2L72-0002 | SE | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-1000 - LPG VAPORIZER |  |  |  | OL1-2M03-1002 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-1001 - LPG STEAM VAPORIZER |  |  |  | OL1-2M03-1003 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-1005 - LPG FEED HEATER |  |  |  | OL1-2M03-1005 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-1015 - LPG SUPERHEATER |  |  |  | OL1-2M03-1015 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-1020 - LIQUID FEED HEATER |  |  |  | OL1-2M03-1020 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-1050 - C2 FEED SUPERHEATER |  |  |  | OL1-2M03-1051 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-1950 - DECOKE AIR RECEIVER |  |  |  | OL1-2M03-1951 | ME | [6 empty] | Transmitted
| ELEVATOR DATA SHEET |  |  |  | OL1-2M03-2002 | ME | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  |  |  | OL1-2M03-2003 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2008 - QUENCH OIL FILTER |  |  |  | OL1-2M03-2007 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2008 - VLP STEAM GENERATORS |  |  |  | OL1-2M03-2008 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2009 - QO PUMP PURGE OIL FILTER |  |  |  | OL1-2M03-2009 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2026 - CRACKER BOTTOMS PRODUCT FILTER |  |  |  | OL1-2M03-2025 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2026 - FUEL OIL PRODUCT COOLER |  |  |  | OL1-2M03-2026 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2028 - FO PUMP PURGE OIL FILTER |  |  |  | OL1-2M03-2028 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2048 - HEAVY FUEL OIL PRODUCT COOLER |  |  |  | OL1-2M03-2048 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2048 - HEAVY FUEL OIL FILTERS |  |  |  | OL1-2M03-2049 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2090 - QUENCH OIL DRAIN DRUM |  |  |  | OL1-2M03-2090 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2090 - QUENCH OIL DRAIN DRUM PUMPS |  |  |  | OL1-2M03-2091 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2105 - QUENCH OIL REFLUX FILTER |  |  |  | OL1-2M03-2104 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2110 - INTERCEPTION DRUM |  |  |  | OL1-2M03-2110 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-2120 - DISTILLTATE STRIPPER |  |  |  | OL1-2M03-2120 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2125 - DISTILLATE STRIPPER REBOILER |  |  |  | OL1-2M03-2125 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2136 - PROCESS WATER FEED COALESCER |  |  |  | OL1-2M03-2136 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2136 - PROCESS WATER STRIPPER FEED HEATER |  |  |  | OL1-2M03-2137 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2136 - PROCESS WATER FEED FILTER |  |  |  | OL1-2M03-2138 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2145 - PROCESS WATER STRIPPER REBOILER |  |  |  | OL1-2M03-2145 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2146 - DSG FEED HEATER |  |  |  | OL1-2M03-2147 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2160 - DILUTION STEAM SUPERHEATER |  |  |  | OL1-2M03-2161 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2165 - DSG REBOILER COND POT |  |  |  | OL1-2M03-2164 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2165 - DSG REBOILER |  |  |  | OL1-2M03-2165 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2166 - DSG BLOWDOWN COOLER |  |  |  | OL1-2M03-2166 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2190 - QUENCH WATER DRAIN DRUM |  |  |  | OL1-2M03-2190 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2206 - WASH WATER COOLER |  |  |  | OL1-2M03-2206 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2210 - CG 1ST STAGE SUCTION DRUM |  |  |  | OL1-2M03-2210 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2210 - CG 1ST STAGE AFTERCOOLER |  |  |  | OL1-2M03-2211 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2220 - CG 2ND STAGE AFTERCOOLER |  |  |  | OL1-2M03-2221 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2230 - CG 3RD STAGE AFTERCOOLER |  |  |  | OL1-2M03-2231 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2240 - CG 4TH STAGE AFTERCOOLER |  |  |  | OL1-2M03-2241 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2245 - CG 4TH STAGE DISCHARGE DRUM |  |  |  | OL1-2M03-2245 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-C-2200 - CRACKED GAS COMPRESSOR |  |  |  | OL1-2M03-2250 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2305 - CAUSTIC TOWER FEED HEATER |  |  |  | OL1-2M03-2305 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2306 - WEAK CAUSTIC STRAINER |  |  |  | OL1-2M03-2307 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2310 - SPENT CAUSTIC DEOILING DRUM |  |  |  | OL1-2M03-2310 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2312 - SPENT WASH OIL DRUM |  |  |  | OL1-2M03-2312 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2310 - WASH OIL CIRCULATION FILTER |  |  |  | OL1-2M03-2314 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2316 - SPENT CAUSTIC DEGASSING DRUM |  |  |  | OL1-2M03-2316 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2316 - SPENT CAUSTIC DISCHARGE PUMP |  |  |  | OL1-2M03-2317 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-2320 - SPENT CAUSTIC PUMP DISCHARGE FILTER |  |  |  | OL1-2M03-2319 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-2320 - SPENT CAUSTIC STORAGE TANK |  |  |  | OL1-2M03-2320 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2326 - SPENT CAUSTIC STRIPPER FEED HEATER |  |  |  | OL1-2M03-2326 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND POT |  |  |  | OL1-2M03-2327 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2326 - SPENT CAUSTIC STRIPPER FEED HTR COND PUMP |  |  |  | OL1-2M03-2328 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2330 - SPENT CAUSTIC STRIPPER OVERHEAD DRUM |  |  |  | OL1-2M03-2331 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2390 - CAUSTIC DRAIN DRUM |  |  |  | OL1-2M03-2390 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2390 - CAUSTIC DRAIN DRUM PUMP |  |  |  | OL1-2M03-2391 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2392 - SPENT CAUSTIC DRAIN DRUM |  |  |  | OL1-2M03-2392 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2405 - GAS DRYER FEED KO DRUM |  |  |  | OL1-2M03-2405 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2405 - GAS DRYER FEED CHILLER |  |  |  | OL1-2M03-2406 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2410 - CRACKED GAS DRYER |  |  |  | OL1-2M03-2410 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2411 - CRACKED GAS MERCURY ADSORBER |  |  |  | OL1-2M03-2411 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2412 - HP DEPROPANIZER FEED CHILLER |  |  |  | OL1-2M03-2412 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2413 - HP DEPROP FEED / OVERHEAD EXCHANGER |  |  |  | OL1-2M03-2413 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2415 - CG LIQUID DRYER FEED COALESCER |  |  |  | OL1-2M03-2415 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2420 - CG LIQUID DRYER |  |  |  | OL1-2M03-2420 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2430 - REGEN GAS FEED HEATER |  |  |  | OL1-2M03-2430 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2432 - REGEN GAS SHP HEATER |  |  |  | OL1-2M03-2432 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2435 - REGEN GAS EFFLUENT COOLER |  |  |  | OL1-2M03-2434 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2435 - REGEN GAS SEPARATOR |  |  |  | OL1-2M03-2435 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2436 - MERCURY ADSORBER |  |  |  | OL1-2M03-2436 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2440 - HP DEPROPANIZER CONDENSER |  |  |  | OL1-2M03-2439 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2441 - HP DEPROP REFLUX CHILLER NO. 2 |  |  |  | OL1-2M03-2441 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2442 - HP DEPROP REFLUX CHILLER NO. 1 |  |  |  | OL1-2M03-2442 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2445 - HP DEPROPANIZER COND PUMP |  |  |  | OL1-2M03-2443 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2445 - HP DEPROP REBOILER COND POT |  |  |  | OL1-2M03-2444 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2445 - HP DEPROPANIZER REBOILER |  |  |  | OL1-2M03-2445 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2446 - LP DEPROPANIZER FEED COOLER |  |  |  | OL1-2M03-2446 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2450 - LP DEPROPANIZER CONDENSER |  |  |  | OL1-2M03-2451 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2450 - LP DEPROPANIZER REFLUX DRUM |  |  |  | OL1-2M03-2452 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2455 - LP DEPROPANIZER REBOILER |  |  |  | OL1-2M03-2455 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2455 - LP DEPROP REBOILER COND POT |  |  |  | OL1-2M03-2456 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2455 - LP DEPROPANIZER COND PUMP |  |  |  | OL1-2M03-2457 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2460 - C2 HYDROG ARSINE GUARD BED |  |  |  | OL1-2M03-2460 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2460 - C2 HYDROG FEED COOLER |  |  |  | OL1-2M03-2461 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2465 - C2 HYDROG FEED HEATER |  |  |  | OL1-2M03-2465 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2465 - C2 HYDROG FEED HEATER COND POT |  |  |  | OL1-2M03-2466 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2465 - C2 HYDROG FEED HEATER COND PUMP |  |  |  | OL1-2M03-2467 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-R-2470 - C2 HYDROG REACTOR |  |  |  | OL1-2M03-2470 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2470 - C2 HYDROG 1ST STAGE INTERCOOLER |  |  |  | OL1-2M03-2471 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2472 - C2 HYDROG 2ND STAGE INTERCOOLER |  |  |  | OL1-2M03-2472 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2474 - C2 HYDROG AFTERCOOLER |  |  |  | OL1-2M03-2474 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2480 - CG SECONDARY DRYER |  |  |  | OL1-2M03-2480 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2506 - DEMETH PREFRAC FEED SEPARATOR NO. 2 |  |  |  | OL1-2M03-2506 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2508 - DEMETH PREFRAC FEED SEPARATOR NO. 3 |  |  |  | OL1-2M03-2508 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2515 - DEMETH PREFRACTIONATOR REBOILER |  |  |  | OL1-2M03-2515 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-2520 - RESIDUE GAS RECTIFIER |  |  |  | OL1-2M03-2520 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2525 - HYDROGEN DRUM |  |  |  | OL1-2M03-2525 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2545 - DEMETHANIZER REBOILER |  |  |  | OL1-2M03-2545 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2546 - DEMETHANIZER BOTTOMS COOLER |  |  |  | OL1-2M03-2546 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2548 - DEMETHANIZER BOTTOMS VAPORIZER |  |  |  | OL1-2M03-2548 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2550 - EXPANDER SUCTION DRUM |  |  |  | OL1-2M03-2551 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2555 - EXPANDER DISCHARGE DRUM |  |  |  | OL1-2M03-2555 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2570 - DEETHANIZER REFLUX PUMP |  |  |  | OL1-2M03-2573 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2575 - DEETHANIZER REBOILER COND POT |  |  |  | OL1-2M03-2574 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2575 - DEETHANIZER REBOILER |  |  |  | OL1-2M03-2575 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2576 - DEETHANIZER BOTTOMS COOLER |  |  |  | OL1-2M03-2576 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2575 - DEETHANIZER REBOILER COND PUMP |  |  |  | OL1-2M03-2577 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-2580 - C2 TOWER |  |  |  | OL1-2M03-2580 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2582 - C2 TOWER REFLUX COOLER |  |  |  | OL1-2M03-2582 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2856 - ETHYLENE PRODUCT SUBCOOLER |  |  |  | OL1-2M03-2591 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2600 - C3 HYDROG GUARD ADSORBER |  |  |  | OL1-2M03-2600 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2610 - C3 HYDROG ARSINE GUARD BED |  |  |  | OL1-2M03-2610 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-R-2620 - C3 HYDROG REACTOR |  |  |  | OL1-2M03-2620 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2620 - C3 HYDROG AFTERCOOLER |  |  |  | OL1-2M03-2621 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2620 - C3 HYDROG RECYCLE DRUM |  |  |  | OL1-2M03-2622 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2620 - C3 HYDROG RECYCLE PUMPS |  |  |  | OL1-2M03-2623 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2630 - SECONDARY DEETH REFLUX DRUM |  |  |  | OL1-2M03-2632 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2635 - SECONDARY DEETH REBOILER |  |  |  | OL1-2M03-2635 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2645 - C3 TOWER REBOILER COND POT |  |  |  | OL1-2M03-2644 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2646 - PROPANE RECYCLE PUMP |  |  |  | OL1-2M03-2646 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2647 - HP PROPYLENE / OFF SPEC PUMP |  |  |  | OL1-2M03-2647 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2660 - DEBUTANIZER REFLUX DRUM |  |  |  | OL1-2M03-2662 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2660 - DEBUTANIZER REFLUX / PRODUCT PUMP |  |  |  | OL1-2M03-2663 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2666 - C5 / PYGAS SURGE DRUM |  |  |  | OL1-2M03-2667 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2666 - C5 / PYGAS PUMPS |  |  |  | OL1-2M03-2668 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-R-2700 - GHU-1 REACTOR |  |  |  | OL1-2M03-2700 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2701 - GHU-1 FEED / EFFLUENT EXCHANGERS |  |  |  | OL1-2M03-2701 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2702 - GHU-1 S/U HEATER |  |  |  | OL1-2M03-2702 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2705 - GHU-1 RECYCLE COOLER |  |  |  | OL1-2M03-2703 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2705 - GHU-1 RECYCLE PUMPS |  |  |  | OL1-2M03-2704 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2705 - GHU-1 HOT SEPARATOR |  |  |  | OL1-2M03-2705 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2706 - GHU-1 COLD SEPARATOR |  |  |  | OL1-2M03-2706 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2706 - GHU-1 COOLER |  |  |  | OL1-2M03-2707 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-2710 - DEPENTANIZER |  |  |  | OL1-2M03-2710 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2710 -DEPENTANIZER CONDENSER |  |  |  | OL1-2M03-2711 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2710 - DEPENTANIZER REFLUX DRUM |  |  |  | OL1-2M03-2712 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2710 - DEPENTANIZER REFLUX PUMPS |  |  |  | OL1-2M03-2713 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2714 - C5 CUT PUMPS |  |  |  | OL1-2M03-2714 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2715 - DEPENTANIZER REBOILER |  |  |  | OL1-2M03-2715 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2714 - C5 CUT COOLER |  |  |  | OL1-2M03-2716 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2720 - RERUN TOWER REFLUX DRUM |  |  |  | OL1-2M03-2718 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2720 - RERUN TOWER REFLUX / PRODUCT PUMPS |  |  |  | OL1-2M03-2719 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-2720 - RERUN TOWER |  |  |  | OL1-2M03-2720 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2720 - RERUN TOWER CONDENSER |  |  |  | OL1-2M03-2721 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2722 - GHU-1 PRODUCT COOLER |  |  |  | OL1-2M03-2722 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2724 - WASH OIL CONDENSER |  |  |  | OL1-2M03-2723 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2724 - WASH OIL DEGASSING DRUM |  |  |  | OL1-2M03-2724 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2725 - RERUN TOWER REBOILER |  |  |  | OL1-2M03-2725 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2726 - PYGAS FUEL OIL PUMPS |  |  |  | OL1-2M03-2726 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2726 - PYGAS FUEL OIL COOLER |  |  |  | OL1-2M03-2727 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2724 - RECYCLE WASH OIL PUMPS |  |  |  | OL1-2M03-2728 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2730 - HYDROG REGEN HEATER |  |  |  | OL1-2M03-2730 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2735 - REGEN HYDROG DRUM |  |  |  | OL1-2M03-2735 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2750 - C4 / C5 HYDROG SURGE DRUM |  |  |  | OL1-2M03-2750 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2750 - C4 / C5 HYDROG FEED PUMPS |  |  |  | OL1-2M03-2751 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2755 - C4 / C5 HYDROG S/U HEATER |  |  |  | OL1-2M03-2755 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-R-2760 - C4 / C5 HYDROG REACTOR |  |  |  | OL1-2M03-2760 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2761 - C4 / C5 HYDROG VENT CHILLER |  |  |  | OL1-2M03-2761 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2760 - C4 / C5 HYDROG RECYCLE DRUM |  |  |  | OL1-2M03-2762 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2760 - C4 / C5 HYDROG VENT CONDENSER |  |  |  | OL1-2M03-2763 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2760 - C4 / C5 HYDROG RECYCLE PUMPS |  |  |  | OL1-2M03-2764 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2765 - C4 / C5 HYDROG RECYCLE COOLER |  |  |  | OL1-2M03-2765 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2790 - LIGHT OIL DRAIN DRUM |  |  |  | OL1-2M03-2790 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2790 - LIGHT OIL DRAIN DRUM PUMP |  |  |  | OL1-2M03-2791 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2805 - PROPYLENE PRODUCT PUMP |  |  |  | OL1-2M03-2801 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2805 - C3R CONDENSER |  |  |  | OL1-2M03-2806 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2807 - C3 CHILLER NO. 1 |  |  |  | OL1-2M03-2807 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2809 - C3 CHILLER NO. 2 |  |  |  | OL1-2M03-2809 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2815 - C3R DRAIN DRUM |  |  |  | OL1-2M03-2815 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2815 - PROPYLENE REFRIG RECOVERY PUMP |  |  |  | OL1-2M03-2816 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 1 |  |  |  | OL1-2M03-2852 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2852 - C2R DESUPERHEATER NO. 2 |  |  |  | OL1-2M03-2853 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2855 - C2R SURGE DRUM |  |  |  | OL1-2M03-2854 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2855 - ETHYLENE PRODUCT PUMP |  |  |  | OL1-2M03-2855 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-2858 - HP ETHYLENE PRODUCT SUPERHEATER |  |  |  | OL1-2M03-2858 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2860 - C2R 1ST STAGE SUCTION DRUM |  |  |  | OL1-2M03-2860 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2865 - C2R DRAIN DRUM |  |  |  | OL1-2M03-2865 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-2870 - C2R 2ND STAGE SUCTION DRUM |  |  |  | OL1-2M03-2870 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-2910 - WASH OIL DAY TANK |  |  |  | OL1-2M03-2910 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-2910 - WASH OIL INJECTION PUMP |  |  |  | OL1-2M03-2911 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3000 - PREDISTILLATION TOWER |  |  |  | OL1-2M03-3000 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3000 - PREDISTILLATION CONDENSER |  |  |  | OL1-2M03-3001 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3002 - PREDISTILLATION FEED PUMP |  |  |  | OL1-2M03-3002 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3000 - PREDISTILLATION REFLUX PUMP |  |  |  | OL1-2M03-3003 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3004 - PREDISTILLATION TRIM REBOILER |  |  |  | OL1-2M03-3004 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3005 - PREDISTILLATION REBOILER |  |  |  | OL1-2M03-3005 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3000 - PREDISTILLATION REFLUX DRUM |  |  |  | OL1-2M03-3006 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3002 - PREDISTILLATION FEED DRUM |  |  |  | OL1-2M03-3007 | ME | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  |  |  | OL1-2M03-3008 | ME | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  |  |  | OL1-2M03-3009 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3010 - C4 FEED DRUM |  |  |  | OL1-2M03-3010 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3014 - C4 TRIM VAPORIZER |  |  |  | OL1-2M03-3014 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3015 - C4 VAPORIZER |  |  |  | OL1-2M03-3015 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3016 - HEAVY END DISCHARGE PUMP |  |  |  | OL1-2M03-3016 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3018 - SOLVENT COOLER |  |  |  | OL1-2M03-3018 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3020 - MAIN WASHER |  |  |  | OL1-2M03-3020 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3020 - MAIN WASHER REFLUX DRUM |  |  |  | OL1-2M03-3021 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3020 - MAIN WASHER CONDENSER |  |  |  | OL1-2M03-3022 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3020 - MAIN WASHER REFLUX PUMP |  |  |  | OL1-2M03-3023 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3026 - MAIN WASHER BOTTOM PUMP |  |  |  | OL1-2M03-3026 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3030 - AFTER WASHER |  |  |  | OL1-2M03-3030 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3030 - AFTER WASHER CONDENSER |  |  |  | OL1-2M03-3031 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3030 - AFTER WASHER REFLUX PUMP |  |  |  | OL1-2M03-3032 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3030 - AFTER WASHER REFLUX DRUM |  |  |  | OL1-2M03-3033 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3036 - AFTER WASHER BOTTOM PUMP |  |  |  | OL1-2M03-3036 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3040 - RECTIFIER |  |  |  | OL1-2M03-3040 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3044 - SOLVENT HEATER |  |  |  | OL1-2M03-3044 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3045 - SOLVENT HEAT EXCHANGER |  |  |  | OL1-2M03-3045 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3046 - DEGASSER FEED PUMP |  |  |  | OL1-2M03-3046 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3045 - RECTIFIER PUMPS |  |  |  | OL1-2M03-3047 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3050 - DEGASSER |  |  |  | OL1-2M03-3050 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3055 - DEGASSER REBOILER |  |  |  | OL1-2M03-3055 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3056 - DEGASSER BOTTOM PUMP |  |  |  | OL1-2M03-3056 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3060 - ACETYLENE WASHER |  |  |  | OL1-2M03-3060 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3060 - ACETYLENE WASHER CONDENSER |  |  |  | OL1-2M03-3061 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3062 - ACETYLENE CONDENSER |  |  |  | OL1-2M03-3062 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3060 - WASTE WATER PUMP |  |  |  | OL1-2M03-3063 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3062 - C4 ACETYLENE PUMP |  |  |  | OL1-2M03-3064 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3061 - WASTE HC PUMP |  |  |  | OL1-2M03-3065 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3062 - ACETYLENE ACCUMULATOR |  |  |  | OL1-2M03-3066 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3060 - C4 FEED DRUM |  |  |  | OL1-2M03-3067 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3070 - DIRECT COOLER |  |  |  | OL1-2M03-3070 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-C-3070 - RECYCLE GAS COMPRESSOR |  |  |  | OL1-2M03-3071 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3070 - WATER / NMP COOLER |  |  |  | OL1-2M03-3073 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3076 - DIRECT COOLER PUMP |  |  |  | OL1-2M03-3076 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3080 - BUTADIENE TOWER |  |  |  | OL1-2M03-3080 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3080 - BUTADIENE TOWER REFLUX DRUM |  |  |  | OL1-2M03-3081 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3080 - BUTADIENE TOWER CONDENSER |  |  |  | OL1-2M03-3082 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3080 - BUTADIENE TOWER REFLUX PUMPS |  |  |  | OL1-2M03-3083 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3084 - BUTADIENE TOWER TRIM REBOILER |  |  |  | OL1-2M03-3084 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3085 - BUTADIENE TOWER REBOILER |  |  |  | OL1-2M03-3085 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3086 - C4 / C5 HC PUMP |  |  |  | OL1-2M03-3086 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3090 - BUTADIENE DRYING TOWER |  |  |  | OL1-2M03-3090 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3095 - BUTADIENE DRYING TOWER REBOILER |  |  |  | OL1-2M03-3095 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3096 - BUTADIENE PRODUCT COOLER |  |  |  | OL1-2M03-3096 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3096 - BUTADIENE PRODUCT PUMPS |  |  |  | OL1-2M03-3097 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3098 - BUTADIENE PRODUCT SUBCOOLER |  |  |  | OL1-2M03-3098 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3100 - SOLVENT REGEN DRUM |  |  |  | OL1-2M03-3100 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-T-3110 - WATER WASHER |  |  |  | OL1-2M03-3110 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3110 - WATER WASHER ACCUMULATOR |  |  |  | OL1-2M03-3111 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3110 - WATER WASHER CONDENSER |  |  |  | OL1-2M03-3112 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3110 - SOLVENT RETURN PUMP |  |  |  | OL1-2M03-3113 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3120 - REGEN STEAM EJECTOR COOLER |  |  |  | OL1-2M03-3120 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3126 - EJECTOR SEAL DRUM |  |  |  | OL1-2M03-3126 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3126 - WASTE WATER RETURN PUMPS |  |  |  | OL1-2M03-3127 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3150 - CONDENSATE HEATER |  |  |  | OL1-2M03-3150 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3150 - CONDENSATE FLASH DRUM |  |  |  | OL1-2M03-3151 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-3160 - CONDENSATE COOLER |  |  |  | OL1-2M03-3160 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3160 - CONDENSATE DRUM |  |  |  | OL1-2M03-3161 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3160 - CONDENSATE RECYCLE PUMP |  |  |  | OL1-2M03-3162 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3180 - BLOWDOWN DRUM |  |  |  | OL1-2M03-3180 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3190 - NMP SLOP DRUM |  |  |  | OL1-2M03-3190 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3190 - SOLVENT SLOP PUMP |  |  |  | OL1-2M03-3191 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-3900 - NMP STORAGE TANK |  |  |  | OL1-2M03-3900 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3900 - NMP STORAGE PUMP |  |  |  | OL1-2M03-3901 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3902 - SOLVENT INHIBITOR DRUM |  |  |  | OL1-2M03-3902 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3902 - SOLVENT INHIBITOR DOSING PUMP |  |  |  | OL1-2M03-3903 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3904 - PRODUCT INHIBITOR DRUM |  |  |  | OL1-2M03-3904 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3904 - PRODUCT INHIBITOR DOSING PUMP |  |  |  | OL1-2M03-3905 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3906 - ANTI FOAM AGENT DRUM |  |  |  | OL1-2M03-3906 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3906 - ANTIFOAM DOSING PUMP |  |  |  | OL1-2M03-3907 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-3908 - PREDISTILLATION INHIBITOR DRUM |  |  |  | OL1-2M03-3908 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-3908 - PREDISTILLATION INHIBITOR DOSING PUMP |  |  |  | OL1-2M03-3909 | ME | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  |  |  | OL1-2M03-4001 | ME | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  |  |  | OL1-2M03-4003 | ME | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  |  |  | OL1-2M03-5001 | ME | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  |  |  | OL1-2M03-5003 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5100 - DEARATOR VENT CONDENSER |  |  |  | OL1-2M03-5103 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5112 - SUSPECT CONDENSATE FLASH DRUM VENT CONDENSER |  |  |  | OL1-2M03-5107 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5110 - SUSPECT CONDENSATE COOLER |  |  |  | OL1-2M03-5108 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5110 - CONDENSATE TANK |  |  |  | OL1-2M03-5110 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5112 - SUSPECT CONDENSATE FLASH DRUM |  |  |  | OL1-2M03-5112 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5113 - FOUL CONDENSATE COOLER |  |  |  | OL1-2M03-5113 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5114 - LP CONDENSATE FLASH DRUM |  |  |  | OL1-2M03-5114 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5120 - RAW CONDENSATE TANK |  |  |  | OL1-2M03-5120 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5140 - INTERMITTENT BLOWDOWN DRUM |  |  |  | OL1-2M03-5140 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5150 - CONTINUOUS BLOWDOWN FLASH DRUM |  |  |  | OL1-2M03-5150 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5200 - FUEL GAS DRUM |  |  |  | OL1-2M03-5200 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5200 - MP ETHYLENE SUPERHEATER |  |  |  | OL1-2M03-5201 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5210 - PILOT GAS VAPORIZER |  |  |  | OL1-2M03-5210 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5220 - PILOT GAS SUPERHEATER |  |  |  | OL1-2M03-5220 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5370 - CW FILTER BACKWASH PUMPS |  |  |  | OL1-2M03-5371 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5400 - INSTRUMENT AIR RECEIVER |  |  |  | OL1-2M03-5400 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5500 - HOT BLOWDOWN PUMPS |  |  |  | OL1-2M03-5501 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5510 - COLD FLARE DRUM |  |  |  | OL1-2M03-5510 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5510 - COLD FLARE BLOWDOWN VAPORIZER |  |  |  | OL1-2M03-5511 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5512 - COLD FLARE SUPERHEATER |  |  |  | OL1-2M03-5512 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5513 - METHANOL VAPORIZER |  |  |  | OL1-2M03-5513 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5513 - METHANOL VAPROIZER COND POT |  |  |  | OL1-2M03-5514 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5515 - METHANOL MAKE-UP DRUM |  |  |  | OL1-2M03-5515 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5520 - VENT COLLECTION DRUM |  |  |  | OL1-2M03-5520 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5550 - HP FLARE KNOCK OUT DRUM |  |  |  | OL1-2M03-5550 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5550 - HP FLARE KNOCK OUT DRUM PUMPS |  |  |  | OL1-2M03-5551 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-D-5552 - LPG STORAGE DRUM |  |  |  | OL1-2M03-5552 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-E-5552 - LPG VAPORIZER / SUPERHEATER |  |  |  | OL1-2M03-5553 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5552 - LPG UNLOADING PUMP |  |  |  | OL1-2M03-5554 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET- 10-D-5565 - LLDPE LP FLARE KNOCK OUT DRUM |  |  |  | OL1-2M03-5565 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5600 - PYGAS AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2M03-5606 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5601 - BUTADIENE AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2M03-5607 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5602 - QW AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2M03-5608 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5603 - CGC AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2M03-5609 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5610 - HYDROBLAST PUMPS |  |  |  | OL1-2M03-5611 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-F-5610 - HYDROBLAST FILTER |  |  |  | OL1-2M03-5612 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5604 - REFRIG AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2M03-5613 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5605 - FURNACE AREA OILY WATER PUMPS |  |  |  | OL1-2M03-5614 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5615 - OLEFINS STORMWATER SUMP PUMPS |  |  |  | OL1-2M03-5616 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5621 - OLEFINS HOLDING BASIN SKIM OIL PUMPS |  |  |  | OL1-2M03-5621 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5620 - OLEFINS HOLDING BASIN PUMPS |  |  |  | OL1-2M03-5622 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5630 - CT AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2M03-5635 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5631 - CWWT AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2M03-5636 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5632 - HP FLARE AREA OILY WASTEWATER PUMPS |  |  |  | OL1-2M03-5637 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5633 - HP FLARE AREA STORMWATER SUMP PUMPS |  |  |  | OL1-2M03-5638 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5640 - OILY WASTEWATER EQUALIZATION TANKS |  |  |  | OL1-2M03-5640 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5641 - WASTEWATER EQ TANK SKIMMED OIL PUMP |  |  |  | OL1-2M03-5641 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5642 - COOLING WATER BD BASIN PUMPS |  |  |  | OL1-2M03-5643 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5640 - OILY WASTEWATER EQ TANK PUMPS |  |  |  | OL1-2M03-5645 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5655 - EQUALIZATION PIT PUMPS |  |  |  | OL1-2M03-5654 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5656 - FINAL CHECK BASIN PUMPS |  |  |  | OL1-2M03-5657 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5675 - SLOP OIL TRANSFER PUMPS |  |  |  | OL1-2M03-5674 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5675 - SLOP OIL TANKS |  |  |  | OL1-2M03-5675 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5676 - OILY SLUDGE TANK |  |  |  | OL1-2M03-5676 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5676 - OILY SLUDGE TRANSFER PUMPS |  |  |  | OL1-2M03-5677 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5900 - SULFURIC ACID TANK |  |  |  | OL1-2M03-5900 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5900 - SULFURIC ACID PUMPS |  |  |  | OL1-2M03-5901 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-TK-5950 - SODIUM HYPOCHLORITE TANK |  |  |  | OL1-2M03-5950 | ME | [6 empty] | Transmitted
| MECHANICAL EQUIPMENT DATA SHEET - 10-P-5950 - SODIUM HYPOCHLORITE METERING PUMPS |  |  |  | OL1-2M03-5951 | ME | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR API 560 INDUCED DRAFT FAN (132SU FURNACE) |  |  |  | OL1-2M03-6001 | ME | [6 empty] | Transmitted
| MECHANICAL DATASHEET FOR MOTOR FOR INDUCED DRAFT FAN (132SU FURNACE) |  |  |  | OL1-2M03-6003 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  |  |  | OL1-2M06-1003 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  |  |  | OL1-2M06-1004 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE REFRACTORY & INSULATION RADIANT SECTION DETAILS |  |  |  | OL1-2M06-1101 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE REFRACTORY & INSULATION CONVECTION SECTION DETAILS |  |  |  | OL1-2M06-1102 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE INSULATION INSTALLATION DETAILS |  |  |  | OL1-2M06-1103 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE REFRACTORY AND INSULATION ANCHOR DETAILS |  |  |  | OL1-2M06-1104 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  |  |  | OL1-2M06-1105 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE PEEP DOOR INSERT DETAILS |  |  |  | OL1-2M06-1106 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE USX ASSEMBLY INSULATION DETAILS |  |  |  | OL1-2M06-1107 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE DECOKE NOZZLE DETAILS |  |  |  | OL1-2M06-1108 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE SEAL BOOT DETAILS |  |  |  | OL1-2M06-1109 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  |  |  | OL1-2M06-1110 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  |  |  | OL1-2M06-1205 | ME | [6 empty] | Transmitted
| USC "36M" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  |  |  | OL1-2M06-1206 | ME | [6 empty] | Transmitted
| USC "36M" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  |  |  | OL1-2M06-1303 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  |  |  | OL1-2M06-2003 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  |  |  | OL1-2M06-2004 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  |  |  | OL1-2M06-2107 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  |  |  | OL1-2M06-2205 | ME | [6 empty] | Transmitted
| USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  |  |  | OL1-2M06-2206 | ME | [6 empty] | Transmitted
| DILUTION STEAM MIXING TEE DRAWING |  |  |  | OL1-2M06-2207 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  |  |  | OL1-2M06-2303 | ME | [6 empty] | Transmitted
| FURNACE PEEP DOOR DETAILS (LEFT HAND) |  |  |  | OL1-2M06-2555 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  |  |  | OL1-2M06-3001 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  |  |  | OL1-2M06-3002 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  |  |  | OL1-2M06-3003 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  |  |  | OL1-2M06-3004 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  |  |  | OL1-2M06-3107 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  |  |  | OL1-2M06-3201 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  |  |  | OL1-2M06-3202 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  |  |  | OL1-2M06-3203 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  |  |  | OL1-2M06-3204 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  |  |  | OL1-2M06-3205 | ME | [6 empty] | Transmitted
| USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  |  |  | OL1-2M06-3206 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  |  |  | OL1-2M06-3301 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  |  |  | OL1-2M06-3302 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  |  |  | OL1-2M06-3303 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  |  |  | OL1-2M06-4001 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  |  |  | OL1-2M06-4002 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  |  |  | OL1-2M06-4003 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  |  |  | OL1-2M06-4004 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  |  |  | OL1-2M06-4107 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  |  |  | OL1-2M06-4201 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  |  |  | OL1-2M06-4202 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  |  |  | OL1-2M06-4203 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  |  |  | OL1-2M06-4204 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  |  |  | OL1-2M06-4205 | ME | [6 empty] | Transmitted
| USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  |  |  | OL1-2M06-4206 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  |  |  | OL1-2M06-4301 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  |  |  | OL1-2M06-4302 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  |  |  | OL1-2M06-4303 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  |  |  | OL1-2M06-5001 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  |  |  | OL1-2M06-5002 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  |  |  | OL1-2M06-5003 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  |  |  | OL1-2M06-5004 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  |  |  | OL1-2M06-5107 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  |  |  | OL1-2M06-5201 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  |  |  | OL1-2M06-5202 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  |  |  | OL1-2M06-5203 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  |  |  | OL1-2M06-5204 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  |  |  | OL1-2M06-5205 | ME | [6 empty] | Transmitted
| USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  |  |  | OL1-2M06-5206 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  |  |  | OL1-2M06-5301 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  |  |  | OL1-2M06-5302 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  |  |  | OL1-2M06-5303 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT CROSS SECTION ELEVATION |  |  |  | OL1-2M06-6001 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT LONGITUDINAL ELEVATION |  |  |  | OL1-2M06-6002 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT RADIANT CROSS SECTION PLANS |  |  |  | OL1-2M06-6003 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE GENERAL ARRANGEMENT INSTRUMENTATION |  |  |  | OL1-2M06-6004 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE USX ASSEMBLY INSULATION DETAILS |  |  |  | OL1-2M06-6107 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE RADIANT COIL ASSEMBLY AND DETAILS |  |  |  | OL1-2M06-6201 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE TRANSFER LINE & CLEAN OUT DETAILS |  |  |  | OL1-2M06-6202 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE RADIANT COIL TUBESKIN THERMOCOUPLE DETAILS |  |  |  | OL1-2M06-6203 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE FABRICATION ASSEMBLY OF CONVECTION COILS, FINNED TUBES, AND BILL OF MATERIAL |  |  |  | OL1-2M06-6204 | ME | [6 empty] | Transmitted
| USC "132U" FURNACE CONVECTION COILS, CENTER WELD MAP, AND FINNING TABLE |  |  |  | OL1-2M06-6205 | ME | [6 empty] | Transmitted
| USC "132U" CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  |  |  | OL1-2M06-6206 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT & DETAILS |  |  |  | OL1-2M06-6301 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT DETAILS |  |  |  | OL1-2M06-6302 | ME | [6 empty] | Transmitted
| USC "132SU" FURNACE CONVECTION CAST INTERMEDIATE TUBE SUPPORT LOCATION |  |  |  | OL1-2M06-6303 | ME | [6 empty] | Transmitted
| MR API CENTRIFUGAL PUMPS |  |  |  | OL1-2M55-0002 | ME | [6 empty] | Transmitted
| MR HIGH SPEED PUMPS |  |  |  | OL1-2M55-0004 | ME | [6 empty] | Transmitted
| MR SUBMERSIBLE PUMPS |  |  |  | OL1-2M55-0005 | ME | [6 empty] | Transmitted
| MR MECH.SEALS & FLUSHING CONSOLES |  |  |  | OL1-2M55-0007 | ME | [6 empty] | Transmitted
| MR RECYCLE GAS SCREW COMPRESSOR |  |  |  | OL1-2M55-0010 | ME | [6 empty] | Transmitted
| MR VENT GAS BLOWER |  |  |  | OL1-2M55-0011 | ME | [6 empty] | Transmitted
| MR AGITATORS |  |  |  | OL1-2M55-0013 | ME | [6 empty] | Transmitted
| MR FOR SHOP ASSEMBLED REACTORS AND THICKER VESSELS |  |  |  | OL1-2M55-0050 | ME | [6 empty] | Transmitted
| MR FOR REACTORS TRAYS (BY AXENS) |  |  |  | OL1-2M55-0051 | ME | [6 empty] | Transmitted
| MR FOR SHOP ASS. LARGE COLUMNS |  |  |  | OL1-2M55-0052 | ME | [6 empty] | Transmitted
| MR FOR SHOP ASS. COLUMNS |  |  |  | OL1-2M55-0053 | ME | [6 empty] | Transmitted
| MR FOR SHOP ASS. COLUMNS (BUTADIENE UNIT BY LURGI) |  |  |  | OL1-2M55-0054 | ME | [6 empty] | Transmitted
| MR FOR COLUMNS TRAYS (RIPPLE TYPE) |  |  |  | OL1-2M55-0056 | ME | [6 empty] | Transmitted
| MR FOR COLUMNS TRAYS & INTERN. (BUTADIENE BY LURGI) |  |  |  | OL1-2M55-0057 | ME | [6 empty] | Transmitted
| MR FOR S&T HEAT EXCHANGERS (LARGE) |  |  |  | OL1-2M55-0059 | ME | [6 empty] | Transmitted
| MR FOR C.S. S&T HEAT EXCHANGERS |  |  |  | OL1-2M55-0060 | ME | [6 empty] | Transmitted
| MR FOR C.S. CLAD, S.S. AND LOW ALLOY S&T HEAT EXCHANGERS |  |  |  | OL1-2M55-0061 | ME | [6 empty] | Transmitted
| MR FOR C.S. S&T HEAT EXCHANGERS (BUTADIENE BY LURGI) |  |  |  | OL1-2M55-0062 | ME | [6 empty] | Transmitted
| MR FOR HAIRPIN H.E. |  |  |  | OL1-2M55-0063 | ME | [6 empty] | Transmitted
| MR FOR HEAT RECOVERY SYSTEM |  |  |  | OL1-2M55-0065 | ME | [6 empty] | Transmitted
| MR FOR SHOP ASSEMBLED C.S. LARGE DRUMS |  |  |  | OL1-2M55-0068 | ME | [6 empty] | Transmitted
| MR FOR SHOP ASSEMBLED C.S. VESSELS |  |  |  | OL1-2M55-0069 | ME | [6 empty] | Transmitted
| MR FOR SHOP ASSEMBLED C.S. CLAD, LOW ALLOY & S.S. VESSELS |  |  |  | OL1-2M55-0070 | ME | [6 empty] | Transmitted
| MR FOR SHOP ASSEMBLED C.S. DRUMS (BUTADIENE BY LURGI) |  |  |  | OL1-2M55-0071 | ME | [6 empty] | Transmitted
| MR FOR SHOP ASSEMBLED VESSELS |  |  |  | OL1-2M55-0072 | ME | [6 empty] | Transmitted
| MR FOR FIXED OR FLOATING ROOF TANKS |  |  |  | OL1-2M55-0073 | ME | [6 empty] | Transmitted
| MR FOR S&T HEAT EXCHANGERS |  |  |  | OL1-2M55-0074 | ME | [6 empty] | Transmitted
| MR DEMINERALIZATION AND POLISHING PACKAGE |  |  |  | OL1-2M55-0100 | ME | [6 empty] | Transmitted
| MR CONDENSATE CARBON FILTER PACKAGE |  |  |  | OL1-2M55-0101 | ME | [6 empty] | Transmitted
| MR COMPLEX WASTE WATER TREATMENT PACKAGE |  |  |  | OL1-2M55-0102 | ME | [6 empty] | Transmitted
| MR SILENCERS |  |  |  | OL1-2M55-0105 | ME | [6 empty] | Transmitted
| MR FILTERS AND COALESCERS |  |  |  | OL1-2M55-0106 | ME | [6 empty] | Transmitted
| MR QUENCH OIL FILTERS |  |  |  | OL1-2M55-0107 | ME | [6 empty] | Transmitted
| MR EJECTORS & STATIC MIXERS |  |  |  | OL1-2M55-0110 | ME | [6 empty] | Transmitted
| MR CHEMICAL DOSING SYSTEMS |  |  |  | OL1-2M55-0112 | ME | [6 empty] | Transmitted
| MR CRANES (BRIDGE, GANTRY ETC.) |  |  |  | OL1-2M55-0113 | ME | [6 empty] | Transmitted
| MR SANITARY WATER PACKAGE |  |  |  | OL1-2M55-0115 | ME | [6 empty] | Transmitted
| MR HP FLARE SYSTEM |  |  |  | OL1-2M55-0116 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR PEEP DOOR |  |  |  | OL1-2M55-2008 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR ELEVATOR |  |  |  | OL1-2M55-2009 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR MOV |  |  |  | OL1-2M55-2010 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR ATTEMPERATOR |  |  |  | OL1-2M55-2011 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR CONVECTION FINNING |  |  |  | OL1-2M55-2012 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR RADIANT REFRACTORY |  |  |  | OL1-2M55-2013 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR RADIANT STEEL PANEL |  |  |  | OL1-2M55-2014 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR CONVECTION FABRICATION |  |  |  | OL1-2M55-2015 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR UTILITY STEEL |  |  |  | OL1-2M55-2016 | ME | [6 empty] | Transmitted
| MATERIAL REQUISITION FOR PIPING SPRING SUPPORTS |  |  |  | OL1-2M55-2017 | ME | [6 empty] | Transmitted
| SPECIFICATION FOR FABRICATION OF CONVECTION COILS FOR CRACKING FURNACES |  |  |  | OL1-2M92-2004 | ME | [6 empty] | Transmitted
| SPECIFICATION FOR SUPPLY & INSTALLATION OF CERAMIC FIBER BLANKET & CF MODULE |  |  |  | OL1-2M92-2005 | ME | [6 empty] | Transmitted
| SPECIFICATION FOR SUPPLY & INSTALLATION OF REFRACTORY INSULATION |  |  |  | OL1-2M92-2006 | ME | [6 empty] | Transmitted
| PCC&SU SCHEDULE (LEVEL 1) |  |  |  | OL1-2O01-0001 | PE | [6 empty] | Transmitted
| PCC&SU SCHEDULE (LEVEL 2) |  |  |  | OL1-2O01-0002 | PE | [6 empty] | Transmitted
| PCC&SU SCHEDULE (LEVEL 3) |  |  |  | OL1-2O01-0003 | PE | [6 empty] | Transmitted
| PCC&SU MANPOWER SCHEDULE (INCLUDING RECRUITING) |  |  |  | OL1-2O01-0004 | PE | [6 empty] | Transmitted
| VENDORS AND LICENSORS FOR PCC&SU SUPPORT - SCHEDULE FOR EPCC PHASE |  |  |  | OL1-2O01-0005 | PE | [6 empty] | Transmitted
| CUO 107 - TRAINING SCHEDULE |  |  |  | OL1-2O01-0006 | PE | [6 empty] | Transmitted
| RAW MATERIAL, CHEMICALS AND UTILITIES SUPPLY PLAN & SCHEDULE |  |  |  | OL1-2O01-0007 | PE | [6 empty] | Transmitted
| PERFORMANCE TEST PROCEDURE |  |  |  | OL1-2O04-1004 | PE | [6 empty] | Transmitted
| CUO 107 - OPERATING MANUALS |  |  |  | OL1-2O06-0001 | PE | [6 empty] | Transmitted
| CUO 110 - PLANT MAINTENANCE MANUAL - COOLING WATER UNIT - S02 |  |  |  | OL1-2O07-0001 | PE | [6 empty] | Transmitted
| CUO 110 - PLANT MAINTENANCE MANUAL - OFFSITES - S04 |  |  |  | OL1-2O07-0002 | PE | [6 empty] | Transmitted
| CUO 110 - PLANT MAINTENANCE MANUAL - WASTE WATER TREATMENT - S05 |  |  |  | OL1-2O07-0003 | PE | [6 empty] | Transmitted
| CUO 110 - PLANT MAINTENANCE MANUAL - FURNACES - S06 |  |  |  | OL1-2O07-0004 | PE | [6 empty] | Transmitted
| CUO 110 - PLANT MAINTENANCE MANUAL - FRACTIONATION #1 & #2 - S07 |  |  |  | OL1-2O07-0005 | PE | [6 empty] | Transmitted
| CUO 110 - PLANT MAINTENANCE MANUAL - FRACTIONATION #3 & BUTADIENE EXTRACTION & AMINE TREATEMENT - S08 |  |  |  | OL1-2O07-0006 | PE | [6 empty] | Transmitted
| START-UP DELIVERABLE LIST |  |  |  | OL1-2O08-0001 | PE | [6 empty] | Transmitted
| START-UP PACKAGE LIST |  |  |  | OL1-2O08-0002 | PE | [6 empty] | Transmitted
| PROJECT SYSTEM LIST |  |  |  | OL1-2O08-0003 | PE | [6 empty] | Transmitted
| SPECIAL ACTIVITIES DOSSIER |  |  |  | OL1-2O08-0004 | PE | [6 empty] | Transmitted
| SYSTEM COMPONENT LIST WITH MARKED-UP DWGS |  |  |  | OL1-2O08-0005 | PE | [6 empty] | Transmitted
| CUO 110 - OPERATING SPARE PARTS STATUS REPORT |  |  |  | OL1-2O08-0007 | PE | [6 empty] | Transmitted
| RESPONSABILITY MATRIX - DEFINITION OF MECHANICAL COMPLET./PRE-COMMISSIONING TPIT-SUBCONTRACTOR |  |  |  | OL1-2O09-0001 | PE | [6 empty] | Transmitted
| DEFINITION OF SCOPE OF WORK - TPIT - SPECIALIZED COMPANY |  |  |  | OL1-2O09-0002 | PE | [6 empty] | Transmitted
| SYSTEMIZATION PHILOSOPHY |  |  |  | OL1-2O10-0001 | PE | [6 empty] | Transmitted
| CUO 110 - MAINTENANCE PHILOSOPHY DURING INTERIM MAINTENANCE MANAGEMENT |  |  |  | OL1-2O10-0002 | PE | [6 empty] | Transmitted
| PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - PIPING - ( 51 ÷ 99 ) |  |  |  | OL1-2O20-0001 | PE | [6 empty] | Transmitted
| PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - INSTRUMENTATION - ( 51 ÷ 99 ) |  |  |  | OL1-2O20-0002 | PE | [6 empty] | Transmitted
| PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - ELECTRICAL - ( 51 ÷ 99 ) |  |  |  | OL1-2O20-0003 | PE | [6 empty] | Transmitted
| PRE-COMMISSIONING/COMMISSIONING QUALITY CONTROL PLAN - MECHANICAL - ( 51 ÷ 99 ) |  |  |  | OL1-2O20-0004 | PE | [6 empty] | Transmitted
| ALARM & SETPOINT SUMMARY |  |  |  | OL1-2O67-1001 | PE | [6 empty] | Transmitted
| ALARM & SETPOINT SUMMARY |  |  |  | OL1-2O67-2001 | PE | [6 empty] | Transmitted
| ALARM & SETPOINT SUMMARY |  |  |  | OL1-2O67-3001 | PE | [6 empty] | Transmitted
| ALARM & SETPOINT SUMMARY |  |  |  | OL1-2O67-4001 | PE | [6 empty] | Transmitted
| ALARM & SETPOINT SUMMARY |  |  |  | OL1-2O67-5001 | PE | [6 empty] | Transmitted
| ALARM & SETPOINT SUMMARY |  |  |  | OL1-2O67-6001 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR WATER FLUSHING OF PIPING & EQUIPMENT |  |  |  | OL1-2O71-0001 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR AIR BLOWING OF PIPING & EQUIPMENT |  |  |  | OL1-2O71-0002 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR DRYING OF PIPING & EQUIPMENT |  |  |  | OL1-2O71-0003 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR GROSS LEAK TEST |  |  |  | OL1-2O71-0004 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR TIGHTNESS TEST |  |  |  | OL1-2O71-0005 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR STEAM BLOWING OF PIPING & EQUIPMENT |  |  |  | OL1-2O71-0006 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR CHEMICAL CLEANING OF CS OF PIPING & EQUIPMENT |  |  |  | OL1-2O71-0007 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR CHEMICAL CLEANING OF SS OF PIPING & EQUIPMENT |  |  |  | OL1-2O71-0008 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR NITROGEN PURGING OF PIPING & EQUIPMENT |  |  |  | OL1-2O71-0009 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR HYDRO-JETTING OF PIPING & EQUIPMENT |  |  |  | OL1-2O71-0010 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR OIL FLUSHING |  |  |  | OL1-2O71-0011 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR MANUAL CLEANING FOR LARGE BORE PIPING PROCEDURE |  |  |  | OL1-2O71-0012 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR PIPING INSPECTION |  |  |  | OL1-2O71-0013 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR RELIEF VALVE MANAGEMENT |  |  |  | OL1-2O71-0014 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR SPRING HANGER SETTING |  |  |  | OL1-2O71-0015 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR TIGHTNESS TEST WITH NITROGEN & HELIUM |  |  |  | OL1-2O71-0016 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR LOOP CHECK MANAGEMENT |  |  |  | OL1-2O71-0017 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR LOOP FOLDER MANAGEMENT |  |  |  | OL1-2O71-0018 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR ELECTRICAL MOTOR SOLO RUN |  |  |  | OL1-2O71-0019 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR ELECTRICAL SUBSTATION ENERGIZATION |  |  |  | OL1-2O71-0020 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR PUMP ALIGNMENT |  |  |  | OL1-2O71-0021 | PE | [6 empty] | Transmitted
| JOB START UP SPECIFICATION FOR VESSELS/EQUIPMENT INSPECTION |  |  |  | OL1-2O71-0022 | PE | [6 empty] | Transmitted
| CUO 110 - JOB START UP SPECIF.FOR MTL PRESERVATION DURING CONSTRUCTION, PRECOMM., COMMISS. AND STARTUP |  |  |  | OL1-2O71-0023 | PE | [6 empty] | Transmitted
| SITE PCC&SU ORGANIZATION CHART |  |  |  | OL1-2O71-0024 | PE | [6 empty] | Transmitted
| OVERALL PCC&SU EXECUTION PLAN |  |  |  | OL1-2O71-0025 | PE | [6 empty] | Transmitted
| RESPONSIBILITY MATRIX - DEFINIT.OF MECH.COMPLET./PRE-COMM./COMM./START UP/OPERAT.TPIT-OWNER |  |  |  | OL1-2O71-0026 | PE | [6 empty] | Transmitted
| HANDOVER PROCEDURE (INLUDING PUNCH LIST MANAGEMENT & INDEX DOSSIER) |  |  |  | OL1-2O71-0027 | PE | [6 empty] | Transmitted
| JOB START SPECIFICATION FOR FUNCTIONAL TEST MANAGEMENT |  |  |  | OL1-2O71-0029 | PE | [6 empty] | Transmitted
| GOVERNANCE FOR INTEGRATED TEAM |  |  |  | OL1-2O71-0030 | PE | [6 empty] | Transmitted
| PLANT OPERATION PLAN |  |  |  | OL1-2O71-0032 | PE | [6 empty] | Transmitted
| CUO 107 - GUIDELINES FOR SUPERVISORY AND COMPREHENSIVE OPERATING MANUALS |  |  |  | OL1-2O71-0033 | PE | [6 empty] | Transmitted
| GUIDELINES FOR OTP PREPARATION |  |  |  | OL1-2O71-0034 | PE | [6 empty] | Transmitted
| CUO 107 - TRAINING PLAN |  |  |  | OL1-2O71-0036 | PE | [6 empty] | Transmitted
| CUO 107 - PLAN OF INSTRUCTION |  |  |  | OL1-2O71-0037 | PE | [6 empty] | Transmitted
| CUO 107 - TRAINING MANUAL |  |  |  | OL1-2O71-0039 | PE | [6 empty] | Transmitted
| FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  |  | OL1-2O71-1001 | PE | [6 empty] | Transmitted
| FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  |  | OL1-2O71-2001 | PE | [6 empty] | Transmitted
| FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  |  | OL1-2O71-3001 | PE | [6 empty] | Transmitted
| FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  |  | OL1-2O71-4001 | PE | [6 empty] | Transmitted
| FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  |  | OL1-2O71-5001 | PE | [6 empty] | Transmitted
| FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  |  | OL1-2O71-6001 | PE | [6 empty] | Transmitted
| OPERATIONAL TEST PROCEDURE (OTP) |  |  |  | OL1-2O75-0001 | PE | [6 empty] | Transmitted
| SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  |  | OL1-2O75-1001 | PE | [6 empty] | Transmitted
| SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  |  | OL1-2O75-2001 | PE | [6 empty] | Transmitted
| SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  |  | OL1-2O75-3001 | PE | [6 empty] | Transmitted
| SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  |  | OL1-2O75-4001 | PE | [6 empty] | Transmitted
| SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  |  | OL1-2O75-5001 | PE | [6 empty] | Transmitted
| SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  |  | OL1-2O75-6001 | PE | [6 empty] | Transmitted
| SAMPLING AND ANALYTICAL MANUAL |  |  |  | OL1-2O80-1003 | PE | [6 empty] | Transmitted
| INSTRUCTIONS TO SUPPLIER FOR FILLING-UP OF SPARE PARTS AND INTERCHANGEABILITY RECORD (SPIR FORM) |  |  |  | OL1-2O92-0001 | PE | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM - DATA SHEETS |  |  |  | OL1-2P03-1101 | MP | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM - DATA SHEETS |  |  |  | OL1-2P03-1201 | MP | [6 empty] | Transmitted
| SP/RO DATASHEETS - MIXING T |  |  |  | OL1-2P03-1202 | MP | [6 empty] | Transmitted
| SP/RO DATASHEETS - ANGLE VALVES |  |  |  | OL1-2P03-1203 | MP | [6 empty] | Transmitted
| SP/RO DATASHEETS - SAMPLE COOLER |  |  |  | OL1-2P03-1204 | MP | [6 empty] | Transmitted
| SP/RO DATASHEETS - ISOKINETIC NOZZLE |  |  |  | OL1-2P03-1205 | MP | [6 empty] | Transmitted
| SP/RO DATASHEETS - SILENCER |  |  |  | OL1-2P03-1206 | MP | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM - DATA SHEETS |  |  |  | OL1-2P03-1301 | MP | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM - DATA SHEETS |  |  |  | OL1-2P03-1401 | MP | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM - DATA SHEETS |  |  |  | OL1-2P03-1501 | MP | [6 empty] | Transmitted
| PIPING SPECIALTY ITEM - DATA SHEETS |  |  |  | OL1-2P03-1601 | MP | [6 empty] | Transmitted
| AREA 30 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2P03-XXXA | MP | [6 empty] | Transmitted
| AREA 53 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2P03-XXXB | MP | [6 empty] | Transmitted
| AREA 55 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2P03-XXXC | MP | [6 empty] | Transmitted
| AREA 56 SP ITEM DATA SHEETS & INDEX, OLEFINS UNIT |  |  |  | OL1-2P03-XXXD | MP | [6 empty] | Transmitted
| SP ITEM DATA SHEETS, OLEFINS UNIT |  |  |  | OL1-2P03-XXXX | MP | [6 empty] | Transmitted
| CRITICAL LINE LIST - COOLING WATER UNIT |  |  |  | OL1-2P05-0002 | MP | [6 empty] | Transmitted
| CRITICAL LINE LIST - MAIN PIPE RACK |  |  |  | OL1-2P05-0003 | MP | [6 empty] | Transmitted
| CRITICAL LINE LIST - OFF-SITES |  |  |  | OL1-2P05-0004 | MP | [6 empty] | Transmitted
| CRITICAL LINE LIST - WASTE WATER TREATMENT |  |  |  | OL1-2P05-0005 | MP | [6 empty] | Transmitted
| CRITICAL LINE LIST - FURNACES UTILITIES |  |  |  | OL1-2P05-0006 | MP | [6 empty] | Transmitted
| CRITICAL LINE LIST - FRACTIONATION #1 & #2 |  |  |  | OL1-2P05-0007 | MP | [6 empty] | Transmitted
| CRITICAL LINE LIST - FRACTIONATION #3 & BUTADIENE EXTRACTION |  |  |  | OL1-2P05-0008 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  |  | OL1-2P05-1101 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  |  | OL1-2P05-1102 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  |  | OL1-2P05-1103 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  |  | OL1-2P05-1104 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  |  | OL1-2P05-1105 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  |  | OL1-2P05-1106 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  |  | OL1-2P05-1107 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  |  | OL1-2P05-1108 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  |  | OL1-2P05-1109 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  |  | OL1-2P05-1110 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  |  | OL1-2P05-1111 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  |  | OL1-2P05-1112 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  |  | OL1-2P05-1113 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  |  | OL1-2P05-1114 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  |  | OL1-2P05-1115 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  |  | OL1-2P05-1116 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  |  | OL1-2P05-1117 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  |  | OL1-2P05-1118 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  |  | OL1-2P05-1119 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  |  | OL1-2P05-1120 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  |  | OL1-2P05-1121 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  |  | OL1-2P05-1122 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  |  | OL1-2P05-1123 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  |  | OL1-2P05-1124 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  |  | OL1-2P05-1201 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  |  | OL1-2P05-1202 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  |  | OL1-2P05-1203 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  |  | OL1-2P05-1204 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  |  | OL1-2P05-1205 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  |  | OL1-2P05-1206 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  |  | OL1-2P05-1207 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  |  | OL1-2P05-1208 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  |  | OL1-2P05-1209 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  |  | OL1-2P05-1210 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  |  | OL1-2P05-1211 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  |  | OL1-2P05-1212 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  |  | OL1-2P05-1213 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  |  | OL1-2P05-1214 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  |  | OL1-2P05-1215 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  |  | OL1-2P05-1216 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  |  | OL1-2P05-1217 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  |  | OL1-2P05-1218 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  |  | OL1-2P05-1219 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  |  | OL1-2P05-1220 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  |  | OL1-2P05-1221 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  |  | OL1-2P05-1222 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  |  | OL1-2P05-1223 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  |  | OL1-2P05-1224 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  |  | OL1-2P05-1301 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  |  | OL1-2P05-1302 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  |  | OL1-2P05-1303 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  |  | OL1-2P05-1304 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  |  | OL1-2P05-1305 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  |  | OL1-2P05-1306 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  |  | OL1-2P05-1307 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  |  | OL1-2P05-1308 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  |  | OL1-2P05-1309 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  |  | OL1-2P05-1310 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  |  | OL1-2P05-1311 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  |  | OL1-2P05-1312 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  |  | OL1-2P05-1313 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  |  | OL1-2P05-1314 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  |  | OL1-2P05-1315 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  |  | OL1-2P05-1316 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  |  | OL1-2P05-1317 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  |  | OL1-2P05-1318 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  |  | OL1-2P05-1319 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  |  | OL1-2P05-1320 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  |  | OL1-2P05-1321 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  |  | OL1-2P05-1322 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  |  | OL1-2P05-1323 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  |  | OL1-2P05-1324 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  |  | OL1-2P05-1401 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  |  | OL1-2P05-1402 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  |  | OL1-2P05-1403 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  |  | OL1-2P05-1404 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  |  | OL1-2P05-1405 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  |  | OL1-2P05-1406 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  |  | OL1-2P05-1407 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  |  | OL1-2P05-1408 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  |  | OL1-2P05-1409 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  |  | OL1-2P05-1410 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  |  | OL1-2P05-1411 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  |  | OL1-2P05-1412 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  |  | OL1-2P05-1413 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  |  | OL1-2P05-1414 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  |  | OL1-2P05-1415 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  |  | OL1-2P05-1416 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  |  | OL1-2P05-1417 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  |  | OL1-2P05-1418 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  |  | OL1-2P05-1419 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  |  | OL1-2P05-1420 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  |  | OL1-2P05-1421 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  |  | OL1-2P05-1422 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  |  | OL1-2P05-1423 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  |  | OL1-2P05-1424 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  |  | OL1-2P05-1501 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  |  | OL1-2P05-1502 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  |  | OL1-2P05-1503 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  |  | OL1-2P05-1504 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  |  | OL1-2P05-1505 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  |  | OL1-2P05-1506 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  |  | OL1-2P05-1507 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  |  | OL1-2P05-1508 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  |  | OL1-2P05-1509 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  |  | OL1-2P05-1510 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  |  | OL1-2P05-1511 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  |  | OL1-2P05-1512 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  |  | OL1-2P05-1513 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  |  | OL1-2P05-1514 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  |  | OL1-2P05-1515 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  |  | OL1-2P05-1516 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  |  | OL1-2P05-1517 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  |  | OL1-2P05-1518 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  |  | OL1-2P05-1519 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  |  | OL1-2P05-1520 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  |  | OL1-2P05-1521 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  |  | OL1-2P05-1522 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  |  | OL1-2P05-1523 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  |  | OL1-2P05-1524 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  |  | OL1-2P05-1601 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  |  | OL1-2P05-1602 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  |  | OL1-2P05-1603 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  |  | OL1-2P05-1604 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  |  | OL1-2P05-1605 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  |  | OL1-2P05-1606 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  |  | OL1-2P05-1607 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  |  | OL1-2P05-1608 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  |  | OL1-2P05-1609 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  |  | OL1-2P05-1610 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  |  | OL1-2P05-1611 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  |  | OL1-2P05-1612 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  |  | OL1-2P05-1613 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  |  | OL1-2P05-1614 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  |  | OL1-2P05-1615 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  |  | OL1-2P05-1616 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  |  | OL1-2P05-1617 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  |  | OL1-2P05-1618 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  |  | OL1-2P05-1619 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  |  | OL1-2P05-1620 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  |  | OL1-2P05-1621 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  |  | OL1-2P05-1622 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  |  | OL1-2P05-1623 | MP | [6 empty] | Transmitted
| PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  |  | OL1-2P05-1624 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 0C |  |  |  | OL1-2P05-2000 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0C |  |  |  | OL1-2P05-2001 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 5T |  |  |  | OL1-2P05-2500 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5T |  |  |  | OL1-2P05-2501 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 0P |  |  |  | OL1-2P05-3000 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0P |  |  |  | OL1-2P05-3001 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 5R |  |  |  | OL1-2P05-4000 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5R |  |  |  | OL1-2P05-4001 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 5F |  |  |  | OL1-2P05-4500 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5F |  |  |  | OL1-2P05-4501 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 5W |  |  |  | OL1-2P05-5000 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5W |  |  |  | OL1-2P05-5001 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 1B |  |  |  | OL1-2P05-6000 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 1B |  |  |  | OL1-2P05-6001 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 2A |  |  |  | OL1-2P05-7000 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2A |  |  |  | OL1-2P05-7001 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 2B |  |  |  | OL1-2P05-7200 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2B |  |  |  | OL1-2P05-7201 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 2D |  |  |  | OL1-2P05-7400 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2D |  |  |  | OL1-2P05-7401 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 2E |  |  |  | OL1-2P05-7600 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2E |  |  |  | OL1-2P05-7601 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 5U |  |  |  | OL1-2P05-7800 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5U |  |  |  | OL1-2P05-7801 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 2C |  |  |  | OL1-2P05-8000 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2C |  |  |  | OL1-2P05-8001 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANAL.CALC.LIST - ZONE 3A |  |  |  | OL1-2P05-8500 | MP | [6 empty] | Transmitted
| COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 3A |  |  |  | OL1-2P05-8501 | MP | [6 empty] | Transmitted
| GENERAL PLOT PLAN |  |  |  | OL1-2P06-0001 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN METERING STATION |  |  |  | OL1-2P06-0002 | MP | [6 empty] | Transmitted
| DETAIL PLOT-PLAN MAIN PIPE RACK |  |  |  | OL1-2P06-0003 | MP | [6 empty] | Transmitted
| DETAIL PLOT-PLAN ELECTRICAL SUB-STATION & FAR E |  |  |  | OL1-2P06-0004 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN FURNACES |  |  |  | OL1-2P06-0005 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN FURNACES AND AUXILIARIES |  |  |  | OL1-2P06-0006 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN QUENCH |  |  |  | OL1-2P06-0007 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN C3 HYDROGENATION |  |  |  | OL1-2P06-0008 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN HOT FRACTIONATION / GHU UNIT |  |  |  | OL1-2P06-0009 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN PROCESS COLD COMPRESSORS |  |  |  | OL1-2P06-0010 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  |  |  | OL1-2P06-0011 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN BUTADIENE EXTRACTION UNIT |  |  |  | OL1-2P06-0012 | MP | [6 empty] | Transmitted
| DETAIL PLOT-PLAN ELECTRICAL SUB-STATION & FAR C |  |  |  | OL1-2P06-0013 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN FLARE UNIT |  |  |  | OL1-2P06-0014 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN COOLING WATER UNIT |  |  |  | OL1-2P06-0015 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN UTILITIES |  |  |  | OL1-2P06-0016 | MP | [6 empty] | Transmitted
| DETAIL PLOT PLAN WASTE WATER TREATMENT UNIT |  |  |  | OL1-2P06-0017 | MP | [6 empty] | Transmitted
| GENERAL KEY-PLAN |  |  |  | OL1-2P06-0020 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN METERING STATION |  |  |  | OL1-2P06-0021 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN MAIN PIPE RACK |  |  |  | OL1-2P06-0022 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  |  |  | OL1-2P06-0023 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN FURNACES |  |  |  | OL1-2P06-0024 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN FURNACES AUXILIARIES |  |  |  | OL1-2P06-0025 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN QUENCH |  |  |  | OL1-2P06-0026 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN C3 HYDROGENATION |  |  |  | OL1-2P06-0027 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN HOT FRACTIONATION / GHU DETAIL |  |  |  | OL1-2P06-0028 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN COLD COMPRESSORS |  |  |  | OL1-2P06-0029 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  |  |  | OL1-2P06-0030 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN BUTADIENE EXTRACTION DETAIL |  |  |  | OL1-2P06-0031 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  |  |  | OL1-2P06-0032 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN FLARE DETAIL |  |  |  | OL1-2P06-0033 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN COOLING WATER DETAIL |  |  |  | OL1-2P06-0034 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN UTILITIES |  |  |  | OL1-2P06-0035 | MP | [6 empty] | Transmitted
| DETAIL KEY-PLAN WASTE WATER TREATMENT DETAIL |  |  |  | OL1-2P06-0036 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN MAIN PIPE RACK |  |  |  | OL1-2P06-0040 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN FURNACES AUXILIARIES |  |  |  | OL1-2P06-0041 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN QUENCH |  |  |  | OL1-2P06-0042 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN C3 HYDROGENATION |  |  |  | OL1-2P06-0043 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN HOT FRACTIONATION / GHU UNIT |  |  |  | OL1-2P06-0044 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN COLD COMPRESSORS |  |  |  | OL1-2P06-0045 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  |  |  | OL1-2P06-0046 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN BUTADIENE EXTRACTION UNIT |  |  |  | OL1-2P06-0047 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN FLARE UNIT |  |  |  | OL1-2P06-0048 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN COOLING WATER UNIT |  |  |  | OL1-2P06-0049 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN UTILITIES |  |  |  | OL1-2P06-0050 | MP | [6 empty] | Transmitted
| UTILITY STATION PLOT PLAN WASTE WATER TREATMENT UNIT |  |  |  | OL1-2P06-0051 | MP | [6 empty] | Transmitted
| STEAM TRACING MANIFOLDS LOCATION PLAN MAIN PIPE RACK |  |  |  | OL1-2P06-0060 | MP | [6 empty] | Transmitted
| STEAM TRACING MANIFOLDS LOCATION PLAN QUENCH |  |  |  | OL1-2P06-0061 | MP | [6 empty] | Transmitted
| STEAM TRACING MANIFOLDS LOCATION PLAN C3 HYDROGENATION |  |  |  | OL1-2P06-0062 | MP | [6 empty] | Transmitted
| STEAM TRACING MANIFOLDS LOCATION PLAN HOT FRACTIONATION / GHU UNIT |  |  |  | OL1-2P06-0063 | MP | [6 empty] | Transmitted
| STEAM TRACING MANIFOLDS LOCATION PLAN COLD COMPRESSORS |  |  |  | OL1-2P06-0064 | MP | [6 empty] | Transmitted
| STEAM TRACING MANIFOLDS LOCATION PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  |  |  | OL1-2P06-0065 | MP | [6 empty] | Transmitted
| STEAM TRACING MANIFOLDS LOCATION PLAN BUTADIENE EXTRACTION UNIT |  |  |  | OL1-2P06-0066 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN MAIN PIPE RACK |  |  |  | OL1-2P06-0070 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN METERING STATION |  |  |  | OL1-2P06-0071 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  |  |  | OL1-2P06-0072 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN FURNACES AUXILIARIES |  |  |  | OL1-2P06-0073 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN QUENCH |  |  |  | OL1-2P06-0074 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN C3 HYDROGENATION |  |  |  | OL1-2P06-0075 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN HOT FRACTIONATION / GHU UNIT |  |  |  | OL1-2P06-0076 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN COLD COMPRESSORS |  |  |  | OL1-2P06-0077 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  |  |  | OL1-2P06-0078 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN BUTADIENE EXTRACTION UNIT |  |  |  | OL1-2P06-0079 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  |  |  | OL1-2P06-0080 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN FLARE UNIT |  |  |  | OL1-2P06-0081 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN FLARE LINES ROUTING |  |  |  | OL1-2P06-0082 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN COOLING WATER UNIT |  |  |  | OL1-2P06-0083 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN UTILITIES |  |  |  | OL1-2P06-0084 | MP | [6 empty] | Transmitted
| STD.AUX.PIPE SUPPORTS COLLECTION |  |  |  | OL1-2P06-0085 | MP | [6 empty] | Transmitted
| GAD KEY-PLAN WASTE WATER TREATMENT UNIT |  |  |  | OL1-2P06-0086 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0C |  |  |  | OL1-2P06-2000 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5T |  |  |  | OL1-2P06-2500 | MP | [6 empty] | Transmitted
| MISC ENGINEERED SUPPORTS |  |  |  | OL1-2P06-2901 | MP | [6 empty] | Transmitted
| ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  |  | OL1-2P06-2902 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0P |  |  |  | OL1-2P06-3000 | MP | [6 empty] | Transmitted
| MISC ENGINEERED SUPPORTS |  |  |  | OL1-2P06-3901 | MP | [6 empty] | Transmitted
| ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  |  | OL1-2P06-3902 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5R |  |  |  | OL1-2P06-4000 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5F |  |  |  | OL1-2P06-4500 | MP | [6 empty] | Transmitted
| MISC ENGINEERED SUPPORTS |  |  |  | OL1-2P06-4901 | MP | [6 empty] | Transmitted
| ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  |  | OL1-2P06-4902 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2C |  |  |  | OL1-2P06-5000 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 3A |  |  |  | OL1-2P06-5500 | MP | [6 empty] | Transmitted
| MISC ENGINEERED SUPPORTS |  |  |  | OL1-2P06-5901 | MP | [6 empty] | Transmitted
| ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  |  | OL1-2P06-5902 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 1B |  |  |  | OL1-2P06-6000 | MP | [6 empty] | Transmitted
| MISC ENGINEERED SUPPORTS |  |  |  | OL1-2P06-6901 | MP | [6 empty] | Transmitted
| ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  |  | OL1-2P06-6902 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2A |  |  |  | OL1-2P06-7000 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2B |  |  |  | OL1-2P06-7200 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2D |  |  |  | OL1-2P06-7400 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2E |  |  |  | OL1-2P06-7600 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5U |  |  |  | OL1-2P06-7800 | MP | [6 empty] | Transmitted
| SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5W |  |  |  | OL1-2P06-8000 | MP | [6 empty] | Transmitted
| FIRE AND GAS DETECTOR LOCATION PLAN, OLEFINS UNIT - PRELIMINARY |  |  |  | OL1-2P06-XXXX | MP | [6 empty] | Transmitted
| FURNACE 10-H-1100 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 LARGE BORE ISOMETRIC DRAWINGS) |  |  |  | OL1-2P10-10XX | MP | [6 empty] | Transmitted
| FURNACE 10-H-1100 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 SMALL BORE ISOMETRIC DRAWINGS) |  |  |  | OL1-2P10-10YY | MP | [6 empty] | Transmitted
| FURNACE 10-H-1200 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 LARGE BORE ISOMETRIC DRAWINGS) |  |  |  | OL1-2P10-20XX | MP | [6 empty] | Transmitted
| FURNACE 10-H-1200 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 SMALL BORE ISOMETRIC DRAWINGS) |  |  |  | OL1-2P10-20YY | MP | [6 empty] | Transmitted
| FURNACE 10-H-1300 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1300 ISOMETRIC DRAWINGS) |  |  |  | OL1-2P10-30XX | MP | [6 empty] | Transmitted
| FURNACE 10-H-1400 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1400 ISOMETRIC DRAWINGS) |  |  |  | OL1-2P10-40XX | MP | [6 empty] | Transmitted
| FURNACE 10-H-1500 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1500 ISOMETRIC DRAWINGS) |  |  |  | OL1-2P10-50XX | MP | [6 empty] | Transmitted
| FURNACE 10-H-1600 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1600 ISOMETRIC DRAWINGS) |  |  |  | OL1-2P10-60XX | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-0100 | MP | [6 empty] | Transmitted
| GAD BATTERY LIMIT OL1-A |  |  |  | OL1-2P20-0101 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-0200 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-0300 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-0400 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-1000 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-2100 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-2200 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-2300 | MP | [6 empty] | Transmitted
| GAD BATTERY LIMIT OU1-A |  |  |  | OL1-2P20-2301 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-2400 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-2500 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-3000 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-5100 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-5200 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-5300 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-5400 | MP | [6 empty] | Transmitted
| GAD (N...) |  |  |  | OL1-2P20-5500 | MP | [6 empty] | Transmitted
| AUX.PIPE SUPP.LIST & BILL OF MTL - COOLING WATER UNIT |  |  |  | OL1-2P30-0002 | MP | [6 empty] | Transmitted
| AUX.PIPE SUPP.LIST & BILL OF MTL - MAIN PIPE RACK |  |  |  | OL1-2P30-0003 | MP | [6 empty] | Transmitted
| AUX.PIPE SUPP.LIST & BILL OF MTL - OFF-SITES |  |  |  | OL1-2P30-0004 | MP | [6 empty] | Transmitted
| AUX.PIPE SUPP.LIST & BILL OF MTL - WASTE WATER TREATMENT |  |  |  | OL1-2P30-0005 | MP | [6 empty] | Transmitted
| AUX.PIPE SUPP.LIST & BILL OF MTL - FURNACES UTILITIES |  |  |  | OL1-2P30-0006 | MP | [6 empty] | Transmitted
| AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION #1 & #2 |  |  |  | OL1-2P30-0007 | MP | [6 empty] | Transmitted
| AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION #3 & BUTADIENE EXTRACTION |  |  |  | OL1-2P30-0008 | MP | [6 empty] | Transmitted
| TIE-INS / INTERFACE POINTS LIST |  |  |  | OL1-2P40-0007 | MP | [6 empty] | Transmitted
| STEAM TRACING MANIFOLD LIST |  |  |  | OL1-2P40-0008 | MP | [6 empty] | Transmitted
| PIPING MTO |  |  |  | OL1-2P54-2001 | MP | [6 empty] | Transmitted
| MR GATE GLOBE & CHECK FORGED VALVES |  |  |  | OL1-2P55-0001 | MP | [6 empty] | Transmitted
| MR GATE GLOBE & CHECK CAST VALVES |  |  |  | OL1-2P55-0002 | MP | [6 empty] | Transmitted
| MR BUTTERFLY VALVES |  |  |  | OL1-2P55-0003 | MP | [6 empty] | Transmitted
| MR PLUG VALVES |  |  |  | OL1-2P55-0004 | MP | [6 empty] | Transmitted
| MR BALL VALVES |  |  |  | OL1-2P55-0005 | MP | [6 empty] | Transmitted
| MR DUAL PLATE CHECK VALVES |  |  |  | OL1-2P55-0006 | MP | [6 empty] | Transmitted
| MR SPRING-ASSISTED CHECK VALVES |  |  |  | OL1-2P55-0007 | MP | [6 empty] | Transmitted
| MR CARBON STEEL SEAMLESS PIPE |  |  |  | OL1-2P55-0008 | MP | [6 empty] | Transmitted
| MR CARBON STEEL WELDED PIPE |  |  |  | OL1-2P55-0009 | MP | [6 empty] | Transmitted
| MR ALLOY STEEL SEAMLESS PIPE |  |  |  | OL1-2P55-0010 | MP | [6 empty] | Transmitted
| MR ALLOY STEEL WELDED PIPE |  |  |  | OL1-2P55-0011 | MP | [6 empty] | Transmitted
| MR STAINLESS STEEL SEAMLESS PIPE |  |  |  | OL1-2P55-0012 | MP | [6 empty] | Transmitted
| MR STAINLESS STEEL WELDED PIPE |  |  |  | OL1-2P55-0013 | MP | [6 empty] | Transmitted
| MR FIBERGLASS REINFORCED PLASTIC PIPING |  |  |  | OL1-2P55-0014 | MP | [6 empty] | Transmitted
| MR PE & PVC PIPING |  |  |  | OL1-2P55-0015 | MP | [6 empty] | Transmitted
| MR BUTTWELDING FITTINGS |  |  |  | OL1-2P55-0016 | MP | [6 empty] | Transmitted
| MR FORGED FITTINGS |  |  |  | OL1-2P55-0017 | MP | [6 empty] | Transmitted
| MR FLANGES BLINDS & DRIP RINGS |  |  |  | OL1-2P55-0018 | MP | [6 empty] | Transmitted
| MR GASKETS |  |  |  | OL1-2P55-0019 | MP | [6 empty] | Transmitted
| MR BOLTING |  |  |  | OL1-2P55-0020 | MP | [6 empty] | Transmitted
| MR STEAM TRAPS AND MANIFOLDS |  |  |  | OL1-2P55-0021 | MP | [6 empty] | Transmitted
| MR HOSE CONNECTIONS AND FLEXIBLE HOSES |  |  |  | OL1-2P55-0022 | MP | [6 empty] | Transmitted
| MR STRAINERS |  |  |  | OL1-2P55-0023 | MP | [6 empty] | Transmitted
| MR SIGHT FLOW INDICATORS |  |  |  | OL1-2P55-0024 | MP | [6 empty] | Transmitted
| MR SAMPLING PANELS |  |  |  | OL1-2P55-0025 | MP | [6 empty] | Transmitted
| MR INTERLOCKS |  |  |  | OL1-2P55-0026 | MP | [6 empty] | Transmitted
| MR FOR CRYOGENIC SUPPORTS |  |  |  | OL1-2P55-0027 | MP | [6 empty] | Transmitted
| MR FOR ITEMIZED SUPPORTS |  |  |  | OL1-2P55-0028 | MP | [6 empty] | Transmitted
| MR FOR EXPANSION JNTS. |  |  |  | OL1-2P55-0029 | MP | [6 empty] | Transmitted
| REQUISITION - ANGLE VALVE |  |  |  | OL1-2P55-2101 | MP | [6 empty] | Transmitted
| REQUISITION - SAMPLE COOLER |  |  |  | OL1-2P55-2102 | MP | [6 empty] | Transmitted
| REQUISITION - STRAINER |  |  |  | OL1-2P55-2103 | MP | [6 empty] | Transmitted
| REQUISITION - ISOKINETIC SAMPLING NOZZLE |  |  |  | OL1-2P55-2104 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 10 |  |  |  | OL1-2P91-1001 | MP | [6 empty] | Transmitted
| LINE DESIGNATION TABLE - FURNACE AREA |  |  |  | OL1-2P91-1101 | MP | [6 empty] | Transmitted
| LINE DESIGNATION TABLE - FURNACE AREA |  |  |  | OL1-2P91-1201 | MP | [6 empty] | Transmitted
| LINE DESIGNATION TABLE - FURNACE AREA |  |  |  | OL1-2P91-1301 | MP | [6 empty] | Transmitted
| LINE DESIGNATION TABLE - FURNACE AREA |  |  |  | OL1-2P91-1401 | MP | [6 empty] | Transmitted
| LINE DESIGNATION TABLE - FURNACE AREA |  |  |  | OL1-2P91-1501 | MP | [6 empty] | Transmitted
| LINE DESIGNATION TABLE - FURNACE AREA |  |  |  | OL1-2P91-1601 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 20 |  |  |  | OL1-2P91-2001 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 21 |  |  |  | OL1-2P91-2101 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 22 |  |  |  | OL1-2P91-2201 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 23 |  |  |  | OL1-2P91-2301 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 24 |  |  |  | OL1-2P91-2401 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 25 |  |  |  | OL1-2P91-2501 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 26 |  |  |  | OL1-2P91-2601 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 27 |  |  |  | OL1-2P91-2701 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 28 |  |  |  | OL1-2P91-2801 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 29 |  |  |  | OL1-2P91-2901 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS PROCESS AREA 30 |  |  |  | OL1-2P91-3001 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS UTILITY AREA 50 |  |  |  | OL1-2P91-5001 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS UTILITY AREA 53 |  |  |  | OL1-2P91-5301 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS UTILITY AREA 55 |  |  |  | OL1-2P91-5501 | MP | [6 empty] | Transmitted
| LINE LIST - OLEFINS UTILITY AREA 56 |  |  |  | OL1-2P91-5601 | MP | [6 empty] | Transmitted
| PIPING STANDARD ASSEMBLY COLLECTION |  |  |  | OL1-2P92-0001 | MP | [6 empty] | Transmitted
| PIPING DESIGN STANDARD DRAWINGS |  |  |  | OL1-2P92-0002 | MP | [6 empty] | Transmitted
| JOB CONSTRUCTION SPECIFICATION FOR BOLTED FLANGED JOINT ASSEMBLY |  |  |  | OL1-2P92-0004 | MP | [6 empty] | Transmitted
| CONSTRUCTION SPECIFICATION FOR PIPING PREFABRICATION, ERECTION AND NON DESTRUCTIVE TESTING |  |  |  | OL1-2P92-0007 | MP | [6 empty] | Transmitted
| HYDROSTATIC LEAK TESTING FOR PIPING SYSTEMS |  |  |  | OL1-2P92-0008 | MP | [6 empty] | Transmitted
| SPECIAL TECH.SPEC.PIP.PREFAB. & ERE. |  |  |  | OL1-2P92-0012 | MP | [6 empty] | Transmitted
| OVERALL PROJECT QUALITY PLAN |  |  |  | OL1-2Q92-0001 | QM | [6 empty] | Transmitted
| CONFIDENTIALITY PLAN |  |  |  | OL1-2Q92-0002 | QM | [6 empty] | Transmitted
| JOB DESIGN SPECIFICATION FOR GEOTECHNICAL RECOMMENDATIONS |  |  |  | OL1-2R02-0002 | CV | [6 empty] | Transmitted
| JOB DESIGN SPECIFICATION FOR PILES |  |  |  | OL1-2R02-0003 | CV | [6 empty] | Transmitted
| JOB SUPPLY SPEC.FOR STEEL STRUCT. |  |  |  | OL1-2R02-0006 | CV | [6 empty] | Transmitted
| TEKLA STRUCTURE MANAGEMENT FOR LSP COMPLEX PROJECT |  |  |  | OL1-2R02-0007 | CV | [6 empty] | Transmitted
| GUIDELINE FOR MTO SUMMARY FOR STEEL STRUCTURES WITH USE OF “TEKLA STRUCTURE” REPORT |  |  |  | OL1-2R02-0008 | CV | [6 empty] | Transmitted
| U/G AND A/G CIVIL MODEL MANAGEMENT |  |  |  | OL1-2R02-0009 | CV | [6 empty] | Transmitted
| 3D MODELING PROCEDURE FOR CIVIL DESIGNERS |  |  |  | OL1-2R02-0010 | CV | [6 empty] | Transmitted
| PIPING CLASSES SUMMARY & PIPING CLASSES |  |  |  | OL1-2R04-0001 | MP | [6 empty] | Transmitted
| JOB SUPPLY SPECIFICATION FOR GASKETS |  |  |  | OL1-2R04-0016 | MP | [6 empty] | Transmitted
| JOB SUPPLY SPECIFICATION FOR BOLTING |  |  |  | OL1-2R04-0017 | MP | [6 empty] | Transmitted
| JOB SUPPLY SPECIFICATION FOR REINFORCED THERMOSETTING RESIN PLASTIC PIPING |  |  |  | OL1-2R04-0018 | MP | [6 empty] | Transmitted
| JSS AUXILIARY PIPING SUPPORTS MATERIALS |  |  |  | OL1-2R04-0035 | MP | [6 empty] | Transmitted
| JSS CRYOGENIC SUPPORTS |  |  |  | OL1-2R04-0036 | MP | [6 empty] | Transmitted
| JSS FOR ROD & SPRING HANGERS |  |  |  | OL1-2R04-0037 | MP | [6 empty] | Transmitted
| JSS SLIDING PLATES |  |  |  | OL1-2R04-0038 | MP | [6 empty] | Transmitted
| JSS DYNAMIC PIPING SUPPORTS |  |  |  | OL1-2R04-0039 | MP | [6 empty] | Transmitted
| JSS METALLIC EXPANSION JOINTS |  |  |  | OL1-2R04-0040 | MP | [6 empty] | Transmitted
| PROTECTIVE RELAY AND CONTROL UNIT |  |  |  | OL1-2R05-0004 | EE | [6 empty] | Transmitted
| SUBSTATION DESIGN |  |  |  | OL1-2R05-0024 | EE | [6 empty] | Transmitted
| TELECOM NUMBERING |  |  |  | OL1-2R05-0028 | EE | [6 empty] | Transmitted
| NUMBERING SYSTEM FOR ELECTRICAL EQUIPMENT |  |  |  | OL1-2R05-0041 | EE | [6 empty] | Transmitted
| INTERCOM/PAGING / AUDIBLE ALARM SYSTEM EXTENT OF SUPPLY |  |  |  | OL1-2R05-1001 | EE | [6 empty] | Transmitted
| SAFETY SUPERVISORY SYSTEM EXTENT OF SUPPLY |  |  |  | OL1-2R05-1002 | EE | [6 empty] | Transmitted
| GROUNDING SYSTEM FOR INSTRUMENT |  |  |  | OL1-2R06-0012 | IE | [6 empty] | Transmitted
| SPEC. FOR ALARM MANAGEMENT |  |  |  | OL1-2R06-1002 | IE | [6 empty] | Transmitted
| JSD FOR CTRL & SAFETY PHILOSOPHY |  |  |  | OL1-2R06-1025 | IE | [6 empty] | Transmitted
| JSD FOR AUTOMATION SYSTEM AVAILABILITY |  |  |  | OL1-2R06-1026 | IE | [6 empty] | Transmitted
| PROCESS ONLINE ANALYZER AND ANALYZER HOUSING |  |  |  | OL1-2R06-2003 | IE | [6 empty] | Transmitted
| TAGGING PROCEDURE |  |  |  | OL1-2R07-0001 | ME | [6 empty] | Transmitted
| EQUIPMENT PRESERVATION |  |  |  | OL1-2R07-0010 | ME | [6 empty] | Transmitted
| DRAFTING PROCEDURE FOR 2D DRAWINGS |  |  |  | OL1-2R07-0023 | ME | [6 empty] | Transmitted
| 3D MODELING |  |  |  | OL1-2R07-0024 | ME | [6 empty] | Transmitted
| REQUIREMENTS FOR EQIPMENT SUPPLIER 3D MODEL |  |  |  | OL1-2R07-0025 | ME | [6 empty] | Transmitted
| 3D MODELING PROCEDURE FOR PIPING DESIGNERS |  |  |  | OL1-2R07-0027 | ME | [6 empty] | Transmitted
| SPECIAL TEC.SP.FOR ERECT |  |  |  | OL1-2R08-0001 | CON | [6 empty] | Transmitted
| GUIDELINE FOR CRACKING FURNACE CONSTRUCTION / ERECTION |  |  |  | OL1-2R93-2001 | CON | [6 empty] | Transmitted
| PROJECT HSSE PLAN |  |  |  | OL1-2S92-0001 | ES | [6 empty] | Transmitted
| INCIDENT INVESTIGATION AND REPORTING PROCEDURE |  |  |  | OL1-2S92-0002 | ES | [6 empty] | Transmitted
| TELECOMM.SYST ARCHITECTURE OF INTERCOM, PAGING AND AUDIBLE ALARM SYSTEMS |  |  |  | OL1-2T11-0001 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT COMMON AREA |  |  |  | OL1-2T12-0002 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT METERING |  |  |  | OL1-2T12-0003 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT MAIN PIPE RACK |  |  |  | OL1-2T12-0004 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT AREA SUBSTATION E & FAR E |  |  |  | OL1-2T12-0005 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT AREA SUBSTATION C & FAR C |  |  |  | OL1-2T12-0006 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT FURNACES UTILITY |  |  |  | OL1-2T12-0007 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT QUENCH |  |  |  | OL1-2T12-0008 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS 20B |  |  |  | OL1-2T12-0009 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS 20C |  |  |  | OL1-2T12-0010 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS COLD COMPRESSORS |  |  |  | OL1-2T12-0011 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT PROCESS CGC |  |  |  | OL1-2T12-0012 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT BUTADIENE |  |  |  | OL1-2T12-0013 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT COOLING WATER UNIT |  |  |  | OL1-2T12-0014 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT UTILITIES |  |  |  | OL1-2T12-0015 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT WASTE WATER TREATMENT |  |  |  | OL1-2T12-0016 | EE | [6 empty] | Transmitted
| TELECOM & SECURITY SYSTEMS DEVICES LAYOUT FLARE AREA |  |  |  | OL1-2T12-0017 | EE | [6 empty] | Transmitted
| TELECOM WIRING DRAWINGS FOR FAR-E SYSTEMS |  |  |  | OL1-2T13-1001 | EE | [6 empty] | Transmitted
| TELECOM WIRING DRAWINGS FOR FAR-C SYSTEMS |  |  |  | OL1-2T13-1002 | EE | [6 empty] | Transmitted
| TELECOM WIRING DRAWINGS FOR FAR-FL SYSTEMS |  |  |  | OL1-2T13-1003 | EE | [6 empty] | Transmitted
| TELECOM WIRING DRAWINGS FOR CCB SYSTEMS |  |  |  | OL1-2T13-1004 | EE | [6 empty] | Transmitted
| TELECOM CABLE LIST FOR FAR C SYSTEMS |  |  |  | OL1-2T16-1001 | EE | [6 empty] | Transmitted
| TELECOM CABLE LIST FOR FAR E SYSTEMS |  |  |  | OL1-2T16-1002 | EE | [6 empty] | Transmitted
| TELECOM CABLE LIST FOR FAR FL SYSTEMS |  |  |  | OL1-2T16-1003 | EE | [6 empty] | Transmitted
| TELECOM CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  |  |  | OL1-2T16-1004 | EE | [6 empty] | Transmitted
| TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST |  |  |  | OL1-2T17-0001 | EE | [6 empty] | Transmitted
| TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST FOR OTHER CONTRACTORS |  |  |  | OL1-2T17-0002 | EE | [6 empty] | Transmitted
| FIBRE OPTIC TERMINATION DRAWINGS |  |  |  | OL1-2T26-0001 | EE | [6 empty] | Transmitted
| JSS FOR INTERCOM/PAGING/AUDIBLE ALARM SYSTEM |  |  |  | OL1-2T92-0001 | EE | [6 empty] | Transmitted
| JSS FOR SAFETY SUPERVISORY SYSTEM |  |  |  | OL1-2T92-0002 | EE | [6 empty] | Transmitted
| INTERFACE MANAGEMENT PLAN |  |  |  | OL1-2V92-0014 | IF | [6 empty] | Transmitted
| COORDINATION PROCEDURE |  |  |  | OL1-2W92-0001 | PC | [6 empty] | Transmitted
| PROJECT DOCUMENT CODING |  |  |  | OL1-2W92-0003 | PC | [6 empty] | Transmitted
| DOCUMENT MANAGEMENT PROCEDURE |  |  |  | OL1-2W92-0004 | PC | [6 empty] | Transmitted
| REQUIREMENTS FOR VENDOR DOCUMENTATION AND EXCHANGE OF CORRESPONDENCE |  |  |  | OL1-2W92-0005 | PC | [6 empty] | Transmitted
| TPSK PROJECT DIRECTORATE ORGANIZATION CHART |  |  |  | OL1-2W92-0006 | PC | [6 empty] | Transmitted
| TPSK ROC ORGANIZATION CHART |  |  |  | OL1-2W92-0007 | PC | [6 empty] | Transmitted
| CRITICALITY RATING PROCEDURE |  |  |  | OL1-2W92-0009 | PC | [6 empty] | Transmitted
| PRESCRIPTIONS FOR PREPARATION OF VENDOR DATA BOOK |  |  |  | OL1-2W92-0010 | PC | [6 empty] | Transmitted
| TPSK HOC ORGANIZATION CHART |  |  |  | OL1-2W92-0011 | PC | [6 empty] | Transmitted
| ITC PLAN |  |  |  | OL1-2W92-0012 | PC | [6 empty] | Transmitted
| PROJECT EXECUTION PLAN |  |  |  | OL1-2W92-0013 | PC | [6 empty] | Transmitted
| PRESCRIPTIONS FOR PREPARATION OF MANUFACTURING DATA RECORD BOOK |  |  |  | OL1-2W92-0015 | PC | [6 empty] | Transmitted
| REPORTING PROCEDURE |  |  |  | OL1-2W92-0016 | PC | [6 empty] | Transmitted
| ENGINEERING EXECUTION PLAN |  |  |  | OL1-2W92-0018 | PC | [6 empty] | Transmitted
| PROJECT CONTROL PROCEDURE |  |  |  | OL1-2W92-0019 | PC | [6 empty] | Transmitted
| TPSK SOC ORGANIZATION CHART |  |  |  | OL1-2W92-0020 | PC | [6 empty] | Transmitted
| TPSK KLOC ORGANIZATION CHART |  |  |  | OL1-2W92-0021 | PC | [6 empty] | Transmitted
| PROJECT ENGINEERING PLAN - PACKAGE A1 - FURNACES - HOUSTON SCOPE (INTERNAL ONLY) |  |  |  | OL1-2W92-2122 | PC | [6 empty] | Transmitted
| PAYMENT AND INVOICING PROCEDURE |  |  |  | OL1-2X01-0001 | PC | [6 empty] | Transmitted

## Foglio1
rev | fake rev
a | a
a | a
b | b
c | c
0 | z0
1 | z1