## CPY_Format
|  |  |  | Master Document Index (MDI) |  | ABBREVIATION | [10 empty] | DOCUMENT NO. | REV.
[6 empty] | **Revision Purpose of Issued Document |  |  |  | *Owner Feedback (Comment) |  |  |  |  | ***Classification
[6 empty] | IFR = Issue For Review |  | IFF = Issue For Final |  | A1 = App. w/o comments |  |  | R1 = No comments |  | Class 1 = For Approval |  | LSP-2W91-0001 | A
[6 empty] | IFA = Issue For Approval |  | ASB = Issue For As-Built |  | A2 = App. with comments, re-submit not required |  |  | R2 = Comments as noted |  | Class 2 = For Review
[6 empty] | IFC = Issue For Construction |  | AFC = Approved for Construction |  | A3 = App. with comments, re-submit for review |  |  |  |  | Class 3 = For Information
Owner: |  | Long Son Pterochemicals C0., Ltd. |  | Plant Name: PACKAGE A1: OLEFINS PLANT |  | IFI = Issue For Information |  | IMP = Issue for Implementation |  | A4 = Not App., re-submit for approval | [6 empty] | Issue Date
|  |  |  | Att. To OL1-2W91-0001 036909C-1000-NM-107 |  | IFP = Issue For Planning |  | / Execution
Document Code : | [5 empty] | IFD = Issue For Design |  | CAN = Issue for Cancellation |  | Period for Company's comment |  |  |  |  | __________ | Working Days
Item | Org. | Document No. | Document Name |  | Classification
Category Code: =Index!B30 =Index!C30
Category Code: A03 Technology transfer dossiers
Category Code: A04 Confidentiality Agreements
Category Code: A05 Laws and Regulations
Category Code: A06 Local content
Category Code: A09 Arbitration and Dispute Resolution
Category Code: A10 Guarantee of Labour Payment Affidavit
Category Code: A11 Termination or Amendment of Contracts
Category Code: A12 Liquidation Contract
Category Code: A13 Claim & Complaint from contractors
Category Code: A14 Claim & Complaint to contractors
Category Code: A15 Variation Change Notice
Category Code: A16 ITC - Instruction to Contractor
Category Code: A17 Contract Variation Form
Category Code: A18 License Agreement
Category Code: A19 Supplement Dossier
| CO | OL1-2A19-0001 | BD AND TD DOSSIER FOR PACKAGE A1 LSP |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CO-01546
Return Date
Owner Cmmt*
| CO | OL1-2A19-0002 | BD AND TD DOSSIER FOR PACKAGE A1 LSP |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CO-01902
Return Date
Owner Cmmt*
| CO | OL1-2A19-0003 | Appraisal BD & TD Documents For Olefins Plant (Excluding EGF) |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-24
[6 empty] | Issue Actual | 2019-09-24
[6 empty] | Transmittal no. | TPSK-LPSA1-T-CO-02692
Return Date
Owner Cmmt*
| CO | OL1-2A19-0004 | Firefighting Technical Design Dossier (Approved by VFFPD) |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-26
[6 empty] | Issue Actual | 2019-09-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CO-02693
Return Date
Owner Cmmt*
Category Code: A20 Certificates
Category Code: A21 Approval Letter
Category Code: A30 Certificate of Work Completion
Category Code: A41 Power of Attorney
Category Code: A42 Power of Attorney
Category Code: A43 Power of Attorney
Category Code: A44 Power of Attorney
Category Code: A51 Contract Document of Consultancy Service
Category Code: A52 Contract Document of EPC Contractor
Category Code: A53 Contract Document of Vendor/Supplier
Category Code: A61 Records of Management of Change (before final investment decision)
Category Code: A62 Records of Management of Change (after final investment decision)
Category Code: A71 Appraisal Report for Consultancy Service
Category Code: A72 Appraisal Report for EPC Contractor Work
Category Code: A73 Appraisal Report for Vendor/Supplier
Category Code: A91 Index/List
Category Code: A92 Procedures & Standards
| PC | OL1-2A92-0001 | Variation Order Procedure |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-10
[6 empty] | Issue Actual | 2018-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CO-00035
Return Date
Owner Cmmt*
| CO | OL1-2A92-0002 | Car & Third Party Insurance Claim Procedure |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-18
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CO-00192
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
Category Code: A93 Policy , Guidelines & Memo
Category Code: A94 Forms & Templates
Category Code: A95 Progress/Status Reports
Category Code: B01 Project Schedule
Category Code: B71 Appraisal Report for Consultancy Service
Category Code: B72 Appraisal Report for EPC Contractor Work
Category Code: B73 Appraisal Report for Vendor/Supplier
Category Code: B91 Index/List
Category Code: B92 Procedures & Standards
| PC | OL1-2B92-0001 | Planning Scheduling And Progress Measurement Procedure |  | Class 2 | Purpose** | IFR | IMP | IMP | IMP
[6 empty] | Rev. | A | 0 | 1 | 2
Issue Plan
[6 empty] | Revised Plan | 2018-09-13 | 2018-12-11
[6 empty] | Issue Actual | 2018-09-13 | 2018-12-11 | 2019-02-13 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00045 | TPSK-LSPA1-T-PC-00469 | TPSK-LSPA1-T-PC-00851 | TPSK-LSPA1-T-PC-02813
[6 empty] | Return Date | 2018-11-05 | 2019-02-25 | 2019-02-25
[6 empty] | Owner Cmmt* | R2 | A4 | A3
| PC | OL1-2B92-0006 | Plant And Section Codes |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 1
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-02075
[6 empty] | Return Date | 2019-07-15
[6 empty] | Owner Cmmt* | R1
Category Code: B93 Policy , Guidelines & Memo
Category Code: B94 Forms & Templates
Category Code: B95 Progress/Status Reports
Category Code: C01 Subvendor List
| PL | OL1-2C01-0001 | Subvendor List For Compressor And Turboexpander - Abstract From Approved Vendor List |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-05
[6 empty] | Issue Actual | 2018-10-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00134
Return Date
Owner Cmmt*
| PL | OL1-2C01-0002 | Subvendor list for PSA/Deareator/Filter Package |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-11-19
[6 empty] | Issue Actual | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00333
Return Date
Owner Cmmt*
| PL | OL1-2C01-0003 | Subvendor list for Pumps |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-11-19
[6 empty] | Issue Actual | 2018-11-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00333
Return Date
Owner Cmmt*
Category Code: C10 Request for Quotation (RFQ) for Civil work (Engineering and Procurement)
Category Code: C11 Request for Quotation (RFQ) for Building work (Engineering and Procurement)
Category Code: C12 Request for Quotation (RFQ) for Steel Structure work (Engineering and Procurement)
| CV | OL1-2C12-000001 | Material Requisition For Steel Structures |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-06 | 2019-09-13
[6 empty] | Revised Plan | 2019-03-11 | 2019-10-10
[6 empty] | Issue Actual | 2019-03-11 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-1010 | TPSK-LSPA1-T-PL-02768
[6 empty] | Return Date | 2019-05-07
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C12-000002 | Material Requisition For Steel Structures |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02769
Return Date
Owner Cmmt*
| PL | OL1-2C12-301000 | Material Requisition for Radiant Steel Panel |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-03
[6 empty] | Issue Actual | 2019-04-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01229
Return Date
Owner Cmmt*
| ME | OL1-2C12-307000 | Material Requisition for Radiant Steel Panel |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2019-07-16 | 2019-10-21
[6 empty] | Revised Plan |  | 2019-05-21
[6 empty] | Issue Actual |  | 2019-05-21 | 2019-05-21
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01699 | TPSK-LSPA1-T-PL-01699
Return Date
Owner Cmmt*
| ME | OL1-2C12-308000 | Material Requisition for Utility Steel |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-07-16 | 2019-10-21
[6 empty] | Revised Plan | 2019-06-21 | 2019-10-10
[6 empty] | Issue Actual | 2019-06-21 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01952 | TPSK-LSPA1-T-PL-02784
Return Date
Owner Cmmt*
Category Code: C13 Request for Quotation (RFQ) for Mechanical work (Engineering and Procurement)
| ME | OL1-2C13-100000 | Material Requisition For Shop Assembled Large Columns |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-15 | 2019-09-26
[6 empty] | Revised Plan | 2019-01-07 | 2019-05-02
[6 empty] | Issue Actual | 2019-01-07 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00586 | TPSK-LSPA1-T-PL-01526
[6 empty] | Return Date | 2019-01-24 | 2019-05-20
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-101000 | Material Requisition For Shop Assembled Columns |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-15 | 2019-09-26
[6 empty] | Revised Plan | 2019-01-23 | 2019-06-26
[6 empty] | Issue Actual | 2019-01-23 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00705 | TPSK-LSPA1-T-PL-01989
[6 empty] | Return Date | 2019-06-06 | 2019-07-10
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-102000 | Material Requisition For Shop Assembled Columns (C4 Unit) |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-15 | 2019-09-26
[6 empty] | Revised Plan | 2019-05-10 | 2019-09-12
[6 empty] | Issue Actual | 2019-05-10 | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01623 | TPSK-LSPA1-T-PL-02616
[6 empty] | Return Date | 2019-05-24 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-111000 | Material Requisition For Reactors And Thicker Vessels Requisition For Iinquiry |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-22 | 2019-06-18
[6 empty] | Revised Plan | 2019-02-26 | 2019-06-25
[6 empty] | Issue Actual | 2019-02-26 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00918 | TPSK-LSPA1-T-PL-01972
[6 empty] | Return Date | 2019-06-06 | 2019-07-04
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-120000 | Material Requisition for Deaerator D-5100 - Ex Doc. Client Ref. OL1-2M55-0108 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-11-06 | 2019-02-15
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02 | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01210 | TPSK-LSPA1-T-PL-01210
[6 empty] | Return Date |  | 2019-06-06 | 2019-06-06
[6 empty] | Owner Cmmt* |  | R1 | R1
| ME | OL1-2C13-131000 | Material Requisition For Shop Assembled Large Drums |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-03-04 | 2019-07-17
[6 empty] | Issue Actual | 2019-03-04 | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00967 | TPSK-LSPA1-T-PL-02070
[6 empty] | Return Date | 2019-06-06 | 2019-08-01
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-132000 | Material Requisition For Shop Assembled CS Drums |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-03-13 | 2019-07-22
[6 empty] | Issue Actual | 2019-03-13 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01032 | TPSK-LSPA1-T-PL-02197
[6 empty] | Return Date | 2019-06-06 | 2019-07-31
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-133000 | Material Requisition For Shop Assembled CS Cladded And SS Vessels |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-03-27 | 2019-07-29
[6 empty] | Issue Actual | 2019-03-27 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01156 | TPSK-LSPA1-T-PL-02262
[6 empty] | Return Date | 2019-06-06 | 2019-08-16
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-134000 | Material Requisition for Shop Assembled Drums (C4 Unit) |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30 | 2019-06-03
[6 empty] | Revised Plan | 2019-07-01 | 2019-10-30 | 2019-07-01
[6 empty] | Issue Actual | 2019-07-01 |  | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02033 |  | TPSK-LSPA1-T-PL-02033
[6 empty] | Return Date | 2019-07-11 |  | 2019-07-11
[6 empty] | Owner Cmmt* | R2 |  | R2
| ME | OL1-2C13-140000 | Material Requisition for Quench Exchangers - For Next Revision See Document OL1-2C13-140000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 1 | 1
[6 empty] | Issue Plan | 2018-10-26 | 2018-12-17
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02 | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01221 | TPSK-LSPA1-T-PL-01221
[6 empty] | Return Date |  | 2019-06-20 | 2019-06-20
[6 empty] | Owner Cmmt* |  | R2 | R2
| ME | OL1-2C13-142000 | Material Requisition Plate And Frame Heat Exchangers Requisition For Purchase - Ex Doc. Client Ref. OL1-2M55-0064 |  |  | Purpose** | IFQ | IFP | IFP | IFP | IFP | IFP | IFP
[6 empty] | Rev. |  | 0 | 1 | 2 | 0 | 1 | 2
[6 empty] | Issue Plan | 2018-10-08 | 2019-02-14
[6 empty] | Revised Plan |  | 2019-02-26
[6 empty] | Issue Actual |  | 2019-02-26 | 2019-06-25 | 2019-07-09 | 2019-02-26 | 2019-06-25 | 2019-07-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-00916 | TPSK-LSPA1-T-PL-01971 | TPSK-LSPA1-T-PL-02098 | TPSK-LSPA1-T-PL-00916 | TPSK-LSPA1-T-PL-01971 | TPSK-LSPA1-T-PL-02098
[6 empty] | Return Date |  | 2019-06-06 | 2019-07-04 | 2019-07-15 | 2019-06-06 | 2019-07-04 | 2019-07-15
[6 empty] | Owner Cmmt* |  | R1 | R1 | R1 | R1 | R1 | R1
| PL | OL1-2C13-143000 | Material Requisition For Heat Recovery System Requisition For Purchase |  | Class 2 | Purpose** | IFP | IFP
[6 empty] | Rev. | 0 | 1
Issue Plan
[6 empty] | Revised Plan | 2019-02-22
[6 empty] | Issue Actual | 2019-02-22 | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00906 | TPSK-LSPA1-T-PL-01452
[6 empty] | Return Date | 2019-06-06 | 2019-05-20
[6 empty] | Owner Cmmt* | R2 | R1
| ME | OL1-2C13-144000 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry - For next rev. see Doc. Client Ref. OL1-2C13-144000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-15 | 2019-02-21
[6 empty] | Revised Plan |  | 2019-04-17
[6 empty] | Issue Actual |  | 2019-04-17 | 2019-04-17
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-1351 | TPSK-LSPA1-T-PL-1351
[6 empty] | Return Date |  | 2019-05-20 | 2019-05-20
[6 empty] | Owner Cmmt* |  | R1 | R1
| ME | OL1-2C13-145000 | Material Requisition For Hairpin Heat Exchangers Requisition For Inquiry |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-30 | 2019-05-10
[6 empty] | Revised Plan | 2019-03-14 | 2019-08-09
[6 empty] | Issue Actual | 2019-03-14 | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01046 | TPSK-LSPA1-T-PL-02389
[6 empty] | Return Date | 2019-06-06 | 2019-08-20
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-151000 | Material Requisition For Condensate Carbon Filter Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-19 | 2019-07-16
[6 empty] | Revised Plan | 2019-03-13 | 2019-08-14
[6 empty] | Issue Actual | 2019-03-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01039 | TPSK-LSPA1-T-PL-02402
[6 empty] | Return Date | 2019-06-07 | 2019-08-22
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-152000 | Material Requisition for Filters and Colaescer |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2019-01-24 | 2019-05-30
[6 empty] | Revised Plan |  | 2019-05-21
[6 empty] | Issue Actual |  | 2019-05-21 | 2019-05-21
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01689 | TPSK-LSPA1-T-PL-01689
[6 empty] | Return Date |  | 2019-05-30 | 2019-05-30
[6 empty] | Owner Cmmt* |  | R2 | R2
| PL | OL1-2C13-152000- | Material Requisition For Filters And Coalescers |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-01-28
[6 empty] | Issue Actual | 2019-01-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00737
[6 empty] | Return Date | 2019-06-06
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-161000 | Material Requisition for Silencers |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-03-18 | 2019-07-05 | 2019-03-18
[6 empty] | Revised Plan | 2019-07-15 | 2019-11-05 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 |  | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02146 |  | TPSK-LSPA1-T-PL-02146
[6 empty] | Return Date | 2019-08-01 |  | 2019-08-01
[6 empty] | Owner Cmmt* | R2 |  | R2
| ME | OL1-2C13-201000 | MATERIAL REQUISITION FOR SITE ASSEMBLED TANKS |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30 | 2019-06-03
[6 empty] | Revised Plan | 2019-05-21 | 2019-10-30 | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21 |  | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01688 |  | TPSK-LSPA1-T-PL-01688
[6 empty] | Return Date | 2019-05-31 |  | 2019-05-31
[6 empty] | Owner Cmmt* | R2 |  | R2
| PL | OL1-2C13-202000 | MATERIAL REQUISITION FOR FRP TANK |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01646
[6 empty] | Return Date | 2019-05-31
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-242000 | Material Requisition For Trays For Columns Requisition For Inquiry - For Next Revision See Document OL1-2C13-242000 |  |  | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. |  | 0 | 1 | 0 | 1
[6 empty] | Issue Plan | 2018-12-17 | 2019-04-10
[6 empty] | Revised Plan |  | 2019-04-17
[6 empty] | Issue Actual |  | 2019-04-17 | 2019-06-11 | 2019-04-17 | 2019-06-11
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01352 | TPSK-LSPA1-T-PL-01844 | TPSK-LSPA1-T-PL-01352 | TPSK-LSPA1-T-PL-01844
[6 empty] | Return Date |  | 2019-05-20 | 2019-06-24 | 2019-05-20 | 2019-06-24
[6 empty] | Owner Cmmt* |  | R1 | R1 | R1 | R1
| PL | OL1-2C13-243000 | Material Requisition For Ripple Trays And Internals |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-01-11
[6 empty] | Issue Actual | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00628
[6 empty] | Return Date | 2019-06-06
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2C13-244000 | MATERIAL REQUISITION FOR TRAYS COLUMNS (C4 UNIT) |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-27 | 2019-07-09
[6 empty] | Revised Plan | 2019-04-08 | 2019-09-03
[6 empty] | Issue Actual | 2019-04-08 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01268 | TPSK-LSPA1-T-PL-02544
[6 empty] | Return Date | 2019-06-07 | 2019-09-10
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-245000 | Material Requisition for High Efficiency Internals for Columns - For next rev see OL1-2C13-245000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-12-24 | 2019-04-17
[6 empty] | Revised Plan |  | 2019-05-23
[6 empty] | Issue Actual |  | 2019-05-23 | 2019-05-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01706 | TPSK-LSPA1-T-PL-01706
[6 empty] | Return Date |  | 2019-05-30 | 2019-05-30
[6 empty] | Owner Cmmt* |  | R1 | R1
| PL | OL1-2C13-246000 | Material Requisition for Packing of Columns (C4 Unit) |  | Class 2 | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-28 | 2019-07-08
[6 empty] | Issue Actual | 2019-03-28 | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01182 | TPSK-LSPA1-T-PL-02081
[6 empty] | Return Date | 2019-06-07 | 2019-07-16
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-251000 | Material Requisition For API Mechanical Seals and Seal System |  |  | Purpose** | IFQ | IFP | IMP
[6 empty] | Rev. | A |  | 0
[6 empty] | Issue Plan | 2019-01-17 | 2019-05-01
[6 empty] | Revised Plan | 2019-03-01 |  | 2019-07-09
[6 empty] | Issue Actual | 2019-03-01 |  | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00949 |  | TPSK-LSPA1-T-PL-02096
[6 empty] | Return Date |  |  | 2019-07-18
[6 empty] | Owner Cmmt* |  |  | R1
| ME | OL1-2C13-271000 | Material Requisition For Wieland Tubes (Solo Source) Requisition For Inquiry - For Next Revision See Document OL1-2C13-271000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan |  | 2019-02-08
[6 empty] | Issue Actual |  | 2019-02-08 | 2019-02-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-00829 | TPSK-LSPA1-T-PL-00829
Return Date
Owner Cmmt*
| ME | OL1-2C13-272000 | Material Requisition For S&T Heat Exchangers - Large - Requisition For Inquiry |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-02-13 | 2019-07-17
[6 empty] | Issue Actual | 2019-02-13 | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00849 | TPSK-LSPA1-T-PL-02169
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-273000 | Material Requisition For CS S-T Heat Exchangers - Lot 2 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-02-15 | 2019-07-25
[6 empty] | Issue Actual | 2019-02-15 | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00866 | TPSK-LSPA1-T-PL-02261
[6 empty] | Return Date | 2019-06-06 | 2019-08-14
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-274000 | Material Requisition For CS Clad SS And LAS S-T Heat Exchangers Requisition For Inquiry |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-02-15 | 2019-07-22
[6 empty] | Issue Actual | 2019-02-15 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00870 | TPSK-LSPA1-T-PL-02195
[6 empty] | Return Date | 2019-06-06 | 2019-07-31
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-275000 | Material Requisition For CS S&T Heat Exchangers (C4 UNIT) |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30 | 2019-06-03
[6 empty] | Revised Plan | 2019-06-10 | 2019-10-30 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10 |  | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01838 |  | TPSK-LSPA1-T-PL-01838
[6 empty] | Return Date | 2019-06-27 |  | 2019-06-27
[6 empty] | Owner Cmmt* | R2 |  | R2
| ME | OL1-2C13-281000 | Material Requisition for Furnace Convection Finnings |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-21 | 2019-03-20
[6 empty] | Revised Plan | 2019-01-23 | 2019-03-18
[6 empty] | Issue Actual | 2019-01-23 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00713 | TPSK-LSPA1-T-PL-01085
Return Date
Owner Cmmt*
| ME | OL1-2C13-282000 | Material Requisition for Convection Fabrication |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-07-16 | 2019-10-21
[6 empty] | Revised Plan | 2019-04-12 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-12 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01316 | TPSK-LSPA1-T-PL-01798
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R2
| ME | OL1-2C13-283000 | Material Requisition for Radiant Refractory |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-02-07 | 2019-04-15
[6 empty] | Revised Plan | 2019-03-21 | 2019-05-14
[6 empty] | Issue Actual | 2019-03-21 | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01108 | TPSK-LSPA1-T-PL-01657
[6 empty] | Return Date |  | 2019-06-19
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2C13-284000 | Material Requisition for Peep Doors - Ex Doc. Client Reference OL1-2M55-2008 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-12-10 | 2019-04-03
[6 empty] | Revised Plan |  | 2019-03-28
[6 empty] | Issue Actual |  | 2019-03-28 | 2019-03-28
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01181 | TPSK-LSPA1-T-PL-01181
Return Date
Owner Cmmt*
| ME | OL1-2C13-285000 | Material Requisition for MOVs - For next Rev. see Doc. Client Ref. OL1-2C13-285000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-12-18 | 2019-03-19
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02 | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01219 | TPSK-LSPA1-T-PL-01219
Return Date
Owner Cmmt*
| ME | OL1-2C13-286000 | Material Requisition for Attemperators |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-16 | 2019-04-03
[6 empty] | Revised Plan | 2019-01-31 | 2019-05-29
[6 empty] | Issue Actual | 2019-01-31 | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00771 | TPSK-LSPA1-T-PL-01756
[6 empty] | Return Date | 2019-06-07 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-300000 | Material Requisition for Radiant Coil Assemblies - For Next Rev See OL1-2C13-300000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 1 | 1
[6 empty] | Issue Plan | 2018-09-19 | 2019-02-14
[6 empty] | Revised Plan |  | 2019-03-26
[6 empty] | Issue Actual |  | 2019-03-26 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-301000 | Material Requisition for Furnace ID Fans - Ex Doc. Client Ref. OL1-2M55-2005 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-11-05 | 2019-01-17
[6 empty] | Revised Plan |  | 2019-03-21
[6 empty] | Issue Actual |  | 2019-03-21 | 2019-03-21
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01109 | TPSK-LSPA1-T-PL-01109
Return Date
Owner Cmmt*
| ME | OL1-2C13-302000 | Material Requisition for Cast Intermediate Tube Supports - For Next Revision see Doc. n. OL1-2C13-302000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 1 | 1
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28
[6 empty] | Revised Plan |  | 2019-03-26
[6 empty] | Issue Actual |  | 2019-03-26 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-303000 | Material Requisition for Convection Tubes - For next Rev. see Doc. Client Ref. OL1-2C13-303000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 1 | 1
[6 empty] | Issue Plan | 2018-10-22 | 2018-12-21
[6 empty] | Revised Plan |  | 2019-03-26
[6 empty] | Issue Actual |  | 2019-03-26 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-304000 | Material Requisition for Furnace Convection Fittings - For Next Rev See OL1-2C13-304000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 1 | 1
[6 empty] | Issue Plan | 2018-10-22 | 2018-12-21
[6 empty] | Revised Plan |  | 2019-03-26
[6 empty] | Issue Actual |  | 2019-03-26 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-305000 | Material Requisition for Furnace Steam Drums - For Next Rev See OL1-2C13-305000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 1 | 1
[6 empty] | Issue Plan | 2018-10-26 | 2018-12-17
[6 empty] | Revised Plan |  | 2019-03-26
[6 empty] | Issue Actual |  | 2019-03-26 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01139 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-306000 | Material Requisition for Furnace Burners - Ex Doc. Client Ref. OL1-2M55-2006 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-11-13 | 2019-01-23
[6 empty] | Revised Plan |  | 2019-02-07
[6 empty] | Issue Actual |  | 2019-02-07 | 2019-02-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00820 | TPSK-LSPA1-T-ME-00820
Return Date
Owner Cmmt*
| ME | OL1-2C13-311000 | Material Requisition for Cooling Tower - For Next Revision See Document OL1-2C13-311000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-31 | 2019-03-26
[6 empty] | Revised Plan |  | 2019-04-25
[6 empty] | Issue Actual |  | 2019-04-25 | 2019-04-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01460 | TPSK-LSPA1-T-PL-01460
[6 empty] | Return Date |  | 2019-05-24 | 2019-05-24
[6 empty] | Owner Cmmt* |  | R1 | R1
| PL | OL1-2C13-321001 | Material Requisition For Ladders And Platforms For Equipment Requisition For Inquiry |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01593
[6 empty] | Return Date | 2019-05-23
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C13-331000 | Material Requisition for Sluice Gates & Screens |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-26
[6 empty] | Issue Actual | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02483
Return Date
Owner Cmmt*
| ME | OL1-2C13-401000 | Material Requisition For Centrifugal Compressors Steam Turbine Driven - Ex Document Cliet Reference OL1-2M55-0008 |  |  | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. |  | 0 | 1 | 0 | 1
[6 empty] | Issue Plan | 2018-10-04 | 2019-04-03
[6 empty] | Revised Plan |  | 2019-03-22
[6 empty] | Issue Actual |  | 2019-03-22 | 2019-04-22 | 2019-03-22 | 2019-04-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01124 | TPSK-LSPA1-T-PL-01420 | TPSK-LSPA1-T-PL-01124 | TPSK-LSPA1-T-PL-01420
[6 empty] | Return Date |  |  | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* |  |  | R1 |  | R1
| ME | OL1-2C13-402000 | Material Requisition For Integrally Geared Decoking Air Compressors |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-10-18 | 2019-04-17
[6 empty] | Revised Plan |  | 2019-05-23
[6 empty] | Issue Actual |  | 2019-05-23 | 2019-05-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01720 | TPSK-LSPA1-T-PL-01720
[6 empty] | Return Date |  | 2019-06-17 | 2019-06-17
[6 empty] | Owner Cmmt* |  | R2 | R2
| ME | OL1-2C13-403000 | Material Requisition for Recycle Gas Compressor |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-02-25 | 2019-07-22
[6 empty] | Revised Plan | 2019-01-23 | 2019-07-10
[6 empty] | Issue Actual | 2019-01-23 | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00714 | TPSK-LSPA1-T-PL-02106
[6 empty] | Return Date | 2019-06-27 | 2019-08-01
[6 empty] | Owner Cmmt* | R2 | R1
| PL | OL1-2C13-404000 | Material Requisition For General Purpose Steam Turbines |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02131
[6 empty] | Return Date | 2019-07-25
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-421000 | Material Requisition For Residue Gas Expander/Recompressor - For Next Revision See Document OL1-2C13-421000 |  |  | Purpose** | IFQ | IFP | IFP | IFP | IFP | IFP | IFP
[6 empty] | Rev. |  | 0 | 1 | 2 | 0 | 1 | 2
[6 empty] | Issue Plan | 2018-10-05 | 2019-04-05
[6 empty] | Revised Plan |  | 2019-03-22
[6 empty] | Issue Actual |  | 2019-03-22 | 2019-04-24 | 2019-10-09 | 2019-03-22 | 2019-04-24 | 2019-10-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01118 | TPSK-LSPA1-T-PL-01443 | TPSK-LSPA1-T-PL-02754 | TPSK-LSPA1-T-PL-01118 | TPSK-LSPA1-T-PL-01443 | TPSK-LSPA1-T-PL-02754
[6 empty] | Return Date |  |  | 2019-05-20 |  |  | 2019-05-20
[6 empty] | Owner Cmmt* |  |  | R1 |  |  | R1
| EE | OL1-2C13-431000 | Material Requisition For Emergency Diesel Engine Generator |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-07-15 | 2019-11-21 | 2019-07-15
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-21 | 2019-08-28
[6 empty] | Issue Actual | 2019-08-28 |  | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02514 |  | TPSK-LSPA1-T-PL-02514
[6 empty] | Return Date | 2019-09-10 |  | 2019-09-10
[6 empty] | Owner Cmmt* | R1 |  | R1
| ME | OL1-2C13-440003 | Material Requisition for Cooling Water Pumps |  |  | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. |  | 1 | 0 | 1 | 0
[6 empty] | Issue Plan | 2019-01-31 | 2019-05-23
Revised Plan
[6 empty] | Issue Actual |  |  | 2019-07-10 |  | 2019-07-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PL-02113 |  | TPSK-LSPA1-T-PL-02113
[6 empty] | Return Date |  |  | 2019-07-30 |  | 2019-07-30
[6 empty] | Owner Cmmt* |  |  | R1 |  | R1
| ME | OL1-2C13-441000 | Material Requisition For API Centrifugal Pumps - LLI |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2019-01-31 | 2019-05-23
[6 empty] | Revised Plan |  | 2019-07-09
[6 empty] | Issue Actual |  | 2019-07-09 | 2019-07-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-02095 | TPSK-LSPA1-T-PL-02095
[6 empty] | Return Date |  | 2019-07-18 | 2019-07-18
[6 empty] | Owner Cmmt* |  | R2 | R2
| ME | OL1-2C13-442000 | Material Requisition For API Centrifugal Pumps |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 1 | 0
[6 empty] | Issue Plan | 2019-01-31 | 2019-05-23
[6 empty] | Revised Plan | 2019-02-19
[6 empty] | Issue Actual | 2019-02-19 |  | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00880 | TPSK-LSPA1-T-PL-02691 | TPSK-LSPA1-T-PL-02408
[6 empty] | Return Date |  | 2019-10-03
[6 empty] | Owner Cmmt* |  | R2
| PL | OL1-2C13-443000 | Material Requisition For Submersible Pumps |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01736
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C13-444000 | Material Requisition For High Speed Pumps |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02782
Return Date
Owner Cmmt*
| PL | OL1-2C13-446000 | Material Requisition For API 685 Sealless Pump |  | Class 2 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02034 | TPSK-LSPA1-T-PL-02476
[6 empty] | Return Date | 2019-07-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2
| PL | OL1-2C13-447000 | Material Requisition For API Centrifugal Pumps |  | Class 2 | Purpose** | IFP | IFP
[6 empty] | Rev. | 0 | 1
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02408 | TPSK-LSPA1-T-PL-02686
[6 empty] | Return Date |  | 2019-10-01
[6 empty] | Owner Cmmt* |  | R2
| PL | OL1-2C13-449000 | Material Requisition For API Centrifugal Pumps |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02408
Return Date
Owner Cmmt*
| ME | OL1-2C13-451000 | Material Requisition For Vent Gas Blower |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2018-12-21 | 2019-04-30 | 2018-12-21
[6 empty] | Revised Plan | 2019-03-08 | 2019-11-15 | 2019-03-08
[6 empty] | Issue Actual | 2019-03-08 |  | 2019-03-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01001 |  | TPSK-LSPA1-T-PL-01001
[6 empty] | Return Date | 2019-03-27 |  | 2019-03-27
[6 empty] | Owner Cmmt* | R2 |  | R2
| PL | OL1-2C13-700000 | Material Requisition For Electric Heater |  | Class 2 | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-04-18 | 2019-08-28
[6 empty] | Issue Actual | 2019-04-18 | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01409 | TPSK-LSPA1-T-PL-02512
[6 empty] | Return Date | 2019-05-30 | 2019-09-10
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-701000 | Material Requisition for Condensate Polisher Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-02-22 | 2019-06-10
[6 empty] | Revised Plan | 2019-02-27 | 2019-09-03
[6 empty] | Issue Actual | 2019-02-27 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00940 | TPSK-LSPA1-T-PL-02545
[6 empty] | Return Date | 2019-06-07 | 2019-09-10
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-702000 | Material Requisition For Complex Waste Water Treatment Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-25 | 2019-05-31
[6 empty] | Revised Plan | 2019-02-15 | 2019-08-09
[6 empty] | Issue Actual | 2019-02-15 | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00862 | TPSK-LSPA1-T-PL-02399
[6 empty] | Return Date | 2019-06-07 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R1
| ME | OL1-2C13-704000 | Material Requisition for Wet Air Oxidation Package - For Next Revision See Document OL1-2C13-704000 |  |  | Purpose** | IFQ | IFP | IFP | IFP | IFP
[6 empty] | Rev. |  | 0 | 1 | 0 | 1
[6 empty] | Issue Plan | 2018-11-30 | 2019-04-15
[6 empty] | Revised Plan |  | 2019-05-09
[6 empty] | Issue Actual |  | 2019-05-09 | 2019-06-20 | 2019-05-09 | 2019-06-20
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-PL-01943 | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-PL-01943
[6 empty] | Return Date |  | 2019-06-16 | 2019-07-08 | 2019-06-16 | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2 | R1 | R2 | R1
| ME | OL1-2C13-705000 | Material Requisition for Hydrogen Production Unit - For Next Revision See Document OL1-2C13-705000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-11-14 | 2019-02-15
[6 empty] | Revised Plan |  | 2019-05-07
[6 empty] | Issue Actual |  | 2019-05-07 | 2019-05-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01580 | TPSK-LSPA1-T-PL-01580
[6 empty] | Return Date |  | 2019-05-27 | 2019-05-27
[6 empty] | Owner Cmmt* |  | R2 | R2
| ME | OL1-2C13-706000 | Material Requisition for Side Stream Filter Package - For Next Revision See Document OL1-2C13-706000 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 0
[6 empty] | Issue Plan | 2018-11-07 | 2019-04-05
[6 empty] | Revised Plan |  | 2019-03-27
[6 empty] | Issue Actual |  | 2019-03-27 | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01165 | TPSK-LSPA1-T-PL-01165
[6 empty] | Return Date |  | 2019-06-07 | 2019-06-07
[6 empty] | Owner Cmmt* |  | R1 | R1
| ME | OL1-2C13-707000 | Material Requisition For Chemical Dosing System |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2019-07-02 | 2019-04-06
[6 empty] | Revised Plan | 2019-04-29 | 2019-10-25 | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29 |  | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01491 |  | TPSK-LSPA1-T-PL-01491
[6 empty] | Return Date | 2019-05-31 |  | 2019-05-31
[6 empty] | Owner Cmmt* | R1 |  | R1
| ME | OL1-2C13-708000 | MR for HP / Polyolefins Flare Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-02-18 | 2019-06-21
[6 empty] | Revised Plan | 2019-01-17 | 2019-06-25
[6 empty] | Issue Actual | 2019-01-17 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00665 | TPSK-LSPA1-T-PL-01951
[6 empty] | Return Date | 2019-06-11 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| ME | OL1-2C13-709000 | Material Requisition for Furnace Elevator |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-12-19 | 2019-02-19
[6 empty] | Revised Plan | 2019-01-22 | 2019-07-25
[6 empty] | Issue Actual | 2019-01-22 | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00697 | TPSK-LSPA1-T-PL-02260
[6 empty] | Return Date | 2019-02-14 | 2019-08-15
[6 empty] | Owner Cmmt* | R2 | R1
| ME | OL1-2C13-771000 | Material Requisition For Bridge Crane |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-15
[6 empty] | Revised Plan | 2019-02-25 | 2019-08-07
[6 empty] | Issue Actual | 2019-02-25 | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00914 | TPSK-LSPA1-T-PL-02361
[6 empty] | Return Date |  | 2019-08-21
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2C13-801000 | Material Requisition For Ejectors And Static Mixers |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-05 | 2019-07-24 | 2019-04-05
[6 empty] | Revised Plan | 2019-04-18 | 2019-10-25 | 2019-04-18
[6 empty] | Issue Actual | 2019-04-18 |  | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01408 |  | TPSK-LSPA1-T-PL-01408
[6 empty] | Return Date | 2019-05-24 |  | 2019-05-24
[6 empty] | Owner Cmmt* | R2 |  | R2
Category Code: C14 Request for Quotation (RFQ) Piping work (Engineering and Procurement)
| MP | OL1-2C14-100001 | Material Requisition For Gate Globe And Check Forged Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-10-15 | 2019-04-13
[6 empty] | Revised Plan | 2019-05-06 | 2020-10-15 | 2019-05-06
[6 empty] | Issue Actual | 2019-05-06 |  | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01567 |  | TPSK-LSPA1-T-PL-01567
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-110001 | Material Requisition For Gate Globe And Check Cast Valves Low Pressure |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01 | 2019-04-13
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01 | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07 |  | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01574 |  | TPSK-LSPA1-T-PL-01574
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| PL | OL1-2C14-115001 | Material Requisition For Gate Globe Check Cast Valves High Pressure |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01579
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C14-120001 | Material Requisition For Butterfly Valves Low Pressure Category A |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01592
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-125001 | Material Requisition For Butterfly Valves High Performance (Category B) |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01 | 2019-04-13
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01 | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07 |  | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01575 |  | TPSK-LSPA1-T-PL-01575
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-130001 | Material Requisition For Plug Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01 | 2019-04-13
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01 | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07 |  | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01576 |  | TPSK-LSPA1-T-PL-01576
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-140001 | Material Requisition For Ball Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01 | 2019-04-13
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01 | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07 |  | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01577 |  | TPSK-LSPA1-T-PL-01577
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-150001 | Material Requisition For Dual Plate Check Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01 | 2019-04-13
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01 | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07 |  | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01578 |  | TPSK-LSPA1-T-PL-01578
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-160001 | Material Requisition For Spring-Assisted Check Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01 | 2019-04-13
[6 empty] | Revised Plan | 2019-09-03 | 2020-07-01 | 2019-09-03
[6 empty] | Issue Actual | 2019-09-03 |  | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02553 |  | TPSK-LSPA1-T-PL-02553
[6 empty] | Return Date | 2019-09-05 |  | 2019-09-05
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-160001-ATT3 | DATS SHEET FOR SPRING ASSISTED CHECK VALVES |  |  | Purpose** | IFR | IMP
Rev.
[6 empty] | Issue Plan | 2019-04-30 | 2020-02-01
[6 empty] | Revised Plan |  | 2020-02-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-210001 | Material Requisition For Carbon Steel Seamless Pipe |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15 | 2019-04-06
[6 empty] | Revised Plan | 2019-05-02 | 2020-10-15 | 2019-05-02
[6 empty] | Issue Actual | 2019-05-02 |  | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01525 |  | TPSK-LSPA1-T-PL-01525
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-215001 | Material Requisition For Carbon Steel Welded Pipe |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-06-17 | 2019-04-06
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-17 | 2019-05-02
[6 empty] | Issue Actual | 2019-05-02 |  | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01527 |  | TPSK-LSPA1-T-PL-01527
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-220001 | Material Requisition For Alloy Steel Seamless Pipe |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-06-17 | 2019-04-06
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-17 | 2019-05-02
[6 empty] | Issue Actual | 2019-05-02 |  | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01528 |  | TPSK-LSPA1-T-PL-01528
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-225001 | Material Requisition For Alloy Steel Welded Pipe |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-06-17 | 2019-04-06
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-17 | 2019-05-02
[6 empty] | Issue Actual | 2019-05-02 |  | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01529 |  | TPSK-LSPA1-T-PL-01529
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-230001 | Material Requisition For Stainless Steel Seamless Pipe |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15 | 2019-04-06
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15 | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03 |  | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01553 |  | TPSK-LSPA1-T-PL-01553
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-235001 | Material Requisition For Stainless Steel Welded Pipe |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15 | 2019-04-06
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15 | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03 |  | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01555 |  | TPSK-LSPA1-T-PL-01555
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-245001 | MR PE & PVC PIPING |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-04-30 | 2020-07-12
[6 empty] | Revised Plan | 2019-11-15 | 2020-07-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-250001 | Material Requisition For Buttwelding Fittings |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15 | 2019-04-06
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15 | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03 |  | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01557 |  | TPSK-LSPA1-T-PL-01557
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-260001 | Material Requisition For Forged Fittings |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15 | 2019-04-06
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15 | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03 |  | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01559 |  | TPSK-LSPA1-T-PL-01559
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-270001 | Material Requisition For Flanges Blinds And Drip Rings |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15 | 2019-04-06
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15 | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03 |  | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01558 |  | TPSK-LSPA1-T-PL-01558
[6 empty] | Return Date | 2019-05-20 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-280001 | MR GASKETS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-04-20 | 2020-10-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-290001 | MR BOLTING |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-04-20 | 2020-10-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-300001 | MR STEAM TRAPS AND MANIFOLDS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-05-14 | 2020-01-27
[6 empty] | Revised Plan | 2020-02-28 | 2020-01-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2C14-301000 | MATERIAL REQUISITION FOR PIPING SPRING SUPPORTS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-11-27 | 2020-01-27
[6 empty] | Revised Plan | 2019-11-27 | 2020-01-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-310001 | MR HOSE CONNECTIONS AND FLEXIBLE HOSES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-01-03 | 2020-10-15
[6 empty] | Revised Plan | 2020-01-03 | 2020-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-320001 | Material Requisition for Filters |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-30 | 2020-01-15 | 2019-06-30
[6 empty] | Revised Plan | 2019-09-03 | 2020-01-15 | 2019-09-03
[6 empty] | Issue Actual | 2019-09-03 |  | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02552 |  | TPSK-LSPA1-T-PL-02552
[6 empty] | Return Date | 2019-09-05 |  | 2019-09-05
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-320001-ATT3 | DATA SHEET FOR STRAINERS |  |  | Purpose** | IFR | IMP
Rev.
[6 empty] | Issue Plan | 2019-06-10 | 2019-12-15
[6 empty] | Revised Plan |  | 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-330001 | MR SIGHT FLOW INDICATORS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-06-30 | 2020-01-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-330001-ATT1 | DATA SHEET FOR SIGHT FLOW INDICATORS |  |  | Purpose** | IFR | IMP
Rev.
[6 empty] | Issue Plan | 2019-06-10 | 2019-12-15
[6 empty] | Revised Plan | 2019-11-29 | 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-340001 | MR SAMPLING PANELS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-01-14 | 2020-08-30
[6 empty] | Revised Plan | 2020-01-14 | 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-350001 | MR INTERLOCKS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-05-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-05-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PL | OL1-2C14-360001 | Material Requisition For Carbon Steel Underground Piping |  | Class 2 | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-04 | 2019-08-14
[6 empty] | Issue Actual | 2019-03-04 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00969 | TPSK-LSPA1-T-PL-02412
[6 empty] | Return Date | 2019-06-06 | 2019-08-21
[6 empty] | Owner Cmmt* | R2 | R2
| PL | OL1-2C14-365001 | Material Requisition For Underground Welded Carbon Steel Pipes |  | Class 2 | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-05 | 2019-08-09
[6 empty] | Issue Actual | 2019-03-05 | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00975 | TPSK-LSPA1-T-PL-02388
[6 empty] | Return Date | 2019-06-06 | 2019-08-21
[6 empty] | Owner Cmmt* | R2 | R1
| MP | OL1-2C14-502000 | Material Requisition for SP Item Angle Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-04-24 | 2019-02-20
[6 empty] | Revised Plan | 2019-06-10 | 2019-11-11 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10 |  | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01800 |  | TPSK-LSPA1-T-PL-01800
[6 empty] | Return Date | 2019-06-21 |  | 2019-06-21
[6 empty] | Owner Cmmt* | R2 |  | R2
| MP | OL1-2C14-503000 | Material Requisition for SP Item - Sample Cooler |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-04-24 | 2019-02-20
[6 empty] | Revised Plan | 2019-07-03 | 2019-11-11 | 2019-07-03
[6 empty] | Issue Actual | 2019-07-03 |  | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02057 |  | TPSK-LSPA1-T-PL-02057
Return Date
Owner Cmmt*
| MP | OL1-2C14-504000 | Material Requisition for SP Item T-Type Filter |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-04-24 | 2019-02-20
[6 empty] | Revised Plan | 2019-06-26 |  | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26 |  | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01996 |  | TPSK-LSPA1-T-PL-01996
Return Date
Owner Cmmt*
| MP | OL1-2C14-505000 | Material Requisition for SP Item Isokinetic Sampling Nozzle |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-04-24 | 2019-02-20
[6 empty] | Revised Plan | 2019-06-10 | 2019-11-11 | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10 |  | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01833 |  | TPSK-LSPA1-T-PL-01833
Return Date
Owner Cmmt*
| PL | OL1-2C14-506000 | Material Requisition for SP Item - Vent Silencer |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-03
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02060
Return Date
Owner Cmmt*
Category Code: C15 Request for Quotation (RFQ) for Fire Fighting work (Engineering and Procurement)
| SE | OL1-2C15-821001 | Material Requisition for Fire Fighting and Safety Equipment Package |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-07-05 | 2019-10-09 | 2019-07-05
[6 empty] | Revised Plan | 2019-07-08 | 2019-12-13 | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08 |  | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02083 |  | TPSK-LSPA1-T-PL-02083
[6 empty] | Return Date | 2019-08-06 |  | 2019-08-06
[6 empty] | Owner Cmmt* | R1 |  | R1
| SE | OL1-2C15-821001-ATT2 | PARTICULAR TECHNICAL SPECIFICATION FOR FIRE FIGHTING AND SAFETY EQUIPMENT |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-07-05 | 2019-10-09
[6 empty] | Revised Plan |  | 2019-12-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2C15-822001 | Material Requisition for Deluge and Sprinkler System Package |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-07-05 | 2019-10-09 | 2019-07-05
[6 empty] | Revised Plan | 2019-07-08 | 2019-12-13 | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08 |  | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02083 |  | TPSK-LSPA1-T-PL-02083
[6 empty] | Return Date | 2019-08-08 |  | 2019-08-08
[6 empty] | Owner Cmmt* | R1 |  | R1
| SE | OL1-2C15-822001-ATT2 | PARTICULAR TECHNICAL SPECIFICATIONFOR DELUGE AND SPRINKLER SYSTEM - ADDED 16-MAY-19 |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-07-05 | 2019-10-09
[6 empty] | Revised Plan |  | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2C15-823001 | Material Requisition for Clean Agent Fire Extinguishing System |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-07-05 | 2019-10-09 | 2019-07-05
[6 empty] | Revised Plan | 2019-07-08 | 2019-12-13 | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08 |  | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02083 |  | TPSK-LSPA1-T-PL-02083
[6 empty] | Return Date | 2019-08-08 |  | 2019-08-08
[6 empty] | Owner Cmmt* | R1 |  | R1
| SE | OL1-2C15-823001-ATT2 | PARTICULAR TECHNICAL SPECIFICATION FOR CLEAN AGENT FIRE EXTINGUISHING SYSTEM |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-07-05 | 2019-10-09
[6 empty] | Revised Plan |  | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: C16 Request for Quotation (RFQ) for Electrical and HVAC work (Engineering and Procurement)
| EE | OL1-2C16-110000 | MR FOR MV SWITCHGEARS (> 1 KV, = 52 KV) - Start & IFQ actual dates are 12-Sep-18 & 7-Dec-18 |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-06-14 | 2019-09-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-150000 | Material Requisition For Distribution Transformer |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-09-05 | 2019-06-03
[6 empty] | Revised Plan | 2019-08-05 | 2019-12-10 | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05 |  | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02326 |  | TPSK-LSPA1-T-PL-02326
[6 empty] | Return Date | 2019-08-26 |  | 2019-08-26
[6 empty] | Owner Cmmt* | R2 |  | R2
| EE | OL1-2C16-160000 | Material Requisition For Power Capacitors |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-14 | 2019-11-18 | 2019-06-14
[6 empty] | Revised Plan | 2019-08-06 | 2019-11-18 | 2019-08-06
[6 empty] | Issue Actual | 2019-08-06 |  | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PL-02342 |  | TPSK-LPSA1-T-PL-02342
[6 empty] | Return Date | 2019-08-26 |  | 2019-08-26
[6 empty] | Owner Cmmt* | R2 |  | R2
| EE | OL1-2C16-200000 | MR FOR AC AND DC UPS SYSTEMS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-10-24 | 2020-01-28
[6 empty] | Revised Plan | 2019-10-24 | 2020-01-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-340000 | Material Requisition for HVAC System |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-08-28 | 2019-12-11 | 2019-08-28
[6 empty] | Revised Plan | 2019-07-08 | 2019-12-11 | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08 |  | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02092 |  | TPSK-LSPA1-T-PL-02092
[6 empty] | Return Date | 2019-07-23 |  | 2019-07-23
[6 empty] | Owner Cmmt* | R2 |  | R2
| EE | OL1-2C16-530000 | MR FOR POWER AND LIGHTING DISTRIBUTION PANELS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-04-30
[6 empty] | Revised Plan | 2020-01-20 | 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-800000 | Material Requisition For Cathodic Protection System |  |  | Purpose** | IFQ | IF1T | IF2T
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-18 | 2020-06-28 | 2020-07-20
[6 empty] | Revised Plan | 2019-05-24 | 2020-06-28 | 2020-07-20
[6 empty] | Issue Actual | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01735
[6 empty] | Return Date | 2019-06-20
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2C16-810000 | MR FOR ELECTRICAL HEAT TRACING SYSTEM |  |  | Purpose** | IFQ | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-03-18 | 2020-06-28 | 2020-08-20
[6 empty] | Revised Plan | 2020-03-18 | 2020-06-28 | 2020-08-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-851000 | Material Requisition For Safety Supervisory System |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-04 | 2020-01-15
[6 empty] | Revised Plan | 2019-03-05 | 2019-08-05
[6 empty] | Issue Actual | 2019-03-05 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00984 | TPSK-LSPA1-T-PL-02309
[6 empty] | Return Date | 2019-04-05 | 2019-08-14
[6 empty] | Owner Cmmt* | R2 | R1
| EE | OL1-2C16-851000-ATT2 | SAFETY SUPERVISORY SYSTEM EXTENT OF SUPPLY |  |  | Purpose** | IFR | IFP
Rev.
[6 empty] | Issue Plan | 2019-03-04 | 2019-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-881000 | Material Requisition For Intercom/Paging/Audible Alarm System |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-04 | 2020-01-15
[6 empty] | Revised Plan | 2019-03-05 | 2019-08-01
[6 empty] | Issue Actual | 2019-03-05 | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00984 | TPSK-LSPA1-T-PL-02306
[6 empty] | Return Date | 2019-04-10 | 2019-08-14
[6 empty] | Owner Cmmt* | R2 | R1
| EE | OL1-2C16-881000-ATT2 | INTERCOM/PAGING / AUDIBLE ALARM SYSTEM EXTENT OF SUPPLY |  |  | Purpose** | IFR | IFP
Rev.
[6 empty] | Issue Plan | 2019-03-04 | 2019-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-900000 | Material Requisition For Electrical Cables |  |  | Purpose** | IFQ | IF1T | IF2T
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-16 | 2019-11-10 | 2020-01-20
[6 empty] | Revised Plan | 2019-08-05 | 2019-11-10 | 2020-01-20
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02328
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2C16-920000 | MR FOR POWER MATERIALS |  |  | Purpose** | IFQ | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2019-09-26 | 2020-01-12 | 2020-02-27
[6 empty] | Revised Plan | 2019-10-23 | 2020-01-12 | 2020-02-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-930000 | MR FOR GROUNDING AND LIGHTNING MATERIAL |  |  | Purpose** | IFQ | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2019-09-04 | 2019-12-06 | 2020-02-04
[6 empty] | Revised Plan | 2019-10-16 | 2019-12-06 | 2020-02-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-930100 | MR FOR LIGHTING MATERIALS |  |  | Purpose** | IFQ | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-04-29 | 2020-07-05
[6 empty] | Revised Plan | 2020-01-20 | 2020-04-29 | 2020-07-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-940000 | MR FOR CABLE TRAYS |  |  | Purpose** | IFQ | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2019-09-26 | 2020-01-12 | 2020-04-25
[6 empty] | Revised Plan | 2019-10-30 | 2020-01-12 | 2020-04-25
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: C17 Request for Quotation (RFQ) for Instrumentation work (Engineering and Procurement)
| IE | OL1-2C17-010101 | Material Requisition For Orifice And Restriction Orifice |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20 | 2019-06-04
[6 empty] | Revised Plan |  | 2019-11-29
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02847 |  | TPSK-LSPA1-T-PL-02847
Return Date
Owner Cmmt*
| IE | OL1-2C17-010201 | MR for Pitot Tube |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20 | 2019-06-04
[6 empty] | Revised Plan | 2019-07-02 | 2019-11-29 | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02 |  | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02035 |  | TPSK-LSPA1-T-PL-02035
[6 empty] | Return Date | 2019-07-17 |  | 2019-07-17
[6 empty] | Owner Cmmt* | R1 |  | R1
| IE | OL1-2C17-010301 | MR For Electromagnetic Flow Meter |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20 | 2019-06-04
[6 empty] | Revised Plan | 2019-07-05 | 2019-11-29 | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05 |  | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02078 |  | TPSK-LSPA1-T-PL-02078
[6 empty] | Return Date | 2019-07-18 |  | 2019-07-18
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-010401 | Material Requisition for Flow Element Rotameter |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20 | 2019-06-04
[6 empty] | Revised Plan |  | 2019-11-29
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-LP-02847 |  | TPSK-LSPA1-T-LP-02847
Return Date
Owner Cmmt*
| IE | OL1-2C17-010601 | MR For Mass Flow Meters Coriolis Effect |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20 | 2019-06-04
[6 empty] | Revised Plan | 2019-07-03 | 2019-11-29 | 2019-07-03
[6 empty] | Issue Actual | 2019-07-03 |  | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02049 |  | TPSK-LSPA1-T-PL-02049
[6 empty] | Return Date | 2019-07-17 |  | 2019-07-17
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-010701 | MR For Venturi |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20 | 2019-06-04
[6 empty] | Revised Plan | 2019-07-05 | 2019-11-29 | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05 |  | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02077 |  | TPSK-LSPA1-T-PL-02077
[6 empty] | Return Date | 2019-07-18 |  | 2019-07-18
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-010801 | MR For Ultrasonic Flow Meter |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20 | 2019-06-04
[6 empty] | Revised Plan | 2019-07-09 | 2019-11-29 | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09 |  | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02093 |  | TPSK-LSPA1-T-PL-02093
[6 empty] | Return Date | 2019-07-19 |  | 2019-07-19
[6 empty] | Owner Cmmt* | R2 |  | R2
| PL | OL1-2C17-012052 | Material Requisition for Orifice Plate |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-24
[6 empty] | Issue Actual | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02244
[6 empty] | Return Date | 2019-08-15
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-012062 | Material Requisition for Flow Element Venturi |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-09 | 2019-07-30 | 2019-04-09
[6 empty] | Revised Plan | 2019-06-27 | 2019-10-31 | 2019-06-27
[6 empty] | Issue Actual | 2019-06-27 |  | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02011 |  | TPSK-LSPA1-T-PL-02011
Return Date
Owner Cmmt*
| IE | OL1-2C17-012253 | Material Requisition for Restriction Orifice |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2019-04-09 | 2019-07-30
[6 empty] | Revised Plan | 2019-06-14 | 2019-09-17
[6 empty] | Issue Actual | 2019-06-14 | 2019-09-17 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01881 | TPSK-LSPA1-T-PL-02644 | TPSK-LSPA1-T-PL-02803
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-014001 | MR For Vortex Meter |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20 | 2019-06-04
[6 empty] | Revised Plan | 2019-07-08 | 2019-11-29 | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08 |  | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02082 |  | TPSK-LSPA1-T-PL-02082
[6 empty] | Return Date | 2019-07-18 |  | 2019-07-18
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-022005 | Material Requisition for Level Gauges |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-26 | 2019-06-26
[6 empty] | Revised Plan | 2019-04-18 | 2019-08-15
[6 empty] | Issue Actual | 2019-04-18 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01393 | TPSK-LSPA1-T-PL-02430
[6 empty] | Return Date | 2019-05-28 | 2019-09-04
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2C17-022060 | Material Requisition for Magnetostrictive Level Transmitter & Magnetic Level Gauge |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-26 | 2019-06-26
[6 empty] | Revised Plan | 2019-06-24 | 2019-08-21
[6 empty] | Issue Actual | 2019-06-24 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01960 | TPSK-LSPA1-T-PL-02458
[6 empty] | Return Date | 2019-07-08 | 2019-09-04
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2C17-022064 | Material Requisition for Guided Wave Radar Level Transmitter & Magnetic Level Gauge |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-03-26 | 2019-06-26 | 2019-03-26
[6 empty] | Revised Plan | 2019-06-21 | 2019-11-13 | 2019-06-21
[6 empty] | Issue Actual | 2019-06-21 |  | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01949 |  | TPSK-LSPA1-T-PL-01949
[6 empty] | Return Date | 2019-07-08 |  | 2019-07-08
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-032061 | Material Requisition for Temperature Elements for Furnace Profile |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-08-27 | 2019-12-03 | 2019-08-27
[6 empty] | Revised Plan | 2019-06-25 | 2019-12-03 | 2019-06-25
[6 empty] | Issue Actual | 2019-06-25 |  | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01977 |  | TPSK-LSPA1-T-PL-01977
[6 empty] | Return Date | 2019-07-08 |  | 2019-07-08
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-032063 | Material Requisition for Temperature Elements for Coil Outlet |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-08-27 | 2019-12-03 | 2019-08-27
[6 empty] | Revised Plan | 2019-05-24 | 2019-12-03 | 2019-05-24
[6 empty] | Issue Actual | 2019-05-24 |  | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01732 |  | TPSK-LSPA1-T-PL-01732
[6 empty] | Return Date | 2019-06-17 |  | 2019-06-17
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-032257 | Material Requisition for Temperature Elements for Thermocouples & RTDs with Wells |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-08-27 | 2019-12-03 | 2019-08-27
[6 empty] | Revised Plan | 2019-09-12 | 2019-12-03 | 2019-09-12
[6 empty] | Issue Actual | 2019-09-12 |  | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02630 |  | TPSK-LSPA1-T-PL-02630
[6 empty] | Return Date | 2019-10-08 |  | 2019-10-08
[6 empty] | Owner Cmmt* | R2 |  | R2
| PL | OL1-2C17-032258 | Material Requisition for Temperature Gauge and Thermowell |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02732
Return Date
Owner Cmmt*
| IE | OL1-2C17-032259 | Material Requisition for Temperature Transmitters |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-08-27 | 2019-12-03 | 2019-08-27
[6 empty] | Revised Plan | 2019-08-28 | 2019-12-03 | 2019-08-28
[6 empty] | Issue Actual | 2019-08-28 |  | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02507 |  | TPSK-LSPA1-T-PL-02507
[6 empty] | Return Date | 2019-09-11 |  | 2019-09-11
[6 empty] | Owner Cmmt* | R2 |  | R2
| PL | OL1-2C17-042254 | Material Requisition for Pressure Gauge |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02572
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2C17-042255 | Material Requisition for Draft Gauge |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-07-23 | 2019-11-05 | 2019-07-23
[6 empty] | Revised Plan | 2019-09-12 | 2019-11-05 | 2019-09-12
[6 empty] | Issue Actual | 2019-09-12 |  | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02627 |  | TPSK-LSPA1-T-PL-02627
[6 empty] | Return Date | 2019-10-08 |  | 2019-10-08
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-042256 | Material Requisition for Material Requisition for Pressure Indicating Transmitters & Flow Indicating D P Transmitters |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-07-23 | 2019-11-05 | 2019-07-23
[6 empty] | Revised Plan | 2019-08-08 | 2019-11-05 | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08 |  | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02375 |  | TPSK-LSPA1-T-PL-02375
Return Date
Owner Cmmt*
| IE | OL1-2C17-050101 | Material Requisition For Control Valves |  |  | Purpose** | IFQ | IFQ | IFP | IFQ | IFQ
[6 empty] | Rev. | A | B |  | A | B
[6 empty] | Issue Plan | 2019-05-28 |  | 2019-11-13 | 2019-05-28
[6 empty] | Revised Plan | 2019-06-13 |  | 2019-11-13 | 2019-06-13
[6 empty] | Issue Actual | 2019-06-13 | 2019-06-28 |  | 2019-06-13 | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01891 | TPSK-LSPA1-T-PL-02017 |  | TPSK-LSPA1-T-PL-01891 | TPSK-LSPA1-T-PL-02017
[6 empty] | Return Date | 2019-09-11 | 2019-07-10 |  | 2019-09-11 | 2019-07-10
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| IE | OL1-2C17-050401 | Material Requisition for Special Control Valves |  |  | Purpose** | IFQ | IFQ | IFP | IFQ | IFQ
[6 empty] | Rev. | A | B |  | A | B
[6 empty] | Issue Plan | 2019-05-28 |  | 2019-11-13 | 2019-05-28
[6 empty] | Revised Plan | 2019-06-13 |  | 2019-11-13 | 2019-06-13
[6 empty] | Issue Actual | 2019-06-13 | 2019-07-01 |  | 2019-06-13 | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01891 | TPSK-LSPA1-T-PL-02022 |  | TPSK-LSPA1-T-PL-01891 | TPSK-LSPA1-T-PL-02022
[6 empty] | Return Date | 2019-06-28 | 2019-07-17 |  | 2019-06-28 | 2019-07-17
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| IE | OL1-2C17-050501 | Material Requisition for Severe Service Control Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13 | 2019-05-28
[6 empty] | Revised Plan | 2019-09-19 | 2019-11-13 | 2019-09-19
[6 empty] | Issue Actual | 2019-09-19 |  | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02664 |  | TPSK-LSPA1-T-PL-02664
[6 empty] | Return Date | 2019-09-27 |  | 2019-09-27
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-052001 | Material Requistion for Control Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-25 | 2019-07-17 | 2019-04-25
[6 empty] | Revised Plan | 2019-04-26 | 2019-10-16 | 2019-04-26
[6 empty] | Issue Actual | 2019-04-26 |  | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01482 |  | TPSK-LSPA1-T-PL-01482
[6 empty] | Return Date | 2019-05-28 |  | 2019-05-28
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-060201 | MR For Special On Off Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13 | 2019-05-28
[6 empty] | Revised Plan | 2019-07-25 | 2019-11-13 | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25 |  | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02255 |  | TPSK-LSPA1-T-PL-02255
[6 empty] | Return Date | 2019-08-07 |  | 2019-08-07
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-060301 | MR For Electric Operated Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13 | 2019-05-28
[6 empty] | Revised Plan | 2019-07-01 | 2019-11-13 | 2019-07-01
[6 empty] | Issue Actual | 2019-07-01 |  | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02026 |  | TPSK-LSPA1-T-PL-02026
[6 empty] | Return Date | 2019-07-17 |  | 2019-07-17
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-060401 | Material Requisition For Pneumatic Actuators For On Off Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-10-29 | 2019-05-28
[6 empty] | Revised Plan | 2019-07-25 | 2019-10-29 | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25 |  | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02257 |  | TPSK-LSPA1-T-PL-02257
[6 empty] | Return Date | 2019-08-07 |  | 2019-08-07
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-060501 | MR For Electric Pneumatic On Off Valves |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13 | 2019-05-28
[6 empty] | Revised Plan | 2019-07-24 | 2019-11-13 | 2019-07-24
[6 empty] | Issue Actual | 2019-07-24 |  | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02245 |  | TPSK-LSPA1-T-PL-02245
[6 empty] | Return Date | 2019-08-07 |  | 2019-08-07
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-070201 | Material Requisition for Safety Relief Valves & Rupture Disks |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-05-31 | 2019-10-29 | 2019-05-31
[6 empty] | Revised Plan | 2019-08-09 | 2019-10-29 | 2019-08-09
[6 empty] | Issue Actual | 2019-08-09 |  | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02395 |  | TPSK-LSPA1-T-PL-02395
Return Date
Owner Cmmt*
| IE | OL1-2C17-072002 | Material Requisition for Pressure Relief Valves |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2019-03-28 | 2019-06-14
[6 empty] | Revised Plan | 2019-04-23 | 2019-08-06
[6 empty] | Issue Actual | 2019-04-23 | 2019-08-06 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01427 | TPSK-LSPA1-T-PL-02351 | TPSK-LSPA1-T-PL-02683
[6 empty] | Return Date | 2019-05-28
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-101001 | Material Requisition for Integrated Control And Safety Systems - ICSS |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-06 | 2020-06-15 | 2019-06-06
[6 empty] | Revised Plan | 2019-06-13 | 2020-06-15 | 2019-06-13
[6 empty] | Issue Actual | 2019-06-13 |  | 2019-06-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01892 |  | TPSK-LSPA1-T-PL-01892
[6 empty] | Return Date | 2019-06-28 |  | 2019-06-28
[6 empty] | Owner Cmmt* | A2 |  | A2
| IE | OL1-2C17-101001-ATT2 | ICSS EXTENT OF SUPPLY |  |  | Purpose** | IFR | IFP
Rev.
[6 empty] | Issue Plan | 2019-06-06 | 2019-09-18
[6 empty] | Revised Plan |  | 2019-10-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-212051 | Material Requisition for O2 & Combustible Analyzer |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-05-23 | 2019-08-26 | 2019-05-23
[6 empty] | Revised Plan | 2019-06-25 | 2019-10-28 | 2019-06-25
[6 empty] | Issue Actual | 2019-06-25 |  | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01979 |  | TPSK-LSPA1-T-PL-01979
[6 empty] | Return Date | 2019-07-08 |  | 2019-07-08
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-230101 | MR For Water Analyzers |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-09-30 | 2020-02-15 | 2019-09-30
[6 empty] | Revised Plan | 2019-10-10 | 2020-02-15 | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10 |  | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02764 |  | TPSK-LSPA1-T-PL-02764
Return Date
Owner Cmmt*
| IE | OL1-2C17-232015 | Material Requisition for pH and Conductivity Analyzer |  |  | Purpose** | IFQ | IFQ | IFP | IFQ | IFQ
[6 empty] | Rev. | A | B |  | A | B
[6 empty] | Issue Plan | 2019-08-27 |  | 2019-12-03 | 2019-08-27
[6 empty] | Revised Plan | 2019-05-27 |  | 2019-12-03 | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27 | 2019-06-21 |  | 2019-05-27 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01744 | TPSK-LSPA1-T-PL-01950 |  | TPSK-LSPA1-T-PL-01744 | TPSK-LSPA1-T-PL-01950
[6 empty] | Return Date | 2019-06-17 | 2019-07-08 |  | 2019-06-17 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2 | R2
| IE | OL1-2C17-2400000 | MR For CEMS |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-06 | 2019-10-30 | 2019-06-06
[6 empty] | Revised Plan | 2019-09-18 | 2019-10-30 | 2019-09-18
[6 empty] | Issue Actual | 2019-09-18 |  | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02654 |  | TPSK-LSPA1-T-PL-02654
[6 empty] | Return Date | 2019-10-04 |  | 2019-10-04
[6 empty] | Owner Cmmt* | A2 |  | A2
| IE | OL1-2C17-260101 | MR for Specific Components & Property Analyzers |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-06 | 2019-10-30 | 2019-06-06
[6 empty] | Revised Plan | 2019-09-18 | 2019-10-30 | 2019-09-18
[6 empty] | Issue Actual | 2019-09-18 |  | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02657 |  | TPSK-LSPA1-T-PL-02657
[6 empty] | Return Date | 2019-10-04 |  | 2019-10-04
[6 empty] | Owner Cmmt* | A2 |  | A2
| IE | OL1-2C17-290000 | Material Requisition for Analyzer Houses Package |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-04-30 | 2019-10-30 | 2019-04-30
[6 empty] | Revised Plan | 2019-07-31 | 2019-10-30 | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31 |  | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02285 |  | TPSK-LSPA1-T-PL-02285
[6 empty] | Return Date | 2019-08-20 |  | 2019-08-20
[6 empty] | Owner Cmmt* | A2 |  | A2
| IE | OL1-2C17-300001 | MR CROSSCHECK CUSTODY METERING SYSTEM (036909C-100M-MR-1584-0003) |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-04-26 | 2019-11-30
[6 empty] | Revised Plan | 2019-10-25 | 2019-11-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-330101 | Material Requisition for Machine Monitoring System - MMS |  |  | Purpose** | IFQ | IFP | IFQ
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-06-21 | 2020-06-30 | 2019-06-21
[6 empty] | Revised Plan | 2019-07-15 | 2020-06-30 | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15 |  | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02149 |  | TPSK-LSPA1-T-PL-02149
[6 empty] | Return Date | 2019-07-30 |  | 2019-07-30
[6 empty] | Owner Cmmt* | A4 |  | A4
| IE | OL1-2C17-330101-ATT2 | MACHINE MONITORING SYSTEM EXTENT OF SUPPLY |  |  | Purpose** | IFR | IFP
Rev.
[6 empty] | Issue Plan | 2019-06-21 | 2019-10-03
[6 empty] | Revised Plan |  | 2019-10-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-330101-ATT5 | JSS FOR MACHINE MONITORING SYST. |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-04-17 | 2019-05-17
[6 empty] | Revised Plan |  | 2019-10-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: C18 Request for Quotation (RFQ) for Chemicals (Engineering and Procurement)
| PL | OL1-2C18-263000 | Material Requisition For Molecular And HG Sieves |  | Class 2 | Purpose** | IMP | IFQ
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-18 | 2019-07-22
[6 empty] | Issue Actual | 2019-03-18 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01076 | TPSK-LSPA1-T-PL-02196
[6 empty] | Return Date | 2019-04-01 | 2019-08-21
[6 empty] | Owner Cmmt* | R1 | R2
| PL | OL1-2C18-264000 | Material Requisition For Adsorbents |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-11
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01295
Return Date
Owner Cmmt*
| PL | OL1-2C18-265000 | Material Requisition For Molecular Sieves |  | Class 2 | Purpose** | IMP | CAN
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-18 | 2019-07-19
[6 empty] | Issue Actual | 2019-03-18 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01077 | TPSK-LSPA1-T-PL-02186
[6 empty] | Return Date | 2019-04-01
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C18-266000 | Material Requisition For Adsorbents |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-11
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01299
Return Date
Owner Cmmt*
| PL | OL1-2C18-267000 | Material Requisition For Hg Sieves |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-11
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01296
Return Date
Owner Cmmt*
| PL | OL1-2C18-268000 | Material Requisition For Support Balls |  | Class 2 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-11
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01297
Return Date
Owner Cmmt*
Category Code: C20 Technical Bid Evaluation for Civil work (Engineering and Procurement)
Category Code: C21 Technical Bid Evaluation for Building work (Engineering and Procurement)
Category Code: C22 Technical Bid Evaluation for Steel Structure work (Engineering and Procurement)
Category Code: C23 Technical Bid Evaluation for Mechanical work (Engineering and Procurement)
| PL | OL1-2C23-0008 | Technical Bid Evaluation For Centrifugal Compressor Steam Turbine Driven |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 1
Issue Plan
[6 empty] | Revised Plan | 2019-03-01
[6 empty] | Issue Actual | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00947
Return Date
Owner Cmmt*
| PL | OL1-2C23-0012 | Technical Bid Evaluation For Residue Gas Expander - Recompressor |  | Class 2 | Purpose** | IFI | IFI
[6 empty] | Rev. | 1 | 2
Issue Plan
[6 empty] | Revised Plan | 2019-01-29
[6 empty] | Issue Actual | 2019-01-29 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00747 | TPSL-LSPA1-T-PL-01057
Return Date
Owner Cmmt*
| PL | OL1-2C23-0014 | Technical Bid Evaluation For Integrally Geared Decoking Air Compressors |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 1
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01595
[6 empty] | Return Date | 2019-05-26
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C23-2009 | Technical Bid Tabulation For Elevator |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-19
[6 empty] | Issue Actual | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02190
[6 empty] | Return Date | 2019-10-09
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C23-2011 | Technical Bid Tabulation For Attemperators |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-24
[6 empty] | Issue Actual | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01734
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C23-2013 | Technical Bid Tabulation for Radiant Refractory |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01608
[6 empty] | Return Date | 2019-07-15
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C23-2014 | Technical Bid Tabulation for Radiant Steel Panel |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01649
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C23-2016 | Technical Bid Tabulation for Utility Steel |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-25
[6 empty] | Issue Actual | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02698
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C23-2202 | Technical Bid Tabulation For Pressure Relief Valves |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-24
[6 empty] | Issue Actual | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02243
[6 empty] | Return Date | 2019-08-15
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C23-2203 | Technical Bid Tabulation for Restriction Orifice |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-01
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02305
[6 empty] | Return Date | 2019-08-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C23-2209 | Technical Bid Tabulation for pH & Conductivity Analyzers |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-17
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02652
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C23-281000 | Technical Bid Tabulation for Convection Tubes Finnings |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-14
[6 empty] | Issue Actual | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01048
Return Date
Owner Cmmt*
| PL | OL1-2C23-282000 | Technical Bid Tabulation for Convection Fabrication |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01719
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C23-28500 | Technical Bid Tabulation for MOVs |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-15
[6 empty] | Issue Actual | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01053
Return Date
Owner Cmmt*
| PL | OL1-2C23-301000 | Technical Bid Tabulation for Furnace ID Fans |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-05
[6 empty] | Issue Actual | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00979
Return Date
Owner Cmmt*
| PL | OL1-2C23-403000 | Technical Bid Evaluation Report for Recycle Gas Compressor Package |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-12
[6 empty] | Issue Actual | 2019-06-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01874
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C23-440003 | Technical Bid Evaluation Report for Cooling Water Pumps |  | Class 2 | Purpose** | IFA
[6 empty] | Rev. | C
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01855
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R1
Category Code: C24 Technical Bid Evaluation for Piping work (Engineering and Procurement)
| PL | OL1-2C24-504000 | Technical Bid Tabulation for SP Item T-Type Filter |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-25
[6 empty] | Issue Actual | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02703
Return Date
Owner Cmmt*
Category Code: C25 Technical Bid Evaluation for Fire Fighting work (Engineering and Procurement)
Category Code: C26 Technical Bid Evaluation for Electrical and HVAC work (Engineering and Procurement)
Category Code: C27 Technical Bid Evaluation for Instrumentation work (Engineering and Procurement)
| PL | OL1-2C27-2201 | Technical Bid Tabulation For Control Valves |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-11
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02100
Return Date
Owner Cmmt*
| PL | OL1-2C27-2206 | Technical Bid Tabulation for Steam Drum Level Gauges |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02373
Return Date
Owner Cmmt*
| PL | OL1-2C27-2207 | Technical Bid Tabulation for Guided Wave Radar & Magnetic Gauges |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02852
Return Date
Owner Cmmt*
| PL | OL1-2C27-2218 | Technical Bid Tabulation for Magnetostrictive Transmitter Magnetic Gauges |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02376
Return Date
Owner Cmmt*
Category Code: C28 Technical Bid Evaluation for Chemicals (Engineering and Procurement)
Category Code: C30 Scope of Supply (SR) for Mechanical Work
Category Code: C31 Scope of Supply (SR) for Piping Work
Category Code: C32 Scope of Supply (SR) for Electrical work
Category Code: C33 Scope of Supply (SR) for Instrumentation work
Category Code: C34 Scope of Supply (SR) for Civil,Structure and Architecture.
Category Code: C35 Extend of Supply (SP) Mechanical Work
Category Code: C36 Extend of Supply (SP) for Piping Work
Category Code: C37 Extend of Supply (SP) for Electrical work
Category Code: C38 Extend of Supply (SP) for Instrumentation work
Category Code: C39 Extend of Supply (SP) for Civil,Structure and Architecture
Category Code: C40 Deviation List (DL) for Mechanical Work
| ME | OL1-2C40-140000 | Deviation List for Quench Exchangers |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01496
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C40-244000 | Deviation List For Trays For Columns (C4 Unit) |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-08-15
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02432
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C40-281000 | Deviation List for Furnace Convection Finnings |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-15
[6 empty] | Issue Actual | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01056
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C40-282000 | Deviation List for Convection Fabrication |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | B | C
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23 | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01718 | TPSK-LSPA1-T-PL-01772
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C40-284000 | Deviation List for Peep Doors |  | Class 2 | Purpose** | IFR | IFP
[6 empty] | Rev. | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-06 | 2019-04-18
[6 empty] | Issue Actual | 2019-02-06 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00812 | TPSK-LSPA1-T-ME-01400
[6 empty] | Return Date | 2019-02-21 | 2019-05-28
[6 empty] | Owner Cmmt* | R2 | R1
| PL | OL1-2C40-285000 | Deviation List for MOVs |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-15
[6 empty] | Issue Actual | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01050
Return Date
Owner Cmmt*
| PL | OL1-2C40-286000 | Deviation List for Attemperators |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-24
[6 empty] | Issue Actual | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01733
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C40-300000 | Deviation List for Radiant Coil |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01473
[6 empty] | Return Date | 2019-05-28
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C40-301000 | Deviation List for Furnace ID Fans |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-05
[6 empty] | Issue Actual | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00978
Return Date
Owner Cmmt*
| PL | OL1-2C40-305000 | Deviation List for Furnace Steam Drums |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-25
[6 empty] | Issue Actual | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01974
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C40-306000 | Deviation List for Furnace Buners |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-02-04
[6 empty] | Issue Actual | 2019-02-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00790
Return Date
Owner Cmmt*
| PL | OL1-2C40-307000 | Deviation List for Radiant Steel Panel |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | LSPA1-TPSK-T-PL-01668
Return Date
Owner Cmmt*
| PL | OL1-2C40-308000 | Deviation List for Utility Steel |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-25
[6 empty] | Issue Actual | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02697
[6 empty] | Return Date | 2019-10-14
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C40-311000 | Deviation List for Cooling Tower |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-08
[6 empty] | Issue Actual | 2019-03-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00879
[6 empty] | Return Date | 2019-06-20
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C40-403000 | Deviation List for Recycle Gas Compressor |  | Class 2 | Purpose** | IFA | IFA | IFA
[6 empty] | Rev. | B | C | D
Issue Plan
[6 empty] | Revised Plan | 2019-05-28
[6 empty] | Issue Actual | 2019-05-28 | 2019-06-20 | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01745 | TPSK-LSPA1-T-PL-01942 | TPSK-LSPA1-T-PL-02104
[6 empty] | Return Date | 2019-06-11
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C40-440003 | Deviation List for Cooling Water Pumps |  | Class 2 | Purpose** | IFA | IFP
[6 empty] | Rev. | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-08 | 2019-07-10
[6 empty] | Issue Actual | 2019-05-08 | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01591 | TPSK-LSPA1-T-PL-02114
Return Date
Owner Cmmt*
| PL | OL1-2C40-701000 | Deviation List for Condensate Polisher Package |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-20
[6 empty] | Issue Actual | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01922
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C40-702000 | Deviation List For Complex Waste Water Treatment Package |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02127
[6 empty] | Return Date | 2019-07-30
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C40-704000 | Deviation List for Wet Air Oxidation Package |  | Class 2 | Purpose** | IFR | IFR | IFP
[6 empty] | Rev. | B | C | 0
Issue Plan
[6 empty] | Revised Plan | 2019-04-08 |  | 2019-06-20
[6 empty] | Issue Actual | 2019-04-08 | 2019-05-09 | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01269 | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-PL-01943
[6 empty] | Return Date | 2019-06-19 | 2019-06-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PL | OL1-2C40-707000 | Deviation List For Chemical Dosing System |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-09-19
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02661
Return Date
Owner Cmmt*
| PL | OL1-2C40-708000 | Deviation List For HP / Polyolefins Flare Package |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | B | C
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21 | 2019-06-25
[6 empty] | Transmittal no. | LSPA1-TPSK-T-PL-01705 | TPSK-LSPA1-T-PL-01968
[6 empty] | Return Date | 2019-06-18 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PL | OL1-2C40-709000 | Deviation List For Furnace Elevator |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | B | C
Issue Plan
[6 empty] | Revised Plan | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02084 | TPSK-LSPA1-T-PL-02191
[6 empty] | Return Date | 2019-07-18 | 2019-08-07
[6 empty] | Owner Cmmt* | R1 | R1
Category Code: C41 Deviation List (DL) for Piping Work
Category Code: C42 Deviation List (DL) for Electrical work
| PL | OL1-2C42-800000 | Deviation List For Cathodic Protection System |  | Class 2 | Purpose** | IFP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-20
[6 empty] | Issue Actual | 2019-09-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02669
[6 empty] | Return Date | 2019-10-01
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C42-851000 | Deviation List For Safety Supervisory System |  | Class 2 | Purpose** | IFR | IFP
[6 empty] | Rev. | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-19 | 2019-08-01
[6 empty] | Issue Actual | 2019-07-19 | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02180 | TPSK-LSPA1-T-PL-02300
[6 empty] | Return Date | 2019-07-30 | 2019-08-14
[6 empty] | Owner Cmmt* | R1 | R1
| PL | OL1-2C42-881000 | ATTACHMENT 4 DEVIATION LIST FOR INTERCOM/PAGING/AUDIBLE ALARM SYSTEM |  | Class 2 | Purpose** | IFR | IFP
[6 empty] | Rev. | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-06-11 | 2019-07-01
[6 empty] | Issue Actual | 2019-06-11 | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01859 | TPSK-LSPA1-T-PL-02032
[6 empty] | Return Date | 2019-06-24 | 2019-07-08
[6 empty] | Owner Cmmt* | R1 | R1
Category Code: C43 Deviation List (DL) for Instrumentation work
Category Code: C44 Deviation List (DL) for Civil,Structure and Architecture
Category Code: C50 Purchase Order (PO) for Civil work, Building work, Steel Structure work
Category Code: C51 Purchase Order (PO) for Mechanical work
| PL | OL1-2C51-0001 | Vendor s Acknowledgment of Purchase Order For Wieland Tubes -Sole Source - MR 0610-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0002 | Vendor s Acknowledgment of Purchase Order For Residue Gas Expander Recompressor – MR 1130-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-04-11
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0003 | Vendor s Acknowledgment of Purchase Order For Steam Turbine Drive Centrifugal Compressor – MR 1011-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0004 | Vendor s Acknowledgment of Purchase Order For Centrifugal Compressor Steam Turbine Driven Site Services |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0005 | Vendor s Acknowledgment of Purchase Order For Deareator MR-0845-0001 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0006 | Vendor s Acknowledgment of Purchase Order For Plate And Frame Heat Exchangers – MR 0661-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0007 | Vendor s Acknowledgment of Purchase Order For Trays For Columns – MR 0570-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01707
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0008 | Vendor s Acknowledgment of Purchase Order For Cold Box And Core Exchangers – MR 0662-0002 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0009 | Vendor s Acknowledgment of Purchase Order For Trays For Shop Assembled Large Columns – MR 0511-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01707
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0010 | Vendor s Acknowledgment of Purchase Order For Cold Box And Core Exchangers Rev. 0 – MR 0662-0002 Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02073
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0011 | Vendor s Acknowledgment of Purchase Order For Integrally Geared Decoking Air Compressor Rev 1 – MR 1013-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02074
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0012 | Vendor s Acknowledgment of Purchase Order For Hydrogen Production Unit - MR 4111-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02076
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0013 | Vendor s Acknowledgment of Purchase Order For Steam Turbine Drive Centrifugal Compressor Rev 1 – MR 1011-0001 Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02076
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0014 | Vendor s Acknowledgment of Purchase Order For Centrifugal Compressor Steam Turbine Driven Site Services Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02076
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0015 | Vendor s Acknowledgment of Purchase Order For Reactors and Thicker Vessels Rev. 0 MR-0411-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-17
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02159
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0016 | Vendor s Acknowledgment of Purchase Order For Residue Gas Expander Recompressor Amd 1 – MR 1130-0001 Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-19
[6 empty] | Issue Actual | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02187
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0017 | Vendor s Acknowledgment of Purchase Order For Hairpin Heat Exchangers Rev. 0 MR-0630-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-30
[6 empty] | Issue Actual | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02536
[6 empty] | Return Date | 2019-09-05
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0018 | Vendor s Acknowledgment of Purchase Order For API Centrifugal Pumps Rev 0 – MR 0910-0002 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02611
[6 empty] | Return Date | 2019-09-24
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C51-0019 | Vendor s Acknowledgment of Purchase Order For LLI API Centrifugal Pumps Rev 0 – MR 0910-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-13
[6 empty] | Issue Actual | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02634
[6 empty] | Return Date | 2019-09-25
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0020 | Vendor s Acknowledgment of Purchase Order For Shop Assembled Columns Rev 0 – MR 0511-0002 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-13
[6 empty] | Issue Actual | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02637
[6 empty] | Return Date | 2019-09-25
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0021 | Vendor s Acknowledgment of Purchase Order For API Centrifugal Pumps Rev 0 – MR 0910-0008 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-13
[6 empty] | Issue Actual | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02637
[6 empty] | Return Date | 2019-09-25
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C51-0101 | Purchase Order for MR-4234-0001 - Side Stream Filter |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01385
Return Date
Owner Cmmt*
| PL | OL1-2C51-0102 | Purchase Order for MR-0310-0001 - Cooling Tower |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01842
[6 empty] | Return Date | 2019-06-28
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0103 | Vendor s Acknowledgment of Purchase Order For Wet Air Oxidation - MR 4100-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01856
[6 empty] | Return Date | 2019-06-28
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0104 | Vendor Acknowledgment of Purchase Order for HP / Polyolefins Flare Package |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-11
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02126
[6 empty] | Return Date | 2019-07-30
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0105 | Vendor’s Acknowledgment of Purchase Order For Packings for Columns (C4 Unit) - MR-0580-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02368
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0108 | Vendor s Acknowledgment of Purchase Order For Shell & Tube Heat Exchangers (Lot-1) |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-07
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02355
Return Date
Owner Cmmt*
| PL | OL1-2C51-0109 | Vendor s Acknowledgment of Purchase Order For Recycle Gas Compressor – MR 1031-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-07
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02355
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2C51-0110 | Vendor s Acknowledgment of Purchase Order For Shell & Tube Heat Exchangers Lot-3 – MR 0610-0004 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-07
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02355
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C51-0113 | Vendor s Acknowledgment of Purchase Order For Cooling Water Pumps – MR 0910-0003 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-07
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02355
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C51-0116 | Vendor's Acknowledgment of Purchase Order for Freight Forwarding Services - MR 6720-0001 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02744
Return Date
Owner Cmmt*
| PL | OL1-2C51-0118 | Vendor's Acknowledgment of Purchase Order for Safety Supervisory System - MR 1530-0002 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-24
[6 empty] | Issue Actual | 2019-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02690
Return Date
Owner Cmmt*
| PL | OL1-2C51-0120 | Vendor Acknowledgment of Purchase Order for Shop Assembled Large Drums |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 1
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
Transmittal no.
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0121 | Vendor s Acknowledgment of Purchase Order For Wet Air Oxidation - MR 4100-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 1
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
Transmittal no.
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0122 | Vendor s Acknowledgment of Purchase Order For Shop Assembled CS Drums– MR 0811-0002 Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 1
Issue Plan
[6 empty] | Revised Plan | 2019-08-28
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02498
[6 empty] | Return Date | 2019-09-10
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0124 | Vendor's Acknowledgment of Purchase Order for Trays for Columns (C4 Unit) - MR 0570-0003 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02743
Return Date
Owner Cmmt*
| PL | OL1-2C51-0125 | Vendor's Acknowledgment of Purchase Order for Shop Assembled Columns (C4 Unit) MR 0511-0003 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02743
Return Date
Owner Cmmt*
| PL | OL1-2C51-0126 | Vendor's Acknowledgment of Purchase Order for Condensate Polisher Package - MR 0213-0001 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02743
Return Date
Owner Cmmt*
| PL | OL1-2C51-0201 | Vendors Acknowledgment of Purchase Order for Quench System - Includes TLEs |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
[6 empty] | Return Date | 2019-10-09
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0202 | Vendors Acknowledgment of Purchase Order for Convection Section Tubes - Tubes for Convection Modules |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0203 | Vendors Acknowledgment of Purchase Order for Cast Tube Supports - Support for Convection Modules |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0204 | Vendors Acknowledgment of Purchase Order for Radiant Coils |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0205 | Vendors Acknowledgment of Purchase Order for Convection Section Fitting - Fittings for Convection Modules |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0206 | Vendors Acknowledgment of Purchase Order for Convection Boxes & Finning - Fabrication of Convection Modules |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0207 | Vendor Acknowledgment of Purchase Order for Furnace Burners |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0208 | Vendor Acknowledgment of Purchase Order for Peep Doors |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0209 | Vendor Acknowledgment of Purchase Order for Furnace Steam Drums |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0210 | Vendor Acknowledgment of Purchase Order for Furnace ID Fans |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0211 | Vendor Acknowledgment of Purchase Order for Crack Gas and Decoke MOV |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0212 | Vendor Acknowledgment of Purchase Order for Radiant Refractory |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0213 | Vendor Acknowledgment of Purchase Order for Radiant Steel Panel |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0214 | Vendor Acknowledgment of Purchase Order for Ripple Trays - Bubble Cap Trays and Hardware |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0215 | Vendor Acknowledgment of Purchase Order for Mesh Pads and Hardware |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0216 | Vendor Acknowledgment of Purchase Order for Cold Box |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0217 | Vendor Acknowledgment of Purchase Order for Support Beams Distributors and Hardware |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0218 | Vendor Acknowledgment of Purchase Order for HRS Gas Rectifier and Reflux Drum |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0219 | Vendor Acknowledgment of Purchase Order for HRS Valve Trays |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
Category Code: C51 Purchase Order (PO) for Mechanical work
| PL | OL1-2C51-0001 | Vendor s Acknowledgment of Purchase Order For Wieland Tubes -Sole Source - MR 0610-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0002 | Vendor s Acknowledgment of Purchase Order For Residue Gas Expander Recompressor – MR 1130-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-04-11
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0003 | Vendor s Acknowledgment of Purchase Order For Steam Turbine Drive Centrifugal Compressor – MR 1011-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0004 | Vendor s Acknowledgment of Purchase Order For Centrifugal Compressor Steam Turbine Driven Site Services |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0005 | Vendor s Acknowledgment of Purchase Order For Deareator MR-0845-0001 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0006 | Vendor s Acknowledgment of Purchase Order For Plate And Frame Heat Exchangers – MR 0661-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0007 | Vendor s Acknowledgment of Purchase Order For Trays For Columns – MR 0570-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01707
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0008 | Vendor s Acknowledgment of Purchase Order For Cold Box And Core Exchangers – MR 0662-0002 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01613
[6 empty] | Return Date | 2019-05-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0009 | Vendor s Acknowledgment of Purchase Order For Trays For Shop Assembled Large Columns – MR 0511-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01707
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0010 | Vendor s Acknowledgment of Purchase Order For Cold Box And Core Exchangers Rev. 0 – MR 0662-0002 Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02073
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0011 | Vendor s Acknowledgment of Purchase Order For Integrally Geared Decoking Air Compressor Rev 1 – MR 1013-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02074
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0012 | Vendor s Acknowledgment of Purchase Order For Hydrogen Production Unit - MR 4111-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02076
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0013 | Vendor s Acknowledgment of Purchase Order For Steam Turbine Drive Centrifugal Compressor Rev 1 – MR 1011-0001 Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02076
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0014 | Vendor s Acknowledgment of Purchase Order For Centrifugal Compressor Steam Turbine Driven Site Services Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-05
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02076
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0015 | Vendor s Acknowledgment of Purchase Order For Reactors and Thicker Vessels Rev. 0 MR-0411-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-17
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02159
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0016 | Vendor s Acknowledgment of Purchase Order For Residue Gas Expander Recompressor Amd 1 – MR 1130-0001 Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-19
[6 empty] | Issue Actual | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02187
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0017 | Vendor s Acknowledgment of Purchase Order For Hairpin Heat Exchangers Rev. 0 MR-0630-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-30
[6 empty] | Issue Actual | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02536
[6 empty] | Return Date | 2019-09-05
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0018 | Vendor s Acknowledgment of Purchase Order For API Centrifugal Pumps Rev 0 – MR 0910-0002 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02611
[6 empty] | Return Date | 2019-09-24
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C51-0019 | Vendor s Acknowledgment of Purchase Order For LLI API Centrifugal Pumps Rev 0 – MR 0910-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-13
[6 empty] | Issue Actual | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02634
[6 empty] | Return Date | 2019-09-25
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0020 | Vendor s Acknowledgment of Purchase Order For Shop Assembled Columns Rev 0 – MR 0511-0002 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-13
[6 empty] | Issue Actual | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02637
[6 empty] | Return Date | 2019-09-25
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0021 | Vendor s Acknowledgment of Purchase Order For API Centrifugal Pumps Rev 0 – MR 0910-0008 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-13
[6 empty] | Issue Actual | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02637
[6 empty] | Return Date | 2019-09-25
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C51-0101 | Purchase Order for MR-4234-0001 - Side Stream Filter |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01385
Return Date
Owner Cmmt*
| PL | OL1-2C51-0102 | Purchase Order for MR-0310-0001 - Cooling Tower |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01842
[6 empty] | Return Date | 2019-06-28
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0103 | Vendor s Acknowledgment of Purchase Order For Wet Air Oxidation - MR 4100-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01856
[6 empty] | Return Date | 2019-06-28
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0104 | Vendor Acknowledgment of Purchase Order for HP / Polyolefins Flare Package |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-11
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02126
[6 empty] | Return Date | 2019-07-30
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0105 | Vendor’s Acknowledgment of Purchase Order For Packings for Columns (C4 Unit) - MR-0580-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02368
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0108 | Vendor s Acknowledgment of Purchase Order For Shell & Tube Heat Exchangers (Lot-1) |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-07
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02355
Return Date
Owner Cmmt*
| PL | OL1-2C51-0109 | Vendor s Acknowledgment of Purchase Order For Recycle Gas Compressor – MR 1031-0001 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-07
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02355
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2C51-0110 | Vendor s Acknowledgment of Purchase Order For Shell & Tube Heat Exchangers Lot-3 – MR 0610-0004 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-07
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02355
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C51-0113 | Vendor s Acknowledgment of Purchase Order For Cooling Water Pumps – MR 0910-0003 Rev 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-07
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02355
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C51-0116 | Vendor's Acknowledgment of Purchase Order for Freight Forwarding Services - MR 6720-0001 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02744
Return Date
Owner Cmmt*
| PL | OL1-2C51-0118 | Vendor's Acknowledgment of Purchase Order for Safety Supervisory System - MR 1530-0002 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-24
[6 empty] | Issue Actual | 2019-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02690
Return Date
Owner Cmmt*
| PL | OL1-2C51-0120 | Vendor Acknowledgment of Purchase Order for Shop Assembled Large Drums |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 1
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
Transmittal no.
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0121 | Vendor s Acknowledgment of Purchase Order For Wet Air Oxidation - MR 4100-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 1
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
Transmittal no.
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0122 | Vendor s Acknowledgment of Purchase Order For Shop Assembled CS Drums– MR 0811-0002 Rev 1 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 1
Issue Plan
[6 empty] | Revised Plan | 2019-08-28
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02498
[6 empty] | Return Date | 2019-09-10
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0124 | Vendor's Acknowledgment of Purchase Order for Trays for Columns (C4 Unit) - MR 0570-0003 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02743
Return Date
Owner Cmmt*
| PL | OL1-2C51-0125 | Vendor's Acknowledgment of Purchase Order for Shop Assembled Columns (C4 Unit) MR 0511-0003 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02743
Return Date
Owner Cmmt*
| PL | OL1-2C51-0126 | Vendor's Acknowledgment of Purchase Order for Condensate Polisher Package - MR 0213-0001 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02743
Return Date
Owner Cmmt*
| PL | OL1-2C51-0201 | Vendors Acknowledgment of Purchase Order for Quench System - Includes TLEs |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
[6 empty] | Return Date | 2019-10-09
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0202 | Vendors Acknowledgment of Purchase Order for Convection Section Tubes - Tubes for Convection Modules |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0203 | Vendors Acknowledgment of Purchase Order for Cast Tube Supports - Support for Convection Modules |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0204 | Vendors Acknowledgment of Purchase Order for Radiant Coils |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0205 | Vendors Acknowledgment of Purchase Order for Convection Section Fitting - Fittings for Convection Modules |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0206 | Vendors Acknowledgment of Purchase Order for Convection Boxes & Finning - Fabrication of Convection Modules |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-08
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02380
Return Date
Owner Cmmt*
| PL | OL1-2C51-0207 | Vendor Acknowledgment of Purchase Order for Furnace Burners |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0208 | Vendor Acknowledgment of Purchase Order for Peep Doors |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0209 | Vendor Acknowledgment of Purchase Order for Furnace Steam Drums |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0210 | Vendor Acknowledgment of Purchase Order for Furnace ID Fans |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0211 | Vendor Acknowledgment of Purchase Order for Crack Gas and Decoke MOV |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0212 | Vendor Acknowledgment of Purchase Order for Radiant Refractory |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0213 | Vendor Acknowledgment of Purchase Order for Radiant Steel Panel |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0214 | Vendor Acknowledgment of Purchase Order for Ripple Trays - Bubble Cap Trays and Hardware |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0215 | Vendor Acknowledgment of Purchase Order for Mesh Pads and Hardware |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0216 | Vendor Acknowledgment of Purchase Order for Cold Box |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0217 | Vendor Acknowledgment of Purchase Order for Support Beams Distributors and Hardware |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0218 | Vendor Acknowledgment of Purchase Order for HRS Gas Rectifier and Reflux Drum |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C51-0219 | Vendor Acknowledgment of Purchase Order for HRS Valve Trays |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-21
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R1
Category Code: C52 Purchase Order (PO) for Piping work
| PL | OL1-2C52-0001 | Vendor s Acknowledgment of Purchase Order For Underground Welded Carbon Steel Pipes Rev 0 – MR 1329-0002 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-12
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02610
[6 empty] | Return Date | 2019-09-25
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2C52-0002 | Vendor s Acknowledgment of Purchase Order For Carbon Steel Underground Piping Rev 0 – MR 1309-0001 Rev. 0 |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-12
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02610
[6 empty] | Return Date | 2019-09-25
[6 empty] | Owner Cmmt* | R1
Category Code: C53 Purchase Order (PO) for Fire Fighting work
Category Code: C54 Purchase Order (PO) for Electrical and HVAC work
Category Code: C55 Purchase Order (PO) for Instrumentation work
| PL | OL1-2C55-0220 | Vendor Acknowledgment of Purchase Order for Pressure Relief Valves |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-22
[6 empty] | Issue Actual | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02469
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
Category Code: C56 Purchase Order (PO) for Chemicals
Category Code: C71 Appraisal Report for Consultancy Service
Category Code: C72 Appraisal Report for EPC Contractor Work
Category Code: C73 Appraisal Report for Vendor/Supplier
Category Code: C91 Index/List
| PL | OL1-2C91-0004 | Subvendor List For Mechanical Packages |  | Class 2 | Purpose** | IFI | IFI
[6 empty] | Rev. | 0 | 1
Issue Plan
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PL-01633 | TPSK-LSPA1-T-PL-02271
[6 empty] | Return Date | 2019-06-20 | 2019-08-14
[6 empty] | Owner Cmmt* | R2 | R2
Category Code: C92 Procedures & Standards
| PC | OL1-2C92-0001 | Project Procurement Execution Plan |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-14
[6 empty] | Issue Actual | 2018-09-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00051
[6 empty] | Return Date | 2018-11-29
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C92-0002 | Project QCS Coordination Procedure |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-13 | 2018-10-30
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046 | TPSK-LSPA1-T-PL-00244
[6 empty] | Return Date | 2018-10-01 | 2019-05-08
[6 empty] | Owner Cmmt* | R2 | R1
| PL | OL1-2C92-0005 | Project QCS Requirements For Suppliers |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-13 | 2018-10-30
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046 | TPSK-LSPA1-T-PL-00244
[6 empty] | Return Date | 2018-10-01 | 2019-05-08
[6 empty] | Owner Cmmt* | R2 | R1
| PL | OL1-2C92-0007 | Prescriptions For Preparation Of Documentation Package For Transportation |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-13 | 2018-10-08
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00048 | TPSK-LSPA1-T-PL-00140
[6 empty] | Return Date | 2018-10-01 | 2018-10-30
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C92-0008 | Project QCS Expediting Procedure |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-13 | 2018-11-09
[6 empty] | Issue Actual | 2018-09-13 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046 | TPSK-LSPA1-T-PL-00297
[6 empty] | Return Date | 2018-12-03
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C92-0009 | Project QCS Inspection Procedure |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-13 | 2018-10-30
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046 | TPSK-LSPA1-T-PL-00244
[6 empty] | Return Date | 2018-10-01 | 2019-05-06
[6 empty] | Owner Cmmt* | R2 | R1
| PL | OL1-2C92-0013 | Spare Parts & Special Tools Instructions |  | Class 2 | Purpose** | IMP | IFR
[6 empty] | Rev. | 0 | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-02 | 2018-10-19
[6 empty] | Issue Actual | 2018-10-02 | 2018-10-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00119 | TPSK-LSPA1-T-PL-00064
[6 empty] | Return Date |  | 2018-09-25
[6 empty] | Owner Cmmt* |  | R2
| PL | OL1-2C92-0014 | Project Expediting And Inspection Level Definition |  | Class 2 | Purpose** | IFR | IMP | IMP
[6 empty] | Rev. | A | 0 | 1
Issue Plan
[6 empty] | Revised Plan | 2018-09-13 | 2018-10-30
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-30 | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00046 | TPSK-LSPA1-T-PL-00244 | TPSK-LSPA1-T-PL-01473
[6 empty] | Return Date | 2018-10-01 | 2019-05-08 | 2019-07-02
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PL | OL1-2C92-0015 | Transportation Plan |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-13 | 2018-10-16
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00048 | TPSK-LSPA1-T-PL-00177
[6 empty] | Return Date | 2018-10-01 | 2018-10-30
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C92-0016 | Parking Marking And Shipping Instructions |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-13 | 2018-10-08
[6 empty] | Issue Actual | 2018-09-13 | 2018-10-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00048 | TPSK-LSPA1-T-PL-00140
[6 empty] | Return Date | 2018-10-01 | 2018-10-30
[6 empty] | Owner Cmmt* | R2
| PL | OL1-2C92-0017 | Project Site Services Conditions For Supplier s Specialists |  | Class 2 | Purpose** | IFR | IMP | IMP
[6 empty] | Rev. | A | 0 | 1
Issue Plan
[6 empty] | Revised Plan | 2018-09-14 | 2018-11-07
[6 empty] | Issue Actual | 2018-09-14 | 2018-11-07 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00051 | TPSK-LSPA1-T-PL-00284 | TPSK-LSPA1-T-PL-00594
[6 empty] | Return Date | 2018-10-04 | 2018-11-20 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PL | OL1-2C92-2126 | Project Procurement Plan - Furnace Island |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | 036909C-JVD-TRN-INTERNAL-00015
Return Date
Owner Cmmt*
Category Code: C93 Policy , Guidelines & Memo
| PL | OL1-2C93-0001 | General Supply Rules for Supplier Documentation |  | Class 2 | Purpose** | IFI | IFI | IFI
[6 empty] | Rev. | B | A | C
Issue Plan
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-19 | 2019-02-01
[6 empty] | Transmittal no. | 036909C-JVD-TRN-INTERNAL-00033 | TPSK-LSPA1-T-PL-00043 | TPSK-LSPA1-T-PL-00777
Return Date
Owner Cmmt*
Category Code: C94 Forms & Templates
Category Code: C95 Progress/Status Reports
| PL | OL1-2C95-0001 | Expediting Execution Plan |  | Class 2 | Purpose** | IFI | IFI | IFI | IFE | IMP | IMP | IMP
[6 empty] | Rev. | 0 | 1 | 2 | 3 | 4 | 5 | 6
Issue Plan
[6 empty] | Revised Plan | 2019-03-22 |  |  | 2019-06-19 | 2019-07-25
[6 empty] | Issue Actual | 2019-03-22 | 2019-04-19 | 2019-05-17 | 2019-06-19 | 2019-07-25 | 2019-09-05 | 2019-09-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01134 | TPSK-LSPA1-T-PL-01419 | TPSK-LSPA1-T-PL-01675 | TPSK-LSPA1-T-PL-01915 | LSPA1-TPSK-T-PL-02256 | TPSK-LSPA1-T-PL-02568 | TPSK-LSPA1-T-PL-02668
[6 empty] | Return Date |  |  | 2019-05-29 | 2019-06-27
[6 empty] | Owner Cmmt* |  |  | A1 | R2
| PL | OL1-2C95-0002 | Monthly Complete Expediting Report |  | Class 2 | Purpose** | IFI | IFI | IFI | IFE | IMP | IMP | IMP
[6 empty] | Rev. | 0 | 1 | 2 | 3 | 4 | 5 | 6
Issue Plan
[6 empty] | Revised Plan | 2019-03-22 |  |  | 2019-06-19 | 2019-07-25
[6 empty] | Issue Actual | 2019-03-22 | 2019-04-19 | 2019-05-17 | 2019-06-19 | 2019-07-25 | 2019-09-05 | 2019-09-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01134 | TPSK-LSPA1-T-PL-01419 | TPSK-LSPA1-T-PL-01675 | TPSK-LSPA1-T-PL-01915 | LSPA1-TPSK-T-PL-02256 | TPSK-LSPA1-T-PL-02568 | TPSK-LSPA1-T-PL-02668
[6 empty] | Return Date |  |  | 2019-05-29 | 2019-06-27 | 2019-08-02 | 2019-09-10
[6 empty] | Owner Cmmt* |  |  | A1 | R1 | R1 | R1
| PL | OL1-2C95-140000 | Hand-Over Meeting Report - Quench Exchanger and Steam D |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-12
[6 empty] | Issue Actual | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01026
Return Date
Owner Cmmt*
| PL | OL1-2C95-300000 | Hand-Over Meeting Report - Radiant Coils |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-04-01
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01194
Return Date
Owner Cmmt*
| PL | OL1-2C95-302000 | Pre-Inspection Meeting Report - Intermediate Tube Supports |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01359
Return Date
Owner Cmmt*
Category Code: Code Information
Category Code: D01 Construction Permits/License/Permit Plan
| CM | OL1-2D01-0001 | Construction Management Plan |  | Class 3 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-27
[6 empty] | Issue Actual | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CM-01166
Return Date
Owner Cmmt*
Category Code: D03 Security Plan
Category Code: D04 Transportation Program
Category Code: D05 Office & Construction Camp Plan
Category Code: D06 Work Change Proposal
Category Code: D71 Appraisal Report for Consultancy Service
Category Code: D72 Appraisal Report for EPC Contractor Work
Category Code: D73 Appraisal Report for Vendor/Supplier
Category Code: D91 Index/List
Category Code: D92 Procedures & Standards
| CM | OL1-2D92-0001 | Construction Subcontracting Plan |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-18
[6 empty] | Issue Actual | 2018-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CM-00193
Return Date
Owner Cmmt*
| CM | OL1-2D92-0003 | Schedule of Construction Subcontracts and Progress Report |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-12-14
[6 empty] | Issue Actual | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CM-00506
Return Date
Owner Cmmt*
| CM | OL1-2D92-0004 | Work Method Statement For Temporary Power Package |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-29
[6 empty] | Issue Actual | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CM-02531
Return Date
Owner Cmmt*
| CM | OL1-2D92-0005 | Site Hand Over Procedure |  | Class 2 | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-12 | 2019-10-15
[6 empty] | Issue Actual | 2019-09-12 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CM-02620 | TPSK-LSPA1-T-CM-02843
Return Date
Owner Cmmt*
Category Code: D93 Policy , Guidelines & Memo
Category Code: D94 Forms & Templates
Category Code: D95 Progress/Status Reports
Category Code: D96 Hydrostatic leak testing for piping systems
Category Code: E01 Electrical design basis
| EE | OL1-2E01-2001 | Electrical Basis of Design For Furnace Island |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-24 | 2019-03-28 | 2019-03-28
[6 empty] | Revised Plan | 2019-01-31 | 2019-10-16 | 2019-10-16
[6 empty] | Issue Actual | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00772
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A4
Category Code: E02 Abbreviation and standard symbols
| EE | OL1-2E02-0001 | Electrical Drawings Legend And Symbols |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-30 | 2019-10-30
[6 empty] | Revised Plan | 2019-04-19 | 2019-10-30
[6 empty] | Issue Actual | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01411
[6 empty] | Return Date | 2019-05-15
[6 empty] | Owner Cmmt* | R2
Category Code: E03 Project electrical specification
| EE | OL1-2E03-0035 | Typical Installation Standards For Electrical Equipment |  |  | Purpose** | IFR | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-10-07 | 2020-02-14
[6 empty] | Revised Plan | 2019-04-02 | 2019-11-29 | 2020-02-14
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01193
[6 empty] | Return Date | 2019-05-07
[6 empty] | Owner Cmmt* | A3
Category Code: E04 Electrical requirement for package unit
| EE | OL1-2E04-6000 | General Design Rule for Package Equipment Electrical System - Ex Client code OL1-2R05-0042 |  |  | Purpose** | IFR | IMP
[6 empty] | Rev. | B
[6 empty] | Issue Plan | 2018-10-14 | 2019-01-30
[6 empty] | Revised Plan | 2018-10-04
[6 empty] | Issue Actual | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00126
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
Category Code: E05 Electrical Equipment datasheets
| EE | CL1-2E05-1200 | Typical Data Sheet for Low Voltage Switchgears/MCCs |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-12-14
[6 empty] | Issue Actual | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00497
[6 empty] | Return Date | 2019-01-07
[6 empty] | Owner Cmmt* | R1
| EE | CL1-2E05-1400 | Typical Data Sheet for Low Voltage Bus Ducts |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-12-14
[6 empty] | Issue Actual | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00497
[6 empty] | Return Date | 2019-01-07
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E05-0020 | Air Conditioning Ventilating And Ducting Design - For Next Revision See Document OL1-2E05-0020 |  |  | Purpose** | IFR | IMP | IMP
[6 empty] | Rev. |  | 0 | 1
[6 empty] | Issue Plan | 2018-10-12 | 2019-01-15
[6 empty] | Revised Plan |  | 2019-01-07
[6 empty] | Issue Actual |  | 2019-01-07 | 2019-08-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00585 | TPSK-LSPA1-T-EE-02487
[6 empty] | Return Date |  | 2019-01-16 | 2019-09-23
[6 empty] | Owner Cmmt* |  | R1 | R2
| EE | OL1-2E05-1100 | Typical Data Sheet for Medium Voltage Switchgears |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-12-11
[6 empty] | Issue Actual | 2018-12-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | 2019-01-07
[6 empty] | Owner Cmmt* | R1
| EE | OL1-2E05-1111 | Data Sheet for Medium Voltage Switchgear |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-01
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-1211 | Data Sheet for 690V Switchgear And MCC |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-01
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-1311 | Data Sheet for 400V SwitchgearAndMCC |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-01
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-1501 | Data Sheet for Distribution Transformer |  | Class 1 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-01
[6 empty] | Issue Actual | 2019-04-01 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192 | TPSK-LSPA1-T-EE-02316
[6 empty] | Return Date | 2019-04-23 | 2019-08-26
[6 empty] | Owner Cmmt* | A3 | A1
| EE | OL1-2E05-1700 | Typical Data Sheet For Medium Voltage Variable Voltage Variable Frequency System |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-12-20
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00529
[6 empty] | Return Date | 2019-01-03
[6 empty] | Owner Cmmt* | R1
| EE | OL1-2E05-2001 | Data Sheet for AC UPS |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-01
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-2101 | Data Sheet For DC UPS |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-01
[6 empty] | Issue Actual | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01192
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E05-3100 | Typical Data Sheet for LV Motors |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-11-26
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00358
[6 empty] | Return Date | 2019-01-03
[6 empty] | Owner Cmmt* | R1
| EE | OL1-2E05-3500 | Typical Data Sheet For Low Voltage Variable Voltage Variable Frequency System |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-11-26
[6 empty] | Issue Actual | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00358
[6 empty] | Return Date | 2019-01-03
[6 empty] | Owner Cmmt* | R1
| EE | OL1-2E05-4100 | Typical Data Sheet For MV Motor |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-12-20
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00529
[6 empty] | Return Date | 2019-01-03
[6 empty] | Owner Cmmt* | R1
Category Code: E10 Power system studies
| EE | OL1-2E10-0001 | Electrical Cable Sizing Criteria |  |  | Purpose** | IFR | IFR | IDD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-14 |  | 2019-10-15 | 2020-01-15
[6 empty] | Revised Plan | 2019-04-24 |  | 2019-11-17 | 2020-01-15
[6 empty] | Issue Actual | 2019-04-24 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01438 | TPSK-LSPA1-T-EE-02593
[6 empty] | Return Date | 2019-05-15 | 2019-09-23
[6 empty] | Owner Cmmt* | A3 | A2
| EE | OL1-2E10-0002 | Electrical Power Balance |  |  | Purpose** | IDD | IDD1 | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-18 | 2019-10-21 | 2020-01-30
[6 empty] | Revised Plan | 2019-11-29 | 2020-04-29 | 2020-07-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0004 | Short-Circuit Analysis |  |  | Purpose** | IFR | IFR | IDD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-01-15 |  | 2020-03-17 | 2020-05-21
[6 empty] | Revised Plan | 2019-04-24 |  | 2020-03-17 | 2020-05-21
[6 empty] | Issue Actual | 2019-04-24 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01438 | TPSK-LSPA1-T-EE-02777
[6 empty] | Return Date | 2019-05-18
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E10-0005 | Load And Flow Voltage Drop Analysis |  |  | Purpose** | IFR | IFR | IDD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-01-15 |  | 2020-03-17 | 2020-05-21
[6 empty] | Revised Plan | 2019-04-24 |  | 2020-03-17 | 2020-05-21
[6 empty] | Issue Actual | 2019-04-24 | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01438 | TPSK-LSPA1-T-EE-02748
[6 empty] | Return Date | 2019-05-18
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E10-0006 | Motor Starting Study |  |  | Purpose** | IFR | IDD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
[6 empty] | Revised Plan | 2019-09-12 | 2020-03-17 | 2020-05-21
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02623
[6 empty] | Return Date | 2019-10-11
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E10-0008 | HARMONIC ANALYSIS |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
[6 empty] | Revised Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0009 | EMC STUDY |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
[6 empty] | Revised Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0010 | ELECTRICAL RELIABILITY ANALYSIS |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
[6 empty] | Revised Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E10-0011 | INSULATION COORDINATION STUDY |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
[6 empty] | Revised Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E11 Arc flash studies
| EE | OL1-2E11-0001 | FLASH PROTECTION STUDY |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
[6 empty] | Revised Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E12 Protective relay selection and coordination study
| EE | OL1-2E12-0001 | PROTECTIVE RELAY SELECTIVITY STUDY |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2020-10-21 | 2020-11-21 | 2020-12-21
[6 empty] | Revised Plan | 2020-10-21 | 2020-11-21 | 2020-12-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E13 Electrical equipment sizing
| EE | OL1-2E13-0001 | Power Factor Improvement System Study |  |  | Purpose** | IFR | IDD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-15 | 2020-03-17 | 2020-05-21
[6 empty] | Revised Plan | 2019-09-12 | 2020-03-17 | 2020-05-21
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02623
[6 empty] | Return Date | 2019-10-09
[6 empty] | Owner Cmmt* | A2
| EE | OL1-2E13-0002 | AC UPS SYSTEM SIZING |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-11 | 2020-03-15 | 2020-05-21
[6 empty] | Revised Plan |  | 2020-03-15 | 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E13-0003 | DC SYSTEM SIZING |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-11 | 2020-03-15 | 2020-05-21
[6 empty] | Revised Plan |  | 2020-03-15 | 2020-05-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E14 Single line diagram
| EE | OL1-2E14-0001 | Key Single Line Diagram |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-03 |  | 2019-11-07 | 2020-04-17
[6 empty] | Revised Plan | 2019-04-19 |  | 2019-11-07 | 2020-04-17
[6 empty] | Issue Actual | 2019-04-19 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01412 | TPSK-LSPA1-T-EE-02329
[6 empty] | Return Date | 2019-05-15 | 2019-08-19
[6 empty] | Owner Cmmt* | A3 | A2
| EE | OL1-2E14-0002 | INTERLOCKING SYSTEM PHYLOSOPHY DRAWING |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17
[6 empty] | Revised Plan | 2019-10-18 | 2019-11-07 | 2020-04-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E14-0003 | Substation E Single Line Diagram |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17 | 2020-07-17
[6 empty] | Revised Plan | 2019-04-02 | 2019-11-07 | 2020-04-17 | 2020-07-17
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01211
[6 empty] | Return Date | 2019-04-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E14-0004 | Substation C Single Line Diagram |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17 | 2020-07-17
[6 empty] | Revised Plan | 2019-04-02 | 2019-11-07 | 2020-04-17 | 2020-07-17
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01211
[6 empty] | Return Date | 2019-04-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E14-0005 | Substation F Single Line Diagram |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17 | 2020-07-17
[6 empty] | Revised Plan | 2019-04-02 | 2019-11-07 | 2020-04-17 | 2020-07-17
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01211
[6 empty] | Return Date | 2019-04-25
[6 empty] | Owner Cmmt* | A3
Category Code: E15 Electrical load schedule
| EE | OL1-2E15-0001 | Electrical Consumer List |  |  | Purpose** | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-03 | 2020-03-17
[6 empty] | Revised Plan | 2019-10-30 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0002 | Electrical Equipment List |  |  | Purpose** | IDD | IDD1 | IFF
Rev.
[6 empty] | Issue Plan | 2019-06-03 | 2019-11-07 | 2020-04-17
[6 empty] | Revised Plan |  | 2019-11-07 | 2020-04-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0003 | EX-EQUIPMENT REGISTER LIST |  |  | Purpose** | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-04-14 | 2020-10-19
[6 empty] | Revised Plan | 2020-04-14 | 2020-10-19
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-0004 | SUBSTATION E - Medium Voltage - Switchboard Composition |  |  | Purpose** | IFQ | IFQ | IFP | IFQ | IFQ | IFF
[6 empty] | Rev. | A | B |  | A | B
[6 empty] | Issue Plan | 2019-06-14 |  | 2019-09-18 | 2019-06-14 |  | 2019-09-18
[6 empty] | Revised Plan | 2019-08-05 |  | 2019-11-04 | 2019-08-05 |  | 2019-11-25
[6 empty] | Issue Actual | 2019-08-05 | 2019-10-15 |  | 2019-08-05 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02315 | TPSK-LSPA1-T-EE-02817 |  | TPSK-LSPA1-T-EE-02315 | TPSK-LSPA1-T-EE-02817
[6 empty] | Return Date | 2019-08-27 |  |  | 2019-08-27
[6 empty] | Owner Cmmt* | A2 |  |  | A2
| EE | OL1-2E15-0005 | Substation C - Medium Voltage - Switchboard Composition |  |  | Purpose** | IFQ | IFQ | IFP | IFQ | IFQ | IFF
[6 empty] | Rev. | A | B |  | A | B
[6 empty] | Issue Plan | 2019-06-14 |  | 2019-09-18 | 2019-06-14 |  | 2019-09-18
[6 empty] | Revised Plan | 2019-08-05 |  | 2019-11-04 | 2019-08-05 |  | 2019-11-25
[6 empty] | Issue Actual | 2019-08-05 | 2019-10-15 |  | 2019-08-05 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02315 | TPSK-LSPA1-T-EE-02817 |  | TPSK-LSPA1-T-EE-02315 | TPSK-LSPA1-T-EE-02817
[6 empty] | Return Date | 2019-08-27 |  |  | 2019-08-27
[6 empty] | Owner Cmmt* | A3 |  |  | A3
| EE | OL1-2E15-0006 | Substation E - Low Voltage - Switchboard Composition |  |  | Purpose** | IFQ | IFP | IFQ | IFF
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-09-07 | 2019-10-12 | 2019-09-07 | 2019-11-26
[6 empty] | Revised Plan | 2019-08-05 | 2019-11-11 | 2019-08-05 | 2019-11-26
[6 empty] | Issue Actual | 2019-08-05 |  | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02315 |  | TPSK-LSPA1-T-EE-02315
[6 empty] | Return Date | 2019-09-03 |  | 2019-09-03
[6 empty] | Owner Cmmt* | A3 |  | A3
| EE | OL1-2E15-0007 | Substation C - Low Voltage - Switchboard Composition |  |  | Purpose** | IFQ | IFP | IFQ | IFF
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-09-07 | 2019-10-12 | 2019-09-07 | 2019-11-26
[6 empty] | Revised Plan | 2019-08-05 | 2019-11-11 | 2019-08-05 | 2019-11-26
[6 empty] | Issue Actual | 2019-08-05 |  | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02315 |  | TPSK-LSPA1-T-EE-02315
[6 empty] | Return Date | 2019-09-03 |  | 2019-09-03
[6 empty] | Owner Cmmt* | A3 |  | A3
| EE | OL1-2E15-0008 | Substation F - Low Voltage - Switchboard Composition |  |  | Purpose** | IFQ | IFP | IFQ | IFF
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-09-07 | 2019-10-12 | 2019-09-07 | 2019-11-26
[6 empty] | Revised Plan | 2019-08-05 | 2019-11-11 | 2019-08-05 | 2019-11-26
[6 empty] | Issue Actual | 2019-08-05 |  | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02315 |  | TPSK-LSPA1-T-EE-02315
[6 empty] | Return Date | 2019-09-03 |  | 2019-09-03
[6 empty] | Owner Cmmt* | A3 |  | A3
| EE | OL1-2E15-1001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-10 | 2019-10-08 | 2019-10-08
[6 empty] | Revised Plan | 2019-12-09 | 2019-12-17 | 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-2001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-10 | 2019-10-08 | 2019-10-08
[6 empty] | Revised Plan | 2019-12-09 | 2019-12-17 | 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-3001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-12-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-4001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-12-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-5001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-12-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E15-6001 | LIST OF ELECTRICAL & INSTRUMENT LOADS |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-12-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E16 Emergency power supply load schedule
Category Code: E17 Motor list
Category Code: E18 Control and Signal List
| EE | OL1-2E18-0001 | Substation Monitoring & Control System Block Diagram for Substation E |  |  | Purpose** | IFQ | IFR | IFP | IFR
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-07-14 |  | 2019-11-04
[6 empty] | Revised Plan |  | 2019-06-14 | 2019-11-04 | 2019-06-14
[6 empty] | Issue Actual |  | 2019-06-14 |  | 2019-06-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-01895 |  | TPSK-LSPA1-T-EE-01895
[6 empty] | Return Date |  | 2019-07-01 |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| EE | OL1-2E18-0002 | Substation Monitoring & Control System Block Diagram for Substation C |  |  | Purpose** | IFQ | IFR | IFP | IFR
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-07-14 |  | 2019-11-04
[6 empty] | Revised Plan |  | 2019-06-14 | 2019-11-04 | 2019-06-14
[6 empty] | Issue Actual |  | 2019-06-14 |  | 2019-06-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-01895 |  | TPSK-LSPA1-T-EE-01895
[6 empty] | Return Date |  | 2019-07-01 |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| EE | OL1-2E18-0003 | Substation Monitoring & Control System Block Diagram for Substation F |  |  | Purpose** | IFQ | IFR | IFP | IFR
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-07-14 |  | 2019-11-04
[6 empty] | Revised Plan |  | 2019-06-14 | 2019-11-04 | 2019-06-14
[6 empty] | Issue Actual |  | 2019-06-14 |  | 2019-06-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-01895 |  | TPSK-LSPA1-T-EE-01895
[6 empty] | Return Date |  | 2019-07-01 |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2 |  | R2
Category Code: E19 Control schematic and control logic diagrams
| EE | OL1-2E19-0001 | Medium Voltage Protection Diagram |  |  | Purpose** | IFQ | IFR | IFP | IFR
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-09-07 |  | 2019-11-12
[6 empty] | Revised Plan |  | 2018-12-20 | 2019-11-12 | 2018-12-20
[6 empty] | Issue Actual |  | 2018-12-20 |  | 2018-12-20
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00555 |  | TPSK-LSPA1-T-EE-00555
[6 empty] | Return Date |  | 2019-01-07 |  | 2019-01-07
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| EE | OL1-2E19-0002 | Low Voltage Protection Diagram |  |  | Purpose** | IFQ | IFR | IFP | IFR
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-09-07 |  | 2019-11-12
[6 empty] | Revised Plan |  | 2018-12-20 | 2019-11-12 | 2018-12-20
[6 empty] | Issue Actual |  | 2018-12-20 |  | 2018-12-20
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00555 |  | TPSK-LSPA1-T-EE-00555
[6 empty] | Return Date |  | 2019-01-07 |  | 2019-01-07
[6 empty] | Owner Cmmt* |  | R2 |  | R2
Category Code: E20 Substation equipment layout
| EE | OL1-2E20-0001 | Substation E Equipment Layout |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-03 |  | 2019-10-08 | 2020-04-17 | 2020-06-17
[6 empty] | Revised Plan | 2019-04-02 |  |  | 2020-04-17 | 2020-06-17
[6 empty] | Issue Actual | 2019-04-02 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01212 | TPSK-LSPA1-T-EE-02488
[6 empty] | Return Date | 2019-06-04 | 2019-09-09
[6 empty] | Owner Cmmt* | A3 | A2
| EE | OL1-2E20-0002 | Substation C Equipment Layout |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-03 |  | 2019-10-08 | 2020-04-17 | 2020-06-17
[6 empty] | Revised Plan | 2019-04-02 |  | 2019-11-19 | 2020-04-17 | 2020-06-17
[6 empty] | Issue Actual | 2019-04-02 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01212 | TPSK-LSPA1-T-EE-02480
[6 empty] | Return Date | 2019-05-07 | 2019-09-09
[6 empty] | Owner Cmmt* | A3 | A3
| EE | OL1-2E20-0003 | Substation F Equipement Layout |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-03 |  | 2019-10-08 | 2020-04-17 | 2020-06-17
[6 empty] | Revised Plan | 2019-04-02 |  |  | 2020-04-17 | 2020-06-17
[6 empty] | Issue Actual | 2019-04-02 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01212 | TPSK-LSPA1-T-EE-02778
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | A3
Category Code: E21 Layout of busduct for substation
Category Code: E22 Cable tray layout for substation
| EE | OL1-2E22-0001 | SUBSTATION E CABLE ROUTING LAYOUT (N...) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
[6 empty] | Revised Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E22-0002 | SUBSTATION C CABLE ROUTING LAYOUT (N...) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
[6 empty] | Revised Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E22-0003 | SATELLITE SUBSTATION CABLE ROUTING LAYOUT (N...) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
[6 empty] | Revised Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E23 Wiring drawing for substation system
| EE | OL1-2E23-0001 | ELECTRICAL INTERCONNECTION WIRING LIST FOR SUBSTATION E |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-21 | 2019-08-21 | 2020-09-24 | 2020-12-15
[6 empty] | Revised Plan | 2020-07-28 | 2020-09-21 | 2020-09-24 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E23-0002 | ELECTRICAL INTERCONNECTION WIRING LIST FOR SUBSTATION C |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-21 | 2019-08-21 | 2020-09-24 | 2020-12-15
[6 empty] | Revised Plan | 2020-07-28 | 2020-09-21 | 2020-09-24 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E23-0003 | ELECTRICAL INTERCONNECTION WIRING LIST FOR SATELLITE SUBSTATION |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-21 | 2019-08-21 | 2020-09-24 | 2020-12-15
[6 empty] | Revised Plan | 2020-07-28 | 2020-09-21 | 2020-09-24 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E24 Diesel engine generator equipment layout
Category Code: E25 Motor Auto restart for power dift.
Category Code: E31 Power equipment layout
| EE | OL1-2E31-0002 | Electrical Main Cable Routing Layout - Zone 5T Cooling Water Unit |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-12 |  | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-07 |  | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-07 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02356 | TPSK-LSPA1-T-EE-2787
[6 empty] | Return Date | 2019-09-03
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0003 | Electrical Main Cable Routing Layout Zone 0P |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02622
[6 empty] | Return Date | 2019-09-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0004 | Electrical Main Cable Routing Layout - Zone 0S Substation E & Far E |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-12 |  | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-08 |  |  | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-08 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02381 | TPSK-LSPA1-T-EE-02787
[6 empty] | Return Date | 2019-09-03
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0005 | Electrical Main Cable Routing Layout - Zone 3S Substation & Far C |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-12 |  | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-07 |  |  | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-07 | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02356 | TPSK-LSPA1-T-EE-02736
[6 empty] | Return Date | 2019-09-03
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0007 | Electrical Main Cable Routing Layout - Zone 0M Metering Zone |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-28 |  | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02359
Return Date
Owner Cmmt*
| EE | OL1-2E31-0008 | Electrical Main Cable Routing Layout - Zone 5F HP & Polyolefins Flares |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-05 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02307
Return Date
Owner Cmmt*
| EE | OL1-2E31-0009 | Electrical Main Cable Routing Layout - Zone 5W Waste Water Treatment |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-12 |  | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-07-30 |  | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-07-30 | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02272 | TPSK-LSPA1-T-EE-02736
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0011 | Electrical Main Cable Routing Layout Zone 2A |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02622
[6 empty] | Return Date | 2019-09-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0012 | Electrical Main Cable Routing Layout Zone 2B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02622
[6 empty] | Return Date | 2019-09-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0013 | Electrical Main Cable Routing Layout Zone 2C |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02622
[6 empty] | Return Date | 2019-09-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0014 | Electrical Main Cable Routing Layout Zone 2D |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02622
[6 empty] | Return Date | 2019-09-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0015 | Electrical Main Cable Routing Layout Zone 2E |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02622
[6 empty] | Return Date | 2019-09-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0016 | Electrical Main Cable Routing Layout - Zone 3A Butadiene Extraction Unit |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-12 |  | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-07-30 |  |  | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-07-30 | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02272 | TPSK-LSPA1-T-EE-02736
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-0017 | Electrical Main Cable Routing Layout- Zone 5U Utilities |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02632
[6 empty] | Return Date | 2019-09-30
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E31-1001 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1002 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-1003 | USC 36M FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-2003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-3003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-4003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-5003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6001 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6002 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E31-6003 | USC 132SU CRACKING FURNACE ELECTRICAL EQUIPMENT LOCATION PLANS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
[6 empty] | Revised Plan | 2019-12-19 | 2020-01-09 | 2020-01-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E32 Main cable route layout
| EE | OL1-2E32-0001 | Power Layout - Zone 5T Cooling Water Unit |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-21 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02448
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0002 | Power Layout - Zone-0P |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02275
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0003 | Power Layout - Zone 0S Electrical Substation E & Far E |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-19 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02445
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0004 | Power Layout - Zone 3S Substation C & Far C |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-16 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02440
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0006 | Power Layout - Zone 0M Metering Station |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-28 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02529
Return Date
Owner Cmmt*
| EE | OL1-2E32-0007 | Power Layout - Zone 5F HP & Polyolefins Flares |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02496
[6 empty] | Return Date | 2019-09-10
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0008 | Power Layout - Zone 5W Waste Water Treatment |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02496
[6 empty] | Return Date | 2019-09-16
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0009 | Power Layout - Zone-1B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02275
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0010 | Power Layout - Zone-2A |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02275
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0011 | Power Layout - Zone-2B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02275
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0012 | Power Layout - Zone 2C - Key Plan |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02268
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0013 | Power Layout - Zone-2D |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02275
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0014 | Power Layout - Zone 2E - Key Plan |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-07-23 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02225
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-0015 | Power Layout - Zone 3A Butadiene Extraction Unit |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02496
[6 empty] | Return Date | 2019-09-16
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E32-0016 | Power Layout- Zone 5U |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Revised Plan | 2019-09-23 | 2019-11-22 | 2020-11-30 | 2021-01-15
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02677
[6 empty] | Return Date | 2019-10-01
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E32-1001 | USC 36M FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1002 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1003 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1004 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1005 | USC 36M FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1006 | USC 36M FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1007 | USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1008 | USC 36M FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-1009 | USC 36M FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-2009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-3009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-4009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-5009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6001 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY KEY PLAN FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6002 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6003 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6004 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6005 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY OVERALL LAYOUT PLANS, ELEVATION AND DETAILS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6006 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY PART NUMBERS |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6007 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6008 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY DETAILS INSTALLATION DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E32-6009 | USC 132SU CRACKING FURNACE ELECTRICAL CABLE TRAY LEGENDS & GENERAL NOTES FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
[6 empty] | Revised Plan | 2020-01-31 | 2020-02-24 | 2020-02-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E33 Power and control wiring layout
Category Code: E34 Power and control cable arrangement drawing
| EE | OL1-2E34-0001 | Cable Routing Cross Section - Zone 5T |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-09-03 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02548
[6 empty] | Return Date | 2019-09-16
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0002 | Electrical Cable Routing Cross Sections - Zone-OP |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02276
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0003 | Cable Routing Cross Section - Zone 0S |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02495
[6 empty] | Return Date | 2019-09-16
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0004 | Cable Routing Cross Section - Zone 3S |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02495
[6 empty] | Return Date | 2019-09-16
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0006 | Cable Routing Cross Section - Zone 0M |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-09-28 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02530
[6 empty] | Return Date | 2019-09-10
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0007 | Cable Routing Cross Section - Zone 5F |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan |  | 2019-11-22 | 2020-06-08 | 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E34-0008 | Cable Routing Cross Section - Zone 5W |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02495
[6 empty] | Return Date | 2019-09-16
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0009 | Electrical Cable Routing Cross Sections - Zone-1B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02276
[6 empty] | Return Date | 2019-09-13
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0010 | Electrical Cable Routing Cross Sections - Zone-2A |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02276
[6 empty] | Return Date | 2019-09-13
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0011 | Electrical Cable Routing Cross Sections - Zone-2B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02276
[6 empty] | Return Date | 2019-09-13
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0012 | Electrical Cable Routing Cross Sections Cover Page - Zone-2C |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02269
[6 empty] | Return Date | 2019-09-13
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0013 | Electrical Cable Routing Cross Sections - Zone-2D |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02276
[6 empty] | Return Date | 2019-09-13
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0014 | Electrical Cable Routing Cross Sections - Zone 2E |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-23 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02226
[6 empty] | Return Date | 2019-09-13
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0015 | Cable Routing Cross Section - Zone 3A |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-08-29 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02530
[6 empty] | Return Date | 2019-09-16
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E34-0016 | Electrical Cable Routing Cross Section- Zone 5U |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-12 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-09-23 | 2019-11-22 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02678
[6 empty] | Return Date | 2019-10-01
[6 empty] | Owner Cmmt* | R2
Category Code: E40 Lighting illumination level calculation
| EE | OL1-2E40-0001 | Lighting Calculation Report |  |  | Purpose** | IFR | IDD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-08-08
[6 empty] | Revised Plan | 2019-06-11 | 2019-12-04 | 2020-08-08
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01864
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | A3
Category Code: E41 Voltage drop calculation for lighting system
Category Code: E42 Lighting and receptacle panel board circuit schedule
| EE | OL1-2E42-0001 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0002 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0003 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0004 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0005 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0006 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0007 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0008 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0009 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0010 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0011 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0012 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0013 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0014 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0015 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0016 | LIGHTING CIRCUITS PANEL SCHEDULES (N...) |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-03-30 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0017 | Welding And Receptacles Panel Schedule - Zone 5T |  |  | Purpose** | IFQ | IFR | IFP | IFR | IFF
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-09-26 |  | 2019-12-13 |  | 2020-06-08
[6 empty] | Revised Plan |  | 2019-10-09 | 2019-12-13 | 2019-10-09 | 2020-06-08
[6 empty] | Issue Actual |  | 2019-10-09 |  | 2019-10-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-02737 |  | TPSK-LSPA1-T-EE-02737
Return Date
Owner Cmmt*
| EE | OL1-2E42-0018 | Welding Receptacles Panel Schedule - Zone 0P |  |  | Purpose** | IFQ | IFR | IFP | IFR | IFF
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-09-26 |  | 2019-12-13 |  | 2020-06-08
[6 empty] | Revised Plan |  | 2019-10-15 | 2019-12-13 | 2019-10-15 | 2020-06-08
[6 empty] | Issue Actual |  | 2019-10-15 |  | 2019-10-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-02816 |  | TPSK-LSPA1-T-EE-02816
Return Date
Owner Cmmt*
| EE | OL1-2E42-0024 | Welding And Receptacles Panel Schedule - Zone 5W |  |  | Purpose** | IFQ | IFR | IFP | IFR | IFF
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-09-26 |  | 2019-12-13 |  | 2020-06-08
[6 empty] | Revised Plan |  | 2019-09-19 | 2019-12-13 | 2019-09-19 | 2020-06-08
[6 empty] | Issue Actual |  | 2019-09-19 |  | 2019-09-19
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-02659 |  | TPSK-LSPA1-T-EE-02659
Return Date
Owner Cmmt*
| EE | OL1-2E42-0025 | Welding Receptacles Panel Schedule - Zone 1B |  |  | Purpose** | IFQ | IFR | IFP | IFR | IFF
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-09-26 |  | 2019-12-13 |  | 2020-06-08
[6 empty] | Revised Plan |  | 2019-10-15 | 2019-12-13 | 2019-10-15 | 2020-06-08
[6 empty] | Issue Actual |  | 2019-10-15 |  | 2019-10-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-02816 |  | TPSK-LSPA1-T-EE-02816
Return Date
Owner Cmmt*
| EE | OL1-2E42-0026 | Welding Receptacles Panel Schedule - Zone 2A |  |  | Purpose** | IFQ | IFR | IFP | IFR | IFF
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-09-26 |  | 2019-12-13 |  | 2020-06-08
[6 empty] | Revised Plan |  | 2019-10-15 | 2019-12-13 | 2019-10-15 | 2020-06-08
[6 empty] | Issue Actual |  | 2019-10-15 |  | 2019-10-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-02816 |  | TPSK-LSPA1-T-EE-02816
Return Date
Owner Cmmt*
| EE | OL1-2E42-0028 | WELDING AND RECEPTACLES PANEL SCHEDULE |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-26 | 2019-12-13 | 2020-06-08
[6 empty] | Revised Plan | 2019-10-30 | 2019-12-13 | 2020-06-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0030 | WELDING AND RECEPTACLES PANEL SCHEDULE |  |  | Purpose** | IFQ | IFP | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-26 | 2019-12-13 | 2020-06-08
[6 empty] | Revised Plan | 2019-10-30 | 2019-12-13 | 2020-06-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-0031 | Welding And Receptacles Panel Schedule - Zone 3A |  |  | Purpose** | IFQ | IFR | IFP | IFR | IFF
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-09-26 |  | 2019-12-13 |  | 2020-06-08
[6 empty] | Revised Plan |  | 2019-10-09 | 2019-12-13 | 2019-10-09 | 2020-06-08
[6 empty] | Issue Actual |  | 2019-10-09 |  | 2019-10-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-02737 |  | TPSK-LSPA1-T-EE-02737
Return Date
Owner Cmmt*
| EE | OL1-2E42-0032 | Welding and Receptacles Panel Schedule- Zone 5U |  |  | Purpose** | IFQ | IFP | IFQ | IFF
[6 empty] | Rev. | A |  | A
[6 empty] | Issue Plan | 2019-09-26 | 2019-12-13 | 2019-09-26 | 2020-06-08
[6 empty] | Revised Plan | 2019-10-10 | 2019-12-13 | 2019-10-10 | 2020-06-08
[6 empty] | Issue Actual | 2019-10-10 |  | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02788 |  | TPSK-LSPA1-T-EE-02788
Return Date
Owner Cmmt*
| EE | OL1-2E42-1001 | USC 36M FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1002 | USC 36M FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
[6 empty] | Revised Plan | 2020-06-01 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-1003 | USC 36M FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
[6 empty] | Revised Plan | 2020-06-01 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-2003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
[6 empty] | Revised Plan | 2020-06-01 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-3003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
[6 empty] | Revised Plan | 2020-06-01 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-4003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
[6 empty] | Revised Plan | 2020-06-01 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-5003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6001 | USC 132SU CRACKING FURNACE LIGHTING PANEL SCHEDULE FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6002 | USC 132SU CRACKING FURNACE RECEPTACLE PANEL SCHEDULE FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-06-01
[6 empty] | Revised Plan | 2020-06-01 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E42-6003 | USC 132SU CRACKING FURNACE SCHEMATIC LIGHTING PANEL DIAGRAM FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
[6 empty] | Revised Plan | 2020-07-28 | 2020-08-17 | 2020-08-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E43 Lighting and receptacle system layout
| EE | OL1-2E43-0001 | Street Lighting System Layout |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-06-10 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01794
[6 empty] | Return Date | 2019-06-12
[6 empty] | Owner Cmmt* | A2
| EE | OL1-2E43-0005 | Lighting Layout-Zone 5T Cooling Water Unit |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-31 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02281
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0006 | Lighting Layout - Zone 0P Main Pipe Rack |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan |  | 2019-12-04 | 2020-06-08 | 2020-08-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-0007 | Lighting Layout-Zone OS Electrical Substation E and FAR E |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-23 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02237
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0008 | Lighting Layout - Zone 3S Substation & Far C |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-23 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02204
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0010 | Lighting Layout-Zone OM Metering Zone |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-09-28 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02237
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0011 | Lighting Layout-Zone 5F HP & Polyolefins Flares Unit |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-23 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02237
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0012 | Lighting Layout-Zone 5W Waste Water Treatment |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-07-23 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02204
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0013 | Lighting Layout 1B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-04-22 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0014 | Lighting layout - Zone 2A Quench |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-04-22 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0015 | Lighting Layout - Zone 2B C3 Hydrogenation |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-04-22 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0016 | Lighting Layout 2C |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-04-22 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0017 | Lighting Layout - Zone 2D - Process Cold Compressor |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-04-22 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0018 | Lighting layout 2E |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-04-22 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01423
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0019 | Lighting Layout - Zone 3A Butadiene Extraction Unit |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-08-05 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02311
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-0020 | Lighting Layout- Zone 5U Utilities |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-19 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Revised Plan | 2019-09-17 | 2019-12-04 | 2020-06-08 | 2020-08-08
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02640
[6 empty] | Return Date | 2019-08-30
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E43-1001 | USC 36M FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1002 | USC 36M FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1003 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1004 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1005 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1006 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1007 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1008 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1009 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1010 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1011 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1012 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1013 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1014 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-1015 | USC 36M FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2018 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2019 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-2020 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-3017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4016 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4017 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4018 | ELECTRICAL LIGHTING FOR ELEVATOR LANDINGS ASSOCIATED WITH FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4019 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-4020 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5016 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-5017 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6001 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING KEY PLAN |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6002 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING LEGEND & GENERAL NOTES FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6003 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE INSTALLATION DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6004 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6005 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6006 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6007 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6008 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6009 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6010 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6011 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6012 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6013 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6014 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6015 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6016 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6017 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6018 | ELECTRICAL LIGHTING FOR STAIR TOWER ASSOCIATED WITH FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6019 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E43-6020 | USC 132SU CRACKING FURNACE ELECTRICAL LIGHTING AND RECEPTACLE PLANS SECTIONS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFD | IFF
Rev.
[6 empty] | Issue Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
[6 empty] | Revised Plan | 2020-04-16 | 2020-05-07 | 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E44 Lighting and receptacle system wiring layout
| EE | OL1-2E44-0001 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0002 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0003 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0004 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0006 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0007 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0008 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0009 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0010 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0011 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0012 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0013 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0014 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0015 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E44-0016 | LIGHTING CIRCUITS BLOCK DIAGRAMS (N...) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E45 POWER BLOCK DIAGRAM (WELDING AND RECEPACLES)
| EE | OL1-2E45-0001 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0002 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0003 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0004 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0005 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0006 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0007 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0008 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0009 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0010 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0011 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0012 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0013 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0014 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0015 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E45-0016 | POWER BLOCK DIAGRAM (WELDING AND RECEPACLES) |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-08 | 2020-09-08
[6 empty] | Revised Plan | 2020-07-08 | 2020-09-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E50 Grounding and lightning network calculation
| EE | OL1-2E50-0001 | Earthing and Lightning Protection System Calculation |  |  | Purpose** | IFR | IDD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-19 | 2019-10-15 | 2020-07-08
[6 empty] | Revised Plan | 2019-06-25 | 2019-11-17 | 2020-07-08
[6 empty] | Issue Actual | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01982
[6 empty] | Return Date | 2019-07-22
[6 empty] | Owner Cmmt* | A3
Category Code: E51 Protective zone for lightning system
Category Code: E52 Grounding and lightning system layout
| EE | OL1-2E52-0001 | Overall Earthing Layout |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-14 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01894
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0002 | Overall Lightning Protection Layout |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-14 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01894
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0003 | Earthing And Lightning Protection Layout - Zone 5T Cooling Water Unit |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-28 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02014
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0004 | Earthing and Lightning Protection Layout - Zone 0P |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-11 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01862
[6 empty] | Return Date | 2019-06-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0005 | Earthing And Lightning Protection Layout - Zone 0S Electrical Substation & Far E |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-07-08 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02089
[6 empty] | Return Date | 2019-07-15
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0006 | Earthing And Lightning Protection Layout - Zone 3S Substation & Far C |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-07-08 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02080
[6 empty] | Return Date | 2019-07-15
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0007 | Earthing And Lightning Protection Layout - Zone 0C Common Area |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-28 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02014
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0008 | Earthing And Lightning Protection Layout - Zone 0M Metering Station |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-09-28 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02014
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0009 | Earthing And Lightning Protection Layout-Zone 5F HP & Polyolefins Flares |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-07-08 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02089
[6 empty] | Return Date | 2019-07-15
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0010 | Earthing And Lightning Protection Layout - Zone 5W Waste Water Treatment |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-28 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02014
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0011 | Earthing And Lightning Protection Layout - Zone 1B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-11 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01862
[6 empty] | Return Date | 2019-06-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0012 | Earthing and Lightning Protection Layout - Zone 2A |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-10 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01793
[6 empty] | Return Date | 2019-07-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0013 | Earthing and Lightning Protection Layout - Zone 2B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-10 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01793
[6 empty] | Return Date | 2019-06-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0014 | Earthing Layout - Zone 2C - Key Plan |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-07-17 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02156
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0015 | Earthing and Lightning Protection Layout - Zone 2D |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-11 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01862
[6 empty] | Return Date | 2019-06-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0016 | Earthing Layout - Zone 2E - Earthing Key Plan |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-06-11 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01862
[6 empty] | Return Date | 2019-06-25
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0017 | Earthing And Lightning Protection Layout - Zone 3A Butadiene Extraction Unit |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-07-01 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02021
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2E52-0018 | Earthing and Lightning Protection Layout- Zone 5U Utilities |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-03 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Revised Plan | 2019-09-10 | 2019-11-15 | 2020-07-20 | 2020-09-20
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02580
[6 empty] | Return Date | 2019-09-18
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E52-0021 | SUBSTATION E EARTHING LAYOUT |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
[6 empty] | Revised Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0022 | SUBSTATION C EARTHING LAYOUT |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
[6 empty] | Revised Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-0023 | SATELLITE SUBSTATION EARTHING LAYOUT |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
[6 empty] | Revised Plan | 2019-11-08 | 2020-05-17 | 2020-11-05 | 2021-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1001 | USC 36M FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-02-03 | 2020-02-03
[6 empty] | Revised Plan | 2020-02-03 | 2020-02-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1002 | USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-02-03 | 2020-02-03
[6 empty] | Revised Plan | 2020-02-03 | 2020-02-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-1003 | USC 36M FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1100 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-02-03 | 2020-02-03
[6 empty] | Revised Plan | 2020-02-03 | 2020-02-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-2003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1200 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-3003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1300 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-4003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1400 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-5003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1500 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6001 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING AT GRADE PLANS AND DETAILS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6002 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E52-6003 | USC 132SU CRACKING FURNACE ELECTRICAL GROUNDING ABOVE GRADE PLANS AND DETAILS FURNACE 10-H-1600 |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-06-05 | 2020-06-05
[6 empty] | Revised Plan | 2020-06-05 | 2020-06-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E53 Wiring drawing for grounding and lightning system
Category Code: E54 Layout of grounding lug
Category Code: E60 Cable drum schedule
| EE | OL1-2E60-0001 | ELECTRICAL CABLE DRUM SCHEDULE |  |  | Purpose** | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-04-14 | 2020-10-19
[6 empty] | Revised Plan | 2020-04-14 | 2020-10-19
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E61 Cable schedule
| EE | OL1-2E61-0001 | Electrical Cable Schedule Sub E |  |  | Purpose** | IDD | IF1T | IF2T | IFF
Rev.
[6 empty] | Issue Plan | 2019-08-10 | 2019-11-15 | 2020-02-15 | 2020-05-15
[6 empty] | Revised Plan | 2019-10-25 | 2019-11-15 | 2020-02-15 | 2020-05-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E61-0002 | Electrical Cable Schedule Sub C |  |  | Purpose** | IDD | IF1T | IF2T | IFF
Rev.
[6 empty] | Issue Plan | 2019-08-10 | 2019-11-15 | 2020-02-15 | 2020-05-15
[6 empty] | Revised Plan | 2019-10-25 | 2019-11-15 | 2020-02-15 | 2020-05-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E61-0003 | Electrical Cable Schedule Sub F |  |  | Purpose** | IDD | IF1T | IF2T | IFF
Rev.
[6 empty] | Issue Plan | 2019-08-10 | 2019-11-15 | 2020-02-15 | 2020-05-15
[6 empty] | Revised Plan | 2019-10-25 | 2019-11-15 | 2020-02-15 | 2020-05-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E62 Connection List
Category Code: E63 Construction material and Bill of quantities
| EE | OL1-2E63-0002 | TECHNICAL SPECIFICATION FOR ELECTRICAL INSTALLATION |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-20 | 2020-05-22
[6 empty] | Revised Plan | 2020-02-20 | 2020-05-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-0004 | Earthing System Material Take-Off (OSBL Units) |  | Class 2 | Purpose** | IF1T
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02581
Return Date
Owner Cmmt*
| EE | OL1-2E63-0006 | Power System Material Take-Off (OSBL Units) |  | Class 2 | Purpose** | IF1T
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02600
[6 empty] | Return Date | 2019-10-01
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E63-0008 | Lighting System Material Take-Off (OSBL Units) |  | Class 2 | Purpose** | IF1T
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02600
[6 empty] | Return Date | 2019-09-30
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E63-0009 | Cables Material Take-Off (OSBL Units) |  | Class 2 | Purpose** | IFT1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-19
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02658
[6 empty] | Return Date | 2019-10-01
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2E63-1001 | ELECTRICAL BULK MATERIAL |  |  | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
[6 empty] | Revised Plan | 2019-10-22 | 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-2001 | ELECTRICAL BULK MATERIAL |  |  | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
[6 empty] | Revised Plan | 2019-10-22 | 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-3001 | ELECTRICAL BULK MATERIAL |  |  | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
[6 empty] | Revised Plan | 2019-10-22 | 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-4001 | ELECTRICAL BULK MATERIAL |  |  | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
[6 empty] | Revised Plan | 2019-10-22 | 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-5001 | ELECTRICAL BULK MATERIAL |  |  | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
[6 empty] | Revised Plan | 2019-10-22 | 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2E63-6001 | ELECTRICAL BULK MATERIAL |  |  | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-20
[6 empty] | Revised Plan | 2019-10-22 | 2020-02-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: E64 Typical drawing
Category Code: E70 Cathodic Protection system schematic diagram
Category Code: E71 Cathodic Protection system layout
Category Code: E72 Cathodic Protection calculation
Category Code: E80 SMCS and PMS system equipment data sheets
Category Code: E81 SMCS and PMS system schematic diagram
Category Code: E82 SMCS and PMS system layout
Category Code: E86 Appraisal Report for Consultancy Service
Category Code: E87 Appraisal Report for EPC Contractor Work
Category Code: E88 Appraisal Report for Vendor/Supplier
Category Code: E90 Vendor documents
Category Code: E91 Index/List
Category Code: E92 Procedures & Standards
| EE | OL1-2E92-0001 | General Design Rule For Smartplant Electrical - For Next Revision See Document OL1-2E92-0001 |  |  | Purpose** | IFR | IFI | IMP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-10-14 |  | 2019-01-30
[6 empty] | Revised Plan |  | 2018-11-29
[6 empty] | Issue Actual |  | 2018-11-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00396
Return Date
Owner Cmmt*
| EE | OL1-2E92-0002 | Coordination Procedure For Smartplant Electrical - For Next Revision See Document OL1-2E92-0002 |  |  | Purpose** | IFR | IFI | IMP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-10-14 |  | 2018-12-03
[6 empty] | Revised Plan |  | 2018-11-29
[6 empty] | Issue Actual |  | 2018-11-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00395
Return Date
Owner Cmmt*
| EE | OL1-2E92-0003 | Coordination Procedure For ETAP - Ex Document Client Reference OL1-2R05-0045 |  |  | Purpose** | IFR | IFI | IMP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2018-10-14 |  | 2018-12-03
[6 empty] | Revised Plan |  | 2018-12-05
[6 empty] | Issue Actual |  | 2018-12-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-EE-00426
Return Date
Owner Cmmt*
Category Code: E93 Policy , Guidelines & Memo
Category Code: E94 Forms & Templates
Category Code: E95 Progress/Status Reports
Category Code: F40 Fire and Gas Layout
| FF | OL1-2F40-5002 | FIRE & GAS DEVICES LAYOUT - ZONE 0M - METERING STATION |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01119 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5003 | FIRE & GAS DEVICES LAYOUT - ZONE 0P - MAIN PIPE RACK |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01119 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5004 | FIRE & GAS DEVICES LAYOUT -ZONE 0S - ELECTRICAL SUBSTATION E & FAR E |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5005 | FIRE & GAS DEVICES LAYOUT - ZONE 3S - AREA SUBSTATION C & FAR C |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5006 | FIRE & GAS DEVICES LAYOUT - ZONE 1B - FURNACES UTILITIES |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R1
| FF | OL1-2F40-5007 | FIRE & GAS DEVICES LAYOUT - ZONE 2A - QUENCH |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5008 | FIRE & GAS DEVICES LAYOUT - ZONE 2B - C3 HYDROGENERATION |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5009 | FIRE & GAS DEVICES LAYOUT - ZONE 2C - HOT FRACTIONATION / GHU UNIT |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-21 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-21 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5010 | FIRE & GAS DEVICES LAYOUT - ZONE 2D - PROCESS COLD COMPRESSOR |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5011 | FIRE & GAS DEVICES LAYOUT - ZONE 2E - CRACKED GAS COMPRESSOR |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5012 | FIRE & GAS DEVICES LAYOUT - ZONE 3A - BUTADIENE EXTRACTION UNIT |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5013 | FIRE & GAS DEVICES LAYOUT -ZONE 5T - COOLING WATER UNIT |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5014 | FIRE & GAS DEVICES LAYOUT -ZONE 5U - UTILITIES |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5015 | FIRE & GAS DEVICES LAYOUT - ZONE 5W - WASTE WATER TREATMENT |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-06-16
[6 empty] | Owner Cmmt* | R2 | R2
| FF | OL1-2F40-5016 | FIRE & GAS DEVICES LAYOUT ZONE 5F - HP & POLYOLEFINS FLARES UNIT |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-15 |  | 2020-01-25 | 2020-05-15
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-01-25 | 2020-05-15
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01120 | TPSK-LSPA1-T-FF-01518
[6 empty] | Return Date | 2019-05-10 | 2019-05-31
[6 empty] | Owner Cmmt* | R2 | R2
Category Code: F41 Fire and Gas Detector C&E
| FF | OL1-2F41-5001 | FIRE AND GAS CAUSE & EFFECT CHART FAR-E SYSTEM |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F41-5002 | FIRE AND GAS CAUSE & EFFECT CHART FAR-C SYSTEM |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| FF | OL1-2F41-5003 | FIRE AND GAS CAUSE & EFFECT CHART CCB SYSTEM |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-07 | 2020-09-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: F71 Appraisal Report for Consultancy Service
Category Code: F72 Appraisal Report for EPC Contractor Work
Category Code: F73 Appraisal Report for Vendor/Supplier
Category Code: F75 Escape Ways Drawing
| SE | OL1-2F75-0001 | Life Saving Equipment and Escape Route Layout - Zone 0S Electrical Sub-station and Far E |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-08-21 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02449
[6 empty] | Return Date | 2019-05-10 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1
| SE | OL1-2F75-0002 | Life Saving Equipment and Escape Route Layout - Zone 3S Electrical Sub-station and Far C |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-08-21 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02449
[6 empty] | Return Date | 2019-05-10 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1
| SE | OL1-2F75-0003 | Life Saving Equipment and Escape Route Layout - Zone 5T Cooling Water Unit |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 |  | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| SE | OL1-2F75-0004 | Life Saving Equipment and Escape Route Layout - Zone 5W Waste Water Treatment |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-07-03 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02050
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
| SE | OL1-2F75-0005 | Life Saving Equipment and Escape Route Layout - Zone 5U Utilities |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-07-03 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2
| SE | OL1-2F75-0006 | Life Saving Equipment and Escape Route Layout - Zone 5F HP & Polyolefins Flares Unit |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-09-05 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02573
[6 empty] | Return Date | 2019-05-10 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1
| SE | OL1-2F75-0007 | Life Saving Equipment and Escape Route Layout - Zone 0M Metering Station |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-09-28 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02573
[6 empty] | Return Date | 2019-05-10 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1
| SE | OL1-2F75-0009 | Life Saving Equipment and Escape Route Layout - - Zone 1B Furnaces Utility |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-07-03 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2
| SE | OL1-2F75-0010 | Life Saving Equipment and Escape Route Layout - Zone 2A Quench |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-07-03 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2
| SE | OL1-2F75-0011 | Life Saving Equipment and Escape Route Layout - Zone 2B C3 Hydrogenation |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-07-03 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2
| SE | OL1-2F75-0012 | Life Saving Equipment and Escape Route Layout - Zone 2D Process Cold Compressor |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-07-03 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2
| SE | OL1-2F75-0013 | Life Saving Equipment and Escape Route Layout - Zone 2E Cracked Gas Compressor |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-07-03 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2
| SE | OL1-2F75-0014 | Life Saving Equipment and Escape Route Layout - Zone 3A Butadiene Extraction Unit |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-07-03 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10 | 2019-07-29
[6 empty] | Owner Cmmt* | R2 | R2
| SE | OL1-2F75-0015 | Life Saving Equipment and Escape Route Layout - Zone 2C Hot Fractionation/GHU Unit |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-10 | 2019-06-07 | 2019-09-23 | 2020-04-06
[6 empty] | Revised Plan | 2019-03-29 | 2019-07-03 | 2019-10-24 | 2020-04-06
[6 empty] | Issue Actual | 2019-03-29 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01191 | TPSK-LSPA1-T-FF-02048
[6 empty] | Return Date | 2019-05-10
[6 empty] | Owner Cmmt* | R2
Category Code: F90 Vendor Document
Category Code: F91 Index/List
Category Code: F92 Procedures & Standards
| FF | OL1-2F92-0001 | Fire and Gas Detection |  |  | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-18 | 2019-02-15
[6 empty] | Revised Plan | 2019-03-22 | 2019-09-25
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-FF-01125 | TPSK-LSPA1-T-FF-02684
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R1
Category Code: F93 Policy , Guidelines & Memo
Category Code: F94 Forms & Templates
Category Code: F95 Progress/Status Reports
Category Code: G01 All Project Philosophies and Process design standard and All Project Studies Records
| PE | OL1-2G01-0001 | JSD for PID Preparation |  |  | Purpose** | IFR | IFA | IMP
[6 empty] | Rev. |  | A | 0
[6 empty] | Issue Plan | 2018-07-31 |  | 2019-03-01
[6 empty] | Revised Plan |  | 2018-07-31 | 2019-03-04
[6 empty] | Issue Actual |  | 2018-07-31 | 2019-03-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00006 | TPSK-LSPA1-T-PE-00965
[6 empty] | Return Date |  | 2018-08-21 | 2019-04-05
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G01-0002 | Cold Box Design Specification |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-04
[6 empty] | Issue Actual | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G01-0003 | Plate-Fin Exchanger Design Specification |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-04
[6 empty] | Issue Actual | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00123
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G01-0004 | Tray Design Specification |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-01-10
[6 empty] | Issue Actual | 2019-01-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00624
[6 empty] | Return Date | 2019-02-04
[6 empty] | Owner Cmmt* | R1
Category Code: G02 Design Basis
| PE | OL1-2G02-0001 | Process Basis of Design |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | C | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-07-27
[6 empty] | Issue Actual |  | 2018-07-27 |  | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00002 | TPSK-LSPA1-T-PE-02733 | TPSK-LSPA1-T-PE-01154
[6 empty] | Return Date |  | 2018-08-17 |  | 2019-05-16
[6 empty] | Owner Cmmt* |  | A3 |  | R2
| PE | OL1-2G02-0002 | Equipment Basis of Design |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | C | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-07-27
[6 empty] | Issue Actual |  | 2018-07-27 |  | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00002 | TPSK-LSPA1-T-PE-02734 | TPSK-LSPA1-T-PE-01154
[6 empty] | Return Date |  | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G02-0003 | Flare and Blowdown System Design Basis |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-09-04 |  | 2019-06-13
[6 empty] | Revised Plan |  | 2018-09-07 | 2019-10-10
[6 empty] | Issue Actual |  | 2018-09-07 | 2019-10-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00034 | TPSK-LSPA1-T-PE-02765
[6 empty] | Return Date |  | 2018-09-28
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G02-0006 | Furnace Process Basis of Design |  |  | Purpose** | IFR | IFA | IFF
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2018-07-31 |  | 2018-11-27
[6 empty] | Revised Plan |  | 2018-07-31
[6 empty] | Issue Actual |  | 2018-07-31
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00004
[6 empty] | Return Date |  | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3
Category Code: G03 Conceptual Design
Category Code: G04 Process Design Package
Category Code: G05 Equipment and Unit Functional Design
| PE | OL1-2G05-1001 | Area Basis of Design - 10 Feed Preparation |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-08 | 2019-03-27
[6 empty] | Issue Actual |  | 2018-08-08 | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-01154
[6 empty] | Return Date |  | 2018-08-27 | 2019-04-22
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G05-1101 | Steam Drum and Superheater PSVs Sizing Calculation |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-10
[6 empty] | Revised Plan | 2019-01-31 | 2019-10-16
[6 empty] | Issue Actual | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00769
[6 empty] | Return Date | 2019-03-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G05-1201 | Steam Drum and Superheater PSVs Sizing Calculation |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-10 | 2019-01-10
[6 empty] | Revised Plan | 2019-01-31 | 2019-10-16
[6 empty] | Issue Actual | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00769
[6 empty] | Return Date | 2019-03-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G05-2001 | Area Basis of Design - 20- 21 Quench and Dilution Steam |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-08 | 2019-04-03
[6 empty] | Issue Actual |  | 2018-08-08 | 2019-04-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-01224
[6 empty] | Return Date |  | 2018-08-27 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A3 | R1
| PE | OL1-2G05-2201 | Area Basis of Design - 22-24 Compresssion Train |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-15 | 2019-04-09
[6 empty] | Issue Actual |  | 2018-08-15 | 2019-04-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00022 | TPSK-LSPA1-T-PE-01272
[6 empty] | Return Date |  | 2018-09-05 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A3 | R2
| PE | OL1-2G05-2301 | Area Basis of Design - 23 Caustic and Spent Caustic Pretreatment |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-09 | 2019-04-12
[6 empty] | Issue Actual |  | 2018-08-09 | 2019-04-12 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00014 | TPSK-LSPA1-T-PE-01317 | TPSK-LSPA1-T-PE-02431
[6 empty] | Return Date |  | 2018-08-31 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A3 | R2
| PE | OL1-2G05-2501 | Area Basis of Design - 25 Cold Fractionation |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-08 | 2019-04-09
[6 empty] | Issue Actual |  | 2018-08-08 | 2019-04-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-01276
[6 empty] | Return Date |  | 2018-08-27
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-2601 | Area Basis of Design - 26 Hot Fractionation |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-09 | 2019-04-05
[6 empty] | Issue Actual |  | 2018-08-09 | 2019-04-05 | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00014 | TPSK-LSPA1-T-PE-01249 | TPSK-LSPA1-T-PE-02638
[6 empty] | Return Date |  | 2018-08-31 | 2019-05-16 | 2019-10-17
[6 empty] | Owner Cmmt* |  | A3 | R1 | R1
| PE | OL1-2G05-2602 | Area Basis of Design - 262 C3 Hydrogenation |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-11-12 | 2019-04-29
[6 empty] | Issue Actual |  | 2018-11-12 | 2019-04-29 | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-01510 | TPSK-LSPA1-T-PE-02638
[6 empty] | Return Date |  | 2019-02-04 | 2019-05-29 | 2019-10-17
[6 empty] | Owner Cmmt* |  | A1 | R2 | R1
| PE | OL1-2G05-2701 | Area Basis of Design - 270 Gasoline Hydrogenation -GHU-1 |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-11-12 | 2019-04-29
[6 empty] | Issue Actual |  | 2018-11-12 | 2019-04-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-01510
[6 empty] | Return Date |  | 2019-02-04 | 2019-05-29
[6 empty] | Owner Cmmt* |  | A1 | Re
| PE | OL1-2G05-2702 | Area Basis of Design - Area 275 C4 C5 Hydrogenation |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-11-12 | 2019-05-16
[6 empty] | Issue Actual |  | 2018-11-12 | 2019-05-16 | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00307 | TPSK-LSPA1-T-PE-01667 | TPSK-LSPA1-T-PE-02638
[6 empty] | Return Date |  | 2019-02-04 | 2019-06-21 | 2019-10-17
[6 empty] | Owner Cmmt* |  | A1 | R2 | R1
| PE | OL1-2G05-2801 | Area Basis of Design - 28 Refrigeration |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-08-15 | 2019-04-03
[6 empty] | Issue Actual |  | 2018-08-15 | 2019-04-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00022 | TPSK-LSPA1-T-PE-01224
[6 empty] | Return Date |  | 2018-09-05 | 2019-05-16
[6 empty] | Owner Cmmt* |  | A1 | R1
| PE | OL1-2G05-3001 | Area Basis of Design - 30 BDU |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-10-10 | 2019-06-20
[6 empty] | Issue Actual |  | 2018-10-10 | 2019-06-20 | 2019-09-28
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00150 | TPSK-LSPA1-T-PE-01932 | TPSK-LSPA1-T-PE-02718
[6 empty] | Return Date |  | 2019-04-02 | 2019-07-11
[6 empty] | Owner Cmmt* |  | R2 | R2
| PE | OL1-2G05-5001 | Area Basis of Design - 50 ISBL Supporting Utilities |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-12 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-07-31 | 2019-08-21
[6 empty] | Issue Actual |  | 2018-07-31 | 2019-08-21
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-02450
[6 empty] | Return Date |  | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-5301 | Area Basis of Design - 53 Cooling Tower System |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-08-09 |  | 2019-03-21
[6 empty] | Revised Plan |  | 2018-07-31 | 2018-09-27
[6 empty] | Issue Actual |  | 2018-07-31 | 2018-09-27 | 2019-08-21
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-00003 | TPSK-LSPA1-T-PE-02450
[6 empty] | Return Date |  | 2018-08-17
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-5501 | Area Basis of Design - 55 Flare System |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-08-09 |  | 2019-03-21
[6 empty] | Revised Plan |  | 2018-08-10 | 2019-08-22
[6 empty] | Issue Actual |  | 2018-08-10 | 2019-08-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00016 | TPSK-LSPA1-T-PE-02470
[6 empty] | Return Date |  | 2018-08-29
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G05-5601 | Area Basis of Design - 56 Waste Water Treatment System |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-09 |  | 2019-03-21
[6 empty] | Revised Plan |  | 2018-08-08 | 2018-09-27
[6 empty] | Issue Actual |  | 2018-08-08 | 2018-09-27 | 2019-02-26 | 2019-08-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00011 | TPSK-LSPA1-T-PE-00091 | TPSK-LSPA1-T-PE-00920 | TPSK-LSPA1-T-PE-02466
[6 empty] | Return Date |  | 2018-08-27 | 2018-10-12 | 2019-03-29 | 2019-09-19
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
Category Code: G06 Process simulation model
Category Code: G20 Design calculations
Category Code: G21 Hydraulic Calculation
Category Code: G22 Flare Calculation
| PE | OL1-2G22-0001 | Flare Load Summary |  |  | Purpose** | IFR | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-10-25 |  | 2019-06-20 | 2019-10-10
[6 empty] | Revised Plan | 2018-10-25 |  | 2019-10-16 | 2019-12-15
[6 empty] | Issue Actual | 2018-10-25 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00229 | TPSK-LSPA1-T-PE-02492
[6 empty] | Return Date | 2018-11-14 | 2019-10-08
[6 empty] | Owner Cmmt* | R2 | R2
Category Code: G23 Sizing data for the relief and blowdown systems
| PE | OL1-2G23-1001 | PSV-1001 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-1002 | PSV-1002 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-1003 | PSV-1003 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-1004 | PSV-1004 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-1006 | PSV-1006 and PSV-1009 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-1007 | PSV-1007 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-1008 | PSV-1008 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-1010 | PSV-1010 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-1011 | PSV-1011 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-1012 | PSV-1012 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-1015 | PSV-1015 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-1016 | PSV-1016 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01380
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-1901 | PSV-1911 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-1902 | PSV-1912 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2001 | PSV-2005 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2002 | PSV-2006 A-C Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2003 | PSV-2010 A-E Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2004 | PSV-2016 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2005 | PSV-2020 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2006 | PSV-2025 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2007 | PSV-2030 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2008 | PSV-2017 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2009 | PSV-2028 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2010 | PSV-2027 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2011 | PSV-2011 A-B-C-D-E Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2012 | PSV-2018 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2101 | PSV-2105 A-O Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2102 | PSV-2108 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2103 | PSV-2111 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2104 | PSV-2115 A-E Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2105 | PSV-2120 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2106 | PSV-2125 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-07-09 | 2019-10-08
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-2108 | PSV-2131 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-15
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2109 | PSV-2130 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2110 | PSV-2135 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2111 | PSV-2136 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-30
[6 empty] | Issue Actual | 2019-05-30 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01763 | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-06-25 | 2019-10-08
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2112 | PSV-2145 A-B-C-D Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01831 | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-07-09 | 2019-10-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G23-2113 | PSV-2146 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-30
[6 empty] | Issue Actual | 2019-05-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01763
[6 empty] | Return Date | 2019-06-25
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2116 | PSV-2165 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2117 | PSV-2166 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2118 | PSV-2132 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811 | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date | 2019-07-09 | 2019-10-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G23-2119 | PSV-2126 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2120 | PSV-2113 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2201 | PSV-2201 A-B-C Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date | 2019-06-04 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G23-2202 | PSV-2210 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2203 | PSV-2225 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2204 | PSV-2230 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474 | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date | 2019-06-04 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2205 | PSV-2235 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2206 | PSV-2246 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01475
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2207 | PSV-2255 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2208 | PSV-2260 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2209 | PSV-2265 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2210 | PSV-2266 A-B Sizing Calulation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01475 | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date | 2019-05-29 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2301 | PSV-2301 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2302 | PSV-2310 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2303 | PSV-2316 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-02
[6 empty] | Issue Actual | 2019-05-02 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530 | TPSK-LSPA1-T-PE-01698
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2304 | PSV-2322 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2305 | PSV-2327 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2306 | PSV-2332 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2307 | PSV-2335 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2308 | PSV-2341 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2309 | PSV-2343 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2390 | Process Datasheet for Restriction Orifice - Unit 23 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-20
[6 empty] | Issue Actual | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01929
Return Date
Owner Cmmt*
| PE | OL1-2G23-2401 | PSV-2401 Sizing Calculaiton |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2402 | PSV-2403 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2403 | PSV-2405 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2404 | PSV-2407 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2405 | PSV-2408 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01474
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2406 | PSV-2410 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2407 | PSV-2411 Sizing Calcuation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2408 | PSV-2414 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-03 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G23-2409 | PSV-2415 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-02
[6 empty] | Issue Actual | 2019-05-02 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530 | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-03 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G23-2410 | PSV-2416 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2411 | PSV-2418 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-17
[6 empty] | Issue Actual | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01680
Return Date
Owner Cmmt*
| PE | OL1-2G23-2412 | PSV-2419 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2413 | PSV-2422 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2414 | PSV-2423 A-B-C Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2415 | PSV-2425 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-01680
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2416 | PSV-2426 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2417 | PSV-2428 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2418 | PSV-2429 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-02
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2419 | PSV-2431 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364 | TPSK-LSPA1-T-PE-01680
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2420 | PSV-2432 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2422 | PSV-2435 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2423 | PSV-2436 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2424 | PSV-2437 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2425 | PSV-2438 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2426 | PSV-2441 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2427 | PSV-2443 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2428 | PSV-2444 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2429 | PSV-2445 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2430 | PSV-2446 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2431 | PSV-2447 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2432 | PSV-2448 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2433 | PSV-2449 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2434 | PSV-2450 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2435 | PSV-2440 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-16
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-001364
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2436 | PSV-2413 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-02
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01530
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2437 | PSV-2452 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-20
[6 empty] | Issue Actual | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01924
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2490 | Process Datasheet for Restriction Orifice - Area 24 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-20
[6 empty] | Issue Actual | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01929
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2501 | PSV-2504 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2503 | PSV-2514 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2504 | PSV-2517 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2505 | PSV-2520 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2506 | PSV-2522 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01382
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2507 | PSV-2524 Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-26
[6 empty] | Issue Actual | 2019-04-26 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488 | TPSK-LSPA1-T-PE-01530
[6 empty] | Return Date |  | 2019-05-29
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G23-2508 | PSV-2525 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01382
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2509 | PSV-2530 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-18
[6 empty] | Issue Actual | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2510 | PSV-2531 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-17
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01382
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2511 | PSV-2535 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-18
[6 empty] | Issue Actual | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2512 | PSV-2539 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2513 | PSV-2540 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-18
[6 empty] | Issue Actual | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2514 | PSV-2544 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2515 | PSV-2545 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2517 | PSV-2548 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-18
[6 empty] | Issue Actual | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2518 | PSV-2550 A-B-C Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2519 | PSV-2551 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-26
[6 empty] | Issue Actual | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01488
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2520 | PSV-2555 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-18
[6 empty] | Issue Actual | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2521 | PSV-2553 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01435
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2522 | PSV-2560 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-18
[6 empty] | Issue Actual | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2523 | PSV-2565 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2524 | PSV-2556 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-18
[6 empty] | Issue Actual | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01395
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2601 | PSV-2626 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2602 | PSV-2639 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2603 | PSV-2633 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759 | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date | 2019-06-21 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G23-2604 | PSV-2601 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2605 | PSV-2605 Sizinig Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2606 | PSV-2610 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2607 | PSV-2614 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2608 | PSV-2615 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2609 | PSV-2620 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2610 | PSV-2624 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2611 | PSV-2630 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2612 | PSV-2637 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2613 | PSV-2638 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2614 | PSV-2645 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2615 | PSV-2650 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2616 | PSV-2652 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2617 | PSV-2655 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01805
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2618 | PSV-2625 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2619 | PSV-2631 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2620 | PSV-2646 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2621 | PSV-2651 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date | 2019-10-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2622 | PSV 2616 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2701 | PSV-2703 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2702 | PSV-2704 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01831
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2703 | PSV-2706 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2704 | PSV-2716 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2705 | PSV-2705 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date | 2019-10-10
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2707 | PSV-2715 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date | 2019-10-10
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2708 | PSV-2719 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2709 | PSV-2723 A-B-C-D Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2710 | PSV-2721 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2711 | PSV-2726 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2712 | PSV-2729 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2713 | PSV-2733 A-B-C-D-E Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-27
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02002
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2714 | PSV-2734 A-B-C Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2715 | PSV-2737 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2716 | PSV-2738 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date | 2019-10-10
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2717 | PSV-2741 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2718 | PSV-2744 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2720 | PSV-2748 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2721 | PSV-2746 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2722 | PSV-2749 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2723 | PSV-2750 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2724 | PSV-2751 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2725 | PSV-2755 Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2726 | PSV-2760 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2727 | PSV-2761 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2728 | PSV-2766 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2729 | PSV-2767 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01988
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2730 | PSV-2771 Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2731 | PSV-2720 A-B-C Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2732 | PSV-2752 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01983
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2733 | PSV-2707 AB Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2734 | PSV-2714 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2735 | PSV-2745 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date | 2019-10-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2736 | PSV-2768 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-27
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02002
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2801 | PSV-2810 A-C Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2802 | PSV-2815 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2803 | PSV-2820 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2804 | PSV-2805 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2805 | PSV-2806 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01508
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2806 | PSV-2823 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2807 | PSV-2826 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2808 | PSV-2829 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2809 | PSV-2832 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-17
[6 empty] | Issue Actual | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01680
Return Date
Owner Cmmt*
| PE | OL1-2G23-2810 | PSV-2835 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2811 | PSV-2836 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2812 | PSV-2837 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-17
[6 empty] | Issue Actual | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01680
Return Date
Owner Cmmt*
| PE | OL1-2G23-2813 | PSV-2838 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2814 | PSV-2839 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2815 | PSV-2841 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2816 | PSV-2842 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2817 | PSV-2843 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2818 | PSV-2845 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2819 | PSV-2846 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2820 | PSV-2847 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2821 | PSV-2851 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2822 | PSV-2852 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2823 | PSV-2854 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2824 | PSV-2855 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-17
[6 empty] | Issue Actual | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01680
Return Date
Owner Cmmt*
| PE | OL1-2G23-2825 | PSV-2856 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2826 | PSV-2857 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2827 | PSV-2858 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2828 | PSV-2861 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2829 | PSV-2864 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2830 | PSV-2867 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2831 | PSV-2870 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01698
Return Date
Owner Cmmt*
| PE | OL1-2G23-2832 | PSV-2833 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2901 | PSV-2925 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2902 | PSV-2926 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2903 | PSV-2928 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2904 | PSV-2929 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2905 | PSV-2930 Sizing Calulation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2906 | PSV-2931 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2907 | PSV-2932 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-16
[6 empty] | Issue Actual | 2019-05-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01672
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2908 | PSV-2934 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2909 | PSV-2936 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2910 | PSV-2938 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2911 | PSV-2951 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2912 | PSV-2956 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2913 | PSV-2958 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2914 | PSV-2959 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2916 | PSV-2962 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2917 | PSV-2965 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2918 | PSV-2966 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2919 | PSV-2967 Sizing Calcuation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2921 | PSV-2974 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2922 | PSV-2976 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2923 | PSV-2981 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2924 | PSV-2985 Sizing Calucation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2925 | PSV-2986 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2927 | PSV-2988 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01759
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2928 | PSV-2963 Sizing Caluclation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-2929 | PSV-2975 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-2930 | PSV-2989 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01737
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-3001 | PSV-3001 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3004 | PSV-3004 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3005 | PSV-3005 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3006 | PSV-3006 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3007 | PSV-3007 & PSV-3008 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3009 | PSV-3009 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02416
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3010 | PSV-3010 & PSV-3012 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3011 | PSV-3011 & PSV-3013 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3014 | PSV-3014 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3015 | PSV-3015 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3016 | PSV-3016 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3017 | PSV-3017 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3018 | PSV-3018 - PSV-3020 - PSV-3022 - PSV-3025 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3019 | PSV-3019 - PSV-3021 - PSV-3023 - PSV-3024 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3026 | PSV-3026 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3027 | PSV-3027 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3028 | PSV-3028 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3029 | PSV-3029 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3031 | PSV-3031 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-08-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3032 | PSV-3032 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3033 | PSV-3033 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3034 | PSV-3034 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3035 | PSV-3035 & PSV-3036 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3037 | PSV-3037 & PSV-3038 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3039 | PSV-3039 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3041 | PSV-3041 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3042 | PSV-3042 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3046 | PSV-3046 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
Return Date
Owner Cmmt*
| PE | OL1-2G23-3049 | PSV-3049 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3072 | PSV-3072 & PSV-3073 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3074 | PSV-3074 & PSV-3075 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3077 | PSV-3077 & PSV-3078 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02320
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3079 | PSV-3079 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02416
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3102 | PSV-3102 & PSV-3103 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3140 | PSV-3140 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3150 | PSV-3150 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3151 | PSV-3151 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3152 | PSV-3152 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3162 | PSV-3162 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3163 | PSV-3163 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3164 | PSV-3164 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3165 | PSV-3165 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3166 | PSV-3166 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-08-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3167 | PSV-3167 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3168 | PSV-3168 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3169 | PSV-3169 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3176 | PSV-3176 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02332
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3643 | PSV-3943 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02416
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3943 | PSV-3943 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-08-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3944 | PSV-3944 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3945 | PSV-3945 & PSV-3946 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3947 | PSV-3947 & PSV-3948 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3953 | PSV-3953 & PSV-3970 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3954 | PSV-3954 PSV-3955 PSV-3956 PSV-3957 PSV-3958 PSV-3959 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-09-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-3960 | PSV-3960 & PSV-3961 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02337
[6 empty] | Return Date | 2019-08-27
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-5102 | PSV-5113 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5103 | PSV-5120 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5104 | PSV-5140 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-5105 | PSV-5143 A-H Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11 | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01851 | TPSK-LSPA1-T-PE-01921
[6 empty] | Return Date | 2019-07-08 | 2019-10-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-5106 | PSV-5150 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10 | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01921
[6 empty] | Return Date | 2019-07-08 | 2019-10-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G23-5107 | PSV-5153 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10 | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834 | TPSK-LSPA1-T-PE-01921
[6 empty] | Return Date | 2019-07-08 | 2019-10-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G23-5201 | PSV-5201 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5202 | PSV-5204 A-D Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-19
[6 empty] | Issue Actual | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01921
[6 empty] | Return Date | 2019-10-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5203 | PSV-5208 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01834
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5204 | PSV-5209 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01851
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G23-5401 | PSV-5401 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01822
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5402 | PSV-5404 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01811
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5501 | PSV-5507 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5502 | PSV-5506 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5503 | PSV-5509 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01912
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5504 | PSV-5510 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01851
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5506 | PSV-5520 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5507 | PSV-5521 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01873
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5508 | PSV-5530 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01883
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5509 | PSV-5531 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01912
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5510 | PSV-5532 A-B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01912
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5901 | PSV-5901 A Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5902 | PSV-5901 B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5903 | PSV-5908 A Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5904 | PSV-5908 B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5905 | PSV-5920 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5906 | PSV-5924 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5907 | PSV-5926 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5908 | PSV-5930 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5909 | PSV-5934 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5910 | PSV-5938 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5911 | PSV-5940 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5912 | PSV-5944 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5913 | PSV-5948 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5914 | PSV-5952 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5915 | PSV-5956 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5916 | PSV-5962 A Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5917 | PSV-5962 B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5918 | PSV-5965 A Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G23-5919 | PSV-5965 B Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01801
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| PE | OL2-2G23-2719 | PSV-2747 Sizing Calculation |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01911
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
Category Code: G30 Process Equipment Data Sheets
| PE | OL1-2G30-1000 | Process Equipment Datasheet - 10-D-1000 - LPG Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-25 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-25 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00227 | TPSK-LSPA1-T-PE-00463
[6 empty] | Return Date | 2018-12-05 | 2019-01-16
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1001 | Process Equipment Datasheet - 10-E-1000 - LPG Vaporizer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-16 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-16 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00451
[6 empty] | Return Date | 2018-11-14 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1003 | Process Equipment Datasheet - 10-E-1001 - LPG Steam Vaporizer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-16 | 2019-01-23
[6 empty] | Issue Actual | 2018-10-16 | 2019-01-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00179 | TPSK-LSPA1-T-PE-00712
[6 empty] | Return Date | 2019-01-28 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1005 | Process Equipment Datasheet - 10-E-1005 - LPG Feed Heater |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-16 | 2019-01-18
[6 empty] | Issue Actual | 2018-10-16 | 2019-01-18 | 2019-03-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00999
[6 empty] | Return Date | 2018-11-14 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1006 | Process Equipment Datasheet - 10-E-1006 - LPG Feed Steam Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-03-07 | 2019-04-05
[6 empty] | Issue Actual | 2019-03-07 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00998 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date |  | 2019-05-16
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-1015 | Process Equipment Datasheet - 10-E-1015 - LPG Superheater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-16 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-16 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00176 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-14 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1020 | Process Equipment Datasheet - 10-E-1020 - Liquid Feed Heater |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-22 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07 | 2019-01-18 | 2019-03-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431 | TPSK-LSPA1-T-PE-00680 | TPSK-LSPA1-T-PE-00999
[6 empty] | Return Date | 2018-11-30 | 2019-01-16 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-1051 | Process Equipment Datasheet - 10-E-1050 - C2 Feed Superheater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-22 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1101 | Process Equipment Datasheet - 10-H-1100 - USM 36M Cracking Furnace Yields |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-08-15 | 2018-08-15
[6 empty] | Revised Plan | 2018-10-22 | 2018-11-26
[6 empty] | Issue Actual | 2018-10-22 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00360
[6 empty] | Return Date | 2018-11-30 | 2018-12-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1102 | Anticipated Operating Conditions - 10-H-1100 - USC 36M Gas Cracking Furnace |  |  | Purpose** | IFR | IFI | IFD | IFF
[6 empty] | Rev. |  | 0 | 1
[6 empty] | Issue Plan | 2019-01-09 |  | 2019-03-06 | 2019-09-30
[6 empty] | Revised Plan |  | 2018-10-24 | 2019-04-03
[6 empty] | Issue Actual |  | 2018-10-24 | 2019-04-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00224 | TPSK-LSPA1-T-PE-01232
Return Date
Owner Cmmt*
| PE | OL1-2G30-1105 | Process Equipment Datasheet - 10-H-1100 - API Fired Heater Process Datasheet |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-09 | 2019-03-06 | 2019-09-30
[6 empty] | Revised Plan | 2019-02-06 | 2019-04-12 | 2019-11-11
[6 empty] | Issue Actual | 2019-02-06 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00814 | TPSK-LSPA1-T-PE-01322
[6 empty] | Return Date |  | 2019-05-15
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-1106 | Process Equipment Datasheet - 10-H-1100 - USC 36M Burner |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-10-30 | 2019-01-16 | 2019-01-16
[6 empty] | Revised Plan | 2018-10-30 | 2019-01-29
[6 empty] | Issue Actual | 2018-10-30 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241 | TPSK-LSPA1-T-PE-00756
[6 empty] | Return Date | 2018-11-27 | 2019-02-26
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-1107 | Process Equipment Datasheet - 10-D-1100 - USC 36M Cracking Furnace Steam Drum |  |  | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-10-11 | 2018-12-03 |  | 2018-12-03
[6 empty] | Revised Plan | 2018-10-12 | 2018-12-12
[6 empty] | Issue Actual | 2018-10-12 | 2018-12-12 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00478 | TPSK-LSPA1-T-PE-00935
[6 empty] | Return Date | 2018-11-05 | 2019-02-11 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1108 | Process Equipment Datasheet - 10-E-1100A1 - F6 - USC 36M USX Exchanger |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 | 2018-12-10
[6 empty] | Revised Plan | 2018-10-29 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00432
[6 empty] | Return Date | 2018-11-30 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1109 | Process Equipment Datasheet - 10-E-1110 - USC 36M TLX-1 Quench Exchanger |  |  | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 |  | 2018-12-10
[6 empty] | Revised Plan | 2018-10-29 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-10 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00459 | TPSK-LSPA1-T-PE-01078
[6 empty] | Return Date | 2018-11-30 | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1110 | Process Equipment Datasheet - 10-E-1120 - USC 36M TLX-2 Quench Exchanger |  |  | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 |  | 2018-12-10
[6 empty] | Revised Plan | 2018-10-29 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-10 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00459 | TPSK-LSPA1-T-PE-01078
[6 empty] | Return Date | 2018-11-30 | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1111 | Process Equipment Datasheet - 10-C-1100 - USC 36M Induced Draft Fan |  |  | Purpose** | IFR | IFD | IFD | IFD | IFF
[6 empty] | Rev. |  | B | C | D
[6 empty] | Issue Plan | 2018-09-26 | 2018-11-17 |  |  | 2018-11-17
[6 empty] | Revised Plan |  | 2018-10-24
[6 empty] | Issue Actual |  | 2018-10-24 | 2019-03-18 | 2019-06-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00222 | TPSK-LSPA1-T-PE-01079 | TPSK-LSPA1-T-PE-01797
[6 empty] | Return Date |  | 2018-11-30 | 2019-04-10 | 2019-07-03
[6 empty] | Owner Cmmt* |  | R1 | R1 | R2
| PE | OL1-2G30-1112 | Process Equipment Datasheet - 10-M-1100 - USC 36M Attemperator |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-03-13 | 2019-03-13
[6 empty] | Revised Plan | 2018-11-16 | 2019-01-29
[6 empty] | Issue Actual | 2018-11-16 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00330 | TPSK-LSPA1-T-PE-00752
[6 empty] | Return Date | 2018-12-13 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1151 | Process Equipment Datasheet 10-MOV-1101 USC 36M Effluent MOV |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-20 | 2019-03-05
[6 empty] | Revised Plan | 2018-12-20
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-1152 | Process Equipment Datasheet 10-MOV-1102A USC 36M Decoke Effluent MOV |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-20 | 2019-03-05
[6 empty] | Revised Plan | 2018-12-20
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-1153 | Process Equipment Datasheet 10-MOV-1102B USC 36M Decoke Effluent Bypass MOV |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2018-12-20 | 2019-04-01
[6 empty] | Issue Actual | 2018-12-20 | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-01195
[6 empty] | Return Date | 2019-01-28 | 2019-04-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1201 | Process Equipment Datasheet - 10-H-1200 - 132U Cracking Furnace Yields |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-08-15 | 2018-08-15
[6 empty] | Revised Plan | 2018-10-22 | 2018-11-27
[6 empty] | Issue Actual | 2018-10-22 | 2018-11-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00204 | TPSK-LSPA1-T-PE-00372
[6 empty] | Return Date | 2018-11-30 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1202 | Anticipated Operating Conditions - 10-H-1200_1600 - USC 132U Liquid Cracking Furnace |  |  | Purpose** | IFR | IFI | IFD | IFF
[6 empty] | Rev. |  | 0 | 1
[6 empty] | Issue Plan | 2019-01-09 |  | 2019-03-06 | 2019-09-30
[6 empty] | Revised Plan |  | 2018-10-24 | 2019-04-03
[6 empty] | Issue Actual |  | 2018-10-24 | 2019-04-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00224 | TPSK-LSPA1-T-PE-01232
Return Date
Owner Cmmt*
| PE | OL1-2G30-1205 | Process Equipment Datasheet - 10-H-1200/1600 - API Fired Heater Process Datasheet |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-09 | 2019-03-06 | 2019-09-30
[6 empty] | Revised Plan | 2019-02-06 | 2019-04-12 | 2019-11-11
[6 empty] | Issue Actual | 2019-02-06 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00814 | TPSK-LSPA1-T-PE-01322
[6 empty] | Return Date |  | 2019-05-15
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-1206 | Process Equipment Datasheet - 10-H-1200-1600 - USC 132U Burner |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-10-30 | 2019-01-16 | 2019-01-16
[6 empty] | Revised Plan | 2018-10-30 | 2019-01-29
[6 empty] | Issue Actual | 2018-10-30 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00241 | TPSK-LSPA1-T-PE-00756
[6 empty] | Return Date | 2018-12-27 | 2019-02-26
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G30-1207 | Process Equipment Datasheet - 10-D-1200_1600 - USC 132U Cracking Furnace Steam Drum |  |  | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-10-11 | 2018-12-03 |  | 2018-12-03
[6 empty] | Revised Plan | 2018-10-12 | 2018-12-12
[6 empty] | Issue Actual | 2018-10-12 | 2018-12-12 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00159 | TPSK-LSPA1-T-PE-00478 | TPSK-LSPA1-T-PE-00935
[6 empty] | Return Date | 2018-11-05 | 2019-02-11 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1208 | Process Equipment Datasheet - 10-E-1200A-F - 10-E-1600A-F - USC 132U SLE Exchanger |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 | 2018-12-10
[6 empty] | Revised Plan | 2018-10-29 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00433
[6 empty] | Return Date | 2018-11-30 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1209 | Process Equipment Datasheet - 10-E-1210_10-E-1610 - USC 132U TLX Quench Exchanger |  |  | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-09-19 | 2018-12-10 |  | 2018-12-10
[6 empty] | Revised Plan | 2018-10-29 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-10 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00237 | TPSK-LSPA1-T-PE-00449 | TPSK-LSPA1-T-PE-01078
[6 empty] | Return Date | 2018-11-30 | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-1211 | Process Equipment Datasheet - 10-C-1200_1600 - USC 132U Induced Draft Fan |  |  | Purpose** | IFR | IFD | IFD | IFD | IFF
[6 empty] | Rev. |  | B | C | D
[6 empty] | Issue Plan | 2018-09-26 | 2018-11-17 |  |  | 2018-11-17
[6 empty] | Revised Plan |  | 2018-10-24
[6 empty] | Issue Actual |  | 2018-10-24 | 2019-03-18 | 2019-06-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00222 | TPSK-LSPA1-T-PE-01079 | TPSK-LSPA1-T-PE-01797
[6 empty] | Return Date |  | 2018-11-30 | 2019-04-10 | 2019-07-03
[6 empty] | Owner Cmmt* |  | R1 | R1 | R2
| PE | OL1-2G30-1212 | Process Equipment Datasheet - 10-ZZ-1200_1600 - USC 132U Attemperator |  |  | Purpose** | IFR | IFD | IFD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-11-16 | 2019-03-13 |  | 2019-03-13
[6 empty] | Revised Plan | 2018-11-16 | 2019-01-29
[6 empty] | Issue Actual | 2018-11-16 | 2019-01-29 | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00330 | TPSK-LSPA1-T-PE-00752 | TPSK-LSPA1-T-PE-01220
[6 empty] | Return Date | 2018-12-13 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R2
| PE | OL1-2G30-1213 | Process Equipment Datasheet - 10-X-1200_1600 A-F - USC 132U Dilution Steam Mixing Tee |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-09 | 2019-01-09
[6 empty] | Revised Plan | 2018-12-07 | 2019-02-27
[6 empty] | Issue Actual | 2018-12-07 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00434 | TPSK-LSPA1-T-PE-00936
[6 empty] | Return Date |  | 2019-03-15
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-1251 | Process Equipment Datasheet 10-MOV-1201 USC 132U Effluent MOV |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-20 | 2019-03-05
[6 empty] | Revised Plan | 2018-12-20
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1252 | Process Equipment Datasheet 10-MOV-1202A USC 132U Decoke Effluent MOV |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-20 | 2019-03-05
[6 empty] | Revised Plan | 2018-12-20
[6 empty] | Issue Actual | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521
[6 empty] | Return Date | 2019-01-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-1253 | Process Equipment Datasheet 10-MOV-1202B USC 132U Decoke Effluent Bypass MOV |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2018-12-20 | 2019-04-01
[6 empty] | Issue Actual | 2018-12-20 | 2019-04-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00521 | TPSK-LSPA1-T-PE-01195
[6 empty] | Return Date | 2019-01-28 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1911 | Process Equipment Datasheet - 10-D-1910 - DMDS Bulk Storage Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-01-22 | 2019-03-20
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-20 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00686 | TPSK-LSPA1-T-PE-01096 | TPSK-LSPA1-T-PE--01280
[6 empty] | Return Date | 2019-02-21 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1912 | Process Equipment Datasheet - 10-D-1912 - DMDS Injection Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-01-22 | 2019-03-20
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-20 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00686 | TPSK-LSPA1-T-PE-01096 | TPSK-LSPA1-T-PE-01280
[6 empty] | Return Date | 2019-02-21 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1913 | Process Equipment Datasheet - 10-P-1910 A-B - DMDS Feed Injection Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-22 | 2019-03-04
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--00687 | TPSK-LSPA1-T-PE-00963
[6 empty] | Return Date | 2019-02-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-1914 | Process Equipment Datasheet - 10-P-1912 - DMDS Presulfiding Injection Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-22 | 2019-03-04
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--00687 | TPSK-LSPA1-T-PE-00963
[6 empty] | Return Date | 2019-02-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-1950 | Process Equipment Datasheet - 10-PK-1950 - Decoke Air Compressor Pkg |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
[6 empty] | Revised Plan |  | 2018-09-03 | 2018-10-01
[6 empty] | Issue Actual |  | 2018-09-03 | 2018-10-01 | 2018-10-30
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00114 | TPSK-LSPA1-T-PE-00242
[6 empty] | Return Date |  | 2018-09-28 | 2018-10-24 | 2018-11-30
[6 empty] | Owner Cmmt* |  | A3 | R2 | A1
| PE | OL1-2G30-2000 | Process Equipment Datasheet - 10-T-2000 - Quench Oil Tower |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-15 | 2018-12-04
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00402
[6 empty] | Return Date | 2018-11-05 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2006 | Process Equipment Datasheet - 10-P-2006 A-C - Quench Oil Pumps |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
[6 empty] | Revised Plan |  | 2018-09-24 | 2018-10-22
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-10-22 | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00071 | TPSK-LSPA1-T-PE-00202 | TPSK-LSPA1-T-PE-01159
[6 empty] | Return Date |  | 2018-10-09 | 2018-11-30 | 2019-04-12
[6 empty] | Owner Cmmt* |  | A3 | A1 | R1
| PE | OL1-2G30-2010 | Process Equipment Datasheet - 10-F-2008 A-C - Quench Oil Filter |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-11-21 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2014 | Process Equipment Datasheet - 10-F-2009 A-B - QO Pump Purge Oil Filter |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-11-21 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2015 | Process Equipment Datasheet - 10-E-2008 A-C - LS2 Steam Generators |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-09 | 2019-01-11
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00305 | TPSK-LSPA1-T-PE-00632
[6 empty] | Return Date | 2018-12-13 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2020 | Process Equipment Datasheet - 10-T-2020 - Light Fuel Oil Stripper |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-29 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00437
[6 empty] | Return Date | 2018-12-04 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2024 | Process Equipment Datasheet - 10-P-2026 A-B - Light Fuel Oil Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-07 | 2019-01-14
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2025 | Process Equipment Datasheet - 10-F-2026 A-B Cracker Bottoms Product Filter |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-11-21 | 2019-01-18
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00676
[6 empty] | Return Date | 2018-12-27 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2026 | Process Equipment Datasheet - 10-E-2026 - FO Product Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-09 | 2019-01-18
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298 | TPSK-LSPA1-T-PE-00680
[6 empty] | Return Date | 2018-12-17 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2028 | Process Equipment Datasheet - 10-F-2028 A-B - FO Pump Purge Oil Filter |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-11-21 | 2019-01-18
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00676
[6 empty] | Return Date | 2018-12-27 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2036 | Process Equipment Datasheet - 10-X-2036 - Quench Fitting |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2018-11-20 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-20 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00338 | TPSK-LSPA1-T-PE-00604
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2040 | Process Equipment Datasheet - 10-T-2040 - Heavy Fuel Oil Stripper |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-15 | 2018-11-21
[6 empty] | Issue Actual | 2018-10-15 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00347
[6 empty] | Return Date | 2018-11-05 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2046 | Process Equipment Datasheet - 10-P-2046 A-B - Heavy Fuel Oil Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-07 | 2019-01-14
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-14 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00648 | TPSK-LPSA1-T-PE-01402
[6 empty] | Return Date | 2018-12-27 | 2019-01-28 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2048 | Process Equipment Datasheet - 10-E-2048 - Heavy Fuel Oil Product Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-09 | 2019-01-18
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00298 | TPSK-LSPA1-T-PE-00680
[6 empty] | Return Date | 2018-12-17 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2049 | Process Equipment Datasheet - 10-F-2048 A-B - Heavy Fuel Oil Filters |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-11-21 | 2019-01-18
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-18 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00676 | TPSK-LSPA1-T-PE-01401
[6 empty] | Return Date | 2018-12-27 | 2019-02-11 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2070 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-2006 A Quench Oil Pump Turbine |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2090 | Process Equipment Datasheet - 10-D-2090 - Quench Oil Drain Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-27 | 2019-03-04
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00368 | TPSK-LSPA1-T-PE-00964
[6 empty] | Return Date | 2019-02-25 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2091 | Process Equipment Datasheet - 10-P-2090 A-B - Quench Oil Drain Drum Pumps |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-27 | 2019-03-04
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-04 | 2019-03-27 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01159 | TPSK-LSPA1-T-PE-01255
[6 empty] | Return Date | 2019-02-25 | 2019-03-21 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2092 | Process Equipment Datasheet - 10-EJ-2090 - Quench Oil Drain Sump Eductor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan |  | 2019-01-07
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2100 | Process Equipment Datasheet - 10-T-2100 - Quench Water Tower |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-29 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-29 | 2018-12-07 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00238 | TPSK-LSPA1-T-PE-00437 | TPSK-LSPA1-T-PE-01184
[6 empty] | Return Date | 2018-12-04 | 2019-01-16 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2101 | Process Equipment Datasheet - 10-E-2100 A-E - Quench Water Cooler |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-07
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-07 | 2019-04-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00143 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2104 | Process Equipment Datasheet - 10-F-2105 A-B - Quench Oil Reflux Filter |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-11-21 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-01072
[6 empty] | Return Date | 2018-12-27 | 2019-02-04 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2105 | Process Equipment Datasheet - 10-P-2105 A-B - Quench Oil Reflux Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-07 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00603 | TPSK-LSPA1-T-PE-01159
[6 empty] | Return Date | 2018-12-27 | 2019-02-04 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2106 | Process Equipment Datasheet - 10-P-2106 A-C - Quench Water Pumps |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
[6 empty] | Revised Plan |  | 2018-09-24 | 2018-10-22
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-10-22 | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00070 | TPSK-LSPA1-T-PE-00202 | TPSK-LSPA1-T-PE-01159
[6 empty] | Return Date |  | 2018-10-09 | 2018-11-30 | 2019-04-12
[6 empty] | Owner Cmmt* |  | A1 | A1 | R1
| PE | OL1-2G30-2110 | Process Equipment Datasheet - 10-D-2110 - Interception Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-10 | 2019-01-18
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-18 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00964
[6 empty] | Return Date | 2019-01-16 | 2019-02-21 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2120 | Process Equipment Datasheet - 10-T-2120 - Distillate Stripper |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-31 | 2018-11-29
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00253 | TPSK-LSPA1-T-PE-00401 | TPSK-LSPA1-T-PE-00437
[6 empty] | Return Date | 2018-12-04 | 2019-01-14 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2125 | Process Equipment Datasheet - 10-E-2125 - Distillate Stripper Reboiler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-01 | 2018-12-13
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00265 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-12-10 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2126 | Process Equipment Datasheet - 10-P-2126 A-B - Distillate Stripper Bottom Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-27 | 2019-03-04
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-04 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01383
[6 empty] | Return Date | 2019-02-25 | 2019-03-21 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2136 | Process Equipment Datasheet - 10-D-2136 - Process Water Feed Coalescer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-10 | 2019-01-18
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00678
[6 empty] | Return Date | 2019-01-16 | 2019-02-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2137 | Process Equipment Datasheet - 10-E-2136 - Process Water Stripper Feed Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-18 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2138 | Process Equipment Datasheet - 10-F-2136 A-B - Process Water Feed Filters |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-11-21 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07 | 2019-03-18 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00350 | TPSK-LSPA1-T-PE-00606 | TPSK-LSPA1-T-PE-01072 | TPSK-LSPA1-T-PE-01401
[6 empty] | Return Date | 2018-12-27 | 2019-02-04 | 2019-04-10 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-2139 | Process Equipment Datasheet - 10-F-2137 A-B - Process Water Coalescer Prefilters |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2019-04-18 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-18 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01401 | TPSK-LSPA1-T-PE-01804
[6 empty] | Return Date | 2019-06-04 | 2019-07-08
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2140 | Process Equipment Datasheet - 10-T-2140 - Process Water Stripper |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-18 | 2018-11-29
[6 empty] | Issue Actual | 2018-10-18 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00189 | TPSK-LSPA1-T-PE-00401
[6 empty] | Return Date | 2018-11-26 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2145 | Process Equipment Datasheet - 10-E-2145 - Process Water Stripper Reboiler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-18 | 2019-01-07
[6 empty] | Issue Actual | 2018-10-18 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00605
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2146 | Process Equipment Datasheet - 10-P-2146 A-B - DSG Feed Pumps |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
[6 empty] | Revised Plan |  | 2018-09-24 | 2018-10-22
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-10-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00069 | TPSK-LSPA1-T-PE-00202
[6 empty] | Return Date |  | 2018-10-09 | 2018-11-30
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G30-2147 | Process Equipment Datasheet - 10-E-2146 - DSG Feed Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-18 | 2019-01-07
[6 empty] | Issue Actual | 2018-10-18 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00605
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2160 | Process Equipment Datasheet - 10-D-2160 - Dilution System Generator |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
[6 empty] | Revised Plan |  | 2018-10-01 | 2019-01-10
[6 empty] | Issue Actual |  | 2018-10-01 | 2019-01-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00115 | TPSK-LSPA1-T-PE-00620
[6 empty] | Return Date |  | 2018-11-05 | 2019-02-11
[6 empty] | Owner Cmmt* |  | A3 | 03
| PE | OL1-2G30-2161 | Process Equipment Datasheet - 10-E-2160 - Dilution Steam Superheater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-18 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2165 | Process Equipment Datasheet - 10-E-2165 A-D - DSG Reboilers |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-18 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00194 | TPSK-LSPA1-T-PE-00467
[6 empty] | Return Date | 2018-11-26 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2166 | Process Equipment Datasheet - 10-E-2166 - DSG Blowdown Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-23 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-23 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00209 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2170 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-2106 A Quench Water Pump Turbine |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2171 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-2146 A DSG Feed Pump Turbine |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2190 | Process Equipment Datasheet - 10-D-2190 - Quench Water Drain Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-27 | 2019-03-04
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00368 | TPSK-LSPA1-T-PE-00964
[6 empty] | Return Date | 2019-02-25 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2191 | Process Equipment Datasheet - 10-P-2190 - Quench Water Drain Drum Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-21 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00346 | TPSK-LSPA1-T-PE-00603
[6 empty] | Return Date | 2018-12-27 | 2019-02-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2192 | Process Equipment Datasheet - 10-EJ-2190 - Quench Water Drain Sump Eductor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan |  | 2019-01-07
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2200 | Process Equipment Data Sheet - 10-C-2200 - Cracked Gas Compressor |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
[6 empty] | Revised Plan |  | 2018-08-23 | 2018-09-18
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-09-18
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date |  | 2018-09-11
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2206 | Process Equipment Datasheet - 10-E-2206 - Wash Water Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-28 | 2019-01-16
[6 empty] | Issue Actual | 2018-11-28 | 2019-01-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00381 | TPSK-LSPA1-T-PE-00655
[6 empty] | Return Date | 2019-01-14 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2210 | Process Equipment Datasheet - 10-D-2210 - CG 1st Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-08 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-05 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2211 | Process Equipment Datasheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-01 | 2018-12-13
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00266 | TPSK-LSPA1-T-PE-00479
[6 empty] | Return Date | 2018-12-10 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2212 | Process Equipment Datasheet - 10-P-2210 A-B - CG 1st Stage Condensate Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-07 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2220 | Process Equipment Datasheet - 10-D-2220 - CG 2nd Stage Suction Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-08 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-10 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00448 | TPSK-LSPA1-T-PE-00678
[6 empty] | Return Date | 2018-11-05 | 2019-01-16 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2221 | Process Equipment Datasheet - 10-E-2220 A-B - CG 2nd Stage Aftercooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-22 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2222 | Process Equipment Datasheet - 10-P-2220 A-B - CG 2nd Stage Condensed HC Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-07 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2230 | Process Equipment Datasheet - 10-D-2230 - CG 3rd Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-08 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-08 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-05 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2231 | Process Equipment Datasheet - 10-E-2230 A-B - CG 3rd Stage Aftercooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-22 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00431
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2240 | Process Equipment Datasheet - 10-D-2240 - CG 4th Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-16 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-16 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00448
[6 empty] | Return Date | 2018-11-14 | 2019-01-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2241 | Process Equipment Datasheet - 10-E-2240 A-B - CG 4th Stage Aftercooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-22 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00206 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-30 | 2019-01-16
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2245 | Process Equipment Datasheet - 10-D-2245 - CG 4th Stage Discharge Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-01 | 2018-12-13
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264 | TPSK-LSPA1-T-PE-00480
[6 empty] | Return Date | 2018-12-10 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2300 | Process Equipment Datasheet - 10-T-2300 - Caustic Tower |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-09-19 | 2018-11-08
[6 empty] | Issue Actual |  | 2018-09-19 | 2018-11-08 | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00060 | TPSK-LSPA1-T-PE-00290 | TPSK-LSPA1-T-PE-00597
[6 empty] | Return Date |  | 2018-10-24 | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* |  | A3 | R2 | A1
| PE | OL1-2G30-2301 | Process Equipment Datasheet - 10-X-2300 - Caustic Dilution Mixer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2018-10-16 | 2018-11-28
[6 empty] | Issue Actual | 2018-10-16 | 2018-11-28 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00383 | TPSK-LSPA1-T-PE-00600
[6 empty] | Return Date | 2018-11-14 | 2019-01-14 | 2019-02-04
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2302 | Process Equipment Datasheet - 10-P-2302 A-B - Strong Caustic Circulating Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-16 | 2018-12-20
[6 empty] | Issue Actual | 2018-10-16 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00524
[6 empty] | Return Date | 2018-11-14 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2304 | Process Equipment Datasheet - 10-P-2304 - Intermediate Caustic Circulating Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-16 | 2018-11-28
[6 empty] | Issue Actual | 2018-10-16 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00382
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2305 | Process Equipment Datasheet - 10-E-2305 - Caustic Tower Feed Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-31 | 2018-12-20
[6 empty] | Issue Actual | 2018-10-31 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00259 | TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-12-10 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2306 | Process Equipment Datasheet - 10-P-2306 A-B - Weak Caustic Circulating Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-16 | 2018-11-28
[6 empty] | Issue Actual | 2018-10-16 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00382
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2307 | Process Equipment Datasheet - 10-F-2306 A-B - Weak Caustic Circulating Filters |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-10-22 | 2018-12-13
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-13 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205 | TPSK-LSPA1-T-PE-00493 | TPSK-LSPA1-T-PE-00775
[6 empty] | Return Date | 2018-11-30 | 2019-01-22 | 2019-02-28
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-2308 | Process Equipment Datasheet - 10-X-2306 - Weak Caustic - Wash Oil Mixer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2018-10-16 | 2018-11-28
[6 empty] | Issue Actual | 2018-10-16 | 2018-11-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00383
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2309 | Process Equipment Datasheet - 10-D-2305 - Yellow Oil Drum |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
[6 empty] | Revised Plan |  | 2018-09-28 | 2019-01-11
[6 empty] | Issue Actual |  | 2018-09-28 | 2019-01-11 | 2019-04-05 | 2019-04-17
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-01260 | TPSK-LSPA1-T-PE-01377
[6 empty] | Return Date |  | 2018-11-14 | 2019-02-11 |  | 2019-05-24
[6 empty] | Owner Cmmt* |  | A3 | R1 |  | R1
| PE | OL1-2G30-2310 | Process Equipment Datasheet - 10-D-2310 - Spent Caustic Deoiling Drum |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-31 | 2019-01-07
[6 empty] | Issue Actual | 2018-10-31 | 2019-01-07 | 2019-07-02 | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00254 | TPSK-LSPA1-T-PE-00599 | TPSK-LSPA1-T-PE-02043 | TPSK-LSPA1-T-PE-02168
[6 empty] | Return Date | 2018-12-27 | 2019-01-28 |  | 2019-08-26
[6 empty] | Owner Cmmt* | R1 | R1 |  | R1
| PE | OL1-2G30-2311 | Process Equipment Datasheet - 10-P-2310 A-B - Wash Oil Circulating Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-16 | 2018-12-20
[6 empty] | Issue Actual | 2018-10-16 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00174 | TPSK-LSPA1-T-PE-00524
[6 empty] | Return Date | 2018-11-14 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2313 | Process Equipment Datasheet - 10-X-2312 - Spent Wash Oil Mixer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2018-10-16 | 2018-12-20
[6 empty] | Issue Actual | 2018-10-16 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00525
[6 empty] | Return Date | 2018-11-14 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2314 | Process Equipment Datasheet - 10-F-2310 A-B - Wash Oil Circulating Filter |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-10-22 | 2018-12-13
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00205 | TPSK-LSPA1-T-PE-00493
[6 empty] | Return Date | 2018-11-30 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2315 | Process Equipment Datasheet - 10-X-2310 - Spent Caustic Mixer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2018-10-16 | 2018-12-20
[6 empty] | Issue Actual | 2018-10-16 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00173 | TPSK-LSPA1-T-PE-00525
[6 empty] | Return Date | 2018-11-14 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2316 | Process Equipment Datasheet - 10-D-2316 - Spent Caustic Degassing Drum |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-16 | 2019-01-11
[6 empty] | Issue Actual | 2018-10-16 | 2019-01-11 | 2019-04-17 | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01785
[6 empty] | Return Date | 2018-11-26 | 2019-02-11 | 2019-05-24 | 2019-06-25
[6 empty] | Owner Cmmt* | R2 | R1 | R2 | R1
| PE | OL1-2G30-2319 | Process Equipment Datasheet - 10-F-2320 A-B - Spent Caustic Pump Discharge Filters |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-10-31 | 2018-12-13
[6 empty] | Issue Actual | 2018-10-31 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00255 | TPSK-LSPA1-T-PE-00493
[6 empty] | Return Date | 2018-12-10 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2320 | Process Equipment Datasheet - 10-TK-2320 - Spent Caustic Storage Tank |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-24 | 2018-10-22
[6 empty] | Issue Actual |  | 2018-09-24 | 2018-10-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00068 | TPSK-LSPA1-T-PE-00203
[6 empty] | Return Date |  | 2018-10-09 | 2018-11-30
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G30-2321 | Process Equipment Datasheet - 10-P-2320 A-B - Spent Caustic Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-31 | 2019-01-07
[6 empty] | Issue Actual | 2018-10-31 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252 | TPSK-LSPA1-T-PE-00598
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2322 | Process Equipment Datasheet - 10-D-2322 - Skim Oil Drum |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
[6 empty] | Revised Plan |  | 2018-09-28 | 2019-03-26
[6 empty] | Issue Actual |  | 2018-09-28 | 2019-03-26 | 2019-04-17 | 2019-05-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00111 | TPSK-LSPA1-T-PE-01142 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01652
[6 empty] | Return Date |  | 2019-02-25 | 2019-04-22 | 2019-06-13 | 2019-06-03
[6 empty] | Owner Cmmt* |  | A1 | TP | R1 | R1
| PE | OL1-2G30-2323 | Process Equipment Datasheet - 10-EJ-2322 - Skim Oil Sump Eductor |  | Class 2 | Purpose** | IFD | CAN
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-01-07 | 2019-03-20
[6 empty] | Issue Actual | 2019-01-07 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00595 | TPSK-LSPA1-T-PE-01098
[6 empty] | Return Date | 2019-01-28 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2324 | Process Equipment Datasheet - 10-TK-2300 - Fresh Caustic Day Tank |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-12-13 | 2019-01-29
[6 empty] | Issue Actual | 2018-12-13 | 2019-01-29 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00495 | TPSK-LSPA1-T-PE-00760 | TPSK-LSPA1-T-PE-00937
[6 empty] | Return Date | 2019-01-22 | 2019-02-25 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2325 | Process Equipment Datasheet - 10-P-2300 A-B - 10 Percent Caustic Makeup Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-20 | 2019-01-29
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00526 | TPSK-LSPA1-T-PE-00759
[6 empty] | Return Date | 2019-01-28 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2326 | Process Equipment Datasheet - 10-E-2326 - Spent Caustic Stripper Feed Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-28 | 2019-01-22
[6 empty] | Issue Actual | 2018-11-28 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00381 | TPSK-LSPA1-T-PE-00690
[6 empty] | Return Date | 2019-01-14 | 2019-03-05
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2327 | Process Equipment Datasheet - 10-P-2322 - Skim Oil Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-03-26 | 2019-04-30
[6 empty] | Issue Actual | 2019-03-26 | 2019-04-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01517
[6 empty] | Return Date | 2019-04-12 | 2019-06-03
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2330 | Process Equipment Datasheet - 10-T-2330 - Spent Caustic Stripper |  |  | Purpose** | IFR | IFA | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-01-21 |  |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-09-25 |  | 2018-11-28
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-10-12 | 2018-11-28 | 2019-06-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00160 | TPSK-LSPA1-T-PE-00384 | TPSK-LSPA1-T-PE-01808
[6 empty] | Return Date |  | 2018-10-12 | 2019-02-25 | 2018-12-27 | 2019-07-08
[6 empty] | Owner Cmmt* |  | A3 | A2 | TP | R2
| PE | OL1-2G30-2331 | Process Equipment Datasheet - 10-D-2330 - Spent Caustic Stripper Ovhd Drum |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E | F
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-16 | 2019-01-11
[6 empty] | Issue Actual | 2018-10-16 | 2019-01-11 | 2019-04-12 | 2019-04-17 | 2019-05-21 | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00175 | TPSK-LSPA1-T-PE-00634 | TPSK-LSPA1-T-PE-01327 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01694 | TPSK-LSPA1-T-PE-02125
[6 empty] | Return Date | 2018-11-26 | 2019-02-11 | 2019-05-16 |  | 2019-06-13 | 2019-08-07
[6 empty] | Owner Cmmt* | R2 | R1 | R2 |  | R1 | R1
| PE | OL1-2G30-2350 | Process Equipment Datasheet - 10-PK-2350 - Wet Air Oxidation Pkg |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2018-10-16 | 2019-04-12
[6 empty] | Issue Actual | 2018-10-16 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00180 | TPSK-LSPA1-T-PE-01328
[6 empty] | Return Date | 2019-02-04 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2389 | Process Equipment Datasheet - 10-EJ-2390 - Caustic Drain Sump Eductor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan |  | 2019-01-07
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2390 | Process Equipment Datasheet - 10-D-2390 - Caustic Drain Drum |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
[6 empty] | Revised Plan |  | 2018-09-28 | 2018-11-27
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-27 | 2019-04-17 | 2019-05-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00369 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01652
[6 empty] | Return Date |  | 2018-11-14 | 2019-01-14 | 2019-06-13 | 2019-06-03
[6 empty] | Owner Cmmt* |  | A3 | R1 | R1 | R1
| PE | OL1-2G30-2391 | Process Equipment Datasheet - 10-P-2390 - Caustic Drain Drum Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-07 | 2019-01-22
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00444 | TPSK-LSPA1-T-PE-00695
[6 empty] | Return Date | 2019-01-16 | 2019-03-05
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2392 | Process Equipment Datasheet - 10-D-2392 - Spent Caustic Drain Drum |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-25
[6 empty] | Revised Plan |  | 2018-09-28 | 2018-11-27
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-27 | 2019-04-17 | 2019-05-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00102 | TPSK-LSPA1-T-PE-00369 | TPSK-LSPA1-T-PE-01377 | TPSK-LSPA1-T-PE-01652
[6 empty] | Return Date |  | 2018-11-14 | 2019-01-14 | 2019-06-13 | 2019-06-03
[6 empty] | Owner Cmmt* |  | A3 | R1 | R1 | R1
| PE | OL1-2G30-2393 | Process Equipment Datasheet - 10-P-2392 - Spent Caustic Drain Drum Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-31 | 2019-01-07
[6 empty] | Issue Actual | 2018-10-31 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00252 | TPSK-LSPA1-T-PE-00598
[6 empty] | Return Date | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2394 | Process Equipment Datasheet - 10-EJ-2392 - Spent Caustic Drain Sump Eductor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan |  | 2019-01-07
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-28
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2405 | Process Equipment Datasheet - 10-D-2405 - Gas Dryer Feed KO Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-14 | 2018-12-13
[6 empty] | Issue Actual | 2018-11-14 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00315 | TPSK-LSPA1-T-PE-00480
[6 empty] | Return Date | 2018-12-10 | 2018-12-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2406 | Process Equipment Datasheet - 10-E-2405 - Gas Dryer Feed Chiller |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-30 | 2018-12-20
[6 empty] | Issue Actual | 2018-10-30 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00239 | TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2410 | Process Equipment Datasheet - 10-D-2410 A-B - Cracked Gas Dryer |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-07 | 2019-01-18
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-18 | 2019-03-05 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00678 | TPSK-LSPA1-T-PE-00980 | TPSK-LSPA1-T-PE-01310
[6 empty] | Return Date | 2018-12-27 | 2019-01-29 | 2019-03-13 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1 | R1 | R1
| PE | OL1-2G30-2411 | Process Equipment Datasheet - 10-D-2411 - Cracked Gas Mercury Adsorber |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-20 | 2019-01-08
[6 empty] | Issue Actual | 2018-11-20 | 2019-01-08 | 2019-03-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00339 | TPSK-LSPA1-T-PE-00610 | TPSK-LSPA1-T-PE-01089
[6 empty] | Return Date | 2018-12-13 | 2019-01-22 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2412 | Process Equipment Datasheet - 10-E-2412 - HP Depropanizer Feed Chiller |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-30 | 2018-12-20
[6 empty] | Issue Actual | 2018-10-30 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00239 | TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2413 | Process Equipment Datasheet - 10-E-2413 - HP Deprop Feed - Overhead Exchanger |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-31 | 2018-11-29
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2415 | Process Equipment Datasheet - 10-D-2415 - CG Liquid Dryer Feed Coalescer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-20 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-20 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00339 | TPSK-LSPA1-T-PE-00596
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | TP
| PE | OL1-2G30-2416 | Process Equipment Datasheet - 10-P-2415 A-B - CG Liquid Dryer Feed Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-07 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2420 | Process Equipment Datasheet - 10-D-2420 A-B - CG Liquid Dryer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-09 | 2019-01-08
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-08 | 2019-03-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00301 | TPSK-LSPA1-T-PE-00610 | TPSK-LSPA1-T-PE-01089
[6 empty] | Return Date | 2018-11-30 | 2019-01-22 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1 | CL
| PE | OL1-2G30-2430 | Process Equipment Datasheet - 10-E-2430 - Regen Gas Feed Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-22
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00574 | TPSK-LSPA1-T-PE-00696
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2432 | Process Equipment Datasheet - 10-E-2432 - Regen Gas Shp Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-22
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00574 | TPSK-LSPA1-T-PE-00696
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2434 | Process Equipment Datasheet - 10-E-2435 - Regen Gas Effluent Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-22
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00574 | TPSK-LSPA1-T-PE-00696
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2435 | Process Equipment Datasheet - 10-D-2435 - Regen Gas Separator |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-20 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00559 | TPSK-LSPA1-T-PE-00725
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2438 | Process Equipment Datasheet - 10-D-2440 - HP Depropanizer Reflux Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-01 | 2018-12-07
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-27 | 2018-12-18
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2439 | Process Equipment Datasheet - 10-E-2440 - HP Depropanizer Condenser |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-31 | 2018-11-29
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2440 | Process Equipment Datasheet - 10-T-2440 - HP Depropanizer |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-09-17 | 2018-10-15
[6 empty] | Issue Actual |  | 2018-09-17 | 2018-10-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date |  | 2018-10-03
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2441 | Process Equipment Datasheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-31 | 2018-11-29
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2442 | Process Equipment Datasheet - 10-E-2442 - HP Deprop Reflux Chiller No 1 |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-31 | 2018-11-29
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2443 | Process Equipment Datasheet - 10-P-2445 A-B - HP Deprop Reboiler Cond Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-04 | 2018-12-27
[6 empty] | Issue Actual | 2018-12-04 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00408 | TPSK-LSPA1-T-PE-00568
[6 empty] | Return Date | 2018-12-17 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2444 | Process Equipment Datasheet - 10-D-2445 - HP Deprop Reboiler Cond Pot |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-11 | 2018-12-27
[6 empty] | Issue Actual | 2018-12-11 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00474 | TPSK-LSPA1-T-PE-00563
[6 empty] | Return Date | 2018-12-21 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2445 | Process Equipment Datasheet - 10-E-2445 A-B - HP Depropanizer Reboilers |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-01 | 2018-12-07
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00267 | TPSK-LSPA1-T-PE-00436
[6 empty] | Return Date | 2018-11-26 | 2018-12-18
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2446 | Process Equipment Datasheet - 10-E-2446 - LP Depropanizer Feed Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-31 | 2018-11-29
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2450 | Process Equipment Datasheet - 10-T-2450 - LP Depropanizer |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-09-17 | 2018-10-15
[6 empty] | Issue Actual |  | 2018-09-17 | 2018-10-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00167
[6 empty] | Return Date |  | 2018-10-03
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2451 | Process Equipment Datasheet - 10-E-2450 - LP Depropanizer Condenser |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-31 | 2018-11-29
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00259 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2452 | Process Equipment Datasheet - 10-D-2450 - LP Depropanizer Reflux Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-01 | 2018-12-07
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00264 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-27 | 2018-12-18
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2453 | Process Equipment Datasheet - 10-P-2450 A-B - LP Depropanizer Reflux-Product Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-07 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00285 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date | 2018-12-27 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2455 | Process Equipment Datasheet - 10-E-2455 A-B - LP Depropanizer Reboilers |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-25 | 2018-12-20
[6 empty] | Issue Actual | 2018-10-25 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00228 | TPSK-LSPA1-T-PE-00523
[6 empty] | Return Date | 2018-11-14 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2456 | Process Equipment Datasheet - 10-D-2455 - LP Deprop Reboiler Cond Pot |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-11 | 2018-12-27
[6 empty] | Issue Actual | 2018-12-11 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00474 | TPSK-LSPA1-T-PE-00563
[6 empty] | Return Date | 2018-12-21 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2457 | Process Equipment Datasheet - 10-P-2455 A-B - LP Deprop Reboiler Cond Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-04 | 2018-12-27
[6 empty] | Issue Actual | 2018-12-04 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00408 | TPSK-LSPA1-T-PE-00568
[6 empty] | Return Date | 2018-12-17 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2460 | Process Equipment Datasheet - 10-D-2460 - C2 Hydrog Arsine Guard Bed |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-10 | 2019-01-16
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00453 | TPSK-LSPA1-T-PE-00660
[6 empty] | Return Date | 2019-01-16 | 2019-01-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2461 | Process Equipment Datasheet - 10-E-2460 - C2 Hydrog Feed Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-31 | 2018-11-29
[6 empty] | Issue Actual | 2018-10-31 | 2018-11-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00250 | TPSK-LSPA1-T-PE-00392
[6 empty] | Return Date | 2018-11-20 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2465 | Process Equipment Datasheet - 10-E-2465 - C2 Hydrog Feed Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-29 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-29 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391 | TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2470 | Process Equipment Datasheet - 10-R-2470 A-C - C2 Hydrog Reactor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-16 | 2019-02-06
[6 empty] | Revised Plan | 2018-11-09 | 2019-01-08
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00299 | TPSK-LSPA1-T-PE-00609
[6 empty] | Return Date | 2018-11-29 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2471 | Process Equipment Datasheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-29 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-29 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391 | TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2472 | Process Equipment Datasheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-29 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-29 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391 | TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2474 | Process Equipment Datasheet - 10-E-2474 - C2 Hydrog Aftercooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-29 | 2019-01-07
[6 empty] | Issue Actual | 2018-11-29 | 2019-01-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00391 | TPSK-LSPA1-T-PE-00602
[6 empty] | Return Date | 2018-12-13 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2480 | Process Equipment Datasheet - 10-D-2480 - CG Secondary Dryer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-28 | 2019-01-11
[6 empty] | Issue Actual | 2018-11-28 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00386 | TPSK-LSPA1-T-PE-00637
[6 empty] | Return Date | 2018-12-13 | 2019-01-31
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2500 | Process Equipment Datasheet - 10-E-2500 - Propylene Refrig Subcooler |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-12 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-12 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-09-28
[6 empty] | Owner Cmmt* |  | A2
| PE | OL1-2G30-2502 | Process Equipment Datasheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-11-05 | 2018-12-11
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00475
[6 empty] | Return Date |  | 2018-10-02 | 2018-11-26 | 2019-01-10
[6 empty] | Owner Cmmt* |  | A1 | A2 | A1
| PE | OL1-2G30-2503 | Process Equipment Datasheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-02 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A2
| PE | OL1-2G30-2504 | Process Equipment Datasheet - 10-D-2504 - Demeth Prefrac Feed Separator No 1 |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-24 | 2018-11-09
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07 | 2018-11-26
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2505 | Process Equipment Datasheet - 10-E2506 & 10-E-2508 - Demeth Prefrac Feed Cooler No 3 & No 4 |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05 | 2019-02-06
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-00811
[6 empty] | Return Date |  | 2018-10-02 |  | 2019-02-25
[6 empty] | Owner Cmmt* |  | A3 |  | R1
| PE | OL1-2G30-2506 | Process Equipment Datasheet - 10-D-2506 - Demeth Prefrac Feed Separator No 2 |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-24 | 2018-11-09
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09 | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303 | TPSK-LSPA1-T-PE-02040
[6 empty] | Return Date | 2018-11-07 | 2018-11-26 | 2019-07-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2508 | Process Equipment Datasheet - 10-D-2508 - Demeth Prefrac Feed Separator No 3 |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-24 | 2018-11-09
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00217 | TPSK-LSPA1-T-PE-00303
[6 empty] | Return Date | 2018-11-07 | 2018-11-26
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2510 | Process Equipment Datasheet - 10-T-2510 - 10-D-2510 - Demethanizer Prefractionator & Reflux Drum |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-11-09
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-11-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00092 | TPSK-LSPA1-T-PE-00306
[6 empty] | Return Date |  | 2018-10-24 | 2018-11-29
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G30-2511 | Process Equipment Datasheet - 10-E-2510 - Demeth Prefrac Condenser |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2515 | Process Equipment Datasheet - 10-E-2515 - Demeth Prefrac Reboiler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-24 | 2018-12-13
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-14 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2520 | Process Equipment Datasheet - 10-T-2520 - 10-D2520 - Residue Gas Rectifier & Reflux Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-16 | 2018-12-04
[6 empty] | Issue Actual | 2018-10-16 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00172 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-11-05 | 2018-12-17
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2521 | Process Equipment Datasheet - 10-E-2520 - Rectifier Condenser |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2525 | Process Equipment Datasheet - 10-D-2525 - Hydrogen Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-24 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-09 | 2018-12-18
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2526 | Process Equipment Datasheet - 10-E-2525 - Hydrogen Core Exchanger |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2531 | Process Equipment Datasheet - 10-E-2530 - Demeth Feed Cooler |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2540 | Process Equipment Datasheet - 10-T-2540 - 10-D-2540 - Demethanizer & Reflux Drum |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-11-09
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-11-09 | 2018-12-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00073 | TPSK-LSPA1-T-PE-00306 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date |  | 2018-10-24 | 2018-11-29 | 2018-12-17
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1
| PE | OL1-2G30-2541 | Process Equipment Datasheet - 10-E-2540 - Demethanizer Condenser |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A1
| PE | OL1-2G30-2545 | Process Equipment Datasheet - 10-E-2545 - Demethanizer Reboiler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-24 | 2018-12-13
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-14 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2546 | Process Equipment Datasheet - 10-E-2546 - Demethanizer Bottoms Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-24 | 2018-12-13
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-14 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2548 | Process Equipment Datasheet - 10-E-2548 - Demethanizer Bottoms Vaporizer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-24 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216 | TPSK-LSPA1-T-PE-00464
[6 empty] | Return Date | 2018-11-14 | 2018-12-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2550 | Process Equipment Datasheet - 10-TX-2550 - 10-C-2550 - Residue Gas Expander - Recompressor |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
[6 empty] | Revised Plan |  | 2018-09-03 | 2018-10-01
[6 empty] | Issue Actual |  | 2018-09-03 | 2018-10-01
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00031 | TPSK-LSPA1-T-PE-00114
[6 empty] | Return Date |  | 2018-09-28 | 2018-10-24
[6 empty] | Owner Cmmt* |  | A3 | R1
| PE | OL1-2G30-2551 | Process Equipment Datasheet - 10-D-2550 - Expander Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-24 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-11-09 | 2019-01-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2555 | Process Equipment Datasheet - 10-D-2555 - Expander Discharge Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-24 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00430
[6 empty] | Return Date | 2018-11-09 | 2018-12-18
[6 empty] | Owner Cmmt* | R1 | em
| PE | OL1-2G30-2560 | Process Equipment Datasheet - 10-PK-2560 - PSA Unit |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2018-10-18 | 2018-12-20
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-20 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00190 | TPSK-LSPA1-T-PE-00530 | TPSK-LSPA1-T-PE-01485
[6 empty] | Return Date | 2018-11-05 | 2019-01-14 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1 | CL
| PE | OL1-2G30-2570 | Process Equipment Datasheet - 10-T-2570 - Deethanizer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-18 | 2018-12-04
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-04 | 2018-12-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00191 | TPSK-LSPA1-T-PE-00407 | TPSK-LSPA1-T-PE-00538
[6 empty] | Return Date | 2018-11-05 | 2018-12-17 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2571 | Process Equipment Data Sheet - 10-E-2570 Deethanizer Condenser |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-02 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A3 | A2
| PE | OL1-2G30-2572 | Process Equipment Datasheet - 10-D-2570 - Deethanizer Reflux Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-25 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-25 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00227 | TPSK-LSPA1-T-PE-00446
[6 empty] | Return Date | 2018-12-05 | 2018-12-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2573 | Process Equipment Datasheet - 10-P-2570 A-B - Deethanizer Reflux Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-20 | 2018-12-13
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-10 | 2018-12-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2574 | Process Equipment Datasheet - 10-D-2575 - Deethanizer Reboiler Cond Pot |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-11 | 2018-12-27
[6 empty] | Issue Actual | 2018-12-11 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00474 | TPSK-LSPA1-T-PE-00563
[6 empty] | Return Date | 2018-12-21 | 2019-01-14
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2575 | Process Equipment Datasheet - 10-E-2575 - Deethanizer Reboiler |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-27 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2576 | Process Equipment Datasheet - 10-E-2576 - Deethanizer Bottoms Cooler |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-27 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2577 | Process Equipment Datasheet - 10-P-2575 A-B - Deethanizer Reboiler Cond Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-04 | 2018-12-27
[6 empty] | Issue Actual | 2018-12-04 | 2018-12-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00408 | TPSK-LSPA1-T-PE-00568
[6 empty] | Return Date | 2018-12-17 | 2019-01-14
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2580 | Process Equipment Datasheet - 10-T-2580 - C2 Tower |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-15 | 2018-12-04
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00162 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-10-31 | 2018-12-17
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2582 | Process Equipment Datasheet - 10-E-2582 - C2 Tower Reflux Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-01 | 2018-12-13
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00265 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-20 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2585 | Process Equipment Datasheet - 10-E-2585 - C2 Tower Bottoms Reboiler |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05 | 2019-04-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date |  | 2018-10-02 |  | 2019-06-07
[6 empty] | Owner Cmmt* |  | A1 |  | R1
| PE | OL1-2G30-2586 | Process Equipment Datasheet - 10-P-2586 A-B - Ethane Recycle Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-20 | 2018-12-13
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481
[6 empty] | Return Date | 2018-12-10 | 2018-12-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2587 | Process Equipment Datasheet - 10-E-2587 - C2 Tower Side Reboiler |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05 | 2019-04-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date |  | 2018-10-02 |  | 2019-06-07
[6 empty] | Owner Cmmt* |  | A1 |  | R1
| PE | OL1-2G30-2591 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler (FOR NEXT REVISION SEE OL1-2G30-2859) |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-24
[6 empty] | Issue Actual | 2018-10-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00216
[6 empty] | Return Date | 2018-11-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2600 | Process Equipment Datasheet - 10-D-2600 A-B - C3 Hydrog Guard Adsorber |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-07 | 2019-01-10
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-10 | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00618 | TPSK-LSPA1-T-PE-01049
[6 empty] | Return Date | 2018-12-27 | 2019-01-24 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2610 | Process Equipment Datasheet - 10-D-2610 - C3 Hydrog Arsine Guard Bed |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-21 | 2019-01-10
[6 empty] | Issue Actual | 2018-11-21 | 2019-01-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00345 | TPSK-LSPA1-T-PE-00618
[6 empty] | Return Date | 2018-12-13 | 2019-01-24
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2620 | Process Equipment Data Sheet - 10-R-2620 - C3 Hydrog Reactor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-16 | 2019-02-06
[6 empty] | Revised Plan | 2019-01-03 | 2019-02-22
[6 empty] | Issue Actual | 2019-01-03 | 2019-02-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00583 | TPSK-LSPA1-T-PE-00910
[6 empty] | Return Date | 2019-01-16 | 2019-03-19
[6 empty] | Owner Cmmt* | R2 | 03
| PE | OL1-2G30-2621 | Process Equipment Datasheet - 10-E-2620 - C3 Hydrog Aftercooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-10 | 2019-03-04
[6 empty] | Issue Actual | 2019-01-10 | 2019-03-04 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00615 | TPSK-LSPA1-T-PE-00966 | TPSK-LSPA1-T-PE-01609
[6 empty] | Return Date | 2019-01-24 | 2019-03-13 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2622 | Process Equipment Datasheet - 10-D-2620 - C3 Hydrog Recycle Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-01-10 | 2019-03-12
[6 empty] | Issue Actual | 2019-01-10 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE-01023
[6 empty] | Return Date | 2019-01-24 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2623 | Process Equipment Data Sheet - 10-P-2620 - C3 Hydrog Recycle Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-07 | 2019-03-04
[6 empty] | Issue Actual | 2019-01-07 | 2019-03-04 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00587 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01739
[6 empty] | Return Date | 2019-01-31 | 2019-03-21 | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2624 | Process Equipment Datasheet - 10-X-2620 - C3 Hydrog Static Mixer |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2019-01-16 | 2019-03-04
[6 empty] | Issue Actual | 2019-01-16 | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00664 | TPSK-LSPA1-T-PE-00968
[6 empty] | Return Date | 2019-01-31 | 2019-03-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2630 | Process Equipment Datasheet - 10-T-2630 - Secondary Deethanizer |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-09-17 | 2018-10-15
[6 empty] | Issue Actual |  | 2018-09-17 | 2018-10-15 | 2018-12-04
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00169 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date |  | 2018-10-03 |  | 2018-12-17
[6 empty] | Owner Cmmt* |  | A3 |  | R1
| PE | OL1-2G30-2631 | Process Equipment Datasheet - 10-E-2630 - Secondary Deeth Condenser |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A2
| PE | OL1-2G30-2632 | Process Equipment Datasheet - 10-D-2630 - Secondary Deeth Reflux Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-07 | 2019-01-11
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00287 | TPSK-LSPA1-T-PE-00633
[6 empty] | Return Date | 2019-01-11 | 2019-01-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2633 | Process Equipment Datasheet - 10-P-2630 A-B - Secondary Deeth Reflux Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-06 | 2019-02-12
[6 empty] | Issue Actual | 2018-11-06 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277 | TPSK-LSPA1-T-PE-00844
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2635 | Process Equipment Datasheet - 10-E-2635 - Secondary Deeth Reboiler |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-11-05 | 2018-12-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00438
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26 | 2018-12-27
[6 empty] | Owner Cmmt* |  | A2 | A2 | A1
| PE | OL1-2G30-2636 | Process Equipment Datasheet - 10-E-2636 - Secondary Deeth Bottoms Cooler |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00074 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2640 | Process Equipment Datasheet - 10-T-2640 - C3 Tower |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2018-10-22 | 2018-12-04
[6 empty] | Issue Actual | 2018-10-22 | 2018-12-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00201 | TPSK-LSPA1-T-PE-00407
[6 empty] | Return Date | 2018-11-05 | 2018-12-17
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2644 | Process Equipment Datasheet - 10-D-2645 - C3 Tower Reboiler Cond Pot |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-01-18 | 2019-02-04
[6 empty] | Issue Actual | 2019-01-18 | 2019-02-04 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00677 | TPSK-LSPA1-T-PE-00796 | TPSK-LSPA1-T-PE-00938
[6 empty] | Return Date | 2019-01-31 | 2019-02-21 | 2019-03-14
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-2645 | Process Equipment Datasheet - 10-E-2645 A-B - C3 Tower Reboilers |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-12 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-12 | 2018-11-05 | 2018-12-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00272 | TPSK-LSPA1-T-PE-00438
[6 empty] | Return Date |  | 2018-10-01 | 2018-11-26 | 2018-11-27
[6 empty] | Owner Cmmt* |  | A1 | A2 | A1
| PE | OL1-2G30-2646 | Process Equipment Datasheet - 10-P-2646 A-B - Propane Recycle Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-06 | 2019-02-12
[6 empty] | Issue Actual | 2018-11-06 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277 | TPSK-LSPA1-T-PE-00844
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2647 | Process Equipment Datasheet - 10-P-2647 - HP Propylene - Off Spec Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-09 | 2019-01-14
[6 empty] | Issue Actual | 2018-11-09 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00302 | TPSK-LSPA1-T-PE-00649
[6 empty] | Return Date | 2019-02-04 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2660 | Process Equipment Datasheet - 10-T-2660 - Debutanizer |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-01-21 |  | 2019-02-25
[6 empty] | Revised Plan |  | 2018-09-17 | 2018-10-15
[6 empty] | Issue Actual |  | 2018-09-17 | 2018-10-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00053 | TPSK-LSPA1-T-PE-00169
[6 empty] | Return Date |  | 2018-10-03
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2661 | Process Equipment Datasheet - 10-E-2660 - Debutanizer Condenser |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-27 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-27 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00094 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2662 | Process Equipment Datasheet - 10-D-2660 - Debutanizer Reflux Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-07 | 2019-01-16
[6 empty] | Issue Actual | 2018-11-07 | 2019-01-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00287 | TPSK-LSPA1-T-PE-00660
[6 empty] | Return Date | 2019-01-11 | 2019-01-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2663 | Process Equipment Datasheet - 10-P-2660 A-B - Debutanizer Reflux - Product Pumps |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-20 | 2018-12-13
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-13 | 2019-01-14 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-01383
[6 empty] | Return Date | 2018-12-10 | 2018-12-27 | 2019-01-28 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R1 | R1 | R1
| PE | OL1-2G30-2664 | Process Equipment Datasheet - 10-F-2666 A-B - C5 - Pygas Feed Filters |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2019-02-20 | 2019-03-12
[6 empty] | Issue Actual | 2019-02-20 | 2019-03-12 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-0900 | TPSK-LSPA1-T-PE-01024 | TPSK-LSPA1-T-PE-01601
[6 empty] | Return Date | 2019-02-26 | 2019-03-29 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R2 | R2
| PE | OL1-2G30-2665 | Process Equipment Datasheet - 10-E-2665 A-B - Debutanizer Reboilers |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-28 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00101 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1
| PE | OL1-2G30-2666 | Process Equipment Datasheet - 10-E-2666 - Debutanizer Bottoms Cooler |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-28 | 2018-11-27
[6 empty] | Issue Actual |  | 2018-09-28 | 2018-11-27 | 2019-01-23 | 2019-04-18
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00112 | TPSK-LSPA1-T-PE-00370 | TPSK-LSPA1-T-PE-00711 | TPSK-LSPA1-T-PE-01387
[6 empty] | Return Date |  | 2018-10-12 | 2018-12-10 | 2019-02-11 | 2019-05-24
[6 empty] | Owner Cmmt* |  | A3 | A1 | A2 | R1
| PE | OL1-2G30-2667 | Process Equipment Datasheet - 10-D-2666 - C5 - Pygas Surge Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-02-01 | 2019-03-21
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-21 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01106 | TPSK-LSPA1-T-PE-01600
[6 empty] | Return Date | 2019-02-21 | 2019-04-10 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2668 | Process Equipment Datasheet - 10-P-2666 A-B - C5 - Pygas Pumps |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-11 | 2019-03-12
[6 empty] | Issue Actual | 2019-02-11 | 2019-03-12 | 2019-04-15 | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-01025 | TPSK-LSPA1-T-PE-01339 | TPSK-LSPA1-T-PE-01739
[6 empty] | Return Date | 2019-02-25 | 2019-03-29 |  | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1 |  | R1
| PE | OL1-2G30-2669 | Process Equipment Datasheet - 10-P-2665 A-B - Debutanizer Bottoms Pumps |  | Class 2 | Purpose** | IFR | IFD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2018-11-27 | 2019-01-14 | 2019-03-20
[6 empty] | Issue Actual | 2018-11-27 | 2019-01-14 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00371 | TPSK-LSPA1-T-PE-00648 | TPSK-LSPA1-T-PE-01099
[6 empty] | Return Date | 2018-12-13 | 2019-01-28 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2700 | Process Equipment Datasheet - 10-R-2700 A-B - GHU-1 Reactor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-16 | 2019-02-06
[6 empty] | Revised Plan | 2019-01-16 | 2019-03-18
[6 empty] | Issue Actual | 2019-01-16 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00659 | TPSK-LSPA1-T-PE-01081
[6 empty] | Return Date | 2019-02-11 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2701 | Process Equipment Datasheet - 10-E-2701 - GHU-1 Feed - Effluent Exchangers |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-23 | 2019-03-21
[6 empty] | Issue Actual | 2019-01-23 | 2019-03-21 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00710 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2702 | Process Equipment Datasheet - 10-E-2702 - GHU-1 Start-up Heater |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-20 | 2019-04-05
[6 empty] | Issue Actual | 2019-02-20 | 2019-04-05 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00899 | TPSK-LSPA1-T-PE-01250 | TPSK-LSPA1-T-PE-01371
[6 empty] | Return Date | 2019-03-19 | 2019-05-16 | 2019-06-07
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2703 | Process Equipment Datasheet - 10-E-2705 - GHU-1 Recycle Cooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-25 | 2019-03-29
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-29 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-15 | 2019-06-07 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2704 | Process Equipment Datasheet - 10-P-2705 A-B - GHU-1 Recycle Pump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-11 | 2019-03-12
[6 empty] | Issue Actual | 2019-02-11 | 2019-03-12 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-01025 | TPSK-LSPA1-T-PE-01739
[6 empty] | Return Date | 2019-02-25 | 2019-03-29 | 2019-06-13
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2705 | Process Equipment Datasheet - 10-D-2705 - GHU-1 Hot Separator |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-02-01 | 2019-03-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01188
[6 empty] | Return Date | 2019-02-21 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2706 | Process Equipment Datasheet - 10-D-2706 - GHU-1 Cold Separator |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-02-01 | 2019-03-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01188
[6 empty] | Return Date | 2019-02-21 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2707 | Process Equipment Datasheet - 10-E-2706 - GHU-1 Cooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-25 | 2019-03-29
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-29 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-15 | 2019-05-16 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2710 | Process Equipment Datasheet - 10-T-2710 Depentanizer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-01-22 | 2019-03-18
[6 empty] | Issue Actual | 2019-01-22 | 2019-03-18 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00688 | TPSK-LSPA1-T-PE-01082 | TPSK-LSPA1-T-PE-01708
[6 empty] | Return Date | 2019-02-15 | 2019-04-02 | 2019-06-12
[6 empty] | Owner Cmmt* | R2 | R1 | CL
| PE | OL1-2G30-2711 | Process Equipment Datasheet - 10-E-2710 - Depentanizer Condenser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-25 | 2019-03-21
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-21 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-15 | 2019-04-10 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2712 | Process Equipment Datasheet - 10-D-2710 - Depentanizer Reflux Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-02-01 | 2019-03-21
[6 empty] | Issue Actual | 2019-02-01 | 2019-03-21 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01106 | TPSK-LSPA1-T-PE-01600
[6 empty] | Return Date | 2019-02-21 | 2019-04-10 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2713 | Process Equipment Datasheet - 10-P-2710 A-B - Depentanizer Reflux Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-11 | 2019-03-12
[6 empty] | Issue Actual | 2019-02-11 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00834 | TPSK-LSPA1-T-PE-01025
[6 empty] | Return Date | 2019-02-25 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2714 | Process Equipment Datasheet - 10-P-2714 A-B - C5 Cut Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-12 | 2019-03-18
[6 empty] | Issue Actual | 2019-02-12 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-01083
[6 empty] | Return Date | 2019-02-25 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2715 | Process Equipment Datasheet - 10-E-2715 A-B - Depentanizer Reboiler |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-25 | 2019-03-21
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-21 | 2019-04-29 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00724 | TPSK-LSPA1-T-PE-01107 | TPSK-LSPA1-T-PE-01507 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2716 | Process Equipment Datasheet - 10-E-2714 - C5 Cut Cooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-25 | 2019-03-29
[6 empty] | Issue Actual | 2019-01-25 | 2019-03-29 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00720 | TPSK-LSPA1-T-PE-01187 | TPSK-LSPA1-T-PE-01990
[6 empty] | Return Date | 2019-02-15 | 2019-05-16 | 2019-07-17
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2717 | Process Equipment Datasheet - 10-PK-2720 - Rerun Tower Liquid Ring Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2019-02-20 | 2019-04-18
[6 empty] | Issue Actual | 2019-02-20 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00902 | TPSK-LSPA1-T-PE-01403
[6 empty] | Return Date | 2019-03-19 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2718 | Process Equipment Datasheet - 10-D-2720 - Rerun Tower Reflux Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-15
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-15 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01342 | TPSK-LSPA1-T-PE-02056
[6 empty] | Return Date | 2019-02-21 |  | 2019-08-05
[6 empty] | Owner Cmmt* | R2 |  | R1
| PE | OL1-2G30-2719 | Process Equipment Datasheet - 10-P-2720 A-B - Rerun Tower Reflux - Product Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-12 | 2019-04-18
[6 empty] | Issue Actual | 2019-02-12 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-01404
[6 empty] | Return Date | 2019-02-25 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2720 | Process Equipment Datasheet - 10-T-2720 - Rerun Tower |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-01-22 | 2019-04-15
[6 empty] | Issue Actual | 2019-01-22 | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00669 | TPSK-LSPA1-T-PE-01340
[6 empty] | Return Date | 2019-02-15 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2721 | Process Equipment Datasheet - 10-E-2720 - Rerun Tower Condenser |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-11 | 2019-04-15
[6 empty] | Issue Actual | 2019-02-11 | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01341
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-2723 | Process Equipment Datasheet - 10-E-2724 - Wash Oil Condenser |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-11 | 2019-04-16
[6 empty] | Issue Actual | 2019-02-11 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01353
[6 empty] | Return Date | 2019-02-25 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2724 | Process Equipment Datasheet - 10-D-2724 - Wash Oil Degrassing Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-16
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00781 | TPSK-LSPA1-T-PE-01354
[6 empty] | Return Date | 2019-02-21 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2725 | Process Equipment Datasheet - 10-E-2725 A-B - Rerun Tower Reboiler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-11 | 2019-04-18
[6 empty] | Issue Actual | 2019-02-11 | 2019-04-18 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01405 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-25 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2726 | Process Equipment Datasheet - 10-P-2726 A-B - Pygas Fuel Oil Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-23
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00873 | TPSK-LSPA1-T-PE-01432
[6 empty] | Return Date | 2019-02-26 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | Re
| PE | OL1-2G30-2727 | Process Equipment Datasheet - 10-E-2726 - Pygas Fuel Oil Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-11 | 2019-04-23
[6 empty] | Issue Actual | 2019-02-11 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00835 | TPSK-LSPA1-T-PE-01431
[6 empty] | Return Date | 2019-02-25 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2728 | Process Equipment Datasheet - 10-P-2724 A-B - Recycle Wash Oil Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-12 | 2019-04-24
[6 empty] | Issue Actual | 2019-02-12 | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00841 | TPSK-LSPA1-T-PE-01458
[6 empty] | Return Date | 2019-02-25 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2729 | Process Equipment Datasheet - 10-P-2721 A-B - Wash Oil Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00873 | TPSK-LSPA1-T-PE-01458
[6 empty] | Return Date | 2019-02-26 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2730 | Process Equipment Datasheet - 10-E-2730 - Regen Gas Electric Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-03-18 | 2019-05-07
[6 empty] | Issue Actual | 2019-03-18 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01070 | TPSK-LSPA1-T-PE-01586
[6 empty] | Return Date | 2019-04-02 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2735 | Process Equipment Datasheet - 10-D-2735 - Regen Hydrog Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-03-14 | 2019-04-09
[6 empty] | Issue Actual | 2019-03-14 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01049 | TPSK-LSPA1-T-PE-01277
[6 empty] | Return Date | 2019-04-02 | 2019-05-16
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2750 | Process Equipment Datasheet - 10-D-2750 - C4-C5 Hydrog Surge Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-02-04 | 2019-03-12
[6 empty] | Issue Actual | 2019-02-04 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00794 | TPSK-LSPA1-T-PE-01023
[6 empty] | Return Date | 2019-02-21 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2751 | Process Equipment Datasheet - 10-P-2750 A-B - C4 - C5 Hydrog Feed Pump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-04 | 2019-03-04
[6 empty] | Issue Actual | 2019-02-04 | 2019-03-04 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00788 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01610
[6 empty] | Return Date | 2019-02-15 | 2019-03-21 | 2019-06-19
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-2755 | Process Equipment Datasheet - 10-E-2755 - C4 - C5 Hydrog Start-up Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-26 | 2019-03-26
[6 empty] | Issue Actual | 2019-02-26 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00924 | TPSK-LSPA1-T-PE-01148
[6 empty] | Return Date | 2019-03-19 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2760 | Process Equipment Datasheet - 10-R-2760 - C4-C5 Hydrog Reactor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-16 | 2019-02-06
[6 empty] | Revised Plan | 2019-01-16 | 2019-03-12
[6 empty] | Issue Actual | 2019-01-16 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00659 | TPSK-LSPA1-T-PE-01030
[6 empty] | Return Date | 2019-02-11 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2762 | Process Equipment Datasheet - 10-D-2760 - C4-C5 Hydrog Recycle Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-02-04 | 2019-03-12
[6 empty] | Issue Actual | 2019-02-04 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00794 | TPSK-LSPA1-T-PE-01023
[6 empty] | Return Date | 2019-02-21 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2763 | Process Equipment Datasheet - 10-E-2760 - C4-C5 Hydrog Vent Condenser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-04 | 2019-03-12
[6 empty] | Issue Actual | 2019-02-04 | 2019-03-12 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00793 | TPSK-LSPA1-T-PE-01027 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-21 | 2019-03-29 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2764 | Process Equipment Datasheet - 10-P-2760 A-B - C4 - C5 Hydrog Recycle Pump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-04 | 2019-03-04
[6 empty] | Issue Actual | 2019-02-04 | 2019-03-04 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00788 | TPSK-LSPA1-T-PE-00963 | TPSK-LSPA1-T-PE-01739
[6 empty] | Return Date | 2019-02-15 | 2019-03-21 | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2765 | Process Equipment Datasheet - 10-E-2765 - C4-C5 Hydrog Recycle Cooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-04 | 2019-03-12
[6 empty] | Issue Actual | 2019-02-04 | 2019-03-12 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00793 | TPSK-LSPA1-T-PE-01027 | TPSK-LSPA1-T-PE-01604
[6 empty] | Return Date | 2019-02-21 | 2019-03-29 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-2767 | Process Equipment Datasheet - 10-D-2765 - C4 - C5 Hydrog Coalescer Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-02-20 | 2019-03-26
[6 empty] | Issue Actual | 2019-02-20 | 2019-03-26 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--00901 | TPSK-LSPA1-T-PE-01145 | TPSK-LSPA1-T-PE-01600
[6 empty] | Return Date | 2019-03-19 | 2019-05-16 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | Re
| PE | OL1-2G30-2790 | Process Equipment Datasheet - 10-D-2790 - Light Oil Drain Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-13 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-13 | 2019-01-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00482 | TPSK-LSPA1-T-PE-00721
[6 empty] | Return Date | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2791 | Process Equipment Datasheet - 10-P-2790 - Light Oil Drain Drum Pump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-13 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-13 | 2019-01-25 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00496 | TPSK-LSPA1-T-PE-00722 | TPSK-LSPA1-T-PE-01434
[6 empty] | Return Date | 2019-01-22 | 2019-02-11 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R2
| PE | OL1-2G30-2792 | Process Equipment Datasheet - 10-EJ-2790 - Light Oil Drain Sump Eductor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan |  | 2019-01-07
[6 empty] | Issue Actual |  | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00595
[6 empty] | Return Date |  | 2019-01-22
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G30-2795 | Data Sheet For Vacuum Units -Multistage Ejectors- Rerun Tower Vacuum Package PK-2720 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02333
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-2800 | Process Equipment Data Sheet - 10-C-2800 - Propylene Refrig Compressor |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
[6 empty] | Revised Plan |  | 2018-08-23 | 2018-09-18
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-09-18
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date |  | 2018-09-11
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2801 | Process Equipment Datasheet - 10-P-2805 A-B - Propylene Product Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-06 | 2019-01-14
[6 empty] | Issue Actual | 2018-11-06 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00277 | TPSK-LSPA1-T-PE-00649
[6 empty] | Return Date | 2019-02-04 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2805 | Process Equipment Datasheet - 10-D-2805 - C3R Surge Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-24 | 2018-11-21
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00348
[6 empty] | Return Date | 2018-11-09 | 2018-12-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2806 | Process Equipment Datasheet - 10-E-2805 A-B - C3 Refrig Condensers |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-10-01 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-10-01 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A3 | A1
| PE | OL1-2G30-2807 | Process Equipment Datasheet - 10-E-2807 - C3 Chiller No 1 |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-10-01 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-10-01 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A2
| PE | OL1-2G30-2809 | Process Equipment Datasheet - 10-E-2809 - C3 Chiller No 2 |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-10-01 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-10-01 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00273
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1
| PE | OL1-2G30-2810 | Process Equipment Datasheet - 10-D-2810 - C3R 1st Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-08 | 2018-11-21
[6 empty] | Issue Actual | 2018-10-08 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2815 | Process Equipment Datasheet - 10-D-2815 - C3R Drain Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-07 | 2019-01-11
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-00633
[6 empty] | Return Date | 2018-12-27 | 2019-01-24
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2816 | Process Equipment Datasheet - 10-P-2815 - Propylene Refrig Recovery Pump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-20 | 2018-12-13
[6 empty] | Issue Actual | 2018-11-20 | 2018-12-13 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00340 | TPSK-LSPA1-T-PE-00481 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-10 | 2018-12-27 | 2019-01-28
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-2820 | Process Equipment Datasheet - 10-D-2820 - C3R 2nd Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-08 | 2018-11-21
[6 empty] | Issue Actual | 2018-10-08 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2830 | Process Equipment Datasheet - 10-D-2830 - C3R 3rd Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-08 | 2018-11-21
[6 empty] | Issue Actual | 2018-10-08 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2840 | Process Equipment Datasheet - 10-D-2840 - C3R 4th Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-08 | 2018-11-21
[6 empty] | Issue Actual | 2018-10-08 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00144 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-05 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2850 | Process Equipment Data Sheet - 10-C-2850 - Ethylene Refrig Compressor |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-12-07 |  | 2019-01-02
[6 empty] | Revised Plan |  | 2018-08-23 | 2018-09-18
[6 empty] | Issue Actual |  | 2018-08-23 | 2018-09-18
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00025 | TPSK-LSPA1-T-PE-00055
[6 empty] | Return Date |  | 2018-09-11
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2852 | Process Equipment Datasheet - 10-E-2852 - C2R Desuperheater No 1 |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-10-01 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-10-01 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A2
| PE | OL1-2G30-2853 | Process Equipment Datasheet - 10-E-2853 - C2R Desuperheater No 2 |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-10-01 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-10-01 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00113 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-12 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A2
| PE | OL1-2G30-2854 | Process Equipment Datasheet - 10-D-2855 - C2R Surge Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-24 | 2019-01-10
[6 empty] | Issue Actual | 2018-10-24 | 2019-01-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00621
[6 empty] | Return Date | 2018-11-09 | 2019-01-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2855 | Process Equipment Datasheet - 10-P-2855 A-B - Ethylene Product Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-11-28 | 2019-01-14
[6 empty] | Issue Actual | 2018-11-28 | 2019-01-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00379 | TPSK-LSPA1-T-PE-00648
[6 empty] | Return Date | 2018-12-13 | 2019-01-28
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2856 | Process Equipment Datasheet - 10-E-2855 - C2R Condenser |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-12 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-12 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00039 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-09-28 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A2 | A1
| PE | OL1-2G30-2857 | Process Equipment Datasheet - 10-E-2857 - HP Ethylene Product Vaporizer |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-12 | 2018-11-05
[6 empty] | Issue Actual |  | 2018-09-12 | 2018-11-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00041 | TPSK-LSPA1-T-PE-00272
[6 empty] | Return Date |  | 2018-10-01 | 2018-11-26
[6 empty] | Owner Cmmt* |  | A1 | A1
| PE | OL1-2G30-2858 | Process Equipment Datasheet - 10-E-2858 - HP Ethylene Product Superheater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-24 | 2018-12-13
[6 empty] | Issue Actual | 2018-10-24 | 2018-12-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00223 | TPSK-LSPA1-T-PE-00492
[6 empty] | Return Date | 2018-11-14 | 2019-01-22
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2859 | Process Equipment Datasheet - 10-E-2856 - Ethylene Product Subcooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. |  | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan |  | 2018-12-13
[6 empty] | Issue Actual |  | 2018-12-13 | 2019-01-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00492 | TPSK-LSPA1-T-PE-00711
[6 empty] | Return Date |  | 2019-01-22 | 2019-02-11
[6 empty] | Owner Cmmt* |  | R1 | R1
| PE | OL1-2G30-2860 | Process Equipment Datasheet - 10-D-2860 - C2R 1st Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-23 | 2019-02-12
[6 empty] | Issue Actual | 2018-10-23 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208 | TPSK-LSPA1-T-PE-00845
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2865 | Process Equipment Datasheet - 10-D-2865 - C2R Drain Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-07 | 2019-01-11
[6 empty] | Issue Actual | 2018-12-07 | 2019-01-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00445 | TPSK-LSPA1-T-PE-00633
[6 empty] | Return Date | 2019-01-10 | 2019-01-24
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2870 | Process Equipment Datasheet - 10-D-2870 - C2R 2nd Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-24 | 2018-11-21
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00218 | TPSK-LSPA1-T-PE-00349
[6 empty] | Return Date | 2018-11-09 | 2018-12-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2880 | Process Equipment Datasheet - 10-D-2880 - C2R 3rd Stage Suction Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-23 | 2019-02-12
[6 empty] | Issue Actual | 2018-10-23 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00208 | TPSK-LSPA1-T-PE-00845
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | TP
| PE | OL1-2G30-2882 | Process Equipment Datasheet - 10-E-2882 - LP Ethylene Product Cooler No 1 |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2884 | Process Equipment Datasheet - 10-E-2884 - LP Ethylene Product Cooler No 2 |  |  | Purpose** | IFR | IFA | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan |  | 2018-09-11 | 2018-10-05
[6 empty] | Issue Actual |  | 2018-09-11 | 2018-10-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00036 | TPSK-LSPA1-T-PE-00131
[6 empty] | Return Date |  | 2018-10-02
[6 empty] | Owner Cmmt* |  | A3
| PE | OL1-2G30-2900 | Process Equipment Datasheet - 10-PK-2900 - pH Ctrl - Corrosion Inhibitor Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-20 | 2019-02-01
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-01 | 2019-03-21 | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00532 | TPSK-LSPA1-T-PE-00780 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02284
[6 empty] | Return Date | 2019-01-28 | 2019-02-28 | 2019-04-10 | 2019-09-05
[6 empty] | Owner Cmmt* | R1 | R2 | R1 | R2
| PE | OL1-2G30-2902 | Process Equipment Datasheet - 10-PK-2902 - Emulsion Breaker Injection Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-20 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-21 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-10 | 2019-08-16
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R2
| PE | OL1-2G30-2904 | Process Equipment Datasheet - 10-PK-2904 - Process Water Stripper Chem Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-20 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-21 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-10 | 2019-08-16
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R2
| PE | OL1-2G30-2906 | Process Equipment Datasheet - 10-PK-2906 - DSG Anti-Foulant Injection Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-20 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-21 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-10 | 2019-08-16
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R2
| PE | OL1-2G30-2910 | Process Equipment Datasheet - 10-TK-2910 - Wash Oil Day Tank |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-12-27 | 2019-01-29
[6 empty] | Issue Actual | 2018-12-27 | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00561 | TPSK-LSPA1-T-PE-00760
[6 empty] | Return Date | 2019-01-28 | 2019-02-25
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2911 | Process Equipment Datasheet - 10-P-2910 - Wash Oil Injection Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-10 | 2019-02-27
[6 empty] | Issue Actual | 2019-01-10 | 2019-02-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00613 | TPSK-LSPA1-T-PE-00939
[6 empty] | Return Date | 2019-02-04 | 2019-03-21
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2912 | Process Equipment Datasheet - 10-PK-2912 - Caustic Tower Anti-Foulant Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-20 | 2019-02-01
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-01 | 2019-03-21 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00780 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-02-28 | 2019-04-10 | 2019-08-16
[6 empty] | Owner Cmmt* | R2 | R1 | R1 | R2
| PE | OL1-2G30-2914 | Process Equipment Datasheet - 10-PK-2914 - Neutralization Injection Pkg |  | Class 2 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-16 | 2019-04-12
[6 empty] | Issue Actual | 2018-10-16 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00181 | TPSK-LSPA1-T-PE-01329
[6 empty] | Return Date | 2019-02-04 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-2920 | Process Equipment Datasheet - 10-PK-2920 - Polymerization Inhibitor Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E | F
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-20 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-21 | 2019-05-17 | 2019-07-09 | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01686 | TPSK-LSPA1-T-PE-02099 | TPSK-LSPA1-T-PE-02284
[6 empty] | Return Date | 2019-01-22 | 2019-02-11 | 2019-04-10 | 2019-06-13 | 2019-08-08 | 2019-09-05
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R2 | R2 | R2
| PE | OL1-2G30-2922 | Process Equipment Datasheet - 10-PK-2922 - CO Injection Pkg |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-20 | 2019-01-16
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00560 | TPSK-LSPA1-T-PE-00656
[6 empty] | Return Date | 2019-01-14 | 2019-01-31
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2931 | Process Equipment Datasheet - 10-PK-2931 - Propanol Injection Pkg |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2019-01-22 | 2019-02-12
[6 empty] | Issue Actual | 2019-01-22 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00689 | TPSK-LSPA1-T-PE-00846
[6 empty] | Return Date | 2019-02-11 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2932 | Process Equipment Datasheet - 10-D-2930 - Methanol Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-01-14 | 2019-02-04
[6 empty] | Issue Actual | 2019-01-14 | 2019-02-04 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00644 | TPSK-LSPA1-T-PE-00796 | TPSK-LSPA1-T-PE-01162
[6 empty] | Return Date | 2019-01-31 | 2019-02-21 | 2019-05-16
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-2934 | Process Equipment Datasheet - 10-P-2930 - Methanol Injection Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-14 | 2019-02-12
[6 empty] | Issue Actual | 2019-01-14 | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00645 | TPSK-LSPA1-T-PE-00844
[6 empty] | Return Date | 2019-02-04 | 2019-02-25
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-2940 | Process Equipment Datasheet - 10-PK-2940 - C4 Polymer Inhibitor Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-20 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-20 | 2019-01-25 | 2019-03-21 | 2019-04-17 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00533 | TPSK-LSPA1-T-PE-00726 | TPSK-LSPA1-T-PE-01103 | TPSK-LSPA1-T-PE-01384 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-01-22 | 2019-03-14 | 2019-04-10 | 2019-05-24 | 2019-08-09
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1 | R2
| PE | OL1-2G30-2945 | Process Equipment Datasheet - 10-PK-2945 - Anti-Oxidant Injection Package |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2019-05-09 | 2019-06-20
[6 empty] | Issue Actual | 2019-05-09 | 2019-06-20 | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01617 | TPSK-LSPA1-T-PE-01930 | TPSK-LSPA1-T-PE-02184
[6 empty] | Return Date | 2019-06-19 | 2019-07-11 | 2019-08-09
[6 empty] | Owner Cmmt* | R1 | R1 | R2
| PE | OL1-2G30-3000 | Process Equipment Datasheet - 10-T-3000 - Predistillation Tower |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-02-26 | 2019-05-23
[6 empty] | Issue Actual | 2019-02-26 | 2019-05-23 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00923 | TPSK-LSPA1-T-PE-01708 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-03-15 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3001 | Process Equipment Datasheet - 10-E-3000 - Predistillation Tower Condenser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-03-26 | 2019-06-10
[6 empty] | Issue Actual | 2019-03-26 | 2019-06-10 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01148 | TPSK-LSPA1-T-PE-01796 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-11 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3002 | Process Equipment Data Sheet - 10-D-3002 - Predistillation Feed Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01802 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3003 | Process Equipment Data Sheet - 10-D-3000 - Predistillation Tower Reflux Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01802 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3004 | Process Equipment Datasheet - 10-E-3004 A-B - Predistillation Tower Trim Reboiler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-03-26 | 2019-06-10
[6 empty] | Issue Actual | 2019-03-26 | 2019-06-10 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01148 | TPSK-LSPA1-T-PE-01796 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-11 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3005 | Process Equipment Datasheet - 10-E-3005 - Predistillation Tower Reboiler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-03-26 | 2019-06-10
[6 empty] | Issue Actual | 2019-03-26 | 2019-06-10 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01148 | TPSK-LSPA1-T-PE-01796 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-11 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3006 | Process Equipment Data Sheet - 10-P-3002 A-B - Predistillation Tower Feed Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01836
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3007 | Process Equipment Data Sheet - 10-P-3000 A-B - Predistillation Tower Reflux Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01836
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3010 | Process Equipment Datasheet - 10-T-3010 - C4 Vaporization Tower |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-02-26 | 2019-05-21
[6 empty] | Issue Actual | 2019-02-26 | 2019-05-21 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00923 | TPSK-LSPA1-T-PE-01684 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-03-15 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3014 | Process Equipment Datasheet - 10-E-3014 A-B - C4 Trim Vaporizer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-03-26 | 2019-05-30
[6 empty] | Issue Actual | 2019-03-26 | 2019-05-30 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01148 | TPSK-LSPA1-T-PE-01762 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-11 | 2019-06-21 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3015 | Process Equipment Datasheet - 10-E-3015 - C4 Trim Vaporizer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-05-31
[6 empty] | Issue Actual | 2019-04-01 | 2019-05-31 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01776 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-06-25 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3016 | Process Equipment Data Sheet - 10-P-3016 A-B Heavy End Discharge Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01836
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3018 | Process Equipment Datasheet - 10-E-3018 A-B - Solvent Cooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-02 | 2019-05-30
[6 empty] | Issue Actual | 2019-04-02 | 2019-05-30 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214 | TPSK-LSPA1-T-PE-01762 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-06-21 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3020 | Process Equipment Datasheet - 10-T-3020 - Main Washer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-02-27 | 2019-05-23
[6 empty] | Issue Actual | 2019-02-27 | 2019-05-23 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00932 | TPSK-LSPA1-T-PE-01708 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-03-15 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3021 | Process Equipment Datasheet - 10-E-3020 - Main Washer Condenser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-02 | 2019-05-30
[6 empty] | Issue Actual | 2019-04-02 | 2019-05-30 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214 | TPSK-LSPA1-T-PE-01762 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-06-21 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3022 | Process Equipment Data Sheet - 10-D-3020 - Main Washer Reflux Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01820 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3023 | Process Equipment Data Sheet - 10-P-3020 A-B Main Washer Reflux -C4 Raffinate-I-Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3026 | Process Equipment Data Sheet - 10-P-3026 A-B - Main Washer Bottom Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3030 | Process Equipment Datasheet - 10-T-3030 - After Washer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-03-01 | 2019-05-21
[6 empty] | Issue Actual | 2019-03-01 | 2019-05-21 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00955 | TPSK-LSPA1-T-PE-01684 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-03-15 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | Re
| PE | OL1-2G30-3031 | Process Equipment Datasheet - 10-E-3030 - After Washer Condenser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-02 | 2019-05-30
[6 empty] | Issue Actual | 2019-04-02 | 2019-05-30 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214 | TPSK-LSPA1-T-PE-01762 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-06-21 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3032 | Process Equipment Data Sheet - 10-D-3030 - After Washer Reflux Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01802 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3033 | Process Equipment Data Sheet - 10-P-3030 A-B After Washer Reflux - Crude Butadiene Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01836
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3036 | Process Equipment Data Sheet - 10-P-3036 A-B - After Washer Bottom Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-11
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01846
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3040 | Process Equipment Datasheet - 10-T-3040 - Rectifier |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-03-04 | 2019-05-23
[6 empty] | Issue Actual | 2019-03-04 | 2019-05-23 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00958 | TPSK-LSPA1-T-PE-01708 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-04-02 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3044 | Process Equipment Datasheet - 10-E-3044 - Solvent Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-02 | 2019-05-31
[6 empty] | Issue Actual | 2019-04-02 | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214 | TPSK-LSPA1-T-PE-01776
[6 empty] | Return Date | 2019-04-12 | 2019-06-25
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3045 | Process Equipment Datasheet - 10-E-3045 A-D - Solvent Heat Exchanger |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-02 | 2019-05-31
[6 empty] | Issue Actual | 2019-04-02 | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214 | TPSK-LSPA1-T-PE-01776
[6 empty] | Return Date | 2019-04-12 | 2019-06-25
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3046 | Process Equipment Data Sheet - 10-P-3046 A-B - Degasser Feed Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3047 | Process Equipment Data Sheet - 10-P-3045 A-B - Rectifier Bottom Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-11
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01847
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3050 | Process Equipment Datasheet - 10-T-3050 - Degasser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-03-01 | 2019-05-21
[6 empty] | Issue Actual | 2019-03-01 | 2019-05-21 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00955 | TPSK-LSPA1-T-PE-01684 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-03-15 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3055 | Process Equipment Datasheet - 10-E-3055 A-B - Degasser Reboiler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-05-31
[6 empty] | Issue Actual | 2019-04-01 | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01776
[6 empty] | Return Date | 2019-04-12 | 2019-06-25
[6 empty] | Owner Cmmt* | R2 | Re
| PE | OL1-2G30-3056 | Process Equipment Data Sheet - 10-P-3056 A-B - Degasser Bottom Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3060 | Process Equipment Datasheet - 10-T-3060 - C4 Acetylene Washer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-02-26 | 2019-05-23
[6 empty] | Issue Actual | 2019-02-26 | 2019-05-23 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00923 | TPSK-LSPA1-T-PE-01708 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-03-15 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3061 | Process Equipment Data Sheet - 10-P-3061 A-B - Dimer Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01945
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3062 | Process Equipment Datasheet - 10-E-3062 - C4 Acetylene Condenser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-05-31
[6 empty] | Issue Actual | 2019-04-01 | 2019-05-31 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01776 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-06-25 | 2019-09-19
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G30-3063 | Process Equipment Datasheet - 10-E-3060 - C4 Acetylene Washer Condenser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-05-31
[6 empty] | Issue Actual | 2019-04-01 | 2019-05-31 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01776 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-06-25 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3064 | Process Equipment Data Sheet - 10-D-3060 - BDU HC-Water Separator |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01802 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3065 | Process Equipment Data Sheet - 10-D-3062 - C4 Acetylene Accumulator |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01813 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3066 | Process Equipment Data Sheet - 10-P-3060 A-B - Wastewater Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3067 | Process Equipment Data Sheet - 10-P-3062 A-B - C4 Acetylene Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01945
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | Re
| PE | OL1-2G30-3070 | Process Equipment Datasheet - 10-T-3070 - Direct Cooler Tower |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-03-01 | 2019-05-21
[6 empty] | Issue Actual | 2019-03-01 | 2019-05-21 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00955 | TPSK-LSPA1-T-PE-01684 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-03-15 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3071 | Process Equipment Datasheet - 10-E-3070 - Water - NMP Cooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-01 | 2019-06-10 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01796 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3072 | Process Equipment Datasheet - 10-EJ-3070 - BDU Recycle Gas Ejector |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2019-04-10 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-10 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01283 | TPSK-LSPA1-T-PE-01827
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3073 | Process Equipment Data Sheet - 10-C-3070 - BDU Recycle Gas Compressor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-11-20 | 2019-01-18
[6 empty] | Issue Actual | 2018-11-20 | 2019-01-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00344 | TPSK-LSPA1-T-PE-00675
[6 empty] | Return Date | 2018-12-13 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3076 | Process Equipment Data Sheet - 10-P-3076 A-B - Direct Cooler Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01946
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3080 | Process Equipment Datasheet - 10-T-3080 - Butadiene Tower |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-02-26 | 2019-05-21
[6 empty] | Issue Actual | 2019-02-26 | 2019-05-21 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00923 | TPSK-LSPA1-T-PE-01684 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-03-15 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3081 | Process Equipment Datasheet - 10-E-3080 A-B - Butadiene Tower Condenser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-05-31
[6 empty] | Issue Actual | 2019-04-01 | 2019-05-31 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01784 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-06-21 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3082 | Process Equipment Data Sheet - 10-D-3080 - Butadiene Tower Reflux Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01813 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3083 | Process Equipment Data Sheet - 10-P-3080 A-B Butadiene Tower Reflux Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01946
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3084 | Process Equipment Datasheet - 10-E-3084 - Butadiene Tower Trim Reboiler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-01 | 2019-06-10 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01796 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3085 | Process Equipment Datasheet - 10-E-3085 A-B - Butadiene Tower Reboiler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-05-31
[6 empty] | Issue Actual | 2019-04-01 | 2019-05-31 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01784 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-06-21 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3086 | Process Equipment Data Sheet - 10-P-3086 A-B Butadiene Tower Bottom Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01946
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3090 | Process Equipment Datasheet - 10-T-3090 - Butadiene Drying Tower |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-02-27 | 2019-05-23
[6 empty] | Issue Actual | 2019-02-27 | 2019-05-23 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00932 | TPSK-LSPA1-T-PE-01708 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-03-15 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3095 | Process Equipment Datasheet - 10-E-3095 - Butadiene Drying Tower Reboiler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-01 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-04-12 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3097 | Process Equipment Data Sheet - 10-P-3096 A-B Butadiene Product Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01946
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3098 | Process Equipment Datasheet - 10-E-3098 - Butadiene Product Subcooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-05-30
[6 empty] | Issue Actual | 2019-04-01 | 2019-05-30 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01762 | TPSK-LSPA1-T-PE-02461
[6 empty] | Return Date | 2019-04-12 | 2019-06-21 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3100 | Process Equipment Data Sheet - 10-D-3100 - Solvent Regen Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01813 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3101 | Process Equipment Datasheet - 10-A-3100 - Solvent Regen Agitator |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2019-04-12 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-12 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01319 | TPSK-LSPA1-T-PE-01824
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | Re
| PE | OL1-2G30-3110 | Process Equipment Datasheet - 10-T-3110 - Water Washer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-01-21 | 2019-02-25
[6 empty] | Revised Plan | 2019-03-04 | 2019-05-23
[6 empty] | Issue Actual | 2019-03-04 | 2019-05-23 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00973 | TPSK-LSPA1-T-PE-01711 | TPSK-LSPA1-T-PE-02266
[6 empty] | Return Date | 2019-04-02 | 2019-06-13 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3111 | Process Equipment Datasheet - 10-E-3110 - Water Washer Condenser |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-01 | 2019-05-31
[6 empty] | Issue Actual | 2019-04-01 | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01202 | TPSK-LSPA1-T-PE-01786
[6 empty] | Return Date | 2019-04-12 | 2019-06-25
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3112 | Process Equipment Data Sheet - 10-D-3110 - Water Washer Accumulator |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01813 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3113 | Process Equipment Data Sheet - 10-P-3110 A-B - Solvent Return Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01947
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3123 | Process Equipment Datasheet - 10-PK-3120 - Regeneration Steam Ejector Package Unit |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan | 2019-04-10 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-10 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01284 | TPSK-LSPA1-T-PE-01823
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3126 | Process Equipment Data Sheet - 10-D-3126 - Ejector Seal Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01813 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3127 | Process Equipment Data Sheet - 10-P-3126 A-B - BDU Ejector Seal Drum Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01947
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3150 | Process Equipment Datasheet - 10-E-3150 - BDU Condensate Heater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-02 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-02 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214 | TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-04-12 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | Re
| PE | OL1-2G30-3151 | Process Equipment Data Sheet - 10-D-3150 - BDU Condensate Flash Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01813 | TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3160 | Process Equipment Datasheet - 10-E-3160 - BDU Condensate Cooler |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-02 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-02 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSAP1-T-PE-01214 | TPSK-LSPA1-T-PE-01796
[6 empty] | Return Date | 2019-04-12 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3161 | Process Equipment Data Sheet - 10-D-3160 - BDU Condensate Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01813 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3162 | Process Equipment Data Sheet - 10-P-3160 - BDU Condensate Recycle Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01947
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3180 | Process Equipment Data Sheet - 10-D-3180 - BDU Knock Out Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01820 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3190 | Process Equipment Data Sheet - 10-D-3190 - NMP Slop Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01820 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3191 | Process Equipment Data Sheet - 10-P-3190 - Solvent Slop Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01265 | TPSK-LSPA1-T-PE-01945
[6 empty] | Return Date | 2019-05-16 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3192 | Process Equipment Datasheet - 10-EJ-3190 - NMP Slop Sump Eductor |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-11
[6 empty] | Revised Plan |  | 2019-03-27
[6 empty] | Issue Actual |  | 2019-03-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01160
[6 empty] | Return Date |  | 2019-04-11
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G30-3900 | Process Equipment Datasheet - 10-TK-3900 - NMP Storage Tank |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-04-12 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-12 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01318 | TPSK-LSPA1-T-PE-01825
[6 empty] | Return Date | 2019-05-16 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-3901 | Process Equipment Datasheet - 10-P-3900 - NMP Storage Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-10 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-10 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285 | TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3902 | Process Equipment Data Sheet - 10-D-3902 - BDU Solvent Inhibitor Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-11
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-11 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01849 | TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-3903 | Process Equipment Datasheet - 10-P-3902 A-B - BDU Solvent Inhibitor Dosing Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-04-10 | 2019-06-21
[6 empty] | Issue Actual | 2019-04-10 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285 | TPSK-LSPA1-T-PE-01954
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3904 | Process Equipment Data Sheet - 10-D-3904 - BDU Product Inhibitor Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01826 | TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-3905 | Process Equipment Datasheet - 10-P-3904 A-B - BDU Product Inhibitor Dosing Pump |  |  | Purpose** | IFR | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
[6 empty] | Revised Plan | 2019-04-10 |  | 2019-10-16
[6 empty] | Issue Actual | 2019-04-10 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285 | TPSK-LSPA1-T-PE-01978
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3906 | Process Equipment Data Sheet - 10-D-3906 - BDU Anti Foam Agent Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01826 | TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-19
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G30-3907 | Process Equipment Datasheet - 10-P-3906 A-B - BDU Anti-Foam Dosing Pump |  |  | Purpose** | IFR | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
[6 empty] | Revised Plan | 2019-04-10 |  | 2019-10-16
[6 empty] | Issue Actual | 2019-04-10 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285 | TPSK-LSPA1-T-PE-01978
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3908 | Process Equipment Datasheet - 10-P-3908 A-B - BDU Predistillation Inhibitor Dosing Pump |  |  | Purpose** | IFR | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
[6 empty] | Revised Plan | 2019-04-10 |  | 2019-10-16
[6 empty] | Issue Actual | 2019-04-10 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA-1-PE-01285 | TPSK-LSPA1-T-PE-01978
[6 empty] | Return Date | 2019-05-16
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-3910 | Process Equipment Data Sheet - 10-D-3908 - Predistillation Inhibitor Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-04-08 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-08 | 2019-06-10 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01263 | TPSK-LSPA1-T-PE-01826 | TPSK-LSPA1-T-PE-02427
[6 empty] | Return Date | 2019-05-09 | 2019-07-08 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5100 | Process Equipment Datasheet - 10-D-5100 - Deaerator |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-10 | 2018-11-14
[6 empty] | Issue Actual | 2018-10-10 | 2018-11-14 | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00151 | TPSK-LSPA1-T-PE-00318 | TPSK-LSPA1-T-PE-01174
[6 empty] | Return Date | 2018-11-05 | 2019-02-21 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5101 | Process Equipment Datasheet - 10-P-5100 A-C - SHP BFW Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-09 | 2018-10-31
[6 empty] | Issue Actual | 2018-10-09 | 2018-10-31 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-01483
[6 empty] | Return Date | 2018-10-26 | 2018-12-13 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-5102 | Process Equipment Datasheet - 10-P-5102 A-B - VLP BFW Pumps |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-09 | 2018-10-31
[6 empty] | Issue Actual | 2018-10-09 | 2018-10-31 | 2019-04-01 | 2019-04-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-01196 | TPSK-LSPA1-T-PE-01484
[6 empty] | Return Date | 2018-10-26 | 2018-12-13 | 2019-06-07 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R1 | R1 | R1
| PE | OL1-2G30-5103 | Process Equipment Datasheet - 10-E-5100 - Deaerator Vent Condenser |  | Class 2 | Purpose** | IFR | IFD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2018-10-25 | 2018-11-26 | 2019-03-20
[6 empty] | Issue Actual | 2018-10-25 | 2018-11-26 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00366 | TPSK-LSPA1-T-PE-01097
[6 empty] | Return Date | 2018-11-14 | 2018-12-10 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5107 | Process Equipment Datasheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-30 | 2019-01-14
[6 empty] | Issue Actual | 2018-10-30 | 2019-01-14 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243 | TPSK-LSPA1-T-PE-00646 | TPSK-LSPA1-T-PE-02346
[6 empty] | Return Date | 2018-11-14 | 2019-02-21 | 2019-09-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5108 | Process Equipment Datasheet - 10-E-5110 - Suspect Condensate Cooler |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-30 | 2019-01-14
[6 empty] | Issue Actual | 2018-10-30 | 2019-01-14 | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00243 | TPSK-LSPA1-T-PE-00652 | TPSK-LSPA1-T-PE-01918
[6 empty] | Return Date | 2018-11-14 | 2019-02-21 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5109 | Process Equipment Datasheet - 10-P-5110 A-B - Condensate Pumps |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-09 | 2018-10-31
[6 empty] | Issue Actual | 2018-10-09 | 2018-10-31 | 2019-03-15 | 2019-03-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00141 | TPSK-LSPA1-T-PE-00251 | TPSK-LSPA1-T-PE-01051 | TPSK-LSAP1-T-PE-01189
[6 empty] | Return Date | 2018-10-26 | 2018-12-13 | 2019-04-02 | 2019-05-09
[6 empty] | Owner Cmmt* | R1 | R2 | R2 | Re
| PE | OL1-2G30-5110 | Condensate Tank PDS |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-27 | 2019-03-12
[6 empty] | Issue Actual | 2018-11-27 | 2019-03-12 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00374 | TPSK-LSPA1-T-PE-01017 | TPSK-LSPA1-T-PE-02701
[6 empty] | Return Date | 2018-12-18 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5111 | Process Equipment Datasheet - 10-P-5112 A-B - Suspect Condensate Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-24 | 2018-11-26
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-00363
[6 empty] | Return Date | 2018-11-14 | 2018-12-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5112 | Process Equipment Datasheet - 10-D-5112 - Suspect Condensate Flash Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-05 | 2018-12-14
[6 empty] | Issue Actual | 2018-11-05 | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00274 | TPSK-LSPA1-T-PE-00498
[6 empty] | Return Date | 2018-12-10 | 2019-01-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5113 | Process Equipment Datasheet - 10-E-5113 - Foul Condensate Cooler |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-10-25 | 2018-11-26
[6 empty] | Issue Actual | 2018-10-25 | 2018-11-26 | 2019-04-09 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00230 | TPSK-LSPA1-T-PE-00366 | TPSK-LSPA1-T-PE-01278 | TPSK-LSPA1-T-PE-01406
[6 empty] | Return Date | 2018-11-14 | 2018-12-10 | 2019-06-07 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R1 | R1 | R1
| PE | OL1-2G30-5114 | Process Equipment Datasheet - 10-D-5114 - LP Condensate Flash Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-05 | 2018-12-14
[6 empty] | Issue Actual | 2018-11-05 | 2018-12-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00274 | TPSK-LSPA1-T-PE-00498
[6 empty] | Return Date | 2018-12-10 | 2019-01-10
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5115 | Process Equipment Datasheet - 10-PK-5115 - Condensate Carbon Filter Pkg |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2018-11-26 | 2019-02-01
[6 empty] | Issue Actual | 2018-11-26 | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00362 | TPSK-LSPA1-T-PE-00778
[6 empty] | Return Date | 2018-12-18 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5120 | Raw Condensate Tank PDS |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-26 | 2019-03-15
[6 empty] | Issue Actual | 2018-11-26 | 2019-03-15 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00364 | TPSK-LSPA1-T-PE-01055 | TPSK-LSPA1-T-PE-02701
[6 empty] | Return Date | 2018-12-17 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5121 | Process Equipment Datasheet - 10-P-5120 A-B - Raw Condensate Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-24 | 2018-11-26
[6 empty] | Issue Actual | 2018-10-24 | 2018-11-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-00363
[6 empty] | Return Date | 2018-11-14 | 2018-12-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5125 | Process Equipment Datasheet - 10-PK-5125 - Condensate Polisher Pkg |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2018-11-27 | 2019-02-01
[6 empty] | Issue Actual | 2018-11-27 | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00373 | TPSK-LSPA1-T-PE-00778
[6 empty] | Return Date | 2018-12-13 | 2019-02-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5140 | Process Equipment Datasheet - 10-D-5140 - Intermittent Blowdown Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-19 | 2018-12-14
[6 empty] | Issue Actual | 2018-11-19 | 2018-12-14 | 2019-03-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00504 | TPSK-LSPA1-T-PE-00988
[6 empty] | Return Date | 2018-12-04 | 2019-01-10 | 2019-03-15
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5141 | Process Equipment Datasheet - 10-P-5140 A-B - Intermittent Blowdown Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-10-24 | 2019-03-15
[6 empty] | Issue Actual | 2018-10-24 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00219 | TPSK-LSPA1-T-PE-01051
[6 empty] | Return Date | 2018-11-14 | 2019-04-02
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5150 | Process Equipment Datasheet - 10-D-5150 - Continuous Blow Down Flash Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-19 | 2018-12-07
[6 empty] | Issue Actual | 2018-11-19 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-12-04 | 2019-03-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5170 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-5100 A-B SHP BFW Pumps Turbines |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PL | OL1-2G30-5171 | Process Data Sheet For General Purpose Steam Turbines - API 611-4TH - PT-5102 A VLP BFW Pump Turbine |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5172 | Process Data Sheet For General Purpose Steam Turbines Pt-5110A Condensate Pump Turbine |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-01867
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5200 | Process Equipment Datasheet - 10-D-5200 - Fuel Gas Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-19 | 2018-12-07
[6 empty] | Issue Actual | 2018-11-19 | 2018-12-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00331 | TPSK-LSPA1-T-PE-00440
[6 empty] | Return Date | 2018-12-04 | 2019-01-04
[6 empty] | Owner Cmmt* | R2 | TP
| PE | OL1-2G30-5201 | Process Equipment Datasheet - 10-E-5200 - MP Ethylene Superheater |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-05 | 2019-02-15
[6 empty] | Issue Actual | 2018-11-05 | 2019-02-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00275 | TPSK-LSPA1-T-PE-00853
[6 empty] | Return Date | 2018-11-29 | 2019-03-13
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5202 | Process Equipment Datasheet - 10-D-5220 - MP Ethylene Superhtr Cond Pot |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-01-10 | 2019-02-11
[6 empty] | Issue Actual | 2019-01-10 | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE--00836
[6 empty] | Return Date | 2019-01-24 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5210 | Process Equipment Datasheet - 10-E-5210 - Pilot Gas Vaporizer |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-15 | 2019-03-15
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-15 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00321 | TPSK-LSPA1-T-PE-01054 | TPSK-LSPA1-T-PE-01278
[6 empty] | Return Date | 2018-12-13 | 2019-03-29 | 2019-06-07
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5211 | Process Equipment Datasheet - 10-D-5210 - Pilot Gas Vaporizer Cond Pot |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-01-10 | 2019-02-11
[6 empty] | Issue Actual | 2019-01-10 | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE--00836
[6 empty] | Return Date | 2019-01-24 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5301 | Process Data Sheet for 10-S-5301 A-H |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02323
[6 empty] | Return Date | 2019-08-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5302 | Process Data Sheet for 10-S-5302 A-B |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02323
[6 empty] | Return Date | 2019-08-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5350 | Process Equipment Datasheet - 10-PK-5350 - Cooling Tower |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-12-03 |  | 2018-12-26
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-10-24
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-10-24 | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00226 | TPSK-LSPA1-T-PE-01150
[6 empty] | Return Date |  | 2018-10-13 | 2018-11-14 | 2019-04-12
[6 empty] | Owner Cmmt* |  | A3 | A1 | Re
| PE | OL1-2G30-5351 | Process Equipment Datasheet - 10-PIT-5351 A-H - Olefins CW Pumps Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-03 | 2018-12-26
[6 empty] | Revised Plan | 2018-12-20 | 2019-02-04
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-04 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA1-T-PE-00791 | TPSK-LSPA1-T-PE-02339
[6 empty] | Return Date | 2019-01-16 | 2019-03-13 | 2019-08-22
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5352 | Process Equipment Datasheet - 10-P-5350 A-H - Olefins Cooling Water Pumps |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-10-24
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-10-24 | 2018-10-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075
[6 empty] | Return Date |  | 2019-04-22 | 2018-11-14 | 2018-11-14
[6 empty] | Owner Cmmt* |  | A1 | A1 | A1
| PE | OL1-2G30-5355 | Process Equipment Datasheet - 10-PK-5355 - Side Stream Filter Pkg |  |  | Purpose** | IFR | IFA | IFD | IFD
[6 empty] | Rev. |  | A | B | C
[6 empty] | Issue Plan | 2018-12-03 |  | 2018-12-26
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-10-24
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-10-24 | 2019-01-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00082 | TPSK-LSPA1-T-PE-00226 | TPSK-LSPA1-T-PE-00611
[6 empty] | Return Date |  | 2018-10-13 | 2018-11-14 | 2019-01-24
[6 empty] | Owner Cmmt* |  | A3 | A1 | A1
| PE | OL1-2G30-5360 | Process Equipment Datasheet - 10-PIT-5360 A-C - CTU CW Pumps Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-03 | 2018-12-26
[6 empty] | Revised Plan | 2018-12-20 | 2019-02-04
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-04 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA1-T-PE-00791 | TPSK-LSPA1-T-PE-02323
[6 empty] | Return Date | 2019-01-16 | 2019-03-13 | 2019-08-23
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5361 | Process Equipment Datasheet - 10-P-5360 A-C - CTU Cooling Water Pumps |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 |  | 2019-04-01
[6 empty] | Revised Plan |  | 2018-09-25 | 2018-10-24
[6 empty] | Issue Actual |  | 2018-09-25 | 2018-10-24 | 2018-10-26 | 2019-01-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00225 | TPSK-LSPA1-T-PE-00075 | TPSK-LSPA1-T-PE-00593
[6 empty] | Return Date |  | 2018-10-24 | 2018-11-14 | 2018-11-14 | 2019-02-04
[6 empty] | Owner Cmmt* |  | A3 | A1 | A1 | R1
| PE | OL1-2G30-5370 | Process Equipment Datasheet - 10-PIT-5370 - CW Filter Backwash Sump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-03 | 2018-12-26
[6 empty] | Revised Plan | 2018-12-20 | 2019-02-04
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-04
[6 empty] | Transmittal no. | TPSK-LSPA-1-T-PE-00539 | TPSK-LSPA1-T-PE-00791
[6 empty] | Return Date | 2019-01-16 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5371 | Process Equipment Datasheet - 10-P-5370 A-B - CW Filter Backwash Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-10 | 2019-04-17
[6 empty] | Issue Actual | 2019-01-10 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00623 | TPSK-LSPA1-T-PE-01366
[6 empty] | Return Date | 2019-02-04 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5390 | Process Equipment Datasheet - 10-PK-5390 - Copper Corrosion Inhibitor Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-11-27 | 2019-02-19
[6 empty] | Issue Actual | 2018-11-27 | 2019-02-19 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2018-12-13 | 2019-03-13 | 2019-04-10 | 2019-08-06
[6 empty] | Owner Cmmt* | R2 | R1 | R1 | R2
| PE | OL1-2G30-5392 | Process Equipment Datasheet - 10-PK-5392 - Mild Steel Corr Inhibitor Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-11-27 | 2019-02-19
[6 empty] | Issue Actual | 2018-11-27 | 2019-02-19 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00890 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2018-12-13 | 2019-03-13 | 2019-04-10 | 2019-08-06
[6 empty] | Owner Cmmt* | R2 | R1 | R1 | R2
| PE | OL1-2G30-5394 | Process Equipment Datasheet - 10-PK-5394 - Dispersant Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-11-27 | 2019-02-19
[6 empty] | Issue Actual | 2018-11-27 | 2019-02-19 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2018-12-13 | 2019-03-13 | 2019-04-10 | 2019-08-06
[6 empty] | Owner Cmmt* | R2 | R1 | R1 | R2
| PE | OL1-2G30-5397 | Process Equipment Datasheet - 10-PK-5397 - Non-oxidizing Biocide Inj Pkg |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-11-27 | 2019-02-19
[6 empty] | Issue Actual | 2018-11-27 | 2019-02-19 | 2019-03-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00375 | TPSK-LSPA1-T-PE-00877 | TPSK-LSPA1-T-PE-01111
[6 empty] | Return Date | 2018-12-13 | 2019-03-13 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5400 | Process Equipment Datasheet - 10-D-5400 - Instrument Air Receiver |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-13 | 2019-02-06
[6 empty] | Issue Actual | 2018-12-13 | 2019-02-06 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00485 | TPSK-LSPA1-T-PE-00800 | TPSK-LSPA1-T-PE-00983
[6 empty] | Return Date | 2019-01-07 | 2019-03-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5500 | Process Equipment Datasheet - 10-D-5500 - Hot Flare Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-15 | 2018-12-05
[6 empty] | Issue Actual | 2018-10-15 | 2018-12-05 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00168 | TPSK-LSPA1-T-PE-00417 | TPSK-LSPA1-T-PE-01020
[6 empty] | Return Date | 2018-11-14 | 2019-01-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5501 | Process Equipment Datasheet - 10-P-5500 A-B - Hot Blowdown Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-27 | 2019-01-31
[6 empty] | Issue Actual | 2018-12-27 | 2019-01-31 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01022
[6 empty] | Return Date | 2019-01-24 | 2019-03-05 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-5510 | Process Equipment Datasheet - 10-D-5510 - Cold Flare Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-29 | 2019-03-12
[6 empty] | Issue Actual | 2018-11-29 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00397 | TPSK-LSPA1-T-PE-01018
[6 empty] | Return Date | 2019-01-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5511 | Process Equipment Datasheet - 10-E-5510 - Cold Flare Blowdown Vaporizer |  |  | Purpose** | IFR | IFR | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan | 2019-01-03 |  | 2019-04-05
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-11 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-01261
[6 empty] | Return Date | 2019-03-13 | 2019-02-04 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5512 | Process Equipment Datasheet - 10-E-5512 - Cold Flare Superheater |  |  | Purpose** | IFR | IFR | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan | 2019-01-03 |  | 2019-03-27
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-11 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-01161
[6 empty] | Return Date | 2019-03-13 | 2019-02-04 | 2019-04-11
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-5513 | Process Equipment Datasheet - 10-E-5513 - Methanol Vaporizer |  |  | Purpose** | IFR | IFR | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 |  | 2019-03-18
[6 empty] | Revised Plan | 2019-01-03 |  | 2019-03-27
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-11 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00575 | TPSK-LSPA1-T-PE-00626 | TPSK-LSPA1-T-PE-01161
[6 empty] | Return Date | 2019-03-13 | 2019-02-04 | 2019-04-11
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5514 | Process Equipment Datasheet - 10-D-5513 - Methanol Vaporizer Cond Pot |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-01-10 | 2019-02-04
[6 empty] | Issue Actual | 2019-01-10 | 2019-02-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00614 | TPSK-LSPA1-T-PE-00785
[6 empty] | Return Date | 2019-01-24 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5515 | Process Equipment Datasheet - 10-D-5515 - Methanol Makeup Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-20 | 2019-03-15
[6 empty] | Issue Actual | 2018-12-20 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00527 | TPSK-LSPA1-T-PE-01052
[6 empty] | Return Date | 2019-01-24 | 2019-03-29
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5520 | Process Equipment Datasheet - 10-D-5520 - Vent Collection Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-11-26 | 2019-02-15
[6 empty] | Issue Actual | 2018-11-26 | 2019-02-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00365 | TPSK-LSPA1-T-PE-00856
[6 empty] | Return Date | 2018-12-13 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5521 | Process Equipment Datasheet - 10-PK-5520 - LP Vent Blower Pkg |  | Class 2 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-11-19 | 2019-03-21
[6 empty] | Issue Actual | 2018-11-19 | 2019-03-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00332 | TPSK-LSPA1-T-PE-01112
[6 empty] | Return Date | 2018-12-06 | 2019-04-10
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5522 | Process Equipment Datasheet - 10-C-5520 A-B - LP Vent Blowers |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-12-20 | 2019-02-11
[6 empty] | Issue Actual | 2018-12-20 | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00528 | TPSK-LSPA1-T-PE-00837
[6 empty] | Return Date | 2019-01-24 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5550 | Process Equipment Datasheet - 10-D-5550 - HP Flare Knock-Out Drum |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-10-07 | 2018-12-07
[6 empty] | Issue Actual | 2018-10-07 | 2018-12-07 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00142 | TPSK-LSPA1-T-PE-00440 | TPSK-LSPA1-T-PE-01020
[6 empty] | Return Date | 2018-10-26 | 2019-01-04 | 2019-03-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5551 | Process Equipment Datasheet - 10-P-5550 A-B - HP Flare Knock-Out Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-27 | 2019-01-31
[6 empty] | Issue Actual | 2018-12-27 | 2019-01-31 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01366
[6 empty] | Return Date | 2019-01-24 | 2019-03-05 | 2019-05-24
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-5552 | Process Equipment Datasheet - 10-D-5552 - LPG Storage Drum |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-07 | 2019-03-08
[6 empty] | Issue Actual | 2018-12-07 | 2019-03-08 | 2019-04-05 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00439 | TPSK-LSPA1-T-PE-01008 | TPSK-LSPA1-T-PE-01260 | TPSK-LSPA1-T-PE-01677
[6 empty] | Return Date | 2018-12-27 | 2019-03-27 | 2019-05-09 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1
| PE | OL1-2G30-5553 | Process Equipment Datasheet - 10-E-5552 - LPG Vaporizer - Superheater |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-01-10 | 2019-03-15
[6 empty] | Issue Actual | 2019-01-10 | 2019-03-15 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00622 | TPSK-LSPA1-T-PE-01054 | TPSK-LSPA1-T-PE-01589
[6 empty] | Return Date | 2019-02-04 | 2019-03-29
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5555 | Process Equipment Datasheet - 10-D-5553 - LPG Vaporizer - Superhtr Cond Pot |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2019-01-10 | 2019-03-12
[6 empty] | Issue Actual | 2019-01-10 | 2019-03-12 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00619 | TPSK-LSPA1-T-PE-01018 | TPSK-LSPA1-T-PE-01590
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5560 | Process Equipment Datasheet - 10-PK-5560 - HP - Polyolefins Flare Pkg |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-11-29 | 2019-03-08
[6 empty] | Issue Actual | 2018-11-29 | 2019-03-08 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00398 | TPSK-LSPA1-T-PE-01007 | TPSK-LSPA1-T-PE-01506
[6 empty] | Return Date | 2018-12-13 | 2019-03-29 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5565 | Process Equipment Datasheet - 10-D-5565 - Polyolefins Flare Knock-Out Drum |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-25
[6 empty] | Revised Plan | 2018-12-20 | 2019-03-06
[6 empty] | Issue Actual | 2018-12-20 | 2019-03-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00558 | TPSK-LSPA1-T-PE-00989
[6 empty] | Return Date | 2019-01-22 | 2019-03-21
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5566 | Process Equipment Datasheet - 10-P-5565 A-B - Polyolefins Flare Knock-out Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-10 | 2019-04-17
[6 empty] | Issue Actual | 2019-01-10 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00623 | TPSK-LSPA1-T-PE-01366
[6 empty] | Return Date | 2019-02-04 | 2019-05-24
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5570 | Process Equipment Datasheet - 10-PK-5570 - Enclosed Ground Flare Package |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2019-03-04 | 2019-04-12
[6 empty] | Issue Actual | 2019-03-04 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00959 | TPSK-LSPA1-T-PE-01326
[6 empty] | Return Date | 2019-03-21 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5600 | Process Equipment Datahseet - 10-PIT-5600 - Pygas Area Oily Wastewater Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-11
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5601 | Process Equipment Datasheet - 10-PIT-5601 - Butadiene Area Oily Wastewater Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-07
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5602 | Process Equipment Datasheet - 10-PIT-5602 - QW Area Oily Wastewater Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-07
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5603 | Process Equipment Datasheet - 10-PIT-5603 - CGC Area Oily Wastewater Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-07
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5604 | Process Equipment Datasheet - 10-PIT-5604 - Refrig Area Oily Wastewater Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-07
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5605 | Process Equipment Datasheet - 10-PIT-5605 - Furnace Area Oily Wastewater Sump |  | Class 2 | Purpose** | IFR | IFD | IFD | CAN
[6 empty] | Rev. | A | B | C | 0
Issue Plan
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-07 |  | 2019-05-10
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-05 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-01630
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5606 | Process Equipment Datasheet - 10-P-5600 A-B - Pygas Area Oily Wastewater Pump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-02-01
[6 empty] | Issue Actual | 2019-01-03 | 2019-02-01 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-01051
[6 empty] | Return Date | 2019-01-22 | 2019-03-04 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5607 | Process Equipment Datasheet - 10-P-5601 A-B - Butadiene Area Oily Wastewater Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5608 | Process Equipment Datasheet - 10-P-5602 A-B - QW Area Oily Wastewater Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5609 | Process Equipment Datasheet - 10-P-5603 A-B - CGC Area Oily Wastewater Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5610 | Process Equipment Datasheet - 10-PIT-5610 - Hydroblast Sump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-04-09
[6 empty] | Issue Actual | 2019-01-07 | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-01281
[6 empty] | Return Date | 2019-02-04 | 2019-06-07
[6 empty] | Owner Cmmt* | R2 | Re
| PE | OL1-2G30-5611 | Process Equipment Datasheet - 10-P-5610 - Hydroblast Sump Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-07 | 2019-03-15
[6 empty] | Issue Actual | 2019-01-07 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00590 | TPSK-LSPA1-T-PE-01051
[6 empty] | Return Date | 2019-01-24 | 2019-04-02
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5612 | Process Equipment Datasheet - 10-F-5610 - Hydroblast Filter |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-07 | 2019-01-02
[6 empty] | Revised Plan | 2018-12-10 | 2019-03-08
[6 empty] | Issue Actual | 2018-12-10 | 2019-03-08 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00454 | TPSK-LSPA1-T-PE-01009 | TPSK-LSPA1-T-PE-01259
[6 empty] | Return Date | 2019-03-11 | 2019-03-27 | 2019-05-09
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-5613 | Process Equipment Datasheet - 10-P-5604 A-B - Refrig Area Oily Wastewater Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5614 | Process Equipment Datasheet - 10-P-5605 A-B - Furnace Area Oily Wastewater Pump |  | Class 2 | Purpose** | IFR | IFD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-01-03 | 2019-02-01 | 2019-05-10
[6 empty] | Issue Actual | 2019-01-03 | 2019-02-01 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-01631
[6 empty] | Return Date | 2019-01-22 | 2019-03-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-5615 | Process Equipment Datasheet - 10-PIT-5615 - Olefins Stormwater Sump |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | D | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-11
[6 empty] | Issue Actual | 2019-01-11 |  | 2019-03-04 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00636 | TPSK-LSPA1-T-PE-02673 | TPSK-LSPA1-T-PE-00960 | TPSK-LSPA1-T-PE-01068
[6 empty] | Return Date | 2019-02-04 | 2019-10-14 | 2019-03-14 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1
| PE | OL1-2G30-5616 | Process Equipment Datasheet - 10-P-5615 A-B - Olefins Stormwater Sump Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5620 | Process Equipment Datasheet - 10-PIT-5620 A-C - Olefins Holding Basin |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | D | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07
[6 empty] | Issue Actual | 2019-01-07 |  | 2019-03-04 | 2019-03-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-02673 | TPSK-LSPA1-T-PE-00960 | TPSK-LSPA1-T-PE-01068
[6 empty] | Return Date | 2019-02-04 | 2019-10-14 | 2019-03-14 | 2019-04-02
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1
| PE | OL1-2G30-5621 | Process Equipment Datasheet - 10-P-5621 - Olefins Holding Basin Skimmed Oil Pump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01022
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-5622 | Process Equipment Datasheet - 10-P-5620 A-C - Olefins Holding Basin Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-11 | 2019-04-05
[6 empty] | Issue Actual | 2019-01-11 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00635 | TPSK-LSPA1-T-PE-01255
[6 empty] | Return Date | 2019-02-04 | 2019-05-09
[6 empty] | Owner Cmmt* | R2 | Re
| PE | OL1-2G30-5623 | Process Equipment Datasheet - 10-P-5626 A-B - Far C Septic Tank Pumps |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31 | 2019-03-26 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01152 | TPSK-LSPA1-T-PE-01255
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| PE | OL1-2G30-5624 | Process Equipment Datasheet - 10-P-5627 A-B - Gate 4 Septic Tank Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-5625 | Process Equipment Datasheet - 10-P-5628 A-B - Gate 3 Septic Tank Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-01-22 | 2019-03-05 | 2019-04-12
[6 empty] | Owner Cmmt* | R1 | R2 | R1
| PE | OL1-2G30-5626 | Process Equipment Datasheet - 10-PIT-5626 - Far C Septic Tank |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-11
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-01257
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | Re
| PE | OL1-2G30-5627 | Process Equipment Datasheet - 10-PIT-5627 - Gate 4 Septic Tank |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-11
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-01257
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | Re
| PE | OL1-2G30-5628 | Process Equipment Datasheet - 10-PIT-5628 - Gate 3 Septic Tank |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-11
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-01257
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | Re
| PE | OL1-2G30-5629 | Data Sheet For Basins PIT-5621 Skimmed Oil Sump |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02673
[6 empty] | Return Date | 2019-10-14
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5630 | Process Equipment Datasheet - 10-PIT-5630 - CT Area Oily Wastewater Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-11
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5631 | Process Equipment Datasheet - 10-PIT-5631 - CWWT Area Oily Wastewater Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-11
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5632 | Process Equipment Datasheet - 10-PIT-5632 - HP Flare Area Oily WW Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-11
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-11 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00838 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5633 | Process Equipment Datasheet - 10-PIT-5633 - HP Flare Area Stormwater Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | C | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-11
[6 empty] | Issue Actual | 2019-01-11 |  | 2019-03-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00636 | TPSK-LSPA1-T-PE-02735 | TPSK-LSPA1-T-PE-00960
[6 empty] | Return Date | 2019-02-04 |  | 2019-03-14
[6 empty] | Owner Cmmt* | R2 |  | R1
| PE | OL1-2G30-5635 | Process Equipment Datasheet - 10-P-5630 A-B - CT Area Oily WWater Sump Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5636 | Process Equipment Datasheet - 10-P-5631 A-B - CWWT Area Oily WWater Sump Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5637 | Process Equipment Datasheet - 10-P-5632 A-B - HP Flare Area Oily WW Sump Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-03-12
[6 empty] | Issue Actual | 2019-01-03 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-01019
[6 empty] | Return Date | 2019-01-22 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5638 | Process Equipment Datasheet - 10-P-5633 A-B - HP Flare Area SW Sump Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-03-12
[6 empty] | Issue Actual | 2019-01-03 | 2019-03-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00576 | TPSK-LSPA1-T-PE-01019
[6 empty] | Return Date | 2019-01-22 | 2019-03-27
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5640 | Process Equipment Datasheet - 10-TK-5640 - Oily Wastewater Tank |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-28
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-28 | 2019-06-19 | 2019-08-08 | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-01176 | TPSK-LSPA1-T-PE-01920 | TPSK-LSPA1-T-PE-02378 | TPSK-LSPA1-T-PE-02720
[6 empty] | Return Date | 2019-03-15 | 2019-04-22 | 2019-07-15 | 2019-08-27
[6 empty] | Owner Cmmt* | R1 | R2 | R2 | R2
| PE | OL1-2G30-5641 | Process Equipment Datasheet - 10-P-5641 - Wastewater EQ Tank Skimmed Oil Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-26
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | CL
| PE | OL1-2G30-5642 | Process Equipment Datasheet - 10-PIT-5642 - Cooling Water Blowdown Basin |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | C | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-02-06
[6 empty] | Issue Actual | 2019-02-06 |  | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-02673 | TPSK-LSPA1-T-PE-01511
[6 empty] | Return Date | 2019-03-15 | 2019-10-14 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5643 | Process Equipment Datasheet - 10-P-5642 A-B - Cooling Water BD Basin Pumps |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-06 | 2019-05-02
[6 empty] | Issue Actual | 2019-02-06 | 2019-05-02 | 2019-06-25 | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01543 | TPSK-LSPA1-T-PE-01981 | TPSK-LSPA1-T-PE-02377
[6 empty] | Return Date | 2019-03-15 | 2019-06-17 | 2019-07-17 | 2019-08-27
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G30-5644 | Process Equipment Datasheet - 10-PK-5644 - Wastewater CPI - IGF Package |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E | F
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-11-06 | 2018-12-07
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07 | 2019-02-04 | 2019-05-08 | 2019-07-23 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-01606 | TPSK-LSPA1-T-PE-02214 | TPSK-LSPA1-T-PE-02327
[6 empty] | Return Date | 2018-11-26 | 2019-01-04 | 2019-03-04 | 2019-06-19 | 2019-08-15
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2
| PE | OL1-2G30-5645 | Process Equipment Datasheet - 10-P-5640 A-B - Oily Wastewater EQ Tank Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-28
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01177
[6 empty] | Return Date | 2019-03-15
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G30-5646 | Process Equipment Datasheet - 10-PIT-5606 - C3 Hydrog Area Oily Wastewater Sump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-07
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5647 | Process Equipment Datasheet - 10-PIT-5607 - Flare KO Drum Oily Wastewater Sump |  | Class 2 | Purpose** | IFR | IFD | IFD | CAN
[6 empty] | Rev. | A | B | C | 0
Issue Plan
[6 empty] | Revised Plan | 2019-01-07 | 2019-02-07 |  | 2019-05-10
[6 empty] | Issue Actual | 2019-01-07 | 2019-02-07 | 2019-03-05 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00589 | TPSK-LSPA1-T-PE-00819 | TPSK-LSPA1-T-PE-00982 | TPSK-LSPA1-T-PE-01630
[6 empty] | Return Date | 2019-02-04 | 2019-03-27 | 2019-03-13 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R1
| PE | OL1-2G30-5648 | Process Equipment Datasheet - 10-P-5606 A-B - C3 Hydrog Area Oily Wastewater Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-03 | 2019-01-31
[6 empty] | Issue Actual | 2019-01-03 | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00774
[6 empty] | Return Date | 2019-01-22 | 2019-03-05
[6 empty] | Owner Cmmt* | R1 | R1
| PE | OL1-2G30-5649 | Process Equipment Datasheet - 10-P-5607 A-B - Flare KO Drum Oily Wastewater Pump |  | Class 2 | Purpose** | IFR | IFD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-01-03 | 2019-02-01 | 2019-05-10
[6 empty] | Issue Actual | 2019-01-03 | 2019-02-01 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00572 | TPSK-LSPA1-T-PE-00779 | TPSK-LSPA1-T-PE-01631
[6 empty] | Return Date | 2019-01-22 | 2019-03-04 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| PE | OL1-2G30-5650 | Process Equipment Datasheet - 10-PK-5650 - Bio Treatment Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E | F
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-11-06 | 2018-12-07
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07 | 2019-02-04 | 2019-05-08 | 2019-07-23 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-01606 | TPSK-LSPA1-T-PE-02214 | TPSK-LSPA1-T-PE-02327
[6 empty] | Return Date | 2018-11-26 | 2019-01-04 | 2019-03-04 | 2019-06-19 | 2019-08-15
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2
| PE | OL1-2G30-5652 | Process Equipment Datasheet - 10-P-5653 - Bio Equalization Pit Sludge Pump |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-05-31 | 2019-06-25
[6 empty] | Issue Actual | 2019-05-31 | 2019-06-25 | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE--01775 | TPSK-LSPA1-T-PE-01981 | TPSK-LSPA1-T-PE-02377
[6 empty] | Return Date | 2019-06-21 | 2019-07-17 | 2019-08-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5653 | Process Equipment Datasheet - 10-PK-5653 - Wastewater Dual Media Filters Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E | F
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2018-11-06 | 2018-12-07
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07 | 2019-02-04 | 2019-05-08 | 2019-07-23 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00282 | TPSK-LSPA1-T-PE-00441 | TPSK-LSPA1-T-PE-00798 | TPSK-LSPA1-T-PE-01607 | TPSK-LSPA1-T-PE-02214 | TPSK-LSPA1-T-PE-02327
[6 empty] | Return Date | 2018-11-26 | 2019-01-04 | 2019-03-11 | 2019-06-19 | 2019-08-15
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R2 | R1
| PE | OL1-2G30-5654 | Process Equipment Datasheet - 10-P-5655 A-B-C - Equalization Pit Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-26
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | CL
| PE | OL1-2G30-5655 | Process Equipment Datasheet - 10-PIT-5655 - Bio Equalization Pit |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-28
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-28 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-01178 | TPSK-LSPA1-T-PE-01981
[6 empty] | Return Date | 2019-03-15 | 2019-05-09 | 2019-07-17
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5656 | Process Equipment Datasheet - 10-PIT-5656 - Final Check Basin |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-12-20 | 2019-01-07
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-28
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00808 | TPSK-LSPA1-T-PE-01178
[6 empty] | Return Date | 2019-03-15 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5657 | Process Equipment Datasheet - 10-P-5656 A-B - Final Check Basin Pumps |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-06 | 2019-04-29
[6 empty] | Issue Actual | 2019-02-06 | 2019-04-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01512
[6 empty] | Return Date | 2019-03-15 | 2019-06-17
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5670 | Process Equipment Datasheet - 10-PK-5670 - Dewatering Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E | F
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-11-06 | 2018-12-07
[6 empty] | Issue Actual | 2018-11-06 | 2018-12-07 | 2019-02-04 | 2019-05-08 | 2019-07-23 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00281 | TPSK-LSPA1-T-PE-00442 | TPSK-LSPA1-T-PE-00797 | TPSK-LSPA1-T-PE-01606 | TPSK-LSPA1-T-PE-02214 | TPSK-LSPA1-T-PE-02327
[6 empty] | Return Date | 2018-11-26 | 2019-01-04 | 2019-03-04 | 2019-06-19 | 2019-08-15
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2 | R2
| PE | OL1-2G30-5674 | Process Equipment Datasheet - 10-P-5675 - Slop Oil Transfer Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-26
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | CL
| PE | OL1-2G30-5675 | Process Equipment Datasheet - 10-TK-5675 A-B - Slop Oil Tanks |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-28
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-28 | 2019-06-19 | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-01176 | TPSK-LSPA1-T-PE-01920 | TPSK-LSPA1-T-PE-02377
[6 empty] | Return Date | 2019-03-15 | 2019-04-22 | 2019-07-15 | 2019-08-27
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G30-5676 | Process Equipment Datasheet - 10-TK-5676 - Oily Sludge Tank |  | Class 2 | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
Issue Plan
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-28
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-28 | 2019-06-19 | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00809 | TPSK-LSPA1-T-PE-01176 | TPSK-LSPA1-T-PE-01920 | TPSK-LSPA1-T-PE-02377
[6 empty] | Return Date | 2019-03-15 | 2019-04-22 | 2019-07-15 | 2019-08-27
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R2
| PE | OL1-2G30-5677 | Process Equipment Datasheet - 10-P-5676 - Oily Sludge Transfer Pump |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-02-06 | 2019-03-26
[6 empty] | Issue Actual | 2019-02-06 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00810 | TPSK-LSPA1-T-PE-01152
[6 empty] | Return Date | 2019-03-15 | 2019-04-12
[6 empty] | Owner Cmmt* | R2 | CL
| PE | OL1-2G30-5690 | Process Equipment Datasheet - 10-PK-5690 - Slop Tank Polymer Injection Pkg |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2019-02-07 | 2019-04-09
[6 empty] | Issue Actual | 2019-02-07 | 2019-04-09 | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00821 | TPSK-LSPA1-T-PE-01274 | TPSK-LSPA1-T-PE-02214
[6 empty] | Return Date | 2019-03-14 | 2019-05-16 | 2019-08-15
[6 empty] | Owner Cmmt* | R1 | R2 | R2
| PE | OL1-2G30-5691 | Process Equipment Datasheet - 10-PK-5691 - Slop Tank Acid Injection Pkg |  | Class 2 | Purpose** | IFR | IFD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-07 | 2019-04-09 | 2019-05-10
[6 empty] | Issue Actual | 2019-02-07 | 2019-04-09 | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00821 | TPSK-LSPA1-T-PE-01274 | TPSK-LSPA1-T-PE-01628
[6 empty] | Return Date | 2019-03-14 | 2019-05-16 | 2019-06-25
[6 empty] | Owner Cmmt* | R1 | R2 | R2
| PE | OL1-2G30-5695 | Process Equipment Datasheet - 10-PK-5695 - Bio Treat Sulfuric Acid Inj Pkg |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2019-05-10 | 2019-10-16
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01629
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5698 | Process Equipment Datasheet - 10-PK-5698 - Bio Treat Caustic Inj Pkg |  |  | Purpose** | IFR | IFD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2019-05-10 | 2019-10-16
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01629
[6 empty] | Return Date | 2019-06-04
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-5900 | Sulfuric Acid Tank PDS |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-11-26 | 2019-01-14
[6 empty] | Issue Actual | 2018-11-26 | 2019-01-14 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00364 | TPSK-LSPA1-T-PE-00647 | TPSK-LSPA1-T-PE-02701
[6 empty] | Return Date | 2018-12-17 | 2019-02-04
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G30-5901 | Process Equipment Datasheet - 10-P-5900 A-B - Sulfuric Acid Distribution Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2019-01-28 | 2019-03-28
[6 empty] | Issue Actual | 2019-01-28 | 2019-03-28 | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00738 | TPSK-LSPA1-T-PE-01177 | TPSK-LSPA1-T-PE-01678
[6 empty] | Return Date | 2019-03-04 | 2019-05-09 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | Re
| PE | OL1-2G30-5902 | Process Equipment Datasheet - 10-P-5901 A-B - Sulfuric Acid Metering Pumps |  |  | Purpose** | IFR | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-27 | 2019-01-31
[6 empty] | Issue Actual | 2018-12-27 | 2019-01-31 | 2019-03-22 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-00774 | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-01-24 | 2019-03-05 | 2019-04-04 | 2019-05-16
[6 empty] | Owner Cmmt* | R1 | R2 | R2 | R1
| PE | OL1-2G30-5905 | Process Equipment Datasheet - 10-P-5905 A-B - CTU Sulfuric Acid Metering Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-03-22
[6 empty] | Issue Actual |  | 2019-03-22 | 2019-04-12
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date |  | 2019-04-04 | 2019-05-16
[6 empty] | Owner Cmmt* |  | R2 | R1
| PE | OL1-2G30-5910 | Process Equipment Datasheet - 10-PK-5910 - Oxygen Scavenger Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-10 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-25 | 2019-03-15 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00727 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2019-01-04 | 2019-03-04 | 2019-04-02 | 2019-04-10 | 2019-08-06
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1 | R2
| PE | OL1-2G30-5912 | Process Equipment Datasheet - 10-PK-5912 - Neutralization Amine Inhibitor Inj Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-10 | 2019-01-25
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-25 | 2019-03-15 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00727 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2019-01-04 | 2019-03-04 | 2019-04-02 | 2019-04-10 | 2019-08-06
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1 | R2
| PE | OL1-2G30-5914 | Process Equipment Datasheet - 10-PK-5914 - Phosphate Injection Pkg |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-10
[6 empty] | Revised Plan | 2018-12-10 | 2019-01-28
[6 empty] | Issue Actual | 2018-12-10 | 2019-01-28 | 2019-03-15 | 2019-03-21 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00456 | TPSK-LSPA1-T-PE-00739 | TPSK-LSPA1-T-PE-01063 | TPSK-LSPA1-T-PE-01111 | TPSK-LSPA1-T-PE-02198
[6 empty] | Return Date | 2019-01-04 | 2019-03-04 | 2019-04-02 | 2019-04-10 | 2019-08-06
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1 | R2
| PE | OL1-2G30-5950 | Process Equipment Datasheet - 10-TK-5950 - Sodium Hypochlorite Tank |  |  | Purpose** | IFR | IFD | IFD | IFD | IFD
[6 empty] | Rev. | A | B | C | D | E
[6 empty] | Issue Plan | 2019-02-18 | 2019-03-18
[6 empty] | Revised Plan | 2018-12-04 | 2019-03-15
[6 empty] | Issue Actual | 2018-12-04 | 2019-03-15 | 2019-04-05 | 2019-05-17 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00406 | TPSK-LSPA1-T-PE-01055 | TPSK-LSPA1-T-PE-01258 | TPSK-LSPA1-T-PE-01679 | TPSK-LSPA1-T-PE-02701
[6 empty] | Return Date | 2019-01-22 | 2019-03-29 | 2019-05-09 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2 | R2 | R1
| PE | OL1-2G30-5951 | Process Equipment Datasheet - 10-P-5950 A-B - Olefins NaOCL Metering Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-22
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-22 | 2019-04-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00569 | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date | 2019-01-24 | 2019-04-04 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G30-5955 | Process Equipment Datasheet - 10-P-5955 A-B - CTU NaOCL Metering Pumps |  |  | Purpose** | IFR | IFD | IFD
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-01
[6 empty] | Revised Plan |  | 2019-03-22
[6 empty] | Issue Actual |  | 2019-03-22 | 2019-04-12
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01129 | TPSK-LSPA1-T-PE-01323
[6 empty] | Return Date |  | 2019-04-04 | 2019-05-16
[6 empty] | Owner Cmmt* |  | R2 | R1
| PE | OL1-2G30-6100 | Datasheet Cooling Water Basin Sluice Gates 10-Z-5301 A-I |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-09
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02387
[6 empty] | Return Date | 2019-08-29
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G30-6101 | Datasheet CTU Sump Sluice Gates Z-5302/Z-5303/Z-5304 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-09
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02387
[6 empty] | Return Date | 2019-08-29
[6 empty] | Owner Cmmt* | R2
| PE | OL1-4G30-1001 | See document number 036909C-1011-PDS-0117-1101 or OL1-2G30-1101 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-01
[6 empty] | Issue Actual | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00117
Return Date
Owner Cmmt*
| PE | OL1-4G30-1008 | See document number 036909C-1011-PDS-0630-1108 or OL1-2G30-1108 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-19
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-4G30-1009 | See document number 036909C-1011-PDS-0610-1109 or OL1-2G30-1109 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-19
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-1010 | See document number 036909C-1011-PDS-0610-1110 or OL1-2G30-1110 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-19
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-1011 | See document number 036909C-1011-PDS-1040-1111 or OL1-2G30-1111 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-27
[6 empty] | Issue Actual | 2018-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
| PE | OL1-4G30-2001 | See document number 036909C-1012-PDS-0117-1201 or OL1-2G30-1201 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-01
[6 empty] | Issue Actual | 2018-10-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00117
Return Date
Owner Cmmt*
| PE | OL1-4G30-2008 | See document number 036909C-1012-PDS-0630-1208 or OL1-2G30-1208 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-19
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-2009 | See document number 036909C-1012-PDS-0610-1209 or OL1-2G30-1209 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-19
[6 empty] | Issue Actual | 2018-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00066
Return Date
Owner Cmmt*
| PE | OL1-4G30-2011 | See document number 036909C-1012-PDS-1040-1211 or OL1-2G30-1211 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-27
[6 empty] | Issue Actual | 2018-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00090
[6 empty] | Return Date | 2018-10-12
[6 empty] | Owner Cmmt* | R1
Category Code: G31 Process Instrument Data sheets
| PE | OL1-2G31-1001 | Process Data Sheet For Analyzers Feed Preparation - Area 10 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-06-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-1101 | Process Data Sheet For Analyzers Recycle Gas Furnace - Area 11 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-06-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-1102 | Process Data Sheet For CEMS - Area 11 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-1103 | Process Data Sheet For Pitot Tube On Cems Furnace Area 10-H-1100 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-1112 | Process Equipment Datasheet - 10-ZZ-1100 - USC 36M Attemperator |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-14 | 2019-03-27
[6 empty] | Revised Plan | 2019-01-29
[6 empty] | Issue Actual | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00757
[6 empty] | Return Date | 2019-02-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-1190 | Process Datasheet for Restriction Orifice Furnace Area 10-H-1100 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-10 | 2019-08-21
[6 empty] | Issue Actual | 2019-06-10 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01830 | TPSK-LSPA1-T-PE-02452
[6 empty] | Return Date | 2019-07-08 | 2019-10-08
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G31-1201 | Process Data Sheet For Analyzers Liquid Cracking Furnace - Area 12 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-06-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-1202 | Process Data Sheet For CEMS - Area 12 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-1203 | Process Data Sheet For Pitot Tube On Cems Furnace Area 12-H-1200-1600 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01875
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-1212 | Process Equipment Datasheet - 10-ZZ-1200 - 1600 USC 132U Attemperator |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-12-14 | 2019-03-27
[6 empty] | Revised Plan | 2019-01-29
[6 empty] | Issue Actual | 2019-01-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00757
[6 empty] | Return Date | 2019-02-26
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-1290 | Process Datasheet for Restriction Orifice Furnace Area 10-H-1200_1600 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-31 | 2019-08-21
[6 empty] | Issue Actual | 2019-05-31 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01781 | TPSK-LSPA1-T-PE-02452
[6 empty] | Return Date | 2019-06-21 | 2019-10-08
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G31-2001 | Process Data Sheet For Analyzers Quench Oil - Area 20 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-06-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2090 | Process Datasheet for Restriction Orifice - Area 20 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-03
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02061
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-2101 | Process Data Sheet For Analyzer Quench Water - Dilution Steam - Area 21 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01634
[6 empty] | Return Date | 2019-06-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2190 | Process Datasheet for Restriction Orifice - Area 21 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02044
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-2301 | Process Data Sheet For Analyzers Caustic - Area 23 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01637
[6 empty] | Return Date | 2019-06-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2311 | SP Item Data Sheet - Desuperheater - SP-23011 - Superseded By OL1-2G31-2311 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02859
Return Date
Owner Cmmt*
| PE | OL1-2G31-2401 | Data Sheet For Analyzers Dehydration - Regen - Deprop - C2 Hydrog - Area 24 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01664
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2402 | Piping Specialty Item - Datasheet - Desuperheater - SP-24012 - Superseded by doc. n. OL1-2G31-2402 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02794
Return Date
Owner Cmmt*
| PE | OL1-2G31-2411 | Piping Specialty Item - Datasheet - Desuperheater - SP-24009 - Superseded by OL1-2G31-2411 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02794
Return Date
Owner Cmmt*
| PE | OL1-2G31-2501 | Data Sheet For Analyzers Cold Fractionation - Area 25 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01664
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2590 | Process Datasheet for Restriction Orifice Unit 25 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-28
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-2601 | Process Data Sheet For Analyzers Hot Fractionantion - Area 26 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01693
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2690 | Process Datasheet for Restriction Orifice - Unit 26 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02338
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-2701 | Process Data Sheet For Analyzers Ghu And C4 - C5 Hydrog - Area 27 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01693
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2710 | SP Item Datasheet - Desuperheater - HP Steam to E-2715 A-B & E-2725 A-C - SP-27010 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02794
Return Date
Owner Cmmt*
| PE | OL1-2G31-2790 | Process Datasheet for Restriction Orifice - Unit 27 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02338
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-2801 | Process Data Sheet For Analyzers Refrigeration Sytem - Area 28 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01693
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2890 | Process Datasheet for Restriction Orifice Unit 28 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-28
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2901 | Process Data Sheet For Analyzers Ethylene Auxiliariers - Area 29 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01693
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-2990 | Process Datasheet for Restriction Orifice Unit 29 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-28
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-3001 | Process Data Sheet For Analyzers Butadiene Extraction Unit Bdu - Area 30 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-01
[6 empty] | Issue Actual | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02027
[6 empty] | Return Date | 2019-07-18
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-3090 | Process Datasheet for Restriction Orifice Unit 30 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-15
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02436
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-3101 | SP Item Datasheet - BDU MP Steam Desuperheater - SP-31018 - Superseded by OL1-2G31-3101 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02794
Return Date
Owner Cmmt*
| PE | OL1-2G31-3102 | Process Data Sheet For BDU LP Desuperheater DH-3102 - Supersedes Doc. N. OL1-2P03-3119 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02794
Return Date
Owner Cmmt*
| PE | OL1-2G31-3190 | Process Datasheet for Restriction Orifice Unit 31 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-15
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02436
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-3990 | Process Datasheet for Restriction Orifice Unit 39 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-15
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02436
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-5101 | Process Data Sheeet For Analyzers BFW-Steam-Steam OCndensate System - Area 51 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01740
Return Date
Owner Cmmt*
| PE | OL1-2G31-5102 | SP Item Data Sheet - HP - MP Letdown Desuperheater - SP-51007 - Superseded by OL1-2G31-5102 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-10
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02586
Return Date
Owner Cmmt*
| PE | OL1-2G31-5103 | Process Data Sheet For MS/LS1 Desuperheater DH-3103 A/B - Ex Doc CLient Ref OL1-2P03-5106 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02605
[6 empty] | Return Date | 2019-10-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-5104 | SP Item Data Sheet - LP LS1 VLP LS2 Letdown Desuperheater - SP-51005 - Superseded by OL1-2G31-5104 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-10
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02586
Return Date
Owner Cmmt*
| PE | OL1-2G31-5151 | Process Data Sheet For SS/HS Desuperheater DH-5101 - Ex Doc Cliet Ref OL1-2P03-5108 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02605
[6 empty] | Return Date | 2019-10-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-5190 | Process Datasheet for Restriction Orifice - Area 51 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02044
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-5201 | Process Data Sheet For Analyzers Fuel System - Area 52 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01740
Return Date
Owner Cmmt*
| PE | OL1-2G31-5301 | Process Data Sheet For Anaqlyzers Cooling Water - Area 53 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01740
Return Date
Owner Cmmt*
| PE | OL1-2G31-5390 | Process Datasheet for Restriction Orifice Area 53 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-28
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-5501 | Data Sheet For Analyzers Vent Gas And Flare System - Area 55 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01816
[6 empty] | Return Date | 2019-06-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-5590 | Process Datasheet for Restriction Orifice - Area 55 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02044
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-5601 | Data Sheet For Analyzers Wastewater - Area 56 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01816
[6 empty] | Return Date | 2019-06-28
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G31-5690 | Process Datasheet for Restriction Orifice Area 56 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-28
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02018
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G31-5990 | Process Datasheet for Restriction Orifice Area 59 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-28
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02019
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
Category Code: G32 Process Safety Valve Data sheets
| PE | OL1-2G32-1101 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142A |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-12 | 2019-05-08
[6 empty] | Issue Actual | 2019-03-12 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01028 | TPSK-LSPA1-T-PE-01602
[6 empty] | Return Date | 2019-04-02 | 2019-05-31
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G32-1102 | USC 36M Steam Drum PSV Datasheet - 10-PSV-1142B |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-12 | 2019-05-08
[6 empty] | Issue Actual | 2019-03-12 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01028 | TPSK-LSPA1-T-PE-01602
[6 empty] | Return Date | 2019-04-02 | 2019-05-31
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G32-1103 | USC 36M Superheater Outlet PSV Datasheet - 10-PSV-1144 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-12 | 2019-05-08
[6 empty] | Issue Actual | 2019-03-12 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01028 | TPSK-LSPA1-T-PE-01602
[6 empty] | Return Date | 2019-04-02 | 2019-05-31
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G32-1201 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242A |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-12 | 2019-05-08
[6 empty] | Issue Actual | 2019-03-12 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01029 | TPSK-LSPA1-T-PE-01603
[6 empty] | Return Date | 2019-04-02 | 2019-05-31
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G32-1202 | USC 132U Steam Drum PSV Datasheet - 10-PSV-1242B |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-12 | 2019-05-08
[6 empty] | Issue Actual | 2019-03-12 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01029 | TPSK-LSPA1-T-PE-01603
[6 empty] | Return Date | 2019-04-02 | 2019-05-31
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G32-1203 | USC 132U Superheater Outlet PSV Datasheet - 10-PSV-1244 |  | Class 2 | Purpose** | IFR | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-12 | 2019-05-08
[6 empty] | Issue Actual | 2019-03-12 | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01029 | TPSK-LSPA1-T-PE-01603
[6 empty] | Return Date | 2019-04-02 | 2019-05-31
[6 empty] | Owner Cmmt* | R2 | R2
Category Code: G40 Block Flow Diagram
| PE | OL1-2G40-0010 | Block Flow Diagram - Olefins Unit 10 - 00-General - Overall Plant Scheme |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2018-10-10
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-19 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
Category Code: G41 Process Flow Diagrams
| PE | OL1-2G41-0001 | Process Flow Diagram - Olefins Unit 10 - 00-General - Legend & Symbols |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-0002 | Process Flow Diagram - Olefins Unit 10 - 00-General - Drawing Index |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-1001 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-1003 | Process Flow Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-1101 | Process Flow Diagram - Olefins Unit 10 - 11 - Furnaces - Recycle Gas Cracking Furnace |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-1201 | Process Flow Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-1901 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-1902 | Process Flow Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2001 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2002 | Process Flow Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2101 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2102 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2103 | Process Flow Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2201 | Process Flow Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-2301 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2302 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2303 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2304 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2305 | Process Flow Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-06-03 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R1 | R2
| PE | OL1-2G41-2401 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-2402 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-2403 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-2404 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2405 | Process Flow Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2501 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2502 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2503 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2504 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2505 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2506 | Process Flow Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-2601 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2602 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2603 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2604 | Process Flow Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2701 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Reactor & Depentanizer |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2702 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - GHU-1 Rerun Tower |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2703 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - Hydrog Reactivation Gas System |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2704 | Process Flow Diagram - Olefins Unit 10 - 27 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2801 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2802 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2803 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2804 | Process Flow Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-2901 | Process Flow Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-3001 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G41-3002 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Evaporation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-3003 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-3004 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-3005 | Process Flow Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-3101 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-3102 | Process Flow Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam and Condensate System |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G41-3901 | Process Flow Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-23 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
Category Code: G42 Utility Flow Diagrams
| PE | OL1-2G42-5001 | Utility Flow Diagram - Olefins Unit 10 - 50 - Water System - Treated Potable and Demin Water Systems |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5101 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Steam Balance Diagram |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5102 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate and Boiler Feedwater Systems |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5103 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Condensate Treatment System |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5104 | Utility Flow Diagram - Olefins Unit 10 - 51 - BFW Steam and Condensate System - Furnace Blowdown System |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5201 | Utility Flow Diagram - Olefins Unit 10 - 52 - Fuel System - Fuel Gas System |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5301 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Water Diagram |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5311 | Utility Flow Diagram - Olefins Unit 10 - 53 - Cooling Water System - Cooling Tower |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5401 | Utility Flow Diagram - Olefins Unit 10 - 54 - Air and Nitrogen System - Plant Air Instrument Air and Nitrogen Systems |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5501 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Flare and Blowdown System |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5502 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Process Vent Gas Collection |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5511 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - HP - LLDPE LP Flare |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5512 | Utility Flow Diagram - Olefins Unit 10 - 55 - Vent Gas and Flare System - Enclosed Ground Flare |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5601 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Collection |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5602 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Surface Runoff Collection |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5603 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Cracker Holding Basin |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5604 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Domestic Wastewater Collection |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5610 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - HP Flare Area SW & Oily WW Collection |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5611 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - OSBL Oily Wastewater Collection |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5612 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Oily Wastewater Equalization Tank |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5613 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - CPI & IGF Packages |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5614 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Biotreatment Package |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5615 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Check Basin |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
| PE | OL1-2G42-5616 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Sludge Dewatering Package |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5617 | Utility Flow Diagram - Olefins Unit 10 - 56 - Wastewater - Slop & Oil Sludge |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5901 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R1
| PE | OL1-2G42-5911 | Utility Flow Diagram - Olefins Unit 10 - 59 - Utilities Auxilliaries - Complex U & O Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFD | IFD
[6 empty] | Rev. |  | A | B | C | D
[6 empty] | Issue Plan | 2018-08-27 |  | 2019-06-20
[6 empty] | Revised Plan |  | 2018-08-24 | 2018-10-11
[6 empty] | Issue Actual |  | 2018-08-24 | 2018-10-11 | 2019-04-30 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-00026 | TPSK-LSPA1-T-PE-00155 | TPSK-LSPA1-T-PE-01516 | TPSK-LSPA1-T-PE-02422
[6 empty] | Return Date |  | 2018-10-29 | 2018-12-27 | 2019-05-29 | 2019-09-24
[6 empty] | Owner Cmmt* |  | A3 | A3 | R2 | R2
Category Code: G43 Process and Instrument Diagrams (P&ID)
| PE | OL1-2G43-0001 | P&ID- Olefins Unit 10- Common- Abreviations And Numbering |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-11-15 | 2019-03-28 | 2019-09-27 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-28 | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02709
[6 empty] | Return Date | 2019-02-11 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-0002 | P&ID- Olefins Unit 10- Common- Piping Symbols |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-11-15 | 2019-03-28 | 2019-09-27 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-28 | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02709
[6 empty] | Return Date | 2019-02-11 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-0003 | P&ID- Olefins Unit 10- Common- Instrumentation Symbols |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-11-15 | 2019-03-28 | 2019-09-27 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-28 | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02709
[6 empty] | Return Date | 2019-02-11 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-0004 | P&ID- Olefins Unit 10- Common- Equipment Symbols 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-11-15 | 2019-03-28 | 2019-09-27 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-28 | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02709
[6 empty] | Return Date | 2019-02-11 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-0005 | P&ID- Olefins Unit 10- Common- Equipment Symbols 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-11-15 | 2019-03-28 | 2019-09-27 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-28 | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02709
[6 empty] | Return Date | 2019-02-11 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-0010 | P&ID- Olefins Unit 10- Common-Instrument Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-05-16 | 2019-05-16 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-11-15 | 2019-03-28 | 2019-09-27 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-28 | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02709
[6 empty] | Return Date | 2019-02-11 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-0011 | P&ID- Olefins Unit 10- Common-EIV Block Valve Typical |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2018-11-15 | 2019-03-28 | 2019-09-27
[6 empty] | Issue Actual | 2018-11-15 | 2019-03-28 | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02709
[6 empty] | Return Date | 2019-02-11 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-0013 | P&ID- Olefins Unit 10- Common- Typicals For Motors |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-27
[6 empty] | Issue Actual | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02709
Return Date
Owner Cmmt*
| PE | OL1-2G43-0014 | P&ID- Olefins Unit 10- Common- Typicals For Motors |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-27
[6 empty] | Issue Actual | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02709
Return Date
Owner Cmmt*
| PE | OL1-2G43-0015 | P&ID- Olefins Unit 10- Common- Typicals For Mov |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-27
[6 empty] | Issue Actual | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02709
Return Date
Owner Cmmt*
| PE | OL1-2G43-0016 | P&ID- Olefins Unit 10- Common- Typicals For Mov |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-27
[6 empty] | Issue Actual | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02709
Return Date
Owner Cmmt*
| PE | OL1-2G43-0017 | P&ID- Olefins Unit 10- Common- Typicals For ON-OFF Valves-1 |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-27
[6 empty] | Issue Actual | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02709
Return Date
Owner Cmmt*
| PE | OL1-2G43-0018 | P&ID- Olefins Unit 10- Common- Typicals For ON-OFF Valves-2 |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-27
[6 empty] | Issue Actual | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02709
Return Date
Owner Cmmt*
| PE | OL1-2G43-0019 | P&ID- Olefins Unit 10- Common- Typicals For Control Valves |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-27
[6 empty] | Issue Actual | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02709
Return Date
Owner Cmmt*
| PE | OL1-2G43-1001 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Liquid Feed Heater |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1002 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Feed Heater |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1003 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Drum & LPG Vaporizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1004 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Superheater |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1005 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - LPG Steam Vaporizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1006 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - LPG Feed Steam Heater |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date |  | 2019-05-05 | 2019-09-11
[6 empty] | Owner Cmmt* |  | CA | R2
| PE | OL1-2G43-1023 | P&ID - Olefins Unit 10 - Feed Preparation and Furnaces - C2 Feed Superheater |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1030 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1031 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1035 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution Utility Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1036 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Cracking Furnace Distribution Utility Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1090 | P&ID - Olefins Unit 10 - Feed Preparation And Furnaces - Naphtha Feed - C3 LPG Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-14
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date |  |  | 2019-09-11
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-1101 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed Distribution Header |  | Class 2 | Purpose** | IFR | IBD | IDD1
[6 empty] | Rev. | A | B | C
Issue Plan
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1105 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Dilution Steam Distribution Header |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1106 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoke Air Header Distribution Header |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1107 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1108 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1109 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1110 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed-Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1111 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 5 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1112 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Feed- Sheet 6 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1115 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Convection Section |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1116 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 1 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1117 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 2 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1118 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell A - Sheet 3 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1119 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 4 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1120 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 5 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1121 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Radiant Section Cell B - Sheet 6 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1125 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - TLX Quench Exchangers |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1126 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Furnace Effluent And Decoke MOVs |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1127 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - USX Drain Header |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1128 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - SHP Steam Drum |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1129 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Drum-USX And TLX-1 Risers |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1130 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Boiler Feed Water Supply Export Steam |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-1131 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Steam Coils |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1135 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Fuel Gas |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1140 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Burners |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1145 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Decoking Effluent |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1150 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Flue Gas |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1160 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Utility Stations |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-10
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02578
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-1165 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - MOV Purge Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02578
[6 empty] | Return Date |  |  | 2019-10-08
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-1170 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Instrument Air Distribution |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-10
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02578
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-1175 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1100 - Cooling Water Supply and Return |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02578
[6 empty] | Return Date |  |  | 2019-10-08
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-1201 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - C3 LPG Feed Distribution Header |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1202 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Liquid Feed Distribution Header |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1205 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Dilution Steam Distribution Header |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1206 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Decoke Air Header Distribution Header |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1207 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1208 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1209 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1210 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1211 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 5 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1212 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Feed- Sheet 6 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1215 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Convection Section |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1216 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 1 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1217 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 2 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1218 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 |  |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323
[6 empty] | Return Date | 2019-02-11
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-1218. | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell A - Sheet 3 |  | Class 2 | Purpose** | IBD
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-02-13
[6 empty] | Issue Actual | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-04-10
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-1219 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 4 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1220 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 5 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1221 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Radiant Section Cell B - Sheet 6 |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1225 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - TLX Exchanger |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1226 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Furnace Effluent & Decoke MOV's |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1227 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - SLE Drain Header |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1228 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Shp Steam Drum |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1229 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Drum-SLE And TLX Risers |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1230 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Boiler Feed Water Supply Export Steam |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1231 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Steam Coils |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1235 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-11 | 2019-04-10 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1240 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Burners |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1245 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Flue Gas |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1250 | P&ID - Olefins Unit 10 - Liquid Cracking Furnace 10-H-1200 - Fuel Gas |  |  | Purpose** | IFR | IBD | IFD | IFF
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28 | 2019-05-24 | 2019-10-14
[6 empty] | Revised Plan | 2018-11-15 | 2019-02-13 |  | 2019-11-29
[6 empty] | Issue Actual | 2018-11-15 | 2019-02-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00323 | TPSK-LSPA1-T-PE-00850
[6 empty] | Return Date | 2019-02-11 | 2019-04-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-1260 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1200 - Utility Stations |  | Class 2 | Purpose** | IDD1
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-10
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02578
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G43-1265 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1200 - MOV Purge Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02578
[6 empty] | Return Date |  |  | 2019-10-08
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-1270 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1200 - Instrument Air Distribution |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02578
[6 empty] | Return Date |  |  | 2019-10-08
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-1275 | P&ID - Olefins Unit 10 - Recycle Gas Cracking Furnace 10-H-1200 - Cooling Water Supply and Return |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02578
[6 empty] | Return Date |  |  | 2019-10-08
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-1315 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 CONVECTION SECTION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1316 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 1 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1317 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 2 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1318 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL A - SHEET 3 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1319 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 4 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1320 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 5 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1321 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 RADIANT SECTION CELL B - SHEET 6 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1325 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 TLX EXCHANGER - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1327 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 INTERMITTENT BLOWDOWN HEADER - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1328 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 VHP STEAM DRUM - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1329 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM DRUM-USX AND TLX RISERS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1331 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 STEAM COILS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1340 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 BURNERS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1345 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 DECOKING EFFLUENT - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1350 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 FLUE GAS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1360 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY STATION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1361 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1300 UTILITY DISTRIBUTION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1415 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 CONVECTION SECTION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1416 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 1 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1417 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 2 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1418 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL A - SHEET 3 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1419 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 4 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1420 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 5 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1421 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 RADIANT SECTION CELL B - SHEET 6 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1425 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 TLX EXCHANGER - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1427 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 INTERMITTENT BLOWDOWN HEADER - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1428 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 VHP STEAM DRUM - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1429 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM DRUM-USX AND TLX RISERS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1431 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 STEAM COILS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1440 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 BURNERS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1445 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 DECOKING EFFLUENT - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1450 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 FLUE GAS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1460 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY STATION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1461 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1400 UTILITY DISTRIBUTION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1515 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 CONVECTION SECTION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1516 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 1 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1517 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 2 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1518 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL A - SHEET 3 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1519 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 4 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1520 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 5 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1521 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 RADIANT SECTION CELL B - SHEET 6 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1525 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 TLX EXCHANGER - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1527 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 INTERMITTENT BLOWDOWN HEADER - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1528 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 VHP STEAM DRUM - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1529 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM DRUM-USX AND TLX RISERS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1531 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 STEAM COILS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1540 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 BURNERS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1545 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 DECOKING EFFLUENT - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1550 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 FLUE GAS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1560 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY STATION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1561 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1500 UTILITY DISTRIBUTION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1615 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 CONVECTION SECTION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1616 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 1 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1617 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 2 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1618 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL A - SHEET 3 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1619 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 4 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1620 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 5 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1621 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 RADIANT SECTION CELL B - SHEET 6 - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1625 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 TLX EXCHANGER - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1627 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 INTERMITTENT BLOWDOWN HEADER - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1628 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 VHP STEAM DRUM - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1629 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM DRUM-USX AND TLX RISERS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1631 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 STEAM COILS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1640 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 BURNERS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1645 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 DECOKING EFFLUENT - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1650 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 FLUE GAS - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1660 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY STATION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1661 | PIPING & INSTRUMENT DIAGRAM CRACKING FURNACE 1 10-H-1600 UTILITY DISTRIBUTION - (Duplication after IFC Issue) |  |  | Purpose** | IFF
Rev.
[6 empty] | Issue Plan | 2019-10-14
[6 empty] | Revised Plan | 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G43-1901 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - Dmds Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-1915 | P&ID - Olefins Unit 10 - Furnace Auxiliaries - Decoke Air Receiver |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2001 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Tower |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2003 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2005 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Filtration |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2006 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2007 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2008 | P&ID - Olefins Unit 10 - Quench Oil - VLP Steam Generation - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date |  | 2019-04-05 | 2019-09-13
[6 empty] | Owner Cmmt* |  | CA | R2
| PE | OL1-2G43-2020 | P&ID - Olefins Unit 10 - Quench Oil - Light Fuel Oil Stripper |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2021 | P&ID - Olefins Unit 10 - Quench Oil - Fuel Oil Product Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2022 | P&ID - Olefins Unit 10 - Quench Oil - Purge Oil Filtration |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2025 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Stripper |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2026 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2027 | P&ID - Olefins Unit 10 - Quench Oil - Heavy Fuel Oil Product Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2040 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2042 | P&ID - Olefins Unit 10 - Quench Oil - Quench Oil Drain Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-03-28 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-03-28 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01180 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2090 | P&ID - Olefins Unit 10 - Quench Oil - Cracker Product- Hexane- Flux Oil Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-15
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date |  |  | 2019-09-13
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2101 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Tower |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2102 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Tower Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2104 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Quench Oil Fractionator Reflux |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2106 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2108 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Distribution |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2110 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2115 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Drain Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2117 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Quench Water Drain Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2120 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Distillate Stripper |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2122 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Distillate Stripper Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2123 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Process Water Stripper Feed |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2125 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Process Water Stripper |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2126 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Process Water Stripper Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2127 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator Feed Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2130 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Feed Heating |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2131 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Generator |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2132 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Reboilers - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2134 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Generator Reboilers - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2137 | P&ID - Olefins Unit 10 - Quench Water - Dilution Steam - Dilution Steam Superheating |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2138 | P&ID - Olefins Unit 10 - Quench Water and Dilution Steam - Dilution Steam Blowdown Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02473
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2201 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Suction Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2203 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st and 2nd Stages |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2204 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 1st Stage Aftercooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2206 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Suction Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2208 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 2nd Stage Aftercooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2210 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Suction Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2211 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd and 4th Stages |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2212 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 3rd Stage Aftercooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2214 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Suction Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2215 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Aftercooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2217 | P&ID - Olefins Unit 10 - Cracked Gas Compression - CG Compressor 4th Stage Discharge Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2220 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2222 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Water Injection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2224 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Wash Oil Injection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-01 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-01 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00566 | TPSK-LSPA1-T-PE-01201 | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date | 2019-02-21 | 2019-04-22 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2290 | P&ID - Olefins Unit 10 - Cracked Gas Compression - Propylene Off Gas-C2 Off-C3-C4 Vapor Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-26
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02478
[6 empty] | Return Date |  |  | 2019-09-16
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2301 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic Tower |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2303 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Weak-Intermediate Caustic Circulation |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2305 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Strong Caustic Circulation |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2310 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Fresh Caustic Supply |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2311 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Deoiling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2313 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Degassing |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2314 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Drain Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2315 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic Drain Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2316 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic Drain Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2317 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Yellow Oil Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2318 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Drain Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2319 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Skim Oil Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2320 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Storage |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2325 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Stripper Feed Heater |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2326 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Stripper |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2328 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Spent Caustic Stripper Ovhd Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2329 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Wet Air Oxidation Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date | 2019-02-21 |  | 2019-09-16
[6 empty] | Owner Cmmt* | R2 |  | R2
| PE | OL1-2G43-2390 | P&ID - Olefins Unit 10 - Caustic And Spent Caustic Treatment - Caustic - Vent Gas Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-26
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02477
[6 empty] | Return Date |  |  | 2019-09-16
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2401 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Caustic Tower Overhead Chilling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2402 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Caustic Tower Overhead Ko Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2404 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Liquid Drier Feed Coalescer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2406 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Liquid Driers - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2407 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Liquid Driers - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2409 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Dehydration - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2410 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Dehydration - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2412 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Regeneration Gas Heating |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2414 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Regeneration Gas Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2419 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - Cracked Gas Mercury Adsorber |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2420 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer Feed Chilling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2422 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2423 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2425 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2426 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2427 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - LP Depropanizer Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2428 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer Product-Reflux Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2430 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - 5th Stage Cracked Gas Compression |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2432 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - CG Compressor 5th Stage Aftercooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2433 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Arsine Guard Removal |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2435 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Feed Heating |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2437 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor A |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2438 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor A Intercooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2439 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor B |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2440 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation Reactor B Intercooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2442 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - C2 Hydrogenation Reactor C |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2444 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - CG Secondary Dehydrator |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2446 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Reflux Chilling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2447 | P&ID - Olefins Unit 10 - Dehydration Regen Deprop C2 Hydrog - HP Depropanizer Reflux |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2018-12-27 | 2019-04-08 | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2018-12-27 | 2019-04-08 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00567 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date | 2019-02-21 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2490 | P&ID - Olefins Unit 10 - Dehydration - Regen - Deprop - C2 Hydrog - Off-Spec Ethylene Liquid Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-21 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-21
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02459
[6 empty] | Return Date |  |  | 2019-09-16
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2501 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Chilling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2503 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No. 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2505 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No. 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2507 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Feed Separator No. 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2511 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Prefractionator |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2513 | P&ID - Olefins Unit 10 - Cold Fractionation - Demeth Prefrac Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2515 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier Condenser |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2517 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Rectifier |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2520 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Feed Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2521 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2522 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2525 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander Suction-Discharge Drums |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2527 | P&ID - Olefins Unit 10 - Cold Fractionation - Residue Gas Expander-Recompressor |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2529 | P&ID - Olefins Unit 10 - Cold Fractionation - Hydrogen Recovery |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2530 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2531 | P&ID - Olefins Unit 10 - Cold Fractionation - Propylene Refrigerant Subcooler - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2532 | P&ID - Olefins Unit 10 - Cold Fractionation - Pressure Swing Absorption Unit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2541 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2543 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2546 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Condenser |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2547 | P&ID - Olefins Unit 10 - Cold Fractionation - Deethanizer Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2551 | P&ID - Olefins Unit 10 - Cold Fractionation - Demethanizer Bottoms |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2552 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2553 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Bottoms Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2554 | P&ID - Olefins Unit 10 - Cold Fractionation - C2 Tower Side Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2556 | P&ID - Olefins Unit 10 - Cold Fractionation - Ethane Recycle Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-08 | 2019-04-08 | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-08 | 2019-04-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00612 | TPSK-LSPA1-T-PE-01264 | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date | 2019-02-25 | 2019-05-09 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2561 | P&ID- Olefins Unit 10- Cold Fractionation- Seal Gas Expander |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-29 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-29
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date |  |  | 2019-09-24
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2562 | P&ID- Olefins Unit 10- Cold Fractionation- Residue Gas Expander-Compressor |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-29 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-29
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date |  |  | 2019-09-24
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2563 | P&ID- Olefins Unit 10- Cold Fractionation- Residue Gas Expander-Compressor |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-29 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-29
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date |  |  | 2019-09-24
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2590 | P&ID - Olefins Unit 10 - Cold Fractionation - Hydrogrn Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-27 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-27
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02489
[6 empty] | Return Date |  |  | 2019-09-16
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2601 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2602 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Guard Adsorbers - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2603 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Arsine Guard Bed |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2604 | P&ID - Olefins Unit 10 - Hot Fractionation - Feed Section |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2605 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Reactors - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2608 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Aftercooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2610 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Hydrogenation Recycle |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2615 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2616 | P&ID - Olefins Unit 10 - Hot Fractionation - Secondary Deethanizer Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2620 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2621 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Reboilers |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2622 | P&ID - Olefins Unit 10 - Hot Fractionation - C3 Tower Bottoms |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2625 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2627 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2628 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Overhead Product-Reflux |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-10 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-10 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01294 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-05-16 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2629 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Cooling |  |  | Purpose** | IFR | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 |  | 2019-05-07 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-03-15 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-04-12 | 2019-07-02 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R2
| PE | OL1-2G43-2630 | P&ID - Olefins Unit 10 - Hot Fractionation - C5-Pygas Surge Drum |  |  | Purpose** | IFR | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C | D
[6 empty] | Issue Plan | 2019-02-20 |  | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 |  | 2019-05-07 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-03-15 | 2019-05-07 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-04-12 | 2019-07-02 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R1 | R2
| PE | OL1-2G43-2631 | P&ID - Olefins Unit 10 - Hot Fractionation - Debutanizer Bottoms Pumps |  | Class 2 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-11
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01298
[6 empty] | Return Date | 2019-02-25 | 2019-05-16
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-2690 | P&ID - Olefins Unit 10 - Hot Fractionation - RAW C4S - PYGAS - OFF-SPEC PROPYLENE BATTERY LIMIT |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-14
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date |  |  | 2019-09-03
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2701 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Feed Heating |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2702 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2703 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Reactors - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2704 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Hot Separator |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2705 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Cold Separator |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2706 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2707 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU C5 Cut Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2708 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Depentanizer Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2710 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Rerun Tower |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2711 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Condenser |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2712 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU Rerun Tower Reflux-Product Pump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2713 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Product - Wash Oil Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2715 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - GHU-1 Recycle Wash Oil |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2716 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Pygas Fuel Oil Product |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2717 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Refun Tower Liquid Ring Pump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2718 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Anti-Oxidant Injection Package |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2720 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Reactivation Gas Heating |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2722 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Regeneration Decoke Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2730 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Surge Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2732 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Pump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2733 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Feed Heating |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2734 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Reactor |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2736 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Separator Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2738 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - C4-C5 Hydrogenation Recycle-Product Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2740 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2742 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Light Oil Drain Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-07 | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-07 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01061 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date | 2019-04-12 | 2019-07-02 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-2790 | P&ID - Olefins Unit 10 - GHU & C4-C5 Hydrog - Pygas - C4/C5 - Treated Gas Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-22 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-22
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02471
[6 empty] | Return Date |  |  | 2019-09-16
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2801 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2802 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2803 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Condenser |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2804 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Receiver |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2805 | P&ID - Olefins Unit 10 - Refrigeration System - Hp C3 Refrigeration Distribution |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2806 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 4th Stage Suction |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2807 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Compressor - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2808 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 3rd Stage Suction |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2810 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 2nd Stage Suction |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2812 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant 1st Stage Suction |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2814 | P&ID - Olefins Unit 10 - Refrigeration System - C3 Refrigerant Drain Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2816 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Pump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2818 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2819 | P&ID - Olefins Unit 10 - Refrigeration System - Propylene Product Chilling - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2821 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2822 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2823 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Compressor - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date |  | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* |  | R2 | R2
| PE | OL1-2G43-2824 | P&ID - Olefins Unit 10 - Refrigeration System - C2 Refrigerant Desuperheaters |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2825 | P&ID - Olefins Unit 10 - Refrigeration System - C2R Desuperheater And Condenser |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2828 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Surge Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2830 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Liquid Product Chiller |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2834 | P&ID - Olefins Unit 10 - Refrigeration System - HP Ethylene Vapor Product |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2836 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 3rd Stage Suction |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2838 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 2nd Stage Suction |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2840 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant 1st Stage Suction |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2842 | P&ID - Olefins Unit 10 - Refrigeration System - LP Ethylene Product Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2846 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Refrigerant Drain Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-01-16 | 2019-04-15 | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-01-16 | 2019-04-15 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00653 | TPSK-LSPA1-T-PE-01345 | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date | 2019-02-25 | 2019-07-02 | 2019-09-13
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2890 | P&ID - Olefins Unit 10 - Refrigeration System - HP Vapor-Liquid Ethylene-HP-LP Propylene BL |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-15 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-15
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date |  |  | 2019-09-13
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2891 | P&ID - Olefins Unit 10 - Refrigeration System - Ethylene Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-16 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-16
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02434
[6 empty] | Return Date |  |  | 2019-09-13
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2901 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - pH Control - Corrosion Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2902 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Emulsion Breaker Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2903 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Process Water Stripping Chemical Injection Pkg |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2904 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - DSG Anti Foulant Injection Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2905 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Polymerization Inhibitor Injection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2906 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C4 Polymer Inhibitor Injection Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2907 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Caustic Tower Anti Foulant Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2908 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Neutralization Injection |  | Class 2 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397
[6 empty] | Return Date | 2019-02-25 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-2909 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Methanol Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2910 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Anti-Oxidant Injection Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-08-14
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date |  |  | 2019-09-11
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-2915 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Wash Oil Storage |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2920 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - Quench Oil Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-04 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-04 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2922 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - Quench Water Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2924 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - DSG Feed Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2930 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02406
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2932 | P&Id - Olefins Unit 10 - Ethylene Auxiliaries - CG Compressor Auxiliaries - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2934 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - CGC Lube Oil Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-11
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2955 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C3 Refrig Compressor Turbine Details - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2960 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C3R Refrig Compressor Turbine Details - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2965 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C3R Compressor Lube Oil Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2970 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2975 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Compressor Auxiliaries Details - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-2976 | P&ID - Olefins Unit 10 - Ethylene Auxiliaries - C2R Lube Oil Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-02-05 | 2019-04-18 | 2019-08-14 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-02-05 | 2019-04-18 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00799 | TPSK-LSPA1-T-PE-01397 | TPSK-LSPA1-T-PE-02403
[6 empty] | Return Date | 2019-02-25 | 2019-06-03 | 2019-09-03
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3001 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Feed Drum & Feed Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3002 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Tower & Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3003 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Tower Trim Reboilers |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3004 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Predistillation Tower Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3005 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 Vaporization Tower & Heavy End Disch Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3006 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 Vaporizers |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3007 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Main Washer & Solvent Cooler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3008 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Main Washer Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3009 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Main Washer Bottom Pump & Reflux Pump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3010 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Rectifier |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3011 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Rectifier Pump And Degasser Feed Pump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3012 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - After Washer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-04-12 | 2019-06-17 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3013 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - After Washer Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-04-12 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3014 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Solvent Heat Exchangers - I |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-04-12 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3015 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Solvent Heat Exchanger-II And Solvent Heater |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-04-12 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3016 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Direct Cooler And NMP Cooler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3017 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Degassing Tower And Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3018 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Direct Cooler Pump & Degasser Bottom Pump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3019 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - HC - Water Separator |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3020 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Acetylene Wash Condenser |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3021 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Acetylene Condenser And Accumulator |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3022 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 Acetylene Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3023 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Recycle Gas Compressor |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3024 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3025 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower Reboilers |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3026 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower Bottom Pump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3027 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Tower Overhead |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3028 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Drying Tower And Reboiler |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3029 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - Butadiene Product To B L |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-25
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3090 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit BDU - C4 - Butadiene - OFF-SPEC 1-3 BD Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02574
[6 empty] | Return Date |  |  | 2019-09-25
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-3101 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Solvent Regeneration |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3102 | P&ID- Olefins Unit 10- Butadiene Extraction Unit Utlities- Water Washer And Condenser |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3103 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer And Condenser |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3104 | P&ID- Olefins Unit 10- Butadiene Extraction Unit Utlities- Water Washer Accumulator & Solvent Return Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3105 | P&ID- Olefins Unit 10- Butadiene Extraction Unit Utilities- Ejector Seal Drum And Waste Water Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3106 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Regen Steam Ejector Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3107 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3108 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Water Washer Accumulator & Solvent Return Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3109 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Condensate Drum And Recycle Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-29 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-3110 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - Ejector Seal Drum And Waste Water Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-30 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | CA | R2 | R2
| PE | OL1-2G43-3111 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - BDU Steam Letdown |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-13 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02633
[6 empty] | Return Date | 2019-03-30 | 2019-06-21 | 2019-10-01
[6 empty] | Owner Cmmt* | CA | R2 | R2
| PE | OL1-2G43-3112 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-30 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | CA | R1 | R2
| PE | OL1-2G43-3113 | P&ID - Olefins Unit 10 - Butadiene Extraction Unit Utilities - NMP Slop Drain System - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-30 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | CA | R1 | R2
| PE | OL1-2G43-3901 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - NMP Storage |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-30 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | CA | R2 | R2
| PE | OL1-2G43-3902 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Solvent Inhibitor Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-30 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | CA | R2 | R2
| PE | OL1-2G43-3903 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Product Inhibitor Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-30 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | CA | R2 | R2
| PE | OL1-2G43-3904 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Anti-Foam Agent Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-30 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | CA | R2 | R2
| PE | OL1-2G43-3905 | P&ID - Olefins Unit 10 - C4 Unit Auxiliaries - Predistillation Inhibitor System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-03-15 | 2019-05-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-03-15 | 2019-05-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01067 | TPSK-LSPA1-T-PE-01722 | TPSK-LSPA1-T-PE-02602
[6 empty] | Return Date | 2019-03-30 | 2019-06-21 | 2019-09-24
[6 empty] | Owner Cmmt* | CA | R2 | R2
| PE | OL1-2G43-5001 | P&Id - Olefins Unit 10 - Water System - Treated - Potable - Demin - Demineralized Water |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5010 | P&Id - Olefins Unit 10 - Water System - Treated - Potable - Demin - Supporting Utilities Auxiliaries Treated Water |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-15 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5020 | P&Id - Olefins Unit 10 - Water System -Treated - Potable - Demin - Potable Water |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-23 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-23 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5090 | P&ID- Olefins Unit 10- Water System -Treated Potable Demin- Demin- Potable- Treated Water Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02588
Return Date
Owner Cmmt*
| PE | OL1-2G43-5101 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5102 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Stations - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5103 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Steam Letdown Station - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5105 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Deaerator |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-09-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5110 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Boiler Feedwater Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-09-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5111 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Boiler Feedwater Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-09-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5113 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP & HP BFW Distribution |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5114 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP BFW Distribution |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5115 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-11 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02609
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5118 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Suspect Condensate Cooling |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-09-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5120 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Carbon Filters |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-09-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5125 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Raw Condensate Tank |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5127 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-09-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5128 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Polisher - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-09-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5130 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Condensate Tank |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5132 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Low Pressure Steam Flash Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-09-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5134 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - Furnace Blowdown System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-09-27
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5135 | P&ID- Olefins Unit 10- BFW-Steam- Steam Condensate System- Condensate Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-09-04
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date |  |  | 2019-09-27
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G43-5140 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP Steam Distribution |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5143 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribtion - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5144 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - HP Steam Distribution - Sheet 02 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5145 | P&ID- Olefins Unit 10- BFW- Steam- Steam Condensate System- VLP BFW Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-09-04
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date |  |  | 2019-09-27
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G43-5150 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 01 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5151 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5152 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Steam Distribution - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5153 | P&ID- Olefins Unit 10-BFW- Steam- Steam Condensate System- SHP BFW Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-09-04
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date |  |  | 2019-09-27
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G43-5160 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5161 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5162 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5163 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5164 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 5 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5166 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Steam LS1 Distribution - Sheet 6 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5168 | P&ID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Steam LS2 Distribution - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5170 | PID - Instrument Diagram Olefins Unit 10 - BFW - Steam - Steam Condensate System - SHP - HP Condensate Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5172 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - MP Condensate Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5176 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5177 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5178 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - LP Condensate Collection - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5179 | PID - Olefins Unit 10 - BFW - Steam - Steam Condensate System - VLP Condensate Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00718 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5180 | P&ID- Olefins Unit 10- BFW-Steam- Steam Condensate System- SHP BFW Lube Oil Pump Turbine A Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-09-04
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date |  |  | 2019-09-27
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G43-5183 | P&ID- Olefins Unit 10- BFW- Steam- Steam Condensate System- SHP BFW Lube Oil Pump Turbine B Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-09-04
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date |  |  | 2019-09-27
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G43-5186 | P&ID- Olefins Unit 10- BFW- Steam Condensate System- VLP BFW Lube Oil Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-09-04 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-09-04
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02564
[6 empty] | Return Date |  |  | 2019-09-27
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G43-5190 | P&ID- Olefins Unit 10- BFW- Steam- Steam Condensate System- Return Condensate-HP Steam- HBFW BL |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02588
Return Date
Owner Cmmt*
| PE | OL1-2G43-5201 | PID - Olefins Unit 10 - Fuel System - Fuel Gas |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-06-19 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5202 | PID - Olefins Unit 10 - Fuel System - Fuel Gas Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-06-19 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5203 | PID - Olefins Unit 10 - Fuel System - Pilot Gas Vaporizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-06-19 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5210 | PID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-06-19 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5211 | PID - Olefins Unit 10 - Fuel System - Fuel Gas Distribution - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-26 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-26 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-26 | 2019-06-19 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5301 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Tower - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5302 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Tower - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5303 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Tower - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5305 | P&Id - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5306 | P&Id - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Supply Pumps - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5307 | P&Id - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply Pumps |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5310 | P&Id - Olefins Unit 10 - Cooling Water - Olefins Cooling Water Suppy |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5311 | P&Id - Olefins Unit 10 - Cooling Water - CTU Cooling Water Supply |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5313 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-08-30
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date |  |  | 2019-09-17
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5314 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-08-30
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date |  |  | 2019-09-17
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5315 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Side Stream Filter Package Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5317 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Filter Backwash |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5320 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5321 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-09-11 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02609
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5322 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5323 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-09-11 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02609
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5324 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 5 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5325 | P&ID - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 06 |  | Class 2 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425
[6 empty] | Return Date | 2019-02-15 | 2019-06-04
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-5326 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Distribution - Sheet 7 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5330 | P&Id - Olefins Unit 10 - Cooling Water - Olefins CW Pump Turbine Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-08-30
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02542
[6 empty] | Return Date |  |  | 2019-09-19
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5333 | P&Id - Olefins Unit 10 - Cooling Water -Olefins CW Pump Turbine Details - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-08-30
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date |  |  | 2019-09-17
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5339 | P&Id - Olefins Unit 10 - Cooling Water - CTU Cooling Water Pump Turbine Details |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-08-30
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date |  |  | 2019-09-17
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5351 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Chemical Injection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5352 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Corrosion Inhibitor Injection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5390 | P&Id - Olefins Unit 10 - Cooling Water - Cooling Water Return - Cooling Water Supply B L |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-08-30
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date |  |  | 2019-09-17
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5401 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-5402 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-5403 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-5404 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Plant Air Distribution - Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-5410 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Receiver |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5411 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5412 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Instrument Air Distribution - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02541
[6 empty] | Return Date | 2019-02-26 | 2019-07-11 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5420 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-5421 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5422 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-07-11
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5424 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G43-5425 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 5 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5426 | P&ID - Olefins Unit 10 - Plant Air - Instrument Air - Nitrogen - Nitrogen Distribution - Sheet 6 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-29 | 2019-04-26 | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-29 | 2019-04-26 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00758 | TPSK-LSPA1-T-PE-01478 | TPSK-LSPA1-T-PE-02588
[6 empty] | Return Date | 2019-02-26 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5490 | P&ID- Olefins Unit 10- Plant Air- Instrument Air- Nitrogen- Plant Air- Instrument Air- MP Nitrogen BL |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-10 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-10
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02588
Return Date
Owner Cmmt*
| PE | OL1-2G43-5501 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Hot Flare Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5502 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5503 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Methanol Vaporizer |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5510 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5511 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5512 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5514 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5516 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 5 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5518 | PID - Olefins Unit 10 - Vent Gas And Flare System - Wet Flare Header - Sheet 6 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5519 | PID - Olefins Unit 10 - Vent Gas And Flare System - LP Flare Header - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5520 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5521 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5523 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5524 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Flare Header - Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5526 | PID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5528 | PID - Olefins Unit 10 - Vent Gas And Flare System - Propylene Blowdown Header - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5529 | PID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5531 | PID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5533 | PID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5534 | PID - Olefins Unit 10 - Vent Gas And Flare System - Hot Blowdown Header - Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5535 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5536 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5540 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5542 | PID - Olefins Unit 10 - Vent Gas And Flare System - Cold Blowdown Header - Sheet 4 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5545 | PID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5546 | PID - Olefins Unit 10 - Vent Gas And Flare System - Vent Collection System - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5551 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare KO Drum |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5553 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Pilot Gas |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5555 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - Polyolefins Flare |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5575 | P&ID - Olefins Unit 10 - Vent Gas And Flare System - HP Flare Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-01-23 | 2019-05-07 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-01-23 | 2019-05-07 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00706 | TPSK-LSPA1-T-PE-01587 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-02-15 | 2019-07-02 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R1 | R2
| PE | OL1-2G43-5590 | P&ID- Olefins Unit 10- Vent Gas And Flare System- Flare No1-No2-No3- Relief And Flare Pilot Gas BL |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-03
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date |  |  | 2019-09-24
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5591 | P&ID- Olefins Unit 10- Vent Gas Flare System- MP-LP Steam-MP Nitrogen-Plant Air-Instr Air BL |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-03
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date |  |  | 2019-09-24
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5592 | P&ID- Olefins Unit 10- Vent Gas And Flare System- Oily Waste Water-Potable-Treated Water BL |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-03
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date |  |  | 2019-09-24
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5593 | P&ID- Olefins Unit 10- Vent Gas And Flare System- Others Units HP-Polyolefins Flare Relief BL |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-03
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date |  |  | 2019-09-24
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5594 | P&ID- Olefins Unit 10- Vent Gas And flare System- HP Flare- Flare No1- Interconnecting |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-03
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date |  |  | 2019-09-24
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5595 | P&ID- Olefins Unit 10- Vent gas And Flare System- Polyolefins Flare- Flare No2- Interconnecting |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-03
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date |  |  | 2019-09-24
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5601 | P&ID - Olefins Unit 10 - Wastewater - Pygas Area Oily Wastewater Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5602 | P&ID - Olefins Unit 10 - Wastewater - Butadiene Area Oily Wastewater Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5603 | P&ID - Olefins Unit 10 - Wastewater - QW Area Oily Wastewater Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5604 | P&ID - Olefins Unit 10 - Wastewater - CGC Area Oily Wastewater Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5605 | P&ID - Olefins Unit 10 - Wastewater - Refrig Area Oily Wastewater Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5606 | P&ID - Olefins Unit 10 - Wastewater - Furnace Area Oily Wastewater Sump |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5607 | P&ID - Olefins Unit 10 - Wastewater - Hydroblast Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-28 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5608 | P&ID - Olefins Unit 10 - Wastewater - C3 Hydrog Area Oily Wastewater Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5609 | P&ID - Olefins Unit 10 - Wastewater - Flare Kod Area Oily Wastewater Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5610 | P&ID - Olefins Unit 10 - Wastewater - Oily Waste Water Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5620 | P&ID - Olefins Unit 10 - Wastewater - Olefins Storm Water Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5621 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Oily Storm Water Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-10-09 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02750
[6 empty] | Return Date | 2019-03-13 | 2019-05-29
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G43-5630 | PID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5631 | PID - Olefins Unit 10 - Wastewater - Olefins Holding Basin - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5632 | P&ID - Olefins Unit 10 - Wastewater - Skimmed Oil Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-09-25
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date |  |  | 2019-10-10
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5640 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 1 |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5641 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 2 |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5642 | P&ID - Olefins Unit 10 - Wastewater - Sanitary Lift Station - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-29 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5649 | P&ID - Olefins Unit 10 - Wastewater - HP Flare Area Oily Wastewater Sump |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-09-25
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R1
| PE | OL1-2G43-5650 | P&ID - Olefins Unit 10 - Wastewater - CT Area Oily Wastewater Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5651 | P&ID - Olefins Unit 10 - Wastewater - CWWT Area Oily Wastewater Sump |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5652 | P&ID - Olefins Unit 10 - Wastewater - Cooling Water Blowdown Basin |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-09-25 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02680
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5653 | PID - Olefins Unit 10 - Wastewater - Oily Waste Water Distribution |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5654 | PID - Olefins Unit 10 - Wastewater - Oily Waste Water Tank |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5655 | P&ID - Olefins Unit 10 - Wastewater - Waste Water CPI-IGF Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5656 | PID - Olefins Unit 10 - Wastewater - Domestic Wastewater Collection |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02649
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5657 | P&ID - Olefins Unit 10 - Wastewater - Bio Equalization Pit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5658 | P&ID - Olefins Unit 10 - Wastewater - Bio Treatment Package |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5660 | P&ID - Olefins Unit 10 - Wastewater - Final Check Basin |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-09-11 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02609
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5662 | P&ID - Olefins Unit 10 - Wastewater - Dewatering System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5665 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank A |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5666 | P&ID - Olefins Unit 10 - Wastewater - Slop Oil Tank B |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5667 | P&ID - Olefins Unit 10 - Wastewater - Oily Sludge Tank |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-15 | 2019-04-29 | 2019-08-26 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-15 | 2019-04-29 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00855 | TPSK-LSPA1-T-PE-01499 | TPSK-LSPA1-T-PE-02479
[6 empty] | Return Date | 2019-03-13 | 2019-05-29 | 2019-09-16
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5903 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sodium Hypochlorite Chemical Injection - Sheet 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-09-13 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02633
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5904 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chemical Injection - Sheet - 1 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-09-13 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02633
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5905 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Neutralizing Amine Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-09-13 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02633
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5907 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Oxygen Scavenger Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5908 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Phosphate Injection System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-09-03 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02555
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-24
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5915 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - Condensate Pump Turbine Details |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5920 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 1 |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5921 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Olefins CW Pump Turbine Details - Sheet 2 |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5922 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - CTU Cooling Water Pump Turbine Details |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5925 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Pump Turbine Details |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5927 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine A Details |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5928 | P&Id - Olefins Unit 10 - Supporting Utilities Auxiliaries - SHP BFW Lube Oil Pump Turbine B Details |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5929 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Pump Turbine Details |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5930 | P&ID - Olefins Unit 10 - Supporting Utilities Auxiliaries - VLP BFW Lube Oil Pump Turbine Details |  | Class 2 | Purpose** | IFR | IBD | CAN
[6 empty] | Rev. | A | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Issue Actual | 2019-02-01 | 2019-04-23 | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00776 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02516
[6 empty] | Return Date | 2019-02-26 | 2019-06-04 | 2019-09-17
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5932 | PID- Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chehical Injection Sheet-2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan | 2018-12-13 | 2019-04-23 | 2019-09-13 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual | 2018-12-13 | 2019-04-23 | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00491 | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02633
[6 empty] | Return Date | 2019-02-15 | 2019-06-04 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2 | R2
| PE | OL1-2G43-5933 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sulfuric Acid Chemical Injection - Sheet 3 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  | 2019-04-23 | 2019-09-13 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-04-23 | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02633
[6 empty] | Return Date |  | 2019-06-04 | 2019-10-01
[6 empty] | Owner Cmmt* |  | R2 | R2
| PE | OL1-2G43-5934 | PID - Olefins Unit 10 - Supporting Utilities Auxiliaries - Sodium Hypochlorite Chemical Injection - Sheet 2 |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | C
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  | 2019-04-23 | 2019-09-13 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  | 2019-04-23 | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01425 | TPSK-LSPA1-T-PE-02633
[6 empty] | Return Date |  | 2019-06-04 | 2019-10-01
[6 empty] | Owner Cmmt* |  | R2 | R2
| PE | OL1-2G43-5990 | P&ID- Olefins Unit 10- Supporting Utilities Auxiliaries- HP Propane and Hydrogen Meters |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-08-30
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02542
[6 empty] | Return Date |  |  | 2019-09-19
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G43-5991 | P&ID- Olefins Unit 10- Supporting Utilities Auxiliaries- Treated Water Meter |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-19 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Revised Plan |  |  | 2019-08-30 | 2019-11-11 | 2020-02-07 | 2020-04-24 | 2020-07-24
[6 empty] | Issue Actual |  |  | 2019-08-30
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02542
[6 empty] | Return Date |  |  | 2019-09-19
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-3G43-5290 | PID Olefins Unit 10 Fuel System Pilot Gas And Fuel Gas Battery Limit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date |  |  | 2019-10-01
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-3G43-5690 | PID Olefins Unit 10 Wastewater Oily-Treated-CW- BD-Domestic-Mixed Wastewater BL |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date |  |  | 2019-10-01
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-3G43-5691 | PID Olefins Unit 10 Wastewater Domestic - Neutralization - Oily Waste Water B.L. |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  |  | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-03-29 | 2019-08-06 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  |  | 2019-09-17 | 2019-11-11 | 2020-02-07 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  |  | 2019-09-17
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-02651
[6 empty] | Return Date |  |  | 2019-10-01
[6 empty] | Owner Cmmt* |  |  | R2
Category Code: G44 Heat and Material Balance
| PE | OL1-2G44-1001 | Overall Material Balance |  |  | Purpose** | IFI | IFI | IFI
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2019-01-21
[6 empty] | Revised Plan | 2018-08-07
[6 empty] | Issue Actual | 2018-08-07 | 2019-04-01 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00009 | TPSK-LSPA1-T-PE-01199 | TPSK-LSPA1-T-PE-02336
[6 empty] | Return Date | 2018-08-23 | 2019-04-22
[6 empty] | Owner Cmmt* | R2 | R1
| PE | OL1-2G44-1002 | Heat & Material Balance - Design Case 6 |  |  | Purpose** | IFI | IFI
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-21
[6 empty] | Revised Plan | 2018-09-03
[6 empty] | Issue Actual | 2018-09-03 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032 | TPSK-LSPA1-T-PE-02334
[6 empty] | Return Date |  | 2019-09-11
[6 empty] | Owner Cmmt* |  | Re
| PE | OL1-2G44-1003 | Heat & Material Balance - Design Case 8 |  |  | Purpose** | IFI | IFI
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-21
[6 empty] | Revised Plan | 2018-09-03
[6 empty] | Issue Actual | 2018-09-03 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032 | TPSK-LSPA1-T-PE-02334
[6 empty] | Return Date |  | 2019-09-11
[6 empty] | Owner Cmmt* |  | Re
| PE | OL1-2G44-1004 | Heat & Material Balance - Design Case 9 |  |  | Purpose** | IFI | IFI
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-21
[6 empty] | Revised Plan | 2018-09-03
[6 empty] | Issue Actual | 2018-09-03 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00032 | TPSK-LSPA1-T-PE-02334
[6 empty] | Return Date |  | 2019-09-11
[6 empty] | Owner Cmmt* |  | Re
| PE | OL1-2G44-1005 | Heat & Material Balance - C3 Hydrogenation Unit & Gasoline Hydrogenation GHU & C4-C5 Hydrogenation Unit |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02334
[6 empty] | Return Date | 2019-09-11
[6 empty] | Owner Cmmt* | Re
| PE | OL1-2G44-1006 | Heat & Material Balance - Butadiene Unit BDU |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-08-05
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02334
[6 empty] | Return Date | 2019-09-11
[6 empty] | Owner Cmmt* | Re
| PE | OL1-2G44-1010 | Heat and Material Balance - ISBL Supporting Utilities |  |  | Purpose** | IFI | IFI
[6 empty] | Rev. | 0 | A
[6 empty] | Issue Plan | 2019-01-21
Revised Plan
[6 empty] | Issue Actual |  | 2018-10-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02810 | TPSK-LSPA1-T-PE-00128
Return Date
Owner Cmmt*
| PE | OL1-2G44-1011 | Heat & Material Balance - Cooling Water System |  |  | Purpose** | IFI | IFI
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-21
[6 empty] | Revised Plan | 2018-10-02
[6 empty] | Issue Actual | 2018-10-02 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00116 | TPSK-LSPA1-T-PE-02780
Return Date
Owner Cmmt*
| PE | OL1-2G44-1012 | Heat & Material Balance Area 55 - Flare System |  |  | Purpose** | IFI | IFI
[6 empty] | Rev. | 0 | 1
[6 empty] | Issue Plan | 2019-01-21
[6 empty] | Revised Plan | 2019-04-29
[6 empty] | Issue Actual | 2019-04-29 | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01492 | TPSK-LSPA1-T-PE-02755
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G44-1013 | Heat and Material Balance - 56 Waste Water Treatment System |  |  | Purpose** | IFI | IFI | IFI
[6 empty] | Rev. | A | 1 | 2
[6 empty] | Issue Plan | 2019-01-21
[6 empty] | Revised Plan | 2019-01-03
[6 empty] | Issue Actual | 2019-01-03 | 2019-02-19 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00581 | TPSK-LSPA1-T-PE-00892 | TPSK-LSPA1-T-PE-02705
Return Date
Owner Cmmt*
Category Code: G50 Interlocking Description/Cause and Effect Diagrams
| IE | OL1-2G50-1001 | CAUSE AND EFFECT DIAGRAMS CRACKING FURNACE |  |  | Purpose** | IFR | IFD | IBD | IFC
[6 empty] | Rev. |  |  | C
[6 empty] | Issue Plan | 2018-12-13 | 2019-01-16 | 2019-03-15 | 2019-10-28
[6 empty] | Revised Plan |  |  | 2019-05-29 | 2019-10-28
[6 empty] | Issue Actual |  |  | 2019-05-29
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-PE-01758
[6 empty] | Return Date |  |  | 2019-06-21
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G50-1002 | 132U Cause and Effect Diagram Cracking Furnaces |  | Class 3 | Purpose** | IBD
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-29
[6 empty] | Issue Actual | 2019-05-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01758
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G50-1003 | Cause and Effect Diagram Area 10 Feed Preparation and Feed Preheat - Ex. Client Doc. N. OL1-2I30-1001 |  |  | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2G50-1004 | Instrument Interlock Descriptions Area 10 Feed Preparation and Feed Preheat |  |  | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-1101 | Shutdown Interlock Narrative - 36M - Area 11 Recycle Gas Cracking Furnace |  |  | Purpose** | IFR | IFD | IBD | IFD | IFC
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-03-19 | 2019-04-11 | 2019-10-22 | 2019-04-11 | 2019-10-28
[6 empty] | Revised Plan | 2019-04-17 | 2019-07-10 |  | 2019-07-10 | 2019-10-28
[6 empty] | Issue Actual | 2019-04-17 | 2019-07-10 |  | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01367 | TPSK-LSPA1-T-PE-02112 |  | TPSK-LSPA1-T-PE-02112
[6 empty] | Return Date | 2019-05-24 | 2019-08-07 |  | 2019-08-07
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G50-1102 | Cause and Effect Diagrams Cracking Furnace - 36M - Ex Doc Client Ref OL1-2G50-1001 |  | Class 3 | Purpose** | IBD
[6 empty] | Rev. | D
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02111
[6 empty] | Return Date | 2019-08-07
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2G50-1201 | Shutdown Interlock Narrative - 132U - Area 12-16 Liquid and Gas Cracking Furnaces |  |  | Purpose** | IFR | IFD | IBD | IFD | IFC
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-03-19 | 2019-04-11 | 2019-10-22 | 2019-04-11 | 2019-10-28
[6 empty] | Revised Plan | 2019-05-03 | 2019-07-10 |  | 2019-07-10 | 2019-10-28
[6 empty] | Issue Actual | 2019-05-03 | 2019-07-10 |  | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01561 | TPSK-LSPA1-T-PE-02112 |  | TPSK-LSPA1-T-PE-02112
[6 empty] | Return Date | 2019-05-29 | 2019-08-19 |  | 2019-08-19
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| PE | OL1-2G50-1202 | Cause and Effect Diagrams Liquid Cracking Furnaces - 132U - Ex Doc Client Ref OL1-2G50-1002 |  | Class 3 | Purpose** | IBD
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02111
[6 empty] | Return Date | 2019-08-07
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G50-2001 | Cause and Effect Diagram Area 20 Quench Oil |  |  | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2G50-2002 | Instrument Interlock Descriptions Area 20 Quench Oil |  |  | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G50-2101 | Cause and Effect Diagram Area 21 Quench Water Dilution Steam |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-26 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01137
[6 empty] | Return Date |  | 2019-04-22
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-2102 | Instrument Interlock Descriptions - Area 21 - Quench Water - Dilution Steam |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-03-26 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01149
[6 empty] | Return Date |  | 2019-04-22
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-2201 | Cause and Effect Diagram - Area 22 - Cracked Gas Compressor |  |  | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-07-19 |  |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-29 |  | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-29 | 2019-04-01
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01183 | TPSK-LSPA1-T-PE--01204
[6 empty] | Return Date |  | 2019-08-05 | 2019-08-05
[6 empty] | Owner Cmmt* |  | R2 | R2
| IE | OL1-2G50-2202 | Instrument Interlock Descriptions - Area 22 - Cracked Gas Compressor |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-04-01 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-04-01
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01203
[6 empty] | Return Date |  | 2019-06-04
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-2301 | Cause and Effect Diagram Area 23: Caustic and Spent Caustic Treatment |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-29 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01183
[6 empty] | Return Date |  | 2019-06-04
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-2302 | Instrument Interlock Descriptions - Area 23 - Caustic and Spent Caustic Treatment |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-03-29 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-03-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01185
[6 empty] | Return Date |  | 2019-06-04
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-2401 | Cause And Effect Diagram Area 24 - Dehydration - Regen - Deprop - C2 Hydrog |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-08 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-04-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01267
[6 empty] | Return Date |  | 2019-05-09
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-2402 | Instrument Interlock Descriptions Area 24 - Dehydration - Regen - Deprop - C2 Hydrog |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-04-08 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-04-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01266
[6 empty] | Return Date |  | 2019-05-09
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-2501 | Cause and Effect Diagram - Area 25 - Cold Fractionation "CAUSE AND EFFECT DIAGRAM AREA 25: COLD FRACTIONATION" |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-03-22 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-03-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01133
[6 empty] | Return Date |  | 2019-04-11
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-2502 | Instrument Interlock Descriptions - Area 25 - Cold Fractionation |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-04-03 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-04-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01225
[6 empty] | Return Date |  | 2019-05-16
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-2601 | Cause and Effect Diagram Area 26 - Hot Fractionation |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-23 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-04-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01429
[6 empty] | Return Date |  | 2019-06-05
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-2602 | Instrument Interlock Descriptions Area 26 - Hot Fractionation |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-21 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-05-21
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01691
[6 empty] | Return Date |  | 2019-06-13
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-2701 | Cause And Effect Diagram Area 27 - Ghu & C4-C5 Hydrog |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-26 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-04-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01481
[6 empty] | Return Date |  | 2019-05-29
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-2702 | Instrument Interlock Descriptions Area 27 - Ghu &C4-C5 Hydrog |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-21 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-05-21
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01697
[6 empty] | Return Date |  | 2019-06-13
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-2801 | Cause And Effect Diagram Area 28 - Refrigeration System |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-02 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-05-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01540
[6 empty] | Return Date |  | 2019-05-29
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-2802 | Instrument Interlock Descriptions Area 28 - Refrigeration System |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-29 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-05-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01753
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-2901 | Cause And Effect Diagram Area 29 - Ethylene Auxiliaries |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-02 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-05-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01539
[6 empty] | Return Date |  | 2019-05-29
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-2902 | Instrument Interlock Descriptions Area 29 - Ethylene Auxiliaries |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-29 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-05-29
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01753
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-3001 | Cause And Effect Diagram Area 30 - Butadiene Extraction Unit BDU |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-31 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-05-31
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01773
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-3002 | Instrument Interlock Descriptions Area 30 - Butadiene Extraction Unit BDU |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-06-11 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-06-11
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01868
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-5101 | Cause And Effect Diagram Area 51 - BFW - Steam - Steam Condensate System |  | Class 3 | Purpose** | IFR | IBD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-25 | 2019-08-06
[6 empty] | Issue Actual | 2019-04-25 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01471 | TPSK-LSPA1-T-PE-02343
[6 empty] | Return Date | 2019-05-29 | 2019-09-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G50-5102 | Instrument Interlock Descriptions Area 51- BFW - Steam - Steam Condensate System |  | Class 3 | Purpose** | IFR | IBD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-07 | 2019-08-07
[6 empty] | Issue Actual | 2019-05-07 | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01573 | TPSK-LSPA1-T-IE-02345
[6 empty] | Return Date | 2019-05-29 | 2019-09-19
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G50-5201 | Cause And Effect Diagram Area 52 - Fuel System |  | Class 3 | Purpose** | IFR | IBD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-26 | 2019-08-06
[6 empty] | Issue Actual | 2019-04-26 | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01480 | TPSK-LSPA1-T-PE-02343
[6 empty] | Return Date | 2019-05-29 | 2019-09-04
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G50-5202 | Instrument Interlock Descriptions Area 52 - Fuel System |  | Class 3 | Purpose** | IFR | IBD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-07 | 2019-08-07
[6 empty] | Issue Actual | 2019-05-07 | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01573 | TPSK-LSPA1-T-IE-02345
[6 empty] | Return Date | 2019-05-29 | 2019-09-19
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G50-5301 | Cause and Effect Diagram Area 53 Cooling Water System |  |  | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  |  | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2G50-5302 | Instrument Interlock Descriptions Area 53 Cooling Water System |  |  | Purpose** | IFI | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | C
[6 empty] | Issue Plan | 2019-07-19 | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-10-15 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-10-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02836
Return Date
Owner Cmmt*
| PE | OL1-2G50-5501 | Cause and Effect Diagram Area 55 Vent Gas and Flare System |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-23 | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-04-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01429
[6 empty] | Return Date |  | 2019-06-05
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2G50-5502 | Instrument Interlock Descriptions Area 55 Vent Gas and Flare System |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-02 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-05-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01523
[6 empty] | Return Date |  | 2019-05-29
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-5601 | Cause and Effect Diagram Area 56 Wastewater |  |  | Purpose** | IFI | IFR | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-07-19 |  |  | 2019-09-05 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-25 |  | 2019-11-14 | 2019-12-12 | 2020-03-06 | 2020-05-05 | 2020-08-05
[6 empty] | Issue Actual |  | 2019-04-25 | 2019-05-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01462 | TPSK-LSPA1-T-PE-01537
[6 empty] | Return Date |  |  | 2019-05-29
[6 empty] | Owner Cmmt* |  |  | R2
| IE | OL1-2G50-5602 | Instrument Interlock Descriptions Area 56 Wastewater |  |  | Purpose** | IFI | IFR | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19 |  | 2019-09-05 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Revised Plan |  | 2019-05-02 | 2019-11-14 | 2020-01-07 | 2020-03-06 | 2020-05-30 | 2020-08-30
[6 empty] | Issue Actual |  | 2019-05-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01538
[6 empty] | Return Date |  | 2019-05-29
[6 empty] | Owner Cmmt* |  | R2
| PE | OL1-2G50-5901 | Cause and Effect Diagram Area 59 Supporting Utilities Auxiliaries |  | Class 3 | Purpose** | IBD
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02036
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2G50-5902 | Instrument Interlock Descriptions Area 59 Supporting Utilities Auxiliaries |  | Class 3 | Purpose** | IBD
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02038
[6 empty] | Return Date | 2019-08-05
[6 empty] | Owner Cmmt* | R2
Category Code: G51 Sequence of Operation
| IE | OL1-2G51-2403 | Sequence Narratives Area 24 - Dehydration_Regen_Deprop_C2 Hydrog |  |  | Purpose** | IFI | IFR | IDD | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-05 |  | 2019-12-20 | 2020-04-30
[6 empty] | Revised Plan |  | 2019-04-17 | 2019-12-20 | 2020-04-30
[6 empty] | Issue Actual |  | 2019-04-17
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-01374
[6 empty] | Return Date |  | 2019-05-24
[6 empty] | Owner Cmmt* |  | R2
Category Code: G60 Battery Limit and Tie-in
| PE | OL1-2G60-0001 | Battery limit Summary |  |  | Purpose** | IFR | IDD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-12 | 2019-11-15 | 2020-08-15
[6 empty] | Revised Plan | 2019-03-01 |  | 2020-08-15
[6 empty] | Issue Actual | 2019-03-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00948
[6 empty] | Return Date | 2019-04-10
[6 empty] | Owner Cmmt* | R2
Category Code: G61 Equipment List
Category Code: G62 Utility Summary
| PE | OL1-2G62-0001 | UTILITY CONSUMPTION SUMMARY |  |  | Purpose** | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-11-15 | 2020-02-21
[6 empty] | Revised Plan | 2019-11-15 | 2020-02-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G62-1001 | Steam Balance |  |  | Purpose** | IFI | IFI
[6 empty] | Rev. | 0 | A
[6 empty] | Issue Plan | 2019-01-02
Revised Plan
[6 empty] | Issue Actual |  | 2018-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02811 | TPSK-LSPA1-T-PE-00059
[6 empty] | Return Date |  | 2018-10-04
Owner Cmmt*
| PE | OL1-2G62-1006 | Cooling Water Balance |  |  | Purpose** | IFI | IFI | IFF
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-09-12 |  | 2020-04-30
[6 empty] | Revised Plan | 2018-09-18 |  | 2020-04-30
[6 empty] | Issue Actual | 2018-09-18 | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00054 | TPSK-LSPA1-T-PE-02579
[6 empty] | Return Date | 2018-10-09 | 2019-10-10
[6 empty] | Owner Cmmt* | R2 | R2
| PE | OL1-2G62-1008 | Fuel Balance |  |  | Purpose** | IFI | IFI
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-02
[6 empty] | Revised Plan | 2018-09-14
[6 empty] | Issue Actual | 2018-09-14 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00049 | TPSK-LSPA1-T-PE-02780
Return Date
Owner Cmmt*
| PE | OL1-2G62-1010 | Air & Nitrogen Balances |  |  | Purpose** | IFI
[6 empty] | Rev. | 0
[6 empty] | Issue Plan | 2019-01-02
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01644
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | R2
Category Code: G63 Plant Efffluent Summary
| PE | OL1-2G63-0001 | Effluent Summary |  |  | Purpose** | IFR | IFD | IFD | IDD | IFF
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-02-21 | 2019-03-14 |  | 2019-12-03 | 2020-03-30
[6 empty] | Revised Plan | 2019-02-26 | 2019-05-13 |  | 2019-12-03 | 2020-03-30
[6 empty] | Issue Actual | 2019-02-26 | 2019-05-13 | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-00922 | TPSK-LSPA1-T-PE-01639 | TPSK-LSPA1-T-PE-02123
[6 empty] | Return Date | 2019-03-21 | 2019-05-31
[6 empty] | Owner Cmmt* | R1 | R2
Category Code: G64 Catalyst, Adsobent, and Chemicals Summary
| PE | OL1-2G64-1002 | Catalyst & Chemicals Summary |  |  | Purpose** | IFI | IFI | IFI | IFF
[6 empty] | Rev. | 0 | 1 | 2
[6 empty] | Issue Plan | 2019-02-07 |  |  | 2019-12-13
[6 empty] | Revised Plan | 2019-03-26 |  |  | 2019-12-13
[6 empty] | Issue Actual | 2019-03-26 | 2019-05-15 | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01143 | TPSK-LSPA1-T-PE-01659 | TPSK-LSPA1-T-PE-02039
[6 empty] | Return Date | 2019-04-22 | 2019-06-03
[6 empty] | Owner Cmmt* | R2 | R2
Category Code: G70 Materials specification and; Utilities specfication and; Catalyst, Adsobent,; and Chemicals specification and ; Fluid and Solid properties
Category Code: G71 Effluent and Waste specification
Category Code: G72 Standard and Specification
Category Code: G73 Guide to Safe Handling of Material
Category Code: G74 Material Selection Guideline
| ME | OL1-2G74-0001 | Material Selection Diagram - Olefins Unit 10 - Legend & Notes |  | Class 3 | Purpose** | IFA | IFD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2018-11-09 | 2019-08-15
[6 empty] | Issue Actual | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* | A2 | R1
| PE | OL1-2G74-1001 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feed Preheat |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-1003 | Material Selection Diagram - Olefins Unit 10 - 10 - Feed Preparation - Feedstock Distribution |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-1101 | Material Selection Diagram - Olefins Unit 10 - 11 - Furnaces - Gas Cracking Furnace |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-1201 | Material Selection Diagram - Olefins Unit 10 - 12 - Furnaces - Liquid Cracking Furnaces |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-1901 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Decoke Air Compressor |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-1902 | Material Selection Diagram - Olefins Unit 10 - 19 - Cracking Furnace Unit Aux - Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-ME-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2001 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Quench Oil Tower |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2002 | Material Selection Diagram - Olefins Unit 10 - 20 - Quench Oil - Heavy Fuel Oil Stripper |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2101 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Tower |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2102 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Quench Water Circuit |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2103 | Material Selection Diagram - Olefins Unit 10 - 21 - Quench Water - Dilution Steam - Dilution Steam Generation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2201 | Material Selection Diagram - Olefins Unit 10 - 22 - Cracked Gas Compression - Cracked Gas Compression |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2301 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Caustic Tower |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2302 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Handling |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2303 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Storage |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2304 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Spent Caustic Treatment |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2305 | Material Selection Diagram - Olefins Unit 10 - 23 - Caustic & Spent Caustic Treatment - Wet Air Oxidation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2401 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - CG Dehydration |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2402 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - Regeneration |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2403 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - HP Depropanizer |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2404 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - C2 Hydrogenation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2405 | Material Selection Diagram - Olefins Unit 10 - 24 - Dehydration - Regen - Deprop - C2 Hydrog - LP Depropanizer |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2501 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer Prefractionator |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2502 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Residue Gas System |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2503 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Demethanizer |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2504 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Deethanizer |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2505 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Ethylene Fractionation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2506 | Material Selection Diagram - Olefins Unit 10 - 25 - Cold Fractionation - Hydrogen Purification |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2601 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - C3 Hydrogenation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2602 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Secondary Deethanizer |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2603 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Propylene Fractionation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2604 | Material Selection Diagram - Olefins Unit 10 - 26 - Hot Fractionation - Debutanizer |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2701 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog GHU-1 Reactor & Depentanizer |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02007 | TPSK-LSPA1-T-PE-02809
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-2702 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog - GHU-1 Rerun Tower |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-02007 | TPSK-LSPA1-T-PE-02809
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-2703 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog - Hydrog Reactivation Gas System |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02809
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-2704 | Material Selection Diagram - Olefins Unit 10 - 27 - GHU & C4/C5 Hydrog - C4/C5 Hydrogenation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02809
Return Date
Owner Cmmt*
| PE | OL1-2G74-2801 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 1 |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2802 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Propylene Refrigeration 2 |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2803 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 1 |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-2804 | Material Selection Diagram - Olefins Unit 10 - 28 - Refrigeration System - Ethylene Refrigeration 2 |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-2901 | Material Selection Diagram - Olefins Unit 10 - 29 - Olefins Recovery Unit Aux - Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2018-11-09 |  | 2019-04-08 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-09 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-09 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00295 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2018-12-10 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-3001 | Material Selection Diagram - Olefins Unit 10 - 30-C4 Unit BDU - Predistillation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02850
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-3002 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Predistillation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02809
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-3003 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Rectifier |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02809
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-3004 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Degassing |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02809
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-3005 | Material Selection Diagram - Olefins Unit 10 - 30 - C4 Unit BDU - Fractionation |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02809
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-3101 | Material Selection Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Solvent Regeneration |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02850
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-3102 | Material Selection Diagram - Olefins Unit 10 - 31 - C4 Unit BDU Utilities - Steam And Condensate System |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02809
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-3901 | Material Selection Diagram - Olefins Unit 10 - 39 - C4 Unit Aux - BDU Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-06-27 |  | 2020-04-20
[6 empty] | Issue Actual |  | 2019-06-27
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PE-02013 | TPSK-LSPA1-T-PE-02850
[6 empty] | Return Date |  | 2019-07-23
[6 empty] | Owner Cmmt* |  | R1
| PE | OL1-2G74-5001 | Material Selection Diagram - Olefins Unit 10 - 50 Water Systems - Treated -Potable and Demin Water Systems |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5101 | Material Selection Diagram - Olefins Unit 10 - 51 BFW- Steam- Cond Systems - Steam Balance Diagram |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5102 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Condensate and Boiler Feedwater Systems |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608, TPSK-LSPA1-T-PE-02428, TPSK-LSPA1-T-PE-02428 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G74-5103 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Condensate Treatment System |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608, TPSK-LSPA1-T-PE-02428, TPSK-LSPA1-T-PE-02428 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G74-5104 | Material Selection Diagram - Olefins Unit 10 - 51 BFW Steam Cond Systems - Furnace Blowdown System |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608, TPSK-LSPA1-T-PE-02428, TPSK-LSPA1-T-PE-02428 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5201 | Material Selection Diagram - Olefins Unit 10 - 52 Fuel System - Fuel Gas System |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G74-5301 | Material Selection Diagram - Olefins Unit 10 - 53 Cooling Water System Cooling Water Diagram |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-29 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-29 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00399 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2019-02-15 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R1
| PE | OL1-2G74-5311 | Material Selection Diagram - Olefins Unit 10 - 53-Cooling Water System Cooling Tower |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2018-11-29 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2018-11-29 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00399 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  | 2019-02-15 | 2019-09-23
[6 empty] | Owner Cmmt* |  | A2 | R2
| PE | OL1-2G74-5401 | Material Selection Diagram - Olefins Unit 10 - 54 Air and Nitrogen System - Plant Air - Instrument Air and Nitrogen Systems |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5501 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Flare and Blowdown System |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5502 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Process Vent Gas Collection |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5511 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - HP-LLDPE LP Flare |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G74-5512 | Material Selection Diagram - Olefins Unit 10 - 55 Vent Gas and Flare System - Enclosed Ground |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5601 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Oily Wastewater Collection |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G74-5602 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Surface Runoff Collection |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G74-5603 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Cracker Holding Basin |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R2
| PE | OL1-2G74-5604 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Domestic Wastewater Collection |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5610 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - HP Flare Area SW & Oily WW Collection |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5611 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - OSBL Oily Wastewater Collection |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5612 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Oily Wastewater Equilization Tank |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5613 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - CPI & IGF Packages |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5614 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Biotreatment Package |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5615 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Check Basin |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5616 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Sludge Dewatering Package |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5617 | Material Selection Diagram - Olefins Unit 10 - 56 Wastewater - Slop and Oil Sludge |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5901 | Material Selection Diagram - Olefins Unit 10 - 59 Utilities Aux - Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
| PE | OL1-2G74-5911 | Material Selection Diagram - Olefins Unit 10 - 59 Utilities And Auxiliaries Complex U & O Chemical Storage |  |  | Purpose** | IFR | IFA | IFD | IFF
[6 empty] | Rev. |  | A | B
[6 empty] | Issue Plan | 2019-03-04 |  | 2019-06-15 | 2019-09-15
[6 empty] | Revised Plan |  | 2019-01-08 | 2019-08-15 | 2020-04-20
[6 empty] | Issue Actual |  | 2019-01-08 | 2019-08-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00608 | TPSK-LSPA1-T-PE-02428
[6 empty] | Return Date |  |  | 2019-09-23
[6 empty] | Owner Cmmt* |  |  | R1
Category Code: G75 Engineering Procedure
Category Code: G76 Supervisory Level Operating Procedures for all Process/Utility System(s). (Shall include Steady State, Stat-Up, Shutdown & transient Operations
| PE | OL1-2G76-1002 | BALANCE OF PLANT SUPERVISORY OPERATING MANUAL |  |  | Purpose** | IFR | IFD
Rev.
[6 empty] | Issue Plan | 2019-07-19 | 2019-08-30
[6 empty] | Revised Plan | 2019-10-21 | 2019-10-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2G76-1003 | C3 Hydrogenation Unit Operating Manual |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-25
[6 empty] | Issue Actual | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02699
Return Date
Owner Cmmt*
| PE | OL1-2G76-1004 | Gasoline Hydrogenation Unit GHU Operating Manual |  |  | Purpose** | IFI
[6 empty] | Rev. | 0
[6 empty] | Issue Plan | 2019-09-30
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02614
Return Date
Owner Cmmt*
| PE | OL1-2G76-1006 | C4 & C5 Hydrogenation Unit Operating Manual |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02614
Return Date
Owner Cmmt*
| PE | OL1-2G76-1007 | Butadiene Unit BDU Operating Manual |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-09-11
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02614
Return Date
Owner Cmmt*
Category Code: G77 APC Functional specification
Category Code: G81 Appraisal Report for Consultancy Service
Category Code: G82 Appraisal Report for EPC Contractor Work
Category Code: G83 Appraisal Report for Vendor/Supplier
Category Code: G90 Vendor Document/drawings
Category Code: G91 Index/List
| PE | OL1-2G91-1001 | Piping Specialty Item - Datasheet Index - Feed Preparation and Furnaces - Area 10 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-06-28 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-1101 | Piping Specialty Item Datasheet Index - Recycle Gas Furnace Area 11 |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-10 | 2019-02-20
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01642
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-1201 | Piping Specialty Item Datasheet Index - Liquid Cracking Furnace Areas 12-16 |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-01-10 | 2019-02-20
[6 empty] | Revised Plan | 2019-05-13
[6 empty] | Issue Actual | 2019-05-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01642
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-1901 | Piping Specialty Item - Datasheet Index - Furnace Auxiliaries - Area 19 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-28
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-2001 | Piping Specialty Item - Datasheet Index - Quench Oil - Area 20 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-07-03 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-2101 | Piping Specialty Item - Datasheet Index - Quench Water-Dilution Steam - Area 21 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-07-03 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-2201 | Piping Specialty Item - Datasheet Index - Cracked Gas Compression - Area 22 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-06-26 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01991
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-2301 | Piping Specialty Item - Datasheet Index - Caustic and Spent Caustic Treatment - Area 23 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-06-26 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-01992
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-2501 | Piping Specialty Item - Datasheet Index - Cold Fractionation - Area 25 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-06-28 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-2601 | Piping Specialty Item - Datasheet Index - Hot Fractionation - Area 26 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-06-28 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-2701 | Piping Specialty Item - Datasheet Index - GHU and C4-C5 Hydrog - Area 27 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-07-03 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G91-2801 | Piping Specialty Item - Datasheet Index - Refrigeration System - Area 28 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-07-03 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G91-2901 | Piping Specialty Item - Datasheet Index - Ethylene Auxiliaries - Area 29 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-06-28 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02020
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-3001 | Piping Specialty Item - Datasheet Index - Butadiene Extraction Unit - Area 30 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-07-08 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02085
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G91-3101 | Piping Specialty Item - Datasheet Index - Butadiene Extraction Unit Utilities - Area 31 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02085
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G91-3901 | Piping Specialty Item - Datasheet Index - Butadiene Extraction Unit Auxiliaries - Area 39 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02085
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-5001 | Piping Specialty Item - Datasheet Index - Water System-Treated Potable Demin - Area 50 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-07-03 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-5101 | Piping Specialty Item - Datasheet Index - BFW-Steam-Steam Condensation System - Area 51 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-03
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G91-5201 | Piping Specialty Item - Datasheet Index - Fuel Gas System - Area 52 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-03
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-5301 | Piping Specialty Item - Datasheet Index - Cooling Water - Area 53 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-07-03 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R2
| PE | OL1-2G91-5401 | Piping Specialty Item - Datasheet Index - Plant Air-Instrument Air-Nitrogen - Area 54 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-03
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-5501 | Piping Specialty Item - Datasheet Index - Vent Gas and Flare System - Area 55 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-07-03 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-5601 | Piping Specialty Item - Datasheet Index - WasteWater - Area 56 |  |  | Purpose** | IFR | IFD | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-18 | 2019-05-16 | 2020-08-15
[6 empty] | Revised Plan | 2019-07-03 | 2019-10-16 | 2020-08-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
| PE | OL1-2G91-5901 | Piping Specialty Item - Datasheet Index - Supporting Utilities Auxiliaries - Area 59 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-03
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PE-02055
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R1
Category Code: G92 Procedures & Standards
Category Code: G93 Policy , Guidelines & Memo
Category Code: G94 Forms & Templates
Category Code: G95 Progress/Status Reports
Category Code: H01 Design basis
Category Code: H02 Abbreviation and standard symbols
Category Code: H03 Project HVAC specification
| EE | OL1-2H03-0001 | Air Conditioning Ventilating And Ducting Design - For Next Revision See Document OL1-2E05-0020 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-10-15
[6 empty] | Issue Actual | 2018-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-00165
[6 empty] | Return Date | 2018-10-26
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2H03-0002 | ROC - Job Supply Specification For HVAC Systems |  |  | Purpose** | IFR | IMP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-30 | 2019-07-29
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-02147
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R1
Category Code: H04 Equipment, material specification
Category Code: H05 Equipment datasheet
Category Code: H10 Calculation
| EE | OL1-2H10-0001 | Electrical SUB-E And FAR-1 – HVAC Thermal Calculation |  |  | Purpose** | IFR | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-30 |  | 2019-07-29
[6 empty] | Revised Plan | 2019-04-24 |  | 2019-10-30
[6 empty] | Issue Actual | 2019-04-24 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01442 | TPSK-LSPA1-T-EE-02773
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2H10-0002 | Electrical SUB-C & FAR-C – HVAC Thermal Calculation |  |  | Purpose** | IFR | IDD | IDD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-06-30 | 2019-07-29
[6 empty] | Revised Plan | 2019-04-24 | 2019-08-08
[6 empty] | Issue Actual | 2019-04-24 | 2019-08-08 | 2019-08-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01446 | TPSK-LSPA1-T-EE-02369 | TPSK-LSPA1-T-EE-02481
[6 empty] | Return Date | 2019-05-17 | 2019-08-21 | 2019-09-03
[6 empty] | Owner Cmmt* | A3 | A2 | A4
| EE | OL1-2H10-0003 | Gatehouse A HVAC Thermal Calculation |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-02 | 2019-06-01
[6 empty] | Revised Plan | 2019-04-09 | 2019-07-04
[6 empty] | Issue Actual | 2019-04-09 | 2019-07-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01273 | TPSK-LSPA1-T-EE-02068
[6 empty] | Return Date | 2019-05-07 | 2019-07-17
[6 empty] | Owner Cmmt* | A2 | A2
| EE | OL1-2H10-0004 | PREFABRICATED GATEHOUSE – HVAC Thermal Calculation |  | Class 1 | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-09 | 2019-07-04
[6 empty] | Issue Actual | 2019-04-09 | 2019-07-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01273 | TPSK-LSPA1-T-EE-02068
[6 empty] | Return Date | 2019-05-07 | 2019-07-17
[6 empty] | Owner Cmmt* | A2 | A2
| CV | OL1-2H10-0005 | Electrical SUB-F & FAR-F – HVAC Thermal Calculation |  |  | Purpose** | IFR | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-30 |  | 2019-07-29
[6 empty] | Revised Plan | 2019-04-24 |  | 2019-10-30
[6 empty] | Issue Actual | 2019-04-24 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01446 | TPSK-LSPA1-T-EE-02773
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A3
Category Code: H20 System schematic diagram
| EE | OL1-2H20-0001 | Electrical Sub-e- And Far-1-HVAC Process Flow Diagram |  |  | Purpose** | IFR | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-30 |  | 2019-07-29
[6 empty] | Revised Plan | 2019-04-19 |  | 2019-10-30
[6 empty] | Issue Actual | 2019-04-19 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01416 | TPSK-LSPA1-T-EE-02775
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2H20-0003 | Electrical Sub-C- And Far-C - HVAC Process Flow Diagram |  |  | Purpose** | IFR | IDD | IDD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-06-30 | 2019-07-29
[6 empty] | Revised Plan | 2019-04-24 | 2019-08-08
[6 empty] | Issue Actual | 2019-04-24 | 2019-08-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01454 | TPSK-LSPA1-T-EE-02371 | TPSK-LSPA1-T-EE-02485
[6 empty] | Return Date | 2019-05-17 | 2019-08-21 | 2019-09-03
[6 empty] | Owner Cmmt* | A3 | A3 | A4
| CV | OL1-2H20-0010 | Electrical Sub-F- And Far-F - HVAC Process Flow Diagram |  |  | Purpose** | IFR | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-30 |  | 2019-07-29
[6 empty] | Revised Plan | 2019-04-24 |  | 2019-10-30
[6 empty] | Issue Actual | 2019-04-24 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01454 | TPSK-LSPA1-T-EE-02775
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A3
Category Code: H21 Arrangement drawing
| EE | OL1-2H21-0001 | Electrical Sub-e- And Far-1-HVAC Layout |  |  | Purpose** | IFR | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-30 |  | 2019-07-29
[6 empty] | Revised Plan | 2019-04-19 |  | 2019-10-30
[6 empty] | Issue Actual | 2019-04-19 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01417 | TPSK-LSPA1-T-EE-02774
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A3
| EE | OL1-2H21-0005 | Electrical SUB-C & FAR-C HVAC Layout |  |  | Purpose** | IFR | IDD | IDD
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-06-30 | 2019-07-29
[6 empty] | Revised Plan | 2019-04-24 | 2019-08-08
[6 empty] | Issue Actual | 2019-04-24 | 2019-08-08 | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01453 | TPSK-LSPA1-T-EE-02370 | TPSK-LSPA1-T-EE-02486
[6 empty] | Return Date | 2019-05-17 | 2019-08-19 | 2019-09-03
[6 empty] | Owner Cmmt* | A3 | A3 | A4
| EE | OL1-2H21-0010 | Gatehouse A - HVAC Layout And Process Flow Diagram |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-02 | 2019-06-01
[6 empty] | Revised Plan | 2019-04-05 | 2019-07-03
[6 empty] | Issue Actual | 2019-04-05 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-1238 | TPSK-LSPA1-T-EE-02053
[6 empty] | Return Date |  | 2019-07-17
[6 empty] | Owner Cmmt* |  | A2
| EE | OL1-2H21-0011 | Prefabricated Gatehouse - HVAC Layout And Process Flow Diagram |  | Class 1 | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-05 | 2019-07-03
[6 empty] | Issue Actual | 2019-04-05 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-1238 | TPSK-LSPA1-T-EE-02053
[6 empty] | Return Date |  | 2019-07-17
[6 empty] | Owner Cmmt* |  | A2
| EE | OL1-2H21-0015 | Operation Tool Room - HVAC Layout And Section |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-02 | 2019-06-01
[6 empty] | Revised Plan | 2019-04-05 | 2019-07-03
[6 empty] | Issue Actual | 2019-04-05 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-1238 | TPSK-LSPA1-T-EE-02053
[6 empty] | Return Date |  | 2019-07-17
[6 empty] | Owner Cmmt* |  | A2
| CV | OL1-2H21-0020 | Electrical Sub-F- And Far-F - HVAC Layout |  |  | Purpose** | IFR | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-30 |  | 2019-07-29
[6 empty] | Revised Plan | 2019-04-24 |  | 2019-10-30
[6 empty] | Issue Actual | 2019-04-24 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-EE-01453 | TPSK-LSPA1-T-EE-02774
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A3
Category Code: H22 Electrical and control drawing/ document
Category Code: H60 Cable drum schedule
Category Code: H61 Cable schedule
Category Code: H62 Connection list
Category Code: H63 Construction material and Bill of quantities
Category Code: H64 Typical installation drawing
Category Code: H71 Appraisal Report for Consultancy Service
Category Code: H72 Appraisal Report for EPC Contractor Work
Category Code: H73 Appraisal Report for Vendor/Supplier
Category Code: H90 Vendor documents
Category Code: H91 Index/List
Category Code: H92 Procedures & Standards
Category Code: H93 Policy , Guidelines & Memo
Category Code: H94 Forms & Templates
Category Code: H95 Progress/Status Reports
Category Code: I10 MAC FEED Document
Category Code: I20 Instrument datasheet
| IE | OL1-2I20-0120 | DATA SHEET FOR CUSTODY TRANSFER METERING |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-04-26 | 2019-11-30
[6 empty] | Revised Plan | 2019-10-25 | 2019-11-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1001 | USC 36M and USC 132U Instrument Datasheets for Control Valve |  |  | Purpose** | IFR | IFA | IFQ | IFP
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-25 |  | 2019-04-03 | 2019-05-10
[6 empty] | Revised Plan |  | 2019-03-22 |  | 2019-10-16
[6 empty] | Issue Actual |  | 2019-03-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01130
[6 empty] | Return Date |  | 2019-04-02
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I20-1002 | Instrument Datasheet for Pressure Relief Valve |  | Class 1 | Purpose** | IFP | IFP
[6 empty] | Rev. | 0 | 1
Issue Plan
[6 empty] | Revised Plan | 2019-08-06
[6 empty] | Issue Actual | 2019-08-06 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02350 | TPSK-LSPA1-T-IE-02681
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1005 | USC 36M and USC 132U Instrument Datasheets for Level Gauge |  |  | Purpose** | IFR | IFQ | IFP | IFP
[6 empty] | Rev. | A |  | 0 | 0
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05
[6 empty] | Revised Plan | 2019-03-14 |  | 2019-08-14
[6 empty] | Issue Actual | 2019-03-14 |  | 2019-08-14 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01047 |  | TPSK-LSPA1-T-IE-02414 | TPSK-LSPA1-T-IE-02414
[6 empty] | Return Date | 2019-03-27 |  | 2019-09-19 | 2019-09-19
[6 empty] | Owner Cmmt* | R2 |  | R2 | R2
| IE | OL1-2I20-1006 | Instrument Datasheets for Level Transmitter and Level Transmitter W-Gauge |  |  | Purpose** | IFR | IFQ | IFR | IFP | IFR
[6 empty] | Rev. | A |  | A |  | A
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-08-06 | 2019-11-05 | 2019-08-06
[6 empty] | Revised Plan | 2019-04-10 |  | 2019-04-10 | 2019-11-05 | 2019-04-10
[6 empty] | Issue Actual | 2019-04-10 |  | 2019-04-10 |  | 2019-04-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01288 |  | TPSK-LSPA1-T-IE-01288 |  | TPSK-LSPA1-T-IE-01288
[6 empty] | Return Date | 2019-05-13 |  | 2019-05-13 |  | 2019-05-13
[6 empty] | Owner Cmmt* | R2 |  | R2 |  | R2
| IE | OL1-2I20-1009 | Instrument Datasheets for Control Valve - Globe Type - Area 10 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01692
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1010 | Instrument Datasheets for ON-OFF Valve -Ball Type -Area 10 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01658
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1011 | Instrument Datasheets for Temperature Elements for Coil Outlet |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan | 2019-04-11 | 2019-05-24 | 2019-11-05 | 2019-05-24
[6 empty] | Issue Actual | 2019-04-11 | 2019-05-24 |  | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01309 | TPSK-LSPA1-T-IE-01729 |  | TPSK-LSPA1-T-IE-01729
[6 empty] | Return Date |  | 2019-07-17 |  | 2019-07-17
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1012 | Instrument Datasheets for ON-OFF Valve -Butterfly Type- Area 10 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1015 | USC 36M and USC 132U Instrument Datasheets for pH and Conductivity Analyzer |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan | 2019-03-22 | 2019-05-24 | 2019-11-05 | 2019-05-24
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-24 |  | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01131 | TPSK-LSPA1-T-IE-01730 |  | TPSK-LSPA1-T-IE-01730
[6 empty] | Return Date | 2019-04-02 | 2019-06-13 |  | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| IE | OL1-2I20-1016 | Instrument Datasheets for Pressure Safety Valve - Area 10 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1022 | Instrument Datasheets for Flow Element -Orifice - Area 10 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1101 | Instrument Datasheets for Control Valve -Globe Type- Area 11 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
Return Date
Owner Cmmt*
| IE | OL1-2I20-1106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 11 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1111 | Instrument Datasheets for ON-OFF Valve Ball Type - Area 11 BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1112 | Instrument Datasheets for ON-OFF Valve Butterfly Type - Area 11 BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2I20-1122 | Instrument Datasheets for Flow Element Orifice- Area 11 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1125 | Instrument Data Sheets Flow Element Pitot Furmace Area 10-H-1100 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-24
[6 empty] | Issue Actual | 2019-06-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01965
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-1127 | Instrument Datasheets for Flow Instrument -Vortex-Area 11 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1151 | Instrument Datasheets for O2 & Combustible Analyzer |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-05-09 | 2019-06-22 | 2019-08-05 | 2019-06-22
[6 empty] | Revised Plan | 2019-05-30 | 2019-06-25 | 2019-10-25 | 2019-06-25
[6 empty] | Issue Actual | 2019-05-30 | 2019-06-25 |  | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01761 | TPSK-LSPA1-T-IE-01976 |  | TPSK-LSPA1-T-IE-01976
[6 empty] | Return Date | 2019-06-21 | 2019-07-31 |  | 2019-07-31
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| IE | OL1-2I20-1152 | Instrument Datasheets for Orifice Plate |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-23
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02217
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1153 | Instrument Datasheets for Orifice Plate & Restriction Orifice |  |  | Purpose** | IFR | IFQ | IFP | IFP
[6 empty] | Rev. |  | A | 0 | 1
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-17 | 2019-05-24
[6 empty] | Revised Plan |  | 2019-06-14 | 2019-09-17
[6 empty] | Issue Actual |  | 2019-06-14 | 2019-09-17 | 2019-10-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01879 | TPSK-LSPA1-T-IE-02643 | TPSK-LSPA1-T-IE-02802
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I20-1154 | Instrument Datasheets for Pressure Gauge |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-07-01 | 2019-08-14 | 2019-09-27 | 2019-08-14
[6 empty] | Revised Plan |  | 2019-09-05 | 2019-12-17 | 2019-09-05
[6 empty] | Issue Actual |  | 2019-09-05 |  | 2019-09-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-TE-IE-02571 |  | TPSK-LSPA1-TE-IE-02571
[6 empty] | Return Date |  | 2019-10-08 |  | 2019-10-08
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1155 | Instrument Datasheets for Draft Gauge |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-07-01 | 2019-08-14 | 2019-09-27 | 2019-08-14
[6 empty] | Revised Plan |  | 2019-09-10 | 2019-12-17 | 2019-09-10
[6 empty] | Issue Actual |  | 2019-09-10 |  | 2019-09-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-02598 |  | TPSK-LSPA1-T-IE-02598
[6 empty] | Return Date |  | 2019-10-10 |  | 2019-10-10
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1156 | Instrument Datasheets for Pressure Indicating Transmitters & Flow Indicating DP Transmitters |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-07-01 | 2019-08-14 | 2019-09-27 | 2019-08-14
[6 empty] | Revised Plan | 2019-07-23 | 2019-08-21 | 2019-12-17 | 2019-08-21
[6 empty] | Issue Actual | 2019-07-23 | 2019-08-21 |  | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02222 | TPSK-LSPA1-T-IE-02456 |  | TPSK-LSPA1-T-IE-02456
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1157 | Instrument Datasheets for Temperature Elements for Thermocouples & RTDs with Wells |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan |  | 2019-09-10 | 2019-11-05 | 2019-09-10
[6 empty] | Issue Actual |  | 2019-09-10 |  | 2019-09-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-02598 |  | TPSK-LSPA1-T-IE-02598
[6 empty] | Return Date |  | 2019-10-10 |  | 2019-10-10
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1158 | Instrument Datasheets for Temperature Gauge and Thermowell |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan |  | 2019-09-28 | 2019-11-05 | 2019-09-28
[6 empty] | Issue Actual |  | 2019-09-28 |  | 2019-09-28
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-02723 |  | TPSK-LSPA1-T-PL-02723
Return Date
Owner Cmmt*
| IE | OL1-2I20-1159 | Instrument Datasheets for Temperature Transmitters |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan |  | 2019-08-28 | 2019-11-05 | 2019-08-28
[6 empty] | Issue Actual |  | 2019-08-28 |  | 2019-08-28
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-02506 |  | TPSK-LSPA1-T-IE-02506
[6 empty] | Return Date |  | 2019-10-08 |  | 2019-10-08
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1160 | Instrument Datasheets for Magnetostrictive Level Transmitter & Magnetic Level Gauge |  | Class 1 | Purpose** | IFQ | IFP
[6 empty] | Rev. | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-06-21 | 2019-08-21
[6 empty] | Issue Actual | 2019-06-21 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01953 | TPSK-LSPA1-T-IE-02454
[6 empty] | Return Date | 2019-07-31 | 2019-10-08
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2I20-1161 | Instrument Datasheets for Temperature Elements for Furnace Profile |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | B |  | B
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan |  | 2019-06-25 | 2019-11-05 | 2019-06-25
[6 empty] | Issue Actual |  | 2019-06-25 |  | 2019-06-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01975 |  | TPSK-LSPA1-T-IE-01975
[6 empty] | Return Date |  | 2019-07-31 |  | 2019-07-31
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1162 | Instrument Datasheets for Flow Element Venturi |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-17 | 2019-05-24 | 2019-04-17
[6 empty] | Revised Plan | 2019-05-29 | 2019-06-27 | 2019-10-16 | 2019-06-27
[6 empty] | Issue Actual | 2019-05-29 | 2019-06-27 |  | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01757 | TPSK-LSPA1-T-IE-02006 |  | TPSK-LSPA1-T-IE-02006
[6 empty] | Return Date | 2019-06-21 | 2019-07-31 |  | 2019-07-31
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| IE | OL1-2I20-1164 | Instrument Datasheets for Guided Wave Radar Level Transmitter & Magnetic Level Gauge |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-21
[6 empty] | Issue Actual | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01948
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1201 | Instrument Datasheets for Control Valve - Globe Type Area 12 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1206 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 12 - BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2I20-1211 | Instrument Datasheets for ON-OFF Valve -Ball Type -Area 12 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1212 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 12 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1222 | Instrument Datasheets for Flow Element -Orifice- Area 12 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1225 | Instrument Data Sheets For Flow Element Pitot Furmace Area 10-H-1200 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-24
[6 empty] | Issue Actual | 2019-06-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01965
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-1227 | Instrument Datasheets for Flow Instrument -Vortex - Area 12 - BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1906 | Instrument Datasheets for Self Actuated pressure Control Valve Area 19 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01692
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1911 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 19 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1916 | Instrument Datasheets for Pressure Safety Valve - Area 19 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2001 | Instrument Datasheets for Control Valve -Globe Type- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2002 | Instrument Datasheets for Control Valve -Butterfly Type- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2006 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2011 | Instrument Datasheets for ON-OFF Valve -Ball Type- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2012 | Instrument Datasheets for ON-OFF Valve -Butterfly Type- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2016 | Instrument Datasheets for Pressure Safety Valve - Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2018 | Instrument Data Sheets for Particulate Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-10
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02599
[6 empty] | Return Date | 2019-10-09
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2I20-2022 | Instrument Datasheets for Flow Element - Orifice - Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2024 | Instrument Datasheets for Flow Element -Flow Nozzle -Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2026 | Instrument Datasheets for Flow Element -Wedge Type-Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2028 | Instrument Datasheets for Flow Element - Rotameter - Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2032 | Instrument Datasheets for Flow Element -Integral Orifice- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2100 | Instrument Data Sheets for Gas Chromatographs |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-30
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02277
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2101 | Instrument Datasheets for Control Valve - Globe Type- Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2102 | Instrument Datasheets for Control Valve - Butterfly Type- Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2103 | Instrument DS For Oxygen Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02570
[6 empty] | Return Date | 2019-10-03
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2I20-2106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2107 | Instrument Data Sheets for Continuous Emission Monitoring System - CEMS |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-10
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02599
[6 empty] | Return Date | 2019-10-09
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2111 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2112 | Instrument Datasheets for ON-OFF Valve - Butterfly Type -Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2116 | Instrument Datasheets for Pressure Safety Valve - Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2122 | Instrument Datasheets for Flow Element -Orifice -Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2201 | Instrument Datasheets for Control Valve - Globe Type- Area 22 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01301
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2203 | Instrument DS For Moisture Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02570
[6 empty] | Return Date | 2019-10-03
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2211 | Instrument Datasheets for On-Off Vales - Ball Type - Area 22 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01301
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2213 | Instrument Datasheets for Motor Operated Valve - MOV - Area 22 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01301
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2216 | Instrument Datasheets for Pressure Safety Valve - Area 22 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2301 | Instrument Datasheets for Control Valve - Globe Type - Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2306 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2I20-2311 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2313 | Instrument Datasheets for Motor Operated Valve Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2316 | Instrument Datasheets for Pressure Safety Valve - Area 23 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2322 | Instrument Datasheets for Flow Element -Orifice -Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2329 | Instrument Datasheets for Flow transmitter - Electromagnetic - Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2332 | Instrument Datasheets for Flow Element - Integral Orifice- Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2401 | Instrument Datasheets for Control Valve - Globe Type - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2402 | Instrument Datasheets for Control Valve - Butterfly Type - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2403 | Instrument Data Sheet For Water Analyzer |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02761
Return Date
Owner Cmmt*
| IE | OL1-2I20-2411 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2412 | Instrument Datasheets for On-Off Valve - Butterfly Type - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2413 | Instrument Datasheets for Motor Operated Valve - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2416 | Instrument Datasheets for Pressure Safety Valve - Area 24 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-2422 | Instrument Datasheets for Flow Element -Orifice- Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2423 | Instrument Datasheets for Flow Element - Venturi - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01428
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2425 | Instrument Datasheets for Flow Element -Pitot - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01428
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2428 | Instrument Datasheets for Flow Element - Rotameter- Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01428
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2501 | Instrument Datasheets for Control Valve - Globe Type -Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2502 | Instrument Datasheets for Control Valve - Butterfly Type- Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2506 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01692
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2511 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2512 | Instrument Datasheets - ON-OFF Valve - Butterfly Type - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2513 | Instrument Datasheets for Motor Operated Valve Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2516 | Instrument Datasheets for Pressure Safety Valve - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-2522 | Instrument Datasheets for Flow Element - Orifice - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01338
Return Date
Owner Cmmt*
| IE | OL1-2I20-2523 | Instrument Datasheets for Flow Element -Venturi - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01388
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2528 | Instrument Datasheets for Flow Element - Rotameter - Area 25 |  | Class 1 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-15
[6 empty] | Issue Actual | 2019-04-15 | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01338 | TPSK-LSPA1-T-IE-01728
[6 empty] | Return Date |  | 2019-06-17
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I20-2601 | Instrument Datasheets for Control Valve - Globe Type - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2602 | Instrument Datasheet for Control Valve - Butterfly Type - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2603 | Instrument DS For Viscosity Analyzer |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02570
[6 empty] | Return Date | 2019-10-03
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2604 | Instrument DS For Density Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02570
[6 empty] | Return Date | 2019-10-03
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2I20-2611 | Instrument Datasheet for ON-OFF Valve - Ball Type- Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2612 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2613 | Instrument Datasheets for Motor Operated Valve - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2616 | Instrument Datasheets for Pressure Safety Valve - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2619 | Instrument Datasheets for Rupture Disc - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-04
[6 empty] | Issue Actual | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02565
Return Date
Owner Cmmt*
| IE | OL1-2I20-2622 | Instrument Datasheets for Flow Element Orifice Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSAP1-T-IE-01890
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2701 | Instrument Datasheets for Control Valve - Globe Type - Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-19
[6 empty] | Issue Actual | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01919
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2706 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01907
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2711 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-19
[6 empty] | Issue Actual | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01919
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2712 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-19
[6 empty] | Issue Actual | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01919
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2716 | Instrument Datasheets for Pressure Safety Valve - Area 27 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2722 | Instrument Datasheets for Flow Element - Orifice - Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01908
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2801 | Instrument Datasheets for Control Valve - Globe Type -Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2802 | Instrument Datasheets for Control Valve -Butterfly Type- Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2803 | Instrument Datasheets for Wobbe Index Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02280
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2804 | Instrument Datasheets for CO- CO2 Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02280
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2806 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 28 |  | Class 1 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01338 | TPSK-LSPA1-T-IE-01738
[6 empty] | Return Date |  | 2019-06-17
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I20-2811 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | 2019-06-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2812 | Instrument Datasheets - ON-OFF Valve - Butterfly Type- Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2813 | Instrument Datasheets for Motor Operated Valve Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2816 | Instrument Datasheets for Pressure Safety Valve - Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2822 | Instrument Datasheet for Flow Element -Orifice- Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01360
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2823 | Instrument Datasheets for Flow Element -Venturi- Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01360
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2828 | Instrument Datasheet for Flow Element - Rotameter - Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-17
[6 empty] | Issue Actual | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01681
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2830 | Instrument Datasheets for Flow Element - Coriolis - Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01360
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2901 | Instrument Datasheets for Control Valve - Globe Type - Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2902 | Instrument Datasheets for TOC - COD Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02280
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2906 | Instrument Datasheets for Self Actuated Pressure Control Valve - Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2911 | Instrument Datasheets for ON-OFF Valve (Ball Type) Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2916 | Instrument Datasheets for Pressure Safety Valve - Area 29 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-2922 | Instrument Datasheets for Flow Element -Orifice- Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2923 | Instrument Datasheets for Flow Element (Venturi Type) Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2924 | Instrument Datasheets for Flow Element - Flow Nozzle - Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01738
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3001 | Instrument Datasheets for Control Valve - Globe Type - Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02133
[6 empty] | Return Date | 2019-08-07
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3002 | Instrument Datasheets for Control Valve - Butterfly Type - Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02133
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3011 | Instrument Datasheets for ON-OFF Valve Ball Type Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3012 | Instrument Datasheets for ON-OFF Valve Butterfly Type Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3016 | Instrument Datasheets for Pressure Safety Valve - Area 30 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-15
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02429
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3019 | Instrument Datasheets for Rupture Disc - Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-04
[6 empty] | Issue Actual | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02565
Return Date
Owner Cmmt*
| IE | OL1-2I20-3022 | Instrument Datasheets for Flow Element (Orifice) Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3023 | Instrument Datasheets for Flow Element Venturi Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3027 | Instrument Datasheets for Flow Instrument Vortex Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
Return Date
Owner Cmmt*
| IE | OL1-2I20-3028 | Instrument Datasheets for Flow Element Rotameter - Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02087
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3029 | Instrument Datasheets for Flow Transmitter Electromagnetic Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3030 | Instrument Datasheets for Flow Element Coriolis Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-27
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02000
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3032 | Instrument Datasheets for Flow Element (Integral Orifice). Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3101 | Instrument Datasheets for Control Valve Globe Type - Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02087
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3106 | Instrument Datasheets for Self Actuated Pressure Control Valve.Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3111 | Instrument Datasheets for ON-OFF Valve Ball Type Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3112 | Instrument Datasheets for ON-OFF Valve Butterfly Type Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3116 | Instrument Datasheets for Pressure Safety Valve - Area 31 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02413
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3117 | Instrument Datasheets for Control Valve Angle Type - Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02087
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3119 | Instrument Datasheets for Rupture Disc - Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-04
[6 empty] | Issue Actual | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02565
Return Date
Owner Cmmt*
| IE | OL1-2I20-3122 | Instrument Datasheets for Flow Element Orifice Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3128 | Instrument Datasheets for Flow Element (Rotameter) Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3132 | Instrument Datasheets for Flow Element Integral Orifice Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3906 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 39 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3916 | Instrument Datasheets for Pressure Safety Valve - Area 39 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02413
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5001 | Instrument Datasheets for Control Valve - Globe Type - Area 50 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-31
[6 empty] | Issue Actual | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01774
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5022 | Instrument Datasheets for Flow Element -Orifice - Area 50 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-31
[6 empty] | Issue Actual | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01774
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5029 | Instrument Datasheets for Flow Transmitter -Electromagnetic- Area 50 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-31
[6 empty] | Issue Actual | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01774
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5031 | Instrument Datasheet for Flow Element - Ultrasonic - Area 50 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5101 | Instrument Datasheets for Control Valve - Globe Type- Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5112 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5116 | Instrument Datasheets for Pressure Safety Valve - Area 51 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-5117 | Instr. DS for Control Valve - Angle Type - Area 51 |  | Class 1 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14 | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01878 | TPSK-LSPA1-T-IE-02663
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5118 | Instrument Datasheets for Control Valve - Three way Type - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5122 | Instrument Datasheets for Flow Element - Orifice - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5124 | Instrument Datasheets for Flow Element - Flow Nozzle - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5128 | Instrument Datasheets for Flow Element - Rotameter - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5201 | Instrument Datasheets for Control Valve - Globe Type - Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5202 | Instrument Datasheets for Control Valve - Butterfly Type - Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5211 | Instrument Datasheets for ON-OFF - Ball Type - Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5212 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5216 | Instrument Datasheets for Pressure Safety Valve - Area 52 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-23
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02213
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5222 | Instrument Datasheets for Flow Element -Orifice- Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5301 | Instrument Datasheets for Control Valve - Globe Type - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5302 | Instrument Datasheets for Control Valve -Butterfly Type - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5322 | Instrument Datasheets for Flow Element - Orifice - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5325 | Instrument Datasheets for Flow Element - Pitot - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5329 | Instrument Datasheets for Flow Transmitter - Electromagnetic - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2I20-5401 | Instrument Datasheets Control Valve - Globe Type - Area 54 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5416 | Instrument Datasheet for Pressure Safety Valve - Area 54 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-23
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02213
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5422 | Instrument Datasheets for Flow Element - Orifice- Area 54 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5430 | Instrument Datasheets for Flow Element - Coriolis- Area 54 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5501 | Instrument Datasheets for Control Valve - Globe Type- Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5506 | Instrument Datasheets for Self Actuated Pressure Control Valve - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5511 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5512 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5516 | Instrument Datasheets for Pressure Safety Valve - Area 55 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-23
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02213
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5522 | Instrument Datasheets for Flow Element - Orifice - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5529 | Instrument Datasheets for Flow Transmitter - Electromagnetic - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5531 | Instrument Datasheets for Flow Element - Ultrasonic - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5601 | Instrument Datasheets for Control Valve - Globe Type - Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01866
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5606 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5611 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01866
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5612 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01866
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5622 | Instrument Datasheets for Flow Element - Orifice - Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5901 | Instrument Datasheets for Control Valve - Globe Type - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5906 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5911 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5916 | Instrument Datasheets for Pressure Safety Valve - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-5922 | Instrument Datasheets for Flow Element - Orifice - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5924 | Instrument Datasheets for Flow Element - Flow Nozzle- Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5932 | Instrument Datasheets for Flow Element - Integral Orifice - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
Category Code: I20 Instrument datasheet
| IE | OL1-2I20-0120 | DATA SHEET FOR CUSTODY TRANSFER METERING |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-04-26 | 2019-11-30
[6 empty] | Revised Plan | 2019-10-25 | 2019-11-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I20-1001 | USC 36M and USC 132U Instrument Datasheets for Control Valve |  |  | Purpose** | IFR | IFA | IFQ | IFP
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-02-25 |  | 2019-04-03 | 2019-05-10
[6 empty] | Revised Plan |  | 2019-03-22 |  | 2019-10-16
[6 empty] | Issue Actual |  | 2019-03-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01130
[6 empty] | Return Date |  | 2019-04-02
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I20-1002 | Instrument Datasheet for Pressure Relief Valve |  | Class 1 | Purpose** | IFP | IFP
[6 empty] | Rev. | 0 | 1
Issue Plan
[6 empty] | Revised Plan | 2019-08-06
[6 empty] | Issue Actual | 2019-08-06 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02350 | TPSK-LSPA1-T-IE-02681
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1005 | USC 36M and USC 132U Instrument Datasheets for Level Gauge |  |  | Purpose** | IFR | IFQ | IFP | IFP
[6 empty] | Rev. | A |  | 0 | 0
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05
[6 empty] | Revised Plan | 2019-03-14 |  | 2019-08-14
[6 empty] | Issue Actual | 2019-03-14 |  | 2019-08-14 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01047 |  | TPSK-LSPA1-T-IE-02414 | TPSK-LSPA1-T-IE-02414
[6 empty] | Return Date | 2019-03-27 |  | 2019-09-19 | 2019-09-19
[6 empty] | Owner Cmmt* | R2 |  | R2 | R2
| IE | OL1-2I20-1006 | Instrument Datasheets for Level Transmitter and Level Transmitter W-Gauge |  |  | Purpose** | IFR | IFQ | IFR | IFP | IFR
[6 empty] | Rev. | A |  | A |  | A
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-08-06 | 2019-11-05 | 2019-08-06
[6 empty] | Revised Plan | 2019-04-10 |  | 2019-04-10 | 2019-11-05 | 2019-04-10
[6 empty] | Issue Actual | 2019-04-10 |  | 2019-04-10 |  | 2019-04-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01288 |  | TPSK-LSPA1-T-IE-01288 |  | TPSK-LSPA1-T-IE-01288
[6 empty] | Return Date | 2019-05-13 |  | 2019-05-13 |  | 2019-05-13
[6 empty] | Owner Cmmt* | R2 |  | R2 |  | R2
| IE | OL1-2I20-1009 | Instrument Datasheets for Control Valve - Globe Type - Area 10 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01692
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1010 | Instrument Datasheets for ON-OFF Valve -Ball Type -Area 10 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01658
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1011 | Instrument Datasheets for Temperature Elements for Coil Outlet |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan | 2019-04-11 | 2019-05-24 | 2019-11-05 | 2019-05-24
[6 empty] | Issue Actual | 2019-04-11 | 2019-05-24 |  | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01309 | TPSK-LSPA1-T-IE-01729 |  | TPSK-LSPA1-T-IE-01729
[6 empty] | Return Date |  | 2019-07-17 |  | 2019-07-17
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1012 | Instrument Datasheets for ON-OFF Valve -Butterfly Type- Area 10 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1015 | USC 36M and USC 132U Instrument Datasheets for pH and Conductivity Analyzer |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan | 2019-03-22 | 2019-05-24 | 2019-11-05 | 2019-05-24
[6 empty] | Issue Actual | 2019-03-22 | 2019-05-24 |  | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01131 | TPSK-LSPA1-T-IE-01730 |  | TPSK-LSPA1-T-IE-01730
[6 empty] | Return Date | 2019-04-02 | 2019-06-13 |  | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| IE | OL1-2I20-1016 | Instrument Datasheets for Pressure Safety Valve - Area 10 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1022 | Instrument Datasheets for Flow Element -Orifice - Area 10 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1101 | Instrument Datasheets for Control Valve -Globe Type- Area 11 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
Return Date
Owner Cmmt*
| IE | OL1-2I20-1106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 11 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1111 | Instrument Datasheets for ON-OFF Valve Ball Type - Area 11 BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1112 | Instrument Datasheets for ON-OFF Valve Butterfly Type - Area 11 BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2I20-1122 | Instrument Datasheets for Flow Element Orifice- Area 11 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1125 | Instrument Data Sheets Flow Element Pitot Furmace Area 10-H-1100 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-24
[6 empty] | Issue Actual | 2019-06-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01965
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-1127 | Instrument Datasheets for Flow Instrument -Vortex-Area 11 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1151 | Instrument Datasheets for O2 & Combustible Analyzer |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-05-09 | 2019-06-22 | 2019-08-05 | 2019-06-22
[6 empty] | Revised Plan | 2019-05-30 | 2019-06-25 | 2019-10-25 | 2019-06-25
[6 empty] | Issue Actual | 2019-05-30 | 2019-06-25 |  | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01761 | TPSK-LSPA1-T-IE-01976 |  | TPSK-LSPA1-T-IE-01976
[6 empty] | Return Date | 2019-06-21 | 2019-07-31 |  | 2019-07-31
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| IE | OL1-2I20-1152 | Instrument Datasheets for Orifice Plate |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-23
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02217
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1153 | Instrument Datasheets for Orifice Plate & Restriction Orifice |  |  | Purpose** | IFR | IFQ | IFP | IFP
[6 empty] | Rev. |  | A | 0 | 1
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-17 | 2019-05-24
[6 empty] | Revised Plan |  | 2019-06-14 | 2019-09-17
[6 empty] | Issue Actual |  | 2019-06-14 | 2019-09-17 | 2019-10-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01879 | TPSK-LSPA1-T-IE-02643 | TPSK-LSPA1-T-IE-02802
[6 empty] | Return Date |  | 2019-07-08
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I20-1154 | Instrument Datasheets for Pressure Gauge |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-07-01 | 2019-08-14 | 2019-09-27 | 2019-08-14
[6 empty] | Revised Plan |  | 2019-09-05 | 2019-12-17 | 2019-09-05
[6 empty] | Issue Actual |  | 2019-09-05 |  | 2019-09-05
[6 empty] | Transmittal no. |  | TPSK-LSPA1-TE-IE-02571 |  | TPSK-LSPA1-TE-IE-02571
[6 empty] | Return Date |  | 2019-10-08 |  | 2019-10-08
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1155 | Instrument Datasheets for Draft Gauge |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-07-01 | 2019-08-14 | 2019-09-27 | 2019-08-14
[6 empty] | Revised Plan |  | 2019-09-10 | 2019-12-17 | 2019-09-10
[6 empty] | Issue Actual |  | 2019-09-10 |  | 2019-09-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-02598 |  | TPSK-LSPA1-T-IE-02598
[6 empty] | Return Date |  | 2019-10-10 |  | 2019-10-10
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1156 | Instrument Datasheets for Pressure Indicating Transmitters & Flow Indicating DP Transmitters |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-07-01 | 2019-08-14 | 2019-09-27 | 2019-08-14
[6 empty] | Revised Plan | 2019-07-23 | 2019-08-21 | 2019-12-17 | 2019-08-21
[6 empty] | Issue Actual | 2019-07-23 | 2019-08-21 |  | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02222 | TPSK-LSPA1-T-IE-02456 |  | TPSK-LSPA1-T-IE-02456
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1157 | Instrument Datasheets for Temperature Elements for Thermocouples & RTDs with Wells |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan |  | 2019-09-10 | 2019-11-05 | 2019-09-10
[6 empty] | Issue Actual |  | 2019-09-10 |  | 2019-09-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-02598 |  | TPSK-LSPA1-T-IE-02598
[6 empty] | Return Date |  | 2019-10-10 |  | 2019-10-10
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1158 | Instrument Datasheets for Temperature Gauge and Thermowell |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan |  | 2019-09-28 | 2019-11-05 | 2019-09-28
[6 empty] | Issue Actual |  | 2019-09-28 |  | 2019-09-28
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-02723 |  | TPSK-LSPA1-T-PL-02723
Return Date
Owner Cmmt*
| IE | OL1-2I20-1159 | Instrument Datasheets for Temperature Transmitters |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | A |  | A
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan |  | 2019-08-28 | 2019-11-05 | 2019-08-28
[6 empty] | Issue Actual |  | 2019-08-28 |  | 2019-08-28
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-02506 |  | TPSK-LSPA1-T-IE-02506
[6 empty] | Return Date |  | 2019-10-08 |  | 2019-10-08
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1160 | Instrument Datasheets for Magnetostrictive Level Transmitter & Magnetic Level Gauge |  | Class 1 | Purpose** | IFQ | IFP
[6 empty] | Rev. | B | 0
Issue Plan
[6 empty] | Revised Plan | 2019-06-21 | 2019-08-21
[6 empty] | Issue Actual | 2019-06-21 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01953 | TPSK-LSPA1-T-IE-02454
[6 empty] | Return Date | 2019-07-31 | 2019-10-08
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2I20-1161 | Instrument Datasheets for Temperature Elements for Furnace Profile |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. |  | B |  | B
[6 empty] | Issue Plan | 2019-08-06 | 2019-09-20 | 2019-11-05 | 2019-09-20
[6 empty] | Revised Plan |  | 2019-06-25 | 2019-11-05 | 2019-06-25
[6 empty] | Issue Actual |  | 2019-06-25 |  | 2019-06-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01975 |  | TPSK-LSPA1-T-IE-01975
[6 empty] | Return Date |  | 2019-07-31 |  | 2019-07-31
[6 empty] | Owner Cmmt* |  | R2 |  | R2
| IE | OL1-2I20-1162 | Instrument Datasheets for Flow Element Venturi |  |  | Purpose** | IFR | IFQ | IFP | IFQ
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-03-11 | 2019-04-17 | 2019-05-24 | 2019-04-17
[6 empty] | Revised Plan | 2019-05-29 | 2019-06-27 | 2019-10-16 | 2019-06-27
[6 empty] | Issue Actual | 2019-05-29 | 2019-06-27 |  | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01757 | TPSK-LSPA1-T-IE-02006 |  | TPSK-LSPA1-T-IE-02006
[6 empty] | Return Date | 2019-06-21 | 2019-07-31 |  | 2019-07-31
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| IE | OL1-2I20-1164 | Instrument Datasheets for Guided Wave Radar Level Transmitter & Magnetic Level Gauge |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-21
[6 empty] | Issue Actual | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01948
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1201 | Instrument Datasheets for Control Valve - Globe Type Area 12 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1206 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 12 - BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2I20-1211 | Instrument Datasheets for ON-OFF Valve -Ball Type -Area 12 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1212 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 12 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1222 | Instrument Datasheets for Flow Element -Orifice- Area 12 -BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-08
[6 empty] | Issue Actual | 2019-05-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01594
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1225 | Instrument Data Sheets For Flow Element Pitot Furmace Area 10-H-1200 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-24
[6 empty] | Issue Actual | 2019-06-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01965
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-1227 | Instrument Datasheets for Flow Instrument -Vortex - Area 12 - BOP |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-09
[6 empty] | Issue Actual | 2019-05-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01615
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1906 | Instrument Datasheets for Self Actuated pressure Control Valve Area 19 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01692
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1911 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 19 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-1916 | Instrument Datasheets for Pressure Safety Valve - Area 19 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2001 | Instrument Datasheets for Control Valve -Globe Type- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2002 | Instrument Datasheets for Control Valve -Butterfly Type- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2006 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2011 | Instrument Datasheets for ON-OFF Valve -Ball Type- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2012 | Instrument Datasheets for ON-OFF Valve -Butterfly Type- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2016 | Instrument Datasheets for Pressure Safety Valve - Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2018 | Instrument Data Sheets for Particulate Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-10
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02599
[6 empty] | Return Date | 2019-10-09
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2I20-2022 | Instrument Datasheets for Flow Element - Orifice - Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2024 | Instrument Datasheets for Flow Element -Flow Nozzle -Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2026 | Instrument Datasheets for Flow Element -Wedge Type-Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2028 | Instrument Datasheets for Flow Element - Rotameter - Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2032 | Instrument Datasheets for Flow Element -Integral Orifice- Area 20 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2100 | Instrument Data Sheets for Gas Chromatographs |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-30
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02277
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2101 | Instrument Datasheets for Control Valve - Globe Type- Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2102 | Instrument Datasheets for Control Valve - Butterfly Type- Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2103 | Instrument DS For Oxygen Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02570
[6 empty] | Return Date | 2019-10-03
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2I20-2106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2107 | Instrument Data Sheets for Continuous Emission Monitoring System - CEMS |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-10
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02599
[6 empty] | Return Date | 2019-10-09
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2111 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-10
[6 empty] | Issue Actual | 2019-05-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01625
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2112 | Instrument Datasheets for ON-OFF Valve - Butterfly Type -Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-14
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01650
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2116 | Instrument Datasheets for Pressure Safety Valve - Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2122 | Instrument Datasheets for Flow Element -Orifice -Area 21 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2201 | Instrument Datasheets for Control Valve - Globe Type- Area 22 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01301
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2203 | Instrument DS For Moisture Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02570
[6 empty] | Return Date | 2019-10-03
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2211 | Instrument Datasheets for On-Off Vales - Ball Type - Area 22 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01301
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2213 | Instrument Datasheets for Motor Operated Valve - MOV - Area 22 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01301
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2216 | Instrument Datasheets for Pressure Safety Valve - Area 22 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2301 | Instrument Datasheets for Control Valve - Globe Type - Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2306 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2I20-2311 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2313 | Instrument Datasheets for Motor Operated Valve Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2316 | Instrument Datasheets for Pressure Safety Valve - Area 23 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2322 | Instrument Datasheets for Flow Element -Orifice -Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2329 | Instrument Datasheets for Flow transmitter - Electromagnetic - Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2332 | Instrument Datasheets for Flow Element - Integral Orifice- Area 23 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2401 | Instrument Datasheets for Control Valve - Globe Type - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2402 | Instrument Datasheets for Control Valve - Butterfly Type - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2403 | Instrument Data Sheet For Water Analyzer |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02761
Return Date
Owner Cmmt*
| IE | OL1-2I20-2411 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-07
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01581
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2412 | Instrument Datasheets for On-Off Valve - Butterfly Type - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2413 | Instrument Datasheets for Motor Operated Valve - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01550
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2416 | Instrument Datasheets for Pressure Safety Valve - Area 24 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-2422 | Instrument Datasheets for Flow Element -Orifice- Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-03
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01548
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2423 | Instrument Datasheets for Flow Element - Venturi - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01428
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2425 | Instrument Datasheets for Flow Element -Pitot - Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01428
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2428 | Instrument Datasheets for Flow Element - Rotameter- Area 24 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01428
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2501 | Instrument Datasheets for Control Valve - Globe Type -Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2502 | Instrument Datasheets for Control Valve - Butterfly Type- Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2506 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01692
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2511 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2512 | Instrument Datasheets - ON-OFF Valve - Butterfly Type - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2513 | Instrument Datasheets for Motor Operated Valve Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01660
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2516 | Instrument Datasheets for Pressure Safety Valve - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-2522 | Instrument Datasheets for Flow Element - Orifice - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01338
Return Date
Owner Cmmt*
| IE | OL1-2I20-2523 | Instrument Datasheets for Flow Element -Venturi - Area 25 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01388
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2528 | Instrument Datasheets for Flow Element - Rotameter - Area 25 |  | Class 1 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-15
[6 empty] | Issue Actual | 2019-04-15 | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01338 | TPSK-LSPA1-T-IE-01728
[6 empty] | Return Date |  | 2019-06-17
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I20-2601 | Instrument Datasheets for Control Valve - Globe Type - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2602 | Instrument Datasheet for Control Valve - Butterfly Type - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2603 | Instrument DS For Viscosity Analyzer |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02570
[6 empty] | Return Date | 2019-10-03
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2604 | Instrument DS For Density Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02570
[6 empty] | Return Date | 2019-10-03
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2I20-2611 | Instrument Datasheet for ON-OFF Valve - Ball Type- Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2612 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2613 | Instrument Datasheets for Motor Operated Valve - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2616 | Instrument Datasheets for Pressure Safety Valve - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2619 | Instrument Datasheets for Rupture Disc - Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-04
[6 empty] | Issue Actual | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02565
Return Date
Owner Cmmt*
| IE | OL1-2I20-2622 | Instrument Datasheets for Flow Element Orifice Area 26 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSAP1-T-IE-01890
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2701 | Instrument Datasheets for Control Valve - Globe Type - Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-19
[6 empty] | Issue Actual | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01919
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2706 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01907
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2711 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-19
[6 empty] | Issue Actual | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01919
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2712 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-19
[6 empty] | Issue Actual | 2019-06-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01919
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2716 | Instrument Datasheets for Pressure Safety Valve - Area 27 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2722 | Instrument Datasheets for Flow Element - Orifice - Area 27 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-18
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01908
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2801 | Instrument Datasheets for Control Valve - Globe Type -Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2802 | Instrument Datasheets for Control Valve -Butterfly Type- Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2803 | Instrument Datasheets for Wobbe Index Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02280
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2804 | Instrument Datasheets for CO- CO2 Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02280
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2806 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 28 |  | Class 1 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23 | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01338 | TPSK-LSPA1-T-IE-01738
[6 empty] | Return Date |  | 2019-06-17
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I20-2811 | Instrument Datasheets - ON-OFF Valve - Ball Type - Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | 2019-06-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2812 | Instrument Datasheets - ON-OFF Valve - Butterfly Type- Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01376
[6 empty] | Return Date | 2019-05-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2813 | Instrument Datasheets for Motor Operated Valve Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-25
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01464
[6 empty] | Return Date | 2019-07-02
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2816 | Instrument Datasheets for Pressure Safety Valve - Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2822 | Instrument Datasheet for Flow Element -Orifice- Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01360
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2823 | Instrument Datasheets for Flow Element -Venturi- Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01360
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2828 | Instrument Datasheet for Flow Element - Rotameter - Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-17
[6 empty] | Issue Actual | 2019-05-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01681
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2830 | Instrument Datasheets for Flow Element - Coriolis - Area 28 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-23
[6 empty] | Issue Actual | 2019-04-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01360
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2901 | Instrument Datasheets for Control Valve - Globe Type - Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2902 | Instrument Datasheets for TOC - COD Analyzers |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02280
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I20-2906 | Instrument Datasheets for Self Actuated Pressure Control Valve - Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2911 | Instrument Datasheets for ON-OFF Valve (Ball Type) Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2916 | Instrument Datasheets for Pressure Safety Valve - Area 29 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-2922 | Instrument Datasheets for Flow Element -Orifice- Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2923 | Instrument Datasheets for Flow Element (Venturi Type) Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-23
[6 empty] | Issue Actual | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01717
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-2924 | Instrument Datasheets for Flow Element - Flow Nozzle - Area 29 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-27
[6 empty] | Issue Actual | 2019-05-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01738
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3001 | Instrument Datasheets for Control Valve - Globe Type - Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02133
[6 empty] | Return Date | 2019-08-07
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3002 | Instrument Datasheets for Control Valve - Butterfly Type - Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02133
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3011 | Instrument Datasheets for ON-OFF Valve Ball Type Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3012 | Instrument Datasheets for ON-OFF Valve Butterfly Type Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3016 | Instrument Datasheets for Pressure Safety Valve - Area 30 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-15
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02429
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3019 | Instrument Datasheets for Rupture Disc - Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-04
[6 empty] | Issue Actual | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02565
Return Date
Owner Cmmt*
| IE | OL1-2I20-3022 | Instrument Datasheets for Flow Element (Orifice) Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3023 | Instrument Datasheets for Flow Element Venturi Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3027 | Instrument Datasheets for Flow Instrument Vortex Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
Return Date
Owner Cmmt*
| IE | OL1-2I20-3028 | Instrument Datasheets for Flow Element Rotameter - Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02087
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3029 | Instrument Datasheets for Flow Transmitter Electromagnetic Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3030 | Instrument Datasheets for Flow Element Coriolis Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-27
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02000
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3032 | Instrument Datasheets for Flow Element (Integral Orifice). Area 30 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3101 | Instrument Datasheets for Control Valve Globe Type - Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02087
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3106 | Instrument Datasheets for Self Actuated Pressure Control Valve.Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-10
[6 empty] | Issue Actual | 2019-07-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02110
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3111 | Instrument Datasheets for ON-OFF Valve Ball Type Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3112 | Instrument Datasheets for ON-OFF Valve Butterfly Type Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3116 | Instrument Datasheets for Pressure Safety Valve - Area 31 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02413
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3117 | Instrument Datasheets for Control Valve Angle Type - Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-08
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02087
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3119 | Instrument Datasheets for Rupture Disc - Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-04
[6 empty] | Issue Actual | 2019-09-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02565
Return Date
Owner Cmmt*
| IE | OL1-2I20-3122 | Instrument Datasheets for Flow Element Orifice Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3128 | Instrument Datasheets for Flow Element (Rotameter) Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3132 | Instrument Datasheets for Flow Element Integral Orifice Area 31 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-02
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02037
[6 empty] | Return Date | 2019-07-24
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3906 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 39 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-09
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-2097
[6 empty] | Return Date | 2019-07-31
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-3916 | Instrument Datasheets for Pressure Safety Valve - Area 39 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-08-14
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02413
[6 empty] | Return Date | 2019-09-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5001 | Instrument Datasheets for Control Valve - Globe Type - Area 50 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-31
[6 empty] | Issue Actual | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01774
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5022 | Instrument Datasheets for Flow Element -Orifice - Area 50 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-31
[6 empty] | Issue Actual | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01774
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5029 | Instrument Datasheets for Flow Transmitter -Electromagnetic- Area 50 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-31
[6 empty] | Issue Actual | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01774
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5031 | Instrument Datasheet for Flow Element - Ultrasonic - Area 50 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5101 | Instrument Datasheets for Control Valve - Globe Type- Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5106 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5112 | Instrument Datasheets for ON-OFF Valve -Butterfly Type - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5116 | Instrument Datasheets for Pressure Safety Valve - Area 51 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-25
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02258
Return Date
Owner Cmmt*
| IE | OL1-2I20-5117 | Instr. DS for Control Valve - Angle Type - Area 51 |  | Class 1 | Purpose** | IFQ | IFQ
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14 | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01878 | TPSK-LSPA1-T-IE-02663
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5118 | Instrument Datasheets for Control Valve - Three way Type - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5122 | Instrument Datasheets for Flow Element - Orifice - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5124 | Instrument Datasheets for Flow Element - Flow Nozzle - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5128 | Instrument Datasheets for Flow Element - Rotameter - Area 51 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5201 | Instrument Datasheets for Control Valve - Globe Type - Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5202 | Instrument Datasheets for Control Valve - Butterfly Type - Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5211 | Instrument Datasheets for ON-OFF - Ball Type - Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5212 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5216 | Instrument Datasheets for Pressure Safety Valve - Area 52 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-23
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02213
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5222 | Instrument Datasheets for Flow Element -Orifice- Area 52 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5301 | Instrument Datasheets for Control Valve - Globe Type - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5302 | Instrument Datasheets for Control Valve -Butterfly Type - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5322 | Instrument Datasheets for Flow Element - Orifice - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5325 | Instrument Datasheets for Flow Element - Pitot - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5329 | Instrument Datasheets for Flow Transmitter - Electromagnetic - Area 53 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2I20-5401 | Instrument Datasheets Control Valve - Globe Type - Area 54 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5416 | Instrument Datasheet for Pressure Safety Valve - Area 54 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-23
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02213
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5422 | Instrument Datasheets for Flow Element - Orifice- Area 54 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5430 | Instrument Datasheets for Flow Element - Coriolis- Area 54 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5501 | Instrument Datasheets for Control Valve - Globe Type- Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5506 | Instrument Datasheets for Self Actuated Pressure Control Valve - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-06-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5511 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5512 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01792
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5516 | Instrument Datasheets for Pressure Safety Valve - Area 55 |  | Class 1 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-23
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02213
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5522 | Instrument Datasheets for Flow Element - Orifice - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5529 | Instrument Datasheets for Flow Transmitter - Electromagnetic - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5531 | Instrument Datasheets for Flow Element - Ultrasonic - Area 55 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01807
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5601 | Instrument Datasheets for Control Valve - Globe Type - Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01866
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5606 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-14
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01878
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5611 | Instrument Datasheets for ON-OFF Valve - Ball Type - Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01866
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5612 | Instrument Datasheets for ON-OFF Valve - Butterfly Type - Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01866
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5622 | Instrument Datasheets for Flow Element - Orifice - Area 56 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5901 | Instrument Datasheets for Control Valve - Globe Type - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5906 | Instrument Datasheets for Self Actuated Pressure Control Valve Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5911 | Instrument Datasheets for ON-OFF Valve -Ball Type - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5916 | Instrument Datasheets for Pressure Safety Valve - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02291
Return Date
Owner Cmmt*
| IE | OL1-2I20-5922 | Instrument Datasheets for Flow Element - Orifice - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5924 | Instrument Datasheets for Flow Element - Flow Nozzle- Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-10
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK- LSPA1-T-IE-01828
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I20-5932 | Instrument Datasheets for Flow Element - Integral Orifice - Area 59 |  | Class 1 | Purpose** | IFQ
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-06-11
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01845
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | R2
Category Code: I21 Instrument Calculation sheet
| IE | OL1-2I21-1001 | INTRINSIC SAFETY LOOP CALCULATION |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18
[6 empty] | Revised Plan | 2020-04-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I30 Interlock Logic and Sequence Diagram
| IE | OL1-2I30-1001 | Cause and Effect Diagram - Area 10 - Feed Preparation and Feed Preheat |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-14
[6 empty] | Issue Actual | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01043
Return Date
Owner Cmmt*
| IE | OL1-2I30-1002 | Instrument Interlock Descriptions - Area 10 - Feed Preparation and Feed Preheat |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-14
[6 empty] | Issue Actual | 2019-03-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01045
[6 empty] | Return Date | 2019-04-10
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I30-1101 | DCS INTERLOCK AND SEQUENCES DIAGRAMS |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-11-29 | 2020-03-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-11-29 | 2020-03-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-1102 | ESD INTERLOCK LOGIC DIAGRAMS |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-11-29 | 2020-03-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-11-29 | 2020-03-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I30-2001 | Cause and Effect Diagram Area 20 - Quench Oil |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-18
[6 empty] | Issue Actual | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01087
[6 empty] | Return Date | 2019-04-10
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I30-2002 | Instrument Interlock Descriptions Area 20 - Quench Oil |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-18
[6 empty] | Issue Actual | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01088
[6 empty] | Return Date | 2019-04-10
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I30-5301 | Cause and Effect Diagram - Area 53 - Cooling Water System |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-13
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01036
[6 empty] | Return Date | 2019-03-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I30-5302 | Instrument Interlock Descriptions - Area 53- Cooling Water System |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-13
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01037
[6 empty] | Return Date | 2019-03-29
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I30-5901 | Cause and Effect Diagram Area 59 - Supporting Utilities Auxiliaries |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-18
[6 empty] | Issue Actual | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01087
[6 empty] | Return Date | 2019-04-10
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I30-5902 | Instrument Interlock Descriptions Area 59 - Supporting Utilities Auxiliaries |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-03-18
[6 empty] | Issue Actual | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01088
[6 empty] | Return Date | 2019-04-10
[6 empty] | Owner Cmmt* | R2
Category Code: I31 Typical installation / fabrication drawing
| IE | OL1-2I31-0001 | Instr Supports Typical Mount Details |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-12-31 |  | 2020-05-25 | 2020-09-29
[6 empty] | Revised Plan | 2019-03-15 |  | 2019-10-10 | 2020-09-29
[6 empty] | Issue Actual | 2019-03-15 | 2019-04-18 | 2019-10-10
[6 empty] | Transmittal no. | TPSL-LSPA1-T-IE-01058 | TPSK-LPSA1-T-IE-01391 | TPSK-LSPA1-T-IE-02789
[6 empty] | Return Date | 2019-04-05 | 2019-05-18
[6 empty] | Owner Cmmt* | A3 | A3
| IE | OL1-2I31-0200 | Level Istrument Design And Nozzle Study Common Area OSBL 0C |  | Class 1 | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-06-28 | 2019-10-15
[6 empty] | Issue Actual | 2019-06-28 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02015 | TPSK-LSPA1-T-IE-02844
[6 empty] | Return Date | 2019-07-10
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0201 | Level Studies And Instrument Design ISBL - 0P |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-07-30 | 2019-10-15 | 2019-12-15
[6 empty] | Issue Actual | 2019-07-30 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02278 | TPSK-LSPA1-T-IE-02844
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0202 | Level Instrument Design And Nozzle Study for Furnaces Utilities ISBL 1B |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-28 | 2019-10-18 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02015
[6 empty] | Return Date | 2019-07-10
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0203 | Level Instrument Design and Nozzle Study for Quench - ISBL (2A) |  |  | Purpose** | IFR | IFR | IDD | IFC
[6 empty] | Rev. | A | B | C
[6 empty] | Issue Plan | 2019-04-15 |  | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-04-19 |  | 2019-10-10 | 2019-12-15
[6 empty] | Issue Actual | 2019-04-19 | 2019-07-11 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01413 | TPSK-LSPA1-T-IE-02120 | TPSK-LSPA1-T-IE-02789
[6 empty] | Return Date | 2019-05-18 | 2019-07-22
[6 empty] | Owner Cmmt* | A3 | A2
| IE | OL1-2I31-0204 | Level Studies And Instrument Design - ISBL - 2B Area |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-14 | 2019-10-15 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-14 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01888 | TPSK-LSPA1-T-IE-02844
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0205 | Level Studies And Instrument Design - ISBL - 2C Area |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-28 | 2019-10-15 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-28 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02015 | TPSK-LSPA1-T-IE-02844
[6 empty] | Return Date | 2019-07-10
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0206 | Level Instrument Design Process Cold Compressors ISBL |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-24 | 2019-10-18 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01964
[6 empty] | Return Date | 2019-07-05
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0207 | Level Instrument Design Cracked Gas Compressor - ISBL |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-18 | 2019-10-18 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01905
[6 empty] | Return Date | 2019-06-28
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0208 | Level Studies And Instrument Design - OSBL - 3A Area |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-28 | 2019-10-15 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-28 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02015 | TPSK-LSPA1-T-IE-02844
[6 empty] | Return Date | 2019-07-10
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0210 | Level Instrument Design Flare Unit; OSBL |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-14 | 2019-10-18 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01888
[6 empty] | Return Date | 2019-07-01
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0211 | Level Instument Design And Nozzle Studies For Cooling Water Unit OSBL 5T |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-24 | 2019-10-18 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01964
[6 empty] | Return Date | 2019-07-05
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0212 | Level Instrument Design Utilities OSBL |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-24 | 2019-10-18 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01964
[6 empty] | Return Date | 2019-07-05
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0213 | Level Instrument Design And Nozzle Study For Water Treatment Osbl 5W |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-06-28 | 2019-10-18 | 2019-12-15
[6 empty] | Issue Actual | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02015
[6 empty] | Return Date | 2019-07-10
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I31-0214 | Level Instrument Design For Towers and Reactors |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-05-24 | 2019-10-10 | 2019-12-15
[6 empty] | Issue Actual | 2019-05-24 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01725 | TPSK-LSPA1-T-IE-02789
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2I31-0215 | Level Instrument Design for Towers and Reactors - OSBL - Originated by splitting Doc N. OL1-2I31-0214 |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-04-15 | 2019-06-15 | 2019-12-15
[6 empty] | Revised Plan |  | 2019-10-15 | 2019-12-15
[6 empty] | Issue Actual |  | 2019-10-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-02844
Return Date
Owner Cmmt*
| IE | OL1-2I31-1003 | FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1005 | PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1012 | PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1019 | FLOW TRANSMITTER - LIQUID SERVICE 900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1020 | PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1021 | LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-1022 | PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2001 | O2 COMBUSTIBLE ANALYZER PROCESS CONNECTION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2002 | O2 COMBUSTIBLE ANALYZER INSTRUMENT ELECTRICAL CONNECTION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2003 | FLOW TRANSMITTER - VENTURI STEAM LIQUID SERVICE - 900 AND ABOVE TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2004 | PRESSURE GAUGE - GAS SERVICE DRAFT REMOTE MOUNTING |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2005 | PRESSURE TRANSMITTER - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2006 | EYE-HYE LEVEL COMPONENTS ON STEAM DRUM ELECTRICAL CONNECTION |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2007 | COT INSERTION WELL T-C CONNECTION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2008 | INSTRUMENT SUPPORT DETAIL EYE-HYE LEVEL CONTROL UNIT |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2009 | INSTRUMENT PROCESS DETAILS DRAFT D-P TRANSMITTER GAS SERVICE REMOTE MOUNTED |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2010 | INSTRUMENT SUPPORT DETAILS DUAL STAND 4FT-4IN OUTSIDE HANDRAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2011 | INSTRUMENT SUPPORT DETAILS TRIPLE STAND 4FT-4IN OUTSIDE HANDRAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2012 | PRESSURE GAUGE - GAS SERVICE REMOTE MOUNTED TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2013 | THERMOCOUPLE HEAD ELECTRICAL CONNECTION DETAIL 3-4IN CONDUIT |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2014 | TEMPERATURE TRANSMITTER ELECTRICAL CONNECTION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2015 | LUBE OIL VENDOR JUNCTION BOX TO FIE CHARM BOX ELECTRICAL CONNECTION |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2016 | INSTRUMENT SUPPORT DETAIL EYE-HYE MINIATURE LEVEL INDICATOR |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2017 | PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2018 | PH CONDUCTIVITY ANALYZER SAMPLING SYTEM PROCESS CONNECTION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2019 | FLOW TRANSMITTER - LIQUID SERVICE 900 AND ABOVE W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2020 | PRESSURE TRANSMITTER - STEAM SVC 1500 W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2021 | LEVEL TRANSMITTER - STEAM LIQ 900 AND ABOVE W ELECT TRACE INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2022 | PRESSURE GAUGE - STEAM SRV 1500 REMOTE MTD W ELECTRIC TRACE TUBING INSTALLATION DETAIL |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I31-2023 | LEVEL GAUGE - STEAM SERVICE DIRECT MTD W ELECTRIC TRACED |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-09-19 | 2020-03-15
[6 empty] | Revised Plan | 2019-12-10 | 2020-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I32 Instrument installation key plan drawing
Category Code: I33 Instrument cable trays and support layout
Category Code: I34 Instrument main cable layout
| IE | OL1-2I34-0002 | Instrument Main Cable Tray Routing Metering |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-09-28 | 2019-10-15 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-09-28 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02407 | TPSK-LSPA1-T-IE-02818
[6 empty] | Return Date | 2019-08-29
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0003 | Instrument Main Cable Routing Main Pipe Rack |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-14 | 2019-10-15 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-14 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02407 | TPSK-LSPA1-T-IE-02818
[6 empty] | Return Date | 2019-08-29
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0004 | Instrument Main Cable Tray Routing Area Substation E And FAR E |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-07 | 2019-10-15 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-07 | 2019-10-15
[6 empty] | Transmittal no. | 2344-TPSK-LSPA1-T-IE-02362 | TPSK-LSPA1-T-IE-02818
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0005 | Instrument Main Cable Tray Routing SUB C And FAR C |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-07 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02363 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0006 | Instrument Main Cable Routing Furnace Utilities |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-09 | 2019-10-15 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-09 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02392 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0007 | Instrument Main Cable Routing Quench |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-09 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02392 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0008 | Instrument Main Cable Tray Routing C3 Hydrogenation |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-08 | 2019-10-15 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-08 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02372 | TPSK-LSPA1-T-IE-02818
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0009 | Instrument Main Cable Routing Hot Fractionation-GHU Unit |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-09 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02392 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0010 | Instrument Main Cable Tray Routing Process Cold Compressors |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-08 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02372 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0011 | Instrument Main Cable Tray Routing Crack Gas Compressor |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-09 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02392 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0012 | Instrument Main Cable Tray Routing Butadiene |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-09 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02384 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0013 | Instrument Main Cable Routing Cooling Water Unit |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-14 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02407 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-29
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0014 | Instr. Main Cable Routing Utilities |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-07 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02363 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0015 | Instrument Main Cable Routing Waste Water Treatment |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-07 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02363 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0016 | Instrument Main Cable Tray Routing Flare Area |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-07 |  | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02363 | TPSK-LSPA1-T-IE-02829
[6 empty] | Return Date | 2019-08-22
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I34-0017 | Instrument Main Cable Tray Routing Overall |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-11 | 2019-07-11 | 2020-04-30
[6 empty] | Revised Plan |  | 2019-11-15 | 2020-04-30
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02848
Return Date
Owner Cmmt*
| IE | OL1-2I34-0018 | Instrument Main Cable Routing Underground |  |  | Purpose** | IFR | IBD | IDD | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-30 | 2019-07-30 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Revised Plan | 2019-08-14 | 2019-11-15 | 2019-12-24 | 2020-10-09 | 2021-01-31
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02407
[6 empty] | Return Date | 2019-08-29
[6 empty] | Owner Cmmt* | A3
Category Code: I35 Instrument, Junction box and instrument air supply station plot plan drawing
| IE | OL1-2I35-0001 | INSTRUMENT LAYOUT COMMON AREA |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0002 | INSTRUMENT LAYOUT METERING |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0003 | INSTRUMENT LAYOUT MAIN PIPE RACK |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0004 | INSTRUMENT LAYOUT AREA SUBSTATION E & FAR E |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0005 | INSTRUMENT LAYOUT AREA SUBSTATION E & FAR C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0006 | INSTRUMENT LAYOUT FURNACES UTILITY |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0007 | INSTRUMENT LAYOUT QUENCH |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0008 | INSTRUMENT LAYOUT PROCESS 20B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0009 | INSTRUMENT LAYOUT PROCESS 20C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0010 | INSTRUMENT LAYOUT PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0011 | INSTRUMENT LAYOUT PROCESS CGC |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0012 | INSTRUMENT LAYOUT BUTADIENE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0013 | INSTRUMENT LAYOUT COOLING WATER UNIT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0014 | INSTRUMENT LAYOUT UTILITIES |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0015 | INSTRUMENT LAYOUT WASTE WATER TREATMENT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0016 | INSTRUMENT LAYOUT FLARE AREA |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0020 | INSTRUMENT AIR DISTRIBUTION LAYOUT COMMON AREA |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0021 | INSTRUMENT AIR DISTRIBUTION LAYOUT METERING |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0022 | INSTRUMENT AIR DISTRIBUTION LAYOUT MAIN PIPE RACK |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0023 | INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION E & FAR E |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0024 | INSTRUMENT AIR DISTRIBUTION LAYOUT AREA SUBSTATION C & FAR C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0025 | INSTRUMENT AIR DISTRIBUTION LAYOUT FURNACES UTILITY |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0026 | INSTRUMENT AIR DISTRIBUTION LAYOUT QUENCH |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0027 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0028 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS 20C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0029 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0030 | INSTRUMENT AIR DISTRIBUTION LAYOUT PROCESS CGC |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0031 | INSTRUMENT AIR DISTRIBUTION LAYOUT BUTADIENE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0032 | INSTRUMENT AIR DISTRIBUTION LAYOUT COOLING WATER UNIT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0033 | INSTRUMENT AIR DISTRIBUTION LAYOUT UTILITIES |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0034 | INSTRUMENT AIR DISTRIBUTION LAYOUT WASTE WATER TREATMENT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I35-0035 | INSTRUMENT AIR DISTRIBUTION LAYOUT FLARE AREA |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-10-09
[6 empty] | Revised Plan | 2020-06-15 | 2020-10-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I36 Local panel plot plan drawing
Category Code: I37 Local panel arrangement drawing
Category Code: I38 Layout of inst wiring (grounding)
Category Code: I39 Instrument air piping and tubing drawing
Category Code: I40 Instrument utilities tubing layout drawing
Category Code: I41 Instrument wiring connection list
Category Code: I42 Junction box Arrangement Drawing
| IE | OL1-2I42-0001 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-E SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-15 | 2020-10-31 | 2021-02-26
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-15 | 2020-10-31 | 2021-02-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0002 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR-C SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-15 | 2020-10-31 | 2021-02-26
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-15 | 2020-10-31 | 2021-02-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0003 | INSTRUMENT AND F&G WIRING DRAWINGS FOR FAR FL SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-15 | 2020-10-31 | 2021-02-26
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-15 | 2020-10-31 | 2021-02-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-0004 | INSTRUMENT AND F&G WIRING DRAWINGS FOR CCB AND OTHER BUILDINGS SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-15 | 2020-10-31 | 2021-02-26
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-15 | 2020-10-31 | 2021-02-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT GRADE TO EL AAFT-AIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100- AT EL AAFT-AIN TO EL BBFT-BIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1100 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL CCFT-CIN TO EL DDFT-DIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL DDFT-DIN TO EL. EEFT-E |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL EEFT-EIN TO EL FF1FT -F |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL FFFT-FIN TO EL GGFT-GIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL HHFT-HIN TO EL IIFT-IIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1100 AT EL IIFT-IIN TO EL JJFT-JIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL JJFT - JIN TO EL KKFT-KIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-1012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1100 AT EL KKFT - KIN TO EL LLFT-LIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT GRADE TO EL AAFT-AIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200- AT EL AAFT-AIN TO EL BBFT-BIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1200 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL CCFT-CIN TO EL DDFT-DIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL DDFT-DIN TO EL. EEFT-E |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL EEFT-EIN TO EL FF1FT -F |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL FFFT-FIN TO EL GGFT-GIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL HHFT-HIN TO EL IIFT-IIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1200 AT EL IIFT-IIN TO EL JJFT-JIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL JJFT - JIN TO EL KKFT-KIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-2012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1200 AT EL KKFT - KIN TO EL LLFT-LIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT GRADE TO EL AAFT-AIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300- AT EL AAFT-AIN TO EL BBFT-BIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1300 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL CCFT-CIN TO EL DDFT-DIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL DDFT-DIN TO EL. EEFT-E |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL EEFT-EIN TO EL FF1FT -F |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL FFFT-FIN TO EL GGFT-GIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL HHFT-HIN TO EL IIFT-IIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1300 AT EL IIFT-IIN TO EL JJFT-JIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL JJFT - JIN TO EL KKFT-KIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-3012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1300 AT EL KKFT - KIN TO EL LLFT-LIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT GRADE TO EL AAFT-AIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400- AT EL AAFT-AIN TO EL BBFT-BIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1400 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL CCFT-CIN TO EL DDFT-DIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL DDFT-DIN TO EL. EEFT-E |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL EEFT-EIN TO EL FF1FT -F |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL FFFT-FIN TO EL GGFT-GIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL HHFT-HIN TO EL IIFT-IIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1400 AT EL IIFT-IIN TO EL JJFT-JIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL JJFT - JIN TO EL KKFT-KIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-4012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1400 AT EL KKFT - KIN TO EL LLFT-LIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT GRADE TO EL AAFT-AIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500- AT EL AAFT-AIN TO EL BBFT-BIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1500 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL CCFT-CIN TO EL DDFT-DIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL DDFT-DIN TO EL. EEFT-E |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL EEFT-EIN TO EL FF1FT -F |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL FFFT-FIN TO EL GGFT-GIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL HHFT-HIN TO EL IIFT-IIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1500 AT EL IIFT-IIN TO EL JJFT-JIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL JJFT - JIN TO EL KKFT-KIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-5012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1500 AT EL KKFT - KIN TO EL LLFT-LIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6001 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT GRADE TO EL AAFT-AIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6002 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600- AT EL AAFT-AIN TO EL BBFT-BIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6003 | INSTRUMENT LOCATION PLAN- CRACKING FURNACE- 10-H-1600 AT EL BBFT-BIN TO EL CC6FT-CIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6004 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL CCFT-CIN TO EL DDFT-DIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6005 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL DDFT-DIN TO EL. EEFT-E |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6006 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL EEFT-EIN TO EL FF1FT -F |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6007 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL FFFT-FIN TO EL GGFT-GIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6008 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL GGFT TO GIN TO EL HHFT -HIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6009 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL HHFT-HIN TO EL IIFT-IIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6010 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE- 10-H-1600 AT EL IIFT-IIN TO EL JJFT-JIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6011 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL JJFT - JIN TO EL KKFT-KIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I42-6012 | INSTRUMENT LOCATION PLAN-CRACKING FURNACE 10-H-1600 AT EL KKFT - KIN TO EL LLFT-LIN |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-03-16 | 2020-06-01
[6 empty] | Revised Plan | 2020-03-16 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I43 Instrument cable list and cable cutting plan
| IE | OL1-2I43-0001 | INSTRUMENT CABLE LIST FOR FAR C SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0002 | INSTRUMENT CABLE LIST FOR FAR E SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0003 | INSTRUMENT CABLE LIST FOR FAR FL SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0004 | INSTRUMENT CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-15 | 2020-08-15 | 2020-11-15 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0011 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR C SYSTEMS |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-09-15 | 2020-12-31
[6 empty] | Revised Plan | 2020-06-15 | 2020-09-15 | 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0012 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR E SYSTEMS |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-09-15 | 2020-12-31
[6 empty] | Revised Plan | 2020-06-15 | 2020-09-15 | 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0013 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FOR FAR FL SYSTEMS |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-09-15 | 2020-12-31
[6 empty] | Revised Plan | 2020-06-15 | 2020-09-15 | 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I43-0014 | INSTRUMENT / TELECOM CABLE DRUM SCHEDULE FORCCB AND OTHER BULDINGS SYSTEMS |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-06-15 | 2020-09-15 | 2020-12-31
[6 empty] | Revised Plan | 2020-06-15 | 2020-09-15 | 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I44 Power Supply Distribution Drawing
| IE | OL1-2I44-1001 | INST.POW.SUP.DISTRIBUTION FOR CCB |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-06-22 | 2020-01-29 | 2020-06-17
[6 empty] | Revised Plan | 2019-11-15 | 2020-01-29 | 2020-06-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1002 | INST.POW.SUP.DISTRIBUTION FOR FAR C |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-06-22 | 2020-01-29 | 2020-06-17
[6 empty] | Revised Plan | 2019-11-15 | 2020-01-29 | 2020-06-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1003 | INST.POW.SUP.DISTRIBUTION FOR FAR E |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-06-22 | 2020-01-29 | 2020-06-17
[6 empty] | Revised Plan | 2019-11-15 | 2020-01-29 | 2020-06-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I44-1004 | INST.POW.SUP.DISTRIBUTION FOR FAR FL |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-06-22 | 2020-01-29 | 2020-06-17
[6 empty] | Revised Plan | 2019-11-15 | 2020-01-29 | 2020-06-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I45 Control Room and Rack Room Drawings
Category Code: I46 Layout of instrument cabinets / panels in Control Room and Rack Room
| IE | OL1-2I46-1001 | Control and Technical Room Equipment Layout - Central Control Building |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-11-30 | 2020-04-30 | 2020-08-31
[6 empty] | Revised Plan | 2019-05-06 | 2019-09-03 | 2020-08-31
[6 empty] | Issue Actual | 2019-05-06 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01568 | TPSK-LSPA1-T-IE-02543
[6 empty] | Return Date | 2019-05-23
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I46-1002 | FAR-C Instrument Equipment Layout |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-04-30 | 2020-08-31
[6 empty] | Revised Plan | 2019-03-27 | 2020-04-30 | 2020-08-31
[6 empty] | Issue Actual | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01153
[6 empty] | Return Date | 2019-04-05
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I46-1003 | FAR-E Instrument Equipment Layout |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-04-30 | 2020-08-31
[6 empty] | Revised Plan | 2019-03-27 | 2020-04-30 | 2020-08-31
[6 empty] | Issue Actual | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01153
[6 empty] | Return Date | 2019-04-05
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I46-1004 | FAR-FL Instrument Equipment Layout |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-30 | 2020-04-30 | 2020-08-31
[6 empty] | Revised Plan | 2019-03-27 | 2020-04-30 | 2020-08-31
[6 empty] | Issue Actual | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01153
[6 empty] | Return Date | 2019-04-05
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I46-1005 | MAINTENANCE BUILDING INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-30 | 2020-04-30 | 2020-08-31
[6 empty] | Revised Plan | 2019-11-30 | 2020-04-30 | 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I46-1006 | EMERGENCY CENTER BUILDING INSTRUMENT EQUIPMENT LAYOUT |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-30 | 2020-04-30 | 2020-08-31
[6 empty] | Revised Plan | 2019-11-30 | 2020-04-30 | 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I47 Layout of instrument main and secondary cable route in Control Room and Rack Room
| IE | OL1-2I47-1001 | FAR E INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1002 | FAR C INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1003 | FAR FL INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1004 | INSTRUMENT CABLE ROUTING CENTRAL CONTROL BUILDING AND OTHER BUILDINGS |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1005 | CCB Instrument-Telecom Cable Entry Details |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-15 | 2020-07-15 | 2020-12-01
[6 empty] | Revised Plan | 2019-09-25 | 2020-07-15 | 2020-12-01
[6 empty] | Issue Actual | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02687
Return Date
Owner Cmmt*
| IE | OL1-2I47-1006 | FAR E INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-15 | 2020-07-15 | 2020-12-01
[6 empty] | Revised Plan | 2020-02-15 | 2020-07-15 | 2020-12-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1007 | FAR C INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-15 | 2020-07-15 | 2020-12-01
[6 empty] | Revised Plan | 2020-02-15 | 2020-07-15 | 2020-12-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1008 | FAR FL INSTRUMENT / TELECOM MULTI CABLE TRANSIT (MCT) LAYOUT |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-15 | 2020-07-15 | 2020-12-01
[6 empty] | Revised Plan | 2020-02-15 | 2020-07-15 | 2020-12-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1050 | SUB E INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I47-1051 | SUB C INSTRUMENT CABLE ROUTING |  |  | Purpose** | IFR | IDD | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-07-31 | 2020-11-15 | 2021-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I48 Layout of instrument grounding wiring in Control Room and Rack Room
| IE | OL1-2I48-1001 | Instrument And Telecom Grounding Philosophy Diagram |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-14 | 2019-03-14 | 2019-04-14
[6 empty] | Revised Plan | 2019-03-11 |  | 2019-10-18
[6 empty] | Issue Actual | 2019-03-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01013
[6 empty] | Return Date | 2019-05-15
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I48-1002 | Instrument / Telecom Earthing Layout - Central Control Building |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-31 | 2020-05-30 | 2020-09-15
[6 empty] | Revised Plan | 2019-08-07 | 2020-05-30 | 2020-09-15
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02367
[6 empty] | Return Date | 2019-08-23
[6 empty] | Owner Cmmt* | A3
| IE | OL1-2I48-1003 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR E AND SUB E |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-05-30 | 2020-09-15
[6 empty] | Revised Plan | 2020-01-31 | 2020-05-30 | 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1004 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR C AND SUB C |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-05-30 | 2020-09-15
[6 empty] | Revised Plan | 2020-01-31 | 2020-05-30 | 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1005 | INSTRUMENT / TELECOM EARTHING LAYOUT FAR FL |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-05-30 | 2020-09-15
[6 empty] | Revised Plan | 2020-01-31 | 2020-05-30 | 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I48-1006 | INSTRUMENT / TELECOM EARTHING LAYOUT OTHER BUILDINGS |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-01-31 | 2020-05-30 | 2020-09-15
[6 empty] | Revised Plan | 2020-01-31 | 2020-05-30 | 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I49 Instrument Hook-up Drawing
| IE | OL1-2I49-4201 | CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  |  | Purpose** | IF1T | IF2T | IF3T | IF4T
Rev.
[6 empty] | Issue Plan | 2020-05-30 | 2020-08-30 | 2020-11-30 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-30 | 2020-08-30 | 2020-11-30 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4203 | SECONDARY CABLE TRAY & ACCESSORIES MAT.TAKE-OFF |  |  | Purpose** | IF1T | IF2T | IF3T | IF4T
Rev.
[6 empty] | Issue Plan | 2020-05-30 | 2020-08-30 | 2020-11-30 | 2021-01-31
[6 empty] | Revised Plan | 2020-05-30 | 2020-08-30 | 2020-11-30 | 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4301 | JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES MATERIAL TAKE-OFF |  |  | Purpose** | IF1T | IF2T | IF3T | IF4T
Rev.
[6 empty] | Issue Plan | 2020-02-24 | 2020-06-01 | 2020-08-15 | 2020-10-15
[6 empty] | Revised Plan | 2020-02-24 | 2020-06-01 | 2020-08-15 | 2020-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4303 | CABLE GLANDS MAT.TAKE-OFF |  |  | Purpose** | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-10-01
[6 empty] | Revised Plan | 2020-05-15 | 2020-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I49-4304 | MAIN CABLE TRANSIT (MCT) & ACCESSORIES MATERIAL TAKE OFF |  |  | Purpose** | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-10-01
[6 empty] | Revised Plan | 2020-05-15 | 2020-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I50 Hook-up drawing for process lead piping for each instrument
| IE | OL1-2I50-0001 | INSTRUMENT HOOK-UP DRAWINGS ISBL UNITS |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-31 | 2020-05-25 | 2020-09-29
[6 empty] | Revised Plan | 2019-12-31 | 2020-05-25 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I51 Hook-up drawing for IA and pneumatic
| IE | OL1-2I51-0001 | Instrument Typical Hook-up |  |  | Purpose** | IFR | IDD | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-31 | 2020-05-25 | 2020-09-29
[6 empty] | Revised Plan | 2019-04-05 | 2020-05-25 | 2020-09-29
[6 empty] | Issue Actual | 2019-04-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-1254
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | A3
Category Code: I52 Hook-up drawing for Steam tracing
| IE | OL1-2I52-0001 | INSTRUMENT HOOK-UP DRAWINGS OSBL UNITS |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-31 | 2020-05-25 | 2020-09-29
[6 empty] | Revised Plan | 2019-12-31 | 2020-05-25 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I53 Instrument loop drawing diagram
| IE | OL1-2I53-0001 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - FURNACES UTILITY |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0002 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - QUENCH |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0003 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0004 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS 20C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0005 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS COLD COMPRESSORS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0006 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - PROCESS CGC |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0007 | INSTRUMENT LOOP DRAWINGS FAR-E- METERING |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0008 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION E & FAR E |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0009 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - SUBSTATION C & FAR C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0010 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - BUTADIENE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0011 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - COOLING WATER UNIT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0012 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - UTILITIES |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0013 | INSTRUMENT LOOP DRAWINGS FAR-E DCS, ESD, FGS - WASTE WATER TREATMENT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I53-0014 | INSTRUMENT LOOP DRAWINGS FAR-FL DCS, ESD, FGS - FLARE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2021-02-15 | 2021-04-06
[6 empty] | Revised Plan | 2021-02-15 | 2021-04-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I54 Bill of bulk materials take-off
| IE | OL1-2I54-1001 | Furnace - Instrument_Telecom and Fibre Optic Cables Material Take-Off |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02766
Return Date
Owner Cmmt*
| IE | OL1-2I54-2001 | INSTRUMENT MTO 10-H-1200 |  |  | Purpose** | IFI
Rev.
[6 empty] | Issue Plan | 2019-10-22
[6 empty] | Revised Plan | 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-3001 | INSTRUMENT MTO 10-H-1300 |  |  | Purpose** | IFI
Rev.
[6 empty] | Issue Plan | 2019-10-22
[6 empty] | Revised Plan | 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-4001 | INSTRUMENT MTO 10-H-1400 |  |  | Purpose** | IFI
Rev.
[6 empty] | Issue Plan | 2019-10-22
[6 empty] | Revised Plan | 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-4101 | Instrument & Fibre Optic Cables Material Take-Off |  |  | Purpose** | IF1T | IF2T | IF3T | IF4T
Rev.
[6 empty] | Issue Plan | 2019-10-15 | 2020-02-15 | 2020-06-15 | 2020-11-18
[6 empty] | Revised Plan |  | 2020-02-15 | 2020-06-15 | 2020-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-5001 | INSTRUMENT MTO 10-H-1500 |  |  | Purpose** | IFI
Rev.
[6 empty] | Issue Plan | 2019-10-22
[6 empty] | Revised Plan | 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I54-6001 | INSTRUMENT MTO 10-H-1600 |  |  | Purpose** | IFI
Rev.
[6 empty] | Issue Plan | 2019-10-22
[6 empty] | Revised Plan | 2019-10-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I55 In-line & On equipment
| IE | OL1-2I55-0202 | MR MAGNETIC LEVEL GAUGE |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0203 | MR RADAR LEVEL INSTRUMENTS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0211 | MR SPECIAL LEVEL TRANSMITTERS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0212 | MR LEVEL GLASS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0213 | MR LEVEL GLASS FOR STEAM DRUM |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0302 | MR THERMOCOUPLE/RTD WITH WELL |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-07-03
[6 empty] | Revised Plan | 2020-02-05 | 2020-07-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0304 | MR THERMOMETER WITH WELL |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-07-03
[6 empty] | Revised Plan | 2020-02-05 | 2020-07-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0305 | MR MULTIPLE THERMOCOUPLE / RTD |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-07-03
[6 empty] | Revised Plan | 2020-02-05 | 2020-07-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0402 | MR PRESSURE & DIFFER.PRESS.GAUGE |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-08-05
[6 empty] | Revised Plan | 2020-02-05 | 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0505 | MR ANTISURGE VALVES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13
[6 empty] | Revised Plan | 2019-10-18 | 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0506 | MR DESUPERHEATER VALVES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13
[6 empty] | Revised Plan | 2019-10-18 | 2019-11-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0801 | MR ELECTRONIC TRANSMITTER |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-08-05
[6 empty] | Revised Plan | 2020-02-05 | 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-2601 | MR FIRE AND GAS DEVICES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-20
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4101 | MR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-11-04 | 2020-11-15
[6 empty] | Revised Plan | 2019-11-04 | 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4201 | MR CABLE TRAY AND ACCESSORIES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-04-11 | 2020-11-15
[6 empty] | Revised Plan | 2020-04-11 | 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4301 | MR FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-12-15
[6 empty] | Revised Plan | 2020-06-01 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4302 | MR CABLE GLANDS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-12-15
[6 empty] | Revised Plan | 2020-06-01 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4501 | MR MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-04-11 | 2020-11-15
[6 empty] | Revised Plan | 2020-04-11 | 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4502 | MR SUNSHADES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-12-15
[6 empty] | Revised Plan | 2020-06-01 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4503 | MOUNTING ACCESSORIES (TUBING & FITTINGS) MATERIALTAKE-OFF |  |  | Purpose** | IF1T | IF2T | IF3T | IF4T
Rev.
[6 empty] | Issue Plan | 2020-03-30 | 2020-06-15 | 2020-09-15 | 2020-11-15
[6 empty] | Revised Plan | 2020-03-30 | 2020-06-15 | 2020-09-15 | 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4505 | MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) TAKE-OFF |  |  | Purpose** | IF1T | IF2T | IF3T | IF4T
Rev.
[6 empty] | Issue Plan | 2020-03-30 | 2020-06-15 | 2020-09-15 | 2020-11-15
[6 empty] | Revised Plan | 2020-03-30 | 2020-06-15 | 2020-09-15 | 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4507 | STEAM & ELECTRICALTRACING MAT.TAKE-OFF |  |  | Purpose** | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-02-28 | 2020-06-01
[6 empty] | Revised Plan | 2020-02-28 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4510 | MR MAIN CABLE TRANSIT (MCT) & ACCESSORIES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-12-15
[6 empty] | Revised Plan | 2020-06-01 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4511 | MR FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-04-11 | 2020-11-15
[6 empty] | Revised Plan | 2020-04-11 | 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-4511-ATT1 | PARTICULAR TECNICAL SPECIFICATION FOR MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-03-11 | 2020-10-15
[6 empty] | Revised Plan | 2020-03-11 | 2020-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I61 SIL Study Document
| IE | OL1-2I61-1101 | SIS IMPLEMENTATION CALCULATION NOTES |  |  | Purpose** | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2020-03-05
[6 empty] | Revised Plan | 2019-11-15 | 2020-03-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I61-1102 | General Design Rules For SIS Safety Requirements Specification |  |  | Purpose** | IFR | IMP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-07-30 | 2020-03-05
[6 empty] | Revised Plan | 2019-01-25 | 2019-04-18
[6 empty] | Issue Actual | 2019-01-25 | 2019-04-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00719 | TPSK-LSPA1-T-IE-01392
[6 empty] | Return Date | 2019-03-05 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2I61-1103 | PARTICULAR SIS SAFETY REQUIREMENTS SPECIFICATION |  |  | Purpose** | IFR | IMP
Rev.
[6 empty] | Issue Plan | 2019-07-30 | 2020-03-05
[6 empty] | Revised Plan | 2019-12-13 | 2020-03-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I62 FAT Punch Lists
Category Code: I63 SAT Punch Lists
Category Code: I64 Operation and maintenance spare part for 2 years list
Category Code: I65 Initial Spare part list
Category Code: I66 Special tools book
Category Code: I70 Instruction Manual of Instrument
| IE | OL1-2I70-0002 | Design Instruction For Typical Loops For SPI Database |  | Class 3 | Purpose** | IFI
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-28
[6 empty] | Issue Actual | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02714
Return Date
Owner Cmmt*
Category Code: I71 Control narative for complex loop
| IE | OL1-2I71-0001 | TECHNICAL SPECIFICATION FOR ADVANCED REGULATORY CONTROL LOOPS (ADDED 15-APR-2019) |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-11-29 | 2020-03-27
[6 empty] | Revised Plan | 2019-11-29 | 2020-03-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I71-1001 | Complex Loop Narratives Area 10 - Feed Preparation and Feed Preheat |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-03-22
[6 empty] | Issue Actual |  | 2019-03-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01128
[6 empty] | Return Date |  | 2019-04-02
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-1101 | Complex Control Narratives_36M Furnace H-1100 |  | Class 2 | Purpose** | IFD | IFR
[6 empty] | Rev. | B | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21 | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01700 | TPSK-LSPA1-T-IE-01696
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I71-1201 | Complex Control Narratives_132U Furnaces H-1200 - H1600 |  |  | Purpose** | IFR | IFD | IBD | IFD | IFC
[6 empty] | Rev. | A | B |  | B
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-19 | 2019-03-19 | 2019-03-19 | 2019-10-28
[6 empty] | Revised Plan | 2019-04-10 | 2019-05-20 |  | 2019-05-20 | 2019-10-28
[6 empty] | Issue Actual | 2019-04-10 | 2019-05-20 |  | 2019-05-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01289 | TPSK-LSPA1-T-IE-01700 |  | TPSK-LSPA1-T-IE-01700
[6 empty] | Return Date | 2019-06-13 | 2019-06-13 |  | 2019-06-13
[6 empty] | Owner Cmmt* | R2 | R2 |  | R2
| IE | OL1-2I71-2001 | Complex Loop Narratives - Area 20 - Quench Oil |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-03-22
[6 empty] | Issue Actual |  | 2019-03-22
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01132
[6 empty] | Return Date |  | 2019-04-02
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-2101 | Complex Loop Narratives Area 21 - Quench Water - Dilution Steam |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-03-26
[6 empty] | Issue Actual |  | 2019-03-26
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01147
[6 empty] | Return Date |  | 2019-05-24
[6 empty] | Owner Cmmt* |  | R1
| IE | OL1-2I71-2201 | Complex Loop Narratives Area 22 - Cracked Gas Compressor |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-05-02
[6 empty] | Issue Actual |  | 2019-05-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01544
[6 empty] | Return Date |  | 2019-06-03
[6 empty] | Owner Cmmt* |  | R1
| IE | OL1-2I71-2301 | Complex Loop Narratives Area 23 - Caustic and Spent Caustic Treatment |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-04-16
[6 empty] | Issue Actual |  | 2019-04-16
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01358
[6 empty] | Return Date |  | 2019-06-03
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-2401 | Complex Loop Narratives Area 24 - Dehydration - Regen - Deprop - C2 Hydrog |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-05-08
[6 empty] | Issue Actual |  | 2019-05-08
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01605
[6 empty] | Return Date |  | 2019-06-19
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-2501 | Complex Loop Narratives Area 25 Cold Fractionation |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-04-16
[6 empty] | Issue Actual |  | 2019-04-16
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01358
[6 empty] | Return Date |  | 2019-06-03
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-2601 | Complex Loop Narratives Area 26 - Hot Fractionation |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-05-15
[6 empty] | Issue Actual |  | 2019-05-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01662
[6 empty] | Return Date |  | 2019-06-19
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-2701 | Complex Loop Narratives Area 27 GHU & C4-C5 HYDROG |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-05-15
[6 empty] | Issue Actual |  | 2019-05-15
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01662
[6 empty] | Return Date |  | 2019-06-19
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-2801 | Complex Loop Narratives - Area 28 - Refrigeration System |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-05-31
[6 empty] | Issue Actual |  | 2019-05-31
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01778
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-2901 | Complex Loop Narratives Area 29 Ethylene Auxiliaries |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-06-10
[6 empty] | Issue Actual |  | 2019-06-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01791
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-3001 | Complex Loop Narratives Area 30 - Butadiene Extraction Unit BDU |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-06-18
[6 empty] | Issue Actual |  | 2019-06-18
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01906
[6 empty] | Return Date |  | 2019-07-09
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-5101 | Complex Loop Narratives Area 51 BFW - Steam - Steam Condensate System |  | Class 2 | Purpose** | IFR | IBD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-09 | 2019-08-07
[6 empty] | Issue Actual | 2019-05-09 | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01614 | TPSK-LSPA1-T-IE-02344
[6 empty] | Return Date | 2019-06-19 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2I71-5201 | Complex Loop Narratives Area 52 - Fuel System |  | Class 2 | Purpose** | IFR | IBD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-05-10 | 2019-08-07
[6 empty] | Issue Actual | 2019-05-10 | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01632 | TPSK-LSPA1-T-IE-02344
[6 empty] | Return Date | 2019-06-19 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2I71-5301 | Complex Loop Narratives - Area 53 - Cooling Water System |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-03-13
[6 empty] | Issue Actual |  | 2019-03-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01037
Return Date
Owner Cmmt*
| IE | OL1-2I71-5501 | Complex Loop Narratives Area 55 Vent Gas and Flare System |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-05-03
[6 empty] | Issue Actual |  | 2019-05-03
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01564
[6 empty] | Return Date |  | 2019-06-03
[6 empty] | Owner Cmmt* |  | R2
| IE | OL1-2I71-5601 | Complex Loop Narratives Area 56 Wastewater |  |  | Purpose** | IFI | IFR
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-07-19
[6 empty] | Revised Plan |  | 2019-05-02
[6 empty] | Issue Actual |  | 2019-05-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-IE-01544
[6 empty] | Return Date |  | 2019-06-03
[6 empty] | Owner Cmmt* |  | R1
| IE | OL1-2I71-5901 | Complex Loop Narratives - Area 59 - Supporting Utilities Auxiliaries |  | Class 2 | Purpose** | IFR | IBD
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-26 | 2019-07-03
[6 empty] | Issue Actual | 2019-03-26 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01140 | TPSK-LSPA1-T-IE-02052
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
Category Code: I76 Appraisal Report for Consultancy Service
Category Code: I77 Appraisal Report for EPC Contractor Work
Category Code: I78 Appraisal Report for Vendor/Supplier
Category Code: I81 DCS System Document
| IE | OL1-2I81-1001 | Control And Safety Systems Connection Diagram |  |  | Purpose** | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-24 | 2019-05-21 | 2019-10-04 | 2019-10-04
[6 empty] | Revised Plan | 2019-03-11 | 2019-06-14 | 2019-11-15 | 2019-11-15
[6 empty] | Issue Actual | 2019-03-11 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01012 | TPSK-LSPA1-T-IE-01889
[6 empty] | Return Date | 2019-05-15 | 2019-07-01
[6 empty] | Owner Cmmt* | A3 | A3
| IE | OL1-2I81-1002 | Control And Safety Systems Architecture |  |  | Purpose** | IFR | IFR | IBD | IDD | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-01-24 |  | 2019-05-21 | 2019-10-04 | 2019-10-04
[6 empty] | Revised Plan | 2019-02-25 |  | 2019-10-16 | 2019-11-15 | 2019-11-15
[6 empty] | Issue Actual | 2019-02-25 | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-00912 | TPSK-LSPA1-T-IE-01551
[6 empty] | Return Date | 2019-03-08 | 2019-05-18
[6 empty] | Owner Cmmt* | A3 | R2
| IE | OL1-2I81-1004 | GRAPHIC DISLAYS |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-11-29 | 2020-03-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-11-29 | 2020-03-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I81-1005 | OPERATOR TREND DISPLAY DEFINITION |  |  | Purpose** | IFR | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-11-29 | 2020-03-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-11-29 | 2020-03-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I82 ESD system Document
Category Code: I83 FGS system Document
Category Code: I84 Analyzer system Document
| IE | OL1-2I84-2001 | ANALYZER SYST.BLOCK DIAGRAM |  |  | Purpose** | IFR | IBD | IDD
Rev.
[6 empty] | Issue Plan | 2020-03-18 | 2020-05-18 | 2020-11-07
[6 empty] | Revised Plan | 2020-03-18 | 2020-05-18 | 2020-11-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2002 | ANALYZER SHELTER LAYOUT |  |  | Purpose** | IBD
Rev.
[6 empty] | Issue Plan | 2019-03-04
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2003 | ANALYZER SAMPLE LOOP ARRANGEMENT |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-04-17 | 2020-06-17 | 2020-12-07
[6 empty] | Revised Plan | 2020-04-17 | 2020-06-17 | 2020-12-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I84-2004 | AMADAS ARCHITECTURE |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-31
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02283
[6 empty] | Return Date | 2019-08-16
[6 empty] | Owner Cmmt* | A3
Category Code: I85 Custody meter Document
Category Code: I86 Tank gauging Document
Category Code: I87 Pelletizing system Document
Category Code: I90 Vendor documents of Instrument
Category Code: I91 Index/List
| IE | OL1-2I91-0001 | Instrument List |  |  | Purpose** | IFI
Rev.
[6 empty] | Issue Plan | 2019-04-29
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0002 | Preliminary Alarm Summary and Setpoint List - Balance of Plant |  | Class 1 | Purpose** | IBD
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02132
[6 empty] | Return Date | 2019-08-12
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2I91-0004 | INSTRUMENT LIST - FURNACES UTILITY |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0005 | INSTRUMENT LIST - QUENCH |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0006 | INSTRUMENT LIST - PROCESS 20B |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0007 | INSTRUMENT LIST - PROCESS 20C |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0008 | INSTRUMENT LIST - PROCESS COLD COMPRESSORS |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0009 | INSTRUMENT LIST - PROCESS CGC |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0010 | INSTRUMENT LIST - BUTADIENE |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0011 | INSTRUMENT LIST - COOLING WATER UNIT |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0012 | INSTRUMENT LIST - UTILITIES |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0013 | INSTRUMENT LIST - WASTE WATER TREATMENT |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0014 | INSTRUMENT LIST - FLARE |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0020 | INSTRUMENT CLASSES |  |  | Purpose** | IFR | IMP
Rev.
[6 empty] | Issue Plan | 2020-05-19 | 2020-06-30
[6 empty] | Revised Plan | 2020-05-19 | 2020-06-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0100 | INSTRUMENT CONTROL SYSTEMS EQUIPMENT LIST |  |  | Purpose** | IFR | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-04-30 | 2020-08-30 | 2020-12-31
[6 empty] | Revised Plan | 2020-04-30 | 2020-08-30 | 2020-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0102 | ICSS DATA BASE |  |  | Purpose** | IBD | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-28 | 2020-01-29 | 2020-06-01
[6 empty] | Revised Plan | 2019-10-18 | 2020-01-29 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0103 | INSTRUMENT RANGE, ALARM & TRIP LIST |  |  | Purpose** | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-30 | 2020-07-15
[6 empty] | Revised Plan | 2020-05-30 | 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-0104 | INSTRUMENT LIST - METERING |  |  | Purpose** | IDD2 | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
[6 empty] | Revised Plan | 2020-02-26 | 2020-05-15 | 2020-07-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1001 | IN/OUT SUMMARY |  |  | Purpose** | IBD | IDD | IFF
Rev.
[6 empty] | Issue Plan | 2019-05-28 | 2020-01-29 | 2020-06-01
[6 empty] | Revised Plan | 2019-10-18 | 2020-01-29 | 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1002 | INSTRUMENT INDEX |  |  | Purpose** | IFR | IBD | IFD | IFC
Rev.
[6 empty] | Issue Plan | 2019-04-04 | 2019-06-13 | 2019-06-24 | 2019-10-28
[6 empty] | Revised Plan |  |  |  | 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1003 | FURNACE ANALYZER LIST |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-06-10 | 2019-07-01
[6 empty] | Revised Plan |  | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1004 | CONTROLLER AND SPLIT-RANGE LIST OSBL |  |  | Purpose** | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-30 | 2020-07-15
[6 empty] | Revised Plan | 2020-05-30 | 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-1005 | CONTROLLER AND SPLIT-RANGE LIST ISBL |  |  | Purpose** | IDD | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-30 | 2020-07-15
[6 empty] | Revised Plan | 2020-05-30 | 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2000 | ANALYZER LIST |  |  | Purpose** | IBD | IDD
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2020-02-02
[6 empty] | Revised Plan | 2019-10-18 | 2020-02-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2002 | INSTRUMENT INDEX |  |  | Purpose** | IFR | IBD | IFD | IFC
Rev.
[6 empty] | Issue Plan | 2019-04-04 | 2019-06-13 | 2019-06-24 | 2019-10-28
[6 empty] | Revised Plan |  |  |  | 2019-10-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-2003 | FURNACE ANALYZER LIST - FURNACES 10-H-1200 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-07-01
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-3003 | FURNACE ANALYZER LIST - FURNACES 10-H-1300 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-07-01
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-4003 | FURNACE ANALYZER LIST - FURNACES 10-H-1400 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-07-01
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-5003 | FURNACE ANALYZER LIST - FURNACES 10-H-1500 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-07-01
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I91-6003 | FURNACE ANALYZER LIST - FURNACES 10-H-1600 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-07-01
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I92 Procedures & Standards
| IE | OL1-2I92-0050 | Job Supply Specification For Analyzer Systems and Analyzer Houses |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01332
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2I92-0051 | JSS MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-01 | 2020-01-31
[6 empty] | Revised Plan | 2020-01-01 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0052 | JSS CABLE TRAY AND ACCESSORIES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-01 | 2020-01-31
[6 empty] | Revised Plan | 2020-01-01 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0053 | JSS FOR INSTRUMENT / TELECOM AND FIBRE OPTIC CABLES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-15
[6 empty] | Revised Plan | 2019-10-31 | 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0054 | JSS FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-01 | 2020-01-31
[6 empty] | Revised Plan | 2020-01-01 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0055 | JSS FOR CABLE GLANDS AND ACCESSORIES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-01 | 2020-01-31
[6 empty] | Revised Plan | 2020-01-01 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0056 | JSS FOR SUNSHADES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-01 | 2020-01-31
[6 empty] | Revised Plan | 2020-01-01 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0057 | JSS for Cross Check Custody Metering System |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-08
[6 empty] | Revised Plan | 2019-10-09 | 2019-12-23
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02738
Return Date
Owner Cmmt*
| IE | OL1-2I92-0058 | JSS FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-01 | 2020-01-31
[6 empty] | Revised Plan | 2020-01-01 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0059 | JSS FOR MAIN CABLE TRANSIT & ACCESSORIES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-01 | 2020-01-31
[6 empty] | Revised Plan | 2020-01-01 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0060 | JSS FOR FIRE AND GAS DEVICES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-17 | 2020-01-16
[6 empty] | Revised Plan | 2019-12-17 | 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0100 | Job Supply Specification For Flow Meters And Flow Elements |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-15 | 2019-05-15
[6 empty] | Revised Plan | 2019-06-27 | 2019-11-13
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-02016
[6 empty] | Return Date | 2019-07-09
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2I92-0101 | JSS DIFFERENTIAL PRESSURE FLOW ELEMENTS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-17 | 2020-01-16
[6 empty] | Revised Plan | 2019-12-17 | 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0200 | JSS LEVEL INSTRUMENTS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-17 | 2020-01-16
[6 empty] | Revised Plan | 2019-12-17 | 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0201 | JSS FOR SURGE PROTECTION DEVICES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2020-01-01 | 2020-01-31
[6 empty] | Revised Plan | 2020-01-01 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0300 | JSS TEMPERATURE INSTRUMENTS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-17 | 2020-01-16
[6 empty] | Revised Plan | 2019-12-17 | 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0301 | JSS FOR PRESSURE & DIFF.PRESSURE INSTRUMENTS |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-17 | 2020-01-16
[6 empty] | Revised Plan | 2019-12-17 | 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0404 | JSS ANTISURGE VALVES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-08
[6 empty] | Revised Plan | 2019-10-18 | 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0405 | JSS DESUPERHEATERS VALVES |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-08
[6 empty] | Revised Plan | 2019-10-18 | 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0501 | Job Supply Specification For Control Valves |  |  | Purpose** | IFR | IFF
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-08
[6 empty] | Revised Plan | 2019-05-31 | 2019-12-02
[6 empty] | Issue Actual | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-01770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A1
| IE | OL1-2I92-0602 | Job Supply Specification For Electric Operated Valves |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-08
[6 empty] | Revised Plan |  | 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0604 | Job Supply Specification For Pneumatic Actuators For On Off Valves |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-08
[6 empty] | Revised Plan |  | 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0606 | Job Supply Specification For Pneumatic On Off Valves |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-04-08 | 2019-05-08
[6 empty] | Revised Plan |  | 2019-12-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0701 | Job Supply Specification For Safety Relief Valves & Rupture Disks |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-04-11 | 2019-05-11
[6 empty] | Revised Plan |  | 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I92-0801 | JSS ELECTRONIC TRANSMITER |  |  | Purpose** | IFR | IFF
Rev.
[6 empty] | Issue Plan | 2019-12-17 | 2020-01-16
[6 empty] | Revised Plan | 2019-12-17 | 2020-01-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I93 Policy , Guidelines & Memo
Category Code: I94 SPARE NUMBER
Category Code: I94 Forms & Templates
Category Code: I95 SPARE NUMBER
Category Code: I95 Progress/Status Reports
Category Code: I96 SPARE NUMBER
Category Code: I97 SPARE NUMBER
Category Code: I98 SPARE NUMBER
Category Code: I99 SPARE NUMBER
Category Code: J71 Appraisal Report for Consultancy Service
Category Code: J72 Appraisal Report for EPC Contractor Work
Category Code: J73 Appraisal Report for Vendor/Supplier
Category Code: J91 Index/List
Category Code: J92 Procedures & Standards
| HR | OL1-2J92-0002 | Employee Grievance Management Plan |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-12
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
Owner Cmmt*
| HR | OL1-2J92-0003 | Local Recruitment And Procurement Plan |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-02745
Return Date
Owner Cmmt*
| HR | OL1-2J92-0004 | Local Infrastructure Improvement Program |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-02745
Return Date
Owner Cmmt*
| HR | OL1-2J92-0005 | Community Healt Action Plan |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-02745
Return Date
Owner Cmmt*
| HR | OL1-2J92-0006 | Community Grievance Management Plan |  | Class 2 | Purpose** | 0
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-02745
Return Date
Owner Cmmt*
| HR | OL1-2J92-0007 | Project Induced In-Migration Management Plan |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-02745
Return Date
Owner Cmmt*
| HR | OL1-2J92-0008 | Cultural Heritage Chance Finds Procedure |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-02779
Return Date
Owner Cmmt*
Category Code: J93 Policy , Guidelines & Memo
| HR | OL1-2J93-0004 | Human Resource Policy And Procedures |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-12
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
Owner Cmmt*
| HR | OL1-2J93-0005 | Code Of Conduct |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-02747
Return Date
Owner Cmmt*
Category Code: J94 Forms & Templates
| HR | OL1-2J94-0002 | Worker Code Of Conduct Declaration Form |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-12
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
Owner Cmmt*
| HR | OL1-2J94-0003 | HR Department Labor Contract |  | Class 2 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-02746
Return Date
Owner Cmmt*
| HR | OL1-2J94-0004 | Child Labor Risk Assessment Checklist |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-12
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
Owner Cmmt*
| HR | OL1-2J94-0005 | Forced Labor Risk Assessment Checklist |  | Class 2 | Purpose** | IFI
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2018-09-12
[6 empty] | Issue Actual | 2018-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-HR-00040
Return Date
Owner Cmmt*
Category Code: J95 Progress/Status Reports
Category Code: K01 Design Basis Reports
Category Code: K02 Design Verification Reports
Category Code: K03 Master Plan Document
Category Code: K04 Cadastal Map
Category Code: K08 Material Take Off UG
Category Code: K11 Design calculation for pile (including pile driven design) | [5 empty] | Purpose**
| CV | OL1-2K11-0001 | Calculation Note For Piles |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-28 | 2019-04-01
[6 empty] | Revised Plan | 2019-03-20 | 2019-11-15
[6 empty] | Issue Actual | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
Category Code: K12 Design calculation for paving
| CV | OL1-2K12-0001 | CALCULATION NOTES FOR ROAD AND PAVING THICKNESS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-05-30 | 2020-09-29
[6 empty] | Revised Plan | 2019-10-31 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K13 Design calculation for foundations
| CV | OL1-2K13-0001 | Calculation Note For Foundation Of 10-H-1100 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02150
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0002 | Calculation Note For Foundation Of 10-H-1200-1600 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02150
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0004 | Calculation Note For Foundation Of 10-D-5200 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0005 | Calculation Note For Foundation Of 10-E-5200 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00943
[6 empty] | Return Date | 2019-03-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0006 | Calculation Note For Foundation Of 10-E-5210 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0010 | Calculation Note For Foundation Of 10-D-5150 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0011 | Calculation Note For Foundation of 10-D-2160 |  | Class 1 | Purpose** | IFR | CAN
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-01-28 | 2019-10-15
[6 empty] | Issue Actual | 2019-01-28 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00732 | TPSK-LSPA1-T-CV-02814
[6 empty] | Return Date | 2019-03-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0013 | Calculation Note For Foundation Of 10-D-2136 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-09-10 | 2020-06-15
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02583
Return Date
Owner Cmmt*
| CV | OL1-2K13-0016 | Calculation Note For Foundation Of 10-E-2136 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-07 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00992
[6 empty] | Return Date | 2019-03-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0018 | Calculation Note For Foundation Of 10-E-2166 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-08 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | 2019-03-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0020 | Calculation Note For Foundation Of 10-E-2146 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0021 | Calculation Note For Foundation Of 10-E-2026 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0022 | Calculation Note for Foundation of 10-E-2048 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-07 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00816
[6 empty] | Return Date | 2019-03-18
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0023 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5102A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0024 | CALCULATION NOTE FOR FOUNDATION PUMPS 10-P-2026A/B, 10-P-2126A/B, 10-P-2046A/B, 10-P-5140A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0025 | Calculation Note For Foundation Of 10-P-2006 A-B-C |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02806
Return Date
Owner Cmmt*
| CV | OL1-2K13-0026 | Calculation Note For Foundation Of 10-F-2105-A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-29 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02521
Return Date
Owner Cmmt*
| CV | OL1-2K13-0027 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2009A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0028 | Calculation Note For Foundation Of 10-F-2008-A-B-C |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-29 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02518
Return Date
Owner Cmmt*
| CV | OL1-2K13-0029 | Calculation Note For Foundation Of 10-F-2026-A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-30 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02533
Return Date
Owner Cmmt*
| CV | OL1-2K13-0030 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2028A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0031 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2136A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0033 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0036 | Calculation Note For Foundation Of 10-T-2300 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-11 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01857
[6 empty] | Return Date | 2019-08-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0037 | Calculation Note For Foundation Of 10-T-2330 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0038 | Calculation Note For Foundation Of 10-D-2410 A/B/C |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0039 | Calculation Note For Foundation Of 10-D-2435 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0041 | Calculation Note For Foundation Of 10-D-2240 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0042 | Calculation Note For Foundation Of 10-D-2245 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0043 | Calculation Note For Foundation Of 10-D-2445 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0044 | Calculation Note for Foundation of 10-D-2455 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-11 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00832
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0045 | Calculation Note For Foundation Of 10-D-2220 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0046 | Calculation Note For Foundation Of 10-D-2210 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0047 | Calculation Note For Foundation Of 10-D-2230 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0048 | Calculation Note For Foundation Of 10-D-2405 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0049 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2415 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0050 | Calculation Note for Foundation of 10-D-2310 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-08 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00827
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0052 | Calculation Note for Foundation of 10-D-2316 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-01 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00783
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0054 | Calculation Note for Foundation of 10-D-2330 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-01 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00783
[6 empty] | Return Date | 2019-02-25
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0055 | Calculation Note For Foundation Of 10-D-2411 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0056 | Calculation Note For Foundation Of 10-TK-2910 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-24 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02238
Return Date
Owner Cmmt*
| CV | OL1-2K13-0058 | Calculation Note For Foundation of 10-E-2230A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-18
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0059 | Calculation Note For Foundation Of 10-E-2412 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01333
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0060 | Calculation Note for Foundation of 10-E-2413 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-18 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01903
[6 empty] | Return Date | 2019-08-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0061 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2432 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0063 | Calculation Note For Foundation Of 10-E-2446 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0065 | Calculation Note For Foundation of 10-E-2450 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0066 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2470 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0067 | Calculation Note For Foundation Of 10-E-2206 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0068 | Calculation Note For Foundation Of 10-E-2210AB |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0069 | Calculation Note For Foundation Of 10-E-2220AB |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0070 | Calculation Note For Foundation of 10-E-2240A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0071 | Calculation Note for Foundation of 10-D-2305 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-08 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00827
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0072 | Calculation Note for Foundation of 10-E-2630 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-08 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | 2019-03-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0073 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2326 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0074 | Calculation Note For Foundation Of 10-F-2320A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02410
Return Date
Owner Cmmt*
| CV | OL1-2K13-0075 | Calculation Note For Foundation Of 10-F-2310A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02410
Return Date
Owner Cmmt*
| CV | OL1-2K13-0076 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2306A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0077 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0078 | CALCULATION NOTE FOR FOUNDATION OF ANALYZER HOUSE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0079 | CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-5112A/B, 10-P-2714A/B, 10-P-2710A/B, 10-P-2720A/B, 10-P-2721A/B, 10-P-2910 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0080 | CALCULATION NOTE FOR FOUNDATION FOR PUMPS 10-P-2724A/B, 10-P-2726A/B, 10-P-2750A/B, 10-P-2760A/B/C, 10-P-2705A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0081 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5100A/B/C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0082 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2900/2902/2906 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0083 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2920 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0084 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1920 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0085 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2350 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0087 | Calculation Note For Foundation Of 10-F-2048-A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-29 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02518
Return Date
Owner Cmmt*
| CV | OL1-2K13-0088 | Calculation Note For Foundation Of 10-T-2580 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0089 | Calculation Note For Foundation Of 10-T-2640 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-18 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01071
Return Date
Owner Cmmt*
| CV | OL1-2K13-0090 | Calculation Note For Foundation Of 10-T-2570 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0091 | Calculation Note For Foundation Of 10-T-2540 And 10-T-2510 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0093 | Calculation Note For Foundation Of 10-T-2520/10-D-2520 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-01-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-01-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00679
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0094 | Calculation Note For Foundation Of 10-D-2480A |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0096 | Calculation Note For Foundation Of 10-D-2420A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0097 | Calculation Note For Foundation Of 10-E-1006 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01749
[6 empty] | Return Date | 2019-06-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0098 | Calculation Note For Foundation Of 10-D-2815 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-01-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-01-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00732
[6 empty] | Return Date | 2019-03-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0099 | Calculation Note for Foundation of 10-D-2525 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-18 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01903
[6 empty] | Return Date | 2019-08-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0100 | Calculation Note For Foundation Of 10-PIT-5606 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-07-24 | 2020-01-31
[6 empty] | Issue Actual | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02238
Return Date
Owner Cmmt*
| CV | OL1-2K13-0101 | Calculation Note for Foundation of 10-D-2645 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-07 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00816
[6 empty] | Return Date | 2019-03-18
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0102 | Calculation Note For Foundation Of 10-D-2555 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-20 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0103 | Calculation Note For Foundation Of 10-D-2550 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-20 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0104 | Calculation Note For Foundation Of 10-PIT-5628 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02841
Return Date
Owner Cmmt*
| CV | OL1-2K13-0105 | Calculation Note For Foundation Of 10-D-2575 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0106 | Calculation Note For Foundation Of 10-D-2880 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-01
[6 empty] | Issue Actual | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02030
[6 empty] | Return Date | 2019-08-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0107 | Calculation Note For Foundation of 10-D-2870 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-01-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-01-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00679
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0108 | Calculation Note For Foundation Of 10-D-2860 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-01-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-01-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00732
[6 empty] | Return Date | 2019-03-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0109 | Calculation Note For Foundation Of 10-D-2865 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0111 | Calculation Note For Foundation Of 10-E-2587 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0113 | Calculation Note for Foundation of 10-E-2305 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0115 | Calculation Note For Foundation Of 10-E-2576 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-08 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | 2019-03-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0116 | Calculation Note For Foundation of 10-E-2645A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-15
[6 empty] | Transmittal no. | TPSL-LSPA1-T-CV-01059
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0117 | Calculation Note for Foundation of 10-E-2502 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-01-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-01-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00679
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0118 | Calculation Note For Foundation Of 10-E-2515 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-07 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00992
[6 empty] | Return Date | 2019-03-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0119 | Calculation Note For Foundation Of 10-E-2546 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0120 | Calculation Note For Foundation Of 10-E-2548 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0121 | Calculation Note for Foundation Of 10-E-2545 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-01-31 | 2020-06-15
[6 empty] | Issue Actual | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00762
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K13-0123 | Calculation Note For Foundation Of 10-E-2807 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0124 | Calculation Note For Foundation Of 10-E-2809 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0125 | Calculation Note for Foundation of 10-E-2857 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-07 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00816
[6 empty] | Return Date | 2019-03-18
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0126 | Calculation Note For Foundation Of 10-E-2858 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0127 | Calculation Note For Foundation Of 10-E-2856 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0128 | Calculation Note For Foundation of 10-E-2855 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-22 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01126
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0129 | Calculation Note For Foundation Of 10-E-2853 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-19 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00878
[6 empty] | Return Date | 2019-03-11
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0130 | Calculation Note For Foundation Of 10-E-2852 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0132 | Calculation Note For Foundation of 10-E-2582 |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-05-02 |  | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 |  | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12 | 2019-02-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843 | TPSK-LSPA1-T-CV-00904
[6 empty] | Return Date | 2019-02-27 | 2019-03-12
[6 empty] | Owner Cmmt* | A2 | A2
| CV | OL1-2K13-0133 | Calculation Note For Foundation Of 10-E-2504 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-01-31 | 2020-06-15
[6 empty] | Issue Actual | 2019-01-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00762
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K13-0134 | Calculation Note For Foundation Of PSA PKG 10-PK-2560 - 10-D-2560-A-E - 10-D-2565 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-30 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02537
Return Date
Owner Cmmt*
| CV | OL1-2K13-0135 | CALCULATION NOTE FOR PUMPS 10-P-2570A/B, 10-P-2575A/B, 10-P-2586A/B, 10-P-2647, 10-P-2646A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0136 | CALCULATION NOTE FOR PUMPS 10-P-2802A/B, 10-P-2805A/B, 10-P-2815, 10-P-2855A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0137 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2930, 10-D-2930 AND 10-P-2930 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0138 | Calculation Note For Foundation Of 10-R-2700A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0140 | Calculation Note For Foundation Of 10-E-2620 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0141 | Calculation Note For Foundation Of 10-E-2666 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0142 | CALCULATION NOTE FOR FOUNDATION OF 10-F-2666A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0143 | Calculation Note For Foundation Of 10-E-2660 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01469
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0147 | Calculation Note For Foundation Of 10-T-2630 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0148 | Calculation Note For Foundation Of 10-R-2470A-B-C |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0149 | Calculation Note For Foundation Of 10-D-2610 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-11 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00832
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0150 | Calculation Note For Foundation Of 10-D-2600A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-11 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00832
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0151 | Calculation Note For Foundation Of 10-D-2460 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0152 | Calculation Note For Foundation Of 10-D-2440 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01168
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0153 | Calculation Note For Foundation Of 10-D-1000 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0154 | Calculation Note For Foundation Of 10-E-2635 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0155 | Calculation Note For Foundation Of 10-E-2636 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-08 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01005
[6 empty] | Return Date | 2019-03-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0156 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2472 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0157 | Calculation Note for Foundation of 10-E-2474 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0158 | Calculation Note For Foundation Of 10-E-2465 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0159 | Calculation Note For Foundation Of 10-E-2460 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0160 | Calculation Note For Foundation Of 10-E-2440 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01333
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0161 | Calculation Note for Foundation of 10-E-1020 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0162 | Calculation Note For Foundation Of 10-E-1015 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0163 | Calculation Note For Foundation Of 10-E-1001 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01033
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0164 | Calculation Note For Foundation Of 10-E-1000A/B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0165 | Calculation Note For Foundation Of 10-E-1005 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01348
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0166 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2912 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0167 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2922 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0169 | Calculation Note For Foundation Of 10-E-2705 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01521
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0171 | Calculation Note For Foundation Of 10-D-2735 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-19 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01415
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0172 | CALCULATION NOTE FOR FOUNDATION OF 10-D-2724 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0173 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2730 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0175 | Calculation Note For Foundation Of 10-E-2755 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0176 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2725A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0177 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2726 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0179 | Calculation Note For Foundation Of 10-E-2702 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-27 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02003
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0180 | Calculation Note For Foundation Of 10-E-2701 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-24 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01456
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0181 | Calculation Note For Foundation Of 10-E-2706 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0182 | Calculation Note For Foundation Of 10-E-2008A-B-C-D-E |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-02-12 | 2020-06-15
[6 empty] | Issue Actual | 2019-02-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00843
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0186 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2724 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0187 | CALCULATION NOTE FOR FOUNDATION OF 10-E-2714 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0188 | Calculation Note For Foundation Of 10-E-2882 And 10-E-2884 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0191 | Calculation Note for Foundation of 10-E-2100 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-09 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02382
Return Date
Owner Cmmt*
| CV | OL1-2K13-0192 | Calculation Note For Foundation Of 10-D-2705 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01521
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0193 | Calculation Note For Foundation Of 10-TK-2320 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-29 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02517
Return Date
Owner Cmmt*
| CV | OL1-2K13-0194 | Calculation Note For Foundation Of 10-E-1050 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0195 | Calculation Note for Foundation of 10-D-1910 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01469
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0197 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5914 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0198 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5912 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0200 | CALCULATION NOTE FOR FOUNDATION OF IGNITION SYSTEM |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0201 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION FOR 10-C-3070 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0202 | Calculation Note For Foundation Of 10-TK-3900 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-19 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02194
Return Date
Owner Cmmt*
| CV | OL1-2K13-0203 | Calculation Note For Foundation Of 10-T-3000 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-18 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01901
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0204 | Calculation Note For Foundation Of 10-T-3040 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-09 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02739
Return Date
Owner Cmmt*
| CV | OL1-2K13-0205 | Calculation Note For Foundation Of 10-T-3020 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-09 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02739
Return Date
Owner Cmmt*
| CV | OL1-2K13-0207 | Calculation Note For Foundation Of 10-T-3030 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-18 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01901
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0208 | Calculation Note For Foundation Of 10-T-3050 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-18 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01901
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0210 | Calculation Note For Foundation OF 10-T-3080 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-18 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01901
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0212 | Calculation Note For Foundation Of 10-T-3070 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-03 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02064
[6 empty] | Return Date | 2019-09-03
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0214 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3126 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-10 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02791
Return Date
Owner Cmmt*
| CV | OL1-2K13-0215 | Calculation Note For Foundation Of 10-D-3908 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-07 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02358
Return Date
Owner Cmmt*
| CV | OL1-2K13-0216 | Calculation Note For Foundation Of 10-D-3902 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-07 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02358
Return Date
Owner Cmmt*
| CV | OL1-2K13-0217 | Calculation Note For Foundation Of 10-D-3904 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-07 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02358
Return Date
Owner Cmmt*
| CV | OL1-2K13-0218 | Calculation Note For Foundation Of 10-D-3906 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-07 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02358
Return Date
Owner Cmmt*
| CV | OL1-2K13-0219 | Calculation Note For Foundation Of 10-D-3180 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-03 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02064
[6 empty] | Return Date | 2019-09-03
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0220 | CALCULATION NOTE FOR FOUNDATION OF 10-D-3110 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-10 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02791
Return Date
Owner Cmmt*
| CV | OL1-2K13-0221 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3004A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0222 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3014A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0223 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3015 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0224 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3084 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0225 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3085A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0228 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3098 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0229 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3055A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0230 | Calculation Note For Foundation Of 10-E-3045 A/B/C/D |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-27 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02494
Return Date
Owner Cmmt*
| CV | OL1-2K13-0231 | Calculation Note For Foundation Of 10-E-3044 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-27 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02494
Return Date
Owner Cmmt*
| CV | OL1-2K13-0232 | Calculation Note For Foundation Of 10-E-2585 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01207
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0235 | CALCULATION NOTE FOR FOUNDATION OF 10-E-3005 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0236 | Calculation Note For Foundation Of 10-E-3070 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-27 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02494
Return Date
Owner Cmmt*
| CV | OL1-2K13-0237 | CALCULATION FOR FOUNDATION OF METERING STATION |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0238 | Calculation Note For Foundation Of 10-E-2765 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01521
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0240 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5560 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0241 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5394 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0242 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5901 and 10-PK-5905 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0243 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5355 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0244 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5392 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0245 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5390 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0246 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5950 and 10-PK-5955 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0247 | Calculation Note For Foundation Of 10-D-5550 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-03 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01731
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0248 | Calculation Note For Foundation Of 10-D-5500 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-29 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02497
Return Date
Owner Cmmt*
| CV | OL1-2K13-0249 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5510 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0250 | Calculation Note For Foundation Of 10-D-5513 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0251 | Calculation Note For Foundation Of 10-D-5515 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0252 | Calculation Note For Foundation Of 10-D-5520 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0253 | CALCULATION NOTE FOR FOUNDATION OF 10-C-5520A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0254 | Calculation Note For Foundation Of 10-E-5510 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-21 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01702
[6 empty] | Return Date | 2019-06-20
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0255 | Calculation Note For Foundation Of 10-E-5513 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-21 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01702
[6 empty] | Return Date | 2019-06-20
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0256 | Calculation Note For Foundation Of 10-TK-5640 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-03 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01731
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0257 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5675A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0258 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5676 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0259 | Calculation Note for Foundation Of 10-TX-C-2550 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-22 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02202
[6 empty] | Return Date | 2019-10-14
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0260 | CALCULATION NOTE FOR FOUNDATION OF 10-C-5650A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0261 | Calculation Note For Foundations And Elevation Of 10-C-2800 - 10-E-2800 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02729
Return Date
Owner Cmmt*
| CV | OL1-2K13-0262 | Calculation Note Of Concrete Structure Of 10-C-2850- 10-E-2850 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02857
Return Date
Owner Cmmt*
| CV | OL1-2K13-0263 | Calculation Note For Foundation Of 10-C-2200- 10- E-2200 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02857
Return Date
Owner Cmmt*
| CV | OL1-2K13-0264 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5627, 10-PIT-5627, P-10-5627A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0265 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5397 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0266 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5692 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0267 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5693 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0268 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5694 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0269 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5671 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0270 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5672 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0271 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5697 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0272 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5690 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0273 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5691 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0274 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5670 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0275 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5670A/B, 10-P-5671A/B, 10-P-5644A/B, 10-P-5645A/B, 10-P-5646A/B, 10-P-5647A/B, 10-P-5675 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0276 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5646 AND 10-X-5646 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0277 | CALCULATION NOTE FOR FOUNDATION OF 10-D-5644 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0278 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5644 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0279 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5653 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0280 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5650 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0281 | Calculation Note For Foundation 10-TK-5110 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-18 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01901
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0282 | Calculation Note For Foundation 0F 10-TK-5120 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-18 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01901
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0283 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5130 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0284 | Calculation Note For Foundation 10-D-5552 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-03 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01731
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0285 | Calculation Note Foundation Of 10-D-5565 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-10 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0286 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-1950, 10-C-1950A/B, 10-E-1951A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0287 | Calculation Note for Foundation of 10-D-5140 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-01-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-01-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00679
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0288 | Calculation Note For Foundation Of 10-D-5400 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01521
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0289 | Calculation Note For Foundation Of 10-D-5114 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-24 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01456
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0290 | Calculation Note For Foundation Of 10-D-5112 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-24
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01456
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0292 | Calculation Note For Foundation Of 10-E-5113 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0294 | CALCULATION NOTE FOR FOUNDATION OF 10-F-5610 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0295 | Calculation Note For Foundation Of 10-E-5552 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-03 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01731
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0296 | CALCULATION NOTE FOR FOUNDATION OF 10-E-5110 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0297 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5191 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0298 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5192 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0299 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5115, 10-F-5115A/B/C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0300 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5125, 10-D-5125A/B, 10-F-5125A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0301 | Calculation Note For Foundation Of 10-P-2106 A-B-C |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02806
Return Date
Owner Cmmt*
| CV | OL1-2K13-0302 | CALCULATION NOTE FOR SKID 10-P-2201A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0303 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5360A/B/C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0304 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5670 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0305 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5695 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0306 | CALCULATION NOTE FOR PUMPS 10-P-5900A/B, 10-P-5950A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0307 | CALCULATION NOTE FOR FOUNDATION OF 10-P-5350 A/B/C/D/E/F/G/H |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0308 | CALCULATION NOTE FOR PUMPS 10-P-3080A/B, 10-P-3030A/B, 10-P-3000A/B, 10-P-3020A/B, 10-P-3061A/B, 10-P-3060A/B, 10-P-3062A/B, 10- |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0309 | CALCULATION NOTE FOR PUMPS 10-P-3096A/B, 10-P-3086A/B, 10-P-3036A/B, 10-P-3016A/B, 10-P-3900, 10-P-3160A/B, 10-P-3076A/B, 10-P-3 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0310 | CALCULATION NOTE FOR PUMPS 10-P-3046A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0311 | CALCULATION NOTE FOR PUMPS 10-P-3045A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0312 | CALCULATION NOTE FOR PUMPS 10-P-3026A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0313 | CALCULATION NOTE FOR PUMPS 10-P-3056A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0314 | Calculation Note For Foundation Of 10-R-2620A |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0315 | CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2450A/B, 10-P-2455A/B, 10-P-2620A/B, 10-P-2666A/B, 10-P-2660A/B, 10-P-2910 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0316 | CALCULATION NOTE FOR FOUNDATION PUMPS FOR 10-P-2630A/B, 10-P-2310A/B, 10-P-2316A/B, 10-P-2326A/B, 10-P-2320A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0317 | CALCULATION NOTE FOR PUMPS 10-P-2302A/B, 10-P-2415A/B, 10-P-2445A/B, 10-P-2304, 10-P-2306A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0318 | CALCULATION NOTE FOR PUMPS 10-P-2200A/B, 10-P-2220A/B, 10-P-2210A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0319 | CALCULATION NOTE FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0320 | CALCULATION NOTE FOR PUMPS 10-P-5550A/B, 10-P-5552 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0321 | CALCULATION NOTE FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0322 | Calculation Note For Foundation of 10-T-2000 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-20 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0323 | Calculation Note For Foundation Of 10-T-2020 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-20 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0324 | Calculation Note For Foundation Of 10-T-2100 |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-05-02 |  | 2020-06-15
[6 empty] | Revised Plan | 2019-02-22 |  | 2020-06-15
[6 empty] | Issue Actual | 2019-02-22 | 2019-03-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00904 | TPSK-LSPA1-T-CV-01092
[6 empty] | Return Date | 2019-03-12 | 2019-04-12
[6 empty] | Owner Cmmt* | A2 | A2
| CV | OL1-2K13-0325 | Calculation Note For Concrete Structure Of 10-T-2040 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-01 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02030
[6 empty] | Return Date | 2019-08-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0327 | Calculatoin Note For Foundation Of Lifting Station 10-PIT-5610 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-31
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02118
[6 empty] | Return Date | 2019-09-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0328 | Calculation Note For Foundation Of Basin 10-PIT-2390 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-08-05 | 2020-01-31
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02312
Return Date
Owner Cmmt*
| CV | OL1-2K13-0329 | Calculation Note For Foundation Of Lifting Station 10-PIT-5603 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-06-27 | 2020-01-31
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02003
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0330 | Calculation Note For Concrete Basin 10-PIT-5604 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-31
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02118
[6 empty] | Return Date | 2019-09-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0331 | Calculation Note For Foundation of 10-PIT-2090 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-04-11 | 2020-01-31
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01303
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0332 | Calculation Note For Foundation Of 10-PIT-2190 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-31
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02118
[6 empty] | Return Date | 2019-09-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0333 | Calculation Note For Foundation Of Basin 10-PIT-2790 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-07-30 | 2020-01-31
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K13-0335 | CALCULATION NOTE FOR FOUNDATION OF 10-PIT-3190 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-10-10 | 2020-01-31
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02791
Return Date
Owner Cmmt*
| CV | OL1-2K13-0336 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5601 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0337 | Calculation Note For Foundation Of Lifting Station 10-PIT-5600 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-07-30 | 2020-01-31
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K13-0338 | CALCULATION OF BASIN FOR COOLING TOWER 10-PIT-5350 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-12-12 | 2020-01-02 | 2020-01-23 | 2020-03-08
[6 empty] | Revised Plan | 2019-12-12 | 2020-01-02 | 2020-01-23 | 2020-03-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0339 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5370 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0340 | Calculation Note For Foundation Of Basin 10-PIT-5602 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-31
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02118
[6 empty] | Return Date | 2019-09-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0341 | Calculation Note for Foundation of 10-PIT-2392 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-06-24 | 2020-01-31
[6 empty] | Issue Actual | 2019-06-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01961
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0343 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5615 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0344 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5656 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0345 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5620A/B/C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0346 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5630 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0347 | CALCULATION NOTE FOR FOUNDATION OF 10-PIT-5633 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-10-10 | 2020-01-31
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02791
Return Date
Owner Cmmt*
| CV | OL1-2K13-0348 | CALCULATION NOTE FOR FOUNDATION OF LIFTING STATION 10-PIT-5631 [036909C-105T-CN-1734-0005] |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0349 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5671 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0350 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5650A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0351 | CALCULATION NOTE FOR FOUNDATION OF BASIN 10-PIT-5655 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0352 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-5696 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0353 | CALCULATION NOTE FOR FOUNDATION OF CLARIFIER 10-TK-5651A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0356 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0357 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0358 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0359 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0360 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0361 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0362 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0363 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0364 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0365 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0366 | CALCULATION NOTE FOR RETAINING WALL 10-TK-5900 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-10-10 | 2020-06-02
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02791
Return Date
Owner Cmmt*
| CV | OL1-2K13-0367 | CALCULATION NOTE FOR RETAINING WALL 10-TK-5950 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-10-10 | 2020-06-02
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02791
Return Date
Owner Cmmt*
| CV | OL1-2K13-0368 | Calculation For Foundation And Elevation Of Retaining Wall For 10-TK-2320 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-09-10 | 2020-06-02
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02585
Return Date
Owner Cmmt*
| CV | OL1-2K13-0369 | Calculation For Foundation And Elevation Of Retaining Wall For 10-TK-2910 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-09-10 | 2020-06-02
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02589
Return Date
Owner Cmmt*
| CV | OL1-2K13-0370 | CALCULATION NOTE FOR RETAINING WALL 10-TK-3900 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-10-10 | 2020-06-02
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02791
Return Date
Owner Cmmt*
| CV | OL1-2K13-0371 | CALCULATION FOR FOUNDATION AND ELEVATION OF RETAINING WALL FOR 10-PK-1910 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0372 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS FLARE UNIT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0373 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0374 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0375 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0376 | CALCULATION FOR FOUNDATION OF SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0377 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0378 | CALCULATION NOTE FOR 10-SLW-5T02 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0379 | CALCULATION NOTE FOR 10-SLW-5T01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0380 | CALCULATION NOTE FOR 10-SLW-0C01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0381 | CALCULATION NOTE FOR 10-SLW-5W01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0382 | CALCULATION NOTE FOR 10-SLW-5F01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0383 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0384 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0385 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0386 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0387 | CALCULATION NOTE FOR FOUNDATION FOR PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0388 | CALCULATION FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0389 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0391 | CALCULATION NOTE FOR FOUNDATION FOR SUPPORTS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0393 | Calculation Note For Foundation Of 10-TK-5900 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0394 | CALCULATION NOTE FOR FOUNDATION OF 10-TK-5950 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0396 | CALCULATION NOTE FOR SKID 10-P-2801A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0398 | CALCULATION FOR BASIN 10-PIT-5642 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-30 | 2020-01-31
[6 empty] | Revised Plan | 2019-12-30 | 2020-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0399 | CALCULATION NOTE FOR FOUNDATION OF 10-PK-2904 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K13-0400 | Calculation Note For Foundation Of 10-TK-2300 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-24 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02238
Return Date
Owner Cmmt*
| CV | OL1-2K13-0401 | Calculation Note For Foundation Of 10-E-2441 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01333
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0402 | Calculation Note For Foundation Of 10-E-2442 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01372
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K13-0403 | Calculation Note For Foundation Of 10-E-2405 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01661
Return Date
Owner Cmmt*
| CV | OL1-2K13-0404 | Calculation Note For Foundation Of 10-D-1912 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01469
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0405 | Calculation Note For Foundation Of 10-D-2322 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-11 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01857
[6 empty] | Return Date | 2019-08-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K13-0406 | Calculation Note For Foundation Of 10-E-3018 A/B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-27 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02494
Return Date
Owner Cmmt*
| CV | OL1-2K13-0407 | Calculation Note For Foundation Of 10-P-2146 A-B |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02806
Return Date
Owner Cmmt*
| CV | OL1-2K13-4590 | Calculation Note For Foundation Of 10-F-2137-A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-30 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02539
Return Date
Owner Cmmt*
Category Code: K14 Design calculation for concrete structure (including reinforcement detail)
| CV | OL1-2K14-0001 | Calculation Note For Precast Concrete and Foundations For Main Pipe Rack 10-PRK-0P01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0002 | Calculation Note For Precast Concrete Pipe Rack 10-PRK-0P01 - For Previous revision see OL1-2K14-0001 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01749 | TPSK-LSPA1-T-CV-02783
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K14-0003 | Calculation Note For Foundations Of Pipe Rack 10-PRK-0P02 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02121
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K14-0004 | Calculation Note For Precast Concrete Pipe Rack 10-PRK-0P02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02121
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K14-0005 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-3A01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0006 | CALCULATION NOTES FOR PRECAST CONCRETE ELEVATION OF PIPE RACK 10-PRK-3A01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0007 | Calculation Note For Foundation & Elevation Of Pipe Rack 10-Prk-5U01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-19 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02660
Return Date
Owner Cmmt*
| CV | OL1-2K14-0008 | Calculation Note For Precast Concrete Elevation Of Pipe Rack 10-Prk-5U01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-19 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02660
Return Date
Owner Cmmt*
| CV | OL1-2K14-0009 | Calculation Note For Foundations Of Pipe Rack 10-PRK-2D01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-10 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02585
Return Date
Owner Cmmt*
| CV | OL1-2K14-0010 | Calculation Note For Precast Concrete Pipe-Rack 10-PRK-2D01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02646
Return Date
Owner Cmmt*
| CV | OL1-2K14-0011 | Calculation Note For Foundations Of Pipe Rack 10-PRK-2E01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K14-0012 | Calculation Notes For Precast Concrete Elevation Of Pipe Rack 10-PRK-2E01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02303
Return Date
Owner Cmmt*
| CV | OL1-2K14-0013 | Calculation Notes for Foundations of Piperack 10-PRK-2A01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02382
Return Date
Owner Cmmt*
| CV | OL1-2K14-0014 | Calculation Notes for Precast Concrete Piperack 10-PRK-2A01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02382
Return Date
Owner Cmmt*
| CV | OL1-2K14-0015 | Calculation Notes For Foundation And Elevation Of 10-PRK-2B01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan |  | 2019-11-18
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02727
Return Date
Owner Cmmt*
| CV | OL1-2K14-0016 | Calculation Notes For Precast Concrete Elevation Of Pipe Rack 10-PRK-2B01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02758
Return Date
Owner Cmmt*
| CV | OL1-2K14-0017 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-2C01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0018 | Calculation Note for Foundation and Elevation of 10-STR-2B03 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-08-15 | 2020-04-08
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02425
Return Date
Owner Cmmt*
| CV | OL1-2K14-0019 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5T01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0020 | Calculation Note For Foundations For Pipe Rack 10-PRK-0P03 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K14-0021 | CALCULATION NOTES FOR FOUNDATION & ELEVATION OF PIPE RACK 10-PRK-5F01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0023 | Calculation Note For Foundation Of 10-SHT-2E01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-10-15 | 2020-04-08
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02830
Return Date
Owner Cmmt*
| CV | OL1-2K14-0024 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0025 | Calculation Note For Foundation Of 10-SHT-2D02 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-08-01 | 2020-04-08
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02303
Return Date
Owner Cmmt*
| CV | OL1-2K14-0026 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D03 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0027 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D04 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0028 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A06 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0029 | CALCULATION NOTE FOR FOUNDATION AND ELEVATIONOF 10-STR-3A03 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0030 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A05 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0031 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A04 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0032 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A02 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0033 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-3A01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0034 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-3A01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0035 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0036 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T02 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0037 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-5U01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0038 | Calculation Note For Foundation And Elevation Of 10-STR-2E01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-09-17 | 2020-04-08
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02650
Return Date
Owner Cmmt*
| CV | OL1-2K14-0039 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0040 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E03 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0041 | Calculation Note For Foundation Of 10-STR-2E04 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-10-10 | 2020-04-08
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02772
Return Date
Owner Cmmt*
| CV | OL1-2K14-0042 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D05 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0043 | Calculation Note For Foundation And Elevation Of 10-STR-0P01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-07-24 | 2020-04-08
[6 empty] | Issue Actual | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02238
Return Date
Owner Cmmt*
| CV | OL1-2K14-0044 | Calculation Note For Foundation And Elevation Of 10-STR-2A01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-07-22 | 2020-04-08
[6 empty] | Issue Actual | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02202
[6 empty] | Return Date | 2019-10-14
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K14-0045 | Calculation Note For Foundation And Elevation Of 10-STR-2A02 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-09-10 | 2020-04-08
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02596
Return Date
Owner Cmmt*
| CV | OL1-2K14-0046 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2A03 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0047 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0048 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C06 - ADDED 15 APR 19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0049 | Calculation Note For Foundation And Elevation Of 10-STR-2C07 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan |  | 2020-04-08
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02727
Return Date
Owner Cmmt*
| CV | OL1-2K14-0050 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2B04 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0051 | Calculation Note For Foundation And Elevation Of 10-STR-2B02 And 10-T-2330 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-09-28 | 2020-04-08
[6 empty] | Issue Actual | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02713
Return Date
Owner Cmmt*
| CV | OL1-2K14-0052 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2E05 - ADDED 15 APR 19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0053 | Calculation Note For Foundation Of 10-SHT-2D01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-06-11 | 2020-04-08
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01857
[6 empty] | Return Date | 2019-08-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K14-0054 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2D02 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0055 | Calculation Note For Foundation And Elevation Of 10-STR-2C01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-09-19 | 2020-04-08
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02665
Return Date
Owner Cmmt*
| CV | OL1-2K14-0056 | Calculation Note For Steel Pipe Rack 10-PRK-2B02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-09-19 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02665
Return Date
Owner Cmmt*
| CV | OL1-2K14-0057 | Calculation Note For Foundation And Elevation Of 10-STR-2C03 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-09-17 | 2020-04-08
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02650
Return Date
Owner Cmmt*
| CV | OL1-2K14-0058 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C04 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0059 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C05 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0060 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-2C01 - ADDED 15 APR 19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0061 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-1B01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0062 | CALCULATION NOTE FOR FOUNDATION OF WASTE STORAGE BUILDING |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0063 | CALCULATION NOTE FOR FOUNDATION OF LUBRIFICATION OIL & GREASE STORAGE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0064 | CALCULATION NOTE FOR FOUNDATION OF GAS CYLINDER STORAGE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0065 | CALCULATION NOTE FOR FOUNDATION OF TOOL ROOM OPERATION |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0066 | Calculation Note For Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K14-0067 | Calculation Note For Foundation And Elevation Of 10-PRK-2B02 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02646
Return Date
Owner Cmmt*
| CV | OL1-2K14-0068 | Calculation Note For Precast Concrete Elevation Of Pipe Rack 10-PRK-2B02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-19 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02665
Return Date
Owner Cmmt*
| CV | OL1-2K14-0069 | Calculation Notes For Precast Concrete Elevation Of Pipe Rack 10-PRK-2C02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02646
Return Date
Owner Cmmt*
| CV | OL1-2K14-0070 | CALCULATION NOTE FOR FOUNDATION OF 10-SHT-5T03 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0071 | CALCULATION NOTE FOR FOUNDATION OF STORAGE SHELTER FOR CHENICALS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0073 | Calculation Note For Foundations Of 10-STR-1B01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2019-10-10 | 2020-04-08
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02799
Return Date
Owner Cmmt*
| CV | OL1-2K14-0074 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C08 - ADDED 15 JUNE 2019 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0075 | CALCULATION NOTE FOR FOUNDATION AND ELEVATION OF 10-STR-2C09 - ADDED 15 JUNE 2019 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-04-08
[6 empty] | Revised Plan | 2020-02-12 | 2020-04-08
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-0169 | Calculation Notes For Foundation & Elevation Of Pipe Rack 10-PRK-2C02 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-05 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02331
Return Date
Owner Cmmt*
| CV | OL1-2K14-0170 | CALCULATION NOTE FOR FOUNDATION FOR PIPE BRIDGE 10-PRK-5W01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-5001 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CALC. |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-5002 | ELECTRICAL SUBSTATION SUB-E - TRANSFORMERS & WALLS STRUCTURAL CALC. |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-5003 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CALC. |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K14-5004 | ELECTRICAL SUBSTATION SUB-C - TRANSFORMERS & WALLS STRUCTURAL CALC.STRUCTURAL CALC. |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K15 Design calculation for steel structure (including connection joint)
| CV | OL1-2K15-0001 | Calculation Note For Steel Pipe Rack 10-PRK-0P01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01749 | TPSK-LSPA1-T-CV-02834
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K15-0002 | Calculation Note For Steel Pipe Rack 10-PRK-0P02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-11 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02121
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K15-0003 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-3A01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0004 | CALCULATION NOTE FOR STEEL PIPE RACK 10-PRK-5U01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-10 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02791
Return Date
Owner Cmmt*
| CV | OL1-2K15-0005 | Calculation Note For Steel Pipe-Rack 10-PRK-2D01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-09-17 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02645
Return Date
Owner Cmmt*
| CV | OL1-2K15-0006 | Calculation Note For Steel Pipe Rack 10-PRK-2E01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-09-11 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-09-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02612
Return Date
Owner Cmmt*
| CV | OL1-2K15-0007 | Calculation Note For Steel Pipe-Rack 10-PRK-2A01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-09-17 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02645
Return Date
Owner Cmmt*
| CV | OL1-2K15-0008 | Calculation Notes For Steel Pipe Rack 10-PRK-2B01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-09 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02756
Return Date
Owner Cmmt*
| CV | OL1-2K15-0009 | CALCULATION NOTES FOR STEEL PIPE RACK 10-PRK-2C01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0010 | Calculation Note For Steel Pipe Rack 10-PRK-5T01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02840
Return Date
Owner Cmmt*
| CV | OL1-2K15-0011 | CALCULATION NOTES FOR STEEL 10-PRK-5F01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0012 | Calculation Note For Steel Of Structure 10-SHT-2E01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan |  | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02857
Return Date
Owner Cmmt*
| CV | OL1-2K15-0013 | Calculation Note For Steel Structure Of 10-STR-2E01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-09-17 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02645
Return Date
Owner Cmmt*
| CV | OL1-2K15-0014 | Calculation Note For Steel Structure 10-STR-2E02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan |  | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02857
Return Date
Owner Cmmt*
| CV | OL1-2K15-0015 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2E03 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0016 | Calculation Note For Steel Structure 10-STR-2E04 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-10-10 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02772
Return Date
Owner Cmmt*
| CV | OL1-2K15-0017 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D05 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0018 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0019 | CALCULATION FOR STEEL STRUCTURE 10-STR-2C06 - ADDED 15 APR 19 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0020 | Calculation Note For Steel Structure 10-STR-2C07 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan |  | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02728
Return Date
Owner Cmmt*
| CV | OL1-2K15-0021 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2B04 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0022 | Calculation Note For Steel Structure 10-STR-2B02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-09-28 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-09-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02711
Return Date
Owner Cmmt*
| CV | OL1-2K15-0023 | CALCULATION FOR STEEL STRUCTURE 10-STR-2E05 - ADDED 15 APR 19 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0024 | Calculation Note for Steel Structure 10-SHT-2D01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-06-10 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01815
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K15-0025 | Calculation Note For Steel Structure 10-SHT-2D02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-08-01 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02303
Return Date
Owner Cmmt*
| CV | OL1-2K15-0027 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0028 | Calculation Note For Steel Structure 10-STR-2C03 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-09-17 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02645
Return Date
Owner Cmmt*
| CV | OL1-2K15-0029 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C04 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0030 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C05 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0031 | Calculation Note For Steel Structure Of 10-STR-2D06 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-25
[6 empty] | Issue Actual | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02696
Return Date
Owner Cmmt*
| CV | OL1-2K15-0032 | CALCULATION NOTE FOR STEEL STRUCTURE 10-SHT-1B01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0033 | Calculation Note For Steel Structure Of 10-STR-0P01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-09-03 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02550
Return Date
Owner Cmmt*
| CV | OL1-2K15-0034 | Calculation Note For Steel Structure Of 10-STR-2A01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-07-24 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02238
[6 empty] | Return Date | 2019-10-09
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K15-0035 | Calculation Note For Steel Structure Of 10-STR-2A02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-09-10 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02596
Return Date
Owner Cmmt*
| CV | OL1-2K15-0036 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2A03 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0037 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0038 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0039 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D03 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0040 | CALCULATION FOR STEEL STRUCTURE 10-STR-2D04 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0041 | CALCULATION NOTE FOR STEEL FOR WASTE STORAGE BUILDING |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0042 | CALCULATION NOTE FOR STEEL FOR LUBRIFICATION OIL & GREASE STORAGE |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0043 | CALCULATION NOTE FOR STEEL FOR GAS CYLINDER STORAGE |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0045 | Calculation Note For Steel Pipe Rack 10-PRK-0P03 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-30 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02273
Return Date
Owner Cmmt*
| CV | OL1-2K15-0046 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A06 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0047 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A03 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0048 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A05 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0049 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A04 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0050 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0051 | CALCULATION FOR STEEL STRUCTURE 10-STR-3A01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0052 | CALCULATION FOR STEEL STRUCTURE 10-SHT-3A01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0053 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0054 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0055 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-5U01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0057 | Calculation Notes For Steel Pipe Rack 10-PRK-2C02 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Revised Plan | 2019-09-10 | 2020-04-15 | 2020-05-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02596
Return Date
Owner Cmmt*
| CV | OL1-2K15-0058 | CALCULATION NOTE FOR STEEL FOR STORAGE SHELTER FOR CHENICALS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0059 | CALCULATION FOR STEEL STRUCTURE 10-SHT-5T03 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0060 | Calculation Note For Steel Structure 10-STR-1B01 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-10-09 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02756
Return Date
Owner Cmmt*
| CV | OL1-2K15-0061 | CALCULATION FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-12-27 | 2020-01-26 | 2020-02-26 | 2020-03-28 | 2020-04-30
[6 empty] | Revised Plan | 2019-12-27 | 2020-01-26 | 2020-02-26 | 2020-03-28 | 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0062 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0064 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0065 | Calculation Note For Steel Structure Of 10-T-2040 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-18 | 2019-09-16
[6 empty] | Revised Plan | 2019-07-01 | 2019-11-25
[6 empty] | Issue Actual | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02030
[6 empty] | Return Date | 2019-08-28
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K15-0066 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0067 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0068 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-01-15 | 2020-02-15
[6 empty] | Revised Plan | 2020-01-15 | 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0069 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0070 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0071 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0072 | CALCULATION NOTE FOR STEEL STRUCTURE OF 10-C-2850, 10-E-2850 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-12-06 | 2020-02-26 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-12-06 | 2020-02-26 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0073 | CALCULATION NOTE FOR STEEL STRUCTURE OF 10-C-2800, 10-E-2800 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-12-06 | 2020-02-26 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-12-06 | 2020-02-26 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0074 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0075 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0076 | CALCULATION NOTE FOR STEEL STRUCTURE OF 10-C-2200, 10-E-2200 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-12-06 | 2020-02-26 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-12-06 | 2020-02-26 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0077 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0078 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0079 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0080 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0081 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0082 | CALCULATION NOTE FOR STEEL SUPPORTS FLARE UNIT |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0083 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0084 | CALCULATION FOR STEEL COOLING TOWER 5350 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-04-15 | 2020-05-15 | 2020-06-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-04-15 | 2020-05-15 | 2020-06-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0085 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0086 | CALCULATION NOTE FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0087 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0088 | CALCULATION FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-12-27 | 2020-01-26 | 2020-02-26 | 2020-03-28 | 2020-04-30
[6 empty] | Revised Plan | 2019-12-27 | 2020-01-26 | 2020-02-26 | 2020-03-28 | 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0089 | CALCULATION NOTE FOR STEEL PLATFORMS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-07-01 | 2020-07-31 | 2020-09-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0090 | CALCULATION FOR STEEL SUPPORTS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-12-27 | 2020-01-26 | 2020-02-26 | 2020-03-28 | 2020-04-30
[6 empty] | Revised Plan | 2019-12-27 | 2020-01-26 | 2020-02-26 | 2020-03-28 | 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0091 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C08 - ADDED 15 JUNE 2019 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0092 | CALCULATION NOTE FOR STEEL STRUCTURE 10-STR-2C09 - ADDED 15 JUNE 2019 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0094 | Calculation For Steel Platform For 10-PIT-2190 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-08-05 | 2019-12-26
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02312
Return Date
Owner Cmmt*
| CV | OL1-2K15-0095 | Calculation For Steel Platform For 10-PIT-2392 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-08-05 | 2019-12-26
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02312
Return Date
Owner Cmmt*
| CV | OL1-2K15-0096 | Calculation For Steel Platform For 10-PIT-2790 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-09-03 | 2019-12-26
[6 empty] | Issue Actual | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02557
Return Date
Owner Cmmt*
| CV | OL1-2K15-0097 | Calculation For Steel Platform For 10-PIT-2390 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-09-03 | 2019-12-26
[6 empty] | Issue Actual | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02557
Return Date
Owner Cmmt*
| CV | OL1-2K15-0098 | CALCULATION NOTE FOR STEEL PLATFORM 10-PIT-3190 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-10-10 | 2019-12-26
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02791
Return Date
Owner Cmmt*
| CV | OL1-2K15-0099 | CALCULATION FOR STEEL PLATFORM FOR 10-PIT-5633 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-11-25 | 2019-12-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0100 | CALCULATION FOR STEEL PLATFORM FOR 10-PIT-5658 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-11-25 | 2019-12-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0101 | CALCULATION FOR STEEL PLATFORM FOR 10-PIT-5615 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-11-25 | 2019-12-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0102 | CALCULATION FOR STEEL PLATFORM FOR 10-PIT-5656 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-11-25 | 2019-12-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0103 | CALCULATION FOR STEEL PLATFORM FOR 10-PIT-5620A/B/C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-11-25 | 2019-12-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0104 | CALCULATION FOR STEEL PLATFORM FOR 10-PIT-5650A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-11-25 | 2019-12-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0105 | CALCULATION FOR STEEL PLATFORM FOR 10-PIT-5655 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-11-25 | 2019-12-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0106 | CALCULATION FOR STEEL PLATFORM FOR 10-PIT-5671 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-11-25 | 2019-12-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0107 | CALCULATION FOR STEEL PLATFORM FOR 10-PIT-5642 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-11-25 | 2019-12-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K15-0108 | Calculation Note for Steel Structure 10-STR-2B03 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-04-13 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Revised Plan | 2019-08-15 | 2020-05-14 | 2020-07-21 | 2020-09-04
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02425
Return Date
Owner Cmmt*
| CV | OL1-2K15-0110 | Calculation For Steel Platform For 10-PIT-2090 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-25 | 2019-12-26
[6 empty] | Revised Plan | 2019-10-10 | 2019-12-26
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02772
Return Date
Owner Cmmt*
Category Code: K16 Design calculation for all drainage systems (including roof gutter, down spout, and grating cover)
| CV | OL1-2K16-0001 | Hydraulic Calculation Notes For Underground Systems |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan | 2019-04-04 | 2019-12-20
[6 empty] | Issue Actual | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01239
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | A2
Category Code: K17 Design calculation for all blast material i.e. door,wall
Category Code: K20 Standard drawing for civil work
| CV | OL1-2K20-0001 | Construction Standards For Reinforced Concrete Works |  |  | Purpose** | IFR | IFC | IFC
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-09-25 | 2019-01-20
[6 empty] | Revised Plan | 2018-09-27 | 2019-03-07
[6 empty] | Issue Actual | 2018-09-27 | 2019-03-07 | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088 | TPSK-LSPA1-T-CV-00997 | TPSK-LSPA1-T-CV-02136
[6 empty] | Return Date | 2018-11-02 | 2019-03-28 | 2019-10-04
[6 empty] | Owner Cmmt* | R1 | A2 | A1
Category Code: K21 Standard drawing for steel structure work
| CV | OL1-2K21-0001 | Construction Standards For Steel Structures |  |  | Purpose** | IFR | IFC | IFC
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-09-25 | 2019-01-31
[6 empty] | Revised Plan | 2018-09-27 | 2019-03-07
[6 empty] | Issue Actual | 2018-09-27 | 2019-03-07 | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088 | TPSK-LSPA1-T-CV-00996 | TPSK-LSPA1-T-CV-02051
[6 empty] | Return Date | 2018-11-02 | 2019-03-31 | 2019-08-29
[6 empty] | Owner Cmmt* | R1 | A2 | A1
Category Code: K22 Standard drawing for architecture work
Category Code: K23 Land Developmemt Drawing
| CV | OL1-2K23-0001 | Standard Construction Drawings For Underground Systems - For Next Revision See Document OL1-2K24-0001 |  | Class 2 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2018-09-27
[6 empty] | Issue Actual | 2018-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-00088
[6 empty] | Return Date | 2018-11-02
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K23-1511 | USC 36M Recycle Furnace Steel Radiant Floor and Radiant Arch Plans |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-02 | 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K25 Plant Layouts
| CV | OL1-2K25-0001 | Key Plan For Installation Drawings |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-08-01 | 2019-10-30
[6 empty] | Revised Plan | 2019-04-09 | 2019-10-30
[6 empty] | Issue Actual | 2019-04-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01271
[6 empty] | Return Date | 2019-05-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K25-0002 | Key Plan For Structures |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-06 | 2019-08-01
[6 empty] | Revised Plan | 2019-03-28 | 2019-10-30
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01171
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | A1
Category Code: K26 Underground communication Layouts
| CV | OL1-2K26-0001 | Major Underground Networks Zone 0S - Substation-E And Far-E - Ex Doc Client Ref OL1-2K36-0001 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. |  | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan |  | 2019-09-13
[6 empty] | Issue Actual |  | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02635
Return Date
Owner Cmmt*
| CV | OL1-2K26-0002 | Major Underground Networks - Zone 1B- Furnaces Utilities- Ex Doc Client Ref OL1-2K36-0002 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. |  | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan |  | 2019-10-09
[6 empty] | Issue Actual |  | 2019-10-09
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02762
Return Date
Owner Cmmt*
| CV | OL1-2K26-0003 | Major Underground Networks Zone 2A - Quench - For Next Revision See OL1-2K26-0003 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan | 2019-03-26 | 2019-10-10
[6 empty] | Issue Actual | 2019-03-26 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01138 | TPSK-LSPA1-T-CV-02797
[6 empty] | Return Date | 2019-06-05
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K26-0004 | Major Underground Networks - Zone 2B - C3 Hydrogenation - Ex Doc Client Ref OL1-2K36-0004 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan | 2019-03-26
[6 empty] | Issue Actual | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01138 | TPSK-LSPA1-T-CV-02759
[6 empty] | Return Date | 2019-06-05
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K26-0005 | Major Underground Networks - Zone 2C |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. |  | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan |  | 2019-09-25
[6 empty] | Issue Actual |  | 2019-09-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02694
Return Date
Owner Cmmt*
| CV | OL1-2K26-0006 | Major Underground Networks - Zone 2D - Process Cold Compressor - Ex Doc Client Ref OL1-2K36-0006 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan | 2019-03-26
[6 empty] | Issue Actual | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01138 | TPSK-LSPA1-T-CV-02807
[6 empty] | Return Date | 2019-06-05
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K26-0007 | Major Underground Networks - Zone 2E- Ex Doc Client Ref OL1-2K36-0007 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan | 2019-03-26 | 2019-10-09
[6 empty] | Issue Actual | 2019-03-26 | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01138 | TPSK-LSPA1-T-CV-02752
[6 empty] | Return Date | 2019-06-05
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K26-0008 | Major Underground Networks - Zone 3A - Butadiene Extraction Unit - Ex Doc Client Ref OL1-2K36-0008 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan | 2019-03-26
[6 empty] | Issue Actual | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01138 | TPSK-LSPA1-T-CV-02674
[6 empty] | Return Date | 2019-06-05
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K26-0009 | Major Underground Networks - Zone 3S - Substation-C Far-C - Ex Doc Client Ref OL1-2K36-0009 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. |  | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan |  | 2019-09-12
[6 empty] | Issue Actual |  | 2019-09-12
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02635
Return Date
Owner Cmmt*
| CV | OL1-2K26-0010 | Major Underground Networks - Zone 5T - Cooling Water Unit - Ex Doc Client Ref OL1-2K36-0010 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. |  | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan |  | 2019-09-13
[6 empty] | Issue Actual |  | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02635
Return Date
Owner Cmmt*
| CV | OL1-2K26-0011 | Major Underground Networks - Zone 5U - Cooling Water Unit - Ex Doc Client Ref OL1-2K36-0011 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. |  | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan |  | 2019-09-13
[6 empty] | Issue Actual |  | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02635
Return Date
Owner Cmmt*
| CV | OL1-2K26-0012 | Major Underground Networks - Zone 5W - Waste Water Treatment - Ex Doc Client Ref OL1-2K36-0012 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. |  | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan |  | 2019-09-13
[6 empty] | Issue Actual |  | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02635
Return Date
Owner Cmmt*
| CV | OL1-2K26-0014 | Major Underground Networks Zone 0C - Common Area - Ex Doc Client Ref OL1-2K36-0014 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. |  | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan |  | 2019-09-13
[6 empty] | Issue Actual |  | 2019-09-13
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02635
Return Date
Owner Cmmt*
| CV | OL1-2K26-0020 | Interface Point Layout |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
[6 empty] | Revised Plan | 2019-09-25
[6 empty] | Issue Actual | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02688
Return Date
Owner Cmmt*
| CV | OL1-2K26-1000 | Major Underground Networks- Ex Doc Client Ref OL1-2K36-1000 |  |  | Purpose** | IFR | IDD
[6 empty] | Rev. |  | B
[6 empty] | Issue Plan | 2019-06-18 | 2019-12-20
Revised Plan
Issue Actual
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02855
Return Date
Owner Cmmt*
| CV | OL1-2K26-1041 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE OC - COMMON AREA |  |  | Purpose** | IFR | IFC | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-15 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
[6 empty] | Revised Plan | 2019-10-10 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02790
Return Date
Owner Cmmt*
| CV | OL1-2K26-1042 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE OC - COMMON AREA |  |  | Purpose** | IFR | IFC | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-15 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
[6 empty] | Revised Plan | 2019-10-10 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02790
Return Date
Owner Cmmt*
| CV | OL1-2K26-1043 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE OC - COMMON AREA |  |  | Purpose** | IFR | IFC | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-15 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
[6 empty] | Revised Plan | 2019-10-10 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02790
Return Date
Owner Cmmt*
| CV | OL1-2K26-1044 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE OC - COMMON AREA |  |  | Purpose** | IFR | IFC | IFC1 | IFC2 | IFC3
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-15 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
[6 empty] | Revised Plan | 2019-10-10 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02790
Return Date
Owner Cmmt*
| CV | OL1-2K26-1050 | INSTALLATION DWG-DETAILS- ZONE 0C |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
[6 empty] | Revised Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1060 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE 0M |  |  | Purpose** | IFR | IFC | IFC1 | IFC2 | IFC3
Rev.
[6 empty] | Issue Plan | 2019-12-15 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
[6 empty] | Revised Plan | 2019-12-15 | 2020-02-01 | 2020-05-01 | 2020-08-01 | 2020-11-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1070 | INSTALLATION DWG-DETAILS - ZONE 0M |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
[6 empty] | Revised Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1100 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE 1B |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
[6 empty] | Revised Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1110 | INSTALLATION DWG-DETAILS - ZONE 1B |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
[6 empty] | Revised Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1120 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE 2A |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
[6 empty] | Revised Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1130 | INSTALLATION DWG-DETAILS - ZONE 2A |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
[6 empty] | Revised Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1140 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE 2B |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
[6 empty] | Revised Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1150 | INSTALLATION DWG-DETAILS - ZONE 2B |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
[6 empty] | Revised Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1160 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE 2C |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
[6 empty] | Revised Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1170 | INSTALLATION DWG-DETAILS - ZONE 2C |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
[6 empty] | Revised Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1180 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE 2D |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
[6 empty] | Revised Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1190 | INSTALLATION DWG-DETAILS - ZONE 2D |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
[6 empty] | Revised Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1200 | GRADING UNDERGROUND AND FOUNDATION PLAN - ZONE 2E |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
[6 empty] | Revised Plan | 2019-10-16 | 2019-12-16 | 2020-05-13 | 2020-07-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1210 | INSTALLATION DWG-DETAILS - ZONE 2E |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
[6 empty] | Revised Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1270 | INSTALLATION DWG-DETAILS - ZONE 5F |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
[6 empty] | Revised Plan | 2020-02-07 | 2020-04-07 | 2020-06-05 | 2020-09-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1360 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1380 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1400 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1420 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1440 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1460 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1480 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1500 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1520 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1540 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1560 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1580 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1600 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1620 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1640 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1660 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1680 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1700 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1720 | TRENCHES LAYOUTS AND DETAILS FOR CLOSED DRAIN SYSTEM |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1740 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1780 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1800 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1820 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1860 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1900 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1940 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1960 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-1980 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-2000 | TRENCHES/DUCT BANK |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K26-2020 | CHANNELS |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
[6 empty] | Revised Plan | 2020-03-15 | 2020-10-15 | 2020-11-14 | 2020-12-14
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K27 Road and Drainage Layouts
| CV | OL1-2K27-0001 | Roads Paving And Finishing Layout |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2019-03-18 | 2020-09-29
[6 empty] | Issue Actual | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01074
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K27-0001-SH.001 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0001-SH.002 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0002 | ROADS , PAVING AND FINISHING LAYOUT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0004 | Roads Paving And Finishing Layout |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan |  | 2020-09-29
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02854
Return Date
Owner Cmmt*
| CV | OL1-2K27-0005 | ROADS , PAVING AND FINISHING LAYOUT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0006 | ROADS , PAVING AND FINISHING LAYOUT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0008-SH.001 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0008-SH.002 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0008-SH.003 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0008-SH.004 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0009-SH.001 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0009-SH.002 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0009-SH.003 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0009-SH.004 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.001 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.002 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.003 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.004 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.005 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 005 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.006 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 006 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.007 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 007 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.008 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 008 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.009 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 009 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.010 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 010 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.011 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 011 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0010-SH.012 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 012 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0011-SH.001 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0011-SH.002 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012-SH.001 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 001 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
[6 empty] | Revised Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012-SH.002 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 002 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
[6 empty] | Revised Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012-SH.003 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 003 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
[6 empty] | Revised Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012-SH.004 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 004 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
[6 empty] | Revised Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012-SH.005 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 005 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
[6 empty] | Revised Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012-SH.006 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 006 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
[6 empty] | Revised Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012-SH.007 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 007 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
[6 empty] | Revised Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0012-SH.008 | ROADS , PAVING AND FINISHING LAYOUT - Sh. 008 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
[6 empty] | Revised Plan | 2020-07-10 | 2020-09-01 | 2020-10-01 | 2020-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-0014 | ROADS , PAVING AND FINISHING LAYOUT - ZONE 0C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K27-xxxx | ROADS , PAVING AND FINISHING LAYOUT |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-15 | 2020-09-29
[6 empty] | Revised Plan | 2020-05-15 | 2020-09-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K28 Fireproofing Plan
Category Code: K30 General Arrangement for Architectural drawings of Buildings
| CV | OL1-2K30-0001 | Building List |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-09
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02707
Return Date
Owner Cmmt*
| CV | OL1-2K30-0002 | Electrical SUB-E And FAR-E - Architectural Ground Floor Keyplan- Ex Ground Floor Plan |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LSPA1-T-CV-02567
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0003 | Electrical SUB-E And FAR-E - Architectural First Floor Keyplan- Ex First Floor Plan |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LSPA1-T-CV-02567
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0004 | Electrical SUB-E And FAR-E - Architectural Roff Floor Keyplan -Ex Roof Floor Plan |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LSPA1-T-CV-02567
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0005 | Electrical SUB-E And FAR-E - Architectural Sections A - D -Ex Sections View |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LSPA1-T-CV-02567
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0006 | Electrical SUB-E And FAR-E - Architectural Sections B - C- Ex Section D and Elevation 1 View |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LSPA1-T-CV-02567
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0007 | Electrical SUB-E And FAR-E - Architectural Elevations 1 And 2 -Ex Elevations View |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LSPA1-T-CV-02567
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0008 | Electrical SUB-E And FAR-E - Architectural Elevations 3 And 4 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02567
Return Date
Owner Cmmt*
| CV | OL1-2K30-0009 | Electrical SUB-E And FAR-E - Architectural Ground Floor Plan Part 1 of 2 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02567
Return Date
Owner Cmmt*
| CV | OL1-2K30-0010 | Electrical SUB-E And FAR-E - Architectural Ground Floor Plan Part 2 of 2 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02567
Return Date
Owner Cmmt*
| CV | OL1-2K30-0010-SH.001 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - PLUMBING DWGS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0010-SH.002 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - PLUMBING DWGS - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0011 | Electrical SUB-E And FAR-E - Architectural First Floor Plan Part 1 of 2 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02567
Return Date
Owner Cmmt*
| CV | OL1-2K30-0012 | Electrical SUB-E And FAR-E - Architectural First Floor Plan Part 2 of 2 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02567
Return Date
Owner Cmmt*
| CV | OL1-2K30-0013 | Electrical SUB-E And FAR-E - Architectural Roof Floor Plan Part 1 of 2 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02567
Return Date
Owner Cmmt*
| CV | OL1-2K30-0014 | Electrical SUB-E And FAR-E - Architectural Roof Floor Plan Part 2 of 2 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-05
[6 empty] | Issue Actual | 2019-09-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02567
Return Date
Owner Cmmt*
| CV | OL1-2K30-0015 | Electrical SUB-C And FAR-2 - Architectural Ground Floor Plan |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LPSA1-T-CV-02465
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0016 | Electrical SUB-C And FAR-2 - Architectural First Floor Plan |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LPSA1-T-CV-02465
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0017 | Electrical SUB-C And FAR-2 - Architectural Roof Floor Plan |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LPSA1-T-CV-02465
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0018 | Electrical SUB-C And FAR-2 - Architectural Sections |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LPSA1-T-CV-02465
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0019 | Electrical SUB-C And FAR-2 - Architectural Elevations |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2020-03-29 |  | 2020-05-13
[6 empty] | Revised Plan | 2019-03-22 |  | 2020-05-13
[6 empty] | Issue Actual | 2019-03-22 | 2019-08-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LPSA1-T-CV-02465
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0025-SH.001 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - PLUMBING DWGS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0025-SH.002 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - PLUMBING DWGS - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K30-0030 | Gatehouse A - Architectural Plans An Schedules |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-11-28 |  | 2020-01-28
[6 empty] | Revised Plan | 2019-03-15 |  | 2020-01-28
[6 empty] | Issue Actual | 2019-03-15 | 2019-08-27
[6 empty] | Transmittal no. | TPSL-LSPA1-T-CV-01064 | TPSK-LSPA1-T-CV-02484
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0031 | Gatehouse A - Architectural Elevations And Sections |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-11-28 |  | 2020-01-28
[6 empty] | Revised Plan | 2019-03-15 |  | 2020-01-28
[6 empty] | Issue Actual | 2019-03-15 | 2019-08-27
[6 empty] | Transmittal no. | TPSL-LSPA1-T-CV-01064 | TPSK-LSPA1-T-CV-02484
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0032 | Gatehouse A - Architectural Isometric Views |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-11-28 |  | 2020-01-28
[6 empty] | Revised Plan | 2019-03-15 |  | 2020-01-28
[6 empty] | Issue Actual | 2019-03-15 | 2019-08-27
[6 empty] | Transmittal no. | TPSL-LSPA1-T-CV-01064 | TPSK-LSPA1-T-CV-02484
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0038 | Gatehouse A - Architectural Plans Elevations Sections And Schedules |  | Class 1 | Purpose** | IFR | IFR
[6 empty] | Rev. | A | B
Issue Plan
[6 empty] | Revised Plan | 2019-03-15
[6 empty] | Issue Actual | 2019-03-15 | 2019-08-27
[6 empty] | Transmittal no. | TPSL-LSPA1-T-CV-01064 | TPSK-LSPA1-T-CV-02484
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0040 | Operation Tool Room - Architectural Plans And Schedules |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-12-16 |  | 2020-02-15
[6 empty] | Revised Plan | 2019-03-15 |  | 2020-02-15
[6 empty] | Issue Actual | 2019-03-15 | 2019-08-27
[6 empty] | Transmittal no. | TPSL-LSPA1-T-CV-01064 | TPSK-LSPA1-T-CV-02484
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0041 | Operation Tool Room - Architectural Elevations And Sections |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-12-16 |  | 2020-02-15
[6 empty] | Revised Plan | 2019-03-15 |  | 2020-02-15
[6 empty] | Issue Actual | 2019-03-15 | 2019-08-27
[6 empty] | Transmittal no. | TPSL-LSPA1-T-CV-01064 | TPSK-LSPA1-T-CV-02484
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0042 | Operation Tool Room - Architectural Isometric Views |  |  | Purpose** | IFR | IFR | IFC
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-12-16 |  | 2020-02-15
[6 empty] | Revised Plan | 2019-03-15 |  | 2020-02-15
[6 empty] | Issue Actual | 2019-03-15 | 2019-08-27
[6 empty] | Transmittal no. | TPSL-LSPA1-T-CV-01064 | TPSK-LSPA1-T-CV-02484
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0050 | Electrical SUB-F And FAR-FL - Architectural Plans And Schedules |  |  | Purpose** | IFR | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-17 |  | 2019-08-30
[6 empty] | Revised Plan | 2019-03-22
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LSPA1-T-CV-02560
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-0051 | Electrical SUB-F and FAR-FL - Architectural Sections and Elevations |  |  | Purpose** | IFR | IFR | IDD
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-17 |  | 2019-08-30
[6 empty] | Revised Plan | 2019-03-22
[6 empty] | Issue Actual | 2019-03-22 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01122 | TPSK-LSPA1-T-CV-02560
[6 empty] | Return Date | 2019-05-30
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K30-5014 | BUILDING 3D MODEL VIEWS - SUB-C & FAR-2 |  |  | Purpose** | IFR | IDD
Rev.
[6 empty] | Issue Plan | 2019-07-28 | 2019-09-04
[6 empty] | Revised Plan |  | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K31 General Arrangement for Civil Concrete Works drawings
| CV | OL1-2K31-0001 | FOUNDATION FOR 10-TK-5670 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0002 | FOUNDATION FOR 10-PK-5628, 10-PIT-5628, P-10-5628A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0003 | FOUNDATION FOR 10-PK-1950, 10-C-1950A/B, 10-E-1951A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0004 | Foundation For 10-E-2765 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01522
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0005 | Foundation For 10-E-2585 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01206
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0006 | FOUNDATION FOR SKID 10-P-2801A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0011 | FOUNDATION FOR 10-F-5610 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0018 | Foundation For 10-D-2136 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-09-10 | 2020-06-15
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02582
Return Date
Owner Cmmt*
| CV | OL1-2K31-0028 | Foundation For Pumps 10-P-2106 A-B-C |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02815
Return Date
Owner Cmmt*
| CV | OL1-2K31-0029 | FOUNDATION FOR PUMPS 10-P-2026A/B, 10-P-2126A/B, 10-P-2046A/B, 10-P-5140A/B, 10-P-2146A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0030 | Foundation For Pumps 10-P-2006 A-B-C |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02815
Return Date
Owner Cmmt*
| CV | OL1-2K31-0031 | Foundation For 10-F-2105-A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-28
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0032 | FOUNDATION FOR 10-F-2009A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0033 | Foundation For 10-F-2008-A-B-C |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-28
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0034 | Foundation For 10-F-2026-A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-30 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02532
Return Date
Owner Cmmt*
| CV | OL1-2K31-0035 | FOUNDATION FOR 10-F-2028A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0036 | FOUNDATION FOR 10-F-2136A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0038 | FOUNDATION FOR ANALYZER HOUSE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0040 | Foundation for 10-T-2300 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-11 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01854
[6 empty] | Return Date | 2019-08-14
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0051 | Foundation For 10-D-2210 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0052 | Foundation For 10-D-2230 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0053 | Foundation for 10-D-2405 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0054 | FOUNDATION FOR 10-D-2415 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0060 | Foundation For 10-TK-2910 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-23 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-0062 | Foundation For 10-E-2230A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0063 | Foundation For 10-E-2412 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01334
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0064 | Foundation for 10-E-2413 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01470
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0066 | Foundation For 10-E-2446 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0068 | Foundation For 10-E-2450 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0069 | FOUNDATION FOR 10-E-2470 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0070 | Foundation For 10-E-2206 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01206
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0071 | Foundation For 10-E-2210AB |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0072 | Foundation For 10-E-2220A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0073 | Foundation For 10-E-2240A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0075 | Foundation For 10-E-2305 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0077 | FOUNDATION FOR 10-E-2326 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0078 | FOUNDATION FOR PUMPS 10-P-2302A/B, 10-P-2415A/B, 10-P-2445A/B, 10-P-2304, 10-P-2306A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0079 | FOUNDATION FOR PUMPS 10-P-2200A/B, 10-P-2220A/B, 10-P-10-P-2210A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0080 | FOUNDATION PUMPS FOR 10-P-2450A/B, 10-P-2455A/B, 10-P-2620A/B, 10-P-2666A/B, 10-P-2660A/B, 10-P-2910 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0081 | FOUNDATION PUMPS FOR 10-P-2630A/B, 10-P-2310A/B, 10-P-2316A/B, 10-P-2326A/B, 10-P-2320A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0082 | Foundation For 10-F-2320A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02409
Return Date
Owner Cmmt*
| CV | OL1-2K31-0083 | Foundation For 10-F-2310A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02409
Return Date
Owner Cmmt*
| CV | OL1-2K31-0084 | FOUNDATION FOR 10-F-2306A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0085 | FOUNDATION FOR ANALYZER HOUSE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0086 | FOUNDATION FOR ANALYZER HOUSE |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0087 | FOUNDATION FOR 10-PK-2900/2902/2906 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0088 | FOUNDATION FOR 10-PK-2920 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0089 | FOUNDATION FOR 10-PK-1920 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0090 | FOUNDATION FOR 10-PK-2350 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0092 | FOUNDATION FOR SKID 10-P-2201A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0093 | Foundation For 10-F-2048-A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-28
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0094 | Foundation For 10-T-2580 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0096 | Foundation For 10-T-2570 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0097 | Foundation For 10-T-2510 And 10-T-2540 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-04 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01241
[6 empty] | Return Date | 2019-05-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0098 | Foundation For 10-T-2510 And 10-T-2540 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-04 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01241
[6 empty] | Return Date | 2019-05-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0100 | Foundation For 10-D-2411 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0101 | Foundation Vor 10-D-2480A |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0103 | Foundation for 10-D-2322 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-11 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01854
[6 empty] | Return Date | 2019-08-14
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0104 | Foundation For 10-E-1006 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0106 | Foundation For 10-D-2420A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0107 | Concrete Structure For 10-D-2880 And 10-D-2865 - Reinforcement |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-04
[6 empty] | Issue Actual | 2019-07-04
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02071
[6 empty] | Return Date | 2019-08-29
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0111 | Foundation For 10-D-2525 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-20 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01926
[6 empty] | Return Date | 2019-08-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0113 | Concrete Structure For 10-D-2880 And 10-D-2865 - Formworks |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-01
[6 empty] | Issue Actual | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02028
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0117 | Foundation For 10-E-2587 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01206
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0120 | FOUNDATION FOR 10-E-2432 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0142 | FOUNDATION FOR 10-PK-2930, 10-D-2930 AND 10-P-2930 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0143 | Foundation For 10-R-2700A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0144 | Foundation For 10-R-2620 A |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0147 | Foundation For 10-E-2666 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0148 | FOUNDATION FOR 10-F-2666A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0149 | Foundation For 10-E-2660 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01470
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0153 | Foundation for 10-T-2630 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0154 | Foundation For 10-R-2470A-B-C |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0157 | Foundation For 10-D-2460 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0158 | Foundation For 10-D-2440 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-03-28 | 2020-06-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01169
[6 empty] | Return Date | 2019-04-12
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0159 | Foundation for 10-D-1000 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
Return Date
Owner Cmmt*
| CV | OL1-2K31-0160 | Foundation For 10-E-2635 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0162 | FOUNDATION FOR 10-E-2472 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0163 | Foundation for 10-E-2474 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0164 | Foundation For 10-E-2465 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0165 | Foundation For 10-E-2460 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0166 | Foundation For 10-E-2440 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01334
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0170 | Foundation For 10-E-1000 A/B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0171 | Foundation For 10-E-1005 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01349
[6 empty] | Return Date | 2019-04-23
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0172 | FOUNDATION FOR PUMPS 10-P-5112A/B, 10-P-2714A/B, 10-P-2710A/B, 10-P-2720A/B, 10-P-2721A/B, 10-P-2910 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0173 | FOUNDATION FOR PUMPS 10-P-2724A/B, 10-P-2726A/B, 10-P-2750A/B, 10-P-2760A/B/C, 10-P-2705A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0174 | FOUNDATION FOR 10-PK-2912 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0175 | FOUNDATION FOR 10-PK-2922 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0177 | Foundation For 10-D-2705 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01522
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A4
| CV | OL1-2K31-0178 | Foundation For 10-E-2705 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01522
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0180 | Foundation For 10-D-2735 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-19 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01414
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0182 | FOUNDATION FOR 10-E-2730 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0184 | Foundation For 10-E-2755 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0185 | FOUNDATION FOR 10-E-2725A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0186 | FOUNDATION FOR 10-E-2726 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0188 | Foundation For 10-E-2702 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-27 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02004
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0189 | Foundation For 10-E-2701 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-24 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01455
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0190 | Foundation For 10-E-2706 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0195 | FOUNDATION FOR 10-E-2724 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0197 | FOUNDATION FOR 10-E-2714 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0198 | Foundation For 10-E-2882 And 10-E-2884 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01206
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0200 | Foundation For 10-E-2100 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-09 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-0201 | Foundation For 10-TK-2320 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02409
Return Date
Owner Cmmt*
| CV | OL1-2K31-0203 | Foundation For 10-D-1910 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01470
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0205 | FOUNDATION FOR 10-PK-5914 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0206 | FOUNDATION FOR 10-PK-5912 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0208 | FOUNDATION FOR IGNITION SYSTEM |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0210 SH001 | Foundation For 10-TK-3900 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02152
Return Date
Owner Cmmt*
| CV | OL1-2K31-0210 SH002 | Foundation For 10-TK-3900 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-07-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02152
Return Date
Owner Cmmt*
| CV | OL1-2K31-0210-SH001 | FOUNDATION FOR 10-TK-3900 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0210-SH002 | FOUNDATION FOR 10-TK-3900 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0211 | Foundation For 10-T-3000 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01896
[6 empty] | Return Date | 2019-08-19
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0212 | Foundation For 10-T-3040 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-09 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02741
Return Date
Owner Cmmt*
| CV | OL1-2K31-0213 | Foundation For 10-T-3020 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-10-09 | 2020-06-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02741
Return Date
Owner Cmmt*
| CV | OL1-2K31-0215 | Foundation For 10-T-3030 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01896
[6 empty] | Return Date | 2019-08-19
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0216 | Foundation For 10-T-3050 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01898
[6 empty] | Return Date | 2019-08-19
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0219 | Foundation For 10-T-3080 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01898
[6 empty] | Return Date | 2019-08-19
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0220 | Foundation For 10-T-3070 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02047
[6 empty] | Return Date | 2019-09-03
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0222 | FOUNDATION FOR 10-D-3908 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-06 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02340
Return Date
Owner Cmmt*
| CV | OL1-2K31-0223 | FOUNDATION FOR 10-D-3902 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-06 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02340
Return Date
Owner Cmmt*
| CV | OL1-2K31-0224 | FOUNDATION FOR 10-D-3904 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-06 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02340
Return Date
Owner Cmmt*
| CV | OL1-2K31-0225 | FOUNDATION FOR 10-D-3906 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-06 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02340
Return Date
Owner Cmmt*
| CV | OL1-2K31-0226 | Foundation For 10-D-3180 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02047
[6 empty] | Return Date | 2019-09-03
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0227 | Foundation For 10-D-3110 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02047
[6 empty] | Return Date | 2019-09-04
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0235 | FOUNDATION FOR 10-E-3098 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0237 | Foundation For 10-E-3045 A/B/C/D |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02439
Return Date
Owner Cmmt*
| CV | OL1-2K31-0238 | Foundation For 10-E-3044 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02439
Return Date
Owner Cmmt*
| CV | OL1-2K31-0242 | Foundation For 10-E-3070 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02439
Return Date
Owner Cmmt*
| CV | OL1-2K31-0243 | FOUNDATION FOR PUMPS 10-P-2570A/B, 10-P-2575A/B, 10-P-2586A/B, 10-P-2647, 10-P-2646A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0244 | FOUNDATION FOR PUMPS 10-P-2802A/B, 10-P-2805A/B, 10-P-2815, 10-P-2855A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0245 | FOUNDATION FOR PUMPS 10-P-3046A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0246 | FOUNDATION FOR PUMPS 10-P-3045A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0247 | FOUNDATION FOR PUMPS 10-P-3026A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0248 | FOUNDATION FOR PUMPS 10-P-3056A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0256 | FOUNDATION FOR 10-PK-2904 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0259 | Foundation for 10-PK-5355 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0260 | FOUNDATION FOR 10-PK-5394 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0261 | FOUNDATION FOR 10-PK-5901 and 10-PK-5905 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0262 | FOUNDATION FOR 10-PK-5397 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0263 | FOUNDATION FOR 10-PK-5392 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0264 | FOUNDATION FOR 10-PK-5390 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0265 | FOUNDATION FOR 10-PK-5950 and 10-PK-5955 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0266 | Foundation For 10-D-3126 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02047
[6 empty] | Return Date | 2019-09-03
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0267 | Foundation For 10-D-5550 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-11 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01852
Return Date
Owner Cmmt*
| CV | OL1-2K31-0268 | Foundation For 10-D-5500 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-20 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01923
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0269 | FOUNDATION FOR 10-D-5510 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0270 | FOUNDATION FOR 10-D-5513 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0271 | FOUNDATION FOR 10-D-5515 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0272 | FOUNDATION FOR 10-D-5520 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
Return Date
Owner Cmmt*
| CV | OL1-2K31-0273 | FOUNDATION FOR 10-C-5520A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0274 | FOUNDATION FOR 10-PK-5125, 10-D-5125A/B, 10-F-5125A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0275 | FOUNDATION FOR 10-E-5513 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-21 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01687
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0278 | Foundation For 10-TK-5640 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-10 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0278 SH001 | Foundation For 10-TK-5640 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-20 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-20
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01923
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0279 | FOUNDATION FOR 10-TK-5675A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0280 | FOUNDATION FOR 10-TK-5676 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0282 | Foundation For 10-TX-C-2550 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-22 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02203
[6 empty] | Return Date | 2019-10-14
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0283 | FOUNDATION FOR 10-C-5650A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0284 | FOUNDATION FOR 10-E-5510 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-05-21
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01687
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0288 | FOUNDATION FOR 10-PK-5692 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0289 | FOUNDATION FOR 10-PK-5693 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0290 | FOUNDATION FOR 10-PK-5694 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0291 | FOUNDATION FOR 10-PK-5671 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0292 | FOUNDATION FOR 10-PK-5672 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0293 | FOUNDATION FOR 10-PK-5697 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0294 | FOUNDATION FOR 10-PK-5690 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0295 | FOUNDATION FOR 10-PK-5691 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0298 | FOUNDATION FOR 10-D-5646 AND 10-X-5646 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0299 | FOUNDATION FOR 10-D-5644 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0300 | FOUNDATION FOR 10-PK-5644 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0301 | FOUNDATION FOR 10-PK-5653 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0302 | FOUNDATION FOR 10-PK-5650 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0303-001 | Foundation For10-TK-5110 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01886
[6 empty] | Return Date | 2019-08-19
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0303-002 | Foundation For 10-TK-5110 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01886
Return Date
Owner Cmmt*
| CV | OL1-2K31-0304-001 | Foundation For 10-TK-5120 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01886
[6 empty] | Return Date | 2019-08-19
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0304-002 | Foundation For 10-TK-5120 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01886
[6 empty] | Return Date | 2019-08-19
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0305 | FOUNDATION FOR 10-TK-5130 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0307 | Foundation For 10-D-5400 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01522
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0308 | Foundation For 10-D-5114 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-24 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01455
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0309 | Foundation For 10-D-5112 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-24 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01455
[6 empty] | Return Date | 2019-05-27
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0310 | Foundation for 10-D-5552 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-10 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0311 | Foundation for 10-D-5565 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-10 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0313 | Foundation For 10-E-5113 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0314 | Foundation For 10-E-5552 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-10 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01837
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0315 | FOUNDATION FOR 10-E-5110 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0316 | FOUNDATION FOR 10-P-5100A/B/C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0317 | FOUNDATION FOR 10-P-5102A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0318 | FOUNDATION FOR 10-PK-5191 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0319 | FOUNDATION FOR 10-PK-5192 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0320 | FOUNDATION FOR 10-PK-5115, 10-F-5115A/B/C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0321 | FOUNDATION FOR 10-PK-5125, 10-D-5125A/B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0323 | FOUNDATION FOR 10-TK-5900 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-14 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01647
[6 empty] | Return Date | 2019-07-16
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-0325 | FOUNDATION FOR 10-PK-5695 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0326 | FOUNDATION FOR 10-PK-5696 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0328 | Retaining Wall For 10-Tk-5900 - Plan And Sections - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-09-19 | 2020-06-02
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02660
Return Date
Owner Cmmt*
| CV | OL1-2K31-0329 | Retaining Wall For 10-Tk-5900 - Sections - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-09-19 | 2020-06-02
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02660
Return Date
Owner Cmmt*
| CV | OL1-2K31-0330 | Retaining Wall For 10-Tk-5950 - Plan And Section - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-09-19 | 2020-06-02
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02660
Return Date
Owner Cmmt*
| CV | OL1-2K31-0331 | Foundation And Elevation Of Retaining Wall For 10-TK-2320 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-09-10 | 2020-06-02
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02584
Return Date
Owner Cmmt*
| CV | OL1-2K31-0332 | Foundation And Elevation Of Retaining Wall For 10-TK-2910 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-09-10 | 2020-06-02
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02590
Return Date
Owner Cmmt*
| CV | OL1-2K31-0333 | Retaining Wall For 10-Tk-3900 - Plan & Sections - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-09-23 | 2020-06-02
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02675
Return Date
Owner Cmmt*
| CV | OL1-2K31-0334 | Retaining Wall For 10-Tk-3900 - Sections - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-09-19 | 2020-06-02
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02660
Return Date
Owner Cmmt*
| CV | OL1-2K31-0336 | Foundation For 10-TK-2300 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-23 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-0338 | Foundation For 10-E-2441 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-04-15
[6 empty] | Issue Actual | 2019-04-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01334
[6 empty] | Return Date | 2019-06-07
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0339 | Foundation for 10-E-2442 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-17 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01373
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0340 | Foundation For 10-E-2405 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-05-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-05-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01663
[6 empty] | Return Date | 2019-06-13
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0341 | Foundation For 10-D-1912 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-04-25 | 2020-06-15
[6 empty] | Issue Actual | 2019-04-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01470
[6 empty] | Return Date | 2019-05-17
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0342 | Olefins Plant - Preliminary Field Pile Trial - Layout And Programme |  |  | Purpose** | IFR | IMP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-30 | 2019-07-29
[6 empty] | Revised Plan | 2019-05-31
[6 empty] | Issue Actual | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01769
[6 empty] | Return Date | 2019-07-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0343 | Bored Piles For Preliminary Test |  |  | Purpose** | IFR | IMP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-30 | 2019-07-29
[6 empty] | Revised Plan | 2019-05-31
[6 empty] | Issue Actual | 2019-05-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01769
[6 empty] | Return Date | 2019-07-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-0344 | Foundation For 10-E-3018 A/B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-16 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-16
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02439
Return Date
Owner Cmmt*
| CV | OL1-2K31-0345 | Foundation for 10-D-5553 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-27 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0346 | Foundation Details for Pipe Rack 10-PRK-5U01 (Formwork & Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0347 | Foundation Details for Pipe Rack 10-PRK-5U01 (Formwork & Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0348 | Foundation Details for Piperack 10-PRK-5U01 (Formwork & Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0349 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0350 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0351 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0352 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beam Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0353 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beam Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0354 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beams Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0355 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beam Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0356 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Beam Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0357 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Column Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0358 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Column Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0359 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Column Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0360 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Corbel Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0361 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Steel Bracing Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | IFR
Return Date
Owner Cmmt*
| CV | OL1-2K31-0362 | Precast Concrete for Pipe Rack 10-PRK-5U01 - Steel Bracing Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-0365 | Foundation for Pipe Bridge 10-PRK-5W01 - Plan & Detail |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02500
Return Date
Owner Cmmt*
| CV | OL1-2K31-0366 | Foundation for Pipe Bridge 10-PRK-5W01 - Detail |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02500
Return Date
Owner Cmmt*
| CV | OL1-2K31-0367 | CONCRETE BASIN 10-PIT-5620A/B/C - FORMWORK - SECTIONS - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-12-24 | 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0368 | CONCRETE BASIN 10-PIT-5620A/B/C - REINFORCEMENT - PLANS - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-12-24 | 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0369 | CONCRETE BASIN 10-PIT-5620A/B/C - REINFORCEMENT - SECTIONS - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-12-24 | 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0370 | CONCRETE BASIN 10-PIT-5620A/B/C - REINFORCEMENT - SECTIONS - Sh. 005 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-12-24 | 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-0372 | Foundation Details For Piperack 10-Prk-5T01 (Formwork & Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-10 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02601
Return Date
Owner Cmmt*
| CV | OL1-2K31-0373 | Foundation Details For Piperack 10-Prk-5T01 (Formwork & Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-10 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02601
Return Date
Owner Cmmt*
| CV | OL1-2K31-0374 | Foundation For Pipe Rack 10-Prk-5T01 - Tie Beams Details |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-10 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02601
Return Date
Owner Cmmt*
| CV | OL1-2K31-0376 | RETAINING WALL FOR 10-TK-5950 - SECTION - REINFORCEMENT |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2019-10-10 | 2020-06-02
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02792
Return Date
Owner Cmmt*
| CV | OL1-2K31-0390 | Foundation For Pipe Bridge 10-Prk-5T02 - Plan Sections & Details |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-12 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02631
Return Date
Owner Cmmt*
| CV | OL1-2K31-0391 | Spun Piles For Preliminary Test |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-13
[6 empty] | Issue Actual | 2019-09-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02636
Return Date
Owner Cmmt*
| CV | OL1-2K31-0450 | Olefins Plant - Preliminary Field Pile Trial - PHC Piles - Layout And Programme |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02670
Return Date
Owner Cmmt*
| CV | OL1-2K31-1000 | Foundation And Elevation Of Pipe Rack 10-PRK-0P01 - Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-05-28 | 2019-11-18
[6 empty] | Issue Actual | 2019-05-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1001 | Foundation And Elevation Of Pipe Rack 10-PRK-0P01 - Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-05-28 | 2019-11-18
[6 empty] | Issue Actual | 2019-05-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1020 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - 3D View |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1021 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1022 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1023 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1024 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1025 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1026 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1027 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1028 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1029 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1030 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-28 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-28 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01747 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-06-19
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1031 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-05-31 | 2019-10-10 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-05-31 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01771 | TPSK-LSPA1-T-CV-02770
[6 empty] | Return Date | 2019-07-12
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1032 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Steel Bracings Details |  | Class 1 | Purpose** | IFC
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02800
Return Date
Owner Cmmt*
| CV | OL1-2K31-1033 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P01 - Steel Bracings Details |  | Class 1 | Purpose** | IFC
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-10-10
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02770
Return Date
Owner Cmmt*
| CV | OL1-2K31-1040 | Foundation And Elevation Of Piperack 10-PRK-0P02 - Formwork And Reinforcement - |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1041 | Foundation And Elevation Of Piperack 10-PRK-0P02 - Formwork And Reinforcement - |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1060 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - 3D View - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1061 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Plans - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1062 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Plans - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1063 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1064 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1065 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1066 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Elevations - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1067 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1068 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1069 | Precast Concrete Elevation For Piperack 10-PRK-0P02 -Columns - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1070 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1071 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1072 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Columns - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1073 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1074 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1075 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1076 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1077 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Beams - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1078 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A1
| CV | OL1-2K31-1079 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A1
| CV | OL1-2K31-1080 | Foundation And Elevation Of Pipe Rack 10-PRK-0P03 - Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1081 | Foundation And Elevation Of Pipe Rack 10-PRK-0P03 - Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1100 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - 3D View |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1101 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1102 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1103 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1104 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1105 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1106 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1107 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1108 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1109 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1110 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1111 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1112 | Precast Concrete Elevation For Pipe Rack 10-PRK-0P03 - Bracings |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-29 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02263
Return Date
Owner Cmmt*
| CV | OL1-2K31-1120-SH.001 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-3A01 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1120-SH.002 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-3A01 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1120-SH.003 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-3A01 - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.001 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 001 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.002 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 002 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.003 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 003 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.004 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 004 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.005 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 005 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.006 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 006 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.007 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 007 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.008 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 008 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.009 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 009 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1140-SH.010 | PRECAST CONCRETE ELEVATION FOR PIPE RACK 10-PRK-3A01 - Sh. 010 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1160 | Foundation Plan and Details of Pipe Rack 10-PRK-5U01 (Formwork & Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-1180 | Precast Concrete of Pipe Rack 10-PRK-5U01 - 3D View |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-27 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02493
Return Date
Owner Cmmt*
| CV | OL1-2K31-1200 | Piperack 10-PRK-2D01 Foundations -Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-10 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02584
Return Date
Owner Cmmt*
| CV | OL1-2K31-1201 | Piperack 10-PRK-2D01 Foundations -Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-10 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02584
Return Date
Owner Cmmt*
| CV | OL1-2K31-1220 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Isometric 3D View |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1221 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1222 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1223 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1224 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1225 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1226 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1227 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1228 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1229 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1230 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1231 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1232 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1233 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1234 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1235 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1236 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Bracings |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1237 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Bracings |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1238 | Precast Concrete Elevation For Pipe Rack 10-PRK-2D01 - Bracings |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan |  | 2019-11-18 | 2019-12-18 | 2020-01-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02672
Return Date
Owner Cmmt*
| CV | OL1-2K31-1240 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-1241 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-1242 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-1243 | Foundations Pipe Rack 10-PRK-2E01 - Formworks And Reinforcements |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-07-30 | 2019-11-18
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-1260 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - 3D View |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1261 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1262 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1263 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1264 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1265 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1266 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1267 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1268 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1269 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1270 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1271 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1272 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1273 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1274 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1275 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1276 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1277 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1278 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1279 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-1280 | Piperack 10-PRK-2A01 Foundation (Formwork and Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1281 | Piperack 10-PRK-2A01 Foundation (Formwork and Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1300 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Isometric 3D View |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1301 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1302 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1303 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1304 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1305 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1306 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1307 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1308 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1309 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1310 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1311 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1312 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1313 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1314 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1315 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1316 | Precast Concrete Elevation For Piperack 10-PRK-2A01 Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02383
Return Date
Owner Cmmt*
| CV | OL1-2K31-1320 | Concrete Basin 10-Pit-3190 - Plan & Details - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-09-23 | 2020-01-24
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02675
Return Date
Owner Cmmt*
| CV | OL1-2K31-1321 | Concrete Basin 10-Pit-3190 - Sections - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-09-23 | 2020-01-24
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02675
Return Date
Owner Cmmt*
| CV | OL1-2K31-1322 | Concrete Basin 10-Pit-3190 - Plan & Sections - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-09-23 | 2020-01-24
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02675
Return Date
Owner Cmmt*
| CV | OL1-2K31-1331 | Foundation And Elevation Of Pipe Rack 10-PRK-2B01 - Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-10-10 | 2019-11-18
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02760
Return Date
Owner Cmmt*
| CV | OL1-2K31-1332 | Foundation And Elevation Of Pipe Rack 10-PRK-2B01 - Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-10-10 | 2019-11-18
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02760
Return Date
Owner Cmmt*
| CV | OL1-2K31-1340 | Foundation And Elevation Of Pipe Rack 10-PRK-2B02 - Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02648
Return Date
Owner Cmmt*
| CV | OL1-2K31-1360 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - 3D View |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1361 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1362 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1363 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1364 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1365 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1366 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1367 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1368 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1369 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1370 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1371 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1372 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1373 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1374 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 – Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1375 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B01 – Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02753
Return Date
Owner Cmmt*
| CV | OL1-2K31-1380 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - 3D View |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1381 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1382 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1383 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1384 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Elevations |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1385 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1386 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1387 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1388 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1389 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1390 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1391 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1392 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1393 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1394 | Precast Concrete Elevation For Pipe Rack 10-PRK-2B02 - Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1400 | FOUNDATION AND ELEVATION OF PIPE RACK 10-PRK-2C01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1420 | Foundations Pipe Rack 10-PRK-2C02 - (Formworks And Reinforcements) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-05 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02330
Return Date
Owner Cmmt*
| CV | OL1-2K31-1421 | Foundations Pipe Rack 10-PRK-2C02 - (Formworks And Reinforcements) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-05 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02330
Return Date
Owner Cmmt*
| CV | OL1-2K31-1460 | Foundation And Elevation For 10-STR-2B03 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-08-15 | 2020-05-13
[6 empty] | Issue Actual | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02424
Return Date
Owner Cmmt*
| CV | OL1-2K31-1480 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - 3D View |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1481 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1482 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Plans |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1483 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Elevation A/B |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1484 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Elevation 6 To 13 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1485 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Elevation 6 To 13 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1486 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1487 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1488 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Columns |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1489 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1490 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1491 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1492 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1493 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1494 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1495 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1496 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1497 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1498 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1499 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1500 | Foundation For Piperack 10-Prk-5T01 - Plan (Formwork) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-09-10 | 2019-11-18
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02601
Return Date
Owner Cmmt*
| CV | OL1-2K31-1520 | CONCRETE BASIN 10-PIT-5620A/B/C - FORMWORK - PLANS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-12-24 | 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1540 | Foundation For Pipe Rack 10-PRK-5F01 - Plan |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-10-15 | 2019-11-18
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02839
Return Date
Owner Cmmt*
| CV | OL1-2K31-1541 | Foundation For Pipe Rack 10-PRK-5F01 - Pilecap PC2A - Formwork & Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-10-15 | 2019-11-18
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02839
Return Date
Owner Cmmt*
| CV | OL1-2K31-1542 | Foundation For Pipe Rack 10-PRK-5F01 - Pilecap PC2 - Formwork & Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-10-15 | 2019-11-18
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02839
Return Date
Owner Cmmt*
| CV | OL1-2K31-1543 | Foundation For Pipe Rack 10-PRK-5F01 - Pilecap PC3A - Formwork & Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18
[6 empty] | Revised Plan | 2019-10-15 | 2019-11-18
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02839
Return Date
Owner Cmmt*
| CV | OL1-2K31-1544 | Foundation For Pipe Rack 10-PRK-5F01 - Pilecap PC3 - Formwork & Reinforcement |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02839
Return Date
Owner Cmmt*
| CV | OL1-2K31-1545 | Foundation For Pipe Rack 10-PRK-5F01 - Tie Beam Details - Formwork & Reinforcement |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02839
Return Date
Owner Cmmt*
| CV | OL1-2K31-1560 | Foundation And Elevation Of Steel Structure For 10-STR-2E01 and 10-T-2440 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-09-17 | 2020-05-13
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02648
Return Date
Owner Cmmt*
| CV | OL1-2K31-1561 | Concrete Basin 10-Pit-5633 - Sections (Formwork) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-09-23 | 2020-01-24
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02675
Return Date
Owner Cmmt*
| CV | OL1-2K31-1562 | Concrete Basin 10-Pit-5633 - Plans And Details (Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-09-23 | 2020-01-24
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02675
Return Date
Owner Cmmt*
| CV | OL1-2K31-1563 | Concrete Basin 10-Pit-5633 - Sections (Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-09-23 | 2020-01-24
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02675
Return Date
Owner Cmmt*
| CV | OL1-2K31-1564 | Concrete Basin 10-Pit-5633 - Sections (Reinforcement) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-09-23 | 2020-01-24
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02675
Return Date
Owner Cmmt*
| CV | OL1-2K31-1565 | Concrete Basin 10-PIT-5633 -Plans (Formwork) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-09-24 | 2020-01-24
[6 empty] | Issue Actual | 2019-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02689
Return Date
Owner Cmmt*
| CV | OL1-2K31-1580 | FOUNDATION AND ELEVATION FOR 10-STR-2E02, 10-D-2420A/B AND 10-E-2430 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1600 | FOUNDATION AND ELEVATION FOR 10-STR-2E03 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1620 | Foundation And Elevation For 10-STR-2E04 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-10-10 | 2020-05-13
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02776
Return Date
Owner Cmmt*
| CV | OL1-2K31-1640 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D05 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1660 | FOUNDATION AND ELEVATION FOR 10-STR-2B01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1680 | FOUNDATION AND ELEVATION FOR 10-STR-2C06 - ADDED 15 APR 19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1700 | Foundation And Elevation Of Concrete Structure 10-STR-2C07 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02730
Return Date
Owner Cmmt*
| CV | OL1-2K31-1701 | Foundation And Elevation Of Concrete Structure 10-STR-2C07 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02730
Return Date
Owner Cmmt*
| CV | OL1-2K31-1702 | Foundation And Elevation Of Concrete Structure 10-STR-2C07 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02730
Return Date
Owner Cmmt*
| CV | OL1-2K31-1720 | FOUNDATION AND ELEVATION FOR 10-STR-2B04 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1740 | Foundation And Elevation Of Steel Structure For 10-STR-2B02 & 10-T-2330 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02712
Return Date
Owner Cmmt*
| CV | OL1-2K31-1760 | FOUNDATION AND ELEVATION FOR 10-STR-2E05 - ADDED 15 APR 19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1780 | Foundation For Steel Shelter 10-SHT-2D01 - Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-06-11 | 2020-05-13
[6 empty] | Issue Actual | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01858
[6 empty] | Return Date | 2019-08-16
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-1800 | Foundation Of Steel Structure For 10-SHT-2D02 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-08-01 | 2020-05-13
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02304
Return Date
Owner Cmmt*
| CV | OL1-2K31-1820 | Foundation And Elevation Of Concrete Structure 10-STR-2C01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1821 | Foundation And Elevation Of Concrete Structure 10-STR-2C01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-09-18 | 2020-05-13
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1822 | Foundation And Elevation Of Concrete Structure 10-STR-2C01 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-09-18 | 2020-05-13
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02655
Return Date
Owner Cmmt*
| CV | OL1-2K31-1840 | FOUNDATION AND ELEVATION FOR 10-STR-2C02 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1860 | Foundation And Elevation Of Steel Structure For 10-STR-2C03 & 10-T-2720 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-09-17 | 2020-05-13
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-1880 | FOUNDATION AND ELEVATION FOR 10-STR-2C04 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1900 | FOUNDATION AND ELEVATION FOR 10-STR-2C05 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1920 | FOUNDATION AND ELEVATION FOR 10-SHT-2C01 - ADDED 15 APR 19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1940 | FOUNDATION AND ELEVATION FOR 10-SHT-1B01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-1960 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-07-23 | 2020-05-13
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-1961 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-07-23 | 2020-05-13
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-1962 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-07-23 | 2020-05-13
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-1963 | Concrete Structure 10-STR-0P01 - Foundations And Elevations - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-07-23 | 2020-05-13
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-1980 | Foundation And Elevation Of Concrete Structure For 10-STR-2A01 And 10-T-2120 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-07-22 | 2020-05-13
[6 empty] | Issue Actual | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02203
[6 empty] | Return Date | 2019-10-14
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2000 | Foundation For Structure 10-STR-2A02 & 10-T-2140 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-09-10 | 2020-05-13
[6 empty] | Issue Actual | 2019-09-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02597
Return Date
Owner Cmmt*
| CV | OL1-2K31-2020 | FOUNDATION AND ELEVATION FOR 10-STR-2A03 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2040-SH.001 | FOUNDATION AND ELEVATION FOR WASTE STORAGE BUILDING - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2040-SH.002 | FOUNDATION AND ELEVATION FOR WASTE STORAGE BUILDING - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2040-SH.003 | FOUNDATION AND ELEVATION FOR WASTE STORAGE BUILDING - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2060-SH.001 | FOUNDATION AND ELEVATION FOR STORAGE SHELTER FOR CHENICALS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2060-SH.002 | FOUNDATION AND ELEVATION FOR STORAGE SHELTER FOR CHENICALS - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2080-SH.001 | FOUNDATION AND ELEVATION FOR LUBRIFICATION OIL & GREASE STORAGE - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2080-SH.002 | FOUNDATION AND ELEVATION FOR LUBRIFICATION OIL & GREASE STORAGE - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2100-SH.001 | FOUNDATION AND ELEVATION FOR GAS CYLINDER STORAGE - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2100-SH.002 | FOUNDATION AND ELEVATION FOR GAS CYLINDER STORAGE - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2120 | FOUNDATION AND ELEVATION FOR TOOL ROOM OPERATION |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2140 | Foundations Compressor Shelter 10-SHT-2E01 -Formworks And Reinforcements- |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-10-15 | 2020-05-13
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02831
Return Date
Owner Cmmt*
| CV | OL1-2K31-2141 | Foundations Compressor Shelter 10-SHT-2E01 -Formworks And Reinforcements- |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02831
Return Date
Owner Cmmt*
| CV | OL1-2K31-2142 | Foundations Compressor Shelter 10-SHT-2E01 -Formworks And Reinforcements- |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02831
Return Date
Owner Cmmt*
| CV | OL1-2K31-2143 | Foundations Compressor Shelter 10-SHT-2E01 -Formworks And Reinforcements- |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02831
Return Date
Owner Cmmt*
| CV | OL1-2K31-2160 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 - Sh.001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2161 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 - Sh.002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2162 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 - Sh.003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2163 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 - Sh.004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2164 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 - Sh.005 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2165 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D01 - Sh.006 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2180 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D02 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2200 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D03 - Sh.001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2201 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D03 - Sh.002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2202 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D03 - Sh.003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2220 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-2D04 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2240-SH.001 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A06 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2240-SH.002 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A06 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2260-SH.001 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A03 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2260-SH.002 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A03 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2280-SH.001 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A05 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2280-SH.002 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A05 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2300-SH.001 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A04 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2300-SH.002 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A04 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2320-SH.001 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A02 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2320-SH.002 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A02 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2320-SH.003 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A02 - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.001 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.002 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.003 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.004 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.005 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 005 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.006 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 006 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.007 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 007 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.008 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 008 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.009 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 009 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2340-SH.010 | FOUNDATION AND ELEVATION FOR STRUCTURE 10-STR-3A01 - Sh. 010 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2360-SH.001 | FOUNDATION FOR STRUCTURE 10-SHT-3A01 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2360-SH.002 | FOUNDATION FOR STRUCTURE 10-SHT-3A01 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2360-SH.003 | FOUNDATION FOR STRUCTURE 10-SHT-3A01 - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2380-SH.001 | FOUNDATION FOR STRUCTURE 10-SHT-5T01 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2380-SH.002 | FOUNDATION FOR STRUCTURE 10-SHT-5T01 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2400-SH.001 | FOUNDATION FOR STRUCTURE 10-SHT-5T02 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2400-SH.002 | FOUNDATION FOR STRUCTURE 10-SHT-5T02 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2420-SH.001 | FOUNDATION FOR STRUCTURE 10-SHT-5T03 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2420-SH.002 | FOUNDATION FOR STRUCTURE 10-SHT-5T03 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2440-SH.001 | FOUNDATION AND ELEVATION FOR 10-STR-5U01 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2440-SH.002 | FOUNDATION AND ELEVATION FOR 10-STR-5U01 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2460 | Foundation Of 10-STR-1B01 - Formwork And Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2019-10-10 | 2020-05-13
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02798
Return Date
Owner Cmmt*
| CV | OL1-2K31-2480 | FOUNDATION FOR 10-SLW-0C01 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2501 | Basin For Cooling Tower 10-Pit-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-09-19 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02660
Return Date
Owner Cmmt*
| CV | OL1-2K31-2502 | Basin For Cooling Tower 10-Pit-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan |  | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2503 | Basin For Cooling Tower 10-Pit-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-09-19 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02660
Return Date
Owner Cmmt*
| CV | OL1-2K31-2504 | Basin For Cooling Tower 10-Pit-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-09-19 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02660
Return Date
Owner Cmmt*
| CV | OL1-2K31-2505 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2506 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2507 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan |  | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2508 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2509 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2510 | Basin For Cooling Tower 10-PIT-5350 - Plan (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2511 | Basin For Cooling Tower 10-Pit-5350 - Sections (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2512 | Basin For Cooling Tower 10-PIT-5350 - Sections (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2513 | Basin For Cooling Tower 10-PIT-5350 - Opening Details For Trash Screen (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2514 | Basin For Cooling Tower 10-PIT-5350 - Opening Details For Sluice Gate (Formwork) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2515 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 016 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2516 | Basin For Cooling Tower 10-PIT-5350 - Plan (Reinforcement) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan |  | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2517 | Basin For Cooling Tower 10-PIT-5350 - Plan (Reinforcement) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2518 | Basin For Cooling Tower 10-PIT-5350 - Plan (Reinforcement) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2519 | Basin For Cooling Tower 10-Pit-5350 - Plan (Reinforcement) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-2520 | Concrete Basin 10-PIT-2090 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-04-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01304
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2521 | Concrete Basin 10-PIT-2090 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-04-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-04-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01304
[6 empty] | Return Date | 2019-05-09
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2540 | Concrete Basin 10-PIT-5602 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A1
| CV | OL1-2K31-2541 | Concrete Basin 10-PIT-5602 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A1
| CV | OL1-2K31-2560 | Foundation For 10-H-1100 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02148
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2561 | Foundation For 10-H-1100 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02148
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2580 | Foundation For 10-H-1200 To 1600 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02148
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2581 | Foundation For 10-H-1200 To 1600 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-15 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02148
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2600 | Foundation For Basin 10-PIT-2190 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2601 | Foundation For Basin 10-PIT-2190 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A1
| CV | OL1-2K31-2640 | Foundation for Basin 10-PIT-2392 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-06-24 | 2020-01-24
[6 empty] | Issue Actual | 2019-06-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01958
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2641 | Concrete Basin 10-PIT-2392 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-06-27 | 2020-01-24
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02004
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-2660 | FOUNDATION FOR PLATFORMS - 2B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2680 | FOUNDATION FOR SUPPORTS - 2B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2700 | Concrete Basin 10-PIT-2790 - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-30 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-2701 | Concrete Basin 10-PIT-2790 - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-30 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-2720 | Concrete Basin 10-PIT-5600 - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-30 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-2721 | Concrete Basin 10-PIT-5600 - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-30 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02274
Return Date
Owner Cmmt*
| CV | OL1-2K31-2740 | FOUNDATION FOR PLATFORMS - 2C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2760 | FOUNDATION FOR SUPPORTS - 2C |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-2780 | Foundation For PSA Package 10-PK-2560 - 10-D-2560-A-E - 10-D-2565 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-30 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02538
Return Date
Owner Cmmt*
| CV | OL1-2K31-3000 | Foundation And Elevation For 10-C-2800 - Plants - Foundations And Elevations - Formworks |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02730
Return Date
Owner Cmmt*
| CV | OL1-2K31-3001 | Foundation And Elevation For 10-C-2800 - Sections And Details - (Formworks) |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02730
Return Date
Owner Cmmt*
| CV | OL1-2K31-3002 | Foundation And Elevation For 10-C-2800 - Plants - Foundation Elevations And Lube Oil Console - Reinforcements |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02730
Return Date
Owner Cmmt*
| CV | OL1-2K31-3003 | Foundation And Elevation For 10-C-2800 - Sections - Reinforcements |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02730
Return Date
Owner Cmmt*
| CV | OL1-2K31-3004 | Foundation And Elevation For 10-C-2800 - Details - Reinforcements |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02730
Return Date
Owner Cmmt*
| CV | OL1-2K31-3020 | FOUNDATION AND ELEVATION FOR 10-C-2850, 10-E-2850 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-3040 | Concrete Basin 10-PIT-5604 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-3041 | Concrete Basin 10-PIT-5604 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A1
| CV | OL1-2K31-3060 | FOUNDATION FOR PLATFORMS - 2D |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-3080 | FOUNDATION FOR SUPPORTS - 2D |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-3100 | Foundation And Elevation For 10-C-2200- 10-E-2200 - Plan- Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02851
Return Date
Owner Cmmt*
| CV | OL1-2K31-3101 | Foundation And Elevation For 10-C-2200- 10-E-2200- View 1-2-3-4-Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02851
Return Date
Owner Cmmt*
| CV | OL1-2K31-3102 | Foundation And Elevation For 10-C-2200- 10-E-2200- Sections And Details- Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02851
Return Date
Owner Cmmt*
| CV | OL1-2K31-3103 | Foundation And Elevation For 10-C-2200- 10-E-2200- Plan- Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02851
Return Date
Owner Cmmt*
| CV | OL1-2K31-3104 | Foundation And Elevation For 10-C-2200- 10-E-2200- Section A-A -Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02851
Return Date
Owner Cmmt*
| CV | OL1-2K31-3105 | Foundation And Elevation For 10-C-2200- 10-E-2200- Column And Saddle- Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02851
Return Date
Owner Cmmt*
| CV | OL1-2K31-3106 | Foundation And Elevation For 10-C-2200- 10-E-2200- Slab- Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan |  | 2020-06-15
Issue Actual
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02851
Return Date
Owner Cmmt*
| CV | OL1-2K31-3120 | Concrete Basin 10-PIT-2390 - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-08-05 | 2020-01-24
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02313
Return Date
Owner Cmmt*
| CV | OL1-2K31-3121 | Concrete Basin 10-PIT-2390 - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-08-05 | 2020-01-24
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02313
Return Date
Owner Cmmt*
| CV | OL1-2K31-3140 | Concrete Basin 10-PIT-5603 - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-06-27 | 2020-01-24
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02004
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-3141 | Concrete Basin 10-PIT-5603 - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-06-27 | 2020-01-24
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02004
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-3160 | FOUNDATION FOR PLATFORMS - 2E |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-3180 | FOUNDATION FOR SUPPORTS - 2E |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-3440 | FOUNDATION FOR BASIN 10-PIT-5642 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-12-24 | 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4020 | PILING PLAN |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-12-06 | 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4060 | Zone 2A - Piling Plan |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-10-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-03-28 | 2019-12-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01170
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-4080 | PILING PLAN |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-12-06 | 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4100 | PILING PLAN |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-12-06 | 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4120 | Zone 2D - Piling Plan |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-10-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-03-28 | 2019-12-15
[6 empty] | Issue Actual | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01170
[6 empty] | Return Date | 2019-06-03
[6 empty] | Owner Cmmt* | R2
| CV | OL1-2K31-4160 | Zone 3A - Piling Plan |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-10-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-10-09 | 2019-12-15
[6 empty] | Issue Actual | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02742
Return Date
Owner Cmmt*
| CV | OL1-2K31-4200 | PILING PLAN |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-12-06 | 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4220 | PILING PLAN |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-12-06 | 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4240 | PILING PLAN |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-15 | 2019-12-15
[6 empty] | Revised Plan | 2019-12-06 | 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4380 | Foundation For Basin 10-PIT-5606 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-23 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-4381 | Foundation For Basin 10-PIT-5606 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-23 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02233
Return Date
Owner Cmmt*
| CV | OL1-2K31-4460 | Concrete Basin 10-PIT-5610 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-4461 | Concrete Basin 10-PIT-5610 |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-07-11 | 2020-01-24
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A1
| CV | OL1-2K31-4500 | FOUNDATION FOR SUPPORTS - 1B |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4580 | Concrete Structure For 10-T-2040 - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-01 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02028
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-4581 | Concrete Structure For 10-T-2040 - Reinforcement |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-07-01 | 2020-06-15
[6 empty] | Issue Actual | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02028
[6 empty] | Return Date | 2019-08-21
[6 empty] | Owner Cmmt* | A2
| CV | OL1-2K31-4590 | Foundation For 10-F-2137-A-B |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-15
[6 empty] | Revised Plan | 2019-08-30 | 2020-06-15
[6 empty] | Issue Actual | 2019-08-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02540
Return Date
Owner Cmmt*
| CV | OL1-2K31-4620-SH.001 | FOUNDATION FOR SUPPORTS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4620-SH.002 | FOUNDATION FOR SUPPORTS - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4620-SH.003 | FOUNDATION FOR SUPPORTS - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4640 | FOUNDATION FOR PLATFORMS - 2A |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-4660 | FOUNDATION FOR SUPPORTS - 2A |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan | 2020-05-02 | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5020 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - TRANSFORMERS BAY CONSTR. DWGS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5021 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - TRANSFORMERS BAY CONSTR. DWGS - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5022 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - TRANSFORMERS BAY CONSTR. DWGS - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5023 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - TRANSFORMERS BAY CONSTR. DWGS - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5060 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - TRANSFORMERS BAY CONSTR. DWGS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5061 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - TRANSFORMERS BAY CONSTR. DWGS - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5062 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - TRANSFORMERS BAY CONSTR. DWGS - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5063 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - TRANSFORMERS BAY CONSTR. DWGS - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5064 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - TRANSFORMERS BAY CONSTR. DWGS - Sh. 005 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5100 | FOUNDATION AND ELEVATION FOR 10-STR-2C08 - ADDED 15 JUNE 2019 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5120 | FOUNDATION AND ELEVATION FOR 10-STR-2C09 - ADDED 15 JUNE 2019 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-02-12 | 2020-05-13
[6 empty] | Revised Plan | 2020-02-12 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-5140 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A1
| CV | OL1-2K31-5141 | Precast Concrete Elevation For Piperack 10-PRK-0P02 - Steel Bracings Details - |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-07-11 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-07-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02116
[6 empty] | Return Date | 2019-09-26
[6 empty] | Owner Cmmt* | A1
| CV | OL1-2K31-5150 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5151 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5152 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5153 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5154 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5155 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5156 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5157 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5158 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Beams |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5159 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5160 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5161 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5162 | Precast Concrete Elevation For Pipe Rack 10-PRK-2E01 - Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-08-01 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02301
Return Date
Owner Cmmt*
| CV | OL1-2K31-5170 | Precast Concrete Elevation For Pipe Rack 10-PRK-2C02 - Steel Bracings Details |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-18 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-17 | 2019-11-18 | 2019-12-18 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02641
Return Date
Owner Cmmt*
| CV | OL1-2K31-8001 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8002 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8003 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8004 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8005 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 005 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8006 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 006 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8007 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 007 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8008 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 008 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8009 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 009 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8010 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 010 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8011 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 011 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8012 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 012 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8013 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 013 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8014 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 014 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8015 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 015 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8016 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.016 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8017 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.017 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8018 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.018 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8019 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.019 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8020 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.020 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8021 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.021 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8022 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.022 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8023 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.023 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8024 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.024 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8025 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.025 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8026 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.026 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8027 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.027 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8028 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.028 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8029 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.029 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8030 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8031 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8032 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8033 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8034 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 005 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8035 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 006 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8036 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 007 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8037 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 008 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8038 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 009 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8039 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 010 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8040 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 011 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8041 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 012 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan |  | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8042 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 013 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8043 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 014 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8044 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 015 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8045 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 016 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8046 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 017 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8047 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 018 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8048 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 019 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8049 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 020 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8050 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 021 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8051 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 022 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8052 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 023 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8053 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 024 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8054 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 025 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8055 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 026 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8056 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 027 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8057 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 028 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8058 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 029 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2K31-8059 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 030 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8060 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 031 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8061 | ELECTRICAL SUBSTATION SUB-C & FIELD AUXILIARY ROOM FAR-2 - STRUCTURAL CONSTR. DWGS - Sh. 032 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8071 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.030 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8072 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.031 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8073 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.032 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8074 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.033 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8075 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.034 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8076 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh.035 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8077 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 036 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8078 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 037 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8079 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 038 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8080 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 039 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8081 | ELECTRICAL SUBSTATION SUB-E & FIELD AUXILIARY ROOM FAR-1 - STRUCTURAL CONSTR. DWGS - Sh. 040 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8091 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 001 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8092 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 002 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8093 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 003 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8094 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 004 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8095 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 005 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8096 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 006 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8097 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 007 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8098 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 008 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8099 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 009 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8100 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 010 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8101 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 011 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8102 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 012 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8103 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 013 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8104 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 014 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8105 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 015 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8106 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 016 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8107 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 017 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8108 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 018 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8109 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 019 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8110 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 018 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8111 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 021 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8112 | ELECTRICAL SUBSTATION SUB-F & FIELD AUXILIARY ROOM FAR-F - STRUCTURAL CONSTR. DWGS - Sh. 022 - ADDED 15-OCT-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-03-29 | 2020-05-13
[6 empty] | Revised Plan | 2020-03-29 | 2020-05-13
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8260 | STEEL FOR STRUCTURE 10-STR-2C09 - ADDED 15-JUNE-2019 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8300 | Basin For Cooling Tower 10-PIT-5350 - Plan (Reinforcement) |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2019-10-15 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02845
Return Date
Owner Cmmt*
| CV | OL1-2K31-8301 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 022 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8302 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 023 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8303 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 024 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8304 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 025 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8305 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 026 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8306 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 027 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8307 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 028 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8308 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 029 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8309 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 030 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8310 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 031 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8311 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 032 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8312 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 033 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8313 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 034 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8314 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 035 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8315 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 036 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8316 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 037 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8317 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 038 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8318 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 039 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8319 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 040 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8320 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 041 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8321 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 042 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8322 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 043 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8323 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 044 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8324 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 045 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8325 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 046 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8326 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 047 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8327 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 048 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8328 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 049 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8329 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 050 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8330 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 051 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8331 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 052 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8332 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 053 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8333 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 054 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8334 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 055 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8335 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 056 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8336 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 057 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8337 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 058 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8338 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 059 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8339 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 060 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8340 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 061 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8341 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 062 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8342 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 063 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8343 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 064 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8344 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 065 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8345 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 066 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8346 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 067 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8347 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 068 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8348 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 069 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8349 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 070 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8350 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 071 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8351 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 072 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8352 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 073 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8353 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 074 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8354 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 075 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8355 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 076 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8356 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 077 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8357 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 078 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8358 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 079 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8359 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 080 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8360 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 081 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8361 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 082 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8362 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 083 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8363 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 084 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8364 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 085 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8365 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 086 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8366 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 087 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8367 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 088 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8368 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 089 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8369 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 090 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8370 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 091 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8371 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 092 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8372 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 093 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8373 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 094 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8374 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 095 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8375 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 096 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8376 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 097 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8377 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 098 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8378 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 099 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8379 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 100 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8380 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 101 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8381 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 102 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8382 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 103 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8383 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 104 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8384 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 105 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8385 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 106 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8386 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 107 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8387 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 108 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8388 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 109 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8389 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 110 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8390 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 111 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8391 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 112 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8392 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 113 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8393 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 114 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8394 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 115 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8395 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 116 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8396 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 117 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8397 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 118 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8398 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 119 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8399 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 120 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8400 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 121 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8401 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 122 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8402 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 123 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8403 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 124 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8404 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 125 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8405 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 126 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8406 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 127 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8407 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 128 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8408 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 129 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8409 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 130 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8410 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 131 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8411 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 132 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8412 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 133 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8413 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 134 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8414 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 135 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8415 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 136 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8416 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 137 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8417 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 138 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8418 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 139 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8419 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 140 |  |  | Purpose** | IFR | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
[6 empty] | Revised Plan | 2020-01-13 | 2020-03-15 | 2020-04-05 | 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8425 | FOUNDATION FOR 10-SLW-5W01 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan |  | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8426 | FOUNDATION FOR 10-SLW-5W01 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan |  | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8427 | FOUNDATION FOR 10-SLW-5W01 - Sh. 003 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan |  | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8428 | FOUNDATION FOR 10-SLW-5W01 - Sh. 004 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan |  | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8429 | Foundation For Basin 10-Pit-5631 - Plans - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-10-15 | 2020-01-24
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02846
Return Date
Owner Cmmt*
| CV | OL1-2K31-8430 | Foundation For Basin 10-Pit-5631 - Sections - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-10-15 | 2020-01-24
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02846
Return Date
Owner Cmmt*
| CV | OL1-2K31-8431 | Foundation For Basin 10-Pit-5631 - Plans - Reinforcement |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02846
Return Date
Owner Cmmt*
| CV | OL1-2K31-8432 | Foundation For Basin 10-Pit-5631 - Section - Reinforcement |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02846
Return Date
Owner Cmmt*
| CV | OL1-2K31-8433 | Foundation For Basin 10-Pit-5630 - Plans - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-10-15 | 2020-01-24
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02846
Return Date
Owner Cmmt*
| CV | OL1-2K31-8434 | Foundation For Basin 10-Pit-5630 - Sections - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-10-15 | 2020-01-24
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02846
Return Date
Owner Cmmt*
| CV | OL1-2K31-8435 | Foundation For Basin 10-Pit-5630 - Plans - Reinforcement |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02846
Return Date
Owner Cmmt*
| CV | OL1-2K31-8436 | Foundation For Basin 10-Pit-5630 - Sections - Reinforcement |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02846
Return Date
Owner Cmmt*
| CV | OL1-2K31-8437 | Foundation For Basin 10-Pit-5601 - Plans - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan | 2019-10-15 | 2020-01-24
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02838
Return Date
Owner Cmmt*
| CV | OL1-2K31-8438 | Foundation For Basin 10-Pit-5601 - Sections - Formwork |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-12-24 | 2020-01-24
[6 empty] | Revised Plan |  | 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8439 | Foundation For Basin 10-Pit-5601 - Plans - Reinforcement |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8440 | Foundation For Basin 10-Pit-5601 - Sections - Reinforcement |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-10-15
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02839
Return Date
Owner Cmmt*
| CV | OL1-2K31-8449 | FOUNDATION FOR 10-SLW-5T02 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan |  | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8450 | FOUNDATION FOR 10-SLW-5T02 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan |  | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8451 | FOUNDATION FOR 10-SLW-5T01 - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan |  | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K31-8852 | FOUNDATION FOR 10-SLW-5T01 - Sh. 002 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2020-05-02 | 2020-06-02
[6 empty] | Revised Plan |  | 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K32 General Arrangement for Steel Structure drawings
| CV | OL1-2K32-0001 | Steel Structure For 10-STR-2D06 |  | Class 1 | Purpose** | IFR
[6 empty] | Rev. | A
Issue Plan
[6 empty] | Revised Plan | 2019-09-25
[6 empty] | Issue Actual | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02695
Return Date
Owner Cmmt*
| CV | OL1-2K32-1060-SH.001 | STEEL FOR PIPE RACK 10-PRK-3A01 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1060-SH.002 | STEEL FOR PIPE RACK 10-PRK-3A01 - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1060-SH.003 | STEEL FOR PIPE RACK 10-PRK-3A01 - Sh. 003 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1060-SH.004 | STEEL FOR PIPE RACK 10-PRK-3A01 - Sh. 004 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1080 | Steel for Pipe Rack 10-PRK-5U01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1100 | Steel For Pipe Rack 10-PRK-2D01- 3D View |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1101 | Steel For Pipe Rack 10-PRK-2D01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1102 | Steel For Pipe Rack 10-PRK-2D01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1103 | Steel For Pipe Rack 10-PRK-2D01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1104 | Steel For Pipe Rack 10-PRK-2D01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1105 | Steel For Pipe Rack 10-PRK-2D01 - Longitudinal Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1106 | Steel For Pipe Rack 10-PRK-2D01 - Transv. Elevations Al.2D-02 To Al.2D-09 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1107 | Steel For Pipe Rack 10-PRK-2D01 - Transv Elevations Al 2D-10 To Al 2D-17 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1108 | Steel For Pipe Rack 10-PRK-2D01 - Transv Elevations Al 2D-18 To Al 2D-23 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1109 | Steel For Pipe Rack 10-PRK-2D01 - Details |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1120 | Steel Elevation For Pipe Rack 10-PRK-2E01 - 3D View |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1121 | Steel For Pipe Rack 10-PRK-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1122 | Steel For Pipe Rack 10-PRK-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1123 | Steel For Pipe Rack 10-PRK-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1124 | Steel For Pipe Rack 10-PRK-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1125 | Steel For Pipe Rack 10-PRK-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1126 | Steel For Pipe Rack 10-PRK-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1127 | Steel For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1128 | Steel For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1129 | Steel For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1130 | Steel For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1131 | Steel For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1132 | Steel For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1133 | Steel For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1134 | Steel For Pipe Rack 10-PRK-2E01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1135 | Steel Pipe Rack 10-PRK-2E01 - Stair Plan & Sections |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1136 | Steel Pipe Rack 10-PRK-2E01 - Stair Plan & Sections |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1137 | Steel For Pipe Rack 10-PRK-2E01 - Ladder Platform |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1138 | Steel For Pipe Rack 10-PRK-2E01 - Details |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1140 | Steel Structural For Concrete Basin 10-Pit-3190 - Plan And Sections |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-08-22 | 2019-10-21
[6 empty] | Revised Plan | 2019-09-23 | 2019-10-21
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02676
Return Date
Owner Cmmt*
| CV | OL1-2K32-1141 | Steel Structure For Concrete Basin 10-Pit-3190 - Connection Details |  |  | Purpose** | IFR | IFC
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-08-22 | 2019-10-21
[6 empty] | Revised Plan | 2019-09-23 | 2019-10-21
[6 empty] | Issue Actual | 2019-09-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02676
Return Date
Owner Cmmt*
| CV | OL1-2K32-1142 | Steel For Pipe Rack 10-PRK-2A01 – Plans And Sections |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1143 | Steel For Pipe Rack 10-PRK-2A01 – Elevations And Sections |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1144 | Steel For Pipe Rack 10-PRK-2A01 – Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1145 | Steel For Pipe Rack 10-PRK-2A01 - 3D View |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1146 | Steel For Pipe Rack 10-PRK-2A01 - Plans And Sections |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1160 | Steel For Pipe Rack 10-PRK-2B01 - 3D View |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1161 | Steel For Pipe Rack 10-PRK-2B01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1162 | Steel For Pipe Rack 10-PRK-2B01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1163 | Steel For Pipe Rack 10-PRK-2B01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1164 | Steel For Pipe Rack 10-PRK-2B01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1165 | Steel For Pipe Rack 10-PRK-2B01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1166 | Steel For Pipe Rack 10-PRK-2B01 – Elevations And Details |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1167 | Steel For Pipe Rack 10-PRK-2B01 – Elevation Stair |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1180 | Steel For Pipe Rack 10-PRK-2B02 - 3D View |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1181 | Steel For Pipe Rack 10-PRK-2B02 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1182 | Steel For Pipe Rack 10-PRK-2B02 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1183 | Steel For Pipe Rack 10-PRK-2B02 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1184 | Steel For Pipe Rack 10-PRK-2B02 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1185 | Steel For Pipe Rack 10-PRK-2B02 - Details |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1200 | STEEL FOR PIPE RACK 10-PRK-2C01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1220 | Steel For Pipe Rack 10-PRK-2C02 - 3D View |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-10-22 | 2020-02-03 | 2020-03-17
[6 empty] | Revised Plan | 2019-10-22 | 2020-02-03 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1221 | Steel For Pipe Rack 10-PRK-2C02 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1222 | Steel For Pipe Rack 10-PRK-2C02 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1223 | Steel For Pipe Rack 10-PRK-2C02 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1224 | Steel For Pipe Rack 10-PRK-2C02 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1225 | Steel For Pipe Rack 10-PRK-2C02 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1226 | Steel For Pipe Rack 10-PRK-2C02 - Plans & Sections |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1227 | Steel For Pipe Rack 10-PRK-2C02 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1228 | Steel For Pipe Rack 10-PRK-2C02 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1229 | Steel For Pipe Rack 10-PRK-2C02 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1230 | Steel For Pipe Rack 10-PRK-2C02 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1231 | Steel For Pipe Rack 10-PRK-2C02 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1232 | Steel For Pipe Rack 10-PRK-2C02 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1233 | Steel For Pipe Rack 10-PRK-2C02 - Stairs And Ladders |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1234 | Steel For Pipe Rack 10-PRK-2C02 - Details |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240-SH.005 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 005 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240-SH.006 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 006 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240-SH.007 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 007 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240-SH.008 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 008 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240-SH.009 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 009 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240-SH.010 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 010 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240-SH.011 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 011 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1240-SH.012 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 012 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1241 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1242 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 003 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1243 | STEEL FOR PIPE RACK 10-PRK-5T01 - Sh. 004 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1260 | STEEL FOR 10-PRK-5F01 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1261 | STEEL FOR 10-PRK-5F01 - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1262 | STEEL FOR 10-PRK-5F01 - Sh. 003 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1263 | STEEL FOR 10-PRK-5F01 - Sh. 004 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
[6 empty] | Revised Plan | 2019-11-28 | 2020-02-01 | 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1271 | CONCRETE BASIN 10-PIT-5620A/B/C - STEEL PLATFORMS - PLANS & SECTIONS - Sh. 001 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-08-22 | 2019-10-21
[6 empty] | Revised Plan | 2020-02-14 | 2019-10-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1272 | CONCRETE BASIN 10-PIT-5620A/B/C - STEEL PLATFORMS - PLANS - Sh. 002 - ADDED 4-SEP-19 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-15 | 2019-11-15
[6 empty] | Revised Plan |  | 2019-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1280 | Steel For Structure 10-SHT-2E01 - 3D View |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1281 | Steel For Structure 10-SHT-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1282 | Steel For Structure 10-SHT-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1283 | Steel For Structure 10-SHT-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1284 | Steel For Structure 10-SHT-2E01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1285 | Steel For Structure 10-SHT-2E01 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1286 | Steel For Structure 10-SHT-2E01 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1287 | Steel For Structure 10-SHT-2E01 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1288 | Steel For Structure 10-SHT-2E01 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1289 | Steel For Structure 10-SHT-2E01 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1290 | Steel For Structure 10-SHT-2E01 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1291 | Steel For Structure 10-SHT-2E01 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1292 | Steel For Structure 10-SHT-2E01 - Elevation |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1294 | Steel For Structure 10-SHT-2E01 - Stair Plans And Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1300 | Steel Structure For 10-STR-2E01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1301 | Steel Structure For 10-STR-2E01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1304 | USC 36M Recycle Furnace Steel End Wall Tubesheet Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-03-20 |  | 2019-04-10
[6 empty] | Revised Plan |  | 2019-04-12
[6 empty] | Issue Actual |  | 2019-04-12
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01321
Return Date
Owner Cmmt*
| CV | OL1-2K32-1320 | Steel Structure For 10-STR-2E02 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1321 | Steel Structure For 10-STR-2E02 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1340 | STEEL FOR STRUCTURE 10-STR-2E03 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1360 | Steel Structure For 10-STR-2E04 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1361 | Steel Structure For 10-STR-2E04 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1380 | STEEL FOR STRUCTURE 10-STR-2D05 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1400 | STEEL FOR STRUCTURE 10-STR-2B01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1420 | STEEL FOR STRUCTURE 10-STR-2C06 - ADDED 15 APR 19 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1440 | Steel For Structure 10-STR-2C07 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1441 | Steel For Structure 10-STR-2C07 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1460 | STEEL FOR STRUCTURE 10-STR-2B04 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1480 | Steel For Structure 10-STR-2B02 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1481 | Steel For Structure 10-STR-2B02 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1500 | STEEL FOR STRUCTURE 10-STR-2E05 - ADDED 15 APR 19 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1511 | USC 36M Recycle Furnace Steel Radiant Floor and Radiant Arch Plans |  | Class 1 | Purpose** | IFI | IMP | IMP
[6 empty] | Rev. | A | 0 | 1
Issue Plan
[6 empty] | Revised Plan | 2019-04-02 | 2019-05-23
[6 empty] | Issue Actual | 2019-04-02 | 2019-05-23 | 2019-06-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01222, TPSK-LSPA1-T-CV-01702, TPSK-LSPA1-T-CV-01702 | TPSK-LSPA1-T-CV-01709 | TPSK-LSPA1-T-CV-01877
[6 empty] | Return Date |  | 2019-06-21 | 2019-08-20
[6 empty] | Owner Cmmt* |  | R1 | R1
| CV | OL1-2K32-1512 | USC 36M Recycle Furnace Steel Radiant Side Wall at Col Line A1 and D1 |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1513 | USC 36M Recycle Furnace Steel Radiant Side Wall at Col Line B1 and C1 |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1514 | USC 36M Recycle Furnace Steel Radiant End Wall at Col 1 and 6_8 |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1515 | USC 36M Recycle Furnace Steel Transition Floor Plan and Sections |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1516 | USC 36M Recycle Furnace Steel Shadow Box Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1517 | USC 36M Recycle Furnace Steel Radiant Sections and Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1518 | USC 36M Recycle Furnace Steel Radiant Sections and Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1519 | USC 36M Recycle Furnace Steel Radiant Sections and Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1520 | USC 36M Recycle Furnace Steel Convection Side Wall at Col Line B1 |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-11
[6 empty] | Issue Actual |  | 2019-04-11
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-1521 | USC 36M Recycle Furnace Steel Convection Side Wall at COL Line C1 |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-11
[6 empty] | Issue Actual |  | 2019-04-11
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-1522 | USC 36M Recycle Furnace Steel Match Bolting Plans for Field Splice at El 115022 and 132470 |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1523 | USC 36M FURNACE STEEL END WALL TUBE SHEET ELEVATION |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1524 | USC 36M Recycle Furnace Steel Convection Section End Wall Tubesheet Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-10
[6 empty] | Issue Actual |  | 2019-04-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1525 | USC 36M Recycle Furnace Steel Convection Section Header Box Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-10
[6 empty] | Issue Actual |  | 2019-04-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1527 | USC 36M Recycle Furnace Steel Convection Section Header Box Elevations |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-10
[6 empty] | Issue Actual |  | 2019-04-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1528 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1529 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1530 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1531 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1532 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1533 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1534 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1535 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1536 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1537 | USC 36M FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1539 | USC 36M FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1540 | USC 36M Recycle Furnace Steel Crossover Limit Stop Details |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-02 | 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1541 | USC 36M Recycle Furnace Steel Convection Sections and Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-10
[6 empty] | Issue Actual |  | 2019-04-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1542 | USC 36M Recycle Furnace Steel Sections and Details |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-02 | 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1543 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1544 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1545 | USC 36M FURNACE STEEL SECTIONS AND DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1546 | USC 36M Recycle Furnace Steel Name Plate Details |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-02 | 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1550 | USC 36M Cracking Furnace Steel Stack Sections and Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-10
[6 empty] | Issue Actual |  | 2019-04-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1551 | USC 36M Recycle Furnace Steel Instrument Connection Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-01-31
[6 empty] | Issue Actual |  | 2019-01-31
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-ME-00767
[6 empty] | Return Date |  | 2019-02-21
[6 empty] | Owner Cmmt* |  | R2
| CV | OL1-2K32-1552 | USC 36M Recycle Furnace Steel Radiant Coil Removal Access Door Details |  |  | Purpose** | IFR | IFI | IFD | IFF | IMP | IMP
[6 empty] | Rev. |  | A |  |  | 0 | 1
[6 empty] | Issue Plan | 2018-09-18 |  | 2018-12-07 | 2019-01-31
[6 empty] | Revised Plan |  | 2019-04-02 |  |  | 2019-05-23
[6 empty] | Issue Actual |  | 2019-04-02 |  |  | 2019-05-23 | 2019-07-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222 |  |  | TPSK-LSPA1-T-CV-01709 | TPSK-LSPA1-T-CV-02227
[6 empty] | Return Date |  |  |  |  | 2019-06-21
[6 empty] | Owner Cmmt* |  |  |  |  | R1
| CV | OL1-2K32-1553 | USC 36M Recycle Furnace Steel Radiant Coil Tube Pulling Panel Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-1555 | USC 36M Recycle Furnace Steel Inspection Door Lance Door and Access Door Details |  | Class 1 | Purpose** | IFI | IMP
[6 empty] | Rev. | A | 0
Issue Plan
[6 empty] | Revised Plan | 2019-04-10 | 2019-05-30
[6 empty] | Issue Actual | 2019-04-10 | 2019-05-30
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-01293 | TPSK-LSPA1-T-CV-01765
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R1
| CV | OL1-2K32-1560 | USC 36M Recycle Furnace Steel Standard Sections and Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-10
[6 empty] | Issue Actual |  | 2019-04-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1561 | USC 36M Recycle Furnace Steel Access Door Davit Details |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-02 | 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1562 | USC 36M Recycle Furnace Steel Access Door Davit Details |  | Class 1 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-23
[6 empty] | Issue Actual | 2019-07-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02227
Return Date
Owner Cmmt*
| CV | OL1-2K32-1563 | USC 36M Recycle Furnace Steel Access Door Davit Details |  | Class 1 | Purpose** | IMP
[6 empty] | Rev. | 0
Issue Plan
[6 empty] | Revised Plan | 2019-07-24
[6 empty] | Issue Actual | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-CV-02248
[6 empty] | Return Date | 2019-10-14
[6 empty] | Owner Cmmt* | R1
| CV | OL1-2K32-1580 | USC 36M Recycle Furnace Steel Breeching Plan and Elevations |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-10
[6 empty] | Issue Actual |  | 2019-04-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1581 | USC 36M Recycle Furnace Steel Breeching Sections and Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-10
[6 empty] | Issue Actual |  | 2019-04-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1582 | USC 36M Recycle Furnace Steel Duct Plan and Elevations |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-10
[6 empty] | Issue Actual |  | 2019-04-10
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-1583 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1584 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1585 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1586 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1587 | USC 36M FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1600 | Steel For Structure 10-STR-2C03 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1601 | USC 36M Recycle Furnace Steel Platform Plan at TOS EL 103360 |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-05-07
[6 empty] | Issue Actual |  | 2019-05-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R1
| CV | OL1-2K32-1602 | USC 36M Recycle Furnace Steel Platform Plan at TOS El 107100 |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-05-07
[6 empty] | Issue Actual |  | 2019-05-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R1
| CV | OL1-2K32-1603 | USC 36M Recycle Furnace Steel Platform Plan at TOS El 110000 |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-05-07
[6 empty] | Issue Actual |  | 2019-05-07
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R1
| CV | OL1-2K32-1604 | USC 36M Recycle Furnace Steel Platform Plan at TOS EL 112690 |  |  | Purpose** | IFR | IFC
Rev.
[6 empty] | Issue Plan | 2019-09-02 | 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1605 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1606 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. FF |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1607 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1608 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1609 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1610 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1611 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1612 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1613 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1614 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1615 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1616 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1617 | USC 36M FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1618 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1619 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1620 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1621 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1622 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1623 | USC 36M FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1624 | Steel For Structure 10-STR-2C03 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1631 | USC 36M FURNACE STEEL PIPE SUPPORT & DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1632 | USC 36M FURNACE STEEL PIPE SUPPORT & DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1640 | STEEL FOR STRUCTURE 10-STR-2C05 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1641 | USC 36M FURNACE STEEL ID FAN BOLTING PLAN |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1651 | USC 36M FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1660 | STEEL FOR STRUCTURE 10-SHT-2C01 ADDED 15 APR 19 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1680 | STEEL FOR STRUCTURE 10-SHT-1B01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1700 | Steel Structure For 10-STR-0P01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1701 | Steel Structure For 10-STR-0P01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1702 | Steel Structure For 10-STR-0P01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1703 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1704 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1705 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1706 | USC 36M FURNACE STEEL STAIR TOWER PLANS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1707 | USC 36M FURNACE STEEL STAIR TOWER STRINGER SETTING-OUT |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1708 | USC 36M FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1720 | Steel Structure For 10-STR-2A01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1721 | Steel Structure For 10-STR-2A01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1740 | Steel Structure For 10-STR-2A02 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1760 | STEEL FOR STRUCTURE 10-STR-2A03 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1780 | STEEL FOR STRUCTURE 10-STR-2D01 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1800 | STEEL FOR STRUCTURE 10-STR-2D02 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1820 | STEEL FOR STRUCTURE 10-STR-2D03 - Sh.001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1821 | STEEL FOR STRUCTURE 10-STR-2D03 - Sh.002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1840 | STEEL FOR STRUCTURE 10-STR-2D04 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1860-SH.001 | STEEL FOR WASTE STORAGE BUILDING - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1860-SH.002 | STEEL FOR WASTE STORAGE BUILDING - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1860-SH.003 | STEEL FOR WASTE STORAGE BUILDING - Sh. 003 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1860-SH.004 | STEEL FOR WASTE STORAGE BUILDING - Sh. 004 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1860-SH.005 | STEEL FOR WASTE STORAGE BUILDING - Sh. 005 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1880-SH.001 | STEEL FOR STORAGE SHELTER FOR CHEMICALS - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1880-SH.002 | STEEL FOR STORAGE SHELTER FOR CHEMICALS - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1900-SH.001 | STEEL FOR LUBRIFICATION OIL & GREASE STORAGE - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1900-SH.002 | STEEL FOR LUBRIFICATION OIL & GREASE STORAGE - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1901 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1902 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1903 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1904 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1905 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1906 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1907 | USC 36M FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1908 | USC 36M FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1909 | USC 36M FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1910 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1911 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1912 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1913 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1914 | USC 36M FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1920-SH.001 | STEEL FOR GAS CYLINDER STORAGE - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1920-SH.002 | STEEL FOR GAS CYLINDER STORAGE - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1960-SH.001 | STEEL FOR STRUCTURE 10-STR-3A06 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1960-SH.002 | STEEL FOR STRUCTURE 10-STR-3A06 - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1980-SH.001 | STEEL FOR STRUCTURE 10-STR-3A03 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-1980-SH.002 | STEEL FOR STRUCTURE 10-STR-3A03 - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2000-SH.001 | STEEL FOR STRUCTURE 10-STR-3A05 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2020-SH.001 | STEEL FOR STRUCTURE 10-STR-3A04 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2020-SH.002 | STEEL FOR STRUCTURE 10-STR-3A04 - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2020-SH.003 | STEEL FOR STRUCTURE 10-STR-3A04 - Sh. 003 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2040-SH.001 | STEEL FOR STRUCTURE 10-STR-3A02 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2040-SH.002 | STEEL FOR STRUCTURE 10-STR-3A02 - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2060-SH.001 | STEEL FOR STRUCTURE 10-STR-3A01 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2060-SH.002 | STEEL FOR STRUCTURE 10-STR-3A01 - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2060-SH.003 | STEEL FOR STRUCTURE 10-STR-3A01 - Sh. 003 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2060-SH.004 | STEEL FOR STRUCTURE 10-STR-3A01 - Sh. 004 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2060-SH.005 | STEEL FOR STRUCTURE 10-STR-3A01 - Sh. 005 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2080-SH.001 | STEEL FOR STRUCTURE 10-SHT-3A01 - Sh. 001 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2080-SH.002 | STEEL FOR STRUCTURE 10-SHT-3A01 - Sh. 002 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2080-SH.003 | STEEL FOR STRUCTURE 10-SHT-3A01 - Sh. 003 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2080-SH.004 | STEEL FOR STRUCTURE 10-SHT-3A01 - Sh. 004 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2080-SH.005 | STEEL FOR STRUCTURE 10-SHT-3A01 - Sh. 005 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2080-SH.006 | STEEL FOR STRUCTURE 10-SHT-3A01 - Sh. 006 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2100 | Steel Structure For Shelter 10-SHT-2D01 - 3D View |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2101 | Steel Structure For Shelter 10-SHT-2D01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2102 | Steel Structure For Shelter 10-SHT-2D01 - Plan & Details |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2103 | Steel Structure For Shelter 10-SHT-2D01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2104 | Steel Structure For Shelter 10-SHT-2D01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2105 | Steel Structure For Shelter 10-SHT-2D01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2120 | Steel Structure For 10-SHT-2D02 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2121 | Steel Structure For 10-SHT-2D02 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2140 | Steel For Structure 10-STR-2C01 - Plans |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2141 | Steel For Structure 10-STR-2C01 - Elevations |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2160 | STEEL FOR STRUCTURE 10-STR-2C02 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2161 | FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2162 | FURNACE STEEL MOMENT CONNECTION DETAIL AND MISCELLANEOUS DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2163 | FURNACE STEEL STANDARD SECTIONS AND DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2164 | FURNACE STEEL STANDARD FLOOR - TOE PLATE DETAILS |  |  | Purpose** | IFC
Rev.
[6 empty] | Issue Plan | 2019-10-09
[6 empty] | Revised Plan | 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2180 | STEEL FOR STRUCTURE 10-STR-2C04 |  |  | Purpose** | IFC | IFC1 | IFC2
Rev.
[6 empty] | Issue Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
[6 empty] | Revised Plan | 2020-05-25 | 2020-07-24 | 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2304 | USC 132U Recycle Furnace Steel End Wall Tubesheet Details |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-03-20 |  | 2019-04-10
[6 empty] | Revised Plan |  | 2019-04-12
[6 empty] | Issue Actual |  | 2019-04-12
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01321
Return Date
Owner Cmmt*
| CV | OL1-2K32-2500 | USC 36M Recycle and 132U Cracking Furnaces Steel General Notes and Abbreviations |  |  | Purpose** | IFR | IFI | IFC
[6 empty] | Rev. |  | A
[6 empty] | Issue Plan | 2019-09-02 |  | 2019-10-09
[6 empty] | Revised Plan |  | 2019-04-02
[6 empty] | Issue Actual |  | 2019-04-02
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2501 | USC 132U Cracking and 36M Recycle Furnaces Steel Foundation Plan and Loading Diagram |  |  | Purpose** | IFR | IFI | IFD | IFF | IMP | IMP
[6 empty] | Rev. |  | 0 |  |  | 1 | 2
[6 empty] | Issue Plan | 2019-05-07 |  | 2019-06-05 | 2019-06-05
[6 empty] | Revised Plan |  | 2019-05-09 |  |  | 2019-05-30
[6 empty] | Issue Actual |  | 2019-05-09 |  |  | 2019-05-30 | 2019-09-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01618 |  |  | TPSK-LSPA1-T-CV-01765 | TPSK-LSPA1-T-CV-02682
[6 empty] | Return Date |  | 2019-07-01
[6 empty] | Owner Cmmt* |  | R1
| CV | OL1-2K32-2502 | USC 36M Recycle And 132U Cracking Furnace Steel Base Plate Details |  |  | Purpose** | IFR | IFI | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. |  | A |  |  | 0 | 1 | 2 | 3
[6 empty] | Issue Plan | IFR: 2019-05-07; R1 IFD: 2019-06-05; R1 IFF: 2019-06-05
[6 empty] | Revised Plan | R1 IFI: 2019-04-02; R1 IMP: 2019-05-09
[6 empty] | Issue Actual |  | 2019-04-02 |  |  | 2019-05-09 | 2019-05-30 | 2019-07-23 | 2019-09-25
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-01222 |  |  | TPSK-LSPA1-T-CV-01616 | TPSK-LSPA1-T-CV-01765 | TPSK-LSPA1-T-CV-02229 | TPSK-LSPA1-T-CV-02682
[6 empty] | Return Date | R1 IMP: 2019-07-01; R1 IMP: 2019-10-10
Owner Cmmt* | bar: R1 IMP; R1 IMP
| CV | OL1-2K32-2511 | USC 132U Cracking Furnace Steel Radiant Floor And Radiant Arch Plans |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2512 | USC 132U Cracking Furnace Steel Radiant Side Wall at COL Line A2 And D2 |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2513 | USC 132U Cracking Furnace Steel Radiant Side Wall At COL Line B2 And C2 |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2514 | USC 132U Cracking Furnace Steel Radiant End Wall At COL Line 1 And 5 |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2515 | USC 132U Cracking Furnace Steel Transition Floor Plan And Sections |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2516 | USC 132U Cracking Furnace Steel Shadow Box Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2517 | USC 132U Cracking Furnace Steel Radiant Sections And Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2518 | USC 132U Cracking Furnace Steel Radiant Sections And Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2519 | USC 132U Cracking Furnace Steel Radiant Sections And Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2520 | USC 132U Cracking Furnace Steel Convection Side Wall at COL Line B2 thru B6 |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2521 | USC 132U Cracking Furnace Steel Convection Side Wall at COL Line C2 thru C6 |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2522 | USC 132U Cracking Furnace Steel Match Bolting Plans For Field Splice At EL 118240 and 135270 |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-02
[6 empty] | Issue Actual | R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222
Return Date
Owner Cmmt*
| CV | OL1-2K32-2523 | USC 132U Cracking Furnace Steel Convection End Wall Tubesheet Details |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2524 | USC 132U Cracking Furnace Steel Convection End Wall Tubesheet Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2525 | USC 132U Cracking Furnace Steel Convection Section Header Box Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2527 | USC 132U Cracking Furnace Steel Convection Section Header Box Elevations |  |  | Purpose** | IFR | IFI | IFR | IFI | IFC | IFC
Rev. | bar: R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-09-02; R1 IMP: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10; R1 IFF: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10; R1 IFF: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293; R1 IFF: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2528 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE A2 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2529 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE B2 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2530 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE C2 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2531 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D2 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2532 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE D0 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2533 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 1 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2534 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 2 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2535 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 3 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2536 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 4 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2537 | USC 132U FURNACE STEEL ELEVATION VIEW AT COLUMN LINE 5 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2539 | USC 132U FURNACE STEEL CROSSOVER LIMIT STOP DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2540 | USC 132U Cracking Furnace Steel Crossover Limit Stop Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2541 | USC 132U Cracking Furnace Steel Convection Sections and Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-11
[6 empty] | Issue Actual | R1 IFI: 2019-04-11
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01308
Return Date
Owner Cmmt*
| CV | OL1-2K32-2542 | USC 132U Cracking Furnace Steel Sections and Details |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2543 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2544 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2545 | USC 132U FURNACE STEEL SECTIONS AND DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2546 | USC 132U Cracking Furnace Name Plate Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2018-12-04
[6 empty] | Issue Actual | R1 IFI: 2018-12-04
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00423
Return Date
Owner Cmmt*
| CV | OL1-2K32-2550 | USC 132U Cracking Furnace Steel Stack Sections and Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2551 | USC 132U Cracking Furnace Steel Instrument Connection Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-01-31
[6 empty] | Issue Actual | R1 IFI: 2019-01-31
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00767
[6 empty] | Return Date | R1 IFI: 2019-02-21
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K32-2552 | USC 132U Cracking Furnace Steel Radiant Coil Removal_Access Door Details |  |  | Purpose** | IFR | IFI | IFD | IFF | IMP | IMP
[6 empty] | Rev. | R1 IFI: A; R1 IMP: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2018-09-18; R1 IFD: 2018-12-07; R1 IFF: 2019-01-31
[6 empty] | Revised Plan | R1 IFI: 2019-04-02; R1 IMP: 2019-05-23
[6 empty] | Issue Actual | R1 IFI: 2019-04-02; R1 IMP: 2019-05-23; R1 IMP: 2019-07-23
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01222; R1 IMP: TPSK-LSPA1-T-CV-01709; R1 IMP: TPSK-LSPA1-T-CV-02223
[6 empty] | Return Date | R1 IMP: 2019-06-21; R1 IMP: 2019-10-10
Owner Cmmt* | bar: R1 IMP to R1 IMP
| CV | OL1-2K32-2553 | USC 132U Cracking Furnace Steel Radiant Coil Tube Pulling Panel Detail |  | Class 1 | Purpose** | IFR: IFI; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-02; R1 IFI: 2019-05-23
[6 empty] | Issue Actual | IFR: 2019-04-02; R1 IFI: 2019-05-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01222; R1 IFI: TPSK-LSPA1-T-CV-01709
[6 empty] | Return Date | R1 IFI: 2019-06-21
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K32-2555 | USC 132U Cracking Furnace Steel Inspection Door Lance Door and Access Door Details |  | Class 1 | Purpose** | IFR: IFI; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-11; R1 IFI: 2019-05-30
[6 empty] | Issue Actual | IFR: 2019-04-11; R1 IFI: 2019-05-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01308; R1 IFI: TPSK-LSPA1-T-CV-01765
[6 empty] | Return Date | R1 IFI: 2019-06-21
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K32-2560 | USC 132U Cracking Furnace Steel Standard Sections and Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2561 | USC 132U Cracking Furnace Steel Access Door Davit Details |  | Class 1 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02223
[6 empty] | Return Date | IFR: 2019-10-10
Owner Cmmt* | bar: IFR
| CV | OL1-2K32-2562 | USC 132U Cracking Furnace Steel Access Door Davit Details |  | Class 1 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02236
Return Date
Owner Cmmt*
| CV | OL1-2K32-2563 | USC 132U Recycle Furnace Steel Access Door Davit Details |  | Class 1 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-24
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02248
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| CV | OL1-2K32-2580 | USC 132U Cracking Furnace Steel Breeching Plan and Elevations |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2581 | USC 132U Cracking Furnace Steel Breeching Sections and Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2582 | USC 132U Cracking Furnace Steel Duct Plan and Elevations |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01293
Return Date
Owner Cmmt*
| CV | OL1-2K32-2583 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 1 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2584 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 2 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2585 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 3 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2586 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 4 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2587 | USC 132U FURNACE STEEL PARTIAL ELEVATION VIEW AT COLUMN LINE 5 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2601 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 103360 |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-05-07
[6 empty] | Issue Actual | R1 IFI: 2019-05-07
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date | R1 IFI: 2019-06-21
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K32-2601- | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 103360 |  | Class 1 | Purpose** | IFR: IMP
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-28
[6 empty] | Issue Actual | IFR: 2019-09-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02724
Return Date
Owner Cmmt*
| CV | OL1-2K32-2602 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 107100 |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-05-06
[6 empty] | Issue Actual | R1 IFI: 2019-05-06
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date | R1 IFI: 2019-06-21
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K32-2603 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 113000 |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-05-07
[6 empty] | Issue Actual | R1 IFI: 2019-05-07
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01584
[6 empty] | Return Date | R1 IFI: 2019-06-21
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K32-2604 | USC 132U Cracking Furnace Steel Platform Plan at TOS EL 115870 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2605 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. EE |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2607 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. GG |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2608 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2609 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. II |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2610 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. JJ |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2611 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. HH |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2612 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. KK |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2613 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. LL |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2614 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. MM |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2615 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. NN |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2616 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. OO |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2617 | USC 132U FURNACE STEEL PLATFORM PLAN AT TOS EL. PP |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2618 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2619 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2620 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2621 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2622 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2623 | USC 132U FURNACE STEEL PLATFORM SECTIONS & DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2631 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2632 | USC 132U FURNACE STEEL PIPE SUPPORT & DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2641 | USC 132U FURNACE STEEL ID FAN BOLTING PLAN |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2651 | USC 132U FURNACE STEEL TEMPORARY ARCH SUPPORT STEEL |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2659 | USC 36M Recycle & 132U Cracking Furnace Steel Moment Connection Details & Miscellaneous Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2660 | USC 36M Recycle and 132U Cracking Furnaces Steel Standard Sections and Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2661 | USC 36M Recycle Furnace and 132U Cracking Furnaces Steel Platform and TOE Details |  | Class 1 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-07
[6 empty] | Issue Actual | IFR: 2019-05-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01585
[6 empty] | Return Date | IFR: 2019-06-21
Owner Cmmt* | bar: IFR
| CV | OL1-2K32-2701 | USC 132U Cracking Furnace Steel Stair Tower Elevation Views |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2702 | USC 132U Cracking Furnace Steel Stair Tower Elevation Views |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2703 | USC 132U Cracking Furnace Steel Stair Tower Plans |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2704 | USC 132 Cracking Furnace Steel Stair Tower Plans |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2705 | USC 132U Cracking Furnace Steel Stair Tower Plans |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2706 | USC 132U Cracking Furnace Steel Stair Tower Plans |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2707 | USC 132U Cracking Furnace Steel Stair Tower Elevation Views |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-02; R1 IFI: 2019-10-09
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2708 | USC 132U FURNACE STEEL TYPICAL STAIR HANDRAIL DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2801 | USC FURNACE STEEL ELEVATOR ACCESS PLATFORM |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2802 | USC FURNACE STEEL ELEVATOR PLANS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2803 | USC FURNACE STEEL ELEVATOR PLANS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2804 | USC FURNACE STEEL ELEVATOR PLANS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2805 | USC FURNACE STEEL ELEVATOR PLANS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2901 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2902 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2903 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2904 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2905 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2906 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2907 | USC 132U FURNACE STEEL CABLE TRAY SUPPORTS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2908 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2909 | USC 132U FURNACE STEEL TRAY SUPPORT ELEVATIONS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2910 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND ELEVATIONS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2911 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2912 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2913 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-2914 | USC 132U FURNACE STEEL TRAY SUPPORT SECTIONS AND DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-09
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3000-SH.001 | STEEL FOR STRUCTURE 10-SHT-5T01 - Sh. 001 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3000-SH.002 | STEEL FOR STRUCTURE 10-SHT-5T01 - Sh. 002 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3000-SH.003 | STEEL FOR STRUCTURE 10-SHT-5T01 - Sh. 003 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3020-SH.001 | STEEL FOR STRUCTURE 10-SHT-5T02 - Sh. 001 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3020-SH.002 | STEEL FOR STRUCTURE 10-SHT-5T02 - Sh. 002 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3020-SH.003 | STEEL FOR STRUCTURE 10-SHT-5T02 - Sh. 003 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3040-SH.001 | STEEL FOR STRUCTURE 10-SHT-5T03 - Sh. 001 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3040-SH.002 | STEEL FOR STRUCTURE 10-SHT-5T03 - Sh. 002 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3040-SH.003 | STEEL FOR STRUCTURE 10-SHT-5T03 - Sh. 003 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3060-SH.001 | STEEL FOR STRUCTURE 10-STR-5U01 - Sh. 001 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3060-SH.002 | STEEL FOR STRUCTURE 10-STR-5U01 - Sh. 002 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3080 | Steel For Structure 10-STR-1B01 - 3D View |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3081 | Steel For Structure 10-STR-1B01 - Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3082 | Steel For Structure 10-STR-1B01 - Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3083 | Steel For Structure 10-STR-1B01 - Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-3084 | Steel For Structure 10-STR-1B01 - Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-6601 | USC 132U Cracking Furnace Steel Partial Platform Plan at TOS EL 103350 107100 and 113000 |  | Class 1 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02577
Return Date
Owner Cmmt*
| CV | OL1-2K32-7000 | Steel Structure For Pipe Rack 10-PRK-0P01- 3D View |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
[6 empty] | Rev. | IFR: 0
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-10-15; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Issue Actual | IFR: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7001 | Steel Structure For Pipe Rack 10-PRK-0P01- Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
[6 empty] | Rev. | IFR: 0
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7002 | Steel Structure For Pipe Rack 10-PRK-0P01- Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
[6 empty] | Rev. | IFR: 0
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7003 | Steel Structure For Pipe Rack 10-PRK-0P01- Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
[6 empty] | Rev. | IFR: 0
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7004 | Steel Structure For Pipe Rack 10-PRK-0P01- Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
[6 empty] | Rev. | IFR: 0
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7005 | Steel Structure For Pipe Rack 10-PRK-0P01- Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
[6 empty] | Rev. | IFR: 0
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7006 | Steel Structure For Pipe Rack 10-PRK-0P01- Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
[6 empty] | Rev. | IFR: 0
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7007 | Steel Structure For Pipe Rack 10-PRK-0P01- Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
[6 empty] | Rev. | IFR: 0
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7008 | Steel Structure For Pipe Rack 10-PRK-0P01- Sections |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
[6 empty] | Rev. | IFR: 0
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7009 | Steel Structure For Pipe Rack 10-PRK-0P01 - Details |  | Class 1 | Purpose** | IFR: IFC
[6 empty] | Rev. | IFR: 0
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7010 | Steel Structure For Pipe Rack 10-PRK-0P01- Details |  | Class 1 | Purpose** | IFR: IFC
[6 empty] | Rev. | IFR: 0
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7011 | Steel Structure For Pipe Rack 10-PRK-0P01- Stair |  | Class 1 | Purpose** | IFR: IFC
[6 empty] | Rev. | IFR: 0
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7012 | Steel Structure For Pipe Rack 10-PRK-0P01- Details |  | Class 1 | Purpose** | IFR: IFC
[6 empty] | Rev. | IFR: 0
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7013 | Steel Structure For Pipe Rack 10-PRK-0P01- Ladders Platforms And Details |  | Class 1 | Purpose** | IFR: IFC
[6 empty] | Rev. | IFR: 0
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02833
Return Date
Owner Cmmt*
| CV | OL1-2K32-7100 | Steel For Piperack 10-PRK-0P02 - 3D View - |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7101 | Steel For Piperack 10-PRK-0P02 - Plans- |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7102 | Steel For Piperack 10-PRK-0P02 (Plans) |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7103 | Steel For Piperack 10-PRK-0P02 - Plans - |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7104 | Steel For Piperack 10-PRK-0P02 - Plans And Section - |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7105 | Steel For Piperack 10-PRK-0P02 - Elevations - |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7106 | Steel For Piperack 10-PRK-0P02 - Elevations - |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7107 | Steel For Piperack 10-PRK-0P02 - Elevations - |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7108 | Steel For Piperack 10-PRK-0P02 - Elevations - |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7109 | Steel For Piperack 10-PRK-0P02 - Details - |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7200 | Steel For Pipe Rack 10-PRK-0P03 - 3D View |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7201 | Steel For Pipe Rack 10-PRK-0P03 - Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7202 | Steel For Pipe Rack 10-PRK-0P03 - Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7203 | Steel For Pipe Rack 10-PRK-0P03 - Elevations - Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7204 | Steel For Pipe Rack 10-PRK-0P03 - Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7205 | Steel For Pipe Rack 10-PRK-0P03 - Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7206 | Steel For Pipe Rack 10-PRK-0P03 - Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7207 | Steel For Pipe Rack 10-PRK-0P03 - Elevations - Stair |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7208 | Steel For Pipe Rack 10-PRK-0P03 - Details |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7360 | STEEL FOR SUPPORTS - 1B |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7380 | Steel Structure For 10-T-2040 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-26; R1 IFI: 2020-06-10; R1 IFD: 2020-07-25
[6 empty] | Revised Plan | IFR: 2020-02-26; R1 IFI: 2020-06-10; R1 IFD: 2020-07-25
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7420 | Steel Structures For Concrete Basin 10-PIT-2090 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-07
[6 empty] | Revised Plan | IFR: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7440 | STEEL FOR PLATFORMS - 2A |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7460 | STEEL FOR SUPPORTS - 2A |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7480 | Steel Railing For Protection Of Basin 10-PIT-2190 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-07
[6 empty] | Revised Plan | IFR: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7520 | Steel Structures for Concrete Basin 10-PIT-2392 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-07
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7540 | STEEL FOR PLATFORMS - 2B |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7560 | STEEL FOR SUPPORTS - 2B |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7580 | Steel Railng For Protection Of Basin 10-PIT-2790 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-07
[6 empty] | Revised Plan | IFR: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7600 | STEEL FOR PLATFORMS - 2C |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7620 | STEEL FOR SUPPORTS - 2C |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7640 | STEEL STRUCTURE FOR 10-C-2850, 10-E-2850 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-26; R1 IFI: 2020-06-10; R1 IFD: 2020-07-25
[6 empty] | Revised Plan | IFR: 2020-02-26; R1 IFI: 2020-06-10; R1 IFD: 2020-07-25
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7660 | STEEL STRUCTURE FOR 10-C-2800, 10-E-2800 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-26; R1 IFI: 2020-06-10; R1 IFD: 2020-07-25
[6 empty] | Revised Plan | IFR: 2020-02-26; R1 IFI: 2020-06-10; R1 IFD: 2020-07-25
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7680 | STEEL FOR PLATFORMS - 2D |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7700 | STEEL FOR SUPPORTS - 2D |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7720 | STEEL STRUCTURE FOR 10-C-2200, 10-E-2200 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-26; R1 IFI: 2020-06-10; R1 IFD: 2020-07-25
[6 empty] | Revised Plan | IFR: 2020-02-26; R1 IFI: 2020-06-10; R1 IFD: 2020-07-25
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7740 | Steel Railing For Protection Of Basin 10-PIT-2390 |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-07
[6 empty] | Revised Plan | IFR: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7760 | STEEL FOR PLATFORMS - 2E |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7780 | STEEL FOR SUPPORTS - 2E |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-7940 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5642 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-22; R1 IFI: 2019-10-21
[6 empty] | Revised Plan | IFR: 2020-02-14; R1 IFI: 2019-10-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8080 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5615 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-22; R1 IFI: 2019-10-21
[6 empty] | Revised Plan | IFR: 2020-02-14; R1 IFI: 2019-10-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8100 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5656 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-22; R1 IFI: 2019-10-21
[6 empty] | Revised Plan | IFR: 2020-02-14; R1 IFI: 2019-10-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8140 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5650A/B |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-22; R1 IFI: 2019-10-21
[6 empty] | Revised Plan | IFR: 2020-02-14; R1 IFI: 2019-10-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8160 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5655 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-22; R1 IFI: 2019-10-21
[6 empty] | Revised Plan | IFR: 2020-02-14; R1 IFI: 2019-10-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8180 | STEEL RAILING FOR PROTECTION OF BASIN 10-PIT-5671 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-22; R1 IFI: 2019-10-21
[6 empty] | Revised Plan | IFR: 2020-02-14; R1 IFI: 2019-10-21
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8240 | STEEL FOR STRUCTURE 10-STR-2C08 - ADDED 15-JUNE-2019 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8260 | Steel For Structure 10-STR-2B03 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8261 | Steel For Structure 10-STR-2B03 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
[6 empty] | Revised Plan | IFR: 2020-05-25; R1 IFI: 2020-07-24; R1 IFD: 2020-09-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8280 | ZONE 1B - MISCELLANEOUS STEEL STRUCTURES |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-11; R1 IFI: 2020-03-12
[6 empty] | Revised Plan | IFR: 2020-02-11; R1 IFI: 2020-03-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8281 | Steel for Pipe Rack 10-PRK-5U01 - Plans |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8282 | Steel for Pipe Rack 10-PRK-5U01 - Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8283 | Steel For Pipe Bridge 10-PRK-5W01 - Plans And Elevations |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8284 | Steel For Pipe Bridge 10-PRK-5W01 - Connection Details |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
[6 empty] | Revised Plan | IFR: 2019-11-28; R1 IFI: 2020-02-01; R1 IFD: 2020-03-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8286 | Steel Railing For Protection Of Basin 10-PIT-5633 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-08-22; R1 IFI: 2019-10-21
[6 empty] | Revised Plan | IFR: 2019-10-09; R1 IFI: 2019-10-21
[6 empty] | Issue Actual | IFR: 2019-10-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02740
Return Date
Owner Cmmt*
| CV | OL1-2K32-8291 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8292 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8293 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8294 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8295 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8296 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8297 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8298 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8299 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 009 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8300 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 010 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8301 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 011 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8302 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 012 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8303 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 013 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8304 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 014 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8305 | STEEL PLATF. FOR COOLING TOWER 5350 - Sh. 015 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-04-21; R1 IFD: 2020-05-21; R1 IFF: 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8311 | STEEL FOR PLATFORMS - 5W - Sh. 001 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K32-8312 | STEEL FOR PLATFORMS - 5W - Sh. 002 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
[6 empty] | Revised Plan | IFR: 2020-06-17; R1 IFI: 2020-08-01; R1 IFD: 2020-09-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K33 Shop Detail Drawings
Category Code: K34 Foundation for equipment, basin, cooling tower, supports and miscellaneous
| CV | OL1-2K34-0007 | Foundation For 10-D-5200 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0008 | Foundation For 10-E-5200 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-08; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0009 | Foundation For 10-E-5210 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0015 | Foundation for 10-D-5150 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0016 | Foundation For 10-D-2160 |  |  | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28; R1 IFI: 2019-10-15
[6 empty] | Issue Actual | IFR: 2019-01-28; R1 IFI: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00734; R1 IFI: TPSPK-LSPA1-T-CV-02835
[6 empty] | Return Date | IFR: 2019-03-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0020 | Foundation For 10-E-2136 |  |  | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-08
[6 empty] | Issue Actual | IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0023 | Foundation For 10-E-2166 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-08; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0024 | Foundation For 10-E-2146 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0026 | Foundation For 10-E-2026 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0027 | Foundation For 10-E-2048 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-06; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0042 | Foundation For 10-T-2330 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0043 | Foundation For 10-D-2410 A/B/C |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0044 | Foundation For 10-D-2435 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0046 | Foundation For 10-D-2240 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0047 | Foundation For 10-D-2245 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0048 | Foundation For 10-D-2445 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0049 | Foundation For 10-D-2455 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-11; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00833
[6 empty] | Return Date | IFR: 2019-05-31
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0050 | Foundation For 10-D-2220 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0055 | Foundation For 10-D-2310 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-08; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00826
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0057 | Foundation For 10-D-2316 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-06; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0059 | Foundation For 10-D-2330 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-06; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0074 | Foundation For 10-D-2305 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-08; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00826
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0076 | Foundation For 10-E-2630 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-08; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0095 | Foundation For 10-T-2640 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-20; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01105
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0099 | Foundation for 10-T-2520/10-D-2520 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-01-28; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | IFR: 2019-03-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0105 | Foundation For 10-D-2815 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-01-28; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00734
[6 empty] | Return Date | IFR: 2019-03-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0108 | Foundation For 10-D-2645 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-06; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0109 | Foundation For 10-D-2555 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-21; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0110 | Foundation For 10-D-2550 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-21; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0112 | Foundation For 10-D-2575 |  |  | Purpose** | IFR: CAN; R1 IFI: IFR
[6 empty] | Rev. | IFR: 0; R1 IFI: A
Issue Plan
[6 empty] | Revised Plan | R1 IFI: 2019-02-15
[6 empty] | Issue Actual | R1 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSPK-LSPA1-T-CV-02835; R1 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | R1 IFI: 2019-04-12
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K34-0114 | Foundation For 10-D-2870 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-01-28; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | IFR: 2019-03-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0115 | Foundation For 10-D-2860 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-01-28; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00734
[6 empty] | Return Date | IFR: 2019-03-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0116 | Foundation For 10-D-2865 |  |  | Purpose** | IFR: CAN; R1 IFI: IFR
[6 empty] | Rev. | IFR: 0; R1 IFI: A
Issue Plan
[6 empty] | Revised Plan | R1 IFI: 2019-02-15
[6 empty] | Issue Actual | R1 IFI: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSPK-LSPA1-T-CV-02835; R1 IFI: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | R1 IFI: 2019-04-12
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K34-0122 | Foundation For 10-E-2576 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-08; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0123 | Foundation for 10-E-2645A/B |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-14; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01042
[6 empty] | Return Date | IFR: 2019-06-04
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0124 | Foundation for 10-E-2502 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-01-28; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | IFR: 2019-03-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0125 | Foundation for 10-E-2515 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-08; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0126 | Foundation For 10-E-2546 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0127 | Foundation For 10-E-2548 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0128 | Foundation For 10-E-2545 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-01-31; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00763
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0130 | Foundation For 10-E-2807 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0131 | Foundation For 10-E-2809 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0132 | Foundation For 10-E-2857 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-06; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00807
[6 empty] | Return Date | IFR: 2019-03-18
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0133 | Foundation For 10-E-2858 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0134 | Foundation For 10-E-2856 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0135 | Foundation For 10-E-2855 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-21; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0136 | Foundation For 10-E-2853 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00868
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0137 | Foundation For 10-E-2852 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0139 | Foundation For 10-E-2582 |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-02-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854; R1 IFI: TPSK-LSPA1-T-CV-00903
[6 empty] | Return Date | IFR: 2019-04-12; R1 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2K34-0140 | Foundation For 10-E-2504 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-01-31; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00763
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0146 | Foundation For 10-E-2620 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0155 | Foundation For 10-D-2610 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-11; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00833
[6 empty] | Return Date | IFR: 2019-05-31
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0156 | Foundation For 10-D-2600 A-B |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-11; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00833
[6 empty] | Return Date | IFR: 2019-05-31
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0161 | Foundation For 10-E-2636 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-08; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01004
Return Date
Owner Cmmt*
| CV | OL1-2K34-0167 | Foundation For 10-E-1020 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-04-02; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01208
[6 empty] | Return Date | IFR: 2019-06-07
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0168 | Foundation For 10-E-1015 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0169 | Foundation For 10-E-1001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01034
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0191 | Foundation For 10-E-2008A/B/C/D/E |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00854
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0202 | Foundation For 10-E-1050 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-04-02; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01208
[6 empty] | Return Date | IFR: 2019-06-07
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0209-SH.001 | FOUNDATION AND ELEVATION FOR 10-C-3070 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0209-SH.002 | FOUNDATION AND ELEVATION FOR 10-C-3070 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.001 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.002 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.003 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.004 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.005 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.006 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.007 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.008 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.009 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 009 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0249-SH.010 | FOUNDATION FOR 10-P-3080A/B,10-P-3030A/B,10-P-3000A/B,10-P-3020A/B,10-P-3061A/B,10-P-3060A/B,10-P-3062A/B,10-P-3002 - Sh. 010 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.001 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.002 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.003 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.004 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.005 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.006 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.007 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.008 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.009 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 009 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.010 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 010 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0250-SH.011 | FOUNDATION FOR 10-P-3096A/B,10-P-3086A/B,10-P-3036A/B,10-P-3016A/B,10-P-3900,10-P-3160A/B,10-P-3076A/B,10-P-3906A/B - Sh. 011 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0252-SH.001 | FOUNDATION FOR PUMPS 10-P-5900A/B, 10-P-5950A/B - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0252-SH.002 | FOUNDATION FOR PUMPS 10-P-5900A/B, 10-P-5950A/B - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0253-SH.001 | FOUNDATION FOR PUMPS 10-P-5360A/B/C - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0253-SH.002 | FOUNDATION FOR PUMPS 10-P-5360A/B/C - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0254-SH.001 | FOUNDATION FOR PUMPS 10-P-5350 A/B/C/D/E/F/G/H - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0254-SH.002 | FOUNDATION FOR PUMPS 10-P-5350 A/B/C/D/E/F/G/H - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0258-SH.001 | FOUNDATION FOR 10-PK-5560 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0258-SH.002 | FOUNDATION FOR 10-PK-5560 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0258-SH.003 | FOUNDATION FOR 10-PK-5560 - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0276-SH.001 | FOUNDATION FOR PUMPS 10-P-5550A/B, 10-P-5552 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0276-SH.002 | FOUNDATION FOR PUMPS 10-P-5550A/B, 10-P-5552 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0277-SH.001 | FOUNDATION FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0277-SH.002 | FOUNDATION FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0277-SH.003 | FOUNDATION FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0277-SH.004 | FOUNDATION FOR PUMPS 10-P-5110A/B, 10-P-5120A/B, 10-P-5130A/B, 10-P-5500A/B - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0281-SH.001 | FOUNDATION FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0281-SH.002 | FOUNDATION FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0281-SH.003 | FOUNDATION FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0281-SH.004 | FOUNDATION FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0281-SH.005 | FOUNDATION FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0281-SH.006 | FOUNDATION FOR PUMPS 10-P-5620A/B/C,10-P-5621,10-P-5650A/B, 10-P-5651A/B, 10-P-5640A/B, 10-P-5641 - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0287-SH.001 | FOUNDATION FOR 10-PK-5627, 10-PIT-5627, P-10-5627A/B - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0287-SH.002 | FOUNDATION FOR 10-PK-5627, 10-PIT-5627, P-10-5627A/B - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0296-SH.001 | FOUNDATION FOR 10-PK-5670 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0296-SH.002 | FOUNDATION FOR 10-PK-5670 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0297-SH.001 | FOUNDATION FOR 10-P-5670A/B,10-P-5671A/B,10-P-5644A/B,10-P-5645A/B,10-P-5646A/B,10-P-5647A/B,10-P-5675,10-P-5676 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0297-SH.002 | FOUNDATION FOR 10-P-5670A/B,10-P-5671A/B,10-P-5644A/B,10-P-5645A/B,10-P-5646A/B,10-P-5647A/B,10-P-5675,10-P-5676 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0297-SH.003 | FOUNDATION FOR 10-P-5670A/B,10-P-5671A/B,10-P-5644A/B,10-P-5645A/B,10-P-5646A/B,10-P-5647A/B,10-P-5675,10-P-5676 - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0297-SH.004 | FOUNDATION FOR 10-P-5670A/B,10-P-5671A/B,10-P-5644A/B,10-P-5645A/B,10-P-5646A/B,10-P-5647A/B,10-P-5675,10-P-5676 - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0297-SH.005 | FOUNDATION FOR 10-P-5670A/B,10-P-5671A/B,10-P-5644A/B,10-P-5645A/B,10-P-5646A/B,10-P-5647A/B,10-P-5675,10-P-5676 - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0297-SH.006 | FOUNDATION FOR 10-P-5670A/B,10-P-5671A/B,10-P-5644A/B,10-P-5645A/B,10-P-5646A/B,10-P-5647A/B,10-P-5675,10-P-5676 - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0297-SH.007 | FOUNDATION FOR 10-P-5670A/B,10-P-5671A/B,10-P-5644A/B,10-P-5645A/B,10-P-5646A/B,10-P-5647A/B,10-P-5675,10-P-5676 - Sh. 007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0297-SH.008 | FOUNDATION FOR 10-P-5670A/B,10-P-5671A/B,10-P-5644A/B,10-P-5645A/B,10-P-5646A/B,10-P-5647A/B,10-P-5675,10-P-5676 - Sh. 008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0306 | Foundation for 10-D-5140 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-01-28; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00728
[6 empty] | Return Date | IFR: 2019-03-27
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-0324-SH.001 | FOUNDATION FOR 10-TK-5950 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-0324-SH.002 | FOUNDATION FOR 10-TK-5950 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1001 | Foundation for 10-T-2000 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-21; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-1020 | Foundation For 10-T-2020 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-03-21; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K34-1040 | Foundation For 10-T-2100 |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFD: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-02-21; R1 IFD: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-02-21; R1 IFI: 2019-03-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00903; R1 IFI: TPSK-LSPA1-T-CV-01104
[6 empty] | Return Date | IFR: 2019-04-12; R1 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2K34-1400-SH.001 | FOUNDATION FOR LIFTING STATION 10-PIT-5370 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1400-SH.002 | FOUNDATION FOR LIFTING STATION 10-PIT-5370 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1480-SH.001 | FOUNDATION FOR BASIN 10-PIT-5615 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1480-SH.002 | FOUNDATION FOR BASIN 10-PIT-5615 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1480-SH.003 | FOUNDATION FOR BASIN 10-PIT-5615 - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1480-SH.004 | FOUNDATION FOR BASIN 10-PIT-5615 - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1500-SH.001 | FOUNDATION FOR BASIN 10-PIT-5656 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1500-SH.002 | FOUNDATION FOR BASIN 10-PIT-5656 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1500-SH.003 | FOUNDATION FOR BASIN 10-PIT-5656 - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1500-SH.004 | FOUNDATION FOR BASIN 10-PIT-5656 - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1500-SH.005 | FOUNDATION FOR BASIN 10-PIT-5656 - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1500-SH.006 | FOUNDATION FOR BASIN 10-PIT-5656 - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1600-SH.001 | FOUNDATION FOR BASIN 10-PIT-5671 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1600-SH.002 | FOUNDATION FOR BASIN 10-PIT-5671 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1620-SH.001 | FOUNDATION FOR BASIN 10-PIT-5650A/B - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1620-SH.002 | FOUNDATION FOR BASIN 10-PIT-5650A/B - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1620-SH.003 | FOUNDATION FOR BASIN 10-PIT-5650A/B - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1620-SH.004 | FOUNDATION FOR BASIN 10-PIT-5650A/B - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1640-SH.003 | FOUNDATION FOR BASIN 10-PIT-5655 - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1640-SH.004 | FOUNDATION FOR BASIN 10-PIT-5655 - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1640-SH001 | FOUNDATION FOR BASIN 10-PIT-5655 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1640-SH002 | FOUNDATION FOR BASIN 10-PIT-5655 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1680-SH.001 | FOUNDATION FOR CLARIFIER 10-TK-5651A/B - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1680-SH.002 | FOUNDATION FOR CLARIFIER 10-TK-5651A/B - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1680-SH.003 | FOUNDATION FOR CLARIFIER 10-TK-5651A/B - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1680-SH.004 | FOUNDATION FOR CLARIFIER 10-TK-5651A/B - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1680-SH.005 | FOUNDATION FOR CLARIFIER 10-TK-5651A/B - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1680-SH.006 | FOUNDATION FOR CLARIFIER 10-TK-5651A/B - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1680-SH.007 | FOUNDATION FOR CLARIFIER 10-TK-5651A/B - Sh. 007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1680-SH.008 | FOUNDATION FOR CLARIFIER 10-TK-5651A/B - Sh. 008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
[6 empty] | Revised Plan | IFR: 2019-12-24; R1 IFI: 2020-01-24
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1700-SH.001 | FOUNDATION FOR METERING STATION - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1700-SH.002 | FOUNDATION FOR METERING STATION - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-1700-SH.003 | FOUNDATION FOR METERING STATION - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2060-SH.001 | FOUNDATION FOR SUPPORTS FLARE UNIT - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2060-SH.002 | FOUNDATION FOR SUPPORTS FLARE UNIT - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2060-SH.003 | FOUNDATION FOR SUPPORTS FLARE UNIT - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2080-SH.001 | FOUNDATION FOR PLATFORMS - 3A - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2080-SH.002 | FOUNDATION FOR PLATFORMS - 3A - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2080-SH.003 | FOUNDATION FOR PLATFORMS - 3A - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2080-SH.004 | FOUNDATION FOR PLATFORMS - 3A - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2080-SH.005 | FOUNDATION FOR PLATFORMS - 3A - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2080-SH.006 | FOUNDATION FOR PLATFORMS - 3A - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2080-SH.007 | FOUNDATION FOR PLATFORMS - 3A - Sh. 007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2080-SH.008 | FOUNDATION FOR PLATFORMS - 3A - Sh. 008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2100-SH.001 | FOUNDATION FOR SUPPORTS - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2100-SH.002 | FOUNDATION FOR SUPPORTS - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2100-SH.003 | FOUNDATION FOR SUPPORTS - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2100-SH.004 | FOUNDATION FOR SUPPORTS - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2100-SH.005 | FOUNDATION FOR SUPPORTS - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2100-SH.006 | FOUNDATION FOR SUPPORTS - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2100-SH.007 | FOUNDATION FOR SUPPORTS - Sh. 007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2100-SH.008 | FOUNDATION FOR SUPPORTS - Sh. 008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2120-SH.001 | FOUNDATION FOR SUPPORTS - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2120-SH.002 | FOUNDATION FOR SUPPORTS - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2120-SH.003 | FOUNDATION FOR SUPPORTS - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2140-SH.001 | FOUNDATION FOR SUPPORTS - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2140-SH.002 | FOUNDATION FOR SUPPORTS - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2160-SH.001 | FOUNDATION FOR PLATFORMS - 5T - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2160-SH.002 | FOUNDATION FOR PLATFORMS - 5T - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2160-SH.003 | FOUNDATION FOR PLATFORMS - 5T - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2160-SH.004 | FOUNDATION FOR PLATFORMS - 5T - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2160-SH.005 | FOUNDATION FOR PLATFORMS - 5T - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2160-SH.006 | FOUNDATION FOR PLATFORMS - 5T - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2160-SH.007 | FOUNDATION FOR PLATFORMS - 5T - Sh. 007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2160-SH.008 | FOUNDATION FOR PLATFORMS - 5T - Sh. 008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2180-SH.001 | FOUNDATION FOR SUPPORTS - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2180-SH.002 | FOUNDATION FOR SUPPORTS - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2180-SH.003 | FOUNDATION FOR SUPPORTS - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2180-SH.004 | FOUNDATION FOR SUPPORTS - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2180-SH.005 | FOUNDATION FOR SUPPORTS - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2180-SH.006 | FOUNDATION FOR SUPPORTS - Sh. 006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2180-SH.007 | FOUNDATION FOR SUPPORTS - Sh. 007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2180-SH.008 | FOUNDATION FOR SUPPORTS - Sh. 008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2200-SH.001 | FOUNDATION FOR SUPPORTS - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2200-SH.002 | FOUNDATION FOR SUPPORTS - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2200-SH.003 | FOUNDATION FOR SUPPORTS - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2220-SH.001 | FOUNDATION FOR PLATFORMS - 5W - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2220-SH.002 | FOUNDATION FOR PLATFORMS - 5W - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2220-SH.003 | FOUNDATION FOR PLATFORMS - 5W - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2220-SH.004 | FOUNDATION FOR PLATFORMS - 5W - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2220-SH.005 | FOUNDATION FOR PLATFORMS - 5W - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2240-SH.001 | FOUNDATION FOR SUPPORTS - 5W - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2240-SH.002 | FOUNDATION FOR SUPPORTS - 5W - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2240-SH.003 | FOUNDATION FOR SUPPORTS - 5W - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2240-SH.004 | FOUNDATION FOR SUPPORTS - 5W - Sh. 004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2240-SH.005 | FOUNDATION FOR SUPPORTS - 5W - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2260-SH.001 | FOUNDATION FOR PLATFORMS - 5F - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2260-SH.002 | FOUNDATION FOR PLATFORMS - 5F - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2260-SH.003 | FOUNDATION FOR PLATFORMS - 5F - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2280-SH.001 | FOUNDATION FOR PLATFORMS - 5U - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2280-SH.002 | FOUNDATION FOR PLATFORMS - 5U - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2280-SH.003 | FOUNDATION FOR PLATFORMS - 5U - Sh. 003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2360-SH.005 | FOUNDATION FOR 10-SLW-5W01 - Sh. 005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2380-SH.001 | FOUNDATION FOR 10-SLW-5F01 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2380-SH.002 | FOUNDATION FOR 10-SLW-5F01 - Sh. 002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
[6 empty] | Revised Plan | IFR: 2020-05-02; R1 IFI: 2020-06-02
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K34-2500-SH001 | BASIN FOR COOLING TOWER 10-PIT-5350 - Sh. 001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-13; R1 IFI: 2020-03-15; R1 IFD: 2020-04-05; R1 IFF: 2020-04-26
[6 empty] | Revised Plan | IFR: 2020-01-13; R1 IFI: 2020-03-15; R1 IFD: 2020-04-05; R1 IFF: 2020-04-26
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: K36 Major UG networks (Nuovo codice richiesto dal Cliente K26/K27)
| CV | OL1-2K36-0001 | Major Underground Networks Zone 0S - Substation-E And Far-E |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K36-0002 | Major Undergroud Networks - Zone 1B - Furnaces Utilities- For Next Revision See OL1-2K26-0002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K36-0005 | Major Underground Networks - Zone 2C - Hot Fractination-Ghu Unit |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K36-0009 | Major Underground Networks - Zone 3S - Substation-C Far-C |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K36-0010 | Major Underground Networks - Zone 5T - Cooling Water Unit |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K36-0011 | Major Underground Networks - Zone 5U - Utilities |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K36-0012 | Major Underground Networks - Zone 5W - Waste Water Treatment |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-26
[6 empty] | Issue Actual | IFR: 2019-03-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01138
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K36-0013 | Major Underground Network And Finishing Layout - Zone 5F - HP And Polyefins Flares Unit |  |  | Purpose** | IFR: IFR; R1 IFI: IDD
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-06-18; R1 IFI: 2019-12-20
[6 empty] | Revised Plan | IFR: 2019-04-04; R1 IFI: 2019-12-20
[6 empty] | Issue Actual | IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01240
[6 empty] | Return Date | IFR: 2019-06-05
Owner Cmmt* | bar: IFR
| CV | OL1-2K36-0014 | Major Underground Networks Zone 0C - Common Area |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-28
[6 empty] | Issue Actual | IFR: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01172
Return Date
Owner Cmmt*
| CV | OL1-2K36-1000 | Major Underground Networks- For Next Revision See OL1-2K26-1000 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-18
[6 empty] | Issue Actual | IFR: 2019-03-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01073
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
Category Code: K40 Topographic survey report
Category Code: K41 Hydrological survey report
Category Code: K42 Bathymetric survey report
Category Code: K43 Soil investigation & resisitivity report
| CV | OL1-2K43-0002 | Technical Specification for Geotechnical Investigation |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2018-10-08; R1 IFD: 2019-12-17
[6 empty] | Revised Plan | IFR: 2018-10-09; R1 IFD: 2019-12-17
[6 empty] | Issue Actual | IFR: 2018-10-09; R1 IFI: 2018-10-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00147; R1 IFI: TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date | IFR: 2018-12-24; R1 IFI: 2018-11-01
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2K43-0003 | Price List for Geotechnical Investigation |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-09
[6 empty] | Issue Actual | IFR: 2018-10-09; R1 IFI: 2018-10-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00147; R1 IFI: TPSK-LSPA1-T-CV-00188
[6 empty] | Return Date | IFR: 2018-12-24; R1 IFI: 2018-11-01
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2K43-0004 | Soil Investigation Plan |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2018-10-08; R1 IFD: 2019-12-17
[6 empty] | Revised Plan | IFR: 2018-10-09; R1 IFD: 2019-12-17
[6 empty] | Issue Actual | IFR: 2018-10-09; R1 IFI: 2018-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00145; R1 IFI: TPSK-LSPA1-T-CV-00163
[6 empty] | Return Date | IFR: 2018-12-24; R1 IFI: 2018-12-24
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2K43-0005 | Olefin Plant - Additional Ground Investigation - Phase 1 -Platform at 4-5m HDD- Price List |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFI; R1 IFF: IMP
Rev. | bar: R1 IFI to R1 IFD
[6 empty] | Issue Plan | IFR: 2019-05-31; R1 IFF: 2019-08-30
[6 empty] | Revised Plan | R1 IFI: 2019-06-11
[6 empty] | Issue Actual | R1 IFI: 2019-06-11; R1 IFD: 2019-06-24
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01861; R1 IFD: TPSK-LSPA1-T-CV-01963
[6 empty] | Return Date | R1 IFI: 2019-06-27
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K43-0006 | Olefins Plant - Additional Ground Investigation Phase 1 -Platform at 4-5m HDD - Layout of Site Investigations |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2018-10-08; R1 IFD: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-05-31
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01768; R1 IFI: TPSK-LSPA1-T-CV-01853
[6 empty] | Return Date | IFR: 2019-07-16
Owner Cmmt* | bar: IFR
| CV | OL1-2K43-0007 | Olefin Plant - Additional Ground Investigation - Phase 2 -Platform at 6-7m HDD- Price List |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFI; R1 IFF: IMP
Rev. | bar: R1 IFI to R1 IFD
[6 empty] | Issue Plan | IFR: 2019-05-31; R1 IFF: 2019-08-30
[6 empty] | Revised Plan | R1 IFI: 2019-06-11
[6 empty] | Issue Actual | R1 IFI: 2019-06-11; R1 IFD: 2019-06-24
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-01861; R1 IFD: TPSK-LSPA1-T-CV-01963
[6 empty] | Return Date | R1 IFI: 2019-06-27
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2K43-0008 | Olefins Plant - Additional Ground Investigation Phase 2 Platform At 6-7m HDD - Layout Of Site Investigations |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2018-10-08; R1 IFD: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-05-31
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-06-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01768
[6 empty] | Return Date | IFR: 2019-07-16
Owner Cmmt* | bar: IFR
| CV | OL1-2K43-0009 | Flare Area - Additional Ground Investigation- Price List |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-05-31; R1 IFI: 2019-08-30
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2K43-0010 | Flare Area - Additional Ground Investigation Layout Of Site Investigations |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2018-10-08; R1 IFI: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-05-31
[6 empty] | Issue Actual | IFR: 2019-05-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01768
[6 empty] | Return Date | IFR: 2019-07-16
Owner Cmmt* | bar: IFR
Category Code: K50 Concrete Test Results
Category Code: K71 Appraisal Report for Consultancy Service
Category Code: K72 Appraisal Report for EPC Contractor Work
Category Code: K73 Appraisal Report for Vendor/Supplier
Category Code: K90 Vendor Document/drawings
Category Code: K91 Index/List
Category Code: K92 Procedures & Standards
| CV | OL1-2K92-0001 | General Notes For Underground Works |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-24; R1 IFI: 2019-02-10
[6 empty] | Revised Plan | IFR: 2018-09-27; R1 IFI: 2019-02-01
[6 empty] | Issue Actual | IFR: 2018-09-27; R1 IFI: 2019-02-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00086; R1 IFI: TPSK-LSPA1-T-CV-00784
[6 empty] | Return Date | IFR: 2018-11-02; R1 IFI: 2019-02-25
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2K92-0002 | General Notes For Precast Concrete Works |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-05; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | IFR: 2018-10-08; R1 IFI: 2019-07-11
[6 empty] | Issue Actual | IFR: 2018-10-08; R1 IFI: 2019-07-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00137; R1 IFI: TPSK-LSPA1-T-CV-02119
[6 empty] | Return Date | IFR: 2018-12-24; R1 IFI: 2019-10-04
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2K92-0003 | General Notes For Concrete Works |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-24; R1 IFI: 2019-01-15
[6 empty] | Revised Plan | IFR: 2018-09-27; R1 IFI: 2019-02-19
[6 empty] | Issue Actual | IFR: 2018-09-27; R1 IFI: 2019-02-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00086; R1 IFI: TPSK-LSPA1-T-CV-00886
[6 empty] | Return Date | IFR: 2018-11-02; R1 IFI: 2019-03-27
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2K92-0004 | General Notes For Steel Structures |  |  | Purpose** | IFR: IFR; R1 IFI: IFC; R1 IFD: IFC
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 2
[6 empty] | Issue Plan | IFR: 2018-09-24; R1 IFI: 2019-01-15
[6 empty] | Revised Plan | IFR: 2018-09-27; R1 IFI: 2019-02-15
[6 empty] | Issue Actual | IFR: 2018-09-27; R1 IFI: 2019-02-15; R1 IFD: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00086; R1 IFI: TPSK-LSPA1-T-CV-00867; R1 IFD: TPSK-LSPA1-T-CV-02054
[6 empty] | Return Date | IFR: 2018-11-02; R1 IFI: 2019-03-27; R1 IFD: 2019-08-29
[6 empty] | Owner Cmmt* | IFR: R1; R1 IFI: A2; R1 IFD: A1
| CV | OL1-2K92-0005 | General Notes for Bored Piles |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-04-01
[6 empty] | Revised Plan | IFR: 2019-03-20; R1 IFI: 2019-09-12
[6 empty] | Issue Actual | IFR: 2019-03-20; R1 IFI: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01093; R1 IFI: TPSK-LSPA1-T-CV-02621
[6 empty] | Return Date | IFR: 2019-04-12
Owner Cmmt* | bar: IFR
| CV | OL1-2K92-0006 | General Notes For Spun Piles |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-12
[6 empty] | Issue Actual | IFR: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-02621
Return Date
Owner Cmmt*
Category Code: K93 Policy , Guidelines & Memo
Category Code: K94 Forms & Templates
Category Code: K95 Progress/Status Reports
Category Code: K97 Technical Specification/Price list for Architectural Works
| CV | OL1-2K97-0001 | Technical Specification For Buildings |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-21
[6 empty] | Issue Actual | IFR: 2019-03-21
[6 empty] | Transmittal no. | IFR: 1117-TPSK-LSPA1-T-CV-01117
Return Date
Owner Cmmt*
Category Code: L01 Passive & Active Fire Protection Philosophy
| PE | OL1-2L01-0001 | Fire Fighting And Fire Protection |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-16; R1 IFI: 2019-02-13
[6 empty] | Revised Plan | IFR: 2019-02-01; R1 IFI: 2019-07-05
[6 empty] | Issue Actual | IFR: 2019-02-01; R1 IFI: 2019-07-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00782; R1 IFI: TPSK-LSPA1-T-SE-02079
[6 empty] | Return Date | IFR: 2019-03-18
Owner Cmmt* | bar: IFR
| PE | OL1-2L01-0002 | Fire Proof |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-01-18; R1 IFI: 2019-02-15
[6 empty] | Revised Plan | IFR: 2019-01-29
[6 empty] | Issue Actual | IFR: 2019-01-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00749
[6 empty] | Return Date | IFR: 2019-04-04
Owner Cmmt* | bar: IFR
| SE | OL1-2L01-0003 | Clean Agent Fire Extinguishing System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-01-16; R1 IFI: 2019-02-13
[6 empty] | Revised Plan | IFR: 2019-04-24
[6 empty] | Issue Actual | IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01441
Return Date
Owner Cmmt*
Category Code: L02 Active Fire Protection System
Category Code: L03 Firefighting equipment data sheet
| SE | OL1-2L03-0001 | Datasheet for Firefighting Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IFQ; R1 IFD: IFP; R1 IFF: IFQ
Rev. | bar: IFR to R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-08; R1 IFI: 2019-07-19; R1 IFD: 2019-10-09; R1 IFF: 2019-07-19
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-07-08; R1 IFD: 2019-12-13; R1 IFF: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-07-08; R1 IFF: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01840; R1 IFI: TPSK-LSPA1-T-SE-02090; R1 IFF: TPSK-LSPA1-T-SE-02090
[6 empty] | Return Date | IFR: 2019-07-08; R1 IFI: 2019-08-06; R1 IFF: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI; R1 IFF
| SE | OL1-2L03-1001 | Datasheet for Deluge System |  |  | Purpose** | IFR: IFR; R1 IFI: IFQ; R1 IFD: IFP; R1 IFF: IFQ
Rev. | bar: IFR to R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-08; R1 IFI: 2019-07-19; R1 IFD: 2019-10-09; R1 IFF: 2019-07-19
[6 empty] | Revised Plan | IFR: 2019-06-03; R1 IFI: 2019-07-08; R1 IFD: 2019-12-13; R1 IFF: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-06-03; R1 IFI: 2019-07-08; R1 IFF: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01746; R1 IFI: TPSK-LSPA1-T-SE-02090; R1 IFF: TPSK-LSPA1-T-SE-02090
[6 empty] | Return Date | IFR: 2019-07-01; R1 IFI: 2019-08-06; R1 IFF: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI; R1 IFF
| SE | OL1-2L03-2001 | Datasheet for Sprinkler System |  |  | Purpose** | IFR: IFR; R1 IFI: IFQ; R1 IFD: IFP; R1 IFF: IFQ
Rev. | bar: IFR to R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-08; R1 IFI: 2019-07-19; R1 IFD: 2019-10-09; R1 IFF: 2019-07-19
[6 empty] | Revised Plan | IFR: 2019-06-03; R1 IFI: 2019-07-08; R1 IFD: 2019-12-13; R1 IFF: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-06-03; R1 IFI: 2019-07-08; R1 IFF: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01746; R1 IFI: TPSK-LSPA1-T-SE-02090; R1 IFF: TPSK-LSPA1-T-SE-02090
[6 empty] | Return Date | IFR: 2019-07-01; R1 IFI: 2019-08-06; R1 IFF: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI; R1 IFF
| SE | OL1-2L03-3001 | Datasheet for Clean Agent Fire Extinguishing System |  |  | Purpose** | IFR: IFR; R1 IFI: IFQ; R1 IFD: IFP; R1 IFF: IFQ
Rev. | bar: IFR to R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-08; R1 IFI: 2019-07-19; R1 IFD: 2019-10-09; R1 IFF: 2019-07-19
[6 empty] | Revised Plan | IFR: 2019-06-17; R1 IFI: 2019-07-08; R1 IFD: 2019-12-13; R1 IFF: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-06-17; R1 IFI: 2019-07-08; R1 IFF: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01899; R1 IFI: TPSK-LSPA1-T-SE-02088; R1 IFF: TPSK-LSPA1-T-SE-02088
[6 empty] | Return Date | IFR: 2019-07-08; R1 IFI: 2019-07-29; R1 IFF: 2019-07-29
Owner Cmmt* | bar: IFR to R1 IFI; R1 IFF
| SE | OL1-2L03-5001 | Datasheet for Safety & Life Saving Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IFQ; R1 IFD: IFP; R1 IFF: IFQ
Rev. | bar: IFR to R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-08; R1 IFI: 2019-07-19; R1 IFD: 2019-10-09; R1 IFF: 2019-07-19
[6 empty] | Revised Plan | IFR: 2019-05-21; R1 IFI: 2019-07-08; R1 IFD: 2019-12-13; R1 IFF: 2019-07-08
[6 empty] | Issue Actual | IFR: 2019-05-21; R1 IFI: 2019-07-08; R1 IFF: 2019-07-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01703; R1 IFI: TPSK-LSPA1-T-SE-02090; R1 IFF: TPSK-LSPA1-T-SE-02090
[6 empty] | Return Date | IFR: 2019-06-10; R1 IFI: 2019-08-06; R1 IFF: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI; R1 IFF
Category Code: L08 Noise General Specification
Category Code: L09 Noise Map
| SE | OL1-2L09-0001 | Noise Map |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-31; R1 IFI: 2019-09-20
[6 empty] | Revised Plan | IFR: 2019-09-28; R1 IFI: 2019-11-29
[6 empty] | Issue Actual | IFR: 2019-09-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-02721
Return Date
Owner Cmmt*
Category Code: L10 Acoustic Calculation Note
| SE | OL1-2L10-0001 | Noise Control |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-04; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2018-12-11; R1 IFI: 2019-08-28
[6 empty] | Issue Actual | IFR: 2018-12-11; R1 IFI: 2019-08-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-00472; R1 IFI: TPSK-LSPA1-T-SE-02504
[6 empty] | Return Date | IFR: 2019-06-07; R1 IFI: 2019-10-04
Owner Cmmt* | bar: IFR to R1 IFI
| SE | OL1-2L10-0003 | Noise Insulation |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-04; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-04-25; R1 IFI: 2019-08-29
[6 empty] | Issue Actual | IFR: 2019-04-25; R1 IFI: 2019-08-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01461; R1 IFI: TPSK-LSPA1-T-SE-02523
[6 empty] | Return Date | IFR: 2019-06-25
Owner Cmmt* | bar: IFR
| SE | OL1-2L10-0004 | List For Acoustical Insulation On Lines And Associated Components |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-05
[6 empty] | Issue Actual | IFR: 2019-09-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-02569
[6 empty] | Return Date | IFR: 2019-10-03
Owner Cmmt* | bar: IFR
Category Code: L11 Noise Rep
Category Code: L20 Fire system calculation
| SE | OL1-2L20-0001 | Fire Water Demand Calculation And Hydraulic Study For FW Network |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-17; R1 IFI: 2020-03-06
[6 empty] | Revised Plan | IFR: 2019-03-08; R1 IFI: 2019-07-22
[6 empty] | Issue Actual | IFR: 2019-03-08; R1 IFI: 2019-07-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01006; R1 IFI: TPSK-LSPA1-T-SE-02200
[6 empty] | Return Date | IFR: 2019-04-09; R1 IFI: 2019-09-10
Owner Cmmt* | bar: IFR to R1 IFI
Category Code: L40 Active Fire Fighting Systems
| SE | OL1-2L40-0001 | Bill of Material for Firefighting and Safety Equipment |  |  | Purpose** | IFR: IFQ; R1 IFI: IFR; R1 IFD: IFP; R1 IFF: IFR
Rev. | bar: R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2019-07-05; R1 IFD: 2019-10-09
[6 empty] | Revised Plan | R1 IFI: 2019-07-23; R1 IFD: 2019-12-09; R1 IFF: 2019-07-23
[6 empty] | Issue Actual | R1 IFI: 2019-07-23; R1 IFF: 2019-07-23
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-SE-02205; R1 IFF: TPSK-LSPA1-T-SE-02205
[6 empty] | Return Date | R1 IFI: 2019-08-23; R1 IFF: 2019-08-23
Owner Cmmt* | bar: R1 IFI; R1 IFF
| SE | OL1-2L40-1000 | Overall Firewater Network Drawing |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-08; R1 IFI: 2019-05-08
[6 empty] | Revised Plan | IFR: 2019-04-01; R1 IFI: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-04-01; R1 IFI: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01198; R1 IFI: TPSK-LSPA1-T-SE-02172
[6 empty] | Return Date | IFR: 2019-05-14; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| SE | OL1-2L40-5701 | P&ID - FIRE WATER NETWORK (1/6) |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | 2019-05-09 |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 |  | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R1 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R1 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R1 IFI: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI
| SE | OL1-2L40-5702 | P&ID - FIRE WATER NETWORK (2/6) |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | 2019-05-09 |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 |  | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R1 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R1 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R1 IFI: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI
| SE | OL1-2L40-5703 | P&ID - FIRE WATER NETWORK (3/6) |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | 2019-05-09 |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 |  | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R1 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R1 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R1 IFI: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI
| SE | OL1-2L40-5704 | P&ID - FIRE WATER NETWORK (4/6) |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | 2019-05-09 |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 |  | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R1 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R1 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R1 IFI: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI
| SE | OL1-2L40-5705 | P&ID - FIRE WATER NETWORK (5/6) |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | 2019-05-09 |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 |  | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R1 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R1 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R1 IFI: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI
| SE | OL1-2L40-5706 | P&ID - FIRE WATER NETWORK (6/6) |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | 2019-05-09 |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 |  | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R1 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R1 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R1 IFI: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI
| SE | OL1-2L40-5707 | P&ID - DRY RISER SYSTEM |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5708 | P&ID - TYPICAL INSTALLATION OF FIRE PROTECTION EQUIPMENT |  |  | Purpose** | IFR | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | 2019-05-09 |  | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 |  | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02; R1 IFI: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520; R1 IFI: TPSK-LSPA1-T-SE-01622
[6 empty] | Return Date | IFR: 2019-06-16; R1 IFI: 2019-08-06
Owner Cmmt* | bar: IFR to R1 IFI
| SE | OL1-2L40-5709 | P&ID - AUTOMATIC PNEUMATIC & ELECTRIC OPERATED DELUGE SYSTEM |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5710 | P&ID - AUTOMATIC ELECTRIC OPERATED DELUGE SYSTEM |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5711 | P&ID - MANUAL ELECTRIC OPERATED DELUGE SYSTEM |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5712 | P&ID - PRE-ACTION DOUBLE INTERLOCK SPRINKLER SYSTEM |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5713 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 0S |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5714 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2A |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5715 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5716 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2C (1/2) |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5717 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2C (2/2) |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5718 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (1/3) |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5719 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (2/3) |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5720 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2D (3/3) |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5721 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 2E |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5722 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3A (1/2) |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5723 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3A (2/2) |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5724 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 3S |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5725 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 5F |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5726 | P&ID - FIRE WATER SPRAY SYSTEM - ZONE 5U |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5727 | P&ID - FIRE WATER CURTAIN SYSTEM - ZONE 1B |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5728 | P&ID - SPRINKLER SYSTEM - SUBSTATION E CABLE CELLAR |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5729 | P&ID - SPRINKLER SYSTEM - SUBSTATION C CABLE CELLAR |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
| SE | OL1-2L40-5730 | P&ID - SPRINKLER SYSTEM - SUBSTATION F CABLE CELLAR |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-30 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-05-02 | 2019-11-15 | 2020-04-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01520
[6 empty] | Return Date | IFR: 2019-06-16
Owner Cmmt* | bar: IFR
Category Code: L41 Passive Fire Protection Drawings
Category Code: L42 Hazardous Area Classification
| PE | OL1-2L42-0001 | Hazardous Area Classification - Overall |  |  | Purpose** | IFR: IFR; R1 IFI: IFA
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-20
[6 empty] | Revised Plan | R1 IFI: 2019-03-12
[6 empty] | Issue Actual | R1 IFI: 2019-03-12
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | R1 IFI: 2019-03-25
Owner Cmmt* | bar: R1 IFI
| SE | OL1-2L42-0002 | Hazardous Area Classification - Zone 0M - Metering Station |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0003 | Hazardous Area Classification - Zone 0P - Main Pipe Rack |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0004 | Hazardous Area Classification - Zone 0S - Electrical Substation and Far E |  | Class 1 | Purpose** | IFR: IFA
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12
[6 empty] | Issue Actual | IFR: 2019-03-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | IFR: 2019-03-25
Owner Cmmt* | bar: IFR
| SE | OL1-2L42-0005 | Hazardous Area Classification - Zone 3S -Electrical and Substation and Far C |  | Class 1 | Purpose** | IFR: IFA
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-12
[6 empty] | Issue Actual | IFR: 2019-03-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | IFR: 2019-03-25
Owner Cmmt* | bar: IFR
| SE | OL1-2L42-0006 | Hazardous Area Classification - Zone 1A - Furnaces |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0007 | Hazardous Area Classification - Zone 1B -Furnaces Utilities |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0008 | Hazardous Area Classification - Zone 2A - Quench |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0009 | Hazardous Area Classification - Zone 2B - C3 Hydrogenation |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0010 | Hazardous Area Classification - Zone 2C - Hot Fractionation - GHU |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0011 | Hazardous Area Classification - Zone 2D - Process Cold Compressor |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0012 | Hazardous Area Classification - Zone 2E - Cracked Gas Compressor |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0013 | Hazardous Area Classification - Zone 3A - Butadiene Extraction Unit |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0014 | Hazardous Area Classification - Zone 5F - HP and Ployolefins Flare Unit |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0015 | Hazardous Area Classification - Zone 5T - Cooling Water Unit |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0016 | Hazardous Area Classification - Zone 5U - Utilities |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0017 | Hazardous Area Classification - Zone 5W - Waste Water Treatment |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0018 | HAZARDOUS AREA CLASSIFICATION DRAWING |  |  | Purpose** | IFR: IDD; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
[6 empty] | Revised Plan | IFR: 2019-10-17; R1 IFI: 2020-05-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L42-0020 | Hazardous Area Classification - Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFA
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-20
[6 empty] | Revised Plan | R1 IFI: 2019-03-12
[6 empty] | Issue Actual | R1 IFI: 2019-03-12
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-SE-01015
[6 empty] | Return Date | R1 IFI: 2019-03-25
Owner Cmmt* | bar: R1 IFI
Category Code: L43 Risk Matrix
Category Code: L44 Life saving Equip & Escape Route Drawing
Category Code: L60 All project study and Report pertain to Loss control and Safety Process safety report; HAZOP Report; LOPA Report; PSSR Reports; Risk analysis dossiers; and and Project Response;
| SE | OL1-2L60-0002 | HAZOP & SIL Classification Actions Register |  |  | Purpose** | IFR: IFI; R1 IFI: IFR; R1 IFD: IFR
Rev. | bar: R1 IFI to R1 IFD
[6 empty] | Issue Plan | IFR: 2019-09-10
[6 empty] | Revised Plan | R1 IFI: 2019-09-10
[6 empty] | Issue Actual | R1 IFI: 2019-09-10; R1 IFD: 2019-09-28
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-SE-02575; R1 IFD: TPSK-LSPA1-T-SE-02716
Return Date
Owner Cmmt*
| PE | OL1-2L60-0051 | MSDS for Chemicals and Catalysts |  |  | Purpose** | IFR: IFR; R1 IFI: IFI
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-03
[6 empty] | Revised Plan | R1 IFI: 2019-01-23
[6 empty] | Issue Actual | R1 IFI: 2019-01-23
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-SE-00707
Return Date
Owner Cmmt*
| SE | OL1-2L60-0211 | Recovery Process and Utilities Sections HAZOP Report |  |  | Purpose** | IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-06-20
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L60-0215 | Side Stream Filter Package HAZOP Report (Tag No 10-PK-5355) |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-10-15
[6 empty] | Issue Actual | IFR: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-02824
Return Date
Owner Cmmt*
| SE | OL1-2L60-0216 | Wet Air Oxidation Package HAZOP Report (Tag No 10-PK-2350) |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-10-15
[6 empty] | Issue Actual | IFR: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-02824
Return Date
Owner Cmmt*
| SE | OL1-2L60-0231 | Recovery Process and Utilities Sections SIL Classification Report |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02393
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| SE | OL1-2L60-1001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) REPORT |  |  | Purpose** | IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-04
[6 empty] | Revised Plan | IFR: 2019-11-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L62 Recommendation Monitoring System
| SE | OL1-2L62-0003 | Recovery Process And Utilities Section HAZOP FEED Recommendations Mitigation Report - Fisrt Batch |  | Class 1 | Purpose** | IFR: IFA
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-02575
Return Date
Owner Cmmt*
| SE | OL1-2L62-0004 | Recovery Process And Utilities Section HAZOP FEED Recommendations Mitigation Report - Second Batch |  | Class 1 | Purpose** | IFR: IFA
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-28
[6 empty] | Issue Actual | IFR: 2019-09-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-02717
Return Date
Owner Cmmt*
| SE | OL1-2L62-1001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-10
[6 empty] | Revised Plan | IFR: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| SE | OL1-2L62-2001 | HAZARD & OPERABILITY STUDY (DETAIL DESIGN) CLOSEOUT REPORT |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-10
[6 empty] | Revised Plan | IFR: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: L63 Record of Survey
Category Code: L64 Report of audit
Category Code: L65 Hazardous Source Data
Category Code: L66 Register of Safety Devices
Category Code: L67 Equipment Failure Information
Category Code: L70 Emergency Procedures Manual
Category Code: L71 Test Procedures
Category Code: L72 Loss Control and Safety procedure
| SE | OL1-2L72-0001 | HAZOP Procedure |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-19
[6 empty] | Issue Actual | IFR: 2019-02-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-00882
[6 empty] | Return Date | IFR: 2019-03-21
Owner Cmmt* | bar: IFR
| SE | OL1-2L72-0002 | SIL Study Procedure |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-19
[6 empty] | Issue Actual | IFR: 2019-02-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-00894
[6 empty] | Return Date | IFR: 2019-03-21
Owner Cmmt* | bar: IFR
Category Code: L81 Appraisal Report for Consultancy Service
Category Code: L82 Appraisal Report for EPC Contractor Work
Category Code: L83 Appraisal Report for Vendor/Supplier
Category Code: L90 Vendor Document/drawings
Category Code: L91 Index/List
Category Code: L92 Procedures & Standards
Category Code: L93 Policy , Guidelines & Memo
Category Code: L94 Forms & Templates
Category Code: L95 Progress/Status Reports
Category Code: M03 Mechanical datasheet
| ME | 0L1-2M03-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed |  | Class 2 | Purpose** | IFR: IFP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-24
[6 empty] | Issue Actual | IFR: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01966
[6 empty] | Return Date | IFR: 2019-07-16
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-1000 | Mechanical Equipment Data Sheet - LPG Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-04-24
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01448
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 36M |  |  | Purpose** | IFR | IFQ | IFR | IFP | IMP
[6 empty] | Rev. | IFR: A; R1 IFD: A; R1 IMP: 0
[6 empty] | Issue Plan | IFR: 2018-10-31; R1 IFI: 2018-11-05; R1 IFD: 2018-10-31; R1 IFF: 2019-01-03
[6 empty] | Revised Plan | IFR: 2018-10-31; R1 IFD: 2018-10-31; R1 IMP: 2019-03-12
[6 empty] | Issue Actual | IFR: 2018-10-31; R1 IFD: 2018-10-31; R1 IMP: 2019-03-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00247; R1 IFD: TPSK-LSPA1-T-ME-00247; R1 IMP: TPSK-LSPA1-T-ME-01021
[6 empty] | Return Date | R1 IMP: 2019-03-29
Owner Cmmt* | bar: R1 IMP
| ME | OL1-2M03-1002 | Mechanical Equipment Data Sheet - 10-E-1000 - LPG Vaporizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-05-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00684; R1 IFF: TPSK-LSPA1-T-ME-01685
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1003 | Mechanical Equipment Data Sheet - 10-E-1001 - LPG Steam Vaporizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-02-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00573; R1 IFF: TPSK-LSPA1-T-ME-00946
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-03-25
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1005 | Mechanical Equipment Data Sheet - 10-E-1005 - LPG Feed Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00573; R1 IFF: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1006 | Mechanical Equipment Data Sheet - 10-E-1006 - LPG Feed Steam Heater |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFQ; R1 IFD: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-20; R1 IFD: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-03-20; R1 IFI: 2019-04-16; R1 IFD: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01095; R1 IFI: TPSK-LSPA1-T-ME-01362; R1 IFD: TPSK-LSPA1-T-ME-02175
[6 empty] | Return Date | IFR: 2019-04-11; R1 IFD: 2019-08-15
Owner Cmmt* | bar: IFR; R1 IFD
| ME | OL1-2M03-1015 | Mechanical Equipment Data Sheet - 10-E-1015 - LPG Superheater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-27
[6 empty] | Issue Actual | R1 IFD: 2018-12-27; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00571; R1 IFF: TPSK-LSPA1-T-ME-00971
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1020 | Mechanical Equipment Data Sheet - 10-E-1020 - Liquid Feed Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-17
[6 empty] | Issue Actual | R1 IFD: 2019-01-17; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00671; R1 IFF: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1051 | Mechanical Equipment Data Sheet - 10-E-1050 - C2 Feed Superheater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00573; R1 IFF: TPSK-LSPA1-T-ME-00961
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1105 | API Fired Heater Datasheet 10-H-1100 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-18; R1 IFI: 2019-04-26
[6 empty] | Issue Actual | IFR: 2019-03-18; R1 IFI: 2019-04-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01084; R1 IFI: TPSK-LSPA1-T-ME-01486
[6 empty] | Return Date | R1 IFI: 2019-05-29
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2M03-1113 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-11013 - PSV-1144 Outlet |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02129
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-1114 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-11014 - Start-up |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02129
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-1205 | API Fired Heater Datasheet 10-H-1200_1600 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-18; R1 IFI: 2019-04-26
[6 empty] | Issue Actual | IFR: 2019-03-18; R1 IFI: 2019-04-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01084; R1 IFI: TPSK-LSPA1-T-ME-01486
[6 empty] | Return Date | R1 IFI: 2019-05-29
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2M03-1213 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-12013/16013 - PSV-1244 Outlet |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02129
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-1214 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-12014/16014 - Start-up |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02129
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-1911 | Mechanical Equipment Data Sheet - DMDS Bulk Storage Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-04-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00743; R1 IFF: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1912 | Mechanical Equipment Data Sheet - DMDS Injection Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-04-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00744; R1 IFF: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1913 | Mechanical Equipment Datasheet - DMDS Feed Injection Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-02-04
[6 empty] | Issue Actual | R1 IFD: 2019-02-04; R1 IFF: 2019-03-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00787; R1 IFF: TPSK-LSPA1-T-ME-01086
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-04-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1914 | Mechanical Equipment Datasheet - DMDS Presulfiding Injection Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-02-04
[6 empty] | Issue Actual | R1 IFD: 2019-02-04; R1 IFF: 2019-03-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00787; R1 IFF: TPSK-LSPA1-T-ME-01086
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-04-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-1950 | Mechanical Equipment Datasheet - Decoking Air Compressor Package |  |  | Purpose** | IFR | IFA | IFD | IFQ | IFQ
[6 empty] | Rev. | R1 IFI: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2018-09-13; R1 IFD: 2018-10-11
[6 empty] | Revised Plan | R1 IFI: 2018-09-14; R1 IFF: 2018-10-12
[6 empty] | Issue Actual | R1 IFI: 2018-09-14; R1 IFF: 2018-10-12; R1 IMP: 2018-11-01
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00050; R1 IFF: TPSK-LSPA1-T-ME-00161; R1 IMP: TPSK-LSPA1-T-ME-00261
[6 empty] | Return Date | R1 IFI: 2018-10-02; R1 IMP: 2018-11-29
Owner Cmmt* | bar: R1 IFI; R1 IMP
| ME | OL1-2M03-2000 | Mechanical Equipment Data Sheet - Quench Oil Tower |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-04
[6 empty] | Issue Actual | R1 IFD: 2018-12-04; R1 IFF: 2019-02-06
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00420; R1 IFF: TPSK-LSPA1-T-ME-00801
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-02-25
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2001 | Mechanical Equipment Datasheet for Furnace ID Fan USC 132U |  |  | Purpose** | IFR | IFQ | IFR | IFP | IMP
[6 empty] | Rev. | IFR: A; R1 IFD: A; R1 IMP: 0
[6 empty] | Issue Plan | IFR: 2018-10-31; R1 IFI: 2018-11-05; R1 IFD: 2018-10-31; R1 IFF: 2019-01-03
[6 empty] | Revised Plan | IFR: 2018-10-31; R1 IFD: 2018-10-31; R1 IMP: 2019-03-12
[6 empty] | Issue Actual | IFR: 2018-10-31; R1 IFD: 2018-10-31; R1 IMP: 2019-03-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00247; R1 IFD: TPSK-LSPA1-T-ME-00247; R1 IMP: TPSK-LSPA1-T-ME-01021
[6 empty] | Return Date | R1 IMP: 2019-03-29
Owner Cmmt* | bar: R1 IMP
| ME | OL1-2M03-2002 | Elevator Data Sheet |  |  | Purpose** | IFR | IFQ | IFR | IFP | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFD: A; R1 IMP: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2018-12-19; R1 IFI: 2018-12-19; R1 IFD: 2018-12-19; R1 IFF: 2019-02-19
[6 empty] | Revised Plan | IFR: 2019-01-18; R1 IFD: 2019-01-18; R1 IMP: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-01-18; R1 IFD: 2019-01-18; R1 IMP: 2019-06-10; R1 IMP: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00681; R1 IFD: TPSK-LSPA1-T-ME-00681; R1 IMP: TPSK-LSPA1-T-ME-01832; R1 IMP: TPSK-LSPA1-T-ME-02246
[6 empty] | Return Date | IFR: 2019-02-08; R1 IFD: 2019-02-08; R1 IMP: 2019-07-03; R1 IMP: 2019-08-26
Owner Cmmt* | bar: IFR; R1 IFD; R1 IMP to R1 IMP
| ME | OL1-2M03-2006 | Mechanical Equipment Data Sheet - Quench Oil Pump |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-10-26
[6 empty] | Issue Actual | R1 IFD: 2018-10-26; R1 IFF: 2018-12-11; R1 IMP: 2019-03-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00235; R1 IFF: TPSK-LSPA1-T-ME-00476; R1 IMP: TPSK-LSPA1-T-ME-01173
[6 empty] | Return Date | R1 IFD: 2018-11-19; R1 IFF: 2019-01-16; R1 IMP: 2019-04-22
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2010 | Mechanical Equipment Data sheet - Quench Oil Filter |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | R1 IFD: 2019-01-30
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2014 | Mechanical Equipment Datasheet for QO Pump Purge Oil Filter |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | R1 IFD: 2019-01-30
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2015 | Mechanical Equipment Data Sheet - 10-E-2008 - LS2 Steam Generators |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-14
[6 empty] | Issue Actual | R1 IFD: 2019-01-14; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00643; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-02-04; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2020 | Mechanical Equipment Data Sheet - Light Fuel Oil Stripper Elevation View |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-02-06
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00447; R1 IFF: TPSK-LSPA1-T-ME-00801
[6 empty] | Return Date | R1 IFD: 2019-01-27; R1 IFF: 2019-02-25
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2024 | Mechanical Equipment Datasheet - Light Fuel Oil Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-02-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00457; R1 IFF: TPSK-LSPA1-T-ME-00786
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2025 | Mechanical Equipment Datasheet - Cracker Bottoms Product Filter |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-26
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639; R1 IFF: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2026 | Mechanical Equipment Data Sheet - 10-E-2026 - FO Product Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-04-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00683; R1 IFF: TPSK-LSPA1-T-ME-01307
[6 empty] | Return Date | R1 IFD: 2019-02-11
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2028 | Mechanical Equipment Datasheet for FO Pump Purge Oil Filter |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-26
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639; R1 IFF: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2040 | Mechanical Equipment Data Sheet - Heavy Fuel Oil Stripper |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-11-28
[6 empty] | Issue Actual | R1 IFD: 2018-11-28; R1 IFF: 2018-12-05; R1 IMP: 2019-02-06
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00387; R1 IFF: TPSK-LSPA1-T-ME-00418; R1 IMP: TPSK-LSPA1-T-ME-00815
[6 empty] | Return Date | R1 IFD: 2018-12-17; R1 IFF: 2018-12-27; R1 IMP: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2046 | Mechanical Equipment Datasheet - Heavy Fuel Oil Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-02-04; R1 IMP: 2019-04-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00457; R1 IFF: TPSK-LSPA1-T-ME-00786; R1 IMP: TPSK-LSPA1-T-ME-01493
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-02-21; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2048 | Mechanical Equipment Data Sheet - 10-E-2048 - Heavy Fuel Oil Product Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-04-12
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00683; R1 IFF: TPSK-LSPA1-T-ME-01324
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2049 | Mechanical Equipment Datasheet - Heavy Fuel Oil Filters |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-27
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639; R1 IFF: TPSK-LSPA1-T-ME-01157
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2070 | Mechanical Data Sheet For General Purpose Steam Turbines PT-2006 A Quench Oil Pump Turbne |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2090 | Mechanical Equipment Data Sheet - Quench Oil Drain Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-01-21; R1 IFI: 2019-02-08
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00638; R1 IFF: TPSK-LSPA1-T-ME -1226
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-05-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2091 | Mechanical Equipment Datasheet - Quench Oil Drain Drum Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-04-03; R1 IMP: 2019-04-16
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00494; R1 IFF: TPSK-LSPA1-T-ME-01227; R1 IMP: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | R1 IFD: 2019-01-14
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2100 | Mechanical Equipment Data Sheet - Quench Water Tower |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-07
[6 empty] | Issue Actual | R1 IFD: 2018-12-07; R1 IFF: 2019-02-06
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00443; R1 IFF: TPSK-LSPA1-T-ME -00803
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-02-25
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2101 | Mechanical Equipment Data Sheet - 10-E-2100 - Quench Water Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFA; R1 IFD: IFD; R1 IFF: IFQ
Rev. | bar: R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2018-10-20; R1 IFD: 2018-10-20
[6 empty] | Revised Plan | R1 IFI: 2018-09-18; R1 IFF: 2018-10-11
[6 empty] | Issue Actual | R1 IFI: 2018-09-18; R1 IFF: 2018-10-11
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00058; R1 IFF: TPSK-LSPA1-T-ME-00154
[6 empty] | Return Date | R1 IFI: 2018-09-28; R1 IFF: 2018-11-07
Owner Cmmt* | bar: R1 IFI; R1 IFF
| ME | OL1-2M03-2104 | Mechanical Equipment Datasheet - Quench Oil Reflux Filter |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-26
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639; R1 IFF: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2105 | Mechanical Equipment Datasheet - Quench Oil Reflux Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-04-09
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00457; R1 IFF: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-05-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2106 | Mechanical Equipment Data Sheet - Quench Water Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-10-27
[6 empty] | Issue Actual | R1 IFD: 2018-10-27; R1 IFF: 2018-12-11; R1 IMP: 2019-03-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00236; R1 IFF: TPSK-LSPA1-T-ME-00476; R1 IMP: TPSK-LSPA1-T-ME-01173
[6 empty] | Return Date | R1 IFD: 2018-11-19; R1 IFF: 2019-01-16; R1 IMP: 2019-04-22
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2110 | Mechanical Equipment Data Sheet - Interception Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-06-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00685; R1 IFF: TPSK-LSPA1-T-ME-01850
[6 empty] | Return Date | R1 IFD: 2019-02-15; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2120 | Mechanical Equipment Data Sheet - Distillate Stripper |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-02-12
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00546; R1 IFF: TPSK-LSPA1-T-ME-00840
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-02-28
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2125 | Mechanical Equipment Data Sheet - 10-E-2125 - Distillate Stripper Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-07
[6 empty] | Issue Actual | R1 IFD: 2019-01-07; R1 IFF: 2019-04-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00584; R1 IFF: TPSK-LSPA1-T-ME-01302
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-06-05
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2126 | Mechanical Equipment Datasheet - Distillate Stripper Bottom Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-05
[6 empty] | Issue Actual | R1 IFD: 2018-12-05; R1 IFF: 2019-03-21; R1 IMP: 2019-04-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00410; R1 IFF: TPSK-LSPA1-T-ME-01102; R1 IMP: TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-04-10; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2137 | Mechanical Equipment Data Sheet - 10-E-2136 - Process Water Stripper Feed Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-04-05
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00573; R1 IFF: TPSK-LSPA1-T-ME -01251
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-06-05
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2138 | Mechanical Equipment Datasheet - Process Water Feed Filters |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-26
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639; R1 IFF: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2139 | Mechanical Equipment Datasheet - Process Water Coalescer Prefilters |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-05-16
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-05-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01641; R1 IFI: TPSK-LSPA1-T-ME-01669
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2140 | Mechanical Equipment Data Sheet - Process Water Stripper |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-02-06
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00458; R1 IFF: TPSK-LSPA1-T-ME-00801
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-02-25
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2145 | Mechanical Equipment Data Sheet - 10-E-2145 - Process Water Stripper Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-04-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00684; R1 IFF: TPSK-LSPA1-T-ME-01357
[6 empty] | Return Date | R1 IFD: 2019-02-11
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2146 | Mechanical Equipment Data Sheet - DSG Feed Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-10-26
[6 empty] | Issue Actual | R1 IFD: 2018-10-26; R1 IFF: 2018-12-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00235; R1 IFF: TPSK-LSPA1-T-ME-00476
[6 empty] | Return Date | R1 IFD: 2018-11-19; R1 IFF: 2019-01-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2147 | Mechanical Equipment Data Sheet - 10-E-2146 - DSG Feed Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-14
[6 empty] | Issue Actual | R1 IFD: 2019-01-14; R1 IFF: 2019-04-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00650; R1 IFF: TPSK-LSPA1-T-ME-01302
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-06-05
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2160 | Mechanical Equipment Data Sheet - Dilution Steam Generator |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-01-21; R1 IFI: 2019-02-08
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-05-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01760
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2161 | Mechanical Equipment Data Sheet - 10-E-2160 - Dilution Steam Superheater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00641; R1 IFF: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | R1 IFD: 2019-02-04; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2165 | Mechanical Equipment Data Sheet - 10-E-2165 A-D - DSG Reboilers |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: 0
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-04-01; R1 IMP: 2019-07-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00582; R1 IFF: TPSK-LSPA1-T-ME-01205; R1 IMP: TPSK-LSPA1-T-ME-02163
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-05-02; R1 IMP: 2019-08-12
[6 empty] | Owner Cmmt* | R1 IFD: R2; R1 IFF: TP; R1 IMP: R1
| ME | OL1-2M03-2166 | Mechanical Equipment Data Sheet - 10-E-2166 - DSG Blowdown Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-04-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00684; R1 IFF: TPSK-LSPA1-T-ME-01248
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2170 | Mechanical Data Sheet For General Purpose Steam Turbines PT-2106 A Quench Water Pump Turbne |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2171 | Mechanical Equipment Data Sheet For DSG Feed Pump Turbine |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2190 | Mechanical Equipment Data Sheet - Quench Water Drain Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00638; R1 IFF: TPSK-LSPA1-T-ME -1226
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-05-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2191 | Mechanical Equipment Datasheet - Quench Water Drain Drum Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-29
[6 empty] | Issue Actual | R1 IFD: 2018-11-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00400
[6 empty] | Return Date | R1 IFD: 2019-02-21
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2200 | Mechanical DataSheet For Cracked Gas Compressor |  |  | Purpose** | IFR | IFA | IFD | IFQ | IFQ
[6 empty] | Rev. | R1 IFI: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2018-09-13; R1 IFD: 2018-10-04
[6 empty] | Revised Plan | R1 IFI: 2018-09-11; R1 IFF: 2018-10-04
[6 empty] | Issue Actual | R1 IFI: 2018-09-11; R1 IFF: 2018-10-04; R1 IMP: 2018-11-06
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00038; R1 IFF: TPSK-LSPA1-T-ME-00127; R1 IMP: TPSK-LSPA1-T-ME-00280
[6 empty] | Return Date | R1 IFI: 2018-09-28; R1 IMP: 2018-11-30
Owner Cmmt* | bar: R1 IFI; R1 IMP
| ME | OL1-2M03-2206 | Mechanical Equipment Data Sheet - 10-E-2206 - Wash Water Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-07
[6 empty] | Issue Actual | R1 IFD: 2019-01-07; R1 IFF: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00584; R1 IFF: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2210 | Mechanical Equipment Data Sheet - CG 1st Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-04-24
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00685; R1 IFF: TPSK-LSPA1-T-ME-01448
[6 empty] | Return Date | R1 IFD: 2019-02-15; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2211 | Mechanical Equipment Data Sheet - 10-E-2210 A-B - CG 1st Stage Aftercoolers |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00683; R1 IFF: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2212 | Mechanical Equipment Datasheet - CG 1st Stage Condensate Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-05
[6 empty] | Issue Actual | R1 IFD: 2018-12-05
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00413
[6 empty] | Return Date | R1 IFD: 2018-12-27
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2220 | Mechanical Equipment Data Sheet - CG 2nd Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-03-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2221 | Mechanical Equipment Data Sheet - 10-E-2220 - CG 2nd Stage Aftercooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-07
[6 empty] | Issue Actual | R1 IFD: 2019-01-07; R1 IFF: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00588; R1 IFF: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2222 | Mechanical Equipment Datasheet - CG 2nd Stage Condensed HC Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-20
[6 empty] | Issue Actual | R1 IFD: 2018-11-20
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00343
[6 empty] | Return Date | R1 IFD: 2019-02-11
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2230 | Mechanical Equipment Data Sheet - CG 3rd Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-03-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2231 | Mechanical Equipment Data Sheet - 10-E-2230 - CG 3rd Stage Aftercooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-07
[6 empty] | Issue Actual | R1 IFD: 2019-01-07; R1 IFF: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00588; R1 IFF: TPSK-LSPA1-T-ME-01110
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2240 | Mechanical Equipment Data Sheet - CG 4th Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-03-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2241 | Mechanical Equipment Data Sheet - 10-E-2240 - CG 4th Stage Aftercooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-10
[6 empty] | Issue Actual | R1 IFD: 2019-01-10; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00617; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-01-29; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2245 | Mechanical Equipment Data Sheet - CG 4th Stage Discharge Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-16
[6 empty] | Issue Actual | R1 IFD: 2019-01-16; R1 IFF: 2019-04-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00657; R1 IFF: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2300 | Mechanical Equipment Data Sheet - Caustic Tower |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-10-31
[6 empty] | Issue Actual | R1 IFD: 2018-10-31; R1 IFF: 2018-12-05; R1 IMP: 2019-02-19
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00246; R1 IFF: TPSK-LSPA1-T-ME-00419; R1 IMP: TPSK-LSPA1-T-ME -00883
[6 empty] | Return Date | R1 IFD: 2018-11-27; R1 IFF: 2018-12-27; R1 IMP: 2019-03-12
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2302 | MECHANICAL EQUIPMENT DATASHEET - Strong Caustic Circulating Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-15
[6 empty] | Issue Actual | R1 IFD: 2018-11-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00320
[6 empty] | Return Date | R1 IFD: 2018-12-10
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2304 | Mechanical Equipment Datasheet - Intermediate Caustic Circulating Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-15
[6 empty] | Issue Actual | R1 IFD: 2018-11-15; R1 IFF: 2018-12-05
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00320; R1 IFF: TPSK-LSPA1-T-ME-00411
[6 empty] | Return Date | R1 IFD: 2018-12-10; R1 IFF: 2018-12-27
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2305 | Mechanical Equipment Data Sheet - 10-E-2305 - Caustic Tower Feed Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-10
[6 empty] | Issue Actual | R1 IFD: 2019-01-10; R1 IFF: 2019-04-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00617; R1 IFF: TPSK-LSPA1-T-ME-01503
[6 empty] | Return Date | R1 IFD: 2019-01-29; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2306 | Mechanical Equipment Datasheet - Weak Caustic Circulating Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-15
[6 empty] | Issue Actual | R1 IFD: 2018-11-15; R1 IFF: 2018-12-05
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00320; R1 IFF: TPSK-LSPA1-T-ME-00411
[6 empty] | Return Date | R1 IFD: 2018-12-10; R1 IFF: 2018-12-27
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2307 | Mechanical Equipment Datasheet - Weak Caustic Circulating Filters |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-26
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639; R1 IFF: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2309 | Mechanical Equipment Data Sheet - Yellow Oil Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00484; R1 IFF: TPSK-LSPA1-T-ME-01571
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-05-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2310 | Mechanical Equipment Data Sheet - Spent Caustic Deoiling Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-17
[6 empty] | Issue Actual | R1 IFD: 2018-12-17; R1 IFF: 2019-04-24
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00513; R1 IFF: TPSK-LSPA1-T-ME-01448
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2311 | Mechanical Equipment Datasheet - Wash Oil Circulating Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-15
[6 empty] | Issue Actual | R1 IFD: 2018-11-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00320
[6 empty] | Return Date | R1 IFD: 2018-12-10
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2314 | Mechanical Equipment Datasheet - Wash Oil Circulation Filter |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | R1 IFD: 2019-01-30
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2316 | Mechanical Equipment Data Sheet - Spent Caustic Degassing Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-07
[6 empty] | Issue Actual | R1 IFD: 2019-01-07; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00601; R1 IFF: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-07-01
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2319 | Mechanical Equipment Datasheet - Spent Caustic Pump Discharge Filters |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639
[6 empty] | Return Date | R1 IFD: 2019-01-30
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2320 | Mechanical Equipment Data Sheet - Spent Caustic Storage Tank |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-26
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-08-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00745; R1 IFF: TPSK-LSPA1-T-ME-02453
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-09-26
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2321 | Mechanical Equipment Datasheet - Spent Caustic Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-19
[6 empty] | Issue Actual | R1 IFD: 2018-11-19
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00335
[6 empty] | Return Date | R1 IFD: 2018-12-13
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2322 | Mechanical Equipment Data Sheet - Skim Oil Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-07-01
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2324 | Mechanical Equipment Data Sheet - Fresh Caustic Day Tank |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-26
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-08-19
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00745; R1 IFF: TPSK-LSPA1-T-ME-02447
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2325 | Mechanical Equipment Datasheet For 10% Caustic Makeup Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-02-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00580; R1 IFF: TPSK-LSPA1-T-ME-00822
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2326 | Mechanical Equipment Data Sheet - 10-E-2326 - Spent Caustic Stripper Feed Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-01-29; R1 IFI: 2019-01-29
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-05-27
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00740; R1 IFF: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date | R1 IFD: 2019-02-28; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2327 | Mechanical Equipment Datasheet - Skim Oil Pump |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-02
[6 empty] | Issue Actual | IFR: 2019-05-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2330 | Mechanical Equipment Data Sheet - Spent Caustic Stripper |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-02-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00462; R1 IFF: TPSK-LSPA1-T-ME-00857
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-03-12
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2331 | Mechanical Equipment Data Sheet - Spent Caustic Stripper OVHD Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00638; R1 IFF: TPSK-LSPA1-T-ME-01536
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2350 | Mechanical Equipment Datasheet for Wet Air Oxidation Package |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP; R1 IFD: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-29; R1 IFI: 2019-05-09
[6 empty] | Issue Actual | IFR: 2018-11-29; R1 IFI: 2019-05-09; R1 IFD: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00390; R1 IFI: TPSK-LSPA1-T-PL-01611; R1 IFD: TPSK-LSPA1-T-ME-01944
[6 empty] | Return Date | IFR: 2019-02-07; R1 IFI: 2019-05-29
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-2390 | Mechanical Equipment Data Sheet - Caustic Drain Drum |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-17
[6 empty] | Issue Actual | R1 IFD: 2018-12-17; R1 IFF: 2019-03-29; R1 IMP: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00514; R1 IFF: TPSK-LSPA1-T-ME-01186; R1 IMP: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-05-02; R1 IMP: 2019-07-01
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2391 | Mechanical Equipment Datasheet - Caustic Drain Drum Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-17
[6 empty] | Issue Actual | R1 IFD: 2018-12-17; R1 IFF: 2019-02-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00511; R1 IFF: TPSK-LSPA1-T-ME-00822
[6 empty] | Return Date | R1 IFD: 2019-01-14; R1 IFF: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2392 | Mechanical Equipment Data Sheet - Spent Caustic Drain Drum |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-04-04; R1 IMP: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00685; R1 IFF: TPSK-LSPA1-T-ME-01244; R1 IMP: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-02-15; R1 IFF: 2019-05-20; R1 IMP: 2019-07-01
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2393 | Mechanical Equipment Datasheet - Spent Caustic Drain Drum Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00457
[6 empty] | Return Date | R1 IFD: 2018-12-27
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2405 | Mechanical Equipment Data Sheet - Gas Dryer Feed KO Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00629; R1 IFF: TPSK-LSPA1-T-ME-01533
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2406 | Mechanical Equipment Data Sheet - 10-E-2405 - Gas Dryer Feed Chiller |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-07
[6 empty] | Issue Actual | R1 IFD: 2019-01-07; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00584; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2410 | Mechanical Equipment Data Sheet - Cracked Gas Dryer |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-03-04; R1 IMP: 2019-03-12; R1 IMP: 2019-04-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00700; R1 IFF: TPSK-LSPA1-T-ME-00972; R1 IMP: TPSK-LSPA1-T-ME-01016; R1 IMP: TPSK-LSPA1-T-ME-01347
[6 empty] | Return Date | R1 IFD: 2019-04-01; R1 IFF: 2019-03-29; R1 IMP: 2019-04-02; R1 IMP: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2411 | Mechanical Equipment Data Sheet - Cracked Gas Mercury Adsorber |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-01; R1 IMP: 2019-04-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00631; R1 IFF: TPSK-LSPA1-T-ME-00954; R1 IMP: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-25; R1 IMP: 2019-06-04
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2412 | Mechanical Equipment Data Sheet - 10-E-2412 - HP Deprop Feed Chiller |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-10
[6 empty] | Issue Actual | R1 IFD: 2019-01-10; R1 IFF: 2019-03-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00617; R1 IFF: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date | R1 IFD: 2019-01-29; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2413 | Mechanical Equipment Data Sheet - 10-E-2413 - HP Deprop Feed-Overhead Exchanger |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: IFR; R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | IFR: 2019-01-10; R1 IFD: 2019-03-28
[6 empty] | Issue Actual | IFR: 2019-01-10; R1 IFD: 2019-03-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00617; R1 IFD: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date | IFR: 2019-02-11; R1 IFD: 2019-05-02
Owner Cmmt* | bar: IFR; R1 IFD
| ME | OL1-2M03-2416 | Mechanical Equipment Datasheet - CG Liquid Dryer Feed Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-05
[6 empty] | Issue Actual | R1 IFD: 2018-12-05; R1 IFF: 2019-01-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00413; R1 IFF: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2420 | Mechanical Equipment Data Sheet - CG Liquid Dryer |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-03-01; R1 IMP: 2019-04-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00702; R1 IFF: TPSK-LSPA1-T-ME-00950; R1 IMP: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-04-02; R1 IMP: 2019-06-04
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2430 | Mechanical Equipment Data Sheet - 10-E-2430 - Regen Gas Feed Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-04-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00740; R1 IFF: TPSK-LSPA1-T-ME-01315
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-05
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2432 | Mechanical Equipment Data Sheet - 10-E-2432 - Regen Gas SHP Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-01-29; R1 IFI: 2019-01-29
[6 empty] | Revised Plan | R1 IFD: 2019-01-29
[6 empty] | Issue Actual | R1 IFD: 2019-01-29; R1 IFF: 2019-05-27
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00751; R1 IFF: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2434 | Mechanical Equipment Data Sheet - 10-E-2435 - Regen Gas Effluent Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-25
[6 empty] | Issue Actual | R1 IFD: 2019-01-25; R1 IFF: 2019-04-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00723; R1 IFF: TPSK-LSPA1-T-ME-01218
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2435 | Mechanical Equipment Data Sheet - Regen Gas Separator |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00685; R1 IFF: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2438 | Mechanical Equipment Data Sheet - HP Depropanizer Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-04-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00484; R1 IFF: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-06-04
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2439 | Mechanical Equipment Data Sheet - 10-E-2440 - HP Depropanizer Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00683; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2440 | Mechanical Equipment Datasheet - HP Depropanizer |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-10-23
[6 empty] | Issue Actual | R1 IFD: 2018-10-23; R1 IFF: 2018-12-05; R1 IMP: 2019-02-19
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00215; R1 IFF: TPSK-LSPA1-T-ME-00416; R1 IMP: TPSK-LSPA1-T-ME-00884
[6 empty] | Return Date | R1 IFD: 2018-12-17; R1 IFF: 2018-12-27; R1 IMP: 2019-03-12
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2441 | Mechanical Equipment Data Sheet - 10-E-2441 - HP Deprop Reflux Chiller No 2 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-16
[6 empty] | Issue Actual | R1 IFD: 2019-01-16; R1 IFF: 2019-04-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00663; R1 IFF: TPSK-LSPA1-T-ME -01216
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2442 | Mechanical Equipment Data Sheet - 10-E-2442 - HP Deprop Reflux Chiller no 1 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-16
[6 empty] | Issue Actual | R1 IFD: 2019-01-16; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00662; R1 IFF: TPSK-LSPA1-T-ME-01231
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2443 | Mechanical Equipment Datasheet - HP Deprop Reboiler Cond Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-01-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00494; R1 IFF: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date | R1 IFD: 2019-01-14; R1 IFF: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2444 | Mechanical Equipment Data Sheet - HP Deprop Reboiler Cond Pot |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-04-11; R1 IMP: 2019-05-16
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00629; R1 IFF: TPSK-LSPA1-T-ME -01314; R1 IMP: TPSK-LSPA1-T-ME-01670
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-06-05; R1 IMP: 2019-06-19
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2445 | Mechanical Equipment Data Sheet - 10-E-2445 - HP Depropanizer Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-17
[6 empty] | Issue Actual | R1 IFD: 2019-01-17; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00671; R1 IFF: TPSK-LSPA1-T-ME-01231
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2446 | Mechanical Equipment Data Sheet - 10-E-2446 - LP Depropanizer Feed Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-27
[6 empty] | Issue Actual | R1 IFD: 2018-12-27; R1 IFF: 2019-04-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00565; R1 IFF: TPSK-LSPA1-T-ME-01218
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2450 | Mechanical Equipment Data Sheet - LP Depropanizer |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-10-17
[6 empty] | Issue Actual | R1 IFD: 2018-10-17; R1 IFF: 2018-11-06; R1 IMP: 2018-12-05; R1 IMP: 2019-02-19
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00183; R1 IFF: TPSK-LSPA1-T-ME-00283; R1 IMP: TPSK-LSPA1-T-ME-00412; R1 IMP: TPSK-LSPA1-T-ME-00884
[6 empty] | Return Date | R1 IFD: 2018-11-05; R1 IFF: 2018-11-30; R1 IMP: 2018-12-27; R1 IMP: 2019-03-12
[6 empty] | Owner Cmmt* | R1 IFD: A3; R1 IFF: R1; R1 IMP: R2; R1 IMP: R2
| ME | OL1-2M03-2451 | Mechanical Equipment Data Sheet - 10-E-2450 - LP Depropanizer Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-07
[6 empty] | Issue Actual | R1 IFD: 2019-01-07; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00588; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2452 | Mechanical Equipment Data Sheet - LP Depropanizer Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-17
[6 empty] | Issue Actual | R1 IFD: 2018-12-17; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00516; R1 IFF: TPSK-LSPA1-T-ME-01533
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2453 | Mechanical Equipment Datasheet - LP Depropanizer Reflux - Product Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-08
[6 empty] | Issue Actual | R1 IFD: 2018-11-08; R1 IFF: 2019-02-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00294; R1 IFF: TPSK-LSPA1-T-ME-00944
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-12
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2455 | Mechanical Equipment Data Sheet - 10-E-2455 AB - LP Depropanizer Reboilers |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-07
[6 empty] | Issue Actual | R1 IFD: 2019-01-07; R1 IFF: 2019-03-28; R1 IMP: 2019-05-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00584; R1 IFF: TPSK-LSPA1-T-ME-01179; R1 IMP: TPSK-LSPA1-T-ME-01713
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-05-02; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2456 | Mechanical Equipment Data Sheet - LP Deprop Reboilder Cond Pot |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00685; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2457 | Mechanical Equipment Datasheet - LP Deprop Reboiler Cond Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-01-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00494; R1 IFF: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date | R1 IFD: 2019-01-14; R1 IFF: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2460 | Mechanical Equipment Data Sheet - C2 Hydrog Arsine Guard Bed |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-16
[6 empty] | Issue Actual | R1 IFD: 2019-01-16; R1 IFF: 2019-02-15; R1 IMP: 2019-04-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00657; R1 IFF: TPSK-LSPA1-T-ME -00858; R1 IMP: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-03-12; R1 IMP: 2019-06-04
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2461 | Mechanical Equipment Data Sheet - 10-E-2460 - C2 Hydrog Feed Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-03-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00573; R1 IFF: TPSK-LSPA1-T-ME-01179
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2465 | Mechanical Equipment Data Sheet - 10-E-2465 - C2 Hydrog Feed Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00641; R1 IFF: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | R1 IFD: 2019-02-04; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2470 | Mechanical Equipment Data Sheet - C2 Hydrog Reactor |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-16; R1 IFI: 2019-02-16
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-01; R1 IMP: 2019-04-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00630; R1 IFF: TPSK-LSPA1-T-ME-00953; R1 IMP: TPSK-LSPA1-T-ME-01379
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-25; R1 IMP: 2019-06-04
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2471 | Mechanical Equipment Data Sheet - 10-E-2470 - C2 Hydrog 1st Stage Intercooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00641; R1 IFF: TPSK-LSPA1-T-ME-01231
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2472 | Mechanical Equipment Data Sheet - 10-E-2472 - C2 Hydrog 2nd Stage Intercooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00641; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-02-04; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2474 | Mechanical Equipment Data Sheet - 10-E-2474 - C2 Hydrog Aftercooler |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-04-01; R1 IMP: 2019-05-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00641; R1 IFF: TPSK-LSPA1-T-ME-01205; R1 IMP: TPSK-LSPA1-T-ME-01714
[6 empty] | Return Date | R1 IFD: 2019-02-04; R1 IFF: 2019-05-02; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2480 | Mechanical Equipment Data Sheet - CG Secondary Dryer |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-03-01; R1 IMP: 2019-04-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00702; R1 IFF: TPSK-LSPA1-T-ME-00954; R1 IMP: TPSK-LSPA1-T-ME-01378
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-25; R1 IMP: 2019-06-04
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2502 | Mechanical Equipment Data Sheet - 10-E-2502 - Demeth Prefrac Feed Cooler No 1 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00461; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2503 | Mechanical Equipment Data Sheet - 10-E-2504 - Demeth Prefrac Feed Cooler No 2 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-11-28
[6 empty] | Issue Actual | R1 IFD: 2018-11-28; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00389; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2018-12-13; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2504 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 1 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LPSA1-T-ME-01534
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2506 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 2 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00551; R1 IFF: TPSK-LSPA1-T-ME-01583
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2508 | Mechanical Equipment Data Sheet - Demeth Prefrac Feed Separator No 3 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00551; R1 IFF: TPSK-LSPA1-T-ME-01583
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2510 | Mechanical Equipment Data Sheet - Demethanizer Prefractionator & Reflux Drum |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-10-31
[6 empty] | Issue Actual | R1 IFD: 2018-10-31; R1 IFF: 2018-12-05; R1 IMP: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00260; R1 IFF: TPSK-LSPA1-T-ME-00414; R1 IMP: TPSK-LSPA1-T-ME-00970
[6 empty] | Return Date | R1 IFD: 2018-11-29; R1 IFF: 2018-12-27; R1 IMP: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2515 | Mechanical Equipment Data Sheet - 10-E-2515- Demeth Prefrac Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00573; R1 IFF: TPSK-LSPA1-T-ME-00971
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2520 | Mechanical Equipment Data Sheet - Residue Gas Rectifier And Rectifier Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-02-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00534; R1 IFF: TPSK-LSPA1-T-ME-00792
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2525 | Mechanical Equipment Data Sheet - Hydrogen Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-16
[6 empty] | Issue Actual | R1 IFD: 2019-01-16; R1 IFF: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00657; R1 IFF: TPSK-LSPA1-T-ME-01583
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2540 | Mechanical Equipment Data Sheet - Demethanizer Reflux Drum |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-11-09
[6 empty] | Issue Actual | R1 IFD: 2018-11-09; R1 IFF: 2018-12-05; R1 IMP: 2019-02-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00304; R1 IFF: TPSK-LSPA1-T-ME-00415; R1 IMP: TPSK-LSPA1-T-ME-00945
[6 empty] | Return Date | R1 IFD: 2018-12-10; R1 IFF: 2018-12-27; R1 IMP: 2019-03-25
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2545 | Mechanical Equipment Data Sheet - 10-E-2545 - Demethanizer Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-14
[6 empty] | Issue Actual | R1 IFD: 2019-01-14; R1 IFF: 2019-03-22
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00651; R1 IFF: TPSK-LSPA1-T-ME-01123
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2546 | Mechanical Equipment Data Sheet - 10-E-2546 - Demethanizer Bottoms Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-16
[6 empty] | Issue Actual | R1 IFD: 2019-01-16; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00654; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2548 | Mechanical Equipment Data Sheet - 10-E-2548 - Demethanizer Bottoms Vaporizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-10
[6 empty] | Issue Actual | R1 IFD: 2019-01-10; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00617; R1 IFF: TPSK-LSPA1-T-ME-00961
[6 empty] | Return Date | R1 IFD: 2019-01-29; R1 IFF: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2550 | Mechanical Equipment Datasheet for Residue Gas Expander-Recompressor |  |  | Purpose** | IFR: IFR; R1 IFI: IFA; R1 IFD: IFD; R1 IFF: IFQ
Rev. | bar: R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2018-09-13; R1 IFD: 2018-10-04
[6 empty] | Revised Plan | R1 IFI: 2018-09-14; R1 IFF: 2018-10-05
[6 empty] | Issue Actual | R1 IFI: 2018-09-14; R1 IFF: 2018-10-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00050; R1 IFF: TPSK-LSPA1-T-ME-00130
[6 empty] | Return Date | R1 IFI: 2018-10-02; R1 IFF: 2018-10-26
Owner Cmmt* | bar: R1 IFI; R1 IFF
| ME | OL1-2M03-2551 | Mechanical Equipment Data Sheet - Expander Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-05-30
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00551; R1 IFF: TPSK-LSPA1-T-ME-01764
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2555 | Mechanical Equipment Data Sheet - Expander Discharge Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-08
[6 empty] | Issue Actual | R1 IFD: 2019-01-08; R1 IFF: 2019-05-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00607; R1 IFF: TPSK-LSPA1-T-ME-01760
[6 empty] | Return Date | R1 IFD: 2019-01-28; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2570 | Mechanical Equipment Data Sheet - Deethanizer |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-11-29
[6 empty] | Issue Actual | R1 IFD: 2018-11-29; R1 IFF: 2018-12-20; R1 IMP: 2019-02-27
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00394; R1 IFF: TPSK-LSPA1-T-ME-00547; R1 IMP: TPSK-LSPA1-T-ME-00931
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-01-22; R1 IMP: 2019-03-15
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2571 | Mechanical Equipment Data Sheet - 10-E-2570 - Deethanizer Condenser |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-11-13
[6 empty] | Issue Actual | R1 IFD: 2018-11-13; R1 IFF: 2019-01-31; R1 IMP: 2019-04-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00310; R1 IFF: TPSK-LSPA1-T-ME-00773; R1 IMP: TPSK-LSPA1-T-ME-01245
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-02-26; R1 IMP: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2572 | Mechanical Equipment Data Sheet - Deethanizer Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00484
[6 empty] | Return Date | R1 IFD: 2019-01-22
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2573 | Mechanical Equipment Datasheet - Deethanizer Reflux Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00552
[6 empty] | Return Date | R1 IFD: 2019-01-16
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2574 | Mechanical Equipment Data Sheet - Deethanizer Reboilder Cond Pot |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00685; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2575 | Mechanical Equipment Data Sheet - 10-E-2575 - Deethanizer Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00684; R1 IFF: TPSK-LSPA1-T-ME-00961
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2576 | Mechanical Equipment Data Sheet - 10-E-2576 - Deethanizer Bottoms Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-03-22
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00582; R1 IFF: TPSK-LSPA1-T-ME-01123
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2577 | Mechanical Equipment Datasheet - Deethanizer Reboiler Cond Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00494
[6 empty] | Return Date | R1 IFD: 2019-01-14
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2580 | Mechanical Equipment Data Sheet - C2 Tower |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-03-05
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00531; R1 IFF: TPSK-LSPA1-T-ME-00981
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2582 | Mechanical Equipment Data Sheet - 10-E-2582 - C2 Tower Reflux Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-16
[6 empty] | Issue Actual | R1 IFD: 2019-01-16; R1 IFF: 2019-02-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00661; R1 IFF: TPSK-LSPA1-T-ME-00859
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-03-12
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2586 | Mechanical Equipment Datasheet - Ethane Recycle Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-05
[6 empty] | Issue Actual | R1 IFD: 2018-12-05
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00413
[6 empty] | Return Date | R1 IFD: 2018-12-27
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2600 | Mechanical Equipment Data Sheet - C3 Hydrog Guard Adsorber |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-17
[6 empty] | Issue Actual | R1 IFD: 2019-01-17; R1 IFF: 2019-01-22; R1 IMP: 2019-03-01; R1 IMP: 2019-04-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00672; R1 IFF: TPSK-LSPA1-T-ME -00701; R1 IMP: TPSK-LSPA1-T-ME-00954; R1 IMP: TPSK-LSPA1-T-ME -01381
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-02-21; R1 IMP: 2019-03-25; R1 IMP: 2019-06-04
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2610 | Mechanical Equipment Datasheet - C3 Hydrog Arsine Guard Bed |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-27
[6 empty] | Issue Actual | R1 IFD: 2018-12-27; R1 IFF: 2019-01-16; R1 IMP: 2019-03-01; R1 IMP: 2019-04-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00570; R1 IFF: TPSK-LSPA1-T-ME-00658; R1 IMP: TPSK-LSPA1-T-ME-00950; R1 IMP: TPSK-LSPA1-T-ME-01381
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-02-11; R1 IMP: 2019-04-01; R1 IMP: 2019-06-04
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2620 | Mechanical Equipment Data Sheet - C3 Hydrog Reactor |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-16; R1 IFI: 2019-02-16
[6 empty] | Revised Plan | R1 IFD: 2019-02-06
[6 empty] | Issue Actual | R1 IFD: 2019-02-06; R1 IFF: 2019-03-06; R1 IMP: 2019-04-12
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00802; R1 IFF: TPSK-LSPA1-T-ME-00990; R1 IMP: TPSK-LSPA1-T-ME-01346
[6 empty] | Return Date | R1 IFD: 2019-02-26; R1 IFF: 2019-03-29; R1 IMP: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2621 | Mechanical Equipment Data Sheet - 10-E-2620 - C3 Hydrog Aftercooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-02-26
[6 empty] | Issue Actual | R1 IFD: 2019-02-26; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00929; R1 IFF: TPSK-LSPA1-T-ME-01233
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2622 | Mechanical Equipment Data Sheet - C3 Hydrog Recycle Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00685; R1 IFF: TPSK-LSPA1-T-ME-01817
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2623 | Mechanical Equipment Datasheet - C3 Hydrog Recycle Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-27; R1 IMP: 2019-06-14; R1 IMP: 2019-07-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-01158; R1 IMP: TPSK-LSPA1-T-ME-01880; R1 IMP: TPSK-LSPA1-T-ME-02295
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-04-10; R1 IMP: 2019-07-09; R1 IMP: 2019-08-26
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2630 | Mechanical Equipment Data Sheet - Secondary Deethanizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00458; R1 IFF: TPSK-LSPA1-T-ME-00974
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2631 | Mechanical Equipment Data Sheet - 10-E-2630 - Secondary Deeth Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-04-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00455; R1 IFF: TPSK-LSPA1-T-ME-01243
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2632 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-04-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00629; R1 IFF: TPSK-LSPA1-T-ME -01314
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-06-05
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2633 | Mechanical Equipment Data Sheet - Secondary Deeth Reflux Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2018-12-20
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00487; R1 IFF: TPSK-LSPA1-T-ME-00554
[6 empty] | Return Date | R1 IFD: 2019-01-16; R1 IFF: 2019-01-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2635 | Mechanical Equipment Data Sheet - 10-E-2635 - Secondary Deeth Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-03
[6 empty] | Issue Actual | R1 IFD: 2019-01-03; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00582; R1 IFF: TPSK-LSPA1-T-ME-01532
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2636 | Mechanical Equipment Data Sheet - 10-E-2636 - Secondary Deeth Bottoms Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-04-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00465; R1 IFF: TPSK-LSPA1-T-ME -01313
[6 empty] | Return Date | R1 IFD: 2018-12-27
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2640 | Mechanical Equipment Data Sheet - C3 Tower |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-12-05
[6 empty] | Issue Actual | R1 IFD: 2018-12-05; R1 IFF: 2019-02-19; R1 IMP: 2019-03-05
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00415; R1 IFF: TPSK-LSPA1-T-ME-00885; R1 IMP: TPSK-LSPA1-T-ME-00981
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-12; R1 IMP: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2644 | Mechanical Equipment Data Sheet - C3 Tower Reboilder Cond Pot |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-29
[6 empty] | Issue Actual | R1 IFD: 2019-01-29; R1 IFF: 2019-05-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00753; R1 IFF: TPSK-LSPA1-T-ME-01760
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2645 | Mechanical Equipment Data Sheet - 10-E-2645 - C3 Tower Reboilers |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-11-26
[6 empty] | Issue Actual | R1 IFD: 2018-11-26; R1 IFF: 2019-01-31; R1 IMP: 2019-04-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00361; R1 IFF: TPSK-LSPA1-T-ME-00773; R1 IMP: TPSK-LSPA1-T-ME-01286
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-02-26; R1 IMP: 2019-05-20
[6 empty] | Owner Cmmt* | R1 IFD: R2; R1 IFF: R1; R1 IMP: TP
| ME | OL1-2M03-2646 | Mechanical Equipment Datasheet - Propane Recycle Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00543
[6 empty] | Return Date | R1 IFD: 2019-01-16
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2647 | Mechanical Equipment Datasheet - HP Propylene - Off Spec Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-01-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00494; R1 IFF: TPSK-LSPA1-T-ME-00770
[6 empty] | Return Date | R1 IFD: 2019-01-14; R1 IFF: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2660 | Mechanical Equipment Datasheet - Debutanizer |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2018-10-23
[6 empty] | Issue Actual | R1 IFD: 2018-10-23; R1 IFF: 2018-11-08; R1 IMP: 2018-12-05; R1 IMP: 2019-02-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00215; R1 IFF: TPSK-LSPA1-T-ME-00288; R1 IMP: TPSK-LSPA1-T-ME-00415; R1 IMP: TPSK-LSPA1-T-ME-00861
[6 empty] | Return Date | R1 IFF: 2018-11-17; R1 IMP: 2018-12-27; R1 IMP: 2019-03-12
Owner Cmmt* | bar: R1 IFF to R1 IMP
| ME | OL1-2M03-2661 | Mechanical Equipment Data Sheet - 10-E-2660 - Debutanizer Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00465; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2662 | Mechanical Equipment Data Sheet - Debutanizer Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-17
[6 empty] | Issue Actual | R1 IFD: 2018-12-17; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00516; R1 IFF: TPSK-LSPA1-T-ME-01535
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2663 | Mechanical Equipment Datasheet - Debutanizer Reflux - Product Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-17
[6 empty] | Issue Actual | R1 IFD: 2018-12-17; R1 IFF: 2019-02-07; R1 IMP: 2019-04-26
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00511; R1 IFF: TPSK-LSPA1-T-ME-00822; R1 IMP: TPSK-LSPA1-T-ME-01479
[6 empty] | Return Date | R1 IFD: 2019-01-14; R1 IFF: 2019-02-21; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2664 | Mechanical Equipment Datasheet - C5 - Pygas Feed Filters |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-26; R1 IFI: 2019-05-16
[6 empty] | Issue Actual | IFR: 2019-03-26; R1 IFI: 2019-05-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01141; R1 IFI: TPSK-LSPA1-T-ME-01669
[6 empty] | Return Date | IFR: 2019-04-11; R1 IFI: 2019-06-19
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-2665 | Mechanical Equipment Data Sheet - 10-E-2665 AB - Debutanizer Reboilers |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-04-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00468; R1 IFF: TPSK-LSPA1-T-ME -01313
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-06-05
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2666 | Mechanical Equipment Data Sheet - 10-E-2666 - Debutanizer Bottoms Cooler |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-04-15; R1 IMP: 2019-05-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00468; R1 IFF: TPSK-LSPA1-T-ME-01344; R1 IMP: TPSK-LSPA1-T-ME-01712
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-05-20; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2667 | Mechanical Equipment Data Sheet - C5-Pygas Surge Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-02-15
[6 empty] | Issue Actual | R1 IFD: 2019-02-15; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00869; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2668 | Mechanical Equipment Datasheet - C5 - Pygas Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-20
[6 empty] | Issue Actual | R1 IFD: 2019-02-20; R1 IFF: 2019-03-21; R1 IMP: 2019-04-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00898; R1 IFF: TPSK-LSPA1-T-ME-01102; R1 IMP: TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-04-10; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2669 | Mechanical Equipment Datasheet - Debutanizer Bottoms Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-04
[6 empty] | Issue Actual | R1 IFD: 2018-12-04; R1 IFF: 2019-02-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00421; R1 IFF: TPSK-LSPA1-T-ME-00823
[6 empty] | Return Date | R1 IFF: 2019-03-15
Owner Cmmt* | bar: R1 IFF
| ME | OL1-2M03-2700 | Mechanical Equipment Data Sheet - GHU-1 Reactor |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-16; R1 IFI: 2019-02-16
[6 empty] | Revised Plan | R1 IFD: 2019-02-04
[6 empty] | Issue Actual | R1 IFD: 2019-02-04; R1 IFF: 2019-04-12
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00795; R1 IFF: TPSK-LSPA1-T-ME-01346
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2701 | Mechanical Equipment Data Sheet - 10-E-2701 - GHU-1 Feed Effluent Exchanger |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-03-21
[6 empty] | Issue Actual | R1 IFD: 2019-03-21; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01100; R1 IFF: TPSK-LSPA1-T-ME-01230
[6 empty] | Return Date | R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFF
| ME | OL1-2M03-2702 | Mechanical Equipment Data Sheet - 10-E-2702 - GHU-1 Start-Up Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-03-20
[6 empty] | Issue Actual | R1 IFD: 2019-03-20; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01095; R1 IFF: TPSK-LSPA1-T-ME -01806
[6 empty] | Return Date | R1 IFD: 2019-04-11; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2703 | Mechanical Equipment Data Sheet - 10-E-2705 - GHU-1 Recycle Cooler |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-02-19
[6 empty] | Issue Actual | R1 IFD: 2019-02-19; R1 IFF: 2019-04-16; R1 IMP: 2019-05-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00895; R1 IFF: TPSK-LSPA1-T-ME-01357; R1 IMP: TPSK-LSPA1-T-ME-01712
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD; R1 IMP
| ME | OL1-2M03-2704 | Mechanical Equipment Datasheet - GHU-1 Recycle Pump |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-19
[6 empty] | Issue Actual | R1 IFD: 2019-02-19; R1 IFF: 2019-03-21; R1 IMP: 2019-06-14; R1 IMP: 2019-07-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00891; R1 IFF: TPSK-LSPA1-T-ME-01102; R1 IMP: TPSK-LSPA1-T-ME-01880; R1 IMP: TPSK-LSPA1-T-ME-02295
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-04-10; R1 IMP: 2019-07-09; R1 IMP: 2019-08-26
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2705 | Mechanical Equipment Data Sheet - GHU-1 Hot Separator |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-02-19
[6 empty] | Issue Actual | R1 IFD: 2019-02-19; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00893; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2706 | Mechanical Equipment Data Sheet - GHU-1 Cold Separator |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-02-26
[6 empty] | Issue Actual | R1 IFD: 2019-02-26; R1 IFF: 2019-06-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00928; R1 IFF: TPSK-LSPA1-T-ME-01850
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2707 | Mechanical Equipment Data Sheet - 10-E-2706 - GHU-1 Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-02-26
[6 empty] | Issue Actual | R1 IFD: 2019-02-26; R1 IFF: 2019-04-25
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00927; R1 IFF: TPSK-LSPA1-T-ME -01467
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2710 | Mechanical Equipment Data Sheet - Depentanizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-02-06
[6 empty] | Issue Actual | R1 IFD: 2019-02-06; R1 IFF: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00805; R1 IFF: TPSK-LSPA1-T-ME -01588
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-07-17
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2711 | Mechanical Equipment Data Sheet - 10-E-2710 - Depentanizer Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-02-22
[6 empty] | Issue Actual | R1 IFD: 2019-02-22; R1 IFF: 2019-04-16
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00908; R1 IFF: TPSK-LSPA1-T-ME-01362
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-05-24
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2712 | Mechanical Equipment Data Sheet - Depentanizer Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-02-15
[6 empty] | Issue Actual | R1 IFD: 2019-02-15; R1 IFF: 2019-06-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00874; R1 IFF: TPSK-LSPA1-T-ME-01850
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2713 | Mechanical Equipment Datasheet - Depentanizer Reflux Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-19
[6 empty] | Issue Actual | R1 IFD: 2019-02-19; R1 IFF: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00891; R1 IFF: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-04-10
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2714 | Mechanical Equipment Datasheet - C5 Cut Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-19
[6 empty] | Issue Actual | R1 IFD: 2019-02-19; R1 IFF: 2019-04-09
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00891; R1 IFF: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-05-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2715 | Mechanical Equipment Data Sheet - 10-E-2715 A-B - Depentanizer Reboiler |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-02-22
[6 empty] | Issue Actual | R1 IFD: 2019-02-22; R1 IFF: 2019-04-16; R1 IMP: 2019-05-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00908; R1 IFF: TPSK-LSPA1-T-ME-01362; R1 IMP: TPSK-LSPA1-T-ME-01685
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD; R1 IMP
| ME | OL1-2M03-2716 | Mechanical Equipment Data Sheet - 10-E-2714 - C5 Cut Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-01-29; R1 IFI: 2019-01-29
[6 empty] | Revised Plan | R1 IFD: 2019-02-15
[6 empty] | Issue Actual | R1 IFD: 2019-02-15; R1 IFF: 2019-05-27
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00872; R1 IFF: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2718 | Mechanical Equipment Data Sheet - Rerun Tower Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-02-15
[6 empty] | Issue Actual | R1 IFD: 2019-02-15; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00869; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2719 | Mechanical Equipment Datasheet - Rerun Tower Reflux - Product Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-19
[6 empty] | Issue Actual | R1 IFD: 2019-02-19; R1 IFF: 2019-04-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00891; R1 IFF: TPSK-LSPA1-T-ME-01493
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2720 | Mechanical Equipment Data Sheet - Rerun Tower |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-04-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00741; R1 IFF: TPSK-LSPA1-T-ME-01399
[6 empty] | Return Date | R1 IFD: 2019-02-21
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2721 | Mechanical Equipment Data Sheet - 10-E-2720 - Rerun Tower Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-03-01
[6 empty] | Issue Actual | R1 IFD: 2019-03-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -00956
[6 empty] | Return Date | R1 IFD: 2019-03-25
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2723 | Mechanical Equipment Data Sheet - 10-E-2724 - Wash Oil Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-01-29; R1 IFI: 2019-01-29
[6 empty] | Revised Plan | R1 IFD: 2019-02-26
[6 empty] | Issue Actual | R1 IFD: 2019-02-26; R1 IFF: 2019-05-27
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00929; R1 IFF: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2724 | Mechanical Equipment Data Sheet - Wash Oil Degassing Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-02-15
[6 empty] | Issue Actual | R1 IFD: 2019-02-15; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00869; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2725 | Mechanical Equipment Data Sheet - 10-E-2725 A B C - Rerun Tower Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-17
[6 empty] | Issue Actual | R1 IFD: 2019-05-17
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01685
[6 empty] | Return Date | R1 IFD: 2019-06-21
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2726 | Mechanical Equipment Datasheet - Pygas Fuel Oil Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-20
[6 empty] | Issue Actual | R1 IFD: 2019-02-20; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00898; R1 IFF: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | R1 IFD: 2019-03-19; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2727 | Mechanical Equipment Data Sheet - 10-E-2726 - Pygas Fuel Oil Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-01-29; R1 IFI: 2019-01-29
[6 empty] | Revised Plan | R1 IFD: 2019-02-20
[6 empty] | Issue Actual | R1 IFD: 2019-02-20; R1 IFF: 2019-05-27
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00897; R1 IFF: TPSK-LSPA1-T-ME-01743
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2728 | Mechanical Equipment Datasheet - Recycle Wash Oil Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-19
[6 empty] | Issue Actual | R1 IFD: 2019-02-19; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00891; R1 IFF: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2729 | Mechanical Equipment Datasheet -Wash Oil Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-02-20
[6 empty] | Issue Actual | R1 IFD: 2019-02-20; R1 IFF: 2019-04-10; R1 IMP: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00898; R1 IFF: TPSK-LSPA1-T-ME-01287; R1 IMP: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD; R1 IMP
| ME | OL1-2M03-2730 | MECHANICAL EQUIPMENT DATASHEET FOR REGEN GAS ELECTRIC HEATER |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-04-19
[6 empty] | Issue Actual | R1 IFD: 2019-04-19
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01410
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2735 | Mechanical Equipment Data Sheet - Regen Hydrog Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-04-05
[6 empty] | Issue Actual | R1 IFD: 2019-04-05
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01253
[6 empty] | Return Date | R1 IFD: 2019-06-05
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2750 | Mechanical Equipment Data Sheet - C4-C5 Hydrog Surge Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-02-15
[6 empty] | Issue Actual | R1 IFD: 2019-02-15; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00869; R1 IFF: TPSK-LSPA1-T-ME-01817
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2751 | Mechanical Equipment Datasheet - C4-C5 Hydrog Feed Pump |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-07
[6 empty] | Issue Actual | R1 IFD: 2019-02-07; R1 IFF: 2019-03-21; R1 IMP: 2019-05-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00817; R1 IFF: TPSK-LSPA1-T-ME-01102; R1 IMP: TPSK-LSPA1-T-ME-01626
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-04-10; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2755 | Mechanical Equipment Data Sheet - 10-E-2755 - C4 -C5 Hydrog Start-Up Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-03-20
[6 empty] | Issue Actual | R1 IFD: 2019-03-20; R1 IFF: 2019-04-30
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01095; R1 IFF: TPSK-LSPA1-T-ME-01514
[6 empty] | Return Date | R1 IFD: 2019-04-11; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2760 | Mechanical Equipment Data Sheet - C4 -C5 Hydrog Reactor |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-16; R1 IFI: 2019-02-16
[6 empty] | Revised Plan | R1 IFD: 2019-02-04
[6 empty] | Issue Actual | R1 IFD: 2019-02-04; R1 IFF: 2019-04-12
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00795; R1 IFF: TPSK-LSPA1-T-ME -01346
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2762 | Mechanical Equipment Data Sheet - C4-C5 Hydrog Recycle Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-02-15
[6 empty] | Issue Actual | R1 IFD: 2019-02-15; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00869; R1 IFF: TPSK-LSPA1-T-ME-01817
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2763 | Mechanical Equipment Data Sheet - 10-E-2760 - C4-C5 Hydro Vent Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-03-18
[6 empty] | Issue Actual | R1 IFD: 2019-03-18; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01075; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-05-02; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2764 | Mechanical Equipment Datasheet - C4-C5 Hydrog Recycle Pump |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-07
[6 empty] | Issue Actual | R1 IFD: 2019-02-07; R1 IFF: 2019-03-21; R1 IMP: 2019-06-14; R1 IMP: 2019-07-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00817; R1 IFF: TPSK-LSPA1-T-ME-01102; R1 IMP: TPSK-LSPA1-T-ME-01880; R1 IMP: TPSK-LSPA1-T-ME-02295
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-04-10; R1 IMP: 2019-07-09; R1 IMP: 2019-08-26
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2765 | Mechanical Equipment Data Sheet - 10-E-2765 - C4 - C5 Hydrog Recycle Cooler |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-03-05
[6 empty] | Issue Actual | R1 IFD: 2019-03-05; R1 IFF: 2019-04-04; R1 IMP: 2019-05-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00991; R1 IFF: TPSK-LSPA1-T-ME -01242; R1 IMP: TPSK-LSPA1-T-ME-01712
[6 empty] | Return Date | R1 IFD: 2019-03-29; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD; R1 IMP
| ME | OL1-2M03-2790 | Mechanical Equipment Data Sheet - Light Oil Drain Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-08
[6 empty] | Issue Actual | R1 IFD: 2019-01-08; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00607; R1 IFF: TPSK-LSPA1-T-ME-01780
[6 empty] | Return Date | R1 IFD: 2019-01-28; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2791 | Mechanical Equipment Datasheet - Light Oil Drain Drum Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-17
[6 empty] | Issue Actual | R1 IFD: 2018-12-17; R1 IFF: 2019-04-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00515; R1 IFF: TPSK-LSPA1-T-ME-01493
[6 empty] | Return Date | R1 IFD: 2019-01-14; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2800 | Mechanical Datasheet For Propylene Refrigeration Compressor |  |  | Purpose** | IFR: IFR; R1 IFI: IFA; R1 IFD: IFD; R1 IFF: IFQ
Rev. | bar: R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2018-09-13; R1 IFD: 2018-10-04
[6 empty] | Revised Plan | R1 IFI: 2018-09-11; R1 IFF: 2018-10-04
[6 empty] | Issue Actual | R1 IFI: 2018-09-11; R1 IFF: 2018-10-04
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00038; R1 IFF: TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date | R1 IFI: 2018-09-28
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2M03-2801 | Mechanical Equipment Datasheet - Propylene Product Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-03-13
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00543; R1 IFF: TPSK-LSPA1-T-ME-01035
[6 empty] | Return Date | R1 IFD: 2019-01-16; R1 IFF: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2805 | Mechanical Equipment Data Sheet - C3R Surge Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-03-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2806 | Mechanical Equipment Data Sheet - 10-E-2805A-C - C3 Refrig Condensers |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-17
[6 empty] | Issue Actual | R1 IFD: 2019-01-17; R1 IFF: 2019-03-22
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00671; R1 IFF: TPSK-LSPA1-T-ME-01123
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2807 | Mechanical Equipment Data Sheet - 10-E-2807 - C3 Chiller No 1 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-14
[6 empty] | Issue Actual | R1 IFD: 2018-12-14; R1 IFF: 2019-04-12
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00505; R1 IFF: TPSK-LSPA1-T-ME-01324
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2809 | Mechanical Equipment Data Sheet - 10-E-2809 - C3 Chiller No 2 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-14
[6 empty] | Issue Actual | R1 IFD: 2018-12-14; R1 IFF: 2019-04-12
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00505; R1 IFF: TPSK-LSPA1-T-ME-01324
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2810 | Mechanical Equipment Data Sheet - C3R 1st Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2815 | Mechanical Equipment Data Sheet - C3R Drain Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-08
[6 empty] | Issue Actual | R1 IFD: 2019-01-08; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00607; R1 IFF: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-01-28; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2816 | Mechanical Equipment Datasheet - Propylene Refrig Recovery Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-02-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00543; R1 IFF: TPSK-LSPA1-T-ME-00822
[6 empty] | Return Date | R1 IFD: 2019-01-16; R1 IFF: 2019-02-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2820 | Mechanical Equipment Data Sheet - C3R 2nd Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2830 | Mechanical Equipment Data Sheet - C3R 3rd Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483
[6 empty] | Return Date | R1 IFD: 2019-01-22
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2840 | Mechanical Equipment Data Sheet - C3R 4TH Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00460
[6 empty] | Return Date | R1 IFD: 2018-12-27
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2850 | Mechanical Equipment Data Sheet for Ethylene Refrigeration Compressor |  |  | Purpose** | IFR: IFR; R1 IFI: IFA; R1 IFD: IFD; R1 IFF: IFQ
Rev. | bar: R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2018-09-13; R1 IFD: 2018-10-04
[6 empty] | Revised Plan | R1 IFI: 2018-09-11; R1 IFF: 2018-10-04
[6 empty] | Issue Actual | R1 IFI: 2018-09-11; R1 IFF: 2018-10-04
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00038; R1 IFF: TPSK-LSPA1-T-ME-00127
[6 empty] | Return Date | R1 IFI: 2018-09-28; R1 IFF: 2018-10-26
Owner Cmmt* | bar: R1 IFI; R1 IFF
| ME | OL1-2M03-2852 | Mechanical Equipment Data Sheet - 10-E-2852 - C2R Desuperheater No 1 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-14
[6 empty] | Issue Actual | R1 IFD: 2018-12-14; R1 IFF: 2019-04-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00505; R1 IFF: TPSK-LSPA1-T-ME-01311
[6 empty] | Return Date | R1 IFD: 2019-01-22
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2853 | Mechanical Equipment Data Sheet - 10-E-2853 - C2R Desuperheater No 2 |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-04-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00541; R1 IFF: TPSK-LSPA1-T-ME -01313
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-06-05
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2854 | Mechanical Equipment Data Sheet - C2R Surge Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00638
[6 empty] | Return Date | R1 IFD: 2019-01-31
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-2855 | Mechanical Equipment Datasheet - Ethylene Product Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-03-13
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00494; R1 IFF: TPSK-LSPA1-T-ME-01035
[6 empty] | Return Date | R1 IFD: 2019-01-14; R1 IFF: 2019-03-29
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2856 | Mechanical Equipment Data Sheet - 10-E-2855 - C2R Condenser |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-11-14
[6 empty] | Issue Actual | R1 IFD: 2018-11-14; R1 IFF: 2019-01-31; R1 IMP: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00316; R1 IFF: TPSK-LSPA1-T-ME-00773; R1 IMP: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-02-04; R1 IFF: 2019-02-26; R1 IMP: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2857 | Mechanical Equipment Data Sheet - 10-E-2857 - HP Ethylene Product Vaporizer |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2018-11-13
[6 empty] | Issue Actual | R1 IFD: 2018-11-13; R1 IFF: 2019-01-31; R1 IMP: 2019-04-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00312; R1 IFF: TPSK-LSPA1-T-ME-00773; R1 IMP: TPSK-LSPA1-T-ME-01246
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-02-26; R1 IMP: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2858 | Mechanical Equipment Data Sheet - 10-E-2858 - HP Ethylene Product Superheater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-04-05
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00684; R1 IFF: TPSK-LSPA1-T-ME-01256
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-06-05
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2859 | Mechanical Equipment Data Sheet - 10-E-2856 - Ethylene Product Subcooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-16; R1 IFI: 2019-02-16
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-04-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00541; R1 IFF: TPSK-LSPA1-T-ME -01234
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-09
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2860 | Mechanical Equipment Data Sheet - C2R 1ST Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00553; R1 IFF: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2865 | Mechanical Equipment Data Sheet - C2R Drain Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-08
[6 empty] | Issue Actual | R1 IFD: 2019-01-08; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00607; R1 IFF: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-01-28; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2870 | Mechanical Equipment Data Sheet - C2R 2ND Stage Suction Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-17
[6 empty] | Issue Actual | R1 IFD: 2019-01-17; R1 IFF: 2019-03-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00670; R1 IFF: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2880 | Mechanical Equipment Data Sheet - C2R 3RD Stage Suction Drum |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-10
[6 empty] | Issue Actual | R1 IFD: 2018-12-10; R1 IFF: 2019-01-23; R1 IMP: 2019-05-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00460; R1 IFF: TPSK-LSPA1-T-ME-00708; R1 IMP: TPSK-LSPA1-T-ME-01723
[6 empty] | Return Date | R1 IFD: 2018-12-27; R1 IFF: 2019-02-21; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2900 | MECHANICAL EQUIPMENT DATASHEET FOR pH CTRL / CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-2900 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2902 | MECHANICAL EQUIPMENT DATASHEET FOR EMULSION BREAKER INJECTION PACKAGE TAG: 10-PK-2902 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2904 | MECHANICAL EQUIPMENT DATASHEET FOR PROCESS WATER STRIPPER CHEMICAL INJECTION PACKAGE TAG: 10-PK-2904 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2906 | MECHANICAL EQUIPMENT DATASHEET FOR DSG ANTI-FOULANT INJECTION PACKAGE TAG: 10-PK-2906 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2910 | Mechanical Equipment Data Sheet - Wash Oil Day Tank |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-26
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-04-23; R1 IMP: 2019-08-19
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00745; R1 IFF: TPSK-LSPA1-T-ME-01449; R1 IMP: TPSK-LSPA1-T-ME-02447
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-18; R1 IMP: 2019-09-26
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-2911 | Mechanical Equipment Datasheet - Wash Oil Injection Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-02-26
[6 empty] | Issue Actual | R1 IFD: 2019-02-26; R1 IFF: 2019-04-09
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00925; R1 IFF: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | R1 IFD: 2019-03-12; R1 IFF: 2019-05-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2912 | MECHANICAL EQUIPMENT DATASHEET FOR CAUSTIC TOWER ANTI-FOULANT INJECTION PACKAGE TAG: 10-PK-2912 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2913 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29012 - Start-up |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02144
Return Date
Owner Cmmt*
| ME | OL1-2M03-2915 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29015 - Start-up |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2920 | MECHANICAL EQUIPMENT DATASHEET FOR POLYMERIZATION INHIBITOR INJECTION PACKAGE TAG: 10-PK-2920 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2921 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29021 - Start-up |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2926 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-29026 - Start-up |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2931 | MECHANICAL EQUIPMENT DATASHEET FOR PROPANOL INJECTION PACKAGE TAG: 10-PK-2931 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2932 | Mechanical Equipment Data Sheet - Methanol Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-23
[6 empty] | Issue Actual | R1 IFD: 2019-01-23; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00709; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2934 | Mechanical Equipment Datasheet - Methanol Injection Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-04-10
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-2940 | MECHANICAL EQUIPMENT DATASHEET FOR C4 POLYMER INHIBITOR INJECTION PACKAGE TAG: 10-PK-2940 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-2945 | MECHANICAL EQUIPMENT DATASHEET FOR ANTI-OXIDANT INJECTION PACKAGE TAG: 10-PK-2945 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01673
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-3000 | Mechanical Equipment Data Sheet Predistillation Tower |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-09
[6 empty] | Issue Actual | R1 IFD: 2019-04-09; R1 IFF: 2019-06-11; R1 IMP: 2019-06-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01275; R1 IFF: TPSK-LSPA1-T-ME-01870; R1 IMP: TPSK-LSPA1-T-ME-01909
[6 empty] | Return Date | R1 IFD: 2019-05-20; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3001 | Mechanical Equipment Data Sheet - 10-E-3000 - Predistillation Tower Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02502
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3002 | Mechanical Equipment Data Sheet for Predistillation Feed Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-13
[6 empty] | Issue Actual | R1 IFD: 2019-05-13; R1 IFF: 2019-08-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -01645; R1 IFF: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date | R1 IFD: 2019-06-03; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3003 | Mechanical Equipment Data Sheet for Predistillation Tower Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-13
[6 empty] | Issue Actual | R1 IFD: 2019-05-13; R1 IFF: 2019-08-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -01645; R1 IFF: TPSK-LSPA1-T-ME-02453
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-09-26
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3004 | Mechanical Equipment Data Sheet - 10-E-3004 - Predistillation Tower Trim Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02502
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3005 | Mechanical Equipment Data Sheet - 10-E-3005- Predistillation Tower Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02510
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3006 | Mechanical Equipment Datasheet for Predistallation Tower Feed Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-17
[6 empty] | Issue Actual | R1 IFD: 2019-04-17; R1 IFF: 2019-06-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01370; R1 IFF: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date | R1 IFD: 2019-06-17; R1 IFF: 2019-07-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3007 | Mechanical Equipment Datasheet for Predistillation Tower Reflux Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-16
[6 empty] | Issue Actual | R1 IFD: 2019-04-16; R1 IFF: 2019-06-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01363; R1 IFF: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date | R1 IFF: 2019-07-15
Owner Cmmt* | bar: R1 IFF
| ME | OL1-2M03-3010 | Mechanical Equipment Data Sheet C4 Vaporization Tower |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFQ; R1 IFD: IFQ; R1 IFF: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C; R1 IFF: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-08; R1 IFF: 2019-09-12
[6 empty] | Issue Actual | IFR: 2019-04-08; R1 IFI: 2019-06-10; R1 IFD: 2019-06-18; R1 IFF: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01275; R1 IFI: TPSK-LSPA1-T-ME-01818; R1 IFD: TPSK-LSPA1-T-ME-01909; R1 IFF: TPSK-LSPA1-T-ME-02613
[6 empty] | Return Date | IFR: 2019-05-20; R1 IFI: 2019-07-08
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-3014 | Mechanical Equipment Data Sheet - 10-E-3014 - C4 Solvent Vaporizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02510
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3015 | Mechanical Equipment Data Sheet - 10-E-3015 - C4 Trim Vaporizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02510
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3016 | Mechanical Equipment Datasheet for Heavy Ends Discharge Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-24
[6 empty] | Issue Actual | R1 IFD: 2019-04-24; R1 IFF: 2019-06-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01451; R1 IFF: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-07-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3018 | Mechanical Equipment Data Sheet - 10-E-3018 - Solvent Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02508
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3020 | Mechanical Equipment Datasheet - Main Washer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-09
[6 empty] | Issue Actual | R1 IFD: 2019-04-09; R1 IFF: 2019-06-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01275; R1 IFF: TPSK-LSPA1-T-ME-01870
[6 empty] | Return Date | R1 IFD: 2019-05-20; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3021 | Mechanical Equipment Data Sheet - 10-E-3020 - Main Washer Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02510
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3022 | Mechanical Equipment Data Sheet for Main Washer Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFD; R1 IFF: IFQ
Rev. | bar: R1 IFI; R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFD: 2019-05-13
[6 empty] | Revised Plan | R1 IFI: 2019-05-13; R1 IFF: 2019-08-15
[6 empty] | Issue Actual | R1 IFI: 2019-05-13; R1 IFF: 2019-08-15
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME -01645; R1 IFF: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date | R1 IFI: 2019-06-18; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFI; R1 IFF
| ME | OL1-2M03-3023 | Mechanical Equipment Datasheet for Main Washer Reflux C4 Raffinate-I Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-16
[6 empty] | Issue Actual | R1 IFD: 2019-04-16
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | R1 IFD: 2019-06-17
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3026 | Mechanical Equipment Datasheet - Main Washer Bottom Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -01562
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3030 | Mechanical Equipment Data Sheet After Washer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-12
[6 empty] | Issue Actual | R1 IFD: 2019-04-12; R1 IFF: 2019-06-14
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01325; R1 IFF: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date | R1 IFD: 2019-05-20
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3031 | Mechanical Equipment Data Sheet - 10-E-3030 -After Washer Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02508
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3032 | Mechanical Equipment Data Sheet - After Washer Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-13
[6 empty] | Issue Actual | R1 IFD: 2019-05-13; R1 IFF: 2019-08-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -01645; R1 IFF: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3033 | Mechanical Equipment Datasheet for After Washer Reflux-Crude Butadiene Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-17
[6 empty] | Issue Actual | R1 IFD: 2019-04-17; R1 IFF: 2019-06-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01370; R1 IFF: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date | R1 IFD: 2019-06-17; R1 IFF: 2019-07-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3036 | Mechanical Equipment Datasheet for After Washer Bottom Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-17
[6 empty] | Issue Actual | R1 IFD: 2019-04-17; R1 IFF: 2019-06-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01370; R1 IFF: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date | R1 IFD: 2019-06-17; R1 IFF: 2019-07-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3040 | Mechanical Equipment Data Sheet Rectifier |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-09
[6 empty] | Issue Actual | R1 IFD: 2019-04-09; R1 IFF: 2019-06-14
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01275; R1 IFF: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date | R1 IFD: 2019-05-20
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3044 | Mechanical Equipment Data Sheet - 10-E-3044 - Solvent Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02510
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3045 | Mechanical Equipment Data Sheet - 10-E-3045 A-D- Solvent Heat Exchanger |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02509
[6 empty] | Return Date | R1 IFD: 2019-05-29; R1 IFF: 2019-09-26
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3046 | Mechanical Equipment Datasheet for Degasser Feed Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-18
[6 empty] | Issue Actual | R1 IFD: 2019-04-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01398
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3047 | Mechanical Equipment Datasheet for Rectifier Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-18
[6 empty] | Issue Actual | R1 IFD: 2019-04-18; R1 IFF: 2019-06-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01398; R1 IFF: TPSK-LSPA1-T-ME-01910
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-07-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3050 | Mechanical Equipment Data Sheet Degasser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-12
[6 empty] | Issue Actual | R1 IFD: 2019-04-12; R1 IFF: 2019-06-14
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01325; R1 IFF: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date | R1 IFD: 2019-05-20
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3055 | Mechanical Equipment Data Sheet - 10-E-3055 - Degasser Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02509
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3056 | Mechanical Equipment Datasheet - Degasser Bottom Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-07
[6 empty] | Issue Actual | R1 IFD: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01582
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3060 | Mechanical Equipment Datasheet - C4 Acetylene Washer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-09
[6 empty] | Issue Actual | R1 IFD: 2019-04-09; R1 IFF: 2019-06-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01275; R1 IFF: TPSK-LSPA1-T-ME-01870
[6 empty] | Return Date | R1 IFD: 2019-05-20; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3061 | Mechanical Equipment Datasheet - Dimer Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-05-07
[6 empty] | Issue Actual | R1 IFD: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3062 | Mechanical Equipment Data Sheet - 10-E-3062 - Acetylene Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02509
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3063 | Mechanical Equipment Data Sheet - 10-E-3060 - C4 Acetylene Washer Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02510
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3064 | Mechanical Equipment Data Sheet - BDU HC-Water Separator |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date | R1 IFD: 2019-06-03
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3065 | Mechanical Equipment Data Sheet - C4 Acetylene Accumulator |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-13
[6 empty] | Issue Actual | R1 IFD: 2019-05-13
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -01645
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3066 | Mechanical Equipment Datasheet - Wastewater Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date | R1 IFD: 2019-05-24
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3067 | Mechanical Equipment Datasheet - C4 Acetylene Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-07
[6 empty] | Issue Actual | R1 IFD: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3070 | Mechanical Equipment Data Sheet Direct Cooler Tower |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-09
[6 empty] | Issue Actual | R1 IFD: 2019-04-09; R1 IFF: 2019-06-14
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01275; R1 IFF: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date | R1 IFD: 2019-05-20
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3071 | Mechanical Equipment Data Sheet - 10-E-3070 - Water - NMP Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02509
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3073 | Mechanical Equipment Datasheet - BDU Recycle Gas Compressor |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-01-10; R1 IFI: 2019-01-31
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-03-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00692; R1 IFF: TPSK-LSPA1-T-ME-01066
[6 empty] | Return Date | R1 IFD: 2019-02-26; R1 IFF: 2019-04-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3076 | Mechanical Equipment Datasheet - Direct Cooler Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date | R1 IFD: 2019-05-24
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3080 | Mechanical Equipment Data Sheet Butadiene Tower |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-09
[6 empty] | Issue Actual | R1 IFD: 2019-04-09; R1 IFF: 2019-06-14
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01275; R1 IFF: TPSK-LSPA1-T-ME-01893
[6 empty] | Return Date | R1 IFD: 2019-05-20
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3081 | Mechanical Equipment Data Sheet - 10-E-3080 - Butadiene Tower Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02509
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3082 | Mechanical Equipment Data Sheet - Butadiene Tower Reflux Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14; R1 IFF: 2019-08-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654; R1 IFF: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date | R1 IFD: 2019-06-03; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3083 | Mechanical Equipment Datasheet - Butadiene Tower Refllux Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date | R1 IFD: 2019-05-24
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3084 | Mechanical Equipment Data Sheet - 10-E-3084 - Butadiene Tower Trim Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LPSA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02511
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3085 | Mechanical Equipment Data Sheet - 10-E-3085 - Butadiene Tower Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02524
[6 empty] | Return Date | R1 IFD: 2019-05-29; R1 IFF: 2019-09-26
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3086 | Mechanical Equipment Datasheet - Butadiene Tower Bottom Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-07
[6 empty] | Issue Actual | R1 IFD: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3090 | Mechanical Equipment Data Sheet Butadiene Drying Tower |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-11
[6 empty] | Issue Actual | R1 IFD: 2019-04-11; R1 IFF: 2019-06-14
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01312; R1 IFF: TPSK-LSPA1-T-ME-01893
Return Date
Owner Cmmt*
| ME | OL1-2M03-3095 | Mechanical Equipment Data Sheet - 10-E-3095 - Butadiene Drying Tower Reboiler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02520
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3097 | Mechanical Equipment Datasheet - Butadiene Product Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-07
[6 empty] | Issue Actual | R1 IFD: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3098 | Mechanical Equipment Data Sheet - 10-E-3098 - Butadiene Product Subcooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02520
[6 empty] | Return Date | R1 IFD: 2019-05-29; R1 IFF: 2019-09-26
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3100 | Mechanical Equipment Data Sheet - Solvent Regen Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-07
[6 empty] | Issue Actual | R1 IFD: 2019-05-07; R1 IFF: 2019-08-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654; R1 IFF: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date | R1 IFD: 2019-06-03; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3110 | Mechanical Equipment Datasheet - Water Washer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-03-14; R1 IFI: 2019-04-11
[6 empty] | Revised Plan | R1 IFD: 2019-04-09
[6 empty] | Issue Actual | R1 IFD: 2019-04-09; R1 IFF: 2019-06-19
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01275; R1 IFF: TPSK-LSPA1-T-ME-01916
[6 empty] | Return Date | R1 IFD: 2019-05-20; R1 IFF: 2019-07-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3111 | Mechanical Equipment Data Sheet - 10-E-3110 - Water Washer Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02520
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3112 | Mechanical Equipment Data Sheet - Water Washer Accumulator |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date | R1 IFD: 2019-06-03
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3113 | Mechanical Equipment Datasheet - Solvent Return Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date | R1 IFD: 2019-05-24
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3126 | Mechanical Equipment Data Sheet - Ejector Seal Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654
[6 empty] | Return Date | R1 IFD: 2019-06-03
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3127 | Mechanical Equipment Datasheet - BDU Ejector Seal Drum Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date | R1 IFD: 2019-05-24
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3150 | Mechanical Equipment Data Sheet - 10-E-3150 - BDU Condensate Heater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02520
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3151 | Mechanical Equipment Data Sheet - BDU Condensate Flash Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14; R1 IFF: 2019-08-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654; R1 IFF: TPSK-LSPA1-T-ME-02453
[6 empty] | Return Date | R1 IFD: 2019-06-03; R1 IFF: 2019-09-26
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3160 | Mechanical Equipment Data Sheet - 10-E-3160 - BDU Condensate Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03; R1 IFF: 2019-08-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01565; R1 IFF: TPSK-LSPA1-T-ME-02520
[6 empty] | Return Date | R1 IFD: 2019-05-29
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3161 | Mechanical Equipment Data Sheet - BDU Condensate Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14; R1 IFF: 2019-08-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654; R1 IFF: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date | R1 IFD: 2019-06-03; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3162 | Mechanical Equipment Datasheet - BDU Condensate Recycle Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-03
[6 empty] | Issue Actual | R1 IFD: 2019-05-03
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01563
[6 empty] | Return Date | R1 IFD: 2019-05-24
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3180 | Mechanical Equipment Data Sheet - BDU Knock-Out Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14; R1 IFF: 2019-08-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654; R1 IFF: TPSK-LSPA1-T-ME-02453
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-09-26
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3190 | Mechanical Equipment Data Sheet - NMP Slop Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14; R1 IFF: 2019-08-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654; R1 IFF: TPSK-LSPA1-T-ME-02437
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3191 | Mechanical Equipment Datasheet - Solvent Slop Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-07
[6 empty] | Issue Actual | R1 IFD: 2019-05-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01570
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3900 | Mechanical Equipment Data Sheet For NMP Storage Tank |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-26
[6 empty] | Revised Plan | R1 IFD: 2019-04-24
[6 empty] | Issue Actual | R1 IFD: 2019-04-24; R1 IFF: 2019-08-22
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01449; R1 IFF: TPSK-LSPA1-T-ME-02467
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3901 | Mechanical Equipment Datasheet for NMP Storage Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-02
[6 empty] | Issue Actual | R1 IFD: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3902 | Mechanical Equipment Data Sheet - BDU Solvent Inhibitor Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14; R1 IFF: 2019-08-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654; R1 IFF: TPSK-LSPA1-T-ME-02455
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3903 | Mechanical Equipment Datasheet for BDU Solvent Inhibitor Dosing Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-04-24
[6 empty] | Issue Actual | R1 IFD: 2019-04-24
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01451
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3904 | Mechanical Equipment Data Sheet - BDU Product Inhibitor Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14; R1 IFF: 2019-08-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654; R1 IFF: TPSK-LSPA1-T-ME-02455
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3905 | Mechanical Equipment Datasheet for BDU Product Inhibitor Dosing Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-04-24
[6 empty] | Issue Actual | R1 IFD: 2019-04-24
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01451
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3906 | Mechanical Equipment Data Sheet - BDU Anti Form Agent Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-05-14
[6 empty] | Issue Actual | R1 IFD: 2019-05-14; R1 IFF: 2019-08-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01654; R1 IFF: TPSK-LSPA1-T-ME-02453
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-09-26
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-3907 | Mechanical Equipment Datasheet for BDU Anti-Foam Dosing Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-04-24
[6 empty] | Issue Actual | R1 IFD: 2019-04-24
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01451
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-3908 | Mechanical Equipment Data Sheet for Predistillation Inhibitor Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-04-18
[6 empty] | Issue Actual | R1 IFD: 2019-04-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01389
Return Date
Owner Cmmt*
| ME | OL1-2M03-3909 | Mechanical Equipment Datasheet for BDU Predistillation Inhibitor Dosing Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-04-24
[6 empty] | Issue Actual | R1 IFD: 2019-04-24
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01451
[6 empty] | Return Date | R1 IFD: 2019-06-18
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-4311 | Mechanical Equipment Datasheet Emergency Diesel Engine Generator - Substation C |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-28
[6 empty] | Issue Actual | IFR: 2019-08-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02515
Return Date
Owner Cmmt*
| ME | OL1-2M03-4312 | Mechanical Equipment Datasheet Emergency Diesel Engine Generator - Substation E |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-28
[6 empty] | Issue Actual | IFR: 2019-08-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02515
Return Date
Owner Cmmt*
| ME | OL1-2M03-4313 | Mechanical Equipment Datasheet Emergency Diesel Engine Generator - Substation F |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-28
[6 empty] | Issue Actual | IFR: 2019-08-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02515
Return Date
Owner Cmmt*
| ME | OL1-2M03-5100 | Mechanical Equipment Datasheet for Deaerator D-5100 |  | Class 2 | Purpose** | IFR: IFP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-02
[6 empty] | Issue Actual | IFR: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01209
Return Date
Owner Cmmt*
| ME | OL1-2M03-5101 | Mechanical Equipment Data Sheet - SHP BFW Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-10-27
[6 empty] | Issue Actual | R1 IFD: 2018-10-27; R1 IFF: 2018-11-15; R1 IMP: 2018-12-11; R1 IMP: 2019-04-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00236; R1 IFF: TPSK-LSPA1-T-ME-00322; R1 IMP: TPSK-LSPA1-T-ME-00476; R1 IMP: TPSK-LSPA1-T-ME-01433
[6 empty] | Return Date | R1 IFD: 2018-11-19; R1 IFF: 2018-12-10; R1 IMP: 2019-01-16; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-5102 | Mechanical Equipment Data Sheet - VLP BFW Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-10-27
[6 empty] | Issue Actual | R1 IFD: 2018-10-27; R1 IFF: 2018-12-11; R1 IMP: 2019-04-03; R1 IMP: 2019-04-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00236; R1 IFF: TPSK-LSPA1-T-ME-00476; R1 IMP: TPSK-LSPA1-T-ME-01227; R1 IMP: TPSK-LSPA1-T-ME-01433
[6 empty] | Return Date | R1 IFD: 2018-11-19; R1 IFF: 2019-01-16; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF; R1 IMP
| ME | OL1-2M03-5103 | Mechanical Equipment Data Sheet - 10-E-5100 - Deaerator Vent Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-29
[6 empty] | Issue Actual | R1 IFD: 2019-01-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00755
[6 empty] | Return Date | R1 IFD: 2019-02-21
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5107 | Mechanical Equipment Data Sheet - 10-E-5112 - Suspect Cond Flash Drum Vent Condenser |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-29
[6 empty] | Issue Actual | R1 IFD: 2019-01-29; R1 IFF: 2019-04-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00755; R1 IFF: TPSK-LSPA1-T-ME-01396
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5108 | Mechanical Equipment Data Sheet - 10-E-5110 - Suspect Condensate Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2018-10-20; R1 IFI: 2018-10-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-25
[6 empty] | Issue Actual | R1 IFD: 2019-01-25
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00723
[6 empty] | Return Date | R1 IFD: 2019-02-21
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5109 | Mechanical Equipment Data Sheet - Condensate Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. |  |  | A | B | C | D | E
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-10-26
[6 empty] | Issue Actual |  |  | 2018-10-26 | 2018-11-14 | 2018-12-11 | 2019-03-26 | 2019-04-01
[6 empty] | Transmittal no. |  |  | TPSK-LSPA1-T-ME-00235 | TPSK-LSPA1-T-ME-00317 | TPSK-LSPA1-T-ME-00476 | TPSK-LSPA1-T-ME-01151 | TPSK-LSPA1-T-ME-01197
[6 empty] | Return Date | R1 IFD: 2018-11-19; R1 IFF: 2019-02-21; R1 IMP: 2019-01-16; R1 IMP: 2019-04-10
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-5110 | Mechanical Equipment Data Sheet - Condensate Tank |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-26
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-04-23; R1 IMP: 2019-08-22
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00746; R1 IFF: TPSK-LSPA1-T-ME-01430; R1 IMP: TPSK-LSPA1-T-ME-02474
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-18; R1 IMP: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-5111 | Mechanical Equipment Datasheet - Suspect Condensate Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-20
[6 empty] | Issue Actual | R1 IFD: 2018-11-20; R1 IFF: 2018-12-20
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00341; R1 IFF: TPSK-LSPA1-T-ME-00544
[6 empty] | Return Date | R1 IFD: 2018-12-13; R1 IFF: 2019-01-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5112 | Mechanical Equipment Data Sheet - Suspect Condensate Flash Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-16
[6 empty] | Issue Actual | R1 IFD: 2019-01-16
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00657
[6 empty] | Return Date | R1 IFD: 2019-02-11
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5113 | Mechanical Equipment Data Sheet - 10-E-5113 - Foul Condensate Cooler |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-29
[6 empty] | Issue Actual | R1 IFD: 2019-01-29; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00755; R1 IFF: TPSK-LSPA1-T-ME-01545
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5114 | Mechanical Equipment Data Sheet - LP Condensate Flash Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-16
[6 empty] | Issue Actual | R1 IFD: 2019-01-16
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00657
[6 empty] | Return Date | R1 IFD: 2019-02-11
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5115 | Mechanical Equipment Datasheet For Condensate Carbon Filter Package |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-03-13; R1 IFI: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01040; R1 IFI: TPSK-LSPA1-T-ME-02405
[6 empty] | Return Date | IFR: 2019-04-01; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-5120 | Mechanical Equipment Data Sheet - Raw Condensate Tank |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-26
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-08-22
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00746; R1 IFF: TPSK-LSPA1-T-ME-02474
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5121 | Mechanical Equipment Datasheet - Raw Condensate Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-20
[6 empty] | Issue Actual | R1 IFD: 2018-11-20; R1 IFF: 2018-12-20
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00341; R1 IFF: TPSK-LSPA1-T-ME-00544
[6 empty] | Return Date | R1 IFD: 2018-12-13; R1 IFF: 2019-01-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5122 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51022 - PV-5147 Outlet |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5123 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51023 - PV-5155 Outlet |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5124 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51024 - PV-5158 Outlet |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5125 | Mechanical Equipment Datasheet for Condensate Polisher Package |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-28; R1 IFI: 2019-09-03
[6 empty] | Issue Actual | IFR: 2019-02-28; R1 IFI: 2019-09-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00941; R1 IFI: TPSK-LSPA1-T-ME-02546
[6 empty] | Return Date | IFR: 2019-04-01; R1 IFI: 2019-10-01
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-5126 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51026A-H - PSV-5143A-H Outlet |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5127 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51021 - PV-5143 Outlet |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02144
Return Date
Owner Cmmt*
| ME | OL1-2M03-5128 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51025 - PV-5161 Outlet |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02144
Return Date
Owner Cmmt*
| ME | OL1-2M03-5130 | Mechanical Equipment Datasheet for Vent Silencer 10-SP-51030A/B/C/D - PSV-5150A/B/C/D Outlet |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02143
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5140 | Mechanical Equipment Data Sheet - Intermittent Blowdown Drum |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-20
[6 empty] | Issue Actual | R1 IFD: 2018-12-20; R1 IFF: 2019-01-11; R1 IMP: 2019-05-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA-T-ME-00548; R1 IFF: TPSK-LSPA1-T-ME-00638; R1 IMP: TPSK-LSPA1-T-ME-01760
[6 empty] | Return Date | R1 IFD: 2019-01-24; R1 IFF: 2019-01-31; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-5141 | Mechanical Equipment Datasheet - Intermittent Blowdown Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-11-19
[6 empty] | Issue Actual | R1 IFD: 2018-11-19
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00335
[6 empty] | Return Date | R1 IFD: 2018-12-13
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5150 | Mechanical Equipment Data Sheet - Continuous Blow Down Flash Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00629; R1 IFF: TPSK-LSPA1-T-ME-01780
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5170 | Mechanical Data Sheet For General Purpose Turbines PT-5100 A-B SHP BFW Pumps Turbines |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02130
Return Date
Owner Cmmt*
| ME | OL1-2M03-5171 | Mechanical Data Sheet For General Purpose Steam Turbines PT-5102 A VLP BFW Pump Turbine |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5172 | Mechanical Data Sheet For General Purpose Steam Turbines PT-5110 A Condensate Pump Turbine |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02130
[6 empty] | Return Date | IFR: 2019-08-01
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5200 | Mechanical Equipment Data Sheet - Fuel Gas Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00629
[6 empty] | Return Date | R1 IFD: 2019-01-31
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5201 | Mechanical Equipment Data Sheet - 10-E-5200 - MP Ethylene Superheater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-29
[6 empty] | Issue Actual | R1 IFD: 2019-01-29; R1 IFF: 2019-04-15
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00755; R1 IFF: TPSK-LSPA1-T-ME-01344
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5202 | Mechanical Equipment Data Sheet - MP Ethylene Superhtr Cond Pot |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00685; R1 IFF: TPSK-LSPA1-T-ME-01780
[6 empty] | Return Date | R1 IFD: 2019-02-15; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5210 | Mechanical Equipment Data Sheet - 10-E-5210 - Pilot Gas Vaporizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-17
[6 empty] | Issue Actual | R1 IFD: 2019-01-17; R1 IFF: 2019-04-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00673; R1 IFF: TPSK-LSPA1-T-ME-01436
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5211 | Mechanical Equipment Data Sheet - Pilot Gas Vaporizer Cond Pot |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-23
[6 empty] | Issue Actual | R1 IFD: 2019-01-23; R1 IFF: 2019-03-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00709; R1 IFF: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5350 | Mechanical Equipment Datasheet for Cooling Tower |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: B; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-06; R1 IFI: 2019-04-25
[6 empty] | Issue Actual | IFR: 2018-11-06; R1 IFI: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00276; R1 IFI: TPSK-LSPA1-T-ME-01476
[6 empty] | Return Date | IFR: 2019-02-15; R1 IFI: 2019-06-18
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-5352 | Mechanical Equipment DataSheet - Olefins Cooling Water Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-10-23
[6 empty] | Issue Actual | R1 IFD: 2018-10-23; R1 IFF: 2018-11-28
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00210; R1 IFF: TPSK-LSPA1-T-ME-00388
[6 empty] | Return Date | R1 IFD: 2018-11-14; R1 IFF: 2018-12-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5355 | Mechanical Equipment Datasheet for Side Stream Filter Package |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: B; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-31; R1 IFI: 2019-03-27
[6 empty] | Issue Actual | IFR: 2018-10-31; R1 IFI: 2019-03-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00248; R1 IFI: TPSK-LSPA1-T-ME-01164
[6 empty] | Return Date | IFR: 2018-11-27; R1 IFI: 2019-04-25
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2M03-5361 | Mechanical Data Sheet - CTU Cooling Water Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C; R1 IMP: D
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2018-10-23
[6 empty] | Issue Actual | R1 IFD: 2018-10-23; R1 IFF: 2018-11-14; R1 IMP: 2018-11-28; R1 IMP: 2019-01-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00210; R1 IFF: TPSK-LSPA1-T-ME-00317; R1 IMP: TPSK-LSPA1-T-ME-00388; R1 IMP: TPSK-LSPA1-T-ME-00627
[6 empty] | Return Date | R1 IFD: 2018-11-14; R1 IFF: 2019-02-21; R1 IMP: 2018-12-18; R1 IMP: 2019-01-31
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-5371 | Mechanical Equipment Datasheet - CW Filter Backwash Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-13; R1 IMP: 2019-04-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-01038; R1 IMP: TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-29; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-5390 | MECHANICAL EQUIPMENT DATASHEET FOR COPPER CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-5390 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5392 | MECHANICAL EQUIPMENT DATASHEET FOR MILD STEEL CORROSION INHIBITOR INJECTION PACKAGE TAG: 10-PK-5392 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5394 | MECHANICAL EQUIPMENT DATASHEET FOR DISPERSANT INJECTION PACKAGE TAG: 10-PK-5394 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5397 | MECHANICAL EQUIPMENT DATASHEET FOR NON-OXIDIZING BIOCIDE INJECTION PACKAGE TAG: 10-PK-5397 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5400 | Mechanical Equipment Data Sheet - Instrument Air Receiver |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-05-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00685; R1 IFF: TPSK-LSPA1-T-ME-01723
[6 empty] | Return Date | R1 IFD: 2019-02-15; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5500 | Mechanical Equipment Data Sheet - Hot Flare Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2018-12-13
[6 empty] | Issue Actual | R1 IFD: 2018-12-13; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00483; R1 IFF: TPSK-LSPA1-T-ME-01535
[6 empty] | Return Date | R1 IFD: 2019-01-22; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5501 | Mechanical Equipment Datasheet - Hot Blowdown Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-10
[6 empty] | Issue Actual | R1 IFD: 2019-01-10; R1 IFF: 2019-02-07; R1 IMP: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00616; R1 IFF: TPSK-LSPA1-T-ME-00822; R1 IMP: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-02-21; R1 IMP: 2019-04-10
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-5510 | Mechanical Equipment Data Sheet - Cold Flare Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00629
[6 empty] | Return Date | R1 IFD: 2019-01-31
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5511 | Mechanical Equipment Data Sheet - 10-E-5510 - Cold Flare Blowdown Vaporizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-29
[6 empty] | Issue Actual | R1 IFD: 2019-01-29; R1 IFF: 2019-04-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00755; R1 IFF: TPSK-LSPA1-T-ME-01495
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5512 | Mechanical Equipment Data Sheet - 10-E-5512 - Cold Flare Superheater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-29
[6 empty] | Issue Actual | R1 IFD: 2019-01-29; R1 IFF: 2019-04-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00755; R1 IFF: TPSK-LSPA1-T-ME-01247
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-20
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5513 | Mechanical Equipment Data Sheet - 10-E-5513 - Methanol Vaporizer |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-25
[6 empty] | Issue Actual | R1 IFD: 2019-01-25; R1 IFF: 2019-04-01
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00723; R1 IFF: TPSK-LSPA1-T-ME-01205
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5514 | Mechanical Equipment Data Sheet - Methanol Vaporizer Cond Pot |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-23
[6 empty] | Issue Actual | R1 IFD: 2019-01-23; R1 IFF: 2019-03-29
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00709; R1 IFF: TPSK-LSPA1-T-ME-01186
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-02
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5515 | Mechanical Equipment Data Sheet - Methanol Makeup Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-08
[6 empty] | Issue Actual | R1 IFD: 2019-01-08; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00607; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-01-28; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5520 | Mechanical Equipment Data Sheet - Vent Collection Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00638; R1 IFF: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5522 | Mechanical Equipment Datasheet - LP Vent Blower |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00640
[6 empty] | Return Date | R1 IFD: 2019-02-11
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5550 | Mechanical Equipment Data Sheet - HP Flare Knock-Out Drum |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-21; R1 IMP: 2019-05-30
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00629; R1 IFF: TPSK-LSPA1-T-ME-01114; R1 IMP: TPSK-LSPA1-T-ME-01764
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD; R1 IMP
| ME | OL1-2M03-5551 | Mechanical Equipment Datasheet - HP Flare Knock-Out Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-10
[6 empty] | Issue Actual | R1 IFD: 2019-01-10; R1 IFF: 2019-05-02
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00616; R1 IFF: TPSK-LSPA1-T-ME-01524
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5552 | Mechanical Equipment Data Sheet - LPG Storage Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00638; R1 IFF: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-01-31; R1 IFF: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5553 | Mechanical Equipment Data Sheet - 10-E-5552 - LPG Vaporizer - Superheater |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | R1 IFD: 2019-01-22
[6 empty] | Issue Actual | R1 IFD: 2019-01-22; R1 IFF: 2019-04-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00684; R1 IFF: TPSK-LSPA1-T-ME-01436
[6 empty] | Return Date | R1 IFD: 2019-02-11; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5555 | Mechanical Equipment Data Sheet - LPG Vaporizer- Superhtr Cond Pot |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-23
[6 empty] | Issue Actual | R1 IFD: 2019-01-23; R1 IFF: 2019-03-29; R1 IMP: 2019-05-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00709; R1 IFF: TPSK-LSPA1-T-ME-01186; R1 IMP: TPSK-LSPA1-T-ME-01783
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-02; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFD to R1 IMP
| ME | OL1-2M03-5560 | Mechanical Data Sheet for HP / Polyolefins Flare Package |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-17; R1 IFI: 2019-06-25
[6 empty] | Issue Actual | IFR: 2019-01-17; R1 IFI: 2019-06-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00667; R1 IFI: TPSK-LSPA1-T-ME-01969
[6 empty] | Return Date | IFR: 2019-02-08; R1 IFI: 2019-07-15
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-5565 | Mechanical Equipment Data Sheet for Polyolefins Flare Knock-Out Drum |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-08; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | R1 IFD: 2019-01-23
[6 empty] | Issue Actual | R1 IFD: 2019-01-23; R1 IFF: 2019-06-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00709; R1 IFF: TPSK-LSPA1-T-ME-01803
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-07-08
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5566 | Mechanical Equipment Datasheet - Polyolefins Flare Knock-Out Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-04-23
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-01426
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5606 | Mechanical Equipment Datasheet - Pygas Area Oily Wastewater Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-07
[6 empty] | Issue Actual | R1 IFD: 2019-02-07; R1 IFF: 2019-04-09
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00817; R1 IFF: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-05-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5607 | Mechanical Equipment Datasheet - Butadiene Area Oily Wastewater Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5608 | Mechanical Equipment Datasheet - QW Area Oily Wastewater Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5609 | Mechanical Equipment Datasheet - CGC Area Oily Wastewater Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5611 | Mechanical Equipment Datasheet - Hydroblast Sump Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-04-09
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-01279
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-05-16
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5612 | Mechanical Equipment Datasheet for Hydroblast Filter |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-25; R1 IFI: 2019-03-18
[6 empty] | Revised Plan | R1 IFD: 2019-01-11
[6 empty] | Issue Actual | R1 IFD: 2019-01-11; R1 IFF: 2019-03-26
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00639; R1 IFF: TPSK-LSPA1-T-ME-01141
[6 empty] | Return Date | R1 IFD: 2019-01-30; R1 IFF: 2019-04-11
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5613 | Mechanical Equipment Datasheet - Refrig Area Oily Wastewater Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5614 | Mechanical Equipment Datasheet - Furnace Area Oily Wastewater Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5616 | Mechanical Equipment Datasheet - Olefins Stormwater Sump Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5621 | Mechanical Equipment Datasheet - Olefins Holding Basin Skimmed Oil Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -00742; R1 IFF: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-04-10
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5622 | Mechanical Equipment Datasheet - Olefins Holding Basin Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-04-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-06-18
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5623 | Mechanical Equipment Datasheet - Gate House Septic Tank Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-13
[6 empty] | Issue Actual | R1 IFD: 2019-02-13; R1 IFF: 2019-04-16
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -00847; R1 IFF: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | R1 IFD: 2019-03-11; R1 IFF: 2019-06-17
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5624 | Mechanical Equipment Datasheet - West Gate House Septic Tank Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-13
[6 empty] | Issue Actual | R1 IFD: 2019-02-13; R1 IFF: 2019-04-16
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -00847; R1 IFF: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | R1 IFD: 2019-03-11; R1 IFF: 2019-06-17
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5625 | Mechanical Equipment Datasheet - East Gate House Septic Tank Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-13
[6 empty] | Issue Actual | R1 IFD: 2019-02-13; R1 IFF: 2019-04-16
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -00847; R1 IFF: TPSK-LSPA1-T-ME-01363
[6 empty] | Return Date | R1 IFD: 2019-03-11; R1 IFF: 2019-06-17
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5635 | Mechanical Equipment Datasheet - CT Area Oily Wastewater Sump Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-07
[6 empty] | Issue Actual | R1 IFD: 2019-02-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00817
[6 empty] | Return Date | R1 IFD: 2019-03-15
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5636 | Mechanical Equipment Datasheet - CWWT Area Oily Wastewater Sump Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-07
[6 empty] | Issue Actual | R1 IFD: 2019-02-07
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00817
[6 empty] | Return Date | R1 IFD: 2019-03-15
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5637 | Mechanical Equipment Datasheet - HP Flare Area Oily Wastewater Sump Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-07
[6 empty] | Issue Actual | R1 IFD: 2019-02-07; R1 IFF: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00817; R1 IFF: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-04-10
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5638 | Mechanical Equipment Datasheet - HP Flare Area SW Sump Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-02-07
[6 empty] | Issue Actual | R1 IFD: 2019-02-07; R1 IFF: 2019-03-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00817; R1 IFF: TPSK-LSPA1-T-ME-01102
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-04-10
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5640 | Mechanical Equipment Data Sheet - Oily Wastewater Tank |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-26
[6 empty] | Revised Plan | R1 IFD: 2019-02-26
[6 empty] | Issue Actual | R1 IFD: 2019-02-26; R1 IFF: 2019-08-27
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00926; R1 IFF: TPSK-LSPA1-T-ME-02491
[6 empty] | Return Date | R1 IFD: 2019-03-15; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5641 | Mechanical Equipment Datasheet - Wastewater EQ Tank Skimmed Oil Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-10
[6 empty] | Issue Actual | R1 IFD: 2019-04-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01292
[6 empty] | Return Date | R1 IFD: 2019-05-16
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5643 | Mechanical Equipment Datasheet - Cooling Water BD Basin Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-05-07
[6 empty] | Issue Actual | R1 IFD: 2019-05-07; R1 IFF: 2019-07-31
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01582; R1 IFF: TPSK-LSPA1-T-ME-02295
[6 empty] | Return Date | R1 IFD: 2019-06-18; R1 IFF: 2019-08-26
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5644 | Mechanical Equipment Datasheet For Complex Waste Water Treatment Package |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00863; R1 IFI: TPSK-LSPA1-T-ME-02405
[6 empty] | Return Date | IFR: 2019-05-17; R1 IFI: 2019-09-03
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-5645 | Mechanical Equipment Datasheet - Oily Wastewater EQ Tank Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-04-10
[6 empty] | Issue Actual | R1 IFD: 2019-04-10
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-01292
[6 empty] | Return Date | R1 IFD: 2019-05-16
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5648 | Mechanical Equipment Datasheet - C3 Hydrog Area Oily Wastewater Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5649 | Mechanical Equipment Datasheet - Flare KO Drum Oily Wastewater Pump |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-05-07
[6 empty] | Revised Plan | R1 IFD: 2019-01-24
[6 empty] | Issue Actual | R1 IFD: 2019-01-24; R1 IFF: 2019-03-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00716; R1 IFF: TPSK-LSPA1-T-ME-00962
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-03-15
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5900 | Mechanical Equipment Data Sheet - Sulfuric Acid Tank |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-26
[6 empty] | Revised Plan | R1 IFD: 2019-01-29
[6 empty] | Issue Actual | R1 IFD: 2019-01-29; R1 IFF: 2019-08-21
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00754; R1 IFF: TPSK-LSPA1-T-ME-02455
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IFF: 2019-09-19
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5901 | Mechanical Equipment Datasheet - Sulfuric Acid Distribution Pumps |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ
Rev. | bar: R1 IFD
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-02-04
[6 empty] | Issue Actual | R1 IFD: 2019-02-04
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00787
[6 empty] | Return Date | R1 IFD: 2019-02-21
Owner Cmmt* | bar: R1 IFD
| ME | OL1-2M03-5902 | Mechanical Equipment Datasheet - Sulfuric Acid Metering Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-02-04
[6 empty] | Issue Actual | R1 IFD: 2019-02-04; R1 IFF: 2019-04-09; R1 IMP: 2019-04-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00787; R1 IFF: TPSK-LSPA1-T-ME-01279; R1 IMP: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD; R1 IMP
| ME | OL1-2M03-5903 | Mechanical Equipment Datasheet - Sulfuric Acid Distribution Pumps |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFQ
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-16
[6 empty] | Issue Actual | IFR: 2019-04-16; R1 IFI: 2019-05-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01363; R1 IFI: TPSK-LSPA1-T-ME-01710
[6 empty] | Return Date | IFR: 2019-06-17; R1 IFI: 2019-06-21
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-5905 | Mechanical Equipment Datasheet - CTU Sulfuric Acid Metering Pumps |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFQ
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-10
[6 empty] | Issue Actual | IFR: 2019-04-10; R1 IFI: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01292; R1 IFI: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date | R1 IFI: 2019-06-18
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2M03-5910 | MECHANICAL EQUIPMENT DATASHEET FOR OXYGEN SCAVENGER INJECTION PACKAGE TAG: 10-PK-5910 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5912 | MECHANICAL EQUIPMENT DATASHEET FOR NEUTRALIZATION AMINE INHIBITOR INJECTION PACKAGE TAG: 10-PK-5912 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5914 | MECHANICAL EQUIPMENT DATASHEET FOR PHOSPHATE INJECTION PACKAGE TAG: 10-PK-5914 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01490
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-5950 | Mechanical Equipment Data Sheet - Sodium Hypochlorite Tank |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFQ; R1 IFF: IFQ
Rev. | bar: R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-02-18; R1 IFI: 2019-02-26
[6 empty] | Revised Plan | R1 IFD: 2019-02-11
[6 empty] | Issue Actual | R1 IFD: 2019-02-11; R1 IFF: 2019-07-08
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME-00839; R1 IFF: TPSK-LSPA1-T-ME-02086
[6 empty] | Return Date | R1 IFD: 2019-02-28; R1 IFF: 2019-08-06
Owner Cmmt* | bar: R1 IFD to R1 IFF
| ME | OL1-2M03-5951 | Mechanical Equipment Datasheet - Sodium Hypochlorite Metering Pumps |  |  | Purpose** | IFR | IFD | IFQ | IFQ | IFQ
[6 empty] | Rev. | R1 IFD: A; R1 IFF: B; R1 IMP: C
[6 empty] | Issue Plan | IFR: 2018-12-27; R1 IFI: 2019-01-17
[6 empty] | Revised Plan | R1 IFD: 2019-01-28
[6 empty] | Issue Actual | R1 IFD: 2019-01-28; R1 IFF: 2019-04-09; R1 IMP: 2019-04-18
[6 empty] | Transmittal no. | R1 IFD: TPSK-LSPA1-T-ME -00742; R1 IFF: TPSK-LSPA1-T-ME-01279; R1 IMP: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date | R1 IFD: 2019-02-21; R1 IMP: 2019-06-18
Owner Cmmt* | bar: R1 IFD; R1 IMP
| ME | OL1-2M03-5955 | Mechanical Equipment Datasheet - CTU NaOCl Metering Pumps |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFQ
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-10
[6 empty] | Issue Actual | IFR: 2019-04-10; R1 IFI: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01292; R1 IFI: TPSK-LSPA1-T-ME-01390
[6 empty] | Return Date | R1 IFI: 2019-06-18
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2M03-6004 | Mechanical Equipment Datasheet For Cracked Gas Compressor Bridge Crane (10-EL-2300) |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-25; R1 IFI: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-02-25; R1 IFI: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00913; R1 IFI: TPSK-LSPA1-T-ME-02360
[6 empty] | Return Date | IFR: 2019-04-05; R1 IFI: 2019-08-21
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-6005 | Mechanical Equipment Datasheet For Ethylene And Propylene Compressor Bridge Crane (10-EL-2800) |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-25; R1 IFI: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-02-25; R1 IFI: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00913; R1 IFI: TPSK-LSPA1-T-ME-02360
[6 empty] | Return Date | IFR: 2019-04-05; R1 IFI: 2019-08-21
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M03-7000 | Mechanical Equipment Data Sheet 10-d-D-2415 CG Liquid Dryer Feed Coalescer |  | Class 2 | Purpose** | IFR: IFP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01682
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-7001 | Mechanical Equipment Data Sheet 10-D-765 C4-C5 Hydrog Coalescer Drum |  | Class 2 | Purpose** | IFR: IFP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01682
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| ME | OL1-2M03-7002 | Mechanical Equipment Data Sheet 10-D-2136 Process Water Feed Coalescer |  | Class 2 | Purpose** | IFR: IFP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01682
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
Category Code: M04 Mechanical design basic / philosophy / logic diagram
Category Code: M05 Mechanical calculation sheet / report
Category Code: M06 Mechanical equipment drawing
| ME | OL-2M06-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 3
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-12
[6 empty] | Issue Actual | IFR: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02629
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-1001 | USC 36M Recycle Furnace General Arrangement Cross Section Elevation |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1; R1 IMP: 2
[6 empty] | Issue Plan | IFR: 2019-01-08; R1 IFI: 2019-03-13; R1 IFD: 2019-10-14
[6 empty] | Revised Plan | IFR: 2018-11-16; R1 IFD: 2019-11-04; R1 IFF: 2019-04-16
[6 empty] | Issue Actual | IFR: 2018-11-16; R1 IFF: 2019-04-16; R1 IMP: 2019-06-26; R1 IMP: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00327; R1 IFF: TPSK-LSPA1-T-ME-01361; R1 IMP: TPSK-LSPA1-T-ME-01993; R1 IMP: TPSK-LSPA1-T-ME-02626
[6 empty] | Return Date | IFR: 2019-05-24; R1 IMP: 2019-08-05; R1 IMP: 2019-10-14
Owner Cmmt* | bar: IFR; R1 IMP to R1 IMP
| ME | OL1-2M06-1002 | USC 36M Recycle Furnace General Arrangement Longitudinal Elevation |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2019-01-08; R1 IFI: 2019-03-13; R1 IFD: 2019-10-14
[6 empty] | Revised Plan | IFR: 2018-11-16; R1 IFD: 2019-11-04; R1 IFF: 2019-04-16
[6 empty] | Issue Actual | IFR: 2018-11-16; R1 IFF: 2019-04-16; R1 IMP: 2019-06-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00327; R1 IFF: TPSK-LSPA1-T-ME-01361; R1 IMP: TPSK-LSPA1-T-ME-01993
[6 empty] | Return Date | IFR: 2019-05-24; R1 IMP: 2019-08-05
Owner Cmmt* | bar: IFR; R1 IMP
| ME | OL1-2M06-1004 | USC 36M Recycle Furnace General Arrangement Instrumentation |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1; R1 IMP: 2
[6 empty] | Issue Plan | IFR: 2019-01-08; R1 IFI: 2019-03-13; R1 IFD: 2019-10-14
[6 empty] | Revised Plan | IFR: 2019-01-31; R1 IFD: 2019-11-04; R1 IFF: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-01-31; R1 IFF: 2019-04-29; R1 IMP: 2019-06-26; R1 IMP: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00764; R1 IFF: TPSK-LSPA1-T-ME-01500; R1 IMP: TPSK-LSPA1-T-ME-01993; R1 IMP: TPSK-LSPA1-T-ME-02626
[6 empty] | Return Date | IFR: 2019-02-21; R1 IFF: 2019-09-03; R1 IMP: 2019-08-05; R1 IMP: 2019-10-14
Owner Cmmt* | bar: IFR; R1 IFF to R1 IMP
| ME | OL1-2M06-1005 | USC 36M Recycle Furnace General Arrangement Instrumentation Sections |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP; R1 IFF: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1; R1 IFF: 2
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-31; R1 IFI: 2019-04-26
[6 empty] | Issue Actual | IFR: 2019-01-31; R1 IFI: 2019-04-26; R1 IFD: 2019-06-26; R1 IFF: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00764; R1 IFI: TPSK-LSPA1-T-ME-01500; R1 IFD: TPSK-LSPA1-T-ME-01993; R1 IFF: TPSK-LSPA1-T-ME-02629
[6 empty] | Return Date | IFR: 2019-02-21; R1 IFD: 2019-08-05; R1 IFF: 2019-10-14
Owner Cmmt* | bar: IFR; R1 IFD to R1 IFF
| ME | OL1-2M06-1101 | USC 36M Recycle Furnace Refractory and Insulation Radiant Section Details |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2019-01-23; R1 IFI: 2019-02-20; R1 IFD: 2019-02-20
[6 empty] | Revised Plan | IFR: 2019-03-15; R1 IFF: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-15; R1 IFF: 2019-05-14; R1 IMP: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R1 IFF: TPSK-LSPA1-T-ME-01653; R1 IMP: TPSK-LSPA1-T-ME-01876
[6 empty] | Return Date | IFR: 2019-04-02; R1 IFF: 2019-06-13; R1 IMP: 2019-07-08
Owner Cmmt* | bar: IFR; R1 IFF to R1 IMP
| ME | OL1-2M06-1102 | USC 36M Recycle Furnace Refractory and Insulation Convection Section Details |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2019-01-23; R1 IFI: 2019-02-20; R1 IFD: 2019-02-20
[6 empty] | Revised Plan | IFR: 2019-03-15; R1 IFF: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-15; R1 IFF: 2019-05-14; R1 IMP: 2019-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R1 IFF: TPSK-LSPA1-T-ME-01653; R1 IMP: TPSK-LSPA1-T-ME-02700
[6 empty] | Return Date | IFR: 2019-04-02; R1 IFF: 2019-06-13
Owner Cmmt* | bar: IFR; R1 IFF
| ME | OL1-2M06-1103 | USC 36M Recycle Furnace Refractory and Insulation Installation Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-1104 | USC 36M Recycle Furnace Refractory and Insulation Anchor Details |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2019-01-23; R1 IFI: 2019-02-20; R1 IFD: 2019-02-20
[6 empty] | Revised Plan | IFR: 2019-03-15; R1 IFF: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-15; R1 IFF: 2019-05-14; R1 IMP: 2019-09-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R1 IFF: TPSK-LSPA1-T-ME-01653; R1 IMP: TPSK-LSPA1-T-ME-02607
[6 empty] | Return Date | IFR: 2019-04-02; R1 IFF: 2019-06-13; R1 IMP: 2019-10-14
Owner Cmmt* | bar: IFR; R1 IFF to R1 IMP
| ME | OL1-2M06-1105 | USC 36M Recycle Furnace Insulation Details at Radiant Floor Burners |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-1106 | USC 36M Recycle Furnace Peep Door Insert Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-1107 | USC 36M Recycle Furnace USX Assembly Insulation Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-01-28; R1 IFI: 2019-02-25
[6 empty] | Revised Plan | IFR: 2019-05-09
[6 empty] | Issue Actual | IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01619
[6 empty] | Return Date | IFR: 2019-05-31
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-1108 | USC 36M Recycle Furnace Decoke Nozzle Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-1109 | USC 36M Recycle Furnace Seal Boot Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFD: 2019-09-17
[6 empty] | Revised Plan | R1 IFI: 2019-04-17
[6 empty] | Issue Actual | R1 IFI: 2019-04-17
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-01368
Return Date
Owner Cmmt*
| ME | OL1-2M06-1110 | USC 36M FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1201 | USC 36M Recycle Furnace Radiant Coil Assembly and Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFF; R1 IFF: IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0
[6 empty] | Issue Plan | IFR: 2018-09-18; R1 IFI: 2018-12-07; R1 IFD: 2019-01-31
[6 empty] | Revised Plan | IFR: 2018-10-08; R1 IFF: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-10-08; R1 IFF: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; R1 IFF: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | IFR: 2019-02-21; R1 IFF: 2019-01-16
Owner Cmmt* | bar: IFR; R1 IFF
| ME | OL1-2M06-1202 | USC 36M Recycle Furnace Transfer Line And Clean Out Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2018-10-08
[6 empty] | Issue Actual | IFR: 2018-10-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062
[6 empty] | Return Date | IFR: 2019-02-21
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-1203 | USC 36M Recycle Furnace Radiant Coil Tubeskin Thermocouple Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFF; R1 IFF: IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0
[6 empty] | Issue Plan | IFR: 2018-09-18; R1 IFI: 2018-12-07; R1 IFD: 2019-01-31
[6 empty] | Revised Plan | IFR: 2018-10-08; R1 IFF: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-10-08; R1 IFF: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; R1 IFF: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | IFR: 2019-02-21; R1 IFF: 2019-01-16
Owner Cmmt* | bar: IFR; R1 IFF
| ME | OL1-2M06-1204 | USC 36M Recycle Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1; R1 IMP: 2
[6 empty] | Issue Plan | IFR: 2018-10-16; R1 IFI: 2018-12-17; R1 IFD: 2019-03-20
[6 empty] | Revised Plan | IFR: 2018-10-17; R1 IFF: 2019-02-13
[6 empty] | Issue Actual | IFR: 2018-10-17; R1 IFF: 2019-02-13; R1 IMP: 2019-04-16; R1 IMP: 2019-05-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00182; R1 IFF: TPSK-LSPA1-T-ME-00848; R1 IMP: TPSK-LSPA1-T-ME-01356; R1 IMP: TPSK-LSPA1-T-ME-01754
[6 empty] | Return Date | R1 IFF: 2019-03-07; R1 IMP: 2019-05-24; R1 IMP: 2019-06-21
Owner Cmmt* | bar: R1 IFF to R1 IMP
| ME | OL1-2M06-1206 | USC 36M CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-01-31
[6 empty] | Revised Plan | IFR: 2019-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-1301 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-12-17; R1 IFD: 2019-01-28
[6 empty] | Revised Plan | R1 IFI: 2018-11-07
[6 empty] | Issue Actual | R1 IFI: 2018-11-07
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00286
Return Date
Owner Cmmt*
| ME | OL1-2M06-1302 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-12-17; R1 IFD: 2019-01-28
[6 empty] | Revised Plan | R1 IFI: 2018-11-07
[6 empty] | Issue Actual | R1 IFI: 2018-11-07
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00286
Return Date
Owner Cmmt*
| ME | OL1-2M06-1303 | USC 36M Recycle Furnace Convection Cast Intermediate Tube Support Location |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2018-12-17; R1 IFD: 2019-01-28
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-01290
[6 empty] | Return Date | R1 IFI: 2019-05-15
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2M06-2001 | USC 132U Cracking Furnace General Arrangement Cross Section Elevation |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1; R1 IMP: 2
[6 empty] | Issue Plan | IFR: 2019-01-08; R1 IFI: 2019-03-13; R1 IFD: 2019-10-14
[6 empty] | Revised Plan | IFR: 2018-11-16; R1 IFD: 2019-11-04; R1 IFF: 2019-04-17
[6 empty] | Issue Actual | IFR: 2018-11-16; R1 IFF: 2019-04-17; R1 IMP: 2019-06-26; R1 IMP: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00328; R1 IFF: TPSK-LSPA1-T-ME-01369; R1 IMP: TPSK-LSPA1-T-ME-01993; R1 IMP: TPSK-LSPA1-T-ME-02629
[6 empty] | Return Date | R1 IMP: 2019-08-05; R1 IMP: 2019-10-14
Owner Cmmt* | bar: R1 IMP to R1 IMP
| ME | OL1-2M06-2002 | USC 132U Cracking Furnace General Arrangement Longitudinal Elevation |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2019-01-08; R1 IFI: 2019-03-13; R1 IFD: 2019-10-14
[6 empty] | Revised Plan | IFR: 2018-11-16; R1 IFD: 2019-11-04; R1 IFF: 2019-04-17
[6 empty] | Issue Actual | IFR: 2018-11-16; R1 IFF: 2019-04-17; R1 IMP: 2019-06-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00328; R1 IFF: TPSK-LSPA1-T-ME-01369; R1 IMP: TPSK-LSPA1-T-ME-01993
[6 empty] | Return Date | R1 IMP: 2019-08-05
Owner Cmmt* | bar: R1 IMP
| ME | OL1-2M06-2004 | USC 132U Cracking Furnace General Arrangement Instrumentation |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1; R1 IMP: 2
[6 empty] | Issue Plan | IFR: 2019-01-08; R1 IFI: 2019-03-13; R1 IFD: 2019-10-14
[6 empty] | Revised Plan | IFR: 2019-01-31; R1 IFD: 2019-11-04; R1 IFF: 2019-04-26
[6 empty] | Issue Actual | IFR: 2019-01-31; R1 IFF: 2019-04-26; R1 IMP: 2019-06-26; R1 IMP: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00766; R1 IFF: TPSK-LSPA1-T-ME-01500; R1 IMP: TPSK-LSPA1-T-ME-01993; R1 IMP: TPSK-LSPA1-T-ME-02626
[6 empty] | Return Date | IFR: 2019-02-21; R1 IMP: 2019-08-05; R1 IMP: 2019-10-14
Owner Cmmt* | bar: IFR; R1 IMP to R1 IMP
| ME | OL1-2M06-2005 | USC 132U Cracking Furnace Dilution Mixing Tee Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2018-12-21; R1 IFI: 2019-01-23
[6 empty] | Revised Plan | IFR: 2019-01-31
[6 empty] | Issue Actual | IFR: 2019-01-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00768
[6 empty] | Return Date | IFR: 2019-02-21
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-2019 | USC 132U Cracking Furnace Seal Boot Details |  | Class 2 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-17
[6 empty] | Issue Actual | IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01368
Return Date
Owner Cmmt*
| ME | OL1-2M06-2101 | USC 132U Cracking Furnace Refractory and Insulation Radiant Section Details |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2019-01-23; R1 IFI: 2019-02-20; R1 IFD: 2019-02-20
[6 empty] | Revised Plan | IFR: 2019-03-15; R1 IFF: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-15; R1 IFF: 2019-05-14; R1 IMP: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R1 IFF: TPSK-LSPA1-T-ME-01653; R1 IMP: TPSK-LSPA1-T-ME-01876
[6 empty] | Return Date | IFR: 2019-04-02; R1 IFF: 2019-06-13; R1 IMP: 2019-07-08
Owner Cmmt* | bar: IFR; R1 IFF to R1 IMP
| ME | OL1-2M06-2102 | USC 132U Cracking Furnace Refractory and Insulation Convection Section Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFF; R1 IFF: IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0
[6 empty] | Issue Plan | IFR: 2019-01-23; R1 IFI: 2019-02-20; R1 IFD: 2019-02-20
[6 empty] | Revised Plan | IFR: 2019-03-15; R1 IFF: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-15; R1 IFF: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R1 IFF: TPSK-LSPA1-T-ME-01653
[6 empty] | Return Date | IFR: 2019-04-02; R1 IFF: 2019-06-13
Owner Cmmt* | bar: IFR; R1 IFF
| ME | OL1-2M06-2103 | USC 132U Cracking Furnace Refractory and Insulation Installation Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-2104 | USC 132U Cracking Furnace Refractory and Insulation Anchor Details |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2019-01-23; R1 IFI: 2019-02-20; R1 IFD: 2019-02-20
[6 empty] | Revised Plan | IFR: 2019-03-15; R1 IFF: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-03-15; R1 IFF: 2019-05-14; R1 IMP: 2019-09-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065; R1 IFF: TPSK-LSPA1-T-ME-01653; R1 IMP: TPSK-LSPA1-T-ME-02607
[6 empty] | Return Date | IFR: 2019-04-02; R1 IFF: 2019-06-13; R1 IMP: 2019-10-14
Owner Cmmt* | bar: IFR; R1 IFF to R1 IMP
| ME | OL1-2M06-2105 | USC 132U Cracking Furnace Insulation Details at Radiant Floor Burners |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-2106 | USC 132U Cracking Furnace Peep Door Insert Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-2107 | USC 132U Cracking Furnace SLE Assembly Insulation Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-01-28; R1 IFI: 2019-02-25
[6 empty] | Revised Plan | IFR: 2019-05-09
[6 empty] | Issue Actual | IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01619
[6 empty] | Return Date | IFR: 2019-05-31
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-2108 | USC 132U Cracking Furnace Decoke Nozzle Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01065
[6 empty] | Return Date | IFR: 2019-04-02
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-2109 | USC 132U FURNACE SEAL BOOT DETAILS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2110 | USC 132U FURNACE INSULATION DETAILS AT RADIANT FLOOR BURNERS |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-17
[6 empty] | Revised Plan | IFR: 2019-10-16
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2201 | USC 132U Cracking Furnace Radiant Coil Assembly and Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFF; R1 IFF: IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0
[6 empty] | Issue Plan | IFR: 2018-09-18; R1 IFI: 2018-12-07; R1 IFD: 2019-01-31
[6 empty] | Revised Plan | IFR: 2018-10-08; R1 IFF: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-10-08; R1 IFF: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; R1 IFF: TPSK-LSPA1-T-ME-00486
[6 empty] | Return Date | IFR: 2019-02-21; R1 IFF: 2019-01-16
Owner Cmmt* | bar: IFR; R1 IFF
| ME | OL1-2M06-2202 | USC 132U Cracking Furnace Transfer Lines and Clean-Out Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-01; R1 IFI: 2019-09-17
[6 empty] | Revised Plan | IFR: 2018-10-08
[6 empty] | Issue Actual | IFR: 2018-10-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062
[6 empty] | Return Date | IFR: 2019-02-21
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-2203 | USC 132U Cracking Furnace Radiant Coil Tubeskin Thermocouple Details |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP
[6 empty] | Rev. | IFR: A; R1 IFF: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2018-09-18; R1 IFI: 2018-12-07; R1 IFD: 2019-01-31
[6 empty] | Revised Plan | IFR: 2018-10-08; R1 IFF: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-10-08; R1 IFF: 2018-12-13; R1 IMP: 2019-09-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00062; R1 IFF: TPSK-LSPA1-T-ME-00486; R1 IMP: TPSK-LSPA1-T-ME-02625
[6 empty] | Return Date | IFR: 2019-02-21; R1 IFF: 2019-01-16; R1 IMP: 2019-10-14
Owner Cmmt* | bar: IFR; R1 IFF to R1 IMP
| ME | OL1-2M06-2204 | USC 132U Cracking Furnace Fabrication Assembly of Convection Coils Finned Tubes and Bill of Material |  |  | Purpose** | IFR | IFD | IFF | IMP | IMP | IMP | IMP
[6 empty] | Rev. | A |  |  | 0 | 1 | 2 | 3
[6 empty] | Issue Plan | IFR: 2018-10-16; R1 IFI: 2018-12-17; R1 IFD: 2019-03-20
[6 empty] | Revised Plan | IFR: 2018-10-17; R1 IFF: 2019-02-13
[6 empty] | Issue Actual | 2018-10-17 |  |  | 2019-02-13 | 2019-04-16 | 2019-05-29 | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00182 |  |  | TPSK-LSPA1-T-ME-00848 | TPSK-LSPA1-T-ME-01356 | TPSK-LSPA1-T-ME-01754 | TPSK-LSPA1-T-ME-02625
[6 empty] | Return Date | R1 IFF: 2019-03-07; R1 IMP: 2019-05-24; R1 IMP: 2019-06-21; R1 IMP: 2019-10-14
Owner Cmmt* | bar: R1 IFF to R1 IMP
| ME | OL1-2M06-2206 | USC 132U CRACKING FURNACE RADIANT COIL ASSEMBLY KEY PLAN |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-01-31
[6 empty] | Revised Plan | IFR: 2019-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2M06-2207 | USC 132U Cracking Furnace Dilution Mixing Tee Details |  | Class 2 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-23
[6 empty] | Issue Actual | IFR: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00669
Return Date
Owner Cmmt*
| ME | OL1-2M06-2207- | USC 132U Cracking Furnace Dilution Mixing Tee Details |  | Class 2 | Purpose** | IFR: IMP
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01509
[6 empty] | Return Date | IFR: 2019-05-31
Owner Cmmt* | bar: IFR
| ME | OL1-2M06-2301 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-12-17; R1 IFD: 2019-01-28
[6 empty] | Revised Plan | R1 IFI: 2018-11-08
[6 empty] | Issue Actual | R1 IFI: 2018-11-08
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00289
Return Date
Owner Cmmt*
| ME | OL1-2M06-2302 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-12-17; R1 IFD: 2019-01-28
[6 empty] | Revised Plan | R1 IFI: 2018-11-08
[6 empty] | Issue Actual | R1 IFI: 2018-11-08
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00289
Return Date
Owner Cmmt*
| ME | OL1-2M06-2303 | USC 132U Cracking Furnace Convection Cast Intermediate Tube Support Location |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2018-12-17; R1 IFD: 2019-01-28
[6 empty] | Revised Plan | R1 IFI: 2019-04-10
[6 empty] | Issue Actual | R1 IFI: 2019-04-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-01291
[6 empty] | Return Date | R1 IFI: 2019-05-15
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2M06-2554 | USC 132U Cracking Furnace Peep Door Details |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFC
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-29; R1 IFD: 2019-03-27
[6 empty] | Revised Plan | R1 IFI: 2018-12-04
[6 empty] | Issue Actual | R1 IFI: 2018-12-04
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00422
Return Date
Owner Cmmt*
Category Code: M07 Mechanical certification, inspection and test record
Category Code: M20 Static Equipment Datasheet
Category Code: M21 Rotating Machinery Datasheet
Category Code: M22 Package Unit-Datasheet
Category Code: M55 Request for Quotation (RFQ) for Mechanical work
| ME | OL1-2M55-0003 | Material Requisition for Cooling Water Pumps |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-15
[6 empty] | Issue Actual | IFR: 2018-11-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00319
[6 empty] | Return Date | IFR: 2018-12-10
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0008 | Material Requisition For Centrifugal Compressors Steam Turbine Driven - For Next Revision See Document OL1-2C13-401000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-08
[6 empty] | Issue Actual | IFR: 2018-10-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00136
[6 empty] | Return Date | IFR: 2018-10-26
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0012 | Material Requisition For Residue Gas Expander/Recompressor - For Next Revision See Document OL1-2C13-421000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-07
[6 empty] | Issue Actual | IFR: 2018-10-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00139
[6 empty] | Return Date | IFR: 2018-10-26
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0014 | Material Requisition For Integrally Geared Decoking Air Compressors |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-19
[6 empty] | Issue Actual | IFR: 2018-10-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00198
[6 empty] | Return Date | IFR: 2018-11-07
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0015 | Material Requisition For API Centrifugal Pumps - LLI |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-31
[6 empty] | Issue Actual | IFR: 2018-10-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00257
[6 empty] | Return Date | IFR: 2018-11-27
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0055 | Material Requisition For Trays For Columns Requisition For Inquiry - For Next Revision See Document OL1-2C13-242000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-09
[6 empty] | Issue Actual | IFR: 2018-11-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00300
[6 empty] | Return Date | IFR: 2018-12-06
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0058 | Material Requisition For Wieland Tubes (Solo Source) Requisition For Inquiry - For Next Revision See Document OL1-2C13-271000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-28
[6 empty] | Issue Actual | IFR: 2018-11-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00377
[6 empty] | Return Date | IFR: 2019-02-07
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0064 | Material Requisition For Plate And Frame Heat Exchangers Requisition For Inquiry - For next Rev. see Doc. Client Ref. OL1-2C13-142000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-04
[6 empty] | Issue Actual | IFR: 2018-10-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00124
[6 empty] | Return Date | IFR: 2018-10-24
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0066 | Material Requisition For Cold Box And Core Exchangers Requisition For Inquiry |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFQ
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-04
[6 empty] | Issue Actual | IFR: 2018-10-04; R1 IFI: 2018-10-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00125; R1 IFI: TPSK-LSPA1-T-ME-00153
[6 empty] | Return Date | IFR: 2018-10-24; R1 IFI: 2018-11-02
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M55-0075 | Material Requisition for High Efficiency Internals for Columns - For next rev see OL1-2C13-245000 |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IMP
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-07; R1 IFI: 2018-11-14
[6 empty] | Issue Actual | IFR: 2018-11-07; R1 IFI: 2018-11-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00278; R1 IFI: TPSK-LSPA1-T-ME-00314
[6 empty] | Return Date | IFR: 2018-11-29; R1 IFI: 2019-02-08
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2M55-0103 | Material Requisition for Wet Air Oxidation Package - For Next Revision See Document OL1-2C13-704000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-27
[6 empty] | Issue Actual | IFR: 2018-11-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00367
[6 empty] | Return Date | IFR: 2019-02-07
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0104 | Material Requisition for Cooling Tower - For Next Revision See Document OL1-2C13-311000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-06
[6 empty] | Issue Actual | IFR: 2018-11-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00276
[6 empty] | Return Date | IFR: 2019-02-15
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0108 | Material Requisition for Deareator - For next Rev. see Doc. Client Ref. OL1-2C13-120000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-06
[6 empty] | Issue Actual | IFR: 2018-11-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00270
[6 empty] | Return Date | IFR: 2018-11-29
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0109 | Material Requisition for Side Stream Filter Package - For Next Revision See Document OL1-2C13-706000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-31
[6 empty] | Issue Actual | IFR: 2018-10-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00248
[6 empty] | Return Date | IFR: 2018-11-27
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-0114 | Material Requisition for Hydrogen Production Unit - For Next Revision See Document OL1-2C13-705000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-06
[6 empty] | Issue Actual | IFR: 2018-11-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00271
[6 empty] | Return Date | IFR: 2019-02-07
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-2001 | Material Requisition for Convection Tubes - For next Rev. see Doc. Client Ref. OL1-2C13-303000 |  | Class 2 | Purpose** | IFR: IFP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-10
[6 empty] | Issue Actual | IFR: 2018-12-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00450
Return Date
Owner Cmmt*
| ME | OL1-2M55-2002 | Material Requisition for Furnace Convection Fittings |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-22; R1 IFI: 2019-01-07
[6 empty] | Issue Actual | IFR: 2018-10-22; R1 IFI: 2019-01-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00207; R1 IFI: TPSK-LSPA1-T-ME-00592
Return Date
Owner Cmmt*
| ME | OL1-2M55-2003 | Material Requisition for Quench Exchangers |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-26; R1 IFI: 2018-12-10
[6 empty] | Issue Actual | IFR: 2018-10-26; R1 IFI: 2018-12-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00233; R1 IFI: TPSK-LSPA1-T-ME-00466
Return Date
Owner Cmmt*
| ME | OL1-2M55-2004 | Material Requisition for Radiant Coil Assemblies |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-18; R1 IFI: 2018-12-14
[6 empty] | Issue Actual | IFR: 2018-10-18; R1 IFI: 2018-12-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00063; R1 IFI: TPSK-LSPA1-T-ME-00499
Return Date
Owner Cmmt*
| ME | OL1-2M55-2005 | Material Requisition for Furnace ID Fans - For next Rev. see Doc. Client Ref. OL1-2C13-301000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-05
[6 empty] | Issue Actual | IFR: 2018-11-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00269
Return Date
Owner Cmmt*
| ME | OL1-2M55-2006 | Material Requisition for Furnace Burners - For next Rev. see Doc. Client Ref. OL1-2C13-306000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-13
[6 empty] | Issue Actual | IFR: 2018-11-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00313
Return Date
Owner Cmmt*
| ME | OL1-2M55-2007 | Material Requisition for Cast Intermediate Tube Supports - For Next Revision see Doc. n. OL1-2C13-302000 |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-16; R1 IFI: 2018-12-20
[6 empty] | Issue Actual | IFR: 2018-11-16; R1 IFI: 2018-12-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00329; R1 IFI: TPSK-LSPA1-T-ME-00542
[6 empty] | Return Date | IFR: 2018-12-10
Owner Cmmt* | bar: IFR
| ME | OL1-2M55-2008 | Material Requisition for Peep Doors - For next Rev. see Doc. Client Ref. OL1-2C13-284000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-14
[6 empty] | Issue Actual | IFR: 2018-12-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00502
Return Date
Owner Cmmt*
| ME | OL1-2M55-2010 | Material Requisition for MOVs - For next Rev. see Doc. Client Ref. OL1-2C13-285000 |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-18
[6 empty] | Issue Actual | IFR: 2018-12-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00534
Return Date
Owner Cmmt*
| ME | OL1-2M55-2018 | Material Requisition for Furnace Steam Drums |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-01; R1 IFI: 2018-12-17
[6 empty] | Issue Actual | IFR: 2018-11-01; R1 IFI: 2018-12-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00263; R1 IFI: TPSK-LSPA1-T-ME-00518
Return Date
Owner Cmmt*
| ME | OL1-4M55-2001 | Material Requisition for Convection Tubes |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-13
[6 empty] | Issue Actual | IFR: 2018-09-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00044
Return Date
Owner Cmmt*
Category Code: M71 Appraisal Report for Consultancy Service
Category Code: M72 Appraisal Report for EPC Contractor Work
Category Code: M73 Appraisal Report for Vendor/Supplier
Category Code: M90 Vendor Document/drawings
Category Code: M91 Index/List
| ME | OL1-2M91-0001 | Item Index - Excluding Furnaces Island - Area 1A |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IFR
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-18; R1 IFI: 2019-06-14; R1 IFD: 2019-09-27
[6 empty] | Issue Actual | IFR: 2019-03-18; R1 IFI: 2019-06-14; R1 IFD: 2019-09-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01080; R1 IFI: TPSK-LSPA1-T-ME-01887; R1 IFD: TPSK-LSPA1-T-ME-02708
[6 empty] | Return Date | IFR: 2019-04-05; R1 IFD: 2019-10-09
Owner Cmmt* | bar: IFR; R1 IFD
| ME | OL1-2M91-0002 | Item Index Furnace Island |  | Class 2 | Purpose** | IFR | IBD | IBD | IBD | IDD1
[6 empty] | Rev. | A | B | C | D | E
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-18; R1 IFI: 2019-05-31; R1 IMP: 2019-08-14
[6 empty] | Issue Actual | 2019-03-18 | 2019-05-31 | 2019-07-11 | 2019-07-23 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01080 | TPSK-LSPA1-T-ME-01766 | TPSK-LSPA1-T-ME-02122 | TPSK-LSPA1-T-ME-02226 | TPSK-LSPA1-T-ME-02411
[6 empty] | Return Date | IFR: 2019-04-05; R1 IFD: 2019-07-19; R1 IFF: 2019-08-06; R1 IMP: 2019-08-23
Owner Cmmt* | bar: IFR; R1 IFD to R1 IMP
| ME | OL1-2M91-1001 | Approved Vendor List for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-23
[6 empty] | Issue Actual | IFR: 2018-10-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00211
Return Date
Owner Cmmt*
Category Code: M92 Procedures & Standards
| ME | OL1-2M92-0001 | Technical Specification For Mechanical Erection |  | Class 2 | Purpose** | IFR: IFQ; R1 IFI: IFP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-27; R1 IFI: 2019-10-15
[6 empty] | Issue Actual | IFR: 2019-09-27; R1 IFI: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02706; R1 IFI: TPSK-LSPA1-T-ME-02819
[6 empty] | Return Date | IFR: 2019-10-09
Owner Cmmt* | bar: IFR
| ME | OL1-2M92-0002 | Special Technical Specification For Furnace Island Erection |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-24
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-02247
[6 empty] | Return Date | IFR: 2019-08-23
Owner Cmmt* | bar: IFR
| ME | OL1-2M92-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces - Ex Doc. Client Ref. OL1-4M92-2001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFQ; R1 IFD: IFP; R1 IFF: IMP
[6 empty] | Rev. | R1 IFF: 0
[6 empty] | Issue Plan | IFR: 2018-10-26; R1 IFI: 2018-10-26; R1 IFD: 2019-01-07
[6 empty] | Revised Plan | R1 IFF: 2018-12-11
[6 empty] | Issue Actual | R1 IFF: 2018-12-11
[6 empty] | Transmittal no. | R1 IFF: TPSK-LSPA1-T-ME-00470
Return Date
Owner Cmmt*
| ME | OL1-2M92-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces - For Next Revision See Document OL1-2M92-2002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFQ; R1 IFD: IFP; R1 IFF: IMP
[6 empty] | Rev. | R1 IFF: 0
[6 empty] | Issue Plan | IFR: 2018-10-26; R1 IFI: 2018-10-26; R1 IFD: 2019-01-07
[6 empty] | Revised Plan | R1 IFF: 2018-12-11
[6 empty] | Issue Actual | R1 IFF: 2018-12-11
[6 empty] | Transmittal no. | R1 IFF: TPSK-LSPA1-T-ME-00471
Return Date
Owner Cmmt*
| ME | OL1-2M92-2003 | Project Specification for Cast Intermediate Tube Supports |  |  | Purpose** | IFR | IFI | IFQ | IFP | IMP
[6 empty] | Rev. | R1 IFI: 0; R1 IMP: 1
[6 empty] | Issue Plan | IFR: 2018-10-26; R1 IFD: 2018-10-26; R1 IFF: 2019-01-07
[6 empty] | Revised Plan | R1 IFI: 2018-10-26; R1 IMP: 2018-12-17
[6 empty] | Issue Actual | R1 IFI: 2018-10-26; R1 IMP: 2018-12-17
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00232; R1 IMP: TPSK-LSPA1-T-ME-00517
Return Date
Owner Cmmt*
| ME | OL1-2M92-2004 | Project Specification for Fabrication of Convection Coil for Cracking Furnaces |  |  | Purpose** | IFR | IFQ | IFR | IFP | IMP
[6 empty] | Rev. | IFR: A; R1 IFD: A; R1 IMP: 0
[6 empty] | Issue Plan | IFR: 2018-09-07; R1 IFI: 2018-09-19; R1 IFD: 2018-09-07; R1 IFF: 2018-12-13
[6 empty] | Revised Plan | IFR: 2019-02-12; R1 IFD: 2019-02-12; R1 IMP: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-02-12; R1 IFD: 2019-02-12; R1 IMP: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00842; R1 IFD: TPSK-LSPA1-T-ME-00842; R1 IMP: TPSK-LSPA1-T-ME -01640
[6 empty] | Return Date | IFR: 2019-03-07; R1 IFD: 2019-03-07
Owner Cmmt* | bar: IFR; R1 IFD
| ME | OL1-2M92-2005 | Project Specification for Supply and Installation of Ceramics Fiber Blanket and Ceramics Fiber Modules |  |  | Purpose** | IFR | IFQ | IFR | IFP | IMP
[6 empty] | Rev. | IFR: A; R1 IFD: A; R1 IMP: 0
[6 empty] | Issue Plan | IFR: 2019-01-31; R1 IFI: 2019-02-07; R1 IFD: 2019-01-31; R1 IFF: 2019-04-09
[6 empty] | Revised Plan | IFR: 2019-02-12; R1 IFD: 2019-02-12; R1 IMP: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-02-12; R1 IFD: 2019-02-12; R1 IMP: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00842; R1 IFD: TPSK-LSPA1-T-ME-00842; R1 IMP: TPSK-LSPA1-T-ME -01640
[6 empty] | Return Date | IFR: 2019-03-07; R1 IFD: 2019-03-07
Owner Cmmt* | bar: IFR; R1 IFD
| ME | OL1-2M92-2006 | Project Specification for Supply and Installation of Refractory Insulation and Cracking Furnaces |  |  | Purpose** | IFR | IFQ | IFR | IFP | IMP
[6 empty] | Rev. | IFR: A; R1 IFD: A; R1 IMP: 0
[6 empty] | Issue Plan | IFR: 2019-01-31; R1 IFI: 2019-02-07; R1 IFD: 2019-01-31; R1 IFF: 2019-04-09
[6 empty] | Revised Plan | IFR: 2019-02-12; R1 IFD: 2019-02-12; R1 IMP: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-02-12; R1 IFD: 2019-02-12; R1 IMP: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00842; R1 IFD: TPSK-LSPA1-T-ME-00842; R1 IMP: TPSK-LSPA1-T-ME -01640
[6 empty] | Return Date | IFR: 2019-03-07; R1 IFD: 2019-03-07
Owner Cmmt* | bar: IFR; R1 IFD
| ME | OL1-2M92-2007 | Project Specification For SLE and USX Exchangers - Ex Doc. Client Ref. OL1-4M92-2007 |  |  | Purpose** | IFR: IFR; R1 IFI: IFQ; R1 IFD: IFP; R1 IFF: IMP
[6 empty] | Rev. | R1 IFF: 0
[6 empty] | Issue Plan | IFR: 2018-09-20; R1 IFI: 2018-10-26; R1 IFD: 2018-12-10
[6 empty] | Revised Plan | R1 IFF: 2018-12-05
[6 empty] | Issue Actual | R1 IFF: 2018-12-05
[6 empty] | Transmittal no. | R1 IFF: TPSK-LSPA1-T-ME-00427
Return Date
Owner Cmmt*
| ME | OL1-2M92-2008 | Project Specification For Transfer Line Exchangers - For next Rev. see Doc. Client Ref. OL1-2M92-2008 |  |  | Purpose** | IFR: IFR; R1 IFI: IFQ; R1 IFD: IFP; R1 IFF: IMP
[6 empty] | Rev. | R1 IFF: 0
[6 empty] | Issue Plan | IFR: 2018-09-20; R1 IFI: 2018-10-26; R1 IFD: 2018-12-10
[6 empty] | Revised Plan | R1 IFF: 2018-12-05
[6 empty] | Issue Actual | R1 IFF: 2018-12-05
[6 empty] | Transmittal no. | R1 IFF: TPSK-LSPA1-T-ME-00428
Return Date
Owner Cmmt*
| ME | OL1-2M92-2009 | Project Specification for Furnace Burners |  |  | Purpose** | IFR | IFQ | IFR | IFP | IMP
[6 empty] | Rev. | IFR: A; R1 IFD: A; R1 IMP: 0
[6 empty] | Issue Plan | IFR: 2018-10-25; R1 IFI: 2018-10-25; R1 IFD: 2018-10-25; R1 IFF: 2019-01-23
[6 empty] | Revised Plan | IFR: 2018-10-25; R1 IFD: 2018-10-25; R1 IMP: 2019-01-22
[6 empty] | Issue Actual | IFR: 2018-10-25; R1 IFD: 2018-10-25; R1 IMP: 2019-01-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00231; R1 IFD: TPSK-LSPA1-T-PE-00231; R1 IMP: TPSK-LSPA1-T-ME-00698
[6 empty] | Return Date | IFR: 2018-11-14; R1 IFD: 2018-11-14; R1 IMP: 2019-02-14
Owner Cmmt* | bar: IFR; R1 IFD; R1 IMP
| ME | OL1-4M92-2001 | Project Specification for Centrifugally Cast Tubes for Radiant Coils and Transfer Lines in Cracking Furnaces - For next Rev. see Doc. Client Ref. OL1-2M92-2001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-11
[6 empty] | Issue Actual | IFR: 2018-09-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00037
[6 empty] | Return Date | IFR: 2018-09-25
Owner Cmmt* | bar: IFR
| ME | OL1-4M92-2002 | Project Specification for Statically Cast Fittings for Radiant Coils and Transfer Lines in Cracking Furnaces - For Next Revision See Document OL1-2M92-2002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-11
[6 empty] | Issue Actual | IFR: 2018-09-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00037
[6 empty] | Return Date | IFR: 2018-09-25
Owner Cmmt* | bar: IFR
| ME | OL1-4M92-2007 | Project Specification For SLE and USX Exchangers - For next Rev. see Doc. Client Ref. OL1-2M92-2007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-24
[6 empty] | Issue Actual | IFR: 2018-09-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00067
[6 empty] | Return Date | IFR: 2018-10-12
Owner Cmmt* | bar: IFR
| ME | OL1-4M92-2008 | Project Specification For Transfer Line Exchangers - For next Rev. see Doc. Client Ref. OL1-2M92-2008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-24
[6 empty] | Issue Actual | IFR: 2018-09-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00067
[6 empty] | Return Date | IFR: 2018-10-12
Owner Cmmt* | bar: IFR
Category Code: M93 Policy , Guidelines & Memo
Category Code: M94 Forms & Templates
Category Code: M95 Progress/Status Reports
Category Code: M96 Spare part list for construction/precommissioning/commissioning
Category Code: M97 Spare Part List for Maintenance During First Two Years Operation
Category Code: M98 Special tools books
Category Code: M99 Other
Category Code: O01 Precommissioning Plan and Schedule
Category Code: O02 Commissioning Plan and Schedule
Category Code: O03 Startup Plan and Schedule
Category Code: O04 Performance Test Plan and Schedule
Category Code: O05 Production Plan
Category Code: O06 Operating Manuals
| PE | OL1-2O06-0001 | CUO 107 - OPERATING MANUALS |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-12-15; R1 IFI: 2021-06-30
[6 empty] | Revised Plan | IFR: 2020-12-15; R1 IFI: 2021-06-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O07 Startup Lists
| PE | OL1-2O07-0002 | START-UP PACKAGE LIST |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-15; R1 IFI: 2019-12-15
[6 empty] | Revised Plan | IFR: 2019-11-15; R1 IFI: 2019-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0003 | PROJECT SYSTEM LIST |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-15; R1 IFI: 2020-10-01
[6 empty] | Revised Plan | IFR: 2020-09-15; R1 IFI: 2020-10-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0004 | SPECIAL ACTIVITIES DOSSIER |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-12-01; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-12-01; R1 IFI: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0005 | SYSTEM COMPONENT LIST WITH MARKED-UP DWGS |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-10-15; R1 IFI: 2021-02-01
[6 empty] | Revised Plan | IFR: 2020-10-15; R1 IFI: 2021-02-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O07-0007 | CUO 110 - OPERATING SPARE PARTS STATUS REPORT |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-12-31; R1 IFI: 2021-12-31
[6 empty] | Revised Plan | IFR: 2020-12-31; R1 IFI: 2021-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O08 Startup Philosophy
| PE | OL1-2O08-0001 | SYSTEMIZATION PHILOSOPHY |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-01; R1 IFI: 2019-12-01
[6 empty] | Revised Plan | IFR: 2019-11-01; R1 IFI: 2019-12-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O08-0002 | CUO 110 - MAINTENANCE PHILOSOPHY DURING INTERIM MAINTENANCE MANAGEMENT |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2021-10-30; R1 IFI: 2021-12-31
[6 empty] | Revised Plan | IFR: 2021-10-30; R1 IFI: 2021-12-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O09 Scope of Work
| PE | OL1-2O09-0002 | DEFINITION OF SCOPE OF WORK - TPIT - SPECIALIZED COMPANY |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-01-30
[6 empty] | Revised Plan | IFR: 2020-01-15; R1 IFI: 2020-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O10 Maintenance Manuals
| PE | OL1-2O10-0002 | CUO 110 - PLANT MAINTENANCE MANUAL - OFFSITES - S04 |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2021-09-16; R1 IFI: 2021-11-15
[6 empty] | Revised Plan | IFR: 2021-09-16; R1 IFI: 2021-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O10-0003 | CUO 110 - PLANT MAINTENANCE MANUAL - WASTE WATER TREATMENT - S05 |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2021-09-16; R1 IFI: 2021-11-15
[6 empty] | Revised Plan | IFR: 2021-09-16; R1 IFI: 2021-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O10-0004 | CUO 110 - PLANT MAINTENANCE MANUAL - FURNACES - S06 |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2021-09-16; R1 IFI: 2021-11-15
[6 empty] | Revised Plan | IFR: 2021-09-16; R1 IFI: 2021-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O10-0006 | CUO 110 - PLANT MAINTENANCE MANUAL - FRACTIONATION 3 & BUTADIENE EXTRACTION & AMINE TREATEMENT - S08 |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2021-09-16; R1 IFI: 2021-11-15
[6 empty] | Revised Plan | IFR: 2021-09-16; R1 IFI: 2021-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O11 Operating Condition Calculation
Category Code: O12 Product Quality Calculation
Category Code: O13 Training Schedule
Category Code: O20 Precommissioning Form and Checksheet
| PE | OL1-2O20-0001 | PRE-COMMISSIONING STATIC TEST QUALITY CONTROL PLAN - PIPING |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0002 | PRE-COMMISSIONING STATIC TEST QUALITY CONTROL PLAN - INSTRUMENTATION |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0003 | PRE-COMMISSIONING STATIC TEST QUALITY CONTROL PLAN - ELECTRICAL |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O20-0004 | PRE-COMMISSIONING STATIC TEST QUALITY CONTROL PLAN - MECHANICAL |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0005 | PRE-COMMISSIONING STATIC TEST QUALITY CONTROL PLAN - BUILDING |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0006 | PRE-COMMISSIONING STATIC TEST QUALITY CONTROL PLAN - UNDERGROUND |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0007 | PRE-COMMISSIONING STATIC TEST QUALITY CONTROL PLAN - TANKS |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0008 | PRE-COMMISSIONING DYNAMIC TEST QUALITY CONTROL PLAN - ELECTRICAL |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0009 | PRE-COMMISSIONING DYNAMIC TEST QUALITY CONTROL PLAN - INSTRUMENTATION |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0010 | PRE-COMMISSIONING DYNAMIC TEST QUALITY CONTROL PLAN - MECHANICAL |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0011 | PRE-COMMISSIONING DYNAMIC TEST QUALITY CONTROL PLAN - PIPING |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0012 | PRE-COMMISSIONING DYNAMIC TEST QUALITY CONTROL PLAN - BUILDING |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0013 | PRE-COMMISSIONING DYNAMIC TEST QUALITY CONTROL PLAN - UNDERGROUND |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
|  | OL1-2O20-0014 | PRE-COMMISSIONING DYNAMIC TEST QUALITY CONTROL PLAN - TANKS |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-08-01; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-06
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O21 Commissioning Form and Checksheet
Category Code: O22 Operation Form and Checksheet
Category Code: O23 Equipment Patrol Checksheet
Category Code: O51 Appraisal Report for Consultancy Service
Category Code: O52 Appraisal Report for EPC Contractor Work
Category Code: O53 Appraisal Report for Vendor/Supplier
Category Code: O60 Precommissioning Record and Report
Category Code: O61 Commissioning Record and Report
Category Code: O62 Startup, Shutdown and Emergency Shutdown Record and Report
Category Code: O63 Plant performance Test and record
Category Code: O64 Operation Record and Report Production Record,Report
Category Code: O65 Troubleshooting Record, Report
Category Code: O66 Modification Record,Report
Category Code: O67 List of set point and controller parameter
| PE | OL1-2O67-1101 | Alarm & Setpoint Summary 36M Furnace 10-H-1100 |  |  | Purpose** | IFR | IBD | IFD | IFD | IFC
Rev. | bar: IFR; R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-04; R1 IFI: 2019-06-13; R1 IFD: 2019-06-24; R1 IMP: 2019-10-28
[6 empty] | Revised Plan | IFR: 2019-06-11; R1 IFD: 2019-09-03; R1 IMP: 2019-10-28
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFD: 2019-09-03; R1 IFF: 2019-09-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01848; R1 IFD: TPSK-LSPA1-T-IE-02556; R1 IFF: TPSK-LSPA1-T-IE-02556
[6 empty] | Return Date | IFR: 2019-07-23; R1 IFD: 2019-10-17; R1 IFF: 2019-10-17
Owner Cmmt* | bar: IFR; R1 IFD to R1 IFF
| PE | OL1-2O67-1201 | Alarm & Setpoint Summary 132U Furnaces 10-H-1200 - 10-H-1600 |  |  | Purpose** | IFR | IBD | IFD | IFD | IFC
Rev. | bar: IFR; R1 IFD to R1 IFF
[6 empty] | Issue Plan | IFR: 2019-04-04; R1 IFI: 2019-06-13; R1 IFD: 2019-06-24; R1 IMP: 2019-10-28
[6 empty] | Revised Plan | IFR: 2019-06-11; R1 IFD: 2019-09-03; R1 IMP: 2019-10-28
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFD: 2019-09-03; R1 IFF: 2019-09-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01848; R1 IFD: TPSK-LSPA1-T-IE-02556; R1 IFF: TPSK-LSPA1-T-IE-02556
[6 empty] | Return Date | IFR: 2019-07-23; R1 IFD: 2019-10-17; R1 IFF: 2019-10-17
Owner Cmmt* | bar: IFR; R1 IFD to R1 IFF
Category Code: O70 Precommissioning Procedure
Category Code: O71 Commissioning Procedure
| PE | OL1-2O71-0001 | Job Specification For Water Flushing Of Piping & Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-08-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02426
[6 empty] | Return Date | IFR: 2019-09-27
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0002 | Job Specification For Air Blowing Of Piping & Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-08-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02426
Return Date
Owner Cmmt*
| PE | OL1-2O71-0003 | Job Specification For Drying Of Piping & Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-08-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02426
[6 empty] | Return Date | IFR: 2019-09-27
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0004 | Job Specification For Gross Leak Test Of Piping & Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-08-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02426
[6 empty] | Return Date | IFR: 2019-09-27
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0005 | Job Specification For Tightness Test Of Piping And Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-09-25; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02702
Return Date
Owner Cmmt*
| PE | OL1-2O71-0006 | Job Specification For Steam Blowing Of Piping & Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-08-22; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-22
Transmittal no.
[6 empty] | Return Date | IFR: 2019-09-30
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0007 | JOB SPECIFICATION FOR CHEMICAL CLEANING OF CS OF PIPING & EQUIPMENT |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0008 | JOB SPECIFICATION FOR CHEMICAL CLEANING OF SS OF PIPING & EQUIPMENT |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0009 | Job Specification For Nitrogen Purging Of Piping And Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-09-25; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02702
Return Date
Owner Cmmt*
| PE | OL1-2O71-0010 | JOB SPECIFICATION FOR HYDRO-JETTING OF PIPING & EQUIPMENT |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0011 | JOB SPECIFICATION FOR OIL FLUSHING |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0012 | Job Specification For Manual Cleaning Of Large Bore Piping |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-08-22; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-22
Transmittal no.
[6 empty] | Return Date | IFR: 2019-09-30
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0013 | Job Specification For Piping Inspection |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-08-22; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-22
Transmittal no.
[6 empty] | Return Date | IFR: 2019-09-30
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0014 | Job Specification For Relief Valves Management |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-08-15; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02426
[6 empty] | Return Date | IFR: 2019-09-27
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0015 | Job Specification For Deblocking And-Or Adjustment Of Piping And Equipment Special Supports |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-09-25; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02702
Return Date
Owner Cmmt*
| PE | OL1-2O71-0017 | Job Specification For Loop Check Execution |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-15; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-08-15; R1 IFI: 2020-06-01
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02426
[6 empty] | Return Date | IFR: 2019-09-27
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0018 | Job Specification For Loop Folder Management |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-15; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-08-15; R1 IFI: 2020-06-01
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02426
[6 empty] | Return Date | IFR: 2019-09-27
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0019 | Job Specification For Electrical Motor Solo Run |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2019-08-26; R1 IFI: 2020-06-15
[6 empty] | Issue Actual | IFR: 2019-08-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02482
[6 empty] | Return Date | IFR: 2019-09-30
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0020 | Job Specification For Electrical Substation Energization |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-01-15; R1 IFI: 2020-02-01
[6 empty] | Revised Plan | IFR: 2019-09-04; R1 IFI: 2020-02-01
[6 empty] | Issue Actual | IFR: 2019-09-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02563
[6 empty] | Return Date | IFR: 2019-10-03
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0021 | Job Specification For Machinery Alignment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-15; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-09-04; R1 IFI: 2019-10-16
[6 empty] | Issue Actual | IFR: 2019-09-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02562
[6 empty] | Return Date | IFR: 2019-09-30
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0022 | Job Specification For Equipment Inspection |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-15; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-09-04; R1 IFI: 2019-10-16
[6 empty] | Issue Actual | IFR: 2019-09-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02562
[6 empty] | Return Date | IFR: 2019-09-30
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0023 | Job Specification For Material Preservation During Construction Precommissioning Commissioning And Start Up |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-03-31; R1 IFI: 2019-05-31
[6 empty] | Revised Plan | IFR: 2019-03-19; R1 IFI: 2019-07-04
[6 empty] | Issue Actual | IFR: 2019-03-19; R1 IFI: 2019-07-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-01090; R1 IFI: TPSK-LSPA1-T-PE-02067
[6 empty] | Return Date | R1 IFI: 2019-08-02
Owner Cmmt* | bar: R1 IFI
| PE | OL1-2O71-0024 | SITE PCC&SU ORGANIZATION CHART |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-12-01; R1 IFI: 2020-12-15
[6 empty] | Revised Plan | IFR: 2020-12-01; R1 IFI: 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0025 | OVERALL PCC&SU EXECUTION PLAN |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-15; R1 IFI: 2020-01-15
[6 empty] | Revised Plan | IFR: 2019-11-15; R1 IFI: 2020-01-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0026 | RESPONSIBILITY MATRIX - DEFINIT.OF MECH.COMPLET./PRE-COMM./COMM./START UP/OPERAT.TPIT-OWNER |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-01; R1 IFI: 2019-11-15
[6 empty] | Revised Plan | IFR: 2019-10-16; R1 IFI: 2019-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0027 | HANDOVER PROCEDURE (INLUDING PUNCH LIST MANAGEMENT & INDEX DOSSIER) |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-01-30; R1 IFI: 2020-02-15
[6 empty] | Revised Plan | IFR: 2020-01-30; R1 IFI: 2020-02-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0029 | Job Specification For Functional Test Execution |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-09-15; R1 IFI: 2019-10-01
[6 empty] | Revised Plan | IFR: 2019-08-22; R1 IFI: 2020-06-01
[6 empty] | Issue Actual | IFR: 2019-08-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02464
[6 empty] | Return Date | IFR: 2019-09-30
Owner Cmmt* | bar: IFR
| PE | OL1-2O71-0030 | GOVERNANCE FOR INTEGRATED TEAM |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-01; R1 IFI: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-05-01; R1 IFI: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0032 | PLANT OPERATION PLAN |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2021-02-15; R1 IFI: 2021-03-15
[6 empty] | Revised Plan | IFR: 2021-02-15; R1 IFI: 2021-03-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0033 | CUO 107 - GUIDELINES FOR SUPERVISORY AND COMPREHENSIVE OPERATING MANUALS |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-01; R1 IFI: 2020-03-01
[6 empty] | Revised Plan | IFR: 2020-02-01; R1 IFI: 2020-03-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0034 | GUIDELINES FOR OTP PREPARATION |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R1 IFI: 2020-06-15
[6 empty] | Revised Plan | IFR: 2020-05-15; R1 IFI: 2020-06-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-0036 | CUO 107 - TRAINING PLAN |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-01; R1 IFI: 2020-06-01
[6 empty] | Revised Plan | IFR: 2020-03-01; R1 IFI: 2020-06-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-1001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-18
[6 empty] | Revised Plan | IFR: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-2001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-18
[6 empty] | Revised Plan | IFR: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-3001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-18
[6 empty] | Revised Plan | IFR: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-4001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-18
[6 empty] | Revised Plan | IFR: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-5001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-18
[6 empty] | Revised Plan | IFR: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O71-6001 | FURNACE PERFORMANCE TEST RUN PROCEDURE |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-18
[6 empty] | Revised Plan | IFR: 2019-12-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O72 Startup, Shutdown and Emergency Shutdown Procedure
Category Code: O73 Plant performance Test procedure
Category Code: O74 Tag-in Tag-out/Lock-out Tag-out Procedure
Category Code: O75 Operation Work instruction
| PE | OL1-2O75-0001 | OPERATIONAL TEST PROCEDURE (OTP) |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-01; R1 IFI: 2021-07-01
[6 empty] | Revised Plan | IFR: 2021-03-01; R1 IFI: 2021-07-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-1001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
[6 empty] | Revised Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-2001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
[6 empty] | Revised Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-3001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
[6 empty] | Revised Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-4001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
[6 empty] | Revised Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-5001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
[6 empty] | Revised Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| PE | OL1-2O75-6001 | SUPERVISORY OPERATING MANUAL FOR CRACKING FURNACE |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
[6 empty] | Revised Plan | IFR: 2019-11-11; R1 IFI: 2019-12-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: O80 Lab, Product QA and QC
| PE | OL1-2O80-1005 | Sampling and Analytical Manual |  |  | Purpose** | IFR: IFR; R1 IFI: IFI; R1 IFD: IFD; R1 IFF: IFF
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-07-19; R1 IFD: 2019-08-16; R1 IFF: 2020-05-30
[6 empty] | Revised Plan | R1 IFI: 2019-08-05; R1 IFF: 2020-05-30
[6 empty] | Issue Actual | R1 IFI: 2019-08-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-PE-02325
Return Date
Owner Cmmt*
Category Code: O91 Index/List
Category Code: O92 Procedures & Standards
| PE | OL1-2O92-0001 | Instructions To Supplier For Filling-Up Of Spare Parts And Interchangeability Record (SPIR Form) |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-21; R1 IFI: 2019-01-31
[6 empty] | Revised Plan | IFR: 2018-09-27; R1 IFI: 2019-03-04
[6 empty] | Issue Actual | IFR: 2018-09-27; R1 IFI: 2019-03-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00095; R1 IFI: TPSK-LSPA1-T-PE--00957
Return Date
Owner Cmmt*
Category Code: O93 Policy , Guidelines & Memo
Category Code: O94 Forms & Templates
Category Code: O95 Progress/Status Reports
Category Code: P03 Piping datasheet
| MP | OL1-2P03-1101 | Piping Specialty Item Datasheet - Trapped Key Locking Devices - 10-SP-11001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-22; R1 IFI: 2019-05-22
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01683
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1102 | Piping Specialty Item Datasheet - T- Type Filter - Crossover Line - 10-SP-11002 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02162
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1103 | Piping Specialty Item Datasheet - Exhaust Head - 10-SP-11003 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17; R1 IFI: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-05-17; R1 IFI: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01683; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-13; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1104 | Piping Specialty Item – Datasheet Vent Silencer – PSV-1142A-B Outlet SP-11004 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02162
[6 empty] | Return Date | IFR: 2019-06-03; R1 IFI: 2019-08-16
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1105 | Piping Specialty Item Datasheet - T-Type Filter - Fuel Gas Line - 10 SP-11005 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-03; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1107 | Piping Specialty Item Datasheet - Special Tee Fitting 30 inches - 10-SP-11007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1108 | Piping Specialty Item Datasheet - Special Tee Fitting 20 inches - 10-SP-11008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1109 | Piping Specialty Item Datasheet - Special Tee Fitting 16 inches - 10-SP-11009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1110 | Piping Specialty Item Datasheet - Special Tee Fitting 12 inches - 10-SP-11010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1111 | Piping Specialty Item Datasheet - Stop Check Valve - 10-SP-11011 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-03; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1112 | Piping Specialty Item – Datasheet Isokinetic Sampling Nozzle SP-11012 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; R1 IFI: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-04-24; R1 IFI: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-01457; R1 IFI: TPSK-LSPA1-T-MP-02160
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1113 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1144 Outlet - 10-SP-11013 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-03; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1114 | Piping Specialty Item Datasheet - Vent Silencer - Start up - 10-SP-11014 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-30
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-03; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1115 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge SRY-11002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1116 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge Steam SRY-11003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1151 | Piping Specialty Item Datasheet - 10-BDV-11001 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; R1 IFI: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-04-24; R1 IFI: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-01457; R1 IFI: TPSK-LSPA1-T-MP-02160
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-16
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1152 | Piping Specialty Item Datasheet - Flexible Hose - 10-FLX-11001 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17; R1 IFI: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-05-17; R1 IFI: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01683; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-13; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1153 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-11001 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01829; R1 IFI: TPSK-LSPA1-T-MP-02324
[6 empty] | Return Date | IFR: 2019-07-08; R1 IFI: 2019-09-19
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1154 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-11002 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01829; R1 IFI: TPSK-LSPA1-T-MP-02324
[6 empty] | Return Date | IFR: 2019-07-15; R1 IFI: 2019-09-19
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1201 | Piping Specialty Item Datasheet - Trapped Key Locking Devices - 10-SP-12001-16001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-22; R1 IFI: 2019-05-22
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01683
[6 empty] | Return Date | IFR: 2019-07-17
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1202 | Piping Specialty Item Datasheet - T-Type Filter - Crossover Line - 10-SP-12002-16002 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02162
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1203 | Piping Specialty Item Datasheet - Exhaust Head - 10-SP-12003-16003 |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-22; R1 IFI: 2019-05-22
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01683
[6 empty] | Return Date | IFR: 2019-06-13
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1204 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1242 A-B Outlet - 10-SP-12004-16004 |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-22; R1 IFI: 2019-05-22
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1205 | Piping Specialty Item Datasheet - T-Type Filter - Fuel Gas Line - 10-SP-12005-16005 |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-22; R1 IFI: 2019-05-22
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1206 | Piping Specialty Item Datasheet - Special Tee Fitting 36 inches - 10-SP-12006-16006 |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-22; R1 IFI: 2019-05-22
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1207 | Piping Specialty Item Datasheet - Special Tee Fitting 30 inches - 10-SP-12007-16007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1208 | Piping Specialty Item Datasheet - Special Tee Fitting 20 inches - 10-SP-12008-16008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1209 | Piping Specialty Item Datasheet - Special Tee Fitting 16 inches - 10-SP-12009-16009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643
[6 empty] | Return Date | IFR: 2019-06-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1211 | Piping Specialty Item Datasheet - Stop Check Valve - 10-SP-12011-16011 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-03; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1212 | Piping Specialty Item Datasheet - 10-SP-12012-16012 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; R1 IFI: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-04-24; R1 IFI: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-01457; R1 IFI: TPSK-LSPA1-T-MP-02160
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-16
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1213 | Piping Specialty Item Datasheet - Vent Silencer - PSV-1244 Outlet - 10-SP-12013-16013 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-03; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1214 | Piping Specialty Item Datasheet - Vent Silencer - Start up - 10-SP-12014-16014 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-05-13; R1 IFI: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01643; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-03; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1215 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge Steam SRY-12002-16002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-1216 | Piping Specialty Item – Data Sheet Y-Type Filter – Purge Steam SRY-12003-16003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| PE | OL1-2P03-1217 | Piping Specialty Item – Flame Arrestor - Vent Gas to Furnace Firebox FLA-12001-13001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-10-15
[6 empty] | Issue Actual | IFR: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02827
Return Date
Owner Cmmt*
| MP | OL1-2P03-1251 | Piping Specialty Item Datasheet - 10-BDV-12001-16001 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24; R1 IFI: 2019-07-16
[6 empty] | Issue Actual | IFR: 2019-04-24; R1 IFI: 2019-07-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-01457; R1 IFI: TPSK-LSPA1-T-MP-02160
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-16
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1252 | Piping Specialty Item Datasheet - Flexible Hose - 10-FLX-12001-16001 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17; R1 IFI: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-05-17; R1 IFI: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01683; R1 IFI: TPSK-LSPA1-T-MP-02292
[6 empty] | Return Date | IFR: 2019-06-13; R1 IFI: 2019-08-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1253 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-12001 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01829; R1 IFI: TPSK-LSPA1-T-MP-02324
[6 empty] | Return Date | IFR: 2019-07-15; R1 IFI: 2019-09-19
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1254 | Piping Specialty Item Datasheet - Sample Cooler-SHP Steam - 10-SPC-12002 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-08-02
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-08-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01829; R1 IFI: TPSK-LSPA1-T-MP-02324
[6 empty] | Return Date | IFR: 2019-07-15; R1 IFI: 2019-09-19
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-1903 | Piping Specialty Item – Data Sheet T-Type Filter – P-1910/P-1912 SRT-19001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2001 | Piping Specialty Item - Datasheet - Basket-Type Filter - Quench Oil Pump Suction - 10-SP-20001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-18
[6 empty] | Issue Actual | IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | IFR: 2019-10-17
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2003 | Piping Specialty Item - Datasheet - T-Type Filter - P-2026 A-B Suction - SRT-20001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-09-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2004 | Piping Specialty Item - Basket-Type Filter - Heavy Fuel Oil Pump Suction - 10-SP-20004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-18
[6 empty] | Issue Actual | IFR: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | IFR: 2019-10-17
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2005 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2030 A-B - ILK-20001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02347
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2007 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-2006 A-B-C Discharge - SCV-20001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2008 | Piping Specialty Item - Datasheet - Steam Trap - E-2008 A-B Shell Side Outlet - STT-20001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02365
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2101 | Piping Specialty Item - Datasheet - T-Type Filter - P-2126 A-B Suction - SRT-21001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-09-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2102 | Piping Specialty Item - Datasheet - T-Type Filter - P-2105 A-B Suction - SRT-21005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-09-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2103 | Piping Specialty Item - Datasheet - T-Type Filter - P-2106 A-B-C - SRT-21003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-09-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2104 | Piping Specialty Item - Datasheet - T-Type Filter - P-2146 A-B Suction - SRT-21002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-09-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2105 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2120 A-B - ILK-21001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02347
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2106 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2105 A-O - ILK-21002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02347
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2107 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - Quench Water Tower T-2100 Vacuum Protection - ILK-21003 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06; R1 IFI: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02347; R1 IFI: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-09-11; R1 IFI: 2019-10-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-2108 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Device - Process Water Stripper T-2140 Over-Pressure Protection - ILK-21004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02365
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2118 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Device - Furnace Continous Blowdown Overpressure Protection - ILK-10003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02365
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2122 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-2146 A-B Discharge - SCV-21001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02418
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2123 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-2106 A-B-C Discharge - SCV-21002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2124 | Piping Speciality Item - Datasheet Cone Filter - E-2100A-E Quench Water Inlet SRC-21001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-28
[6 empty] | Issue Actual | IFR: 2019-08-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02503
Return Date
Owner Cmmt*
| MP | OL1-2P03-2201 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2201 A-B-C - ILK-22001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2202 | Piping Specialty Item - Datasheet - T-Type Filter - P-2210 A-B Suction - 10-SP-22002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2203 | Piping Specialty Item - Datasheet - T-Type Filter - 1st Stage CG Compressor Suction - 10-SP-22003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2204 | Piping Specialty Item - Datasheet - T-Type Filter - 2nd Stage CG Compressor Suction - 10-SP-22004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2205 | Piping Specialty Item - Datasheet - T-Type Filter - P-2220 A-B Suction - 10-SP-22005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01821
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2206 | Piping Specialty Item - Datasheet - T-Type Filter - 3rd Stage CG Compressor Suction - 10-SP-22006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2207 | Piping Specialty Item - Datasheet - T-Type Filter - 4th Stage CG Compressor Suction - 10-SP-22007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01819
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2208 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 4th Stage Discharge - 10-SP-22008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-26
[6 empty] | Issue Actual | IFR: 2019-06-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01984
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2209 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Looking Device - PSV-2235 A-B-C-D - IKL-22003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-24
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02250
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2211 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 4th Stage Suction - 10-SP-22011 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-26
[6 empty] | Issue Actual | IFR: 2019-06-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01984
[6 empty] | Return Date | IFR: 2019-07-31
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2213 | Piping Specialty Item - Datasheet - Y-Type Filter - C-2200 Heavy Wash Oil - SRY-22002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-24
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02250
[6 empty] | Return Date | IFR: 2019-08-27
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2214 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 4th Stage Suction - 10-SP-22014 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-26
[6 empty] | Issue Actual | IFR: 2019-06-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01985
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2215 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2266 A-B - ILK-22004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-24
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02252
[6 empty] | Return Date | IFR: 2019-08-27
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2301 | Piping Specialty Item - Datasheet - T-Type Filter - P-2306 A-B Suction - 10-SP-23001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2302 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2322 A-B - ILK-23002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2303 | Piping Specialty Item - T-Type Filter - P-2304 Suction - 10-SP-23003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2304 | Piping Specialty Item - Datasheet - T-Type Filter - P-2302 A-B Suction - 10-SP-23004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2305 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2335 A-B - ILK-23003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02296
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2306 | Piping Specialty Item - Datasheet - T-Type Filter - P-2310 A-B Suction - 10-SP-23006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2307 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2327 A-B - ILK-23004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02296
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2308 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2316 A-B - ILK-23001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02296
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2309 | Piping Specialty Item - Datasheet - T-Type Filter - P-2320 A-B Suction - 10-SP-23009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2310 | Piping Specialty Item – Datasheet - Y-Type Filter - SRY-23001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-24
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02252
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2311 | SP Item Data Sheet - Desuperheater - SP-23011 - Superseded By OL1-2G31-2311 |  | Class 2 | Purpose** | IFR: CAN; R1 IFI: IFR
[6 empty] | Rev. | IFR: 0; R1 IFI: A
Issue Plan
[6 empty] | Revised Plan | R1 IFI: 2019-07-24
[6 empty] | Issue Actual | R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02858; R1 IFI: TPSK-LSPA1-T-MP-02253
[6 empty] | Return Date | R1 IFI: 2019-08-26
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P03-2312 | Piping Specialty Item - Datasheet - T-Type Filter - P-2300 A-B Suction - 10-SP-23012 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2323 | Piping Specialty Item - Datasheet - T-Type Filter - P-2300 A-B Suction - 10-SP-23023 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-14
[6 empty] | Issue Actual | IFR: 2019-06-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01884
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2325 | Piping Specialty Item - Datasheet - Sight Glass - SGT-23001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-24
[6 empty] | Issue Actual | IFR: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02254
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2326 | SP Item Datasheet - Double-Keyed Interlocked Locking Device - PSV-2332 A-B - ILK-23005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02296
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2403 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2405 Overhead Cracked Gas - SVC-24012 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02059
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2404 | Piping Specialty Item - Datasheet - T-Type Filter - P-2415 A-B Suction - 10-SP-24004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2405 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2414 A-B - ILK-24010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2406 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2415 A-B - ILK-24007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2407 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2418 A-B-C-D - ILK-24009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2408 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2423 A-B-C - ILK-24004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2409 | Piping Specialty Item - Datasheet - Desuperheater - SP-24009 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25; R1 IFI: 2019-10-10
[6 empty] | Issue Actual | IFR: 2019-07-25; R1 IFI: 2019-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259; R1 IFI: TPSK-LSPA1-T-MP-02793
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2410 | Piping Specialty Item - Datasheet - T-Type Filter - P-2445 A-B Suction - 10-SP-24010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2411 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2428 A-B - ILK-24005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2412 | Piping Specialty Item - Datasheet - Desuperheater - SP-24012 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25; R1 IFI: 2019-10-10
[6 empty] | Issue Actual | IFR: 2019-07-25; R1 IFI: 2019-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259; R1 IFI: TPSK-LSPA1-T-MP-02793
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2413 | Piping Specialty Item - Datasheet - T-Type Filter - P-2455 A-B Suction - 10-SP-24013 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2414 | Piping Specialty Item - Datasheet - T-Type Filter - P-2450 A-B Suction - 10-SP-24014 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2415 | Piping Specialty Item - Datasheet - T-Type Filter - 5th Stage CG Compressor Suction - 10-SP-24015 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01835
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2416 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2435 A-B-C-D - ILK-24008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-25
[6 empty] | Issue Actual | IFR: 2019-07-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02259
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2417 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2200 5th Stage Discharge - SCV-24006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02059
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2418 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - E-2460 -Shell Side- Outlet - SCV-24007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2421 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - D-2480 - ILK-24011 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2428 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2440 Vapor Outlet - SCV-24010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2446 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - E-2460 -Shell Side- Outlet - SCV-24008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2451 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2405 Overhead Cracked Gas - SCV-24013 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2460 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - D-2440 Vapor Outlet - SCV-24009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02062
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2501 | Piping Specialty Item - Datasheet - Cone Filter - E-2506 Cracked Gas Inlet - 10-SP-25001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2502 | Piping Specialty Item - Datasheet - Basket-Type Filter - D-2506 BTMS To E-2506 - 10-SP-25002 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-17
[6 empty] | Issue Actual | IFR: 2019-06-17; R1 IFI: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01913; R1 IFI: TPSK-LSPA1-T-MP-01871
[6 empty] | Return Date | IFR: 2019-10-17; R1 IFI: 2019-07-09
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-25024 | Piping Specialty Item - Datasheet - Cone Filter - E-2525 Hydrogen Inlet - 10-SP-25024 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2503 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2507 - 10-SP-25003 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01871; R1 IFI: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | IFR: 2019-07-09; R1 IFI: 2019-10-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-2504 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Cracked Gas Inlet - 10-SP-25004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2505 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Residue Gas Inlet - 10-SP-25005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2506 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Hydrogen Inlet - 10-SP-25006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-01
[6 empty] | Issue Actual | IFR: 2019-07-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2507 | Piping Specialty Item - Datasheet - Cone Filter - E-2508 Methane Recycle Inlet - 10-SP-25007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2508 | Piping Specialty Item - Datasheet - Basket-Type Filter - D-2508 BTMS To E-2508 - 10-SP-25008 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | IFR: 2019-07-09; R1 IFI: 2019-10-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-2509 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2509 - 10-SP-25009 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | IFR: 2019-07-09; R1 IFI: 2019-10-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-2510 | Piping Specialty Item - Datasheet - Basket-Type Filter - Demeth BTMS To E-2510 - 10-SP-25010 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | IFR: 2019-07-09; R1 IFI: 2019-10-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-2511 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2521 - 10-SP-25011 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | IFR: 2019-07-09; R1 IFI: 2019-10-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-2512 | Piping Specialty Item - Datasheet - Basket-Type Filter - Methane Recycle To E-2520 - 10-SP-25012 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | IFR: 2019-07-09; R1 IFI: 2019-10-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-2513 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Residue Gas Inlet - 10-SP-25013 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2514 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Hydrogen Inlet - 10-SP-25014 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2515 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Cracked Gas inlet - 10-SP-25015 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2516 | Piping Specialty Item - Datasheet - Cone Filter - E-2520 Rectifier Ovhd Inlet - 10-SP-25016 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2517 | Piping Specialty Item - Datasheet - Cone Filter - E-2530 Demeth Prefrac Ovhd Inlet - 10-SP-25017 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2518 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2520 BTMS To E-2530 - 10-SP-25018 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01913
[6 empty] | Return Date | IFR: 2019-07-09; R1 IFI: 2019-10-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-2519 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2530 - 10-SP-25019 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2520 | Piping Specialty Item - Datasheet - Cone Filter - E-2540 Demeth Ovhd Inlet - 10-SP-25020 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2521 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To E-2540 - 10-SP-25021 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2522 | Piping Specialty Item - Datasheet - T-Type Filter - TX-2550 Residue Gas Expander Suction - 10-SP-25022 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2523 | Piping Specialty Item - Datasheet - T-Type Filter - C-2550 Residue Gas Recompressor Suction - 10-SP-25023 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2525 | Piping Specialty Item - Datasheet - Cone Filter - E-2525 Rectifier Relux Drum Ovhd Inlet - 10-SP-25025 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2526 | Piping Specialty Item - Datasheet - Basket-Type Filter - Residue Gas To E-2525 - 10-SP-25026 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2527 | Pipng Specialty Item - Datasheet - Cone Filter - E-2500 Residue Gas Inlet - 10-SO-25027 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2528 | Piping Specialty Item - Datasheet Cone Filter - E-2500 Ethane Recycle Inlet - 10-SP-25028 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2529 | Piping Specialty Item - Datasheet - Cone Filter - E-2500 Methane Recycle Inlet - 10-SP-25029 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2530 | Piping Specialty Item - Datasheet - Cone Filter - E-2500 Hydro gem Inlet - 10-SP-25030 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2531 | Piping Specialty Item - Datasheet - Basket-Type Filter - C3R To E-2500 - 10-SP-25031 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2532 | Piping Specialty Item - Datasheet - Basket-Type Filter - C3R To E-2500 - 10-SP-25032 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2533 | Piping Specialty Item - Datasheet - Cone Filter - E-2585 C2R Inlet - 10-SP-25033 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2534 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2580 Side Reboiler Inlet - 10-SP-25034 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2535 | Piping Specialty Item - Datasheet - Cone Filter - E-2587 C2R Inlet - 10-SP-25035 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02046
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2536 | Piping Specialty Item - Datasheet - T-Type Filter - P-2570 A-B Suction - 10-SP-25036 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2538 | Piping Specialty Item - Datasheet - T-Type Filter - P-2586 A-B Suction - 10-SP-25038 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2539 | Piping Specialty Item - Datasheet - Basket-Type Filter - T-2580 Bottoms Reboiler Inlet - 10-SP-25039 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2540 | Piping Specialty Item - Datasheet - Cone Filter - E-2510 Demeth Prefrac Ovhd Inlet - 10-SP-25040 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02045
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2544 | Piping Specialty Item - Datasheet - T-Type Filter - P-2575 A-b Suction - 10-SP-25044 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2546 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2530 A-B - ILK-25010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02347
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2547 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2550 Discharge - 10-SP-25047 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02418
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2548 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - TX-2550 Discharge - 10-SP-25048 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02418
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2549 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2510 A-B - ILK-25011 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02347
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2550 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2520 A-B - ILK-25001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02347
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2551 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2524 A-B - ILK-25002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2552 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2525 A-B - ILK-25013 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2553 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2539 A-B - ILK-25003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2554 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2540 A-B - ILK-25004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2555 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2544 A-B - ILK-25005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2556 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2550 A-B-C - ILK-25007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2557 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2565 A-B-C - ILK-25008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2558 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2548 A-B - ILK-25009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2559 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2545 A-B - ILK-25012 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2560 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2514 A-B - ILK-25014 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02349
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2601 | Piping Specialty Item - Datasheet - T-Type Filter - 2-2620 A-B Suction - 10-SP-26001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2602 | Piping Specialty Item - Datasheet - T-Type Filter - P-2630 A-B Suction - 10-SP-26002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2603 | Piping Specialty Item - Datasheet - T-Type Filter - P-2666 A-B Suction - 10-SP-26003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2605 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2639 A-B - ILK-26003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2606 | Piping Specialty Item - Datasheet - T-Type Filter - P-2660 A-B Suction - 10-SP-26006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2607 | Piping Specialty Item - Datasheet - T-Type Filter - P-2646 A-B Suction - 10-SP-26007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2608 | Piping Specialty Item - Datasheet - T-Type Filter - P-2647 Suction - 10-SP-26008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01917
Return Date
Owner Cmmt*
| MP | OL1-2P03-2609 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2633 A-B - ILK-26004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2610 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2620 A-B - ILK-26005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2612 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2626 A-B - ILK-26006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2613 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - ILK-26001 & ILK-26007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-04
[6 empty] | Issue Actual | IFR: 2019-09-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02566
[6 empty] | Return Date | IFR: 2019-10-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2614 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - ILK-26008 & ILK-26009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-04
[6 empty] | Issue Actual | IFR: 2019-09-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02566
[6 empty] | Return Date | IFR: 2019-10-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2617 | Piping Specialty Item - Datasheet - Y-Type Filter - R-2620 Hydrogen Inlet - SRY-26001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02365
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2620 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - R-2620 ILK-26010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-04
[6 empty] | Issue Actual | IFR: 2019-09-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02566
[6 empty] | Return Date | IFR: 2019-10-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2621 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to C3 Hydrogenation Reactor R-2620 - FLX-26001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02365
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2702 | Piping Specialty Item - Datasheet - T-Type Filter - P-2705 A-B Suction - SRT-27001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2703 | Piping Specialty Item - Datasheet - T-Type Filter -P-2710 A-B Suction - SRT-27002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2705 | Piping Specialty Item - Datasheet - T-Type Filter - P-2720 A-B Suction - SRT-27003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2706 | Piping Specialty Item - Datasheet - T-Type Filter - P-2724 A-B Suction - SRT-27004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2707 | Piping Specialty Item - Datasheet - T-Type Filter - P-2726 A-B Suction - SRT-27005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2708 | Piping Specialty Item - Datasheet - T-Type Filter - P-2750 A-B Suction - SRT-27006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2710 | SP Item Datasheet - Desuperheater - HP Steam to E-2715 A-B & E-2725 A-C - SP-27010 - Superseded by OL1-2G31-2710 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14; R1 IFI: 2019-10-10
[6 empty] | Issue Actual | IFR: 2019-08-14; R1 IFI: 2019-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419; R1 IFI: TPSK-LSPA1-T-MP-02793
[6 empty] | Return Date | IFR: 2019-10-17
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2712 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2750 A-B - ILK-27001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2713 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2716 A-B - ILK-27002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2715 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2733 A-E - ILK-27003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2716 | Piping Specialty Item - Datasheet - T-Type Filter - P-2721 A-B Suction - SRT-27001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2717 | Piping Specialty Item - Datasheet - Liquid Drain Trap - D-2735 Drain to OWD - STT-27001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-17
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2718 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to GHU-1 Reactor R-2700A - FLX-27001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02365
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2719 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2723 A-D - ILK-27004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2720 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - ILK-27005 & ILK-27009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-04
[6 empty] | Issue Actual | IFR: 2019-09-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02566
[6 empty] | Return Date | IFR: 2019-10-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2723 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - R-2760 ILK-27006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-04
[6 empty] | Issue Actual | IFR: 2019-09-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02566
[6 empty] | Return Date | IFR: 2019-10-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2724 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to C4 C5 Hydrogenation Reactor R-2760 - FLX-27002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02365
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2725 | Piping Specialty Item - Datasheet - T-Type Filter - P-2714 A-B Suction - SRT-27008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2726 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2761 A-B - ILK-27007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2727 | Piping Specialty Item - Datasheet - T-Type Filter - P-2760 A-B Suction - 10-SRT-27009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-31
[6 empty] | Issue Actual | IFR: 2019-07-31
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02297
[6 empty] | Return Date | IFR: 2019-09-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2728 | Piping Specialty Item - Datasheet - Y-Type Filter - R-2760 Hydrogen Inlet - SRY-27001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02365
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2729 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2771 A-B - ILK-27008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2736 | Piping Specialty Item - Datasheet - Flexible Hose - MP Nitrogen to GHU-1 Reactor R-2700B - FLX-27003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02365
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2801 | Piping Specialty Item - Datasheet - T-Type Filter - C-2800 3rd Stage Propylene Refrig. Compressor Suction - 10-SP-28000 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2802 | Piping Specialty Item - Database - T-Type Filter - C-2800 2nd Stage Propylene Refrig. Compressor Suction - 10-SP-28001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2803 | Piping Specialty Item - Datasheet - T-Type Filter - C-2800 - 1st Stage Propylene Refrig. Compressor Suction - 10-SP-28002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2804 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 3rd Stage Suction - 10-SP-28101 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2805 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 2nd Stage Suction - 10-SP-28102 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01928
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2806 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 1st Stage Suction - 10-SP-28103 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01931
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2807 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 5th Stage Discharge - 10-SP-28104 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01933
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2808 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 4th Stage Suction - 10-SP-28105 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01933
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2809 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 4th Stage Discharge - 10-SP-28108 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01934
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2810 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 4th Stage Discharge - 10-SP-28109 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01935
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2811 | Piping Specialty Item - Datasheet - T-Type Filter - C-2800 th Stage Propylene Refrig. Compressor Suction - 10-SP-28003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2812 | Piping Specialty Item - Datasheet - Non-Slam Check valve - C-2800 5th Stage Discharge - 10-SP-28106 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2813 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2800 5th Stage Discharge - 10-SP-28011 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2820 | Piping Specialty Item - Datasheet - T-Type Filter - P-2815 Suction - 10-SP-28009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2821 | Piping Specialty Item - Datasheet - T-Type Filter - P-2805 A-B Suction - 10-SP-28010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2822 | Piping Specialty Item - Datasheet - T-Type Filter - C-2850 3rd Stage Ethylene Refrig. Compressor Suction - 10-SP-28504 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2823 | Piping Specialty Item - Datasheet - T-Type Filter - C-2850 2nd Stage Ethylene Refrig. Compressor Suction - 10-SP-28505 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-19
[6 empty] | Issue Actual | IFR: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2824 | Piping Specialty Item - Datasheets - T-Type Filter - C-2850 1st Stage Ethylene Refrig. Compressor Suction - 10-SP-28506 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01936
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2825 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 3rd Stage Suction - 10-SP-28604 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2826 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 2nd Stage Suction - 10-SP-28605 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2827 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 1st Stage Suction - 10-SP-28606 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01937
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2828 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 3rd Stage Discharge - 10-SP-28602 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20; R1 IFI: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01938; R1 IFI: TPSK-LSPA1-T-MP-01938
[6 empty] | Return Date | R1 IFI: 2019-07-16
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P03-2829 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C-2850 4th Stage Discharge - 10-SP-28603 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01938
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2830 | Piping Specialty Item - Datasheet -Non-Slam Check - C-2850 3 rd Stage Discharge - 10-SP-28607 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01938
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2833 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C2R Desuperheater 2 Outlet - 10-SP-28609 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01939
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2834 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - C2R Desuperheater 2 Outlet - 10-SP-28608 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01939
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2835 | Piping Specialty Item - Datasheet - T-Type Filter - P-2855 A-B Suction - 10-SP-28510 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01940
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2843 | Piping Specialty Item - Datasheet - Basket-Type Filter - C2R Inlet To D-2884 - 10-SP-28508 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2844 | Piping Specialty Item - Datasheet - Basket-Type Filter - LP Ethylene To D-2882 & E-2882 - 10-SP-28512 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-11
[6 empty] | Issue Actual | IFR: 2019-06-11; R1 IFI: 2019-06-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01872; R1 IFI: TPSK-LSPA1-T-MP-01917
[6 empty] | Return Date | IFR: 2019-07-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2855 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2805 A-E - ILK-28001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2856 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2806 A-D - ILK-28002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2857 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2820 A-B - ILK-28003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-08-28
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2858 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2823 A-B - ILK-28004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2859 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2826 A-B - ILK-28005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2860 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2829 A-B - ILK-28006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2861 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2845 A-B - ILK-28013 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02348
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2862 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2867 A-B - ILK-28014 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2863 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2842 A-B - ILK-28007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2864 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2841 A-D - ILK-28008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2865 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2864 A-B - ILK-28009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2866 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2858 A-B - ILK-28011 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2867 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2861 A-B - ILK-28010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2868 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2854 A-B - ILK-28015 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2901 | Piping Specialty Item - Datasheet - T-Type Filter - P-2930 Suction - 10-SP-29001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2902 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2925 - A-B - ILK-29001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2904 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2006A Suction - 10-SP-29004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2905 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2106A Suction - 10-SP-29005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2906 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2146A Suction - 10-SP-29006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-02
[6 empty] | Issue Actual | IFR: 2019-07-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2907 | Piping Specialty Item - Datasheet - T-Type Filter - P-2202 A-B Suction - 10-SP-29007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2910 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2951 A-G - ILK-29003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2911 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2200 Suction - 10-SP-29011 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2912 | Piping Specialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29012 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2915 | Piping Speacialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29015 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2916 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2850 Suction - 10-SP-29016 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2918 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-2976 A-B-C - ILK-29002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-06
[6 empty] | Issue Actual | IFR: 2019-08-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02352
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2919 | Piping Specialty Item - Datasheet - T-Type Filter - P2862 A-B Suction - 10-SP-29019 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2920 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2800 Suction - 10-SP-29020 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2921 | Piping Specialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29021 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2922 | Piping Specialty Item - Datasheet - T-Type Filter - P-2802 A-B Suction - 10-SP-29022 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2924 | Piping Specialty Item - Datasheet - T-Type Filter - CT-2800 Suction - 10-SP-29024 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2926 | Piping Specialty Item - Datasheet - Vent Silencer - Start-Up - 10-SP-29026 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | IFR: 2019-07-08
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2927 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2201A Suction - 10-SP-29027 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2928 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2801A Suction - 10-SP-29028 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02063
[6 empty] | Return Date | IFR: 2019-07-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2929 | Piping Specialty Item - Datasheet - T-Type Filter - PT-2861A Suction - 10-SP-29029 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2931 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 1st STG Suction - 10-SP-29031 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2932 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 2nd STG Suction - 10-SP-29032 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2933 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 3rD STG Suction - 10-SP-29033 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2934 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 4th STG Suction - 10-SP-29034 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-2935 | Piping Specialty Item - Datasheet - T-Type Filter - P-2910 5th STG Suction - 10-SP-29035 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-03
[6 empty] | Issue Actual | IFR: 2019-07-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-02058
[6 empty] | Return Date | IFR: 2019-08-05
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3001 | Piping Specialty Item - Datasheet - T-Type Filter - P-3002 A-B Suction - 10-SP-30001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02012
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3002 | Piping Specialty Item - Datasheet - T-Type Filter - P-3000 A-B Suction - 10-SP-30002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3003 | Piping Specialty Item - Datasheet - T-Type Filter - P-3016 A-B Suction - 10-SP-30003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3004 | Piping Specialty Item - Datasheet - T-Type Filter - P-3026 A-B Suction - 10-SP-30004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3005 | Piping Specialty Item - Datasheet - T-Type Filter - P-3020 A-B Suction - 10-SP-30005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02012
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3006 | Piping Specialty Item – Data Sheet Double-Keyed Interlocked Locking Device - PSV-3001 A/B ILK-30001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3007 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3005 A/B ILK-30002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3008 | Piping Specialty Item - Datasheet - T-Type Filter - P-3030 A-B Suction - 10-SP-30008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3009 | Piping Specialty Item - Datasheet - T-Type Filter - P-3045 A-B Suction - 10-SP-30009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3010 | Piping Specialty Item - Datasheet - T-Type Filter - P-3046 A-B Suction - 10-SP-30010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3011 | Piping Specialty Item - Datasheet - T-Type Filter - P-3036 A-B Suction - 10-SP-30011 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3012 | Piping Specialty Item - Datasheet - T-Type Filter - P-3062 A-B Suction - 10-SP-30012 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3013 | Piping Specialty Item - Datasheet - T-Type Filter - P-3086 A-B Suction - 10-SP-30013 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02009
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3014 | Piping Specialty Item - Datasheet - T-Type Filter - P-3076 A-B Suction - 10-SP-30014 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3015 | Piping Specialty Item - Datasheet - T-Type Filter - P-3056 A-B Suction - 10-SP-30015 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3016 | Piping Specialty Item - Datasheet - T-Type Filter - P-3060 A-B Suction - 10-SP-30016 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3017 | Piping Specialty Item - Datasheet - T-Type Filter - P-3061 A-B Suction - 10-SP-30017 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3018 | Piping Specialty Item - Datasheet - T-Type Filter - P-3096 A-B Suction - 10-SP-30018 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3019 | Piping Specialty Item - Datasheet - T-Type Filter - P-3080 A-B Suction - 10-SP-30019 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02010
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3020 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3016 A-B Discharge - SRY-30001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3024 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3030 Product Inhibitor Inlet - SRY-30002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3025 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3026 A/B ILK-30005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3026 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3080 Product Inhiditor Inlet - SRY-39005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3030 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3055 A-B MP Condensate Outlet - SRY-30003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3031 | Piping Specialty Item - Datasheet - Steam Trap - E-3055 A-B MP Condensate Outlet - STT-30001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3036 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3028 A/B ILK-30006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3037 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3033 A/B ILK-30007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3038 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3039A/B ILK-30008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3039 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3031A/B ILK-30009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3040 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3042A/B ILK-30010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3101 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3163A/B ILK-31001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3102 | Piping Specialty Item – T-Type Filter - P-3160A/B Suction SRT-31001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-11
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3103 | Piping Specialty Item – T-Type Filter - P-3110A/B Suction SRT-31002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3104 | Piping Specialty Item – T-Type Filter - P-3126A/B Suction SRT-31003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3106 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3162A/B ILK-31002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3107 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3164A/B ILK-31003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3108 | Piping Specialty Item - Datasheet - Steam Trap - D-3190 Heating Coil Outlet - 10-STT-31001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3109 | Piping Specialty Item - Datasheet - Y-Type Filter - D-3190 LP Condensate Outlet - SRY-31002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3110 | Piping Specialty Item - Datasheet - Y-Type Filter - D-3190 LP Condensate Outlet - SRY-31001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3111 | Piping Specialty Item - Datasheet - Steam Trap - D-3180 Heating Coil Outlet - 10-STT-31004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3112 | Piping Specialty Item - Datasheet - Y-Type Filter - D-3100 Jacket LP Condensate Outlet - SRY-31003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3113 | Piping Specialty Item - Datasheet - Y-Type Filter - LP Condensate from D-3100 Jacket LP Steam Inlet Line - SRY-31004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3114 | Piping Specialty Item - Datasheet - Steam Trap - LP Condensate D-3100 Jacket - STT-31003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3115 | Piping Specialty Item - Datasheet - Steam Trap - LP Condensate from D-3100 Jacket LP Steam Inlet Line - STT-31002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3118 | SP Item Datasheet - BDU MP Steam Desuperheater - SP-31018 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14; R1 IFI: 2019-10-10
[6 empty] | Issue Actual | IFR: 2019-08-14; R1 IFI: 2019-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02420; R1 IFI: TPSK-LSPA1-T-MP-02793
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3119 | SP Item Datasheet - BDU LP Steam Desuperheater - SP-31019 - Superseded by OL1-2G31-3102 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14; R1 IFI: 2019-10-10
[6 empty] | Issue Actual | IFR: 2019-08-14; R1 IFI: 2019-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02420; R1 IFI: TPSK-LSPA1-T-MP-02793
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3120 | Piping Specialty Item - Datasheet - Y-Type Filter - HP BFW to Desuperheaters - 10-SRY-31005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3121 | Piping Specialty Item – Double-Keyed Interlocked Locking Device - PSV-3165A/B ILK-31004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3122 | Piping Specialty Item - Datasheet - Y-Type Filter - E-3150 LP Condensate Outlet - SRY-31006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3123 | Piping Specialty Item - Datasheet - Steam Trap - LP Condensate from E-3150 - 10-STT-31005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3125 | Piping Specialty Item - Datasheet - Y-Type Filter - PK-3120 MP Steam Inlet - SRY-31007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02415
Return Date
Owner Cmmt*
| MP | OL1-2P03-3901 | Piping Specialty Item – T-Type Filter - P-3900 Suction SRT-39001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3902 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3902 A-B Suction - SRY-39001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3903 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3906 A-B - Suction - SRY-39002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3904 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3908 A-B Suction - SRY-39003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3905 | Piping Specialty Item - Datasheet - Y-Type Filter - P-3904 A-B Suction - SRY-39004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02419
[6 empty] | Return Date | IFR: 2019-10-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-3910 | Piping Specialty Item - Datasheet - Flame Arrestor - TK-3900 Vent FLA-39001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-21
[6 empty] | Issue Actual | IFR: 2019-08-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02457
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5001 | Piping Specialty Item - Datasheet - Safety Shower and Eye Station - Area 50 - SS-50001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5101 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to SHP-HP Steam Letdown - SRT-51001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5102 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to HP-MP Steam Letdown - SRT-51002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5103 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to MP-LP LS1 Steam Letdown - SRT-51003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5104 | Piping Specialty Item - Datasheet - T-Type Filter - VLP BFW to LP LS1 - VLP LS2 Steam Letdown - SRT-51021 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5105 | SP Item Data Sheet - LP LS1 VLP LS2 Letdown Desuperheater - SP-51005 - Superseded by OL1-2G31-5104 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05; R1 IFI: 2019-09-11
[6 empty] | Issue Actual | IFR: 2019-08-05; R1 IFI: 2019-09-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02317; R1 IFI: TPSK-LSPA1-T-MP-02604
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5106 | SP Item Data Sheet - MP - LP LS1 Letdown Desuperheater - SP-51006 - Superseded by OL1-2G31-5103 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05; R1 IFI: 2019-09-11
[6 empty] | Issue Actual | IFR: 2019-08-05; R1 IFI: 2019-09-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02317; R1 IFI: TPSK-LSPA1-T-MP-02604
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5107 | SP Item Data Sheet - HP - MP Letdown Desuperheater - SP-51007 - Superseded by OL1-2G31-5102 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05; R1 IFI: 2019-09-11
[6 empty] | Issue Actual | IFR: 2019-08-05; R1 IFI: 2019-09-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02317; R1 IFI: TPSK-LSPA1-T-MP-02604
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5108 | SP Item Data Sheet - SHP - HP Letdown Desuperheater - SP-51008 - Superseded by OL1-2G31-5151 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05; R1 IFI: 2019-09-11
[6 empty] | Issue Actual | IFR: 2019-08-05; R1 IFI: 2019-09-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02317; R1 IFI: TPSK-LSPA1-T-MP-02604
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5109 | SP Item Data Sheet - SHP - HP Letdown Desuperheater - SP-51009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02317
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5112 | Piping Specialty Item - Datasheet - T-Type Filter - HP BFW to SHP-HP Steam Letdown - SRT-51004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5113 | Piping Specialty Item - Datasheet - T-Type Filter - P-5100 A-B-C Suction - SRT-51018 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5115 | Piping Specialty Item - Datasheet - T-Type Filter - P-5102 A-B Suction - SRT-51016 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5116 | Piping Specialty Item - Datasheet - T-Type Filter - P-5112 A-B Suction - SRT-51023 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5117 | Piping Specialty Item - Datasheet - T-Type Filter - P-5120 A-B Suction - SRT-51022 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5118 | Piping Specialty Item - Datasheet - T-Type Filter - P-5110 A-B Suction - SRT-51027 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5119 | Piping Specialty Item - Datasheet - Exhaust Head - 10-SP-51019 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5120 | Piping Specialty Item - Datasheet - T-Type Filter - P-5140 A-B Suction - SRT-51015 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5121 | Piping Specialty Item - Datasheet - Vent Silencer -PV-5143 Outlet - 10-SP-51021 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809; R1 IFI: TPSK-LSPA1-T-MP-02594
[6 empty] | Return Date | IFR: 2019-06-27; R1 IFI: 2019-10-01
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-5122 | Piping Specialty Item- Datasheet Vent Silencer - PV-5147 Outlet 10-SP-51022 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809; R1 IFI: TPSK-LSPA1-T-MP-02594
[6 empty] | Return Date | IFR: 2019-07-01; R1 IFI: 2019-10-01
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-5123 | Piping Specialty Item- Datasheet Vent Silencer - PV-5155 Outlet 10-SP-51023 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809; R1 IFI: TPSK-LSPA1-T-MP-02594
[6 empty] | Return Date | IFR: 2019-07-01; R1 IFI: 2019-10-01
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-5124 | Piping Specialty Item- Datasheet Vent Silencer - PV-5158 Outlet 10-SP-51024 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809; R1 IFI: TPSK-LSPA1-T-MP-02594
[6 empty] | Return Date | IFR: 2019-07-01; R1 IFI: 2019-10-01
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-5125 | Piping Specialty Item- Datasheet Vent Silencer - PV-5161 Outlet 10-SP-51025 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-06-10; R1 IFI: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809; R1 IFI: TPSK-LSPA1-T-MP-02594
[6 empty] | Return Date | IFR: 2019-07-01; R1 IFI: 2019-10-01
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-5126 | Piping Specialty Item - Datasheet - Vent Silencer - PSV-5134 A-H- Outlet - 10-SP-51026 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20
[6 empty] | Issue Actual | IFR: 2019-06-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01941
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5128 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5143 A-H - ILK-51001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5129 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5150 A-D - ILK-51004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5130 | Piping Specialty Item - Datasheet - Vent Silencer - PSV-5150 A-B-C-D Outlet - 10-SP-51030 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-20; R1 IFI: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-06-20; R1 IFI: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01941; R1 IFI: TPSK-LSPA1-T-MP-02594
[6 empty] | Return Date | IFR: 2019-07-15; R1 IFI: 2019-10-01
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P03-5134 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5153 A-D - ILK-51002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5141 | Piping Specialty Item - Datasheet - Exhaust Head - 10-SP-51041 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01809
[6 empty] | Return Date | IFR: 2019-07-01
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5143 | Piping Specialty Item - Datasheet – Double-Keyed Interlocked Locking Device - PSV-5140 A-B - ILK-51005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5144 | Piping Specialty Item - Datasheet - Injection Quill - Amine Injection to BFW Pump Suction - IJQ-51001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5145 | Piping Specialty Item - Datasheet - Injection Quill - Phosphate Injection to SHP BFW - IJQ-51002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5146 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5102 A-B Discharge - SCV-51004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5147 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5100 A-B-C Discharge - SCV-51001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5148 | Piping Specialty Item - Datasheet - Multistage Restriction Orifice - SHP BFW Pump Warmup - ORI-51003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
Return Date
Owner Cmmt*
| MP | OL1-2P03-5201 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5204 A-B-C-D - ILK-52001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5202 | Piping Specialty Item - Datasheet - Steam Trap - E-5210 Shell Side Outlet - STT-52002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5203 | Piping Specialty Item - Datasheet - Steam Trap - E-5200 Shell Side Outlet - STT-52001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5206 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5209 A-B - ILK-52002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5301 | Piping Specialty Item - Datasheet - Coupon Rack - Olefins Cooling Tower SP-53001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-22
[6 empty] | Issue Actual | IFR: 2019-08-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02468
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5302 | Piping Specialty Item - Datasheet - Coupon Rack - CTU Cooling Tower SP-53002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-22
[6 empty] | Issue Actual | IFR: 2019-08-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02468
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5303 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5350 A-H Discharge - SCV-53004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5304 | Piping Specialty Item - Datasheet - Non-Slam Check Valve - P-5360 A-B-C Discharge - SCV-53001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02319
[6 empty] | Return Date | IFR: 2019-08-26
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5401 | Piping Specialty Item - Datasheet - Liquid Drain Trap - D-5400 Drain to OWD - STT-54001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02421
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5446 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5404 A-B - ILK-54001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5501 | Piping Specialty Item - Datasheet - T-Type Filter - p-5500 A-B Suction - SRT-55003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| ME | OL1-2P03-5502 | Piping Specialty Item – Flame Arrestor - Vent Gas to Furnace Fire-Box SP-55002 |  | Class 2 | Purpose** | IFR: CAN; R1 IFI: IFR
[6 empty] | Rev. | IFR: 0; R1 IFI: A
Issue Plan
[6 empty] | Revised Plan | R1 IFI: 2019-08-21
[6 empty] | Issue Actual | R1 IFI: 2019-08-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02808; R1 IFI: TPSK-LSPA1-T-MP-02457
[6 empty] | Return Date | R1 IFI: 2019-09-19
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P03-5503 | Piping Specialty Item - Datasheet - Flame Arrestor - Vent Gas to Tank Farm Flare SP-55003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-21
[6 empty] | Issue Actual | IFR: 2019-08-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02457
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5508 | Piping Specialty Item - Datasheet - Steam Trap - E-5513 Tube Side Outlet - STT-55001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5510 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5510 A-B - ILK-55003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5512 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5531 A-B - ILK-55002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5514 | Piping Specialty Item - Datasheet - Double-Keyed Interlocked Locking Device - PSV-5532 A-B - ILK-55001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5521 | Piping Specialty Item - Datasheet - T-Type Filter - P-5550 A-B Suction - SRT-55001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5522 | Piping Specialty Item - Datasheet - T-Type Filter - p-5565 A-B Suction - SRT-55002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5523 | Piping Specialty Item - Datasheet - Steam Trap - D-5565 Coil Outlet - STT-55004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5524 | Piping Specialty Item - Datasheet - Liquid Drain Trap - Vent Gas Header in WWT Unit - STT-55005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-14
[6 empty] | Issue Actual | IFR: 2019-08-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02421
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5566 | Piping Specialty Item - Datasheet - Steam Trap - E-5552 Shell Side Outlet - STT-55002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5601 | Piping Specialty Item - Datasheet - T-Type Filter - P-5620 A-C Suction - SRT-56005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5602 | Piping Specialty Item - Datasheet - T-Type Filter - P-5621 Suction - SRT-56002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5603 | Piping Specialty Item - Datasheet - T-Type Filter - P-5655 A-C Suction - SRT-56006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5604 | Piping Specialty Item - Datasheet - T-Type Filter - P-5640 A-B Suction - SRT-56007 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5605 | Piping Specialty Item - Datasheet - T-Type Filter - P-5641 Suction - SRT-56003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5606 | Piping Specialty Item - Datasheet - T-Type Filter - P-5675 Suction - SRT-56004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5607 | Piping Specialty Item - Datasheet - T-Type Filter - P-5676 Suction - SRT-56001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5608 | Piping Specialty Item - Datasheet - Carbon Canister - PIT-5632 Vent SP-56008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-15
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02438
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5609 | Piping Specialty Item - Datasheet - Steam Trap - TK-5675A Coil Outlet - STT-56001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5610 | Piping Specialty Item - Datasheet - Steam Trap - TK-5675B Coil Outlet - STT-56002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5611 | Piping Specialty Item - Datasheet - Steam Trap - TK-5676 Coil Outlet - STT-56003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02335
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5613 | Piping Specialty Item - Datasheet - T-Type Filter - P-5656 A-B Suction - SRT-56008 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5614 | Piping Specialty Item - Datasheet - T-Type Filter - P-5653 A-B Suction - SRT-56009 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5615 | Piping Specialty Item - Datasheet - Sight Glass -P-5621 Discharge STG-56001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-15
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02438
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5901 | Piping Specialty Item - Datasheet - Carbon Canister - TK-5900 Sulfuric Acid Tank Vent SP-59001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-15
[6 empty] | Issue Actual | IFR: 2019-08-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02438
[6 empty] | Return Date | IFR: 2019-09-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5902 | Piping Specialty Item - Datasheet - T-Type Filter - P-5900 A-B Suction - SRT-59004 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5903 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5950 A-B Suction - SRT-59001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5904 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5901 A-B Suction - SRT-59003 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5905 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5110 A Inlet - SRT-51012 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5906 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5350 A-B-C Inlet - SRT- 51010 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5909 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5360 A Inlet - SRT-51011 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5910 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5100 A-B Inlet - SRT-59002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5912 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5101 A Inlet - SRT-51029 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5913 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5103 A- Inlet - SRT-51030 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-09
[6 empty] | Issue Actual | IFR: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02398
[6 empty] | Return Date | IFR: 2019-09-03
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5914 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5102 A Inlet - SRT-51026 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-22
[6 empty] | Issue Actual | IFR: 2019-07-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5915 | Piping Specialty Item - Datasheet - T-Type Filter - PT-5105 A Inlet - SRT-51031 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5917 | Piping Specialty Item - Datasheet - T-Type Filter - P-5905 A-B Suction - SRT-59005 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
| MP | OL1-2P03-5918 | Piping Specialty Item - Datasheet - T-Type Filter - P-5955 A-B Suction - SRT-59006 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-23
[6 empty] | Issue Actual | IFR: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02215
[6 empty] | Return Date | IFR: 2019-08-15
Owner Cmmt* | bar: IFR
Category Code: P04 Piping design basic / philosophy / logic diagram
Category Code: P05 Piping calculation sheet / report
| MP | OL1-2P05-0002 | CRITICAL LINE LIST - COOLING WATER UNIT |  |  | Purpose** | IFR: IDD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-30; R1 IFI: 2020-04-10
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0003 | CRITICAL LINE LIST - MAIN PIPE RACK |  |  | Purpose** | IFR: IDD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-30; R1 IFI: 2020-04-10
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0004 | CRITICAL LINE LIST - OFF-SITES |  |  | Purpose** | IFR: IDD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-30; R1 IFI: 2020-04-10
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0005 | CRITICAL LINE LIST - WASTE WATER TREATMENT |  |  | Purpose** | IFR: IDD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-30; R1 IFI: 2020-04-10
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0006 | CRITICAL LINE LIST - FURNACES UTILITIES |  |  | Purpose** | IFR: IDD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-30; R1 IFI: 2020-04-10
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0007 | CRITICAL LINE LIST - FRACTIONATION 1 & 2 |  |  | Purpose** | IFR: IDD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-30; R1 IFI: 2020-04-10
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0008 | CRITICAL LINE LIST - FRACTIONATION 3 & BUTADIENE EXTRACTION |  |  | Purpose** | IFR: IDD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-09-30; R1 IFI: 2020-04-10
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2020-04-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-0030 | LOADS ON SLEEPER WAY 10-SLW-0C01 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-03
[6 empty] | Issue Actual | IFR: 2019-09-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02549
Return Date
Owner Cmmt*
| MP | OL1-2P05-0031 | LOADS ON SLEEPER WAY 10-SLW-0C02 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-03
[6 empty] | Issue Actual | IFR: 2019-09-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02549
Return Date
Owner Cmmt*
| MP | OL1-2P05-0041 | Loads On Rack 10-PRK-0P01 |  | Class 2 | Purpose** | IFR: IBD; R1 IFI: IDD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-03; R1 IFI: 2019-07-10
[6 empty] | Issue Actual | IFR: 2019-04-03; R1 IFI: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01228; R1 IFI: TPSK-LSPA1-T-MP-02108
[6 empty] | Return Date | IFR: 2019-04-26; R1 IFI: 2019-07-19
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P05-0042 | Loads On Rack 10-PRK-0P02 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24
[6 empty] | Issue Actual | IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01439
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0043 | Loads On Rack 10-PRK-0P03 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-24
[6 empty] | Issue Actual | IFR: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01439
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0073 | Loads On Structure 10-STR-2A02 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | IFR: 2019-08-13
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0112 | Loads On structures 10-STR-2C01-2C |  | Class 2 | Purpose** | IFR: IDB
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | IFR: 2019-08-13
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0113 | Loads On Structures 10-STR-2C03-2C |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | IFR: 2019-08-13
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0131 | Loads On Rack 10-PRK-2D01 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | IFR: 2019-08-13
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0153 | Loads On Structures 10-STR-2E01-2E |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-05
[6 empty] | Issue Actual | IFR: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02322
[6 empty] | Return Date | IFR: 2019-08-13
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0171 | Loads On Rack 10-PRK-3A01 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-10-10
[6 empty] | Issue Actual | IFR: 2019-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-2786
Return Date
Owner Cmmt*
| MP | OL1-2P05-0191 | Loads On Rack 10-PRK-5F01 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02142
[6 empty] | Return Date | IFR: 2019-07-30
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0192 | Loads On Sleeper Way 10-SLW-5F01 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-10
[6 empty] | Issue Actual | IFR: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02103
[6 empty] | Return Date | IFR: 2019-09-18
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0211 | Loads on Rack 10-PRK-5T01 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-07
[6 empty] | Issue Actual | IFR: 2019-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02357
Return Date
Owner Cmmt*
| MP | OL1-2P05-0212 | Loads on Sleeper Way 10-SLW-5T02 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02151
Return Date
Owner Cmmt*
| MP | OL1-2P05-0213 | Loads On Sleeper Way 10-SLW-5T01 |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-08-30
[6 empty] | Issue Actual | IFR: 2019-08-30
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02534
Return Date
Owner Cmmt*
| MP | OL1-2P05-0231 | Loads On Rack 10-PRK-5U01 |  | Class 2 | Purpose** | IFR: IFD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01839
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-0251 | Loads On Sleeper Way 10-SLW-5W01 |  | Class 2 | Purpose** | IFR: IFD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01839
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| MP | OL1-2P05-1101 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1102 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1103 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1104 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1105 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1106 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1107 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1108 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1109 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1110 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1111 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1112 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1113 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1114 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1115 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1116 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1117 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1118 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1119 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1120 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1121 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1122 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1123 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1124 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1201 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1202 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1203 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1204 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1205 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1206 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1207 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1208 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1209 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1210 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1211 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1212 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1213 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1214 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1215 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1216 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1217 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1218 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1219 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1220 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1221 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1222 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1223 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1224 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1301 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1302 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1303 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1304 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1305 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1306 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1307 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1308 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1309 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1310 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1311 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1312 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1313 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1314 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1315 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1316 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1317 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1318 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1319 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1320 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1321 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1322 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1323 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1324 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1401 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1402 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1403 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1404 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1405 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1406 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1407 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1408 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1409 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1410 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1411 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1412 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1413 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1414 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1415 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1416 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1417 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1418 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1419 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1420 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1421 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1422 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1423 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1424 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1501 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1502 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1503 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1504 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1505 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1506 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1507 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1508 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1509 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1510 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1511 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1512 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1513 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1514 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1515 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1516 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1517 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1518 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1519 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1520 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1521 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1522 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1523 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1524 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1601 | PIPE STRESS ANALYSIS OF SYSTEM 1 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1602 | PIPE STRESS ANALYSIS OF SYSTEM 2 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1603 | PIPE STRESS ANALYSIS OF SYSTEM 3 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1604 | PIPE STRESS ANALYSIS OF SYSTEM 4 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1605 | PIPE STRESS ANALYSIS OF SYSTEM 5 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1606 | PIPE STRESS ANALYSIS OF SYSTEM 6 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1607 | PIPE STRESS ANALYSIS OF SYSTEM 7 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1608 | PIPE STRESS ANALYSIS OF SYSTEM 8 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1609 | PIPE STRESS ANALYSIS OF SYSTEM 9 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1610 | PIPE STRESS ANALYSIS OF SYSTEM 10 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1611 | PIPE STRESS ANALYSIS OF SYSTEM 11 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1612 | PIPE STRESS ANALYSIS OF SYSTEM 12 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1613 | PIPE STRESS ANALYSIS OF SYSTEM 13 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1614 | PIPE STRESS ANALYSIS OF SYSTEM 14 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1615 | PIPE STRESS ANALYSIS OF SYSTEM 15 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1616 | PIPE STRESS ANALYSIS OF SYSTEM 16 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1617 | PIPE STRESS ANALYSIS OF SYSTEM 17 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1618 | PIPE STRESS ANALYSIS OF SYSTEM 18 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1619 | PIPE STRESS ANALYSIS OF SYSTEM 19 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1620 | PIPE STRESS ANALYSIS OF SYSTEM 20 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1621 | PIPE STRESS ANALYSIS OF SYSTEM 21 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1622 | PIPE STRESS ANALYSIS OF SYSTEM 22 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1623 | PIPE STRESS ANALYSIS OF SYSTEM 23 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-1624 | PIPE STRESS ANALYSIS OF SYSTEM 24 |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-12-09
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0C |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-2501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5T |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-3001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 0P |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5R |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-4501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5F |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-5001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5W |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-6001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 1B |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2A |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7201 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2B |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7401 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2D |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7601 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2E |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-7801 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 5U |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8001 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 2C |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P05-8501 | COMPUTER STRESS ANALYSIS CALCULATION NOTES - ZONE 3A |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-03-18
[6 empty] | Revised Plan | IFR: 2021-03-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P06 Piping drawing
| MP | OL1-2P06-0001 | General Plot Plan - Draft |  |  | Purpose** | IFR | IBD | IBD | IBD | IDD | IFC
[6 empty] | Rev. | A | B | C | D | E
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IMP: 2019-09-17; R1 IMP: 2020-04-10
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-10
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23; R1 IFF: 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-MP-00871 | TPSK-LSPA1-T-MP-01752 | TPSK-LSPA1-T-MP-02219 | TPSK-LSPA1-T-MP-02386 | TPSK-LSPA1-T-MP-02860
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22; R1 IFF: 2019-10-10
Owner Cmmt* | bar: IFR to R1 IFF
| MP | OL1-2P06-0002 | Detail Plot Plan - Zone 0M - Metering Station |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFD: 2019-09-17; R1 IFF: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-09-28; R1 IFF: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-09-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-02472
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-09-16
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0003 | Unit Plot Plan - Zone 0P - Main Pipe Rack |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C; R1 IFF: D
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219; R1 IFF: TPSK-LSPA1-T-MP-02860
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0004 | Detail Plot Plan - Zone 0S - Electrical Sub-Station And Far E |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFD: 2019-09-17; R1 IFF: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-08-09; R1 IFF: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-02386
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-10-11
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0005 | Detail Plot Plan - Zone 3S - Electrical Sub-Station And Far C |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFD: 2019-09-17; R1 IFF: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-08-09; R1 IFF: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-02386
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-10-11
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0006 | Detail Plot Plan Zone 1A Furnaces |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFD: 2019-09-17; R1 IFF: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-03-08; R1 IFI: 2019-05-29; R1 IFF: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-03-08; R1 IFI: 2019-05-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01003; R1 IFI: TPSK-LSPA1-T-MP-01752
[6 empty] | Return Date | IFR: 2019-04-01; R1 IFI: 2019-06-19
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0007 | Detail Plot Plan - Zone 1B - Furnaces Utilities |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C; R1 IFF: D
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219; R1 IFF: TPSK-LSPA1-T-MP-02860
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0008 | Detail Plot Plan - Zone 2A - Quench |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C; R1 IFF: D
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219; R1 IFF: TPSK-LSPA1-T-MP-02860
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0009 | Detail Plot Plan - Zone 2B - C3 Hydrogenation |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C; R1 IFF: D
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219; R1 IFF: TPSK-LSPA1-T-MP-02860
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0010 | Detail Plot Plan - Zone 2C - Hot Fractionation-GHU Unit |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0011 | Detail Plot Plan - Zone 2D - Process Cold Compressor |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C; R1 IFF: D
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219; R1 IFF: TPSK-LSPA1-T-MP-02860
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0012 | Detail Plot Plan - Zone 2E - Cracked Gas Compressor |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C; R1 IFF: D
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219; R1 IFF: TPSK-LSPA1-T-MP-02860
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0013 | Detail Plot Plan - Zone 3A - Butadiene Extraction Unit |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFD: 2019-09-17; R1 IFF: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-07-23; R1 IFF: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0014 | Detail Plot Plan - Zone 5F HP And Polyolefins Flares Unit |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFD: 2019-09-17; R1 IFF: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-03-13; R1 IFI: 2019-08-21; R1 IFF: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-03-13; R1 IFI: 2019-08-21
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01031; R1 IFI: TPSK-LSPA1-T-MP-02460
[6 empty] | Return Date | IFR: 2019-04-01; R1 IFI: 2019-09-16
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0015 | Detail Plot Plan - Zone 5T - Cooling Water Unit |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0016 | Detail Plot Plan - Zone 5U - Utilities |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0017 | Detail Plot Plan - Zone 5W Waste Water Treatment |  |  | Purpose** | IFR | IBD | IBD | IDD | IFC
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C
[6 empty] | Issue Plan | IFR: 2019-03-19; R1 IFI: 2019-05-02; R1 IFF: 2019-09-17; R1 IMP: 2020-04-01
[6 empty] | Revised Plan | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IMP: 2020-04-01
[6 empty] | Issue Actual | IFR: 2019-02-15; R1 IFI: 2019-05-29; R1 IFD: 2019-07-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00871; R1 IFI: TPSK-LSPA1-T-MP-01752; R1 IFD: TPSK-LSPA1-T-MP-02219
[6 empty] | Return Date | IFR: 2019-03-15; R1 IFI: 2019-06-19; R1 IFD: 2019-08-22
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2P06-0020 | General Key Plan |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0021 | Detail Key Plan Zone 0M - Metering Station |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-09-28; R1 IFI: 2019-10-29; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-09-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01468
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0022 | Detail Key Plan - Zone 0P - Main Pipe Rack |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0023 | DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-10-29; R1 IFI: 2019-10-29; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0024 | Detail Key Plan - Zone 1A - Furnaces |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0025 | Detail Key Plan - Zone 1B - Furnaces Utilities |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0026 | Detail Key Plan - Zone 2A - Quench |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0027 | Detail Key Plan - Zone 2B - C3 Hydrogenation |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0028 | Detail Key Plan - Zone 2C - Hot Fractionation-GHU Unit |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0029 | Detail Key Plan - Zone 2D - Process Cold Compressor |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0030 | Detail Key Plan - Zone 2E - Cracked Gas Compressor |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0031 | Detail Key Plan - Zone 3 A Butadiene Extraction Unit |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-06-18; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-06-18; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01904; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-07-04
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0032 | DETAIL KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-10-29; R1 IFI: 2019-10-29; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0033 | DETAIL KEY-PLAN FLARE DETAIL |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-10-29; R1 IFI: 2019-10-29; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0034 | Detail Key Plan - Zone 5T - Cooling Water Unit |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0035 | Detail Key Plan - Zone 5U - Utilities |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19; R1 IFI: 2019-08-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P06-0036 | Detail Key Plan - Zone 5W - Waste Water Treatment |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD; R1 IFF: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-03-29; R1 IFI: 2019-05-09; R1 IFD: 2019-09-30; R1 IFF: 2020-04-20
[6 empty] | Revised Plan | IFR: 2019-05-31; R1 IFI: 2019-07-24; R1 IFD: 2019-11-15; R1 IFF: 2020-04-20
[6 empty] | Issue Actual | IFR: 2019-05-31; R1 IFI: 2019-07-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01767; R1 IFI: TPSK-LSPA1-T-MP-02242
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0040 | UTILITY STATION PLOT PLAN MAIN PIPE RACK |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0041 | UTILITY STATION PLOT PLAN FURNACES AUXILIARIES |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0042 | UTILITY STATION PLOT PLAN QUENCH |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0043 | UTILITY STATION PLOT PLAN C3 HYDROGENATION |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0044 | UTILITY STATION PLOT PLAN HOT FRACTIONATION / GHU UNIT |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0045 | UTILITY STATION PLOT PLAN COLD COMPRESSORS |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0046 | UTILITY STATION PLOT PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0047 | UTILITY STATION PLOT PLAN BUTADIENE EXTRACTION UNIT |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0048 | UTILITY STATION PLOT PLAN FLARE UNIT |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0049 | UTILITY STATION PLOT PLAN COOLING WATER UNIT |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0050 | UTILITY STATION PLOT PLAN UTILITIES |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0051 | UTILITY STATION PLOT PLAN WASTE WATER TREATMENT UNIT |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0060 | STEAM TRACING MANIFOLDS LOCATION PLAN MAIN PIPE RACK |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0061 | STEAM TRACING MANIFOLDS LOCATION PLAN QUENCH |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0062 | STEAM TRACING MANIFOLDS LOCATION PLAN C3 HYDROGENATION |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0063 | STEAM TRACING MANIFOLDS LOCATION PLAN HOT FRACTIONATION / GHU UNIT |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0064 | STEAM TRACING MANIFOLDS LOCATION PLAN COLD COMPRESSORS |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0065 | STEAM TRACING MANIFOLDS LOCATION PLAN CRACKED GAS COMPRESSOR / DE-PROPANIZER 7 C2 HYDROGENATION |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0066 | STEAM TRACING MANIFOLDS LOCATION PLAN BUTADIENE EXTRACTION UNIT |  |  | Purpose** | IFR: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2020-09-01
[6 empty] | Revised Plan | IFR: 2020-09-01
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0070 | GAD KEY PLAN - ZONE 0P - MAIN PIPE RACK |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0071 | GAD KEY-PLAN METERING STATION |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0072 | GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR E |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0073 | GAD KEY PLAN - ZONE 1B - FURNACES UTILITIES |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0074 | GAD KEY PLAN - ZONE 2A - QUENCH |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0075 | GAD KEY PLAN - ZONE 2B - C3 HYDROGENATION |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0076 | GAD KEY PLAN - ZONE 2C - HOT FRACTIONATION GHU |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0077 | GAD KEY PLAN - ZONE 2D - PROCESS COLD COMPRESSOR |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0078 | GAD KEY PLAN - ZONE 2E - CRACKED GAS COMPRESSOR |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0079 | GAD KEY PLAN - ZONE 3A - BUTADIENE EXTRACTION |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0080 | GAD KEY-PLAN ELECTRICAL SUB-STATION & FAR C |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0081 | GAD KEY PLAN - ZONE 5F - HP & POLYOLEFINS FLARES |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0082 | GAD KEY-PLAN FLARE LINES ROUTING |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-0083 | GAD KEY PLAN - ZONE 5T - COOLING WATER |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0084 | GAD KEY PLAN - ZONE 5U - UTILITIES |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0085 | GAD KEY PLAN - ZONE 5W - WASTE WATER TREATMENT |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2020-11-20; R1 IFI: 2021-01-30
[6 empty] | Revised Plan | IFR: 2019-04-18; R1 IFI: 2021-01-30
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-0086 | GAD KEY PLAN - ZONE 1A - FURNACES |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-18
[6 empty] | Issue Actual | IFR: 2019-04-18
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-MP-01394
[6 empty] | Return Date | IFR: 2019-06-14
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-2000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0C |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5T |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2901 | MISC ENGINEERED SUPPORTS |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-2902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  | Purpose** | IFR: IFD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; R1 IFI: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2019-12-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 0P |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3901 | MISC ENGINEERED SUPPORTS |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-3902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  | Purpose** | IFR: IFD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; R1 IFI: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2019-12-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5F |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4901 | MISC ENGINEERED SUPPORTS |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-4902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  | Purpose** | IFR: IFD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; R1 IFI: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2019-12-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2C |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5126 | Piping Specialty Item - Datasheet - Vent Silencer - PSV-5134 A-H- Outlet - 10-SP-51026 |  | Class 2 | Purpose** | IFR: CAN
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-10
[6 empty] | Issue Actual | IFR: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02594
[6 empty] | Return Date | IFR: 2019-10-01
Owner Cmmt* | bar: IFR
| MP | OL1-2P06-5500 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 3A |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5901 | MISC ENGINEERED SUPPORTS |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-5902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  | Purpose** | IFR: IFD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; R1 IFI: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2019-12-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 1B |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6901 | MISC ENGINEERED SUPPORTS |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-11-19; R1 IFI: 2019-12-17
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-6902 | ENGINEERED SUPPORTS FOR SPRING HANGERS |  |  | Purpose** | IFR: IFD; R1 IFI: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-09; R1 IFI: 2019-08-06
[6 empty] | Revised Plan | IFR: 2019-10-31; R1 IFI: 2019-12-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2A |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7200 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2B |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7400 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2D |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7600 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 2E |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-7800 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5U |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P06-8000 | SPECIAL AUX.PIPE SUPP.COLLECTION - ZONE 5W |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P07 Piping certification, inspection and test record
Category Code: P08 Piping Material Take-off (MTO)
| MP | OL1-2P08-2001 | PIPING MTO |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-07
[6 empty] | Revised Plan | IFR: 2020-05-07
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P09 Painting Material Take-off (MTO)
Category Code: P10 Insulation Material Take-off (MTO)
| MP | OL1-2P10-10XX | FURNACE 10-H-1100 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 LARGE BORE ISOMETRIC DRAWINGS) |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-10YY | FURNACE 10-H-1100 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1100 SMALL BORE ISOMETRIC DRAWINGS) |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-20XX | FURNACE 10-H-1200 LARGE BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 LARGE BORE ISOMETRIC DRAWINGS) |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-20YY | FURNACE 10-H-1200 SMALL BORE PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1200 SMALL BORE ISOMETRIC DRAWINGS) |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-30XX | FURNACE 10-H-1300 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1300 ISOMETRIC DRAWINGS) |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-40XX | FURNACE 10-H-1400 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1400 ISOMETRIC DRAWINGS) |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-50XX | FURNACE 10-H-1500 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1500 ISOMETRIC DRAWINGS) |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-60XX | FURNACE 10-H-1600 PIPING ISOMETRICS (THIS WILL INCLUDE ALL FURNACE 10-H-1600 ISOMETRIC DRAWINGS) |  |  | Purpose** | IFR: IFI
Rev.
[6 empty] | Issue Plan | IFR: 2020-04-30
[6 empty] | Revised Plan | IFR: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAA | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAB | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAC | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAD | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAE | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAF | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAG | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAH | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAI | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAJ | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAK | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAL | ISO.SKETCHES PIPE RACK / SLEEPER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXAM | ISO.SKETCHES PIPE-RACK |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXA | ISO.SKETCHES |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXB | ISO.SKETCHES |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXC | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXD | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXE | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXF | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXG | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXH | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXI | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXJ | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXK | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXL | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXM | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXN | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXO | ISO.SKETCHES AROUND EQUIPMENT |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P10-XXXP | ISO.SKETCHES CWR HEADER |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
[6 empty] | Revised Plan | IFR: 2020-08-30; R1 IFI: 2020-10-08; R1 IFD: 2021-02-18
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P20 Aboveground Piping General Arrangement Drawings
| MP | OL1-2P20-0101 | GAD BATTERY LIMIT OL1-A |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0102 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0200 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0300 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-0400 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-1001 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2101 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2201 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2301 | GAD BATTERY LIMIT OU1-A |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2302 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2401 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-2501 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-3001 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5101 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5300 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5401 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P20-5501 | GAD (N...) |  |  | Purpose** | IFR: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2021-05-30
[6 empty] | Revised Plan | IFR: 2021-05-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P21 Underground Piping General Arrangement Drawings
Category Code: P22 Aboveground Piping Isometric Drawings
Category Code: P23 Underground Piping Isometric Drawings
| CV | OL1-2P23-0001 | ISO PRESSURE SKETCH UG - PIPING ZONE 100C |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0002 | ISO PRESSURE SKETCH UG - PIPING ZONE100M |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0003 | ISO PRESSURE SKETCH UG - PIPING ZONE 100S |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0004 | ISO PRESSURE SKETCH UG - PIPING ZONE 1A/B |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0005 | ISO PRESSURE SKETCH UG - PIPING ZONE 102A |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0006 | ISO PRESSURE SKETCH UG - PIPING ZONE 102B |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0007 | ISO PRESSURE SKETCH UG - PIPING ZONE 102C |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0008 | ISO PRESSURE SKETCH UG - PIPING ZONE 102D |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0009 | ISO PRESSURE SKETCH UG - PIPING ZONE 102E |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0010 | ISO PRESSURE SKETCH UG - PIPING ZONE 103A |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0011 | ISO PRESSURE SKETCH UG - PIPING ZONE 103S |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0012 | ISO PRESSURE SKETCH UG - PIPING ZONE 105F |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0013 | ISO PRESSURE SKETCH UG - PIPING ZONE 105T |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0014 | ISO PRESSURE SKETCH UG - PIPING ZONE 105U |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-0015 | ISO PRESSURE SKETCH UG - PIPING ZONE 105W |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1001 | ISO GRAVITY SKETCH UG (OWS) - ZONE 100C |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1002 | ISO GRAVITY SKETCH UG (OWS) - ZONE 100M |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1003 | ISO GRAVITY SKETCH UG (OWS) - ZONE 100S |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1004 | ISO GRAVITY SKETCH UG (OWS) - ZONE 101B |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1005 | ISO GRAVITY SKETCH UG (OWS) - ZONE 102A |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1006 | ISO GRAVITY SKETCH UG (OWS) - ZONE 102B |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1007 | ISO GRAVITY SKETCH UG (OWS) - ZONE 102C |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1008 | ISO GRAVITY SKETCH UG (OWS) - ZONE 102D |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1009 | ISO GRAVITY SKETCH UG (OWS) - ZONE 102E |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1010 | ISO GRAVITY SKETCH UG (OWS) - ZONE 103A |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1011 | ISO GRAVITY SKETCH UG (OWS) - ZONE 103S |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1012 | ISO GRAVITY SKETCH UG (OWS) - ZONE 105F |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1013 | ISO GRAVITY SKETCH UG (OWS) - ZONE 105T |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1014 | ISO GRAVITY SKETCH UG (OWS) - ZONE 105U |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2P23-1015 | ISO GRAVITY SKETCH UG (OWS) - ZONE 105W |  |  | Purpose** | IFR: IFC1; R1 IFI: IFC2; R1 IFD: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
[6 empty] | Revised Plan | IFR: 2020-05-30; R1 IFI: 2020-10-06; R1 IFD: 2020-12-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P25 Pipe support drawing
| MP | OL1-2P25-0085 | Standard Auxiliary Piping Support Collection |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-01-31; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-02-20
[6 empty] | Issue Actual | IFR: 2019-02-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00896
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
Category Code: P30 3D Model Review File
| MP | OL1-2P30-0002 | AUX.PIPE SUPP.LIST & BILL OF MTL - COOLING WATER UNIT |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2; R1 IFF: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0003 | AUX.PIPE SUPP.LIST & BILL OF MTL - MAIN PIPE RACK |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2; R1 IFF: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0004 | AUX.PIPE SUPP.LIST & BILL OF MTL - OFF-SITES |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2; R1 IFF: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0005 | AUX.PIPE SUPP.LIST & BILL OF MTL - WASTE WATER TREATMENT |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2; R1 IFF: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0006 | AUX.PIPE SUPP.LIST & BILL OF MTL - FURNACES UTILITIES |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2; R1 IFF: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0007 | AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION 1 & 2 |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2; R1 IFF: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0008 | AUX.PIPE SUPP.LIST & BILL OF MTL - FRACTIONATION 3 & BUTADIENE EXTRACTION |  |  | Purpose** | IFR: IFC; R1 IFI: IFC1; R1 IFD: IFC2; R1 IFF: IFC3
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
[6 empty] | Revised Plan | IFR: 2020-05-21; R1 IFI: 2020-07-29; R1 IFD: 2020-11-16; R1 IFF: 2021-03-04
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P30-0014 | Model Review Report Furnace Island Action List 30 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IFR
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-12
[6 empty] | Issue Actual | IFR: 2019-04-12; R1 IFI: 2019-05-31; R1 IFD: 2019-07-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01331; R1 IFI: TPSK-LSPA1-T-MP-01782; R1 IFD: TPSK-LSPA1-T-MP-02107
[6 empty] | Return Date | IFR: 2019-05-27
Owner Cmmt* | bar: IFR
| MP | OL1-2P30-0020 | Model Review Report Metering Station And General Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 0; R1 IFI: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-28
[6 empty] | Issue Actual | IFR: 2019-09-28; R1 IFI: 2019-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; R1 IFI: TPSK-LSPA1-T-MP-02805
[6 empty] | Return Date | IFR: 2019-10-10
Owner Cmmt* | bar: IFR
| MP | OL1-2P30-0022 | Model Review Report Furnace Utilities And Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 0; R1 IFI: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; R1 IFI: TPSK-LSPA1-T-MP-02805
[6 empty] | Return Date | IFR: 2019-10-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P30-0024 | Model Review Report C3 Hydrogenation Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 0; R1 IFI: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; R1 IFI: TPSK-LSPA1-T-MP-02805
[6 empty] | Return Date | IFR: 2019-10-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P30-0025 | Model Review Report Hot Fractioning Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 1; R1 IFI: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02805; R1 IFI: TPSK-LSPA1-T-MP-02145
[6 empty] | Return Date | R1 IFI: 2019-10-09
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P30-0026 | Model Review Report Cold Compression Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 1; R1 IFI: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02805; R1 IFI: TPSK-LSPA1-T-MP-02145
[6 empty] | Return Date | R1 IFI: 2019-10-09
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P30-0027 | Model Review Report Cracked Gas Compressor Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 1; R1 IFI: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02805; R1 IFI: TPSK-LSPA1-T-MP-02145
[6 empty] | Return Date | R1 IFI: 2019-10-09
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P30-0028 | Model Review Report Butadeine Extraction Unit Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 1; R1 IFI: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02805; R1 IFI: TPSK-LSPA1-T-MP-02145
[6 empty] | Return Date | R1 IFI: 2019-10-09
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P30-0029 | Model Review Report Flare Unit Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 1; R1 IFI: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02805; R1 IFI: TPSK-LSPA1-T-MP-02145
[6 empty] | Return Date | R1 IFI: 2019-10-09
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P30-0030 | Model Review Report Cooling Water Unit Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 1; R1 IFI: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02805; R1 IFI: TPSK-LSPA1-T-MP-02145
[6 empty] | Return Date | R1 IFI: 2019-10-09
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P30-0031 | Model Review Report Utilities And Flare KO Drum Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 1; R1 IFI: 0
Issue Plan
Revised Plan
[6 empty] | Issue Actual | R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02805; R1 IFI: TPSK-LSPA1-T-MP-02145
[6 empty] | Return Date | R1 IFI: 2019-10-09
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P30-0032 | Model Review Report Waste Water Treatment Unit Action List 30 Per Cent |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 0; R1 IFI: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-15
[6 empty] | Issue Actual | IFR: 2019-07-15; R1 IFI: 2019-07-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02145; R1 IFI: TPSK-LSPA1-T-MP-02805
[6 empty] | Return Date | IFR: 2019-10-09
Owner Cmmt* | bar: IFR
| MP | OL1-2P30-0033 | Model Review Report Furnace Island Action List 60 |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFR
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-17
[6 empty] | Issue Actual | IFR: 2019-09-17; R1 IFI: 2019-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02642; R1 IFI: TPSK-LSPA1-T-MP-02704
Return Date
Owner Cmmt*
Category Code: P40 Piping Generic Lists
| MP | OL1-2P40-0008 | STEAM TRACING MANIFOLD LIST |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-12; R1 IFI: 2020-03-20; R1 IFD: 2020-04-30
[6 empty] | Revised Plan | IFR: 2019-11-12; R1 IFI: 2020-03-20; R1 IFD: 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: P71 Appraisal Report for Consultancy Service
Category Code: P72 Appraisal Report for EPC Contractor Work
Category Code: P73 Appraisal Report for Vendor/Supplier
Category Code: P90 Vendor Document/drawings
Category Code: P91 Index/List
| MP | OL1-2P91-1001 | Line Designation Table - Feed Preparation and Furnaces |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-02 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-05-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01541
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-1101 | Line Designation Table – Recycle Gas Cracking Furnace 10-H-1100 |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IFD; R1 IFF: IFF
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-01-10; R1 IFI: 2019-02-15; R1 IFD: 2019-06-10; R1 IFF: 2019-09-03
[6 empty] | Revised Plan | R1 IFI: 2019-02-27; R1 IFF: 2019-11-04
[6 empty] | Issue Actual | R1 IFI: 2019-02-27
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-PE-00933
[6 empty] | Return Date | R1 IFI: 2019-05-15
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-1201 | Line Designation Table - Liquid Cracking Furnace 10-H-1200 |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IFD; R1 IFF: IFF
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-01-10; R1 IFI: 2019-02-15; R1 IFD: 2019-06-10; R1 IFF: 2019-09-03
[6 empty] | Revised Plan | R1 IFI: 2019-02-27; R1 IFF: 2019-11-04
[6 empty] | Issue Actual | R1 IFI: 2019-02-27
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-PE-00934
[6 empty] | Return Date | R1 IFI: 2019-05-15
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-1901 | Line Designation Table - Furnace Auxiliaries |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-17
[6 empty] | Issue Actual | IFR: 2019-04-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01375
[6 empty] | Return Date | IFR: 2019-05-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P91-2001 | Line Designation Table - Quench Oil |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-24 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-04-24
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01450
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-2101 | Line Designation Table - Quench Water - Dilution Steam |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-29 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-04-29
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01497
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-2201 | Line Designation Table - Cracked Gas Compression |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-17 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-04-17
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP -01375
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-2301 | Line Designation Table - Caustic and Spent Caustic Treatment |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-17 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-04-17
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP -01375
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-2401 | Line Designation Table - Dehydration - Regen -Deprop - C2 Hydrog |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-02 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-05-02
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01531
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-2501 | Line Designation Table - Cold Fractionation |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-25 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-04-25
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01466
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-2601 | Line Designation Table - Hot Fractionation |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-14 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-05-14
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01651
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-2701 | Line Designation Table - GHU & C4-C5 Hydrog |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-14 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-05-14
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP -01656
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-2801 | Line Designation Table - Refrigeration System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-04-29 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-04-29
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01497
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-2901 | Line Designation Table - Ethylene Auxiliaries |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-09 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-05-09
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01620
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-3001 | Line Designation Table - Butadiene Extraction Unit |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-06-10 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-06-10
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01795
[6 empty] | Return Date | R1 IFI: 2019-06-21
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-3101 | Line Designation Table - Butadiene Extraction Unit Utilities |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01795
[6 empty] | Return Date | IFR: 2019-06-21
Owner Cmmt* | bar: IFR
| MP | OL1-2P91-3901 | Line Designation Table - C4 Unit Auxiliaries |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-10
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01795
[6 empty] | Return Date | IFR: 2019-06-21
Owner Cmmt* | bar: IFR
| MP | OL1-2P91-5001 | Line Designation Table - Water System - Treated - Potable - Demin |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-09 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-05-09
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP-01620
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-5101 | Line Designation Table - BFW - Steam - Steam Condensate System |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-14
[6 empty] | Issue Actual | IFR: 2019-05-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP -01656
[6 empty] | Return Date | IFR: 2019-05-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P91-5201 | Line Designation Table - Fuel System |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01627
[6 empty] | Return Date | IFR: 2019-05-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P91-5301 | Line Designation Table - Cooling Water |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-14 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-05-14
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP -01656
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-5401 | Line Designation Table - Plant Air - Instrument Air - Nitrogen |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01627
[6 empty] | Return Date | IFR: 2019-05-24
Owner Cmmt* | bar: IFR
| MP | OL1-2P91-5501 | Line Designation Table - Vent Gas and Flare System |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-14 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-05-14
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP -01648
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-5601 | Line Designation Table - Wastewater |  |  | Purpose** | IFR | IBD | IDD1 | IDD2 | IFC1 | IFC2 | IFC3
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | 2019-03-19 | 2019-03-26 | 2019-09-06 | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Revised Plan |  | 2019-05-14 |  | 2019-11-26 | 2020-02-21 | 2020-05-13 | 2020-08-05
[6 empty] | Issue Actual | R1 IFI: 2019-05-14
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-MP -01656
[6 empty] | Return Date | R1 IFI: 2019-05-24
Owner Cmmt* | bar: R1 IFI
| MP | OL1-2P91-5701 | Line Designation Table - Fire Water |  |  | Purpose** | IFR | IDD | IFC1 | IFC2 | IFC3
Rev. | bar: IFR
[6 empty] | Issue Plan | 2019-06-10 | 2019-10-30 | 2020-05-06 | 2020-05-29 | 2020-06-08
[6 empty] | Revised Plan | 2019-06-10 | 2019-10-30 | 2020-05-06 | 2020-05-29 | 2020-06-08
[6 empty] | Issue Actual | IFR: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01841
[6 empty] | Return Date | IFR: 2019-06-27
Owner Cmmt* | bar: IFR
| MP | OL1-2P91-5901 | Line Designation Table - Supporting Utilities Auxiliaries |  | Class 2 | Purpose** | IFR: IBD
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-09
[6 empty] | Issue Actual | IFR: 2019-05-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01620
[6 empty] | Return Date | IFR: 2019-05-24
Owner Cmmt* | bar: IFR
Category Code: P92 Procedures & Standards
| MP | OL1-2P92-0001 | Piping MTO Assembly Collection |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-28; R1 IFI: 2019-03-17
[6 empty] | Revised Plan | IFR: 2019-06-20; R1 IFI: 2019-10-15
[6 empty] | Issue Actual | IFR: 2019-06-20; R1 IFI: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01927; R1 IFI: TPSK-LSPA1-T-MP-02820
[6 empty] | Return Date | IFR: 2019-07-10
Owner Cmmt* | bar: IFR
| MP | OL1-2P92-0002 | Piping Design Standard Drawings |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-08; R1 IFI: 2018-11-16
[6 empty] | Issue Actual | IFR: 2018-08-08; R1 IFI: 2018-11-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00012; R1 IFI: TPSK-LSPA1-T-MP-00325
[6 empty] | Return Date | IFR: 2018-09-26; R1 IFI: 2018-12-07
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P92-0003 | Piping Construction Drawing |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: CAN
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-08; R1 IFI: 2018-11-16
[6 empty] | Issue Actual | IFR: 2018-08-08; R1 IFI: 2018-11-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00012; R1 IFI: TPSK-LSPA1-T-MP-00325
[6 empty] | Return Date | IFR: 2018-09-26; R1 IFI: 2018-12-07
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P92-0004 | Job Construction Specification for Bolted Flanged Joints Assembly |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFI: 2019-05-06
[6 empty] | Revised Plan | IFR: 2019-05-13; R1 IFI: 2019-10-30
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01635
[6 empty] | Return Date | IFR: 2019-05-31
Owner Cmmt* | bar: IFR
| MP | OL1-2P92-0007 | Construction Specification For Piping Prefabrication Erection And Non Destructive Examination |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-16; R1 IFI: 2019-06-15
[6 empty] | Revised Plan | IFR: 2019-02-26; R1 IFI: 2019-05-24
[6 empty] | Issue Actual | IFR: 2019-02-26; R1 IFI: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00917; R1 IFI: TPSK-LSPA1-T-MP-01726
[6 empty] | Return Date | IFR: 2019-05-07; R1 IFI: 2019-06-14
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P92-0008 | Job Construction Specification For Pressure Testing |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-16; R1 IFI: 2019-06-15
[6 empty] | Revised Plan | IFR: 2019-03-26; R1 IFI: 2019-05-24
[6 empty] | Issue Actual | IFR: 2019-03-26; R1 IFI: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01136; R1 IFI: TPSK-LSPA1-T-MP-01726
[6 empty] | Return Date | IFR: 2019-04-11; R1 IFI: 2019-06-14
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2P92-0012 | SPECIAL TECH.SPEC.PIP.PREFAB. & ERE. |  |  | Purpose** | IFR: IFQ; R1 IFI: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-01-30; R1 IFI: 2019-03-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2P92-0013 | Piping Spooling Into 3D Model |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-10-10
[6 empty] | Issue Actual | IFR: 2019-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02796
Return Date
Owner Cmmt*
| MP | OL1-2P92-0014 | Spooling Activity Definition |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-10-10
[6 empty] | Issue Actual | IFR: 2019-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02796
Return Date
Owner Cmmt*
Category Code: P93 Policy , Guidelines & Memo
Category Code: P94 Forms & Templates
Category Code: P95 Progress/Status Reports
Category Code: Q07 Quality Audit Reports
Category Code: Q10 QC Record and Report for Civil work (Engineerig and Procurement)
Category Code: Q11 QC Record and Report for Building work (Engineerig and Procurement)
Category Code: Q12 QC Record and Report for Steel Structure work (Engineerig and Procurement)
Category Code: Q13 QC Record and Report for Mechanical work (Engineerig and Procurement)
Category Code: Q14 QC Record and Report for Piping work (Engineerig and Procurement)
Category Code: Q15 QC Record and Report for Fire Fighting work (Engineerig and Procurement)
Category Code: Q16 QC Record and Report for Electrical work (Engineerig and Procurement)
Category Code: Q17 QC Record and Report for Instrumentation work (Engineerig and Procurement)
Category Code: Q20 QC Record and Report for Civil work (construction)
| QM | OL1-2Q20-0001 | Quality Control Plan Civil Works-Fencing |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00488
[6 empty] | Return Date | IFR: 2019-02-25
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0002 | Quality Control Plan Civil Works-Bored Cast In Situ Piles |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0003 | Quality Control Plan Civil Works-Continuous Flight Auger Piles |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0004 | Quality Control Plan Civil Works-Concrete Precast Driven Piles |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0005 | Quality Control Plan Civil Works-Earth Moving |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0006 | Quality Control Plan Civil Works-Asphalt Roads And Yards |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0007 | Quality Control Plan U-G Civil Works-Sewers |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0008 | Quality Control Plan Non Metallic Pressure Piping Installation - Above and Underground |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-11
[6 empty] | Issue Actual | IFR: 2019-01-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00625
Return Date
Owner Cmmt*
| QM | OL1-2Q20-0009 | Quality Control Plan Civil Works-Reinforced Concrete For Foundation-Elevation Structures And Basins |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0010 | Quality Control Plan Civil Works-Prefabrication of Concrete Elements |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0011 | Quality Control Plan Precast Pipe-Rack Erection |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0012 | Quality Control Plan Civil Works-Tank Rings Foundations |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0013 | Quality Control Plan Above Ground Civil Works- Concrete Elements Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0014 | Quality Control Plan Civil Works-Rigid Paving |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0015 | Quality Control Plan U-G Civil Works-Installation of Concrete Pits Cable Duct Banks Trenches-Ditches Cable Trenches Direct Buried Box Culverts and Lighting Poles Foundations |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0016 | Quality Control Plan Civil Works-Concrete Structure for Cooling Tower |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0017 | Quality Control Plan Civil Works-Fire Proofing |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0018 | Quality Control Plan Civil Works-Grouting |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q20-0019 | Quality Control Plan Concrete Protective Coating |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
Category Code: Q21 QC Record and Report for Building work (construction)
| QM | OL1-2Q21-0001 | Quality Control Plan Building -Concrete And Masonry- |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01596
[6 empty] | Return Date | IFR: 2019-06-12
Owner Cmmt* | bar: IFR
Category Code: Q22 QC Record and Report for Steel Structure work (construction)
| QM | OL1-2Q22-0001 | Quality Control Plan Steel Structures Erection |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00729
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| QM | OL1-2Q22-0002 | Quality Control Plan Secondary Steel Structures Erection - Ladders Platforms Walkways Handrails Gratings |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00735
[6 empty] | Return Date | IFR: 2019-03-18
Owner Cmmt* | bar: IFR
Category Code: Q23 QC Record and Report for Mechanical work (construction)
| QM | OL1-2Q23-0001 | Quality Control Plan Fixed Roof Tanks Erection |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-28
[6 empty] | Issue Actual | IFR: 2019-02-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00942
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0002 | Quality Control Plan Floating Roof Tanks Erection |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-28
[6 empty] | Issue Actual | IFR: 2019-02-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00942
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0003 | Quality Control Plan Cryogenic Tanks Erection |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-28
[6 empty] | Issue Actual | IFR: 2019-02-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00942
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0006 | Quality Control Plan Static Equipment Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0007 | Quality Control Plan Package Furnace - Site Assembled - Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0008 | Quality Control Plan Flare System Erection |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0009 | Quality Control Plan Refractory Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0010 | Quality Control Plan Machinery Installation - Centrifugal and Rotary Pumps |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0011 | Quality Control Plan Machinery Installation - Blower and Fans |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0012 | Quality Control Plan Machinery Installation - Centrifugal Compressors |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0013 | Quality Control Plan Machinery Installation - Reciprocating Compressors |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0014 | Quality Control Plan Machinery Installation - Mixers and Agitators |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0015 | Quality Control Plan Elevator Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0016 | Quality Control Plan Equipment Internals Installation - Trays |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0017 | Quality Control Plan Equipment Internals Installation - Distributors-Grids-Demisters-etc |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0018 | Quality Control Plan Air Coolers Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-20
[6 empty] | Issue Actual | IFR: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01091
Return Date
Owner Cmmt*
| QM | OL1-2Q23-0019 | Quality Control Plan Cooling Tower Mechanical Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0020 | Quality Control Plan Packages Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0021 | Quality Control Plan Skid Mounted Packages |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
| QM | OL1-2Q23-0022 | Quality Control Plan Bridge Crane Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-11
[6 empty] | Issue Actual | IFR: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01011
[6 empty] | Return Date | IFR: 2019-04-01
Owner Cmmt* | bar: IFR
Category Code: Q24 QC Dossier for Piping work (construction)
| QM | OL1-2Q24-0001 | Quality Control Plan Piping Prefabrication |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
| QM | OL1-2Q24-0002 | Quality Control Plan Piping Support Prefabrication |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
| QM | OL1-2Q24-0003 | Quality Control Plan Piping Erection - Above & Underground |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
| QM | OL1-2Q24-0004 | Quality Control Plan Piping Support Erection |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
| QM | OL1-2Q24-0005 | Quality Control Plan Steam Tracing System |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
| QM | OL1-2Q24-0006 | Quality Control Plan Piping Tie-ins |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
| QM | OL1-2Q24-0007 | Quality Control Plan Piping NDE PWHT Management |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
| QM | OL1-2Q24-0008 | Quality Control Plan Welders Management |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
| QM | OL1-2Q24-0009 | Quality Control Plan Insulation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
| QM | OL1-2Q24-0010 | Quality Control Plan Painting |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00730
[6 empty] | Return Date | IFR: 2019-04-05
Owner Cmmt* | bar: IFR
Category Code: Q25 QC Record and Report for Fire Fighting work (construction)
| QM | OL1-2Q25-0001 | Quality Control Plan Fire Fighting System Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01596
[6 empty] | Return Date | IFR: 2019-06-19
Owner Cmmt* | bar: IFR
Category Code: Q26 QC Record and Report for Electrical work (construction)
| QM | OL1-2Q26-0001 | Quality Control Plan - Electrical Installation - Grounding And Lightning System |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01676
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0002 | Quality Control Plan -Electrical Installation- Substation Equipment |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-24
[6 empty] | Issue Actual | IFR: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01724
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0003 | Quality Control PlanElectrical InstallationPower System |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-03
[6 empty] | Issue Actual | IFR: 2019-06-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01789
[6 empty] | Return Date | IFR: 2019-06-10
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0004 | Quality Control Plan - Electrical Iinstallation - High Voltage Equipment |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01676
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0005 | Quality Control Plan - Electrical Installation-Electrical Heat Tracing System |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-28
[6 empty] | Issue Actual | IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01750
[6 empty] | Return Date | IFR: 2019-06-10
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0006 | Quality Control Plan - Electrical Installation-Cathodic Protection System |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-28
[6 empty] | Issue Actual | IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01750
[6 empty] | Return Date | IFR: 2019-06-10
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0007 | Quality Control PlanElectrical InstallationLighting System |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-28
[6 empty] | Issue Actual | IFR: 2019-05-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01750
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0008 | Quality Control Plan -Electrical Installation- Rotating Equipment |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-24
[6 empty] | Issue Actual | IFR: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01724
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
| QM | OL1-2Q26-0009 | Quality Control Plan Building HVAC -Heating Ventilation And Air Conditioning- System Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01596
[6 empty] | Return Date | IFR: 2019-06-18
Owner Cmmt* | bar: IFR
Category Code: Q27 QC Record and Report for Instrumentation work (construction)
| QM | OL1-2Q27-0001 | Quality Control Plan - Instrumentation And Communication System - Installation Works In Control Room |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
| QM | OL1-2Q27-0002 | Quality Control Plan - Instrumentation And Communication System Installation - Instrument Cables Junction Boxes And Local Panels Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
| QM | OL1-2Q27-0003 | Quality Control Plan - Instrumentation And Communication System Installation - Field Instrumentation Works |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
| QM | OL1-2Q27-0004 | Quality Control Plan - Instrumentation And Communication System Installation - Analyzer Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
| QM | OL1-2Q27-0005 | Quality Control Plan - Instrumentation And Communication System Installation - Telecommunication Systems Installation |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-10
Owner Cmmt* | bar: IFR
| QM | OL1-2Q27-0006 | Quality Control Plan - Instrumentation And Communication System Installation - Package Instrumentation Test |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-13
[6 empty] | Issue Actual | IFR: 2019-05-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01636
[6 empty] | Return Date | IFR: 2019-06-17
Owner Cmmt* | bar: IFR
Category Code: Q30 Shop Inspection Notice (Civil)
Category Code: Q31 Shop Inspection Notice (Mechanical)
Category Code: Q32 Shop Inspection Notice (Piping)
Category Code: Q33 Shop Inspection Notice (Electrical)
Category Code: Q34 Shop Inspection Notice (Instrumentation)
Category Code: Q35 Mechanical certification (Civil)
Category Code: Q36 Mechanical certification (Static)
Category Code: Q37 Mechanical certification (Rotating)
Category Code: Q38 Mechanical certification (Piping))
Category Code: Q40 Site Inspection Notice (Civil)
Category Code: Q41 Site Inspection Notice (Mechanical)
Category Code: Q42 Site Inspection Notice (Piping)
Category Code: Q43 Site Inspection Notice (Electrical)
Category Code: Q44 Site Inspection Notice (Instrumentation)
Category Code: Q60 Inspection and Test Plan (ITP) for Mechanical Work
Category Code: Q61 Inspection and Test Plan (ITP) for Piping Work
Category Code: Q62 Inspection and Test Plan (ITP) for Electrical work
Category Code: Q63 Inspection and Test Plan (ITP)for Instrumentation work
Category Code: Q64 Inspection and Test Plan (ITP) for Civil,Structure and Architecture.
Category Code: Q65 Inspection and Test Plan (ITP) for Mechanical Work (Construction)
Category Code: Q66 Inspection and Test Plan (ITP) for Piping Work (Construction)
Category Code: Q67 Inspection and Test Plan (ITP) for Electrical work (Construction)
Category Code: Q68 Inspection and Test Plan (ITP)for Instrumentation work (Construction)
Category Code: Q69 Inspection and Test Plan (ITP) for Civil,Structure and Architecture (Construction)
Category Code: Q71 Appraisal Report for Consultancy Service
Category Code: Q72 Appraisal Report for EPC Contractor Work
Category Code: Q73 Appraisal Report for Vendor/Supplier
Category Code: Q90 Vendor Document/drawings
Category Code: Q91 Index/List
Category Code: Q92 Procedures & Standards
| QM | OL1-2Q92-0001 | Overall Project Quality Plan |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-24; R1 IFI: 2018-12-17
[6 empty] | Issue Actual | IFR: 2018-09-24; R1 IFI: 2018-12-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00072; R1 IFI: TPSK-LSPA1-T-QM-00512
[6 empty] | Return Date | IFR: 2018-10-12; R1 IFI: 2019-02-11
Owner Cmmt* | bar: IFR to R1 IFI
| QM | OL1-2Q92-0002 | Confidentiality Plan |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-19; R1 IFI: 2019-06-27
[6 empty] | Issue Actual | IFR: 2018-10-19; R1 IFI: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00199; R1 IFI: TPSK-LSPA1-T-QM-01998
[6 empty] | Return Date | R1 IFI: 2019-09-23
Owner Cmmt* | bar: R1 IFI
| QM | OL1-2Q92-0003 | NON CONFORMITY MANAGEMENT PROCEDURE |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28; R1 IFI: 2019-06-27
[6 empty] | Issue Actual | IFR: 2019-01-28; R1 IFI: 2019-06-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00733; R1 IFI: TPSK-LSPA1-T-QM-01998
[6 empty] | Return Date | IFR: 2019-03-11; R1 IFI: 2019-07-22
Owner Cmmt* | bar: IFR to R1 IFI
| QM | OL1-2Q92-0005 | Site Quality Control Plan |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-02157
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| QM | OL1-2Q92-0006 | Site Inspection Coordination Procedure - Construction Precommissioning And Commissioning |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-24
[6 empty] | Issue Actual | IFR: 2019-06-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01956
[6 empty] | Return Date | IFR: 2019-10-10
Owner Cmmt* | bar: IFR
| QM | OL1-2Q92-0007 | Preparation Of Construction Quality Control Dossier |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-25
[6 empty] | Issue Actual | IFR: 2019-06-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01970
[6 empty] | Return Date | IFR: 2019-07-22
Owner Cmmt* | bar: IFR
| QM | OL1-2Q92-0008 | Quality Control Plan Material Management and Warehouse |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-07
[6 empty] | Issue Actual | IFR: 2019-02-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-00818
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0009 | Piping System Pressure Test And Test Package Management Procedure |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-07-17
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-02157
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| QM | OL1-2Q92-0010 | Site Material Management |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01599
[6 empty] | Return Date | IFR: 2019-06-20
Owner Cmmt* | bar: IFR
| QM | OL1-2Q92-0011 | Job Construction Specification For Welders Management |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-04
[6 empty] | Issue Actual | IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01236
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0012 | Job Construction Specification For Welding Activities Management |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-04
[6 empty] | Issue Actual | IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01236
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0013 | Job Construction Specification For Piping Material Traceability |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-04
[6 empty] | Issue Actual | IFR: 2019-04-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01236
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0014 | Job Construction Specification For Bolted Flange Joint Assembly Management During Construction Precommissioning And Commissioning |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-11
[6 empty] | Issue Actual | IFR: 2019-04-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01306
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0015 | Job Construction Specification For Instrument Installation |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-06-25
[6 empty] | Issue Actual | IFR: 2019-06-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01973
[6 empty] | Return Date | IFR: 2019-07-15
Owner Cmmt* | bar: IFR
| QM | OL1-2Q92-0017 | Job Construction Specification For Material Receiving And Warehousting |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-08
[6 empty] | Issue Actual | IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01597
[6 empty] | Return Date | IFR: 2019-06-20
Owner Cmmt* | bar: IFR
| QM | OL1-2Q92-0018 | Job Construction Specification For Static Equipment and Trays-Internals Installation |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-03
[6 empty] | Issue Actual | IFR: 2019-04-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01237
Return Date
Owner Cmmt*
| QM | OL1-2Q92-0019 | Job Construction Specification For Machinery And Air Coolers Installation |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-11
[6 empty] | Issue Actual | IFR: 2019-04-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-QM-01305
Return Date
Owner Cmmt*
Category Code: Q93 Policy , Guidelines,& Memo
Category Code: Q94 Forms & Templates
Category Code: Q95 Progress/Status Reports
Category Code: Q96 Quality Audit Reports
Category Code: Q97 Non-Conformance Record
Category Code: Q98 Addition Vendors/Subcontractors Assessment and Prequalification Report
Category Code: R01 Process Specification (PE)
Category Code: R02 Civil Specification (CV)
| CV | OL1-2R02-0001 | Job Design Specification For Underground Systems |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-24; R1 IFI: 2019-03-16
[6 empty] | Revised Plan | IFR: 2018-09-27; R1 IFI: 2019-03-07
[6 empty] | Issue Actual | IFR: 2018-09-27; R1 IFI: 2019-03-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00087; R1 IFI: TPSK-LSPA1-T-CV-00994
[6 empty] | Return Date | IFR: 2018-11-02; R1 IFI: 2019-03-15
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2R02-0002 | Geotechnical Interpretative Report |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-02-15; R1 IFI: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-05-08; R1 IFI: 2019-11-07
[6 empty] | Issue Actual | IFR: 2019-05-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01598
[6 empty] | Return Date | IFR: 2019-05-31
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0004 | Job Design Specification For Foundations And Structures |  |  | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
[6 empty] | Issue Plan | IFR: 2018-09-25; R1 IFI: 2019-01-31
[6 empty] | Revised Plan | IFR: 2018-09-27; R1 IFI: 2019-02-19
[6 empty] | Issue Actual | IFR: 2018-09-27; R1 IFI: 2019-02-19; R1 IFD: 2019-07-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00087; R1 IFI: TPSK-LSPA1-T-CV-00887; R1 IFD: TPSK-LSPA1-T-CV-02066
[6 empty] | Return Date | IFR: 2018-11-02; R1 IFI: 2019-03-18; R1 IFD: 2019-08-29
Owner Cmmt* | bar: IFR to R1 IFD
| CV | OL1-2R02-0005 | Buildings Design And Construction |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2018-10-10; R1 IFI: 2019-01-15
[6 empty] | Revised Plan | IFR: 2018-10-11; R1 IFI: 2019-10-30
[6 empty] | Issue Actual | IFR: 2018-10-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00158
[6 empty] | Return Date | IFR: 2019-03-18
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0006 | Job Supply Specification for Steel Structures |  |  | Purpose** | IFR: IFQ; R1 IFI: IFP; R1 IFD: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-05-16; R1 IFD: 2019-10-16
[6 empty] | Revised Plan | R1 IFI: 2019-07-04
[6 empty] | Issue Actual | R1 IFI: 2019-07-04
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-CV-02070
[6 empty] | Return Date | R1 IFI: 2019-08-29
Owner Cmmt* | bar: R1 IFI
| CV | OL1-2R02-0007 | Tekla Structure Management For LSP Complex Project |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-11-22; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2018-11-26; R1 IFI: 2019-09-10
[6 empty] | Issue Actual | IFR: 2018-11-26; R1 IFI: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00355; R1 IFI: TPSK-LSPA1-T-CV-02576
[6 empty] | Return Date | IFR: 2019-03-27
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0009 | U-G And A-G Civil Model Management |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-11-22; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2018-11-26; R1 IFI: 2019-09-10
[6 empty] | Issue Actual | IFR: 2018-11-26; R1 IFI: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-00355; R1 IFI: TPSK-LSPA1-T-CV-02576
[6 empty] | Return Date | IFR: 2019-03-27
Owner Cmmt* | bar: IFR
| ME | OL1-2R02-0010 | 3D Modeling Procedure For Civil Designers |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-05-15; R1 IFI: 2019-05-16
[6 empty] | Revised Plan | IFR: 2018-12-12; R1 IFI: 2019-04-15
[6 empty] | Issue Actual | IFR: 2018-12-12; R1 IFI: 2019-04-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00353; R1 IFI: TPSK-LSPA1-T-CV-01335
[6 empty] | Return Date | IFR: 2019-03-19; R1 IFI: 2019-06-07
Owner Cmmt* | bar: IFR to R1 IFI
| CV | OL1-2R02-0011 | Geotechnical Factual Report |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-02-15; R1 IFI: 2019-10-08
[6 empty] | Revised Plan | IFR: 2019-05-03; R1 IFI: 2019-11-07
[6 empty] | Issue Actual | IFR: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LPSA1-T-CV-01549
[6 empty] | Return Date | IFR: 2019-05-27
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0012 | Additional Ground Investigation Technical Specification |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2018-10-08; R1 IFI: 2019-12-17
[6 empty] | Revised Plan | IFR: 2019-06-03
[6 empty] | Issue Actual | IFR: 2019-06-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01788
[6 empty] | Return Date | IFR: 2019-06-20
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0101 | Technical Specification For Piles |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-15; R1 IFI: 2019-07-15
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| CV | OL1-2R02-0102 | Technical Specification for Civil Works |  |  | Purpose** | IFR: IFQ; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-06-14; R1 IFI: 2019-07-31
[6 empty] | Revised Plan | IFR: 2019-05-16
[6 empty] | Issue Actual | IFR: 2019-05-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01666
[6 empty] | Return Date | IFR: 2019-06-08
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0103 | Technical Specification for Precast Concrete Pipe-Racks |  |  | Purpose** | IFR: IFQ; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-04-30; R1 IFI: 2019-08-31
[6 empty] | Revised Plan | IFR: 2019-05-16
[6 empty] | Issue Actual | IFR: 2019-05-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01666
[6 empty] | Return Date | IFR: 2019-06-08
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-0104 | Technical Specification For Steel Structures Erection |  |  | Purpose** | IFR: IFQ; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-05-16; R1 IFI: 2019-10-16
[6 empty] | Revised Plan | IFR: 2019-05-16
[6 empty] | Issue Actual | IFR: 2019-05-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01666
[6 empty] | Return Date | IFR: 2019-06-08
Owner Cmmt* | bar: IFR
| CV | OL1-2R02-5001 | Technical Specification For Buildings |  |  | Purpose** | IFR: IFQ; R1 IFI: IFP; R1 IFD: IFQ
Rev. | bar: IFR; R1 IFD
[6 empty] | Issue Plan | IFR: 2019-03-05; R1 IFI: 2019-07-05; R1 IFD: 2019-03-05
[6 empty] | Revised Plan | IFR: 2019-06-26; R1 IFI: 2019-10-20; R1 IFD: 2019-06-26
[6 empty] | Issue Actual | IFR: 2019-06-26; R1 IFD: 2019-06-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-CV-01997; R1 IFD: TPSK-LSPA1-T-CV-01997
Return Date
Owner Cmmt*
Category Code: R03 Mechanical Specification (ME)
| ME | OL1-2R03-0001 | Job Specification For Welding And NDE Of Pressure Vessel And Heat Exchanger |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFI: 2019-05-06
[6 empty] | Revised Plan | IFR: 2018-08-29; R1 IFI: 2019-02-26
[6 empty] | Issue Actual | IFR: 2018-08-29; R1 IFI: 2019-02-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00029; R1 IFI: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | IFR: 2018-09-19; R1 IFI: 2019-03-15
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0002 | Job Specification For Materials In Sour Services |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFI: 2019-05-06
[6 empty] | Revised Plan | IFR: 2018-08-29; R1 IFI: 2019-02-26
[6 empty] | Issue Actual | IFR: 2018-08-29; R1 IFI: 2019-02-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00029; R1 IFI: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | IFR: 2018-09-19; R1 IFI: 2019-03-15
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0003 | Job Specification For Supply Positive Alloy Material Identification Of Equipment And Piping |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFI: 2019-05-06
[6 empty] | Revised Plan | IFR: 2018-08-29; R1 IFI: 2019-02-26
[6 empty] | Issue Actual | IFR: 2018-08-29; R1 IFI: 2019-02-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00029; R1 IFI: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | IFR: 2018-09-19; R1 IFI: 2019-03-15
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0004 | Job Specification For Welding And NDE Storage Tanks |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFI: 2019-05-06
[6 empty] | Revised Plan | IFR: 2018-08-29; R1 IFI: 2019-02-26
[6 empty] | Issue Actual | IFR: 2018-08-29; R1 IFI: 2019-02-26
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00029; R1 IFI: TPSK-LSPA1-T-ME-00921
[6 empty] | Return Date | IFR: 2018-09-19; R1 IFI: 2019-03-15
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0005 | ME-005 Double Jacket Pipe Heat Exchangers for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-23
[6 empty] | Issue Actual | IFR: 2018-10-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00212
Return Date
Owner Cmmt*
| ME | OL1-2R03-0006 | Plate Heat Exchanger |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-10; R1 IFI: 2018-09-24
[6 empty] | Revised Plan | R1 IFI: 2018-09-13
[6 empty] | Issue Actual | R1 IFI: 2018-09-13
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00042
Return Date
Owner Cmmt*
| ME | OL1-2R03-0007 | Job Specification for AXENS Standard Material Specifications - Carbon Steels For Pressure Service |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-22
[6 empty] | Issue Actual | IFR: 2019-02-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00909
[6 empty] | Return Date | IFR: 2019-03-15
Owner Cmmt* | bar: IFR
| ME | OL1-2R03-0008 | Job Specification For Axens Standard Material Specifications - Low Alloyed Steels For Pressure Vessels |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-22
[6 empty] | Issue Actual | IFR: 2019-02-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00909
[6 empty] | Return Date | IFR: 2019-03-15
Owner Cmmt* | bar: IFR
| ME | OL1-2R03-0009 | Job Specification For Axens Standard Material Specifications For Wet H2S Service |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-22
[6 empty] | Issue Actual | IFR: 2019-02-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00909
[6 empty] | Return Date | IFR: 2019-03-15
Owner Cmmt* | bar: IFR
| ME | OL1-2R03-0010 | ME-010 Centrifugal Pump |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-25; R1 IFI: 2019-01-22
[6 empty] | Issue Actual | IFR: 2018-09-25; R1 IFI: 2019-01-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00078; R1 IFI: TPSK-LSPA1-T-ME-00693
[6 empty] | Return Date | IFR: 2018-10-12; R1 IFI: 2019-02-14
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0011 | ME-011 RECIPROCATING PUMP |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-25
[6 empty] | Issue Actual | IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01459
[6 empty] | Return Date | IFR: 2019-05-24
Owner Cmmt* | bar: IFR
| ME | OL1-2R03-0013 | ME-013 Diesel Engine |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-18; R1 IFI: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-10-18; R1 IFI: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00196; R1 IFI: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2018-11-02; R1 IFI: 2019-04-25
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0014 | ME-014 Centrifugal Compressor |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-19; R1 IFI: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-10-19; R1 IFI: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00065; R1 IFI: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2018-10-10; R1 IFI: 2019-04-25
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0016 | ME-016 Centrifugal Compressor For PA-IA Servise |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-15; R1 IFI: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-10-15; R1 IFI: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00164; R1 IFI: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2018-11-07; R1 IFI: 2019-04-25
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0017 | ME-017 Root Blower |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-19
[6 empty] | Issue Actual | IFR: 2018-11-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00334
Return Date
Owner Cmmt*
| ME | OL1-2R03-0018 | ME-018 General Purpose Steam Turbines |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-25; R1 IFI: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-09-25; R1 IFI: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00078; R1 IFI: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2018-10-12; R1 IFI: 2019-04-25
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0019 | ME-019 Lube Oil Unit And Seal Oil System |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-19; R1 IFI: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-10-19; R1 IFI: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00065; R1 IFI: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2018-10-10; R1 IFI: 2019-04-25
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0020 | ME-020 Special Purpose Steam Tturbines |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-25; R1 IFI: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-09-25; R1 IFI: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00078; R1 IFI: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2018-10-12; R1 IFI: 2019-04-25
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0021 | ME-021 Flare System |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-06; R1 IFI: 2019-06-25
[6 empty] | Issue Actual | IFR: 2018-12-06; R1 IFI: 2019-06-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00429; R1 IFI: TPSK-LSPA1-T-ME-01969
[6 empty] | Return Date | IFR: 2018-12-26; R1 IFI: 2019-07-08
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0022 | ME-022 Special Purpose Gear |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-15; R1 IFI: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-10-15; R1 IFI: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00166; R1 IFI: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2018-11-07; R1 IFI: 2019-04-25
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0024 | ME-024 Elevator For 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-20
[6 empty] | Issue Actual | IFR: 2018-12-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00537
Return Date
Owner Cmmt*
| ME | OL1-2R03-0028 | ME-028 Mechanical Seal |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-18
[6 empty] | Issue Actual | IFR: 2018-09-18
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00057
Return Date
Owner Cmmt*
| ME | OL1-2R03-0029 | ME-029 Centrifugal Blower for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-17
[6 empty] | Issue Actual | IFR: 2018-10-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00185
[6 empty] | Return Date | IFR: 2018-11-05
Owner Cmmt*
| MP | OL1-2R03-0030 | Job Sprcification For Supply And Fabrication Of Grade 91 Alloy Steel Piping |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-25
[6 empty] | Issue Actual | IFR: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01465
[6 empty] | Return Date | IFR: 2019-05-17
Owner Cmmt* | bar: IFR
| ME | OL1-2R03-0047 | ME-047 Dry Screw Compressor for Hydrocarbon Services |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-06; R1 IFI: 2019-01-17
[6 empty] | Issue Actual | IFR: 2018-12-06; R1 IFI: 2019-01-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00429; R1 IFI: TPSK-LSPA1-T-ME-00666
[6 empty] | Return Date | IFR: 2018-12-26; R1 IFI: 2019-02-04
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0050 | Job Specification For Design Of Pressure And Atmospheric Static Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP; R1 IFF: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0; R1 IFF: 1
[6 empty] | Issue Plan | IFR: 2018-08-10; R1 IFD: 2018-09-20
[6 empty] | Revised Plan | IFR: 2018-08-13; R1 IFD: 2018-10-31
[6 empty] | Issue Actual | IFR: 2018-08-13; R1 IFI: 2018-09-27; R1 IFD: 2018-10-31; R1 IFF: 2019-02-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00017; R1 IFI: TPSK-LSPA1-T-ME-00084; R1 IFD: TPSK-LSPA1-T-ME-00245; R1 IFF: TPSK-LSPA1-T-ME-00888
[6 empty] | Return Date | IFR: 2018-08-27; R1 IFI: 2018-10-24; R1 IFD: 2018-11-26; R1 IFF: 2019-03-15
Owner Cmmt* | bar: IFR to R1 IFI; R1 IFF
| ME | OL1-2R03-0051 | Job Specification For Supply Of Pressure Vessels |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP; R1 IFF: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0; R1 IFF: 1
[6 empty] | Issue Plan | IFR: 2018-09-10; R1 IFD: 2018-09-22
[6 empty] | Revised Plan | IFR: 2018-08-13; R1 IFD: 2018-10-31
[6 empty] | Issue Actual | IFR: 2018-08-13; R1 IFI: 2018-09-27; R1 IFD: 2018-10-31; R1 IFF: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00021; R1 IFI: TPSK-LSPA1-T-ME-00084; R1 IFD: TPSK-LSPA1-T-ME-00249; R1 IFF: TPSK-LSPA1-T-ME-01350
[6 empty] | Return Date | IFR: 2018-08-27; R1 IFI: 2018-10-24; R1 IFD: 2018-11-27; R1 IFF: 2019-05-13
Owner Cmmt* | bar: IFR to R1 IFI; R1 IFF
| ME | OL1-2R03-0052 | Job Specification For Supply Of Column Internals |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-08-10; R1 IFI: 2018-09-23
[6 empty] | Revised Plan | IFR: 2018-08-13; R1 IFI: 2018-09-25
[6 empty] | Issue Actual | IFR: 2018-08-13; R1 IFI: 2018-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00017; R1 IFI: TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | IFR: 2018-08-27; R1 IFI: 2018-10-24
Owner Cmmt* | bar: IFR
| ME | OL1-2R03-0053 | Job Specification For Supply Of Equipment Ladders And Platforms |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-08-10; R1 IFD: 2018-09-25
[6 empty] | Revised Plan | IFR: 2018-08-13
[6 empty] | Issue Actual | IFR: 2018-08-13; R1 IFI: 2018-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00017; R1 IFI: TPSK-LSPA1-T-ME-00081
[6 empty] | Return Date | IFR: 2018-08-27; R1 IFI: 2018-10-24
Owner Cmmt* | bar: IFR
| ME | OL1-2R03-0054 | Construction Standards For Pressure Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2018-08-10; R1 IFD: 2018-10-19
[6 empty] | Revised Plan | IFR: 2018-08-13
[6 empty] | Issue Actual | IFR: 2018-08-13; R1 IFI: 2018-09-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00018; R1 IFI: TPSK-LSPA1-T-ME-00084
[6 empty] | Return Date | IFR: 2018-08-27; R1 IFI: 2018-10-24
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-0055 | Construction Standards For Ladders And Platforms Attached To Pressure Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2018-10-23; R1 IFI: 2018-12-20
[6 empty] | Revised Plan | IFR: 2018-08-29
[6 empty] | Issue Actual | IFR: 2018-08-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00027
[6 empty] | Return Date | IFR: 2018-09-18
Owner Cmmt* | bar: IFR
| ME | OL1-2R03-0102 | Marking For Vessel & Heat Exchanger |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-10; R1 IFI: 2018-09-22
[6 empty] | Revised Plan | R1 IFI: 2018-09-13
[6 empty] | Issue Actual | R1 IFI: 2018-09-13
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ME-00042
Return Date
Owner Cmmt*
| ME | OL1-2R03-0104 | ME-008 Cooling Water |  | Class 2 | Purpose** | IFR: IFQ
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-06
[6 empty] | Issue Actual | IFR: 2018-11-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00276
[6 empty] | Return Date | IFR: 2019-02-15
Owner Cmmt*
| ME | OL1-2R03-0500 | ME-050 Centrifugal Pump (Non API) |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-12; R1 IFI: 2019-01-23
[6 empty] | Issue Actual | IFR: 2018-11-12; R1 IFI: 2019-01-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00308; R1 IFI: TPSK-LSPA1-T-ME-00668
[6 empty] | Return Date | IFR: 2018-12-06; R1 IFI: 2019-04-25
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R03-1001 | ME-001 Pressure Vessel for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IFE
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-07
[6 empty] | Issue Actual | IFR: 2018-11-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00262
Return Date
Owner Cmmt*
| ME | OL1-2R03-1004 | ME-004 Shell and Tube Heat Exchangers for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-24
[6 empty] | Issue Actual | IFR: 2018-10-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00221
Return Date
Owner Cmmt*
| ME | OL1-2R03-1005 | Job Specification for Axens General Statement about Selection of Materials for Equipment and Piping |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01505
[6 empty] | Return Date | IFR: 2019-05-24
Owner Cmmt* | bar: IFR
| ME | OL1-2R03-1006 | Job Specification for Air Liquide-Design Rules- Codes and Standards for Columns and Column Internals |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-04-29
[6 empty] | Issue Actual | IFR: 2019-04-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-01504
[6 empty] | Return Date | IFR: 2019-05-24
Owner Cmmt* | bar: IFR
Category Code: R04 Piping Specification (PIP)
| MP | OL1-2R04-0001 | Piping Class Summary And Piping Classes - Includes ex doc OL1-2P92-0003 as attachment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
[6 empty] | Issue Plan | IFR: 2018-12-19; R1 IFI: 2020-10-15
[6 empty] | Revised Plan | IFR: 2018-12-27; R1 IFI: 2019-04-08; R1 IFD: 2020-10-15
[6 empty] | Issue Actual | IFR: 2018-12-27; R1 IFI: 2019-04-08; R1 IFD: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00562; R1 IFI: 1262-TPSK-LSPA1-T-MP-01262; R1 IFD: TPSK-LSPA1-T-MP-02390
[6 empty] | Return Date | IFR: 2019-01-17; R1 IFD: 2019-08-23
Owner Cmmt* | bar: IFR; R1 IFD
| MP | OL1-2R04-0002 | Piping Design Specification |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2018-11-13; R1 IFD: 2019-02-01
[6 empty] | Revised Plan | IFR: 2018-08-08
[6 empty] | Issue Actual | IFR: 2018-08-08; R1 IFI: 2018-11-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00012; R1 IFI: TPSK-LSPA1-T-MP-00012
[6 empty] | Return Date | IFR: 2018-09-26; R1 IFI: 2018-12-07
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0003 | Job Design Specification For Thermal Insulation (Hot Service) |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IFR; R1 IFF: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C
[6 empty] | Issue Plan | IFR: 2019-04-29; R1 IFF: 2019-08-27
[6 empty] | Revised Plan | IFR: 2018-08-23
[6 empty] | Issue Actual | IFR: 2018-08-23; R1 IFI: 2018-12-27; R1 IFD: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00024; R1 IFI: TPSK-LSPA1-T-MP-00562; R1 IFD: TPSK-LSPA1-T-MP-02391
[6 empty] | Return Date | IFR: 2018-09-12; R1 IFI: 2019-01-17; R1 IFD: 2019-08-28
[6 empty] | Owner Cmmt* | IFR: A4; R1 IFI: R2; R1 IFD: R1
| MP | OL1-2R04-0004 | Job Design Specification For Thermal Insulation (Cold Service) |  |  | Purpose** | IFR | IFR | IFR | IFR | IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C; R1 IFF: D
[6 empty] | Issue Plan | IFR: 2019-04-29; R1 IMP: 2019-08-27
[6 empty] | Revised Plan | IFR: 2018-08-23
[6 empty] | Issue Actual | IFR: 2018-08-23; R1 IFI: 2018-12-27; R1 IFD: 2019-05-16; R1 IFF: 2019-08-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00024; R1 IFI: TPSK-LSPA1-T-MP-00562; R1 IFD: TPSK-LSPA1-T-MP-01665; R1 IFF: TPSK-LSPA1-T-MP-02391
[6 empty] | Return Date | IFR: 2018-09-12; R1 IFI: 2019-01-17; R1 IFD: 2019-05-27; R1 IFF: 2019-08-28
[6 empty] | Owner Cmmt* | IFR: A4; R1 IFI: R2; R1 IFD: R1; R1 IFF: R1
| MP | OL1-2R04-0005 | Job Design Specification For Painting |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP; R1 IFF: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0; R1 IFF: 1
[6 empty] | Issue Plan | IFR: 2019-04-29; R1 IFD: 2019-08-27
[6 empty] | Revised Plan | IFR: 2018-08-23; R1 IFD: 2019-05-21
[6 empty] | Issue Actual | IFR: 2018-08-23; R1 IFI: 2018-12-27; R1 IFD: 2019-05-21; R1 IFF: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00024; R1 IFI: TPSK-LSPA1-T-MP-00562; R1 IFD: TPSK-LSPA1-T-MP-01690; R1 IFF: TPSK-LSPA1-T-MP-02314
[6 empty] | Return Date | IFR: 2018-09-12; R1 IFI: 2019-01-17; R1 IFD: 2019-06-14; R1 IFF: 2019-08-13
[6 empty] | Owner Cmmt* | IFR: A4; R1 IFI: R2; R1 IFD: R2; R1 IFF: R1
| MP | OL1-2R04-0006 | General Supply Specification For Piping Material |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFD: 2019-05-06
[6 empty] | Revised Plan | IFR: 2018-08-29; R1 IFD: 2019-03-01
[6 empty] | Issue Actual | IFR: 2018-08-29; R1 IFI: 2018-11-20; R1 IFD: 2019-03-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00028; R1 IFI: TPSK-LSPA1-T-MP-00342; R1 IFD: TPSK-LSPA1-T-MP-00951
[6 empty] | Return Date | IFR: 2018-09-18; R1 IFI: 2019-01-30; R1 IFD: 2019-04-01
Owner Cmmt* | bar: IFR to R1 IFD
| ME | OL1-2R04-0007 | PIP-007 Marking of Piping Material for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-23
[6 empty] | Issue Actual | IFR: 2018-10-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00213
Return Date
Owner Cmmt*
| MP | OL1-2R04-0008 | Job Supply Specification For Butterfly Valves |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-13; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | IFR: 2018-11-26; R1 IFI: 2019-04-25
[6 empty] | Issue Actual | IFR: 2018-11-26; R1 IFI: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00352; R1 IFI: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | IFR: 2019-01-30; R1 IFI: 2019-05-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0009 | Job Supply Specification For Plug Valves |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-13; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | IFR: 2018-11-26; R1 IFI: 2019-04-25
[6 empty] | Issue Actual | IFR: 2018-11-26; R1 IFI: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00352; R1 IFI: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | IFR: 2019-01-30; R1 IFI: 2019-05-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0010 | Job Supply Specification For Ball Valves |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-13; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | IFR: 2018-11-26; R1 IFI: 2019-04-25
[6 empty] | Issue Actual | IFR: 2018-11-26; R1 IFI: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00352; R1 IFI: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | IFR: 2019-01-30; R1 IFI: 2019-05-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0011 | Job Supply Specification For Pipes |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFD: 2019-05-06
[6 empty] | Revised Plan | IFR: 2018-08-29; R1 IFD: 2019-04-25
[6 empty] | Issue Actual | IFR: 2018-08-29; R1 IFI: 2018-11-20; R1 IFD: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00028; R1 IFI: TPSK-LSPA1-T-MP-00342; R1 IFD: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | IFR: 2018-09-18; R1 IFI: 2019-01-30; R1 IFD: 2019-05-17
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2R04-0012 | Pipe Support |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-16; R1 IFI: 2019-02-08
[6 empty] | Issue Actual | IFR: 2018-11-16; R1 IFI: 2019-02-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00324; R1 IFI: TPSK-LSPA1-T-MP-00828
[6 empty] | Return Date | IFR: 2018-12-18; R1 IFI: 2019-02-25
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0013 | Job Supply Specification For Buttwelding Fittings |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFD: 2019-05-06
[6 empty] | Revised Plan | IFR: 2018-08-29; R1 IFD: 2019-04-25
[6 empty] | Issue Actual | IFR: 2018-08-29; R1 IFI: 2018-11-20; R1 IFD: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00028; R1 IFI: TPSK-LSPA1-T-MP-00342; R1 IFD: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | IFR: 2018-09-18; R1 IFI: 2019-01-30; R1 IFD: 2019-05-17
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2R04-0014 | Job Supply Specification For Forged Fittings |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFD: 2019-05-06
[6 empty] | Revised Plan | IFR: 2018-08-29; R1 IFD: 2019-04-25
[6 empty] | Issue Actual | IFR: 2018-08-29; R1 IFI: 2018-11-20; R1 IFD: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00028; R1 IFI: TPSK-LSPA1-T-MP-00342; R1 IFD: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | IFR: 2018-09-18; R1 IFI: 2019-01-30; R1 IFD: 2019-05-17
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2R04-0015 | Job Supply Specification For Flanges |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0
[6 empty] | Issue Plan | IFR: 2019-04-06; R1 IFD: 2019-05-06
[6 empty] | Revised Plan | IFR: 2018-08-29; R1 IFD: 2019-04-25
[6 empty] | Issue Actual | IFR: 2018-08-29; R1 IFI: 2018-11-20; R1 IFD: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00028; R1 IFI: TPSK-LSPA1-T-MP-00342; R1 IFD: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | IFR: 2018-09-18; R1 IFI: 2019-01-30; R1 IFD: 2019-05-17
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2R04-0016 | Job Supply Specification For Gaskets |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-04-20; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | IFR: 2019-09-10; R1 IFI: 2019-10-25
[6 empty] | Issue Actual | IFR: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02591
[6 empty] | Return Date | IFR: 2019-09-18
Owner Cmmt* | bar: IFR
| MP | OL1-2R04-0017 | Job Supply Specification For Bolting |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-04-20; R1 IFI: 2019-05-20
[6 empty] | Revised Plan | IFR: 2019-09-10; R1 IFI: 2019-11-04
[6 empty] | Issue Actual | IFR: 2019-09-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-02591
[6 empty] | Return Date | IFR: 2019-09-18
Owner Cmmt* | bar: IFR
| MP | OL1-2R04-0030 | Piping Flexibility |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-20; R1 IFI: 2019-02-08
[6 empty] | Issue Actual | IFR: 2018-11-20; R1 IFI: 2019-02-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00336; R1 IFI: TPSK-LSPA1-T-MP-00828
[6 empty] | Return Date | IFR: 2018-12-07; R1 IFI: 2019-02-25
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0031 | Job Design Specification For Steam Tracing |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IFC
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2018-11-13; R1 IFD: 2019-02-01
[6 empty] | Revised Plan | IFR: 2018-08-08
[6 empty] | Issue Actual | IFR: 2018-08-08; R1 IFI: 2018-11-09
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00012; R1 IFI: TPSK-LSPA1-T-MP-00292
[6 empty] | Return Date | IFR: 2018-09-26; R1 IFI: 2019-01-23
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0032 | JSD For Piping Stress Analysis |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-11-12; R1 IFI: 2019-02-15
[6 empty] | Revised Plan | IFR: 2018-11-16; R1 IFI: 2019-02-19
[6 empty] | Issue Actual | IFR: 2018-11-16; R1 IFI: 2019-02-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00324; R1 IFI: TPSK-LSPA1-T-MP-00881
[6 empty] | Return Date | IFR: 2018-12-18; R1 IFI: 2019-03-21
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0033 | JSD for Piping Loads On PRK SLW STR IS |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-11-12; R1 IFI: 2019-02-15
[6 empty] | Revised Plan | IFR: 2018-11-16; R1 IFI: 2019-02-08
[6 empty] | Issue Actual | IFR: 2018-11-16; R1 IFI: 2019-02-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00324; R1 IFI: TPSK-LSPA1-T-MP-00828
[6 empty] | Return Date | IFR: 2018-12-18; R1 IFI: 2019-02-25
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0034 | JSD For Auxiliary Piping Supports |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0
[6 empty] | Issue Plan | IFR: 2018-11-12; R1 IFD: 2019-02-15
[6 empty] | Revised Plan | IFR: 2018-11-16; R1 IFD: 2019-03-08
[6 empty] | Issue Actual | IFR: 2018-11-16; R1 IFI: 2019-02-08; R1 IFD: 2019-03-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00324; R1 IFI: TPSK-LSPA1-T-MP-00830; R1 IFD: TPSK-LSPA1-T-MP-01002
[6 empty] | Return Date | IFR: 2018-12-18; R1 IFI: 2019-02-25; R1 IFD: 2019-04-01
Owner Cmmt* | bar: IFR to R1 IFD
| MP | OL1-2R04-0036 | General Supply Rules For Polyurethane Piping Supports |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-31; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Issue Actual | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00831; R1 IFI: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | IFR: 2019-03-21; R1 IFI: 2019-04-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0037 | General Supply Rules For Rod And Spring Hangers |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-31; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Issue Actual | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00831; R1 IFI: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | IFR: 2019-03-21; R1 IFI: 2019-04-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0038 | General Supply Rules For Sliding Plates |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-31; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Issue Actual | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00831; R1 IFI: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | IFR: 2019-03-21; R1 IFI: 2019-04-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0039 | General Supply Rules For Dynamic Piping Supports |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-31; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Issue Actual | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00831; R1 IFI: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | IFR: 2019-03-21; R1 IFI: 2019-04-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0040 | General Supply Rules For Metallic Expansion Joints |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-31; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Issue Actual | IFR: 2019-02-08; R1 IFI: 2019-04-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00831; R1 IFI: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | IFR: 2019-03-21; R1 IFI: 2019-04-26
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0041 | Job Supply Specification For Valves (Gate - Globe - Check) |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-13; R1 IFI: 2019-05-13
[6 empty] | Revised Plan | IFR: 2018-11-26; R1 IFI: 2019-04-25
[6 empty] | Issue Actual | IFR: 2018-11-26; R1 IFI: 2019-04-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-00356; R1 IFI: TPSK-LSPA1-T-MP-01463
[6 empty] | Return Date | IFR: 2019-01-30; R1 IFI: 2019-05-17
Owner Cmmt* | bar: IFR to R1 IFI
| MP | OL1-2R04-0042 | Job Supply Specification For Non Metallic Expansion Joints |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-31; R1 IFI: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-03-08; R1 IFI: 2019-04-03
[6 empty] | Issue Actual | IFR: 2019-03-08; R1 IFI: 2019-04-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-MP-01000; R1 IFI: TPSK-LSPA1-T-MP-01223
[6 empty] | Return Date | IFR: 2019-04-01; R1 IFI: 2019-04-26
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R04-1004 | PIP-004 Piping Welding Specification for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-17
[6 empty] | Issue Actual | IFR: 2018-10-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00184
Return Date
Owner Cmmt*
Category Code: R05 Electrical Specification (EE)
| EE | OL1-2R05-0001 | General Electrical Design |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | R1 IFI: 2018-12-05
[6 empty] | Issue Actual | R1 IFI: 2018-12-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0002 | Electrical System Design |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | R1 IFI: 2018-12-05
[6 empty] | Issue Actual | R1 IFI: 2018-12-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0003 | Oil Filled Distribution Transformer |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0004 | Protective Relay And Control Unit |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | R1 IFI: 2018-12-20
[6 empty] | Issue Actual | R1 IFI: 2018-12-20
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00522
Return Date
Owner Cmmt*
| EE | OL1-2R05-0005 | Substation Monitoring And Control System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-12-05
[6 empty] | Issue Actual | R1 IFI: 2018-12-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0006 | Medium Voltage Switchgear |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0007 | Low Voltage Distribution Panel |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-12
[6 empty] | Issue Actual | R1 IFI: 2018-11-12
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00309
Return Date
Owner Cmmt*
| EE | OL1-2R05-0008 | Low Voltage Switchgear And Motor Control Center |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
Revised Plan
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0009 | SMCS I/O List |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-06-15; R1 IFD: 2019-08-17
[6 empty] | Revised Plan | IFR: 2019-07-01; R1 IFD: 2019-11-18
[6 empty] | Issue Actual | IFR: 2019-07-01; R1 IFI: 2019-09-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02023; R1 IFI: TPSK-LSPA1-T-EE-02639
[6 empty] | Return Date | IFR: 2019-07-16
Owner Cmmt* | bar: IFR
| EE | OL1-2R05-0010 | Electrical Motos Up To 300 kW |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-09-25
[6 empty] | Issue Actual | R1 IFI: 2018-09-25
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00079
Return Date
Owner Cmmt*
| EE | OL1-2R05-0011 | Electrical Motors Greater Than 300 kW |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-08
[6 empty] | Issue Actual | R1 IFI: 2018-11-08
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00748
[6 empty] | Return Date | R1 IFI: 2019-02-25
Owner Cmmt* | bar: R1 IFI
| EE | OL1-2R05-0012 | Uninterruptible Power Supplies |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0013 | Intercom/Paging/Audible Alarm System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
[6 empty] | Issue Plan | IFR: 2019-01-21; R1 IFI: 2019-02-15
[6 empty] | Revised Plan | IFR: 2018-12-04; R1 IFI: 2019-03-06
[6 empty] | Issue Actual | IFR: 2018-12-04; R1 IFI: 2019-03-06; R1 IFD: 2019-07-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00403; R1 IFI: TPSK-LSPA1-T-EE-00987; R1 IFD: TPSK-LSPA1-T-EE-02031
[6 empty] | Return Date | IFR: 2018-12-17; R1 IFI: 2019-03-21; R1 IFD: 2019-07-08
Owner Cmmt* | bar: IFR to R1 IFD
| EE | OL1-2R05-0014 | LIGHTING SYSTEM |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0015 | Earthing And Lightning Protection |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0016 | Cathodic Protection |  |  | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | R1 IFI: 0; R1 IFD: 1
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05; R1 IFD: 2019-05-03
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268; R1 IFD: TPSK-LSPA1-T-EE-01556
[6 empty] | Return Date | R1 IFD: 2019-05-17
Owner Cmmt* | bar: R1 IFD
| EE | OL1-2R05-0017 | Diesel Engine Generator |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0018 | Power Control And Fiber Optic Cables |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-12-05
[6 empty] | Issue Actual | R1 IFI: 2018-12-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0019 | Safety Supervisory System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
[6 empty] | Issue Plan | IFR: 2019-01-21; R1 IFI: 2019-02-15
[6 empty] | Revised Plan | IFR: 2018-12-04; R1 IFI: 2019-03-06
[6 empty] | Issue Actual | IFR: 2018-12-04; R1 IFI: 2019-03-06; R1 IFD: 2019-07-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00403; R1 IFI: TPSK-LSPA1-T-EE-00987; R1 IFD: TPSK-LSPA1-T-EE-02179
[6 empty] | Return Date | IFR: 2018-12-17; R1 IFI: 2019-03-21; R1 IFD: 2019-07-30
Owner Cmmt* | bar: IFR to R1 IFD
| EE | OL1-2R05-0021 | Power Capacitors |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0022 | Miscellaneous Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0023 | Low Voltage Variable Voltage Variable Frequency System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0024 | Substation Design |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | IFR: 2019-09-11; R1 IFI: 2019-11-29
[6 empty] | Issue Actual | IFR: 2019-09-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02603
[6 empty] | Return Date | IFR: 2019-09-20
Owner Cmmt* | bar: IFR
| EE | OL1-2R05-0027 | Neutral Grounding Resistor |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-12-05
[6 empty] | Issue Actual | R1 IFI: 2018-12-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00425
Return Date
Owner Cmmt*
| EE | OL1-2R05-0029 | Functional and Schematic Diagram |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00258
Return Date
Owner Cmmt*
| EE | OL1-2R05-0036 | Document Template |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | R1 IFI: 2018-12-05
[6 empty] | Issue Actual | R1 IFI: 2018-12-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00424
Return Date
Owner Cmmt*
| EE | OL1-2R05-0037 | Electrical Heat Tracing |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-09-25
[6 empty] | Issue Actual | R1 IFI: 2018-09-25
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00079
Return Date
Owner Cmmt*
| EE | OL1-2R05-0038 | Low Voltage Bus Duct |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0040 | Medium Voltage Variable Voltage Variable Frequency System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2018-12-03
[6 empty] | Revised Plan | R1 IFI: 2018-11-05
[6 empty] | Issue Actual | R1 IFI: 2018-11-05
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-00268
Return Date
Owner Cmmt*
| EE | OL1-2R05-0041 | NUMBERING SYSTEM FOR ELECTRICAL EQUIPMENT |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2018-10-14; R1 IFI: 2019-01-30
[6 empty] | Revised Plan | IFR: 2019-11-04; R1 IFI: 2019-11-29
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2R05-0042 | General Design Rule For Package Equipment Electrical System - Client code for next revision will be OL1-2E04-6000 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-07
[6 empty] | Issue Actual | IFR: 2018-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | IFR: 2018-08-24
Owner Cmmt* | bar: IFR
| EE | OL1-2R05-0043 | General Design Rule For Smartplant Electrical - For Next Revision See Document OL1-2E92-0001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-07
[6 empty] | Issue Actual | IFR: 2018-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | IFR: 2018-08-24
Owner Cmmt* | bar: IFR
| EE | OL1-2R05-0044 | Coordination Procedure For Smartplant Electrical - For Next Revision See Document OL1-2E92-0002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-07
[6 empty] | Issue Actual | IFR: 2018-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | IFR: 2018-08-24
Owner Cmmt* | bar: IFR
| EE | OL1-2R05-0045 | Coordination Procedure For ETAP For Next Revision See Document OL1-2E92-0003 |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-07
[6 empty] | Issue Actual | IFR: 2018-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00008
[6 empty] | Return Date | IFR: 2018-08-24
Owner Cmmt* | bar: IFR
| EE | OL1-2R05-0060 | 3D Modeling Procedure For Electrical Designers |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-03; R1 IFI: 2019-04-02
[6 empty] | Issue Actual | IFR: 2019-01-03; R1 IFI: 2019-04-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00579; R1 IFI: TPSK-LSPA1-T-EE-01217
[6 empty] | Return Date | IFR: 2019-01-23; R1 IFI: 2019-05-07
Owner Cmmt* | bar: IFR to R1 IFI
Category Code: R06 Instrument Specification (INS)
| IE | OL1-2R06-0001 | Instrument General Design |  |  | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
[6 empty] | Issue Plan | IFR: 2018-09-28; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-10-04; R1 IFI: 2018-12-17
[6 empty] | Issue Actual | IFR: 2018-10-04; R1 IFI: 2018-12-17; R1 IFD: 2019-05-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00121; R1 IFI: TPSK-LSPA1-T-IE-00507; R1 IFD: TPSK-LSPA1-T-IE-01741
[6 empty] | Return Date | IFR: 2018-10-09; R1 IFI: 2018-12-26; R1 IFD: 2019-06-17
Owner Cmmt* | bar: IFR to R1 IFD
| IE | OL1-2R06-0003 | Flow Measurement |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-28; R1 IFI: 2018-09-28
[6 empty] | Revised Plan | R1 IFI: 2018-10-03
[6 empty] | Issue Actual | R1 IFI: 2018-10-03
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0005 | Level Measurement |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-28; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-10-04; R1 IFI: 2018-12-17
[6 empty] | Issue Actual | IFR: 2018-10-04; R1 IFI: 2018-12-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00121; R1 IFI: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | IFR: 2018-10-09; R1 IFI: 2018-12-26
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0006 | Pressure Measurement |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-28; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-10-04; R1 IFI: 2018-12-17
[6 empty] | Issue Actual | IFR: 2018-10-04; R1 IFI: 2018-12-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00121; R1 IFI: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | IFR: 2018-10-09; R1 IFI: 2018-12-26
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0007 | Temperature Measurement |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-28; R1 IFI: 2018-12-21
[6 empty] | Revised Plan | IFR: 2018-10-04; R1 IFI: 2018-12-17
[6 empty] | Issue Actual | IFR: 2018-10-04; R1 IFI: 2018-12-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00121; R1 IFI: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | IFR: 2018-10-09; R1 IFI: 2018-12-26
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0008 | Final Control Element |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-28; R1 IFI: 2019-01-21
[6 empty] | Revised Plan | IFR: 2018-10-04; R1 IFI: 2019-05-24
[6 empty] | Issue Actual | IFR: 2018-10-04; R1 IFI: 2019-05-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00121; R1 IFI: TPSK-LSPA1-T-IE-01727
[6 empty] | Return Date | IFR: 2018-10-09; R1 IFI: 2019-06-12
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0010 | Instrument Construction Material |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-15; R1 IFI: 2019-09-28
[6 empty] | Revised Plan | R1 IFI: 2018-10-04
[6 empty] | Issue Actual | R1 IFI: 2018-10-04
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0011 | Instrument Air Supply |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-15; R1 IFI: 2019-09-28
[6 empty] | Revised Plan | IFR: 2018-11-26; R1 IFI: 2019-03-11
[6 empty] | Issue Actual | IFR: 2018-11-26; R1 IFI: 2019-03-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00357; R1 IFI: TPSK-LSPA1-T-IE-01014
[6 empty] | Return Date | IFR: 2019-02-01; R1 IFI: 2019-04-05
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0012 | Grounding System for Instrument |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-15; R1 IFI: 2019-09-28
[6 empty] | Revised Plan | R1 IFI: 2018-12-17
[6 empty] | Issue Actual | R1 IFI: 2018-12-17
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-IE-00508
Return Date
Owner Cmmt*
| IE | OL1-2R06-0013 | Machinery Monitoring System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-07-30; R1 IFI: 2020-03-05
[6 empty] | Revised Plan | IFR: 2018-10-04; R1 IFI: 2019-02-19
[6 empty] | Issue Actual | IFR: 2018-10-04; R1 IFI: 2019-02-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00121; R1 IFI: TPSK-LSPA1-T-IE-00889
[6 empty] | Return Date | IFR: 2018-10-09; R1 IFI: 2019-03-08
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0015 | Integrated Control And Safety System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-11-20; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-11-26; R1 IFI: 2019-06-17
[6 empty] | Issue Actual | IFR: 2018-11-26; R1 IFI: 2019-06-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00357; R1 IFI: TPSK-LSPA1-T-IE-01897
[6 empty] | Return Date | IFR: 2019-02-01; R1 IFI: 2019-06-27
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0016 | Instrument Cabinet |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-11-20; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-10-04; R1 IFI: 2019-03-06
[6 empty] | Issue Actual | IFR: 2018-10-04; R1 IFI: 2019-03-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00121; R1 IFI: TPSK-LSPA1-T-IE-00986
[6 empty] | Return Date | IFR: 2018-10-09; R1 IFI: 2019-05-15
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0017 | Integrated Turbine And Compressor Control System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-11-07; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-10-09; R1 IFI: 2018-12-17
[6 empty] | Issue Actual | IFR: 2018-10-09; R1 IFI: 2018-12-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00148; R1 IFI: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | IFR: 2018-10-24; R1 IFI: 2018-12-26
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0021 | Pressure Safety Valve |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-28; R1 IFI: 2018-09-28
[6 empty] | Revised Plan | R1 IFI: 2018-10-04
[6 empty] | Issue Actual | R1 IFI: 2018-10-04
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0022 | Instrument Numbering |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-03; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-10-05; R1 IFI: 2019-04-12
[6 empty] | Issue Actual | IFR: 2018-10-05; R1 IFI: 2019-04-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00131; R1 IFI: TPSK-LSPA1-T-IE-01320
[6 empty] | Return Date | IFR: 2018-10-24; R1 IFI: 2019-05-09
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-0023 | Instrument Inspection And Test Plan |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-10-03; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | R1 IFI: 2018-10-04
[6 empty] | Issue Actual | R1 IFI: 2018-10-04
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
| IE | OL1-2R06-0024 | General Design Rules For SmartPlant Instrumentation Setup |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: 0
[6 empty] | Issue Plan | IFR: 2018-10-03; R1 IFD: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-09-28; R1 IFD: 2019-03-20
[6 empty] | Issue Actual | IFR: 2018-09-28; R1 IFI: 2018-11-08; R1 IFD: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00109; R1 IFI: TPSK-LSPA1-T-IE-00291; R1 IFD: TPSK-LSPA1-T-IE-01094
[6 empty] | Return Date | IFR: 2018-10-09; R1 IFI: 2019-02-01; R1 IFD: 2019-04-05
Owner Cmmt* | bar: IFR to R1 IFD
| IE | OL1-2R06-0026 | JSD For Automation System Availability |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-01-21; R1 IFI: 2019-02-21
[6 empty] | Revised Plan | IFR: 2019-04-16
[6 empty] | Issue Actual | IFR: 2019-04-16
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-01355
[6 empty] | Return Date | IFR: 2019-05-07
Owner Cmmt* | bar: IFR
| IE | OL1-2R06-0035 | General Design Rules For Instrumentation And Control Of Packaged Equipment |  |  | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
[6 empty] | Issue Plan | IFR: 2018-11-07; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-09-18; R1 IFI: 2018-11-29
[6 empty] | Issue Actual | IFR: 2018-09-18; R1 IFI: 2018-11-29; R1 IFD: 2019-04-12
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00056; R1 IFI: TPSK-LSPA1-T-IE-00393; R1 IFD: TPSK-LSPA1-T-IE-01320
[6 empty] | Return Date | IFR: 2018-10-02; R1 IFI: 2018-12-13; R1 IFD: 2019-05-09
Owner Cmmt* | bar: IFR to R1 IFD
| IE | OL1-2R06-0040 | 3D Modeling Procedure for Instrumentation Designers |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-20
[6 empty] | Issue Actual | IFR: 2018-12-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00556
[6 empty] | Return Date | IFR: 2019-01-17
Owner Cmmt* | bar: IFR
| IE | OL1-2R06-1025 | General Design Rules For Control and Safety Philosophy |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-01-21; R1 IFI: 2019-02-21
[6 empty] | Revised Plan | IFR: 2019-01-29
[6 empty] | Issue Actual | IFR: 2019-01-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00750
[6 empty] | Return Date | IFR: 2019-02-27
Owner Cmmt* | bar: IFR
| IE | OL1-2R06-1301 | Progammable Logic Controller |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-11-07; R1 IFI: 2019-02-02
[6 empty] | Revised Plan | IFR: 2018-11-08; R1 IFI: 2019-03-20
[6 empty] | Issue Actual | IFR: 2018-11-08; R1 IFI: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00291; R1 IFI: TPSK-LSPA1-T-IE-01094
[6 empty] | Return Date | IFR: 2019-02-01; R1 IFI: 2019-04-05
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-2003 | Process On-Line Analyzer And Analyzer Housing |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-01-10; R1 IFI: 2019-02-10
[6 empty] | Revised Plan | IFR: 2019-02-08; R1 IFI: 2019-03-14
[6 empty] | Issue Actual | IFR: 2019-02-08; R1 IFI: 2019-03-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00825; R1 IFI: TPSK-LSPA1-T-IE-01044
[6 empty] | Return Date | IFR: 2019-03-08; R1 IFI: 2019-05-09
Owner Cmmt* | bar: IFR to R1 IFI
| IE | OL1-2R06-3101 | Custody Transfer System |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-11-20; R1 IFI: 2019-01-21
[6 empty] | Revised Plan | IFR: 2018-11-26; R1 IFI: 2019-03-20
[6 empty] | Issue Actual | IFR: 2018-11-26; R1 IFI: 2019-03-20
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00357; R1 IFI: TPSK-LSPA1-T-IE-01094
[6 empty] | Return Date | IFR: 2019-02-01; R1 IFI: 2019-04-05
Owner Cmmt* | bar: IFR to R1 IFI
Category Code: R07 Project Specification (SP)
| ME | OL1-2R07-0001 | Tagging Procedure |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-07-27; R1 IFI: 2018-11-07
[6 empty] | Issue Actual | IFR: 2018-07-27; R1 IFI: 2018-11-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PM-00001; R1 IFI: TPSK-LSPA1-T-ME-00279
[6 empty] | Return Date | IFR: 2018-08-22; R1 IFI: 2019-04-01
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2R07-0009 | SP-009 Painting for 36M and 132U Furnace |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-23
[6 empty] | Issue Actual | IFR: 2018-10-23
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00214
Return Date
Owner Cmmt*
| ME | OL1-2R07-0010 | Equipment Preservation |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-10
[6 empty] | Issue Actual | IFR: 2018-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PE-00149
Return Date
Owner Cmmt*
| ME | OL1-2R07-0018 | Units Of Measurement |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-25
[6 empty] | Issue Actual | IFR: 2018-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00080
[6 empty] | Return Date | IFR: 2018-10-24
Owner Cmmt*
| IE | OL1-2R07-0020 | Electrical And Instrument Interface Philosophy |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2018-09-28; R1 IFI: 2019-01-21
[6 empty] | Revised Plan | IFR: 2018-10-04; R1 IFI: 2018-12-17
[6 empty] | Issue Actual | IFR: 2018-10-04; R1 IFI: 2018-12-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IE-00121; R1 IFI: TPSK-LSPA1-T-IE-00507
[6 empty] | Return Date | IFR: 2018-10-09; R1 IFI: 2018-12-26
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R07-0023 | Drafting Procedure For 2D Drawings |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-27; R1 IFI: 2019-04-18
[6 empty] | Issue Actual | IFR: 2018-09-27; R1 IFI: 2019-04-18; R1 IFD: 2019-05-29
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00089; R1 IFI: TPSK-LSPA1-T-ME-01386; R1 IFD: TPSK-LSPA1-T-ME-01755
[6 empty] | Return Date | IFR: 2018-10-24; R1 IFI: 2019-05-18
Owner Cmmt* | bar: IFR to R1 IFI
| ME | OL1-2R07-0024 | 3D Modeling |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-10
[6 empty] | Issue Actual | IFR: 2018-12-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00452
[6 empty] | Return Date | IFR: 2019-01-21
Owner Cmmt* | bar: IFR
| ME | OL1-2R07-0025 | Requirements For Eqipment Supplier 3D Model |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-28
[6 empty] | Issue Actual | IFR: 2018-09-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00108
[6 empty] | Return Date | IFR: 2018-10-24
Owner Cmmt*
| ME | OL1-2R07-0026 | Project Design Basis |  | Class 2 | Purpose** | IFR: IMP; R1 IFI: IMP
[6 empty] | Rev. | IFR: 0; R1 IFI: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-28
[6 empty] | Issue Actual | IFR: 2018-09-28; R1 IFI: 2019-05-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00110; R1 IFI: TPSK-LSPA1-T-ME-01547
[6 empty] | Return Date | IFR: 2018-10-24; R1 IFI: 2019-05-31
Owner Cmmt* | bar: R1 IFI
| ME | OL1-2R07-0027 | 3D Modeling Procedure For Piping Designers |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-13; R1 IFI: 2019-03-22
[6 empty] | Issue Actual | IFR: 2018-11-13; R1 IFI: 2019-03-22; R1 IFD: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00311; R1 IFI: TPSK-LSPA1-T-ME-01127; R1 IFD: TPSK-LSPA1-T-ME-02823
[6 empty] | Return Date | IFR: 2018-12-10; R1 IFI: 2019-04-12
Owner Cmmt* | bar: IFR to R1 IFI
Category Code: R08 Construction Specification (CON)
| IE | OL1-2R08-0001 | SPECIAL TEC.SP.FOR ERECT |  |  | Purpose** | IFR: IFQ; R1 IFI: IFP
Rev.
[6 empty] | Issue Plan | IFR: 2019-01-27; R1 IFI: 2019-03-27
[6 empty] | Revised Plan | IFR: 2019-10-18; R1 IFI: 2019-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2R08-0003 | Instrument Installation |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-02-15; R1 IFI: 2019-09-28
[6 empty] | Revised Plan | R1 IFI: 2018-10-04
[6 empty] | Issue Actual | R1 IFI: 2018-10-04
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-IE-00122
Return Date
Owner Cmmt*
Category Code: R91 Index/List
Category Code: R92 Procedures & Standards
| PM | OL1-2R92-0001 | Computerized Maintenance Management System CMMS - Ex Document Client reference OL1-2W92-0001 |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-28
[6 empty] | Issue Actual | IFR: 2019-01-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PM-00731
Return Date
Owner Cmmt*
Category Code: R93 Policy , Guidelines & Memo
| ME | OL1-2R93-2001 | GUIDELINE FOR CRACKING FURNACE CONSTRUCTION / ERECTION |  |  | Purpose** | IFR: IFR; R1 IFI: IFD; R1 IFD: IFF
Rev.
[6 empty] | Issue Plan | IFR: 2019-07-30; R1 IFI: 2019-09-03; R1 IFD: 2019-10-08
[6 empty] | Revised Plan | R1 IFI: 2019-10-16; R1 IFD: 2019-10-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: R94 Forms & Templates
Category Code: R95 Progress/Status Reports
Category Code: S01 Environmental Management Plan and program;
Category Code: S02 Waste Material Management
Category Code: S03 Health/Social Management and Program; Community Affairs Management
Category Code: S04 Environmental Management Report
Category Code: S05 Health/Social Management Report
Category Code: S06 ESIA Report
Category Code: S07 ESIA Database
Category Code: S63 EH&S Monitoring report
Category Code: S64 OSHE Review/Audit Report
Category Code: S71 Appraisal Report for Consultancy Service
Category Code: S72 Appraisal Report for EPC Contractor Work
Category Code: S73 Appraisal Report for Vendor/Supplier
Category Code: S81 CSR Procedure & Standard
Category Code: S82 CSR Policy, Guideline & Memo
Category Code: S83 CSR Template & Form
Category Code: S84 CSR Report
Category Code: S85 CSR Audit Report
Category Code: S90 Vendor Document/drawings
Category Code: S91 Index/List
Category Code: S92 Procedures & Standards
| ES | OL1-2S92-0001 | Project HSSE Plan |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-04
[6 empty] | Issue Actual | IFR: 2018-10-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ES-00129
Return Date
Owner Cmmt*
| ES | OL1-2S92-0002 | Incident Investigation And Reporting Procedure |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-10
[6 empty] | Issue Actual | IFR: 2018-10-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ES-00152
Return Date
Owner Cmmt*
| ES | OL1-2S92-0003 | SITE HSSE PLAN |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-25
[6 empty] | Issue Actual | IFR: 2019-02-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ES-00915
Return Date
Owner Cmmt*
| ES | OL1-2S92-0004 | Site Emergency and Evacuation Plan |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-15
[6 empty] | Issue Actual | IFR: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA-1--ES-01069
Return Date
Owner Cmmt*
| ES | OL1-2S92-0005 | Construction Environmental And Social Management Plan (CESMP) |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-27
[6 empty] | Issue Actual | IFR: 2019-03-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ES-01163
Return Date
Owner Cmmt*
| ES | OL1-2S92-0006 | HAZOP Procedure |  |  | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | R1 IFI: 0
[6 empty] | Issue Plan | IFR: 2019-04-10; R1 IFI: 2019-05-10
[6 empty] | Revised Plan | R1 IFI: 2019-03-28
[6 empty] | Issue Actual | R1 IFI: 2019-03-28
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-ES-01175
[6 empty] | Return Date | R1 IFI: 2019-04-22
Owner Cmmt* | bar: R1 IFI
| ES | OL1-2S92-0007 | SIL Study Procedure |  |  | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | R1 IFI: 0; R1 IFD: 1
[6 empty] | Issue Plan | IFR: 2019-04-10; R1 IFI: 2019-05-10
[6 empty] | Revised Plan | R1 IFI: 2019-03-29
[6 empty] | Issue Actual | R1 IFI: 2019-03-29; R1 IFD: 2019-05-07
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSAP1-T-ES-01190; R1 IFD: TPSK-LSPA1-T-ES-01572
[6 empty] | Return Date | R1 IFI: 2019-04-22; R1 IFD: 2019-06-21
Owner Cmmt* | bar: R1 IFI to R1 IFD
| ES | OL1-2S92-0008 | Site Hazard Identification Plan |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-04
[6 empty] | Issue Actual | IFR: 2019-09-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ES-02561
Return Date
Owner Cmmt*
| ES | OL1-2S92-0009 | Site Work Permit Procedure |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-28
[6 empty] | Issue Actual | IFR: 2019-09-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ES-02719
Return Date
Owner Cmmt*
| SE | OL1-2S92-0010 | Site Security Plan |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-10-15
[6 empty] | Issue Actual | IFR: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-02822
Return Date
Owner Cmmt*
| ES | OL1-2S92-0011 | Site Traffic Management Plan |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-SE-02821
Return Date
Owner Cmmt*
Category Code: S93 Policy , Guidelines & Memo
Category Code: S94 Forms & Templates
Category Code: S95 Progress/Status Reports
| ES | OL1-2S95-0210 | Furnace Section HAZOP Report |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-21; R1 IFI: 2019-08-27
[6 empty] | Issue Actual | IFR: 2019-03-21; R1 IFI: 2019-08-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ES-01113; R1 IFI: TPSK-LSPA1-T-ES-02490
[6 empty] | Return Date | IFR: 2019-04-22
Owner Cmmt* | bar: IFR
| ES | OL1-2S95-0230 | Furnace Section SIL Classification Report |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFD
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-03-26; R1 IFI: 2019-08-27
[6 empty] | Issue Actual | IFR: 2019-03-26; R1 IFI: 2019-08-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ES-01146; R1 IFI: TPSK-LSPA1-T-ES-02490
[6 empty] | Return Date | IFR: 2019-04-22
Owner Cmmt* | bar: IFR
| SE | OL1-2S95-0231 | Recovery Process and Utilities Sections SIL Classification Report |  |  | Purpose** | IFR: IMP
Rev.
[6 empty] | Issue Plan | IFR: 2020-03-10
[6 empty] | Revised Plan | IFR: 2020-03-10
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ES | OL1-2S95-0235 | Wet Air Oxidation Package SIL Classification Report (Tag No 10-PK-2350) |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-10-15
[6 empty] | Issue Actual | IFR: 2019-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ES-02825
Return Date
Owner Cmmt*
Category Code: T01 Design basis
| EE | OL1-2T01-0001 | Job Supply Specification For Intercom Paging And Audible Alarm System -Ex Document Client Reference OL1-2T92-0001 |  |  | Purpose** | IFR: IFR; R1 IFI: IFF
Rev. | bar: R1 IFI
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-15
[6 empty] | Revised Plan | R1 IFI: 2019-07-01
[6 empty] | Issue Actual | R1 IFI: 2019-07-01
[6 empty] | Transmittal no. | R1 IFI: TPSK-LSPA1-T-EE-02025
[6 empty] | Return Date | R1 IFI: 2019-07-08
Owner Cmmt* | bar: R1 IFI
| EE | OL1-2T01-0002 | Job Supply Specification For Safety Supervisory System - Ex Doc Client Ref OL1-2T92-0002 |  |  | Purpose** | IFR: IFR; R1 IFI: IFF; R1 IFD: IMP
[6 empty] | Rev. | IFR: B; R1 IFD: 0
[6 empty] | Issue Plan | IFR: 2019-04-15; R1 IFI: 2019-05-15
[6 empty] | Revised Plan | IFR: 2019-03-06; R1 IFD: 2019-07-19
[6 empty] | Issue Actual | IFR: 2019-03-06; R1 IFD: 2019-07-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00985; R1 IFD: TPSK-LSPA1-T-EE-02181
[6 empty] | Return Date | IFR: 2019-03-21; R1 IFD: 2019-08-01
Owner Cmmt* | bar: IFR; R1 IFD
| EE | OL1-2T01-0028 | Telecom Numbering |  |  | Purpose** | IFR: IFR; R1 IFI: IFR; R1 IFD: IFR; R1 IFF: IMP
[6 empty] | Rev. | IFR: C; R1 IFI: A; R1 IFD: B
[6 empty] | Issue Plan | IFR: 2019-01-21; R1 IFF: 2019-02-15
Revised Plan
[6 empty] | Issue Actual | R1 IFI: 2019-02-22; R1 IFD: 2019-08-05
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02804; R1 IFI: TPSK-LSPA1-T-EE-00905; R1 IFD: TPSK-LSPA1-T-EE-02310
[6 empty] | Return Date | R1 IFI: 2019-03-04; R1 IFD: 2019-08-08
Owner Cmmt* | bar: R1 IFI to R1 IFD
Category Code: T02 Abbreviation and standard symbols
Category Code: T03 Project Communication, IT, and Safety Supervisory System specification
Category Code: T04 System philosophy
Category Code: T05 Equipment datasheets
Category Code: T10 Intercom/Paging/Audible Alarm system equipment data sheets
Category Code: T11 Intercom/Paging/Audible Alarm system schematic diagram
| EE | OL1-2T11-0001 | Telecomm Syst Architecture Of Intercom Paging and Audible Alarm Systems |  |  | Purpose** | IFR | IFR | IFR | IBD | IDD
[6 empty] | Rev. | IFR: A; R1 IFI: B; R1 IFD: C
[6 empty] | Issue Plan | IFR: 2019-01-09; R1 IFF: 2019-01-09; R1 IMP: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-03-05
[6 empty] | Issue Actual | IFR: 2019-03-05; R1 IFI: 2019-05-10; R1 IFD: 2019-07-01
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00976; R1 IFI: TPSK-LSPA1-T-EE-01624; R1 IFD: TPSK-LSPA1-T-EE-02024
[6 empty] | Return Date | IFR: 2019-03-21; R1 IFI: 2019-05-26; R1 IFD: 2019-07-22
Owner Cmmt* | bar: IFR to R1 IFD
Category Code: T12 Intercom/Paging/Audible Alarm aystem layout
| EE | OL1-2T12-0002 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT COMMON AREA |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0003 | Telecom and Security System Devices Layout- Metering |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02171
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0004 | TELECOM & SECURITY SYSTEMS DEVICES LAYOUT MAIN PIPE RACK |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-0005 | Telecom And Security System Devices Layout- Area Substation E And FAR E |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0006 | Telecom And Security System Devices Layout- Sub C And Far C |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-19; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02183
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0007 | Telecom And Security System Devices Layout- Furnace Utility |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0008 | Telecom and Security System Devices Layout- Quench |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0009 | Telecom And Security System Devices Layout- C3 Hydrogenation |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0010 | Telecom And Security System Devices Layout- Hot Fractionation - GHU Unit |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0011 | Telecom And Security System Devices Layout- Process Cold Compressors |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0012 | Telecom And Security System Devices Layout- Process Cracked Gas Compressor |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0014 | Telecom And Security System Devices Layout- Cooling Water Unit |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0015 | Telecom And Security System Devices Layout- Utilities |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0016 | Telecom and Security System Devices Layout- Waste Water Treatment |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02161
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0017 | Telecom And Security System Devices Layout- Flare Area Sub-Substation F and FAR FL Area |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02171
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0018 | Telecom And Security System Devices Layout - Process 3A |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev. | bar: IFR
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Revised Plan | IFR: 2019-07-17; R1 IFI: 2020-01-31; R1 IFD: 2020-07-15
[6 empty] | Issue Actual | IFR: 2019-07-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02171
[6 empty] | Return Date | IFR: 2019-08-12
Owner Cmmt* | bar: IFR
| EE | OL1-2T12-0102 | Zone 0M Tel Main Cable Tray Rout Metering |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-09-28
[6 empty] | Issue Actual | IFR: 2019-09-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0103 | Telecom Main Cable Tray Routing Main Pipe Rack |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0104 | Telecom Main Cable Tray Rout SUB E and FAR E |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0105 | Zone 3S Telecom Main Cable Tray Routing Area SUB C and FAR C |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0107 | Zone 2A Telecom Main Cable Tray Routing Quench |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0109 | Telecom Main Cable Tray Routing Hot Fractionation GHU Unit |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0110 | Zone 2D Telecom Main Cable Tray Routing Process Cold Compressors |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0111 | Zone 2E Telecom Main Cable Tray Routing Crack Gas Compressor |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0112 | Zone 3A Telecom Main Cable Tray Routing Butadiene |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0113 | Zone 5T Telecom Main Cable Tray Routing Cooling Water Unit |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0114 | Zone 5U Telecom Main Cable Tray Routing Utilities |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0115 | Zone 5W Telecom Main Cable Tray Routing Waste Water Treatment |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-0116 | Zone 5F Telecom Main Cable Tray Routing Flare Area |  | Class 1 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
Revised Plan
Issue Actual
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-02715
Return Date
Owner Cmmt*
| EE | OL1-2T12-1020 | TELECOM LOCATION AND CABLE ROUTING FAR E AND SUB E |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-1021 | TELECOM LOCATION AND CABLE ROUTING FAR C AND SUB C |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-1022 | TELECOM LOCATION AND CABLE ROUTING FAR FL |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T12-1023 | TELECOM LOCATION AND CABLE ROUTING CENTRAL CONTROL BUILDING |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T13 Intercom/Paging/Audible Alarm aystem wiring layout
| EE | OL1-2T13-1001 | TELECOM WIRING DRAWINGS FOR FAR-E SYSTEMS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2020-02-28; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1002 | TELECOM WIRING DRAWINGS FOR FAR-C SYSTEMS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2020-02-28; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1003 | TELECOM WIRING DRAWINGS FOR FAR-FL SYSTEMS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2020-02-28; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T13-1004 | TELECOM WIRING DRAWINGS FOR CCB SYSTEMS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2020-02-28; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2020-02-28; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T14 Cable drum schedule for Intercom/Paging/Audible Alarm aystem
Category Code: T15 Cable schedule for Intercom/Paging/Audible Alarm aystem
Category Code: T16 Connection List for Intercom/Paging/Audible Alarm aystem
| EE | OL1-2T16-1001 | TELECOM CABLE LIST FOR FAR C SYSTEMS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R1 IFI: 2020-08-15; R1 IFD: 2020-11-15; R1 IFF: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-15; R1 IFI: 2020-08-15; R1 IFD: 2020-11-15; R1 IFF: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1002 | TELECOM CABLE LIST FOR FAR E SYSTEMS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R1 IFI: 2020-08-15; R1 IFD: 2020-11-15; R1 IFF: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-15; R1 IFI: 2020-08-15; R1 IFD: 2020-11-15; R1 IFF: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1003 | TELECOM CABLE LIST FOR FAR FL SYSTEMS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R1 IFI: 2020-08-15; R1 IFD: 2020-11-15; R1 IFF: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-15; R1 IFI: 2020-08-15; R1 IFD: 2020-11-15; R1 IFF: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T16-1004 | TELECOM CABLE LIST FOR CCB AND OTHER BULDINGS SYSTEMS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC1; R1 IFF: IFC2
Rev.
[6 empty] | Issue Plan | IFR: 2020-05-15; R1 IFI: 2020-08-15; R1 IFD: 2020-11-15; R1 IFF: 2021-01-31
[6 empty] | Revised Plan | IFR: 2020-05-15; R1 IFI: 2020-08-15; R1 IFD: 2020-11-15; R1 IFF: 2021-01-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T17 Bill of quantities for Intercom/Paging/Audible Alarm aystem
| EE | OL1-2T17-0001 | TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-04; R1 IFI: 2020-02-28; R1 IFD: 2020-08-30
[6 empty] | Revised Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2T17-0002 | TELECOMM. & SUPERVISORY SYSTEMS EQUIPMENT LIST FOR OTHER CONTRACTORS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-03-04; R1 IFI: 2020-02-28; R1 IFD: 2020-08-30
[6 empty] | Revised Plan | IFR: 2019-12-31; R1 IFI: 2020-02-28; R1 IFD: 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T18 Typical drawing for Intercom/Paging/Audible Alarm aystem
Category Code: T20 Computer Network (LAN) and Telephone system equipment data sheets
Category Code: T21 Computer Network (LAN) and Telephone system schematic diagram
Category Code: T22 Computer Network (LAN) and Telephone system layout
Category Code: T23 Computer Network (LAN) and Telephone system wiring layout
Category Code: T24 Cable drum schedule for Computer Network (LAN) and Telephone system
Category Code: T25 Cable schedule for Computer Network (LAN) and Telephone system
Category Code: T26 Connection List for Computer Network (LAN) and Telephone system
| EE | OL1-2T26-0001 | FIBRE OPTIC TERMINATION DRAWINGS |  |  | Purpose** | IFR: IFR; R1 IFI: IDD; R1 IFD: IFC
Rev.
[6 empty] | Issue Plan | IFR: 2019-11-30; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
[6 empty] | Revised Plan | IFR: 2019-11-30; R1 IFI: 2020-02-28; R1 IFD: 2020-08-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: T27 Bill of quantities for Computer Network (LAN) and Telephone system
Category Code: T28 Typical drawing for Computer Network (LAN) and Telephone system
Category Code: T30 CCTV, Access Control, and Intrusion Alarm system equipment data sheets
Category Code: T31 CCTV, Access Control, and Intrusion Alarm system schematic diagram
| EE | OL1-2T31-0001 | Telecomm Syst Architecture Of Safety Supervisory System |  |  | Purpose** | IFR: IFR; R1 IFI: IBD; R1 IFD: IDD
Rev. | bar: IFR to R1 IFI
[6 empty] | Issue Plan | IFR: 2019-01-09; R1 IFI: 2019-01-09; R1 IFD: 2019-02-28
[6 empty] | Revised Plan | IFR: 2019-03-05; R1 IFI: 2019-05-10
[6 empty] | Issue Actual | IFR: 2019-03-05; R1 IFI: 2019-05-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00976; R1 IFI: TPSK-LSPA1-T-EE-01624
[6 empty] | Return Date | IFR: 2019-03-21; R1 IFI: 2019-05-26
Owner Cmmt* | bar: IFR to R1 IFI
Category Code: T32 CCTV, Access Control, and Intrusion Alarm system layout
Category Code: T33 CCTV, Access Control, and Intrusion Alarm system wiring layout
Category Code: T34 Cable drum schedule for CCTV, Access Control, and Intrusion Alarm system
Category Code: T35 Cable schedule for CCTV, Access Control, and Intrusion Alarm system
Category Code: T36 Connection List for CCTV, Access Control, and Intrusion Alarm system
Category Code: T37 Bill of quantities for CCTV, Access Control, and Intrusion Alarm system
Category Code: T38 Typical drawing for CCTV, Access Control, and Intrusion Alarm system
Category Code: T40 Fire Alarm system equipment data sheets
Category Code: T41 Fire Alarm system schematic diagram
Category Code: T42 Fire alarm system layout
Category Code: T43 Fire alarm system wiring layout
Category Code: T44 Cable drum schedule for Fire alarm system
Category Code: T45 Cable schedule for Fire alarm system
Category Code: T46 Connection List for Fire alarm system
Category Code: T47 Bill of quantities forFire alarm system
Category Code: T48 Typical drawing for Fire alarm system
Category Code: T60 Application software system
Category Code: T61 Application software Procedure
Category Code: T71 Appraisal Report for Consultancy Service
Category Code: T72 Appraisal Report for EPC Contractor Work
Category Code: T73 Appraisal Report for Vendor/Supplier
Category Code: T90 Vendor documents
Category Code: T91 Index/List
Category Code: T92 Procedures & Standards
| EE | OL1-2T92-0001 | Job Supply Specification For Intercom Paging Audible Alarm System - For Next Revision See Document OL1-2T01-0001 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-03
[6 empty] | Issue Actual | IFR: 2019-01-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00577
[6 empty] | Return Date | IFR: 2019-01-23
Owner Cmmt* | bar: IFR
| EE | OL1-2T92-0002 | Job Supply Specification For Safety Supervisory System - For Next Revision See Document OL1-2T01-0002 |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-03
[6 empty] | Issue Actual | IFR: 2019-01-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-EE-00577
[6 empty] | Return Date | IFR: 2019-01-23
Owner Cmmt* | bar: IFR
Category Code: T93 Policy , Guidelines & Memo
Category Code: T94 Forms & Templates
Category Code: T95 Progress/Status Reports
Category Code: U02 Finance Reports
Category Code: U03 Certification(Finance)
Category Code: U07 Bond and other financial security for Consultancy Service
Category Code: U08 Bond and other financial security for EPC Contractor
Category Code: U09 Bond and other financial security for Vendor/Supplier
Category Code: U11 Certificates of Insurance
Category Code: U12 Insurance Policies and Guarantees
Category Code: U71 Appraisal Report for Consultancy Service
Category Code: U72 Appraisal Report for EPC Contractor Work
Category Code: U73 Appraisal Report for Vendor/Supplier
Category Code: U91 Index/List
Category Code: U92 Procedures & Standards
Category Code: U93 Policy , Guidelines & Memo
Category Code: U94 Forms & Templates
Category Code: U95 Progress/Status Reports
Category Code: V04 Interface Matrix (Responsibility Matrix)
Category Code: V71 Appraisal Report for Consultancy Service
Category Code: V72 Appraisal Report for EPC Contractor Work
Category Code: V73 Appraisal Report for Vendor/Supplier
Category Code: V91 Index/List
Category Code: V92 Procedures & Standards
| IF | OL1-2V92-0014 | Interface Management Plan |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IFA
Rev. | bar: IFR to R1 IFI
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-08; R1 IFI: 2019-01-22
[6 empty] | Issue Actual | IFR: 2018-10-08; R1 IFI: 2019-01-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-IF-00138; R1 IFI: TPSK-LSPA1-T-IF-00703
[6 empty] | Return Date | IFR: 2018-10-25
Owner Cmmt* | bar: IFR
Category Code: V93 Policy , Guidelines & Memo
Category Code: V94 Forms & Templates
Category Code: V95 Progress/Status Reports
Category Code: W01 Work Breakdown Structure
| PC | OL1-2W01-0001 | Plant And Section Codes |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-13; R1 IFI: 2018-09-25
[6 empty] | Issue Actual | IFR: 2018-08-13; R1 IFI: 2018-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00019; R1 IFI: TPSK-LSPA1-T-PC-00076
[6 empty] | Return Date | IFR: 2018-08-22
Owner Cmmt* | bar: IFR
| PC | OL1-2W01-0002 | Plant And Zone Codes |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-25
[6 empty] | Issue Actual | IFR: 2018-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00077
[6 empty] | Return Date | IFR: 2018-10-17
Owner Cmmt* | bar: IFR
Category Code: W71 Appraisal Report for Consultancy Service
Category Code: W72 Appraisal Report for EPC Contractor Work
Category Code: W73 Appraisal Report for Vendor/Supplier
Category Code: W90 Technical Report
| PM | OL1-2W90-0001 | Firefighting basic design report for package A1 |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 0; R1 IFI: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-13
[6 empty] | Issue Actual | IFR: 2018-08-13; R1 IFI: 2018-10-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00020; R1 IFI: TPSK-LSPA1-T-PM-00187
[6 empty] | Return Date | IFR: 2018-08-20
Owner Cmmt* | bar: IFR
Category Code: W91 Index/List
Category Code: W92 Procedures & Standards
| PC | OL1-2W92-0001 | Coordination Procedure |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-07-27
[6 empty] | Issue Actual | IFR: 2018-07-27
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PM-00001
[6 empty] | Return Date | IFR: 2018-08-22
Owner Cmmt*
| PM | OL1-2W92-0003 | Project Document Coding |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-07-27; R1 IFI: 2018-10-30
[6 empty] | Issue Actual | IFR: 2018-07-27; R1 IFI: 2018-10-30; R1 IFD: 2019-03-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PM-00001; R1 IFI: TPSK-LSPA1-T-PC-00240; R1 IFD: TPSK-LSPA1-T-PC-01041
[6 empty] | Return Date | IFR: 2018-08-22
Owner Cmmt*
| PC | OL1-2W92-0004 | Document Management Procedure |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-09; R1 IFI: 2019-03-15
[6 empty] | Issue Actual | IFR: 2018-08-09; R1 IFI: 2019-03-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00013; R1 IFI: TPSL-LSPA1-T-PC-01062
[6 empty] | Return Date | IFR: 2018-08-29
Owner Cmmt* | bar: IFR
| PC | OL1-2W92-0005 | Requirements For Vendor Documentation And Exchange Of Correspondence |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-29; R1 IFI: 2019-01-24
[6 empty] | Issue Actual | IFR: 2018-11-29; R1 IFI: 2019-01-24; R1 IFD: 2019-06-10
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00385; R1 IFI: TPSK-LSPA1-T-PC-00717; R1 IFD: TPSK-LSPA1-T-PC-01790
[6 empty] | Return Date | R1 IFD: 2019-06-27
Owner Cmmt* | bar: R1 IFD
| PC | OL1-2W92-0006 | TPSK Project Directorate Organization Chart |  | Class 2 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-08-07
[6 empty] | Issue Actual | IFR: 2018-08-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00010
Return Date
Owner Cmmt*
| PC | OL1-2W92-0007 | TPSK Roc Organization Chart |  | Class 2 | Purpose** | IFR: IFI
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-03
[6 empty] | Issue Actual | IFR: 2018-09-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00030
Return Date
Owner Cmmt*
| PC | OL1-2W92-0009 | Criticality Rating Procedure |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-06; R1 IFI: 2019-01-14
[6 empty] | Issue Actual | IFR: 2018-09-06; R1 IFI: 2019-01-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00033; R1 IFI: TPSK-LSPA1-T-PC-00642
[6 empty] | Return Date | IFR: 2018-10-01
Owner Cmmt* | bar: IFR
| PC | OL1-2W92-0010 | Prescriptions For Preparation Of Vendor Data Book |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-07; R1 IFI: 2019-02-07
[6 empty] | Issue Actual | IFR: 2018-12-07; R1 IFI: 2019-02-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00435; R1 IFI: TPSK-LSPA1-T-PC-00824
[6 empty] | Return Date | R1 IFI: 2019-05-30
Owner Cmmt* | bar: R1 IFI
| PC | OL1-2W92-0011 | TPSK HOC Organization Chart |  | Class 2 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-08
[6 empty] | Issue Actual | IFR: 2018-10-08
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PM-00146
Return Date
Owner Cmmt*
| PC | OL1-2W92-0012 | ITC Plan |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-19; R1 IFI: 2019-04-24
[6 empty] | Issue Actual | IFR: 2018-10-19; R1 IFI: 2019-04-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PM-00197; R1 IFI: TPSK-LSPA1-T-PC-01444
Return Date
Owner Cmmt*
| PC | OL1-2W92-0013 | Project Execution Plan |  | Class 2 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-02
[6 empty] | Issue Actual | IFR: 2018-10-02
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00118
Return Date
Owner Cmmt*
| PC | OL1-2W92-0015 | Prescriptions For Preparation Of Manufacturing Data Record Book |  | Class 2 | Purpose** | IFR: IFR; R1 IFI: IMP; R1 IFD: IMP
[6 empty] | Rev. | IFR: A; R1 IFI: 0; R1 IFD: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-13; R1 IFI: 2018-11-09
[6 empty] | Issue Actual | IFR: 2018-09-13; R1 IFI: 2018-11-09; R1 IFD: 2019-03-22
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00047; R1 IFI: TPSK-LSPA1-T-PC-00296; R1 IFD: TPSK-LSPA1-T-PC-01135
[6 empty] | Return Date | R1 IFD: 2019-06-16
Owner Cmmt* | bar: R1 IFD
| PC | OL1-2W92-0016 | Reporting Procedure |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-09-25
[6 empty] | Issue Actual | IFR: 2018-09-25
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00083
[6 empty] | Return Date | IFR: 2019-03-11
Owner Cmmt* | bar: IFR
| PC | OL1-2W92-0018 | Engineering Execution Plan |  | Class 2 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-15
[6 empty] | Issue Actual | IFR: 2018-10-15
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PM-00170
Return Date
Owner Cmmt*
| PC | OL1-2W92-0019 | Project Control Procedure |  | Class 2 | Purpose** | IFR: IMP
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-11
[6 empty] | Issue Actual | IFR: 2018-10-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00156
Return Date
Owner Cmmt*
| PC | OL1-2W92-0020 | TPSK SOC Organization Chart |  | Class 2 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-11
[6 empty] | Issue Actual | IFR: 2018-10-11
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00157
Return Date
Owner Cmmt*
| PC | OL1-2W92-0021 | TPSK KLOC Organization Chart |  | Class 2 | Purpose** | IFR: IFI; R1 IFI: IFI; R1 IFD: IFI
[6 empty] | Rev. | IFR: 0; R1 IFI: 1; R1 IFD: 2
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-15
[6 empty] | Issue Actual | IFR: 2018-10-15; R1 IFI: 2019-01-31; R1 IFD: 2019-07-19
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00171; R1 IFI: TPSK-LSPA1-T-PC-00761; R1 IFD: TPSK-LSPA1-T-PC-02182
Return Date
Owner Cmmt*
| PC | OL1-2W92-0022 | Computerized Maintenance Management System CMMS |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-01-03
[6 empty] | Issue Actual | IFR: 2019-01-03
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00578
Return Date
Owner Cmmt*
| PC | OL1-2W92-0023 | Lsp Document Coding |  | Class 2 | Purpose** | IFR: IFR
Rev. | bar: IFR
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-05-17
[6 empty] | Issue Actual | IFR: 2019-05-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-01674
[6 empty] | Return Date | IFR: 2019-05-30
Owner Cmmt* | bar: IFR
| PC | OL1-2W92-2122 | Project Engineering Plan - Package A1 - Furnaces - Houston Scope (Internal Only) |  | Class 2 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-10-24
[6 empty] | Issue Actual | IFR: 2018-10-24
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PM-00220
Return Date
Owner Cmmt*
Category Code: W93 Policy , Guidelines & Memo
Category Code: W94 Forms & Templates
Category Code: W95 Progress/Status Reports
Category Code: X71 Appraisal Report for Consultancy Service
Category Code: X72 Appraisal Report for EPC Contractor Work
Category Code: X73 Appraisal Report for Vendor/Supplier
Category Code: X91 Index/List
Category Code: X92 Procedures & Standards
Category Code: X93 Policy , Guidelines & Memo
Category Code: X94 Forms & Templates
Category Code: X95 Progress/Status Reports
Category Code: Y01 Bidding Guideline
Category Code: Y02 Bidding Committee Assignment
Category Code: Y03 Bidding Policy
Category Code: Y04 Pre-Qualification Document
Category Code: Y05 List of qualified Bidders
Category Code: Y06 Bidding Evaluation Criteria for Consultancy Service
Category Code: Y07 Bidding Evaluation Criteria for EPC Contractor
Category Code: Y08 Bidding Evaluation Criteria for Vendor/Supplier
Category Code: Y09 Contractor Selection Plan
Category Code: Y13 ITB Structure
Category Code: Y21 Tender or ITB Document for Consultancy service
Category Code: Y22 Tender or ITB Document for EPC Contractor
Category Code: Y23 Tender or ITB Document for Vendor/Supplier
| ME | OL1-2Y23-2001 | Technical Bid Tabulation for Convection Tubes |  | Class 3 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-04
[6 empty] | Issue Actual | IFR: 2018-12-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00404
Return Date
Owner Cmmt*
| PC | OL1-2Y23-2002 | Technical Bid Tabulation for Convection Fittings |  | Class 3 | Purpose** | IFR: IFI; R1 IFI: IFI
[6 empty] | Rev. | IFR: 0; R1 IFI: 1
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-20
[6 empty] | Issue Actual | IFR: 2018-12-20; R1 IFI: 2019-01-07
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00545; R1 IFI: TPSK-LSPA1-T-PC-00591
Return Date
Owner Cmmt*
| ME | OL1-2Y23-2003 | Technical Bid Tabulation for Quench Exchangers |  | Class 3 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-11-28
[6 empty] | Issue Actual | IFR: 2018-11-28
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00380
Return Date
Owner Cmmt*
| PC | OL1-2Y23-2004 | Technical Bid Tabulation for Radiant Coils |  | Class 3 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-13
[6 empty] | Issue Actual | IFR: 2018-12-13
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-PC-00490
Return Date
Owner Cmmt*
| ME | OL1-2Y23-2006 | Technical Bid Tabulation For Burners |  | Class 3 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-04
[6 empty] | Issue Actual | IFR: 2019-02-04
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00789
[6 empty] | Return Date | IFR: 2019-02-21
Owner Cmmt* | bar: IFR
| ME | OL1-2Y23-2007 | Technical Bid Tabulation for Cast Intermediate Tube Supports |  | Class 3 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-17
[6 empty] | Issue Actual | IFR: 2018-12-17
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00519
Return Date
Owner Cmmt*
| ME | OL1-2Y23-2008 | Technical Bid Tabulation for Peep Doors |  | Class 3 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2019-02-06
[6 empty] | Issue Actual | IFR: 2019-02-06
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00813
[6 empty] | Return Date | IFR: 2019-02-21
Owner Cmmt* | bar: IFR
| ME | OL1-2Y23-2018 | Technical Bid Tabulation for Furnace Steam Drums |  | Class 3 | Purpose** | IFR: IFI
[6 empty] | Rev. | IFR: 0
Issue Plan
[6 empty] | Revised Plan | IFR: 2018-12-14
[6 empty] | Issue Actual | IFR: 2018-12-14
[6 empty] | Transmittal no. | IFR: TPSK-LSPA1-T-ME-00500
Return Date
Owner Cmmt*
Category Code: Y31 Tender or ITB clarification records for Consultancy service
Category Code: Y32 Tender or ITB clarification records for EPC Contractor
Category Code: Y33 Tender or ITB clarification records for Vendor/Supplier
Category Code: Y41 Proposal Document of Consultancy service bidding
Category Code: Y42 Proposal Document of EPC Contractor bidding
Category Code: Y43 Proposal Document of Vendor/Supplier bidding
Category Code: Y51 Proposal clarification records for Consultancy service
Category Code: Y52 Proposal clarification records for EPC Contractor
Category Code: Y53 Proposal clarification records for Vendor/Supplier
Category Code: Y61 Un-Priced Commerical proposals evaluation report
Category Code: Y62 Priced Commercial proposals evaluation report
Category Code: Y63 Bid Evaluation Report (Technical & Un-priced Commercial proposal )
Category Code: Y64 Bid Evaluation report (Executive Summary)
Category Code: Y65 Nomination of successful bidder for approval
Category Code: Y66 EPC Contract Negotiation, Compliance Report
Category Code: Y71 Appraisal Report for Consultancy Service
Category Code: Y72 Appraisal Report for EPC Contractor Work
Category Code: Y73 Appraisal Report for Vendor/Supplier
Category Code: Y81 Consultancy Service Bidding Records
Category Code: Y82 EPC Contractor Bidding Records
Category Code: Y83 Vendor/Supplier Bidding Records