## CPY_Format
|  |  |  | Master Document Index (MDI) |  | ABBREVIATION | [7 empty] | DOCUMENT NO. | REV.
[6 empty] | **Revision Purpose of Issued Document |  |  |  | *Owner Feedback (Comment) |  | ***Classification
[6 empty] | IFR = Issue For Review |  | IFF = Issue For Final |  | A1 = App. w/o comments | R1 = No comments | Class 1 = For Approval |  | LSP-2W91-0001 | A
[6 empty] | IFA = Issue For Approval |  | ASB = Issue For As-Built |  | A2 = App. with comments, re-submit not required | R2 = Comments as noted | Class 2 = For Review
[6 empty] | IFC = Issue For Construction |  | AFC = Approved for Construction |  | A3 = App. with comments, re-submit for review |  | Class 3 = For Information
Owner: |  | Long Son Pterochemicals C0., Ltd. |  | Plant Name: PACKAGE A1: OLEFINS PLANT |  | IFI = Issue For Information |  | IMP = Issue for Implementation |  | A4 = Not App., re-submit for approval |  |  |  | Issue Date
|  |  |  | Att. To OL1-2W91-0001 036909C-1000-NM-107 |  | IFP = Issue For Planning |  | / Execution
Document Code : | [5 empty] | IFD = Issue For Design |  | CAN = Issue for Cancellation |  | Period for Company's comment |  | __________ | Working Days
Item | Org. | Document No. | Document Name |  | Classification
Category Code: =Index!B30 =Index!C30
Category Code: A03 Technology transfer dossiers
Category Code: A04 Confidentiality Agreements
Category Code: A05 Laws and Regulations
Category Code: A06 Local content
Category Code: A09 Arbitration and Dispute Resolution
Category Code: A10 Guarantee of Labour Payment Affidavit
Category Code: A11 Termination or Amendment of Contracts
Category Code: A12 Liquidation Contract
Category Code: A13 Claim & Complaint from contractors
Category Code: A14 Claim & Complaint to contractors
Category Code: A15 Variation Change Notice
Category Code: A16 ITC - Instruction to Contractor
Category Code: A17 Contract Variation Form
Category Code: A18 License Agreement
Category Code: A19 Supplement Dossier
Category Code: A20 Certificates
Category Code: A21 Approval Letter
Category Code: A30 Certificate of Work Completion
Category Code: A41 Power of Attorney
Category Code: A42 Power of Attorney
Category Code: A43 Power of Attorney
Category Code: A44 Power of Attorney
Category Code: A51 Contract Document of Consultancy Service
Category Code: A52 Contract Document of EPC Contractor
Category Code: A53 Contract Document of Vendor/Supplier
Category Code: A61 Records of Management of Change (before final investment decision)
Category Code: A62 Records of Management of Change (after final investment decision)
Category Code: A71 Appraisal Report for Consultancy Service
Category Code: A72 Appraisal Report for EPC Contractor Work
Category Code: A73 Appraisal Report for Vendor/Supplier
Category Code: A91 Index/List
Category Code: A92 Procedures & Standards
Category Code: A93 Policy , Guidelines & Memo
Category Code: A94 Forms & Templates
Category Code: A95 Progress/Status Reports
Category Code: B01 Project Schedule
Category Code: B71 Appraisal Report for Consultancy Service
Category Code: B72 Appraisal Report for EPC Contractor Work
Category Code: B73 Appraisal Report for Vendor/Supplier
Category Code: B91 Index/List
Category Code: B92 Procedures & Standards
Category Code: B93 Policy , Guidelines & Memo
Category Code: B94 Forms & Templates
Category Code: B95 Progress/Status Reports
Category Code: C01 Subvendor List
Category Code: C10 Request for Quotation (RFQ) for Civil work (Engineering and Procurement)
Category Code: C11 Request for Quotation (RFQ) for Building work (Engineering and Procurement)
Category Code: C12 Request for Quotation (RFQ) for Steel Structure work (Engineering and Procurement)
| CV | OL1-2C12-000001 | Material Requisition For Steel Structures |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-06 | 2019-09-13
[6 empty] | Revised Plan | 2019-03-11 | 2019-10-10
[6 empty] | Issue Actual | 2019-03-11 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-1010 | TPSK-LSPA1-T-PL-02768
[6 empty] | Return Date | 2019-05-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2C12-307000 | Material Requisition for Radiant Steel Panel - Ex Document Client Reference OL1-2C12-301000 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-07-16 | 2019-10-21
[6 empty] | Revised Plan | 2019-04-03 | 2019-05-21
[6 empty] | Issue Actual | 2019-04-03 | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01229 | TPSK-LSPA1-T-PL-01699
[6 empty] | Return Date |  | 2019-10-15
[6 empty] | Owner Cmmt* |  | R2
| ME | OL1-2C12-308000 | Material Requisition for Utility Steel |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-07-16 | 2019-10-21
[6 empty] | Revised Plan | 2019-06-21 | 2019-10-10
[6 empty] | Issue Actual | 2019-06-21 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01952 | TPSK-LSPA1-T-PL-02784
[6 empty] | Return Date | 2019-10-15
[6 empty] | Owner Cmmt* | R2
Category Code: C13 Request for Quotation (RFQ) for Mechanical work (Engineering and Procurement)
| ME | OL1-2C13-100000 | Material Requisition For Shop Assembled Large Columns Requisition For Purchase |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-15 | 2019-09-26
[6 empty] | Revised Plan | 2019-01-07 | 2019-05-02
[6 empty] | Issue Actual | 2019-01-07 | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00586 | TPSK-LSPA1-T-PL-01526
[6 empty] | Return Date | 2019-01-24 | 2019-05-20
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-101000 | Material Requisition For Shop Assembled Columns Requisition For Purchase |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-15 | 2019-09-26
[6 empty] | Revised Plan | 2019-01-23 | 2019-06-26
[6 empty] | Issue Actual | 2019-01-23 | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00705 | TPSK-LSPA1-T-PL-01989
[6 empty] | Return Date | 2019-06-06 | 2019-07-10
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-102000 | Material Requisition For Shop Assembled Columns (C4 Unit) |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-15 | 2019-09-26
[6 empty] | Revised Plan | 2019-05-10 | 2019-09-12
[6 empty] | Issue Actual | 2019-05-10 | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01623 | TPSK-LSPA1-T-PL-02616
[6 empty] | Return Date | 2019-05-24 | 2019-10-01
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-111000 | Material Requisition For Reactors And Thicker Vessels Requisition For Purchase |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-22 | 2019-06-18
[6 empty] | Revised Plan | 2019-02-26 | 2019-06-25
[6 empty] | Issue Actual | 2019-02-26 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00918 | TPSK-LSPA1-T-PL-01972
[6 empty] | Return Date | 2019-06-06 | 2019-07-04
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-120000 | Material Requisition for Deaerator D-5100 - Ex Doc. Client Ref. OL1-2M55-0108 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-11-06 | 2019-02-15
[6 empty] | Revised Plan | 2018-11-06 | 2019-04-02
[6 empty] | Issue Actual | 2018-11-06 | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00270 | TPSK-LSPA1-T-PL-01210
[6 empty] | Return Date | 2018-11-29 | 2019-06-06
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-131000 | Material Requisition For Shop Assembled Large Drums |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-03-04 | 2019-07-17
[6 empty] | Issue Actual | 2019-03-04 | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00967 | TPSK-LSPA1-T-PL-02070
[6 empty] | Return Date | 2019-06-06 | 2019-08-01
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-132000 | Material Requisition For Shop Assembled CS Drums |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-03-13 | 2019-07-22
[6 empty] | Issue Actual | 2019-03-13 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01032 | TPSK-LSPA1-T-PL-02197
[6 empty] | Return Date | 2019-06-06 | 2019-07-31
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-133000 | Material Requisition For Shop Assembled CS Cladded & SS Vessels |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-03-27 | 2019-07-29
[6 empty] | Issue Actual | 2019-03-27 | 2019-07-29
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01156 | TPSK-LSPA1-T-PL-02262
[6 empty] | Return Date | 2019-06-06 | 2019-08-16
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-134000 | Material Requisition for Shop Assembled Drums (C4 Unit) |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-07-01 | 2019-11-08
[6 empty] | Issue Actual | 2019-07-01 | 2019-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02033 | TPSK-LSPA1-T-PL-03005
[6 empty] | Return Date | 2019-07-11
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-140000 | Material Requisition for Quench Exchangers - Ex Doc. Client Reference OL1-2M55-2003 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-10-26 | 2018-12-17
[6 empty] | Revised Plan | 2018-10-26 | 2018-12-10
[6 empty] | Issue Actual | 2018-10-26 | 2018-12-10 | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00233 | TPSK-LSPA1-T-ME-00466 | TPSK-LSPA1-T-PL-01221
[6 empty] | Return Date |  |  | 2019-06-20
[6 empty] | Owner Cmmt* |  |  | R2
| ME | OL1-2C13-142000 | Material Requisition For Purchase Plate And Frame Heat Exchangers Requisition For Purchase |  |  | Purpose** | IFQ | IFP | IFP | IFP
[6 empty] | Rev. | A | 0 | 1 | 2
[6 empty] | Issue Plan | 2018-10-08 | 2019-02-14
[6 empty] | Revised Plan | 2018-10-04 | 2019-02-26
[6 empty] | Issue Actual | 2018-10-04 | 2019-02-26 | 2019-06-25 | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00124 | TPSK-LSPA1-T-PL-00916 | TPSK-LSPA1-T-PL-01971 | TPSK-LSPA1-T-PL-02098
[6 empty] | Return Date | 2018-10-24 | 2019-06-06 | 2019-07-04 | 2019-07-15
[6 empty] | Owner Cmmt* | A1 | R1 | R1 | R1
| ME | OL1-2C13-144000 | Material Requisition For Cold Box And Core Exchangers Requisition For Purchase - Ex Doc. Client Ref. OL1-2M55-0066 |  |  | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | B | 0
[6 empty] | Issue Plan | 2018-10-15 |  | 2019-02-21
[6 empty] | Revised Plan | 2018-10-04 |  | 2019-04-17
[6 empty] | Issue Actual | 2018-10-04 | 2018-10-11 | 2019-04-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00125 | TPSK-LSPA1-T-ME-00153 | TPSK-LSPA1-T-PL-1351
[6 empty] | Return Date | 2018-10-24 | 2018-11-02 | 2019-05-20
[6 empty] | Owner Cmmt* | A1 | R1 | R1
| ME | OL1-2C13-145000 | Material Requisition For Hairpin Heat Exchangers Requisition For Purchase |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-30 | 2019-05-10
[6 empty] | Revised Plan | 2019-03-14 | 2019-08-09
[6 empty] | Issue Actual | 2019-03-14 | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01046 | TPSK-LSPA1-T-PL-02389
[6 empty] | Return Date | 2019-06-06 | 2019-08-20
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-151000 | Material Requisition For Condensate Carbon Filter Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-19 | 2019-07-16
[6 empty] | Revised Plan | 2019-03-13 | 2019-08-14
[6 empty] | Issue Actual | 2019-03-13 | 2019-08-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01039 | TPSK-LSPA1-T-PL-02402
[6 empty] | Return Date | 2019-06-07 | 2019-08-22
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-152000 | Material Requisition for Filters and Coalescers |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. |  | 0 | 1
[6 empty] | Issue Plan | 2019-01-24 | 2019-05-30
[6 empty] | Revised Plan |  | 2019-05-21
[6 empty] | Issue Actual |  | 2019-05-21 | 2019-10-23
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-PL-01689 | TPSK-LSPA1-T-PL-02907
[6 empty] | Return Date |  | 2019-05-30 | 2019-11-07
[6 empty] | Owner Cmmt* |  | R2 | R1
| ME | OL1-2C13-161000 | Material Requisition for Silencers |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-18 | 2019-07-05
[6 empty] | Revised Plan | 2019-07-15 | 2019-12-01
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02146
[6 empty] | Return Date | 2019-08-01
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-201000 | MATERIAL REQUISITION FOR SITE ASSEMBLED TANKS |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-05-21 | 2019-11-30
[6 empty] | Issue Actual | 2019-05-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01688
[6 empty] | Return Date | 2019-05-31
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-242000 | Material Requisition For Trays For Columns Requisition For Purchase |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-12-17 | 2019-04-10
[6 empty] | Revised Plan | 2018-11-09 | 2019-04-17
[6 empty] | Issue Actual | 2018-11-09 | 2019-04-17 | 2019-06-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00300 | TPSK-LSPA1-T-PL-01352 | TPSK-LSPA1-T-PL-01844
[6 empty] | Return Date | 2018-12-06 | 2019-05-20 | 2019-06-24
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| ME | OL1-2C13-244000 | MATERIAL REQUISITION FOR TRAYS COLUMNS (C4 UNIT) |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-27 | 2019-07-09
[6 empty] | Revised Plan | 2019-04-08 | 2019-09-03
[6 empty] | Issue Actual | 2019-04-08 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01268 | TPSK-LSPA1-T-PL-02544
[6 empty] | Return Date | 2019-06-07 | 2019-09-10
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-245000 | Material Requisition For High Efficiency Internals For Columns Requisition For Purchase - Ex Doc Client Ref OL1-2M55-0075 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-12-24 | 2019-04-17
[6 empty] | Revised Plan | 2018-11-07 | 2019-05-23
[6 empty] | Issue Actual | 2018-11-07 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00278 | TPSK-LSPA1-T-PL-01706
[6 empty] | Return Date | 2018-11-29 | 2019-05-30
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-251000 | Technical Agreement For Mechanical Seals And Seal System |  |  | Purpose** | IFQ | IFP | IMP
[6 empty] | Rev. | A |  | 0
[6 empty] | Issue Plan | 2019-01-17 | 2019-05-01
[6 empty] | Revised Plan | 2019-03-01 |  | 2019-07-09
[6 empty] | Issue Actual | 2019-03-01 |  | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00949 |  | TPSK-LSPA1-T-PL-02096
[6 empty] | Return Date |  |  | 2019-07-18
[6 empty] | Owner Cmmt* |  |  | R1
| ME | OL1-2C13-271000 | Material Requisition For Wieland Tubes - Solo Source - Requisition For Purchase - Ex Doc. Client Reference OL1-2M55-0058 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2018-11-28 | 2019-02-08
[6 empty] | Issue Actual | 2018-11-28 | 2019-02-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00377 | TPSK-LSPA1-T-PL-00829
[6 empty] | Return Date | 2019-02-07
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2C13-272000 | Material Requisition for Shell & Tube Heat Exchangers Lot-1 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-02-13 | 2019-07-17
[6 empty] | Issue Actual | 2019-02-13 | 2019-07-17
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00849 | TPSK-LSPA1-T-PL-02169
[6 empty] | Return Date | 2019-02-27
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-273000 | Material Requisition for Shell & Tube Heat Exchangers (Lot-2) |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-02-15 | 2019-07-25
[6 empty] | Issue Actual | 2019-02-15 | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00866 | TPSK-LSPA1-T-PL-02261
[6 empty] | Return Date | 2019-06-06 | 2019-08-14
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-274000 | Material Requisition for Shell & Tube Heat Exchangers - Lot-3 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-02-15 | 2019-07-22
[6 empty] | Issue Actual | 2019-02-15 | 2019-07-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00870 | TPSK-LSPA1-T-PL-02195
[6 empty] | Return Date | 2019-06-06 | 2019-07-31
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-275000 | Material Requisition For Cs S & T Heat Exchangers (C4 Unit) |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-06-03 | 2019-10-30
[6 empty] | Revised Plan | 2019-06-10 | 2019-10-22
[6 empty] | Issue Actual | 2019-06-10 | 2019-10-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01838 | TPSK-LSPA1-T-PL-02913
[6 empty] | Return Date | 2019-06-27 | 2019-11-15
[6 empty] | Owner Cmmt* | R2 | R1
| ME | OL1-2C13-281000 | Material Requisition for Furnace Convection Finnings |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-21 | 2019-03-20
[6 empty] | Revised Plan | 2019-01-23 | 2019-03-18
[6 empty] | Issue Actual | 2019-01-23 | 2019-03-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00713 | TPSK-LSPA1-T-PL-01085
Return Date
Owner Cmmt*
| ME | OL1-2C13-282000 | Material Requisition for Convection Fabrication |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-07-16 | 2019-10-21
[6 empty] | Revised Plan | 2019-04-12 | 2019-06-10
[6 empty] | Issue Actual | 2019-04-12 | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-01316 | TPSK-LSPA1-T-PL-01798
[6 empty] | Return Date |  | 2019-06-21
[6 empty] | Owner Cmmt* |  | R2
| ME | OL1-2C13-283000 | Material Requisition for Radiant Refractory |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-02-07 | 2019-04-15
[6 empty] | Revised Plan | 2019-03-21 | 2019-05-14
[6 empty] | Issue Actual | 2019-03-21 | 2019-05-14
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01108 | TPSK-LSPA1-T-PL-01657
[6 empty] | Return Date |  | 2019-06-19
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2C13-284000 | Material Requisition for Peep Doors - Ex Doc. Client Reference OL1-2M55-2008 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-12-10 | 2019-04-03
[6 empty] | Revised Plan | 2018-12-14 | 2019-03-28
[6 empty] | Issue Actual | 2018-12-14 | 2019-03-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00502 | TPSK-LSPA1-T-PL-01181
Return Date
Owner Cmmt*
| ME | OL1-2C13-285000 | Material Requisition for MOVs - Ex Doc. Client Reference OL1-2M55-2010 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-12-18 | 2019-03-19
[6 empty] | Revised Plan | 2018-12-18 | 2019-04-02
[6 empty] | Issue Actual | 2018-12-18 | 2019-04-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00534 | TPSK-LSPA1-T-PL-01219
Return Date
Owner Cmmt*
| ME | OL1-2C13-286000 | Material Requisition for Attemperators |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2019-01-16 | 2019-04-03
[6 empty] | Revised Plan | 2019-01-31 | 2019-05-29
[6 empty] | Issue Actual | 2019-01-31 | 2019-05-29 | 2019-11-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00771 | TPSK-LSPA1-T-PL-01756 | TPSK-LSPA1-T-PL-02994
[6 empty] | Return Date | 2019-06-07 | 2019-06-19
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-300000 | Material Requisition for Radiant Coil Assemblies - Ex Doc Client Ref OL1-2M55-2004 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-09-19 | 2019-02-14
[6 empty] | Revised Plan | 2018-10-18 | 2018-12-14
[6 empty] | Issue Actual | 2018-10-18 | 2018-12-14 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00063 | TPSK-LSPA1-T-ME-00499 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-301000 | Material Requisition for Furnace ID Fans - Ex Doc. Client Ref. OL1-2M55-2005 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-11-05 | 2019-01-17
[6 empty] | Revised Plan | 2018-11-05 | 2019-03-21
[6 empty] | Issue Actual | 2018-11-05 | 2019-03-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00269 | TPSK-LSPA1-T-PL-01109
Return Date
Owner Cmmt*
| ME | OL1-2C13-302000 | Material Requisition for Cast Intermediate Tube Supports - Ex Doc Client Ref OL1-2M55-2007 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-11-16 | 2019-01-28
[6 empty] | Revised Plan | 2018-11-16 | 2018-12-20
[6 empty] | Issue Actual | 2018-11-16 | 2018-12-20 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00329 | TPSK-LSPA1-T-ME-00542 | TPSK-LSPA1-T-PL-01139
[6 empty] | Return Date | 2018-12-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2C13-303000 | Material Requisition for Convection Tubes - Ex Doc. Client Ref. OL1-2M55-2001 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-10-22 | 2018-12-21
[6 empty] | Revised Plan | 2018-09-13 | 2018-12-10
[6 empty] | Issue Actual | 2018-09-13 | 2018-12-10 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00044 | TPSK-LSPA1-T-ME-00450 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-304000 | Material Requisition for Furnace Convection Fittings - Ex Doc Client Ref OL1-2M55-2002 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-10-22 | 2018-12-21
[6 empty] | Revised Plan | 2018-10-22 | 2019-01-07
[6 empty] | Issue Actual | 2018-10-22 | 2019-01-07 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00207 | TPSK-LSPA1-T-ME-00592 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-305000 | Material Requisition for Furnace Steam Drums - Ex Doc Client Ref OL1-2M55-2018 |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-10-26 | 2018-12-17
[6 empty] | Revised Plan | 2018-11-01 | 2018-12-17
[6 empty] | Issue Actual | 2018-11-01 | 2018-12-17 | 2019-03-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00263 | TPSK-LSPA1-T-ME-00518 | TPSK-LSPA1-T-PL-01139
Return Date
Owner Cmmt*
| ME | OL1-2C13-306000 | Material Requisition for Furnace Burners - Ex Doc. Client Ref. OL1-2M55-2006 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-11-13 | 2019-01-23
[6 empty] | Revised Plan | 2018-11-13 | 2019-02-07
[6 empty] | Issue Actual | 2018-11-13 | 2019-02-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00313 | TPSK-LSPA1-T-ME-00820
Return Date
Owner Cmmt*
| ME | OL1-2C13-311000 | Material Requisition for Cooling Tower |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-10-31 | 2019-03-26
[6 empty] | Revised Plan | 2018-11-06 | 2019-04-25
[6 empty] | Issue Actual | 2018-11-06 | 2019-04-25 | 2019-10-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00276 | TPSK-LSPA1-T-PL-01460 | TPSK-LSPA1-T-PL-02895
[6 empty] | Return Date | 2019-02-15 | 2019-05-24 | 2019-11-15
[6 empty] | Owner Cmmt* | R1 | R1 | R1
| ME | OL1-2C13-401000 | Material Requisition For Centrifugal Compressors Steam Turbine Driven |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2018-10-04 | 2019-04-03
[6 empty] | Revised Plan | 2018-10-08 | 2019-03-22
[6 empty] | Issue Actual | 2018-10-08 | 2019-03-22 | 2019-04-22
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00136 | TPSK-LSPA1-T-PL-01124 | TPSK-LSPA1-T-PL-01420
[6 empty] | Return Date | 2018-10-26 |  | 2019-05-20
[6 empty] | Owner Cmmt* | R1 |  | R1
| ME | OL1-2C13-402000 | Material Requisition for Integrally Geared Decoking Air Compressors - Ex Document Client Reference OL1-2M55-0014 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-10-18 | 2019-04-17
[6 empty] | Revised Plan | 2018-10-19 | 2019-05-23
[6 empty] | Issue Actual | 2018-10-19 | 2019-05-23
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00198 | TPSK-LSPA1-T-PL-01720
[6 empty] | Return Date | 2018-11-07 | 2019-06-17
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-403000 | Material Requisition for Recycle Gas Compressor |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2019-02-25 | 2019-07-22
[6 empty] | Revised Plan | 2019-01-23 | 2019-07-10
[6 empty] | Issue Actual | 2019-01-23 | 2019-07-10 | 2019-10-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00714 | TPSK-LSPA1-T-PL-02106 | TPSK-LSPA1-T-CV-02903
[6 empty] | Return Date | 2019-06-27 | 2019-08-01 | 2019-11-15
[6 empty] | Owner Cmmt* | R2 | R1 | R1
| ME | OL1-2C13-421000 | Material Requisition For Residue Gas Expander-Recompressor |  |  | Purpose** | IFQ | IFP | IFP | IFP
[6 empty] | Rev. | A | 0 | 1 | 2
[6 empty] | Issue Plan | 2018-10-05 | 2019-04-05
[6 empty] | Revised Plan | 2018-10-07 | 2019-03-22
[6 empty] | Issue Actual | 2018-10-07 | 2019-03-22 | 2019-04-24 | 2019-10-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00139 | TPSK-LSPA1-T-PL-01118 | TPSK-LSPA1-T-PL-01443 | TPSK-LSPA1-T-PL-02754
[6 empty] | Return Date | 2018-10-26 |  | 2019-05-20 | 2019-10-22
[6 empty] | Owner Cmmt* | R1 |  | R1 | R2
| EE | OL1-2C13-431000 | Material Requisition For Emergency Diesel Engine Generator |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-15 | 2019-11-21
[6 empty] | Revised Plan | 2019-08-28 | 2019-11-21
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02514
[6 empty] | Return Date | 2019-09-10
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2C13-440003 | Material Requisition for Cooling Water Pumps |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2019-01-31 | 2019-05-23
[6 empty] | Revised Plan | 2018-11-15 | 2019-07-10
[6 empty] | Issue Actual | 2018-11-15 | 2019-07-10 | 2019-09-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00319 | TPSK-LSPA1-T-PL-02113 | TPSK-LSPA1-T-PL-02725
[6 empty] | Return Date | 2018-12-10 | 2019-07-30
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-441000 | Material Requisition For API Centrifugal Pumps - LLI- For Previous Revision See Doc N OL1-2M55-0015 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-31 | 2019-05-23
[6 empty] | Revised Plan | 2018-10-31 | 2019-07-09
[6 empty] | Issue Actual | 2018-10-31 | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00257 | TPSK-LSPA1-T-PL-02095
[6 empty] | Return Date | 2018-11-27 | 2019-07-18
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-442000 | Material Requisition For API Centrifugal Pumps |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2019-01-31 | 2019-05-23
[6 empty] | Revised Plan | 2019-02-19 | 2019-08-14
[6 empty] | Issue Actual | 2019-02-19 | 2019-08-14 | 2019-09-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00880 | TPSK-LSPA1-T-PL-02408 | TPSK-LSPA1-T-PL-02691
[6 empty] | Return Date |  | 2019-08-24 | 2019-10-03
[6 empty] | Owner Cmmt* |  | R2 | R2
| ME | OL1-2C13-451000 | Material Requisition For Vent Gas Blower |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-12-21 | 2019-04-30
[6 empty] | Revised Plan | 2019-03-08 | 2019-11-18
[6 empty] | Issue Actual | 2019-03-08 | 2019-11-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01001 | TPSK-LSPA1-T-PL-03102
[6 empty] | Return Date | 2019-03-27
[6 empty] | Owner Cmmt* | R2
| ME | OL1-2C13-701000 | Material Requisition for Condensate Polisher Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-02-22 | 2019-06-10
[6 empty] | Revised Plan | 2019-02-27 | 2019-09-03
[6 empty] | Issue Actual | 2019-02-27 | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00940 | TPSK-LSPA1-T-PL-02545
[6 empty] | Return Date | 2019-06-07 | 2019-09-10
[6 empty] | Owner Cmmt* | R2 | R2
| ME | OL1-2C13-702000 | Material Requisition For Complex Waste Water Treatment Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-01-25 | 2019-05-31
[6 empty] | Revised Plan | 2019-02-15 | 2019-08-09
[6 empty] | Issue Actual | 2019-02-15 | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00862 | TPSK-LSPA1-T-PL-02399
[6 empty] | Return Date | 2019-06-07 | 2019-08-26
[6 empty] | Owner Cmmt* | R2 | R1
| ME | OL1-2C13-704000 | Material Requisition for Wet Air Oxidation Package |  |  | Purpose** | IFQ | IFP | IFP | IFP
[6 empty] | Rev. | A | 0 | 1 | 2
[6 empty] | Issue Plan | 2018-11-30 | 2019-04-15
[6 empty] | Revised Plan | 2018-11-27 | 2019-05-09
[6 empty] | Issue Actual | 2018-11-27 | 2019-05-09 | 2019-06-20 | 2019-10-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00367 | TPSK-LSPA1-T-PL-01611 | TPSK-LSPA1-T-PL-01943 | TPSK-LSPA1-T-PL-02904
[6 empty] | Return Date | 2019-02-07 | 2019-06-16 | 2019-07-08 | 2019-11-15
[6 empty] | Owner Cmmt* | R1 | R2 | R1 | R1
| ME | OL1-2C13-705000 | Material Requisition For Hydrogen Production Unit PK-2560 - Ex Doc. Client Reference OL1-2M55-0114 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-11-14 | 2019-02-15
[6 empty] | Revised Plan | 2018-11-06 | 2019-05-07
[6 empty] | Issue Actual | 2018-11-06 | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00271 | TPSK-LSPA1-T-PL-01580
[6 empty] | Return Date | 2019-02-07 | 2019-05-27
[6 empty] | Owner Cmmt* | R1 | R2
| ME | OL1-2C13-706000 | Material Requisition for Side Stream Filter Package - Ex Doc. Client Reference OL1-2M55-0109 |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-11-07 | 2019-04-05
[6 empty] | Revised Plan | 2018-10-31 | 2019-03-27
[6 empty] | Issue Actual | 2018-10-31 | 2019-03-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00248 | TPSK-LSPA1-T-PL-01165
[6 empty] | Return Date | 2018-11-27 | 2019-06-07
[6 empty] | Owner Cmmt* | R1 | R1
| ME | OL1-2C13-707000 | Material Requisition For Chemical Dosing System |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-04-06 | 2019-07-02
[6 empty] | Revised Plan | 2019-04-29 | 2019-11-15
[6 empty] | Issue Actual | 2019-04-29 | 2019-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01491 | TPSK-LSPA1-T-PL-03074
[6 empty] | Return Date | 2019-05-31
[6 empty] | Owner Cmmt* | R1
| ME | OL1-2C13-708000 | Material Requisition For HP / Polyolefins Flare Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-02-18 | 2019-06-21
[6 empty] | Revised Plan | 2019-01-17 | 2019-06-25
[6 empty] | Issue Actual | 2019-01-17 | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00665 | TPSK-LSPA1-T-PL-01951
[6 empty] | Return Date | 2019-06-11 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R1
| ME | OL1-2C13-709000 | Material Requisition for Furnace Elevator |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2018-12-19 | 2019-02-19
[6 empty] | Revised Plan | 2019-01-22 | 2019-07-25
[6 empty] | Issue Actual | 2019-01-22 | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-ME-00697 | TPSK-LSPA1-T-PL-02260
[6 empty] | Return Date | 2019-02-14 | 2019-08-15
[6 empty] | Owner Cmmt* | R2 | R1
| ME | OL1-2C13-771000 | Material Requisition For Bridge Crane |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-05-09 | 2019-09-15
[6 empty] | Revised Plan | 2019-02-25 | 2019-08-07
[6 empty] | Issue Actual | 2019-02-25 | 2019-08-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PC-00914 | TPSK-LSPA1-T-PL-02361
[6 empty] | Return Date |  | 2019-08-21
[6 empty] | Owner Cmmt* |  | R1
| ME | OL1-2C13-801000 | Material Requisition For Ejectors And Static Mixers |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-04-05 | 2019-07-24
[6 empty] | Revised Plan | 2019-04-18 | 2019-11-15
[6 empty] | Issue Actual | 2019-04-18 | 2019-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01408 | TPSK-LSPA1-T-PL-03070
[6 empty] | Return Date | 2019-05-24
[6 empty] | Owner Cmmt* | R2
Category Code: C14 Request for Quotation (RFQ) Piping work (Engineering and Procurement)
| MP | OL1-2C14-100001 | Material Requisition For Gate Globe And Check Forged Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-10-15
[6 empty] | Revised Plan | 2019-05-06 | 2020-10-15
[6 empty] | Issue Actual | 2019-05-06
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01567
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-110001 | Material Requisition For Gate Globe And Check Cast Valves Low Pressure |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01574
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-125001 | Material Requisition For Butterfly Valves High Performance (Category B) |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01575
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-130001 | Material Requisition For Plug Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01576
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-140001 | Material Requisition For Ball Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01577
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-150001 | Material Requisition For Dual Plate Check Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
[6 empty] | Revised Plan | 2019-05-07 | 2020-07-01
[6 empty] | Issue Actual | 2019-05-07
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01578
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-160001 | Material Requisition For Spring-Assisted Check Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-13 | 2020-07-01
[6 empty] | Revised Plan | 2019-09-03 | 2020-07-01
[6 empty] | Issue Actual | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02553
[6 empty] | Return Date | 2019-09-05
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-210001 | Material Requisition For Carbon Steel Seamless Pipe |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
[6 empty] | Revised Plan | 2019-05-02 | 2020-10-15
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01525
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-215001 | Material Requisition For Carbon Steel Welded Pipe |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-06-17
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-17
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01527
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-220001 | Material Requisition For Alloy Steel Seamless Pipe |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-06-17
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-17
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01528
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-225001 | Material Requisition For Alloy Steel Welded Pipe |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-06-17
[6 empty] | Revised Plan | 2019-05-02 | 2020-06-17
[6 empty] | Issue Actual | 2019-05-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01529
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-230001 | Material Requisition For Stainless Steel Seamless Pipe |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01553
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-235001 | Material Requisition For Stainless Steel Welded Pipe |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01555
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-245001 | MR PE & PVC PIPING |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-04-30 | 2020-07-12
[6 empty] | Revised Plan | 2019-11-18 | 2020-07-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-250001 | Material Requisition For Buttwelding Fittings |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01557
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-260001 | Material Requisition For Forged Fittings |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01559
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-270001 | Material Requisition For Flanges Blinds And Drip Rings |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-06 | 2020-10-15
[6 empty] | Revised Plan | 2019-05-03 | 2020-10-15
[6 empty] | Issue Actual | 2019-05-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01558
[6 empty] | Return Date | 2019-05-20
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-280001 | MR GASKETS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-04-20 | 2020-10-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-290001 | MR BOLTING |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-04-20 | 2020-10-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-300001 | MR STEAM TRAPS AND MANIFOLDS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-05-14 | 2020-01-27
[6 empty] | Revised Plan | 2020-02-28 | 2020-09-25
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| ME | OL1-2C14-301000 | MATERIAL REQUISITION FOR PIPING SPRING SUPPORTS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-11-27 | 2020-01-27
[6 empty] | Revised Plan | 2019-11-27 | 2020-01-27
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-310001 | MR HOSE CONNECTIONS AND FLEXIBLE HOSES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-01-03 | 2020-10-15
[6 empty] | Revised Plan | 2020-01-03 | 2020-10-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-320001 | Material Requisition for Filters |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-30 | 2020-01-15
[6 empty] | Revised Plan | 2019-09-03 | 2020-01-15
[6 empty] | Issue Actual | 2019-09-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02552
[6 empty] | Return Date | 2019-09-05
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-330001 | MR SIGHT FLOW INDICATORS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-06-30 | 2020-01-15
[6 empty] | Revised Plan | 2020-02-28 | 2020-09-25
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-340001 | MR SAMPLING PANELS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-01-14 | 2020-08-30
[6 empty] | Revised Plan | 2020-01-14 | 2020-08-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-350001 | MR INTERLOCKS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-05-15
[6 empty] | Revised Plan | 2020-01-20 | 2020-05-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| MP | OL1-2C14-411000 | Material Requisition For Itemized Supports |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-31 | 2021-02-06
[6 empty] | Revised Plan | 2019-11-08 | 2021-02-06
[6 empty] | Issue Actual | 2019-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-03009
Return Date
Owner Cmmt*
| MP | OL1-2C14-502000 | Material Requisition for SP Item Angle Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-04-24
[6 empty] | Revised Plan | 2019-06-10 | 2019-11-22
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01800
[6 empty] | Return Date | 2019-06-21
[6 empty] | Owner Cmmt* | R2
| MP | OL1-2C14-503000 | Material Requisition for SP Item - Sample Cooler |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-04-24
[6 empty] | Revised Plan | 2019-07-03 | 2019-11-22
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02057
Return Date
Owner Cmmt*
| MP | OL1-2C14-504000 | Material Requisition for SP Item T-Type Filter |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-04-24
[6 empty] | Revised Plan | 2019-06-26
[6 empty] | Issue Actual | 2019-06-26
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01996
Return Date
Owner Cmmt*
| MP | OL1-2C14-505000 | Material Requisition for SP Item Isokinetic Sampling Nozzle |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-02-20 | 2019-04-24
[6 empty] | Revised Plan | 2019-06-10 | 2019-11-22
[6 empty] | Issue Actual | 2019-06-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01833
Return Date
Owner Cmmt*
Category Code: C15 Request for Quotation (RFQ) for Fire Fighting work (Engineering and Procurement)
| SE | OL1-2C15-821001 | Material Requisition for Fire Fighting and Safety Equipment Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-05 | 2019-10-09
[6 empty] | Revised Plan | 2019-07-08 | 2019-12-13
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02083
[6 empty] | Return Date | 2019-08-06
[6 empty] | Owner Cmmt* | R1
| SE | OL1-2C15-822001 | Material Requisition for Deluge and Sprinkler System Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-05 | 2019-10-09
[6 empty] | Revised Plan | 2019-07-08 | 2019-12-13
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02083
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | R1
| SE | OL1-2C15-823001 | Material Requisition for Clean Agent Fire Extinguishing System |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-05 | 2019-10-09
[6 empty] | Revised Plan | 2019-07-08 | 2019-12-13
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02083
[6 empty] | Return Date | 2019-08-08
[6 empty] | Owner Cmmt* | R1
Category Code: C16 Request for Quotation (RFQ) for Electrical and HVAC work (Engineering and Procurement)
| EE | OL1-2C16-110000 | Material Requisition for Medium Voltage Switchgears |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. |  | 0
[6 empty] | Issue Plan | 2019-06-14 | 2019-09-18
[6 empty] | Revised Plan |  | 2019-10-16
[6 empty] | Issue Actual |  | 2019-10-16
[6 empty] | Transmittal no. |  | TPSK-LSPA1-T-CV-02865
[6 empty] | Return Date |  | 2019-11-05
[6 empty] | Owner Cmmt* |  | R2
| EE | OL1-2C16-150000 | Material Requisition For Distribution Transformer |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-03 | 2019-09-05
[6 empty] | Revised Plan | 2019-08-05 | 2019-12-10
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02326
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2C16-160000 | Material Requisition For Power Capacitors |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-14 | 2019-11-18
[6 empty] | Revised Plan | 2019-08-06 | 2019-11-18
[6 empty] | Issue Actual | 2019-08-06
[6 empty] | Transmittal no. | TPSK-LPSA1-T-PL-02342
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2C16-200000 | MR FOR AC AND DC UPS SYSTEMS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-10-24 | 2020-01-28
[6 empty] | Revised Plan | 2019-11-29 | 2020-01-28
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-340000 | Material Requisition for HVAC System |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-08-28 | 2019-12-11
[6 empty] | Revised Plan | 2019-07-08 | 2019-11-15
[6 empty] | Issue Actual | 2019-07-08 | 2019-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02092 | TPSK-LSPA1-T-PL-03075
[6 empty] | Return Date | 2019-07-23
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2C16-530000 | MR FOR POWER AND LIGHTING DISTRIBUTION PANELS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-04-30
[6 empty] | Revised Plan | 2020-01-20 | 2020-04-30
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-800000 | Material Requisition For Cathodic Protection System |  |  | Purpose** | IFQ | IF1T | IF2T
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2020-03-18 | 2020-06-28 | 2020-07-20
[6 empty] | Revised Plan | 2019-05-24 | 2020-06-28 | 2020-07-20
[6 empty] | Issue Actual | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01735
[6 empty] | Return Date | 2019-06-20
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2C16-810000 | MR FOR ELECTRICAL HEAT TRACING SYSTEM |  |  | Purpose** | IFQ | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-03-18 | 2020-06-28 | 2020-08-20
[6 empty] | Revised Plan | 2020-03-18 | 2020-06-28 | 2020-08-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-851000 | Material Requisition For Safety Supervisory System |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-04 | 2020-01-15
[6 empty] | Revised Plan | 2019-03-05 | 2019-08-05
[6 empty] | Issue Actual | 2019-03-05 | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00984 | TPSK-LSPA1-T-PL-02309
[6 empty] | Return Date | 2019-04-05 | 2019-08-14
[6 empty] | Owner Cmmt* | R2 | R1
| EE | OL1-2C16-881000 | Material Requisition For Intercom Paging Audible Alarm System |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-04 | 2020-01-15
[6 empty] | Revised Plan | 2019-03-05 | 2019-08-01
[6 empty] | Issue Actual | 2019-03-05 | 2019-08-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-00984 | TPSK-LSPA1-T-PL-02306
[6 empty] | Return Date | 2019-04-10 | 2019-08-14
[6 empty] | Owner Cmmt* | R2 | R1
| EE | OL1-2C16-900000 | Material Requisition For Electrical Cables |  |  | Purpose** | IFQ | IF1T | IF2T
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-16 | 2019-11-10 | 2020-01-20
[6 empty] | Revised Plan | 2019-08-05 | 2020-01-06 | 2020-01-20
[6 empty] | Issue Actual | 2019-08-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02328
[6 empty] | Return Date | 2019-08-26
[6 empty] | Owner Cmmt* | R2
| EE | OL1-2C16-900501 | MR COMMUNICATION AND SAFETY SUPERVISROY SYSTEM COPPER CABLES - ADDED 25-OCT-19 |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-11-04 | 2020-11-15
[6 empty] | Revised Plan | 2019-11-22
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-910000 | Material Requisition For Electrical Cable Glands |  |  | Purpose** | IFQ | IF1T | IF2T
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-26 | 2020-01-12 | 2020-02-27
[6 empty] | Revised Plan | 2019-10-25 | 2020-01-12 | 2020-02-27
[6 empty] | Issue Actual | 2019-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02938
Return Date
Owner Cmmt*
| EE | OL1-2C16-920000 | Material Requisition For Electrical Power Materials |  |  | Purpose** | IFQ | IF1T | IF2T
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-26 | 2020-01-12 | 2020-02-27
[6 empty] | Revised Plan | 2019-10-25
[6 empty] | Issue Actual | 2019-10-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02939
Return Date
Owner Cmmt*
| EE | OL1-2C16-930100 | MR FOR LIGHTING MATERIALS |  |  | Purpose** | IFQ | IF1T | IF2T
Rev.
[6 empty] | Issue Plan | 2020-01-20 | 2020-04-29 | 2020-07-05
[6 empty] | Revised Plan | 2020-01-20 | 2020-04-29 | 2020-07-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| EE | OL1-2C16-940000 | Material Requisition For Electrical Cable Ladder Trays |  |  | Purpose** | IFQ | IF1T | IF2T
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-26 | 2020-01-12 | 2020-04-25
[6 empty] | Revised Plan | 2019-11-08 | 2020-01-12 | 2020-04-25
[6 empty] | Issue Actual | 2019-11-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-03012
Return Date
Owner Cmmt*
Category Code: C17 Request for Quotation (RFQ) for Instrumentation work (Engineering and Procurement)
| IE | OL1-2C17-010101 | Material Requisition For Orifice And Restriction Orifice |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20
[6 empty] | Revised Plan | 2019-10-15 | 2019-11-29
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02847
[6 empty] | Return Date | 2019-10-30
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2C17-010201 | MR for Pitot Tube |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20
[6 empty] | Revised Plan | 2019-07-02 | 2019-11-29
[6 empty] | Issue Actual | 2019-07-02
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02035
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R1
| IE | OL1-2C17-010301 | MR For Electromagnetic Flow Meter |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20
[6 empty] | Revised Plan | 2019-07-05 | 2019-11-29
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02078
[6 empty] | Return Date | 2019-07-18
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-010401 | Material Requisition for Flow Element Rotameter |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20
[6 empty] | Revised Plan | 2019-10-15 | 2019-11-29
[6 empty] | Issue Actual | 2019-10-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-LP-02847
[6 empty] | Return Date | 2019-10-30
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-010601 | MR For Mass Flow Meters Coriolis Effect |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20
[6 empty] | Revised Plan | 2019-07-03 | 2019-11-29
[6 empty] | Issue Actual | 2019-07-03
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02049
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-010701 | MR For Venturi |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20
[6 empty] | Revised Plan | 2019-07-05 | 2019-11-29
[6 empty] | Issue Actual | 2019-07-05
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02077
[6 empty] | Return Date | 2019-07-18
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-010801 | MR For Ultrasonic Flow Meter |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20
[6 empty] | Revised Plan | 2019-07-09 | 2019-11-29
[6 empty] | Issue Actual | 2019-07-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02093
[6 empty] | Return Date | 2019-07-19
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-012062 | Material Requisition for Flow Element Venturi |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-09 | 2019-07-30
[6 empty] | Revised Plan | 2019-06-27 | 2019-11-18
[6 empty] | Issue Actual | 2019-06-27
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02011
Return Date
Owner Cmmt*
| IE | OL1-2C17-012253 | Material Requisition for Orifice Plate & Restriction Orifice |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2019-04-09 | 2019-07-30
[6 empty] | Revised Plan | 2019-06-14 | 2019-09-17
[6 empty] | Issue Actual | 2019-06-14 | 2019-09-17 | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01881 | TPSK-LSPA1-T-PL-02644 | TPSK-LSPA1-T-PL-02803
[6 empty] | Return Date | 2019-07-01 |  | 2019-10-30
[6 empty] | Owner Cmmt* | R2 |  | R2
| IE | OL1-2C17-014001 | MR For Vortex Meter |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-04 | 2019-09-20
[6 empty] | Revised Plan | 2019-07-08 | 2019-11-29
[6 empty] | Issue Actual | 2019-07-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02082
[6 empty] | Return Date | 2019-07-18
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-020001 | MR MAGNETIC LEVEL GAUGE |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-020002 | MR RADAR LEVEL INSTRUMENTS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-020003 | MR ULTRASONIC LEVEL TRANSMITTERS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-020008 | MR LEVEL GLASS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-020009 | MR LEVEL GLASS FOR STEAM DRUM |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-12
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-12
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-022005 | Material Requisition for Level Gauges |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-26 | 2019-06-26
[6 empty] | Revised Plan | 2019-04-18 | 2019-08-15
[6 empty] | Issue Actual | 2019-04-18 | 2019-08-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01393 | TPSK-LSPA1-T-PL-02430
[6 empty] | Return Date | 2019-05-28 | 2019-09-04
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2C17-022060 | Material Requisition for Magnetostrictive Level Transmitter & Magnetic Level Gauge |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-03-26 | 2019-06-26
[6 empty] | Revised Plan | 2019-06-24 | 2019-08-21
[6 empty] | Issue Actual | 2019-06-24 | 2019-08-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01960 | TPSK-LSPA1-T-PL-02458
[6 empty] | Return Date | 2019-07-08 | 2019-09-04
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2C17-022064 | Material Requisition for Guided Wave Radar Level Transmitter & Magnetic Level Gauge |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-03-26 | 2019-06-26
[6 empty] | Revised Plan | 2019-06-21 | 2019-11-29
[6 empty] | Issue Actual | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01949
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-032061 | Material Requisition for Temperature Elements for Furnace Profile |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-08-27 | 2019-12-03
[6 empty] | Revised Plan | 2019-06-25 | 2019-12-03
[6 empty] | Issue Actual | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01977
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-032063 | Material Requisition for Temperature Elements for Coil Outlet |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-08-27 | 2019-12-03
[6 empty] | Revised Plan | 2019-05-24 | 2019-12-03
[6 empty] | Issue Actual | 2019-05-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01732
[6 empty] | Return Date | 2019-06-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-032257 | Material Requisition for Temperature Elements for Thermocouples & RTDs with Wells |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-08-27 | 2019-12-03
[6 empty] | Revised Plan | 2019-09-12 | 2019-12-03
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02630
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-032259 | Material Requisition for Temperature Transmitters |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-08-27 | 2019-12-03
[6 empty] | Revised Plan | 2019-08-28 | 2019-12-03
[6 empty] | Issue Actual | 2019-08-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02507
[6 empty] | Return Date | 2019-09-11
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-040002 | MR PRESSURE & DIFFER.PRESS.GAUGE |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-08-05
[6 empty] | Revised Plan | 2020-02-05 | 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-042255 | Material Requisition for Draft Gauge |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-23 | 2019-11-05
[6 empty] | Revised Plan | 2019-09-12 | 2019-12-04
[6 empty] | Issue Actual | 2019-09-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02627
[6 empty] | Return Date | 2019-10-08
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-042256 | Material Requisition for Material Requisition for Pressure Indicating Transmitters & Flow Indicating D P Transmitters |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-07-23 | 2019-11-05
[6 empty] | Revised Plan | 2019-08-08 | 2019-12-04
[6 empty] | Issue Actual | 2019-08-08
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02375
Return Date
Owner Cmmt*
| IE | OL1-2C17-050101 | Material Requisition For Control Valves |  |  | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-28 |  | 2019-11-13
[6 empty] | Revised Plan | 2019-06-13 |  | 2020-03-31
[6 empty] | Issue Actual | 2019-06-13 | 2019-06-28
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01891 | TPSK-LSPA1-T-PL-02017
[6 empty] | Return Date | 2019-09-11 | 2019-07-10
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2C17-050401 | Material Requisition For Special Control Valves |  |  | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-05-28 |  | 2019-11-13
[6 empty] | Revised Plan | 2019-06-13 |  | 2020-03-31
[6 empty] | Issue Actual | 2019-06-13 | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01891 | TPSK-LSPA1-T-PL-02022
[6 empty] | Return Date | 2019-06-28 | 2019-07-17
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2C17-050501 | Material Requisition for Severe Service Control Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13
[6 empty] | Revised Plan | 2019-09-19 | 2020-03-31
[6 empty] | Issue Actual | 2019-09-19
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02664
[6 empty] | Return Date | 2019-09-27
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-050701 | Material Requisition For Desuperheater Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13
[6 empty] | Revised Plan | 2019-11-12 | 2020-03-31
[6 empty] | Issue Actual | 2019-11-12
[6 empty] | Transmittal no. | TPSK-LSPA1-T-IE-03033
Return Date
Owner Cmmt*
| IE | OL1-2C17-052001 | Material Requistion for Control Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A | 0
[6 empty] | Issue Plan | 2019-04-25 | 2019-07-17
[6 empty] | Revised Plan | 2019-04-26 | 2019-11-11
[6 empty] | Issue Actual | 2019-04-26 | 2019-11-11
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01482 | TPSK-LSPA1-T-PL-03026
[6 empty] | Return Date | 2019-05-28
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-060201 | MR For Special On Off Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13
[6 empty] | Revised Plan | 2019-07-25 | 2020-01-17
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02255
[6 empty] | Return Date | 2019-08-07
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-060301 | MR For Electric Operated Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13
[6 empty] | Revised Plan | 2019-07-01 | 2020-01-17
[6 empty] | Issue Actual | 2019-07-01
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02026
[6 empty] | Return Date | 2019-07-17
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-060401 | Material Requisition For Pneumatic Actuators For On Off Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-10-29
[6 empty] | Revised Plan | 2019-07-25 | 2020-02-28
[6 empty] | Issue Actual | 2019-07-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02257
[6 empty] | Return Date | 2019-08-07
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-060501 | MR For Electric Pneumatic On Off Valves |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13
[6 empty] | Revised Plan | 2019-07-24 | 2020-01-17
[6 empty] | Issue Actual | 2019-07-24
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02245
[6 empty] | Return Date | 2019-08-07
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-070201 | Material Requisition for Safety Relief Valves & Rupture Disks |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-31 | 2019-10-29
[6 empty] | Revised Plan | 2019-08-09 | 2020-02-14
[6 empty] | Issue Actual | 2019-08-09
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02395
Return Date
Owner Cmmt*
| IE | OL1-2C17-072002 | Material Requisition for Pressure Relief Valves |  |  | Purpose** | IFQ | IFP | IFP
[6 empty] | Rev. | A | 0 | 1
[6 empty] | Issue Plan | 2019-03-28 | 2019-06-14
[6 empty] | Revised Plan | 2019-04-23 | 2019-08-06
[6 empty] | Issue Actual | 2019-04-23 | 2019-08-06 | 2019-09-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01427 | TPSK-LSPA1-T-PL-02351 | TPSK-LSPA1-T-PL-02683
[6 empty] | Return Date | 2019-05-28
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-080001 | MR ELECTRONIC TRANSMITTER |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-08-05
[6 empty] | Revised Plan | 2020-02-05 | 2020-08-05
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-101001 | Material Requisition for Integrated Control And Safety Systems - ICSS |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-06 | 2020-06-15
[6 empty] | Revised Plan | 2019-06-13 | 2020-06-15
[6 empty] | Issue Actual | 2019-06-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01892
[6 empty] | Return Date | 2019-06-28
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2C17-212051 | Material Requisition for O2 & Combustible Analyzer |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-05-23 | 2019-08-26
[6 empty] | Revised Plan | 2019-06-25 | 2019-11-22
[6 empty] | Issue Actual | 2019-06-25
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01979
[6 empty] | Return Date | 2019-07-08
[6 empty] | Owner Cmmt* | R2
| IE | OL1-2C17-230101 | MR For Water Analyzers |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-09-30 | 2020-02-15
[6 empty] | Revised Plan | 2019-10-10 | 2020-02-15
[6 empty] | Issue Actual | 2019-10-10
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02764
[6 empty] | Return Date | 2019-10-24
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2C17-232015 | Material Requisition for pH and Conductivity Analyzer |  |  | Purpose** | IFQ | IFQ | IFP
[6 empty] | Rev. | A | B
[6 empty] | Issue Plan | 2019-08-27 |  | 2019-12-03
[6 empty] | Revised Plan | 2019-05-27 |  | 2019-12-03
[6 empty] | Issue Actual | 2019-05-27 | 2019-06-21
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-01744 | TPSK-LSPA1-T-PL-01950
[6 empty] | Return Date | 2019-06-17 | 2019-07-08
[6 empty] | Owner Cmmt* | R2 | R2
| IE | OL1-2C17-2400000 | MR For CEMS |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-06 | 2019-10-30
[6 empty] | Revised Plan | 2019-09-18 | 2020-01-16
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02654
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2C17-250001 | MR GAS DETECTORS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-12-20 | 2020-06-20
[6 empty] | Revised Plan | 2019-12-20 | 2020-06-20
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-260101 | MR for Specific Components & Property Analyzers |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-06 | 2019-10-30
[6 empty] | Revised Plan | 2019-09-18 | 2020-01-24
[6 empty] | Issue Actual | 2019-09-18
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02657
[6 empty] | Return Date | 2019-10-04
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2C17-290000 | Material Requisition for Analyzer Houses Package |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-30 | 2019-10-30
[6 empty] | Revised Plan | 2019-07-31 | 2020-01-16
[6 empty] | Issue Actual | 2019-07-31
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02285
[6 empty] | Return Date | 2019-08-20
[6 empty] | Owner Cmmt* | A2
| IE | OL1-2C17-300001 | Material Requisition for Cross Check Custody Metering System |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-04-26 | 2019-11-30
[6 empty] | Revised Plan | 2019-11-15 | 2019-11-30
[6 empty] | Issue Actual | 2019-11-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-03058
Return Date
Owner Cmmt*
| IE | OL1-2C17-330101 | Material Requisition for Machine Monitoring System - MMS |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-06-21 | 2020-06-30
[6 empty] | Revised Plan | 2019-07-15 | 2020-06-30
[6 empty] | Issue Actual | 2019-07-15
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-02149
[6 empty] | Return Date | 2019-07-30
[6 empty] | Owner Cmmt* | A4
| IE | OL1-2C17-410001 | Material Requisition for Instrument and Fibre Optic Cables |  |  | Purpose** | IFQ | IFP
[6 empty] | Rev. | A
[6 empty] | Issue Plan | 2019-11-04 | 2020-11-15
[6 empty] | Revised Plan | 2019-11-13 | 2020-11-15
[6 empty] | Issue Actual | 2019-11-13
[6 empty] | Transmittal no. | TPSK-LSPA1-T-PL-03055
Return Date
Owner Cmmt*
| IE | OL1-2C17-420001 | MR CABLE TRAY AND ACCESSORIES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-04-11 | 2020-11-15
[6 empty] | Revised Plan | 2020-04-11 | 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-430001 | MR FOR JUNCTION BOXES, PUSH BUTTONS AND HAND SWITCHES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-12-15
[6 empty] | Revised Plan | 2020-06-01 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-430002 | MR CABLE GLANDS |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-12-15
[6 empty] | Revised Plan | 2020-06-01 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-450001 | MR MOUNTING ACCESSORIES (TUBING & FITTINGS) |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-04-11 | 2020-11-15
[6 empty] | Revised Plan | 2020-04-11 | 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-450002 | MR FOR MOUNTING ACCESSORIES (INSTRUMENT MANIFOLDS, MONOFLANGES, AIR MANIFOLDS ETC) |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-04-11 | 2020-11-15
[6 empty] | Revised Plan | 2020-04-11 | 2020-11-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-450003 | MR SUNSHADES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-12-15
[6 empty] | Revised Plan | 2020-06-01 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2C17-460001 | MR MAIN CABLE TRANSIT (MCT) & ACCESSORIES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-06-01 | 2020-12-15
[6 empty] | Revised Plan | 2020-06-01 | 2020-12-15
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: C18 Request for Quotation (RFQ) for Chemicals (Engineering and Procurement)
Category Code: C20 Technical Bid Evaluation for Civil work (Engineering and Procurement)
Category Code: C21 Technical Bid Evaluation for Building work (Engineering and Procurement)
Category Code: C22 Technical Bid Evaluation for Steel Structure work (Engineering and Procurement)
Category Code: C23 Technical Bid Evaluation for Mechanical work (Engineering and Procurement)
Category Code: C24 Technical Bid Evaluation for Piping work (Engineering and Procurement)
Category Code: C25 Technical Bid Evaluation for Fire Fighting work (Engineering and Procurement)
Category Code: C26 Technical Bid Evaluation for Electrical and HVAC work (Engineering and Procurement)
Category Code: C27 Technical Bid Evaluation for Instrumentation work (Engineering and Procurement)
Category Code: C28 Technical Bid Evaluation for Chemicals (Engineering and Procurement)
Category Code: C30 Scope of Supply (SR) for Mechanical Work
Category Code: C31 Scope of Supply (SR) for Piping Work
Category Code: C32 Scope of Supply (SR) for Electrical work
Category Code: C33 Scope of Supply (SR) for Instrumentation work
Category Code: C34 Scope of Supply (SR) for Civil,Structure and Architecture.
Category Code: C35 Extend of Supply (SP) Mechanical Work
Category Code: C36 Extend of Supply (SP) for Piping Work
Category Code: C37 Extend of Supply (SP) for Electrical work
Category Code: C38 Extend of Supply (SP) for Instrumentation work
Category Code: C39 Extend of Supply (SP) for Civil,Structure and Architecture
Category Code: C40 Deviation List (DL) for Mechanical Work
Category Code: C41 Deviation List (DL) for Piping Work
Category Code: C42 Deviation List (DL) for Electrical work
Category Code: C43 Deviation List (DL) for Instrumentation work
Category Code: C44 Deviation List (DL) for Civil,Structure and Architecture
Category Code: C50 Purchase Order (PO) for Civil work, Building work, Steel Structure work
Category Code: C51 Purchase Order (PO) for Mechanical work
Category Code: C51 Purchase Order (PO) for Mechanical work
Category Code: C52 Purchase Order (PO) for Piping work
Category Code: C53 Purchase Order (PO) for Fire Fighting work
Category Code: C54 Purchase Order (PO) for Electrical and HVAC work
Category Code: C55 Purchase Order (PO) for Instrumentation work
Category Code: C56 Purchase Order (PO) for Chemicals
Category Code: C71 Appraisal Report for Consultancy Service
Category Code: C72 Appraisal Report for EPC Contractor Work
Category Code: C73 Appraisal Report for Vendor/Supplier
Category Code: C91 Index/List
Category Code: C92 Procedures & Standards
Category Code: C93 Policy , Guidelines & Memo
Category Code: C94 Forms & Templates
Category Code: C95 Progress/Status Reports
Category Code: Code Information
Category Code: D01 Construction Permits/License/Permit Plan
Category Code: D03 Security Plan
Category Code: D04 Transportation Program
Category Code: D05 Office & Construction Camp Plan
Category Code: D06 Work Change Proposal
Category Code: D71 Appraisal Report for Consultancy Service
Category Code: D72 Appraisal Report for EPC Contractor Work
Category Code: D73 Appraisal Report for Vendor/Supplier
Category Code: D91 Index/List
Category Code: D92 Procedures & Standards
Category Code: D93 Policy , Guidelines & Memo
Category Code: D94 Forms & Templates
Category Code: D95 Progress/Status Reports
Category Code: D96 Hydrostatic leak testing for piping systems
Category Code: E01 Electrical design basis
Category Code: E02 Abbreviation and standard symbols
Category Code: E03 Project electrical specification
Category Code: E04 Electrical requirement for package unit
Category Code: E05 Electrical Equipment datasheets
Category Code: E10 Power system studies
Category Code: E11 Arc flash studies
Category Code: E12 Protective relay selection and coordination study
Category Code: E13 Electrical equipment sizing
Category Code: E14 Single line diagram
Category Code: E15 Electrical load schedule
Category Code: E16 Emergency power supply load schedule
Category Code: E17 Motor list
Category Code: E18 Control and Signal List
Category Code: E19 Control schematic and control logic diagrams
Category Code: E20 Substation equipment layout
Category Code: E21 Layout of busduct for substation
Category Code: E22 Cable tray layout for substation
Category Code: E23 Wiring drawing for substation system
Category Code: E24 Diesel engine generator equipment layout
Category Code: E25 Motor Auto restart for power dift.
Category Code: E31 Power equipment layout
Category Code: E32 Main cable route layout
Category Code: E33 Power and control wiring layout
Category Code: E34 Power and control cable arrangement drawing
Category Code: E40 Lighting illumination level calculation
Category Code: E41 Voltage drop calculation for lighting system
Category Code: E42 Lighting and receptacle panel board circuit schedule
Category Code: E43 Lighting and receptacle system layout
Category Code: E44 Lighting and receptacle system wiring layout
Category Code: E45 POWER BLOCK DIAGRAM (WELDING AND RECEPACLES)
Category Code: E50 Grounding and lightning network calculation
Category Code: E51 Protective zone for lightning system
Category Code: E52 Grounding and lightning system layout
Category Code: E53 Wiring drawing for grounding and lightning system
Category Code: E54 Layout of grounding lug
Category Code: E60 Cable drum schedule
Category Code: E61 Cable schedule
Category Code: E62 Connection List
Category Code: E63 Construction material and Bill of quantities
Category Code: E64 Typical drawing
Category Code: E70 Cathodic Protection system schematic diagram
Category Code: E71 Cathodic Protection system layout
Category Code: E72 Cathodic Protection calculation
Category Code: E80 SMCS and PMS system equipment data sheets
Category Code: E81 SMCS and PMS system schematic diagram
Category Code: E82 SMCS and PMS system layout
Category Code: E86 Appraisal Report for Consultancy Service
Category Code: E87 Appraisal Report for EPC Contractor Work
Category Code: E88 Appraisal Report for Vendor/Supplier
Category Code: E90 Vendor documents
Category Code: E91 Index/List
Category Code: E92 Procedures & Standards
Category Code: E93 Policy , Guidelines & Memo
Category Code: E94 Forms & Templates
Category Code: E95 Progress/Status Reports
Category Code: F40 Fire and Gas Layout
Category Code: F41 Fire and Gas Detector C&E
Category Code: F71 Appraisal Report for Consultancy Service
Category Code: F72 Appraisal Report for EPC Contractor Work
Category Code: F73 Appraisal Report for Vendor/Supplier
Category Code: F75 Escape Ways Drawing
Category Code: F90 Vendor Document
Category Code: F91 Index/List
Category Code: F92 Procedures & Standards
Category Code: F93 Policy , Guidelines & Memo
Category Code: F94 Forms & Templates
Category Code: F95 Progress/Status Reports
Category Code: G01 All Project Philosophies and Process design standard and All Project Studies Records
Category Code: G02 Design Basis
Category Code: G03 Conceptual Design
Category Code: G04 Process Design Package
Category Code: G05 Equipment and Unit Functional Design
Category Code: G06 Process simulation model
Category Code: G20 Design calculations
Category Code: G21 Hydraulic Calculation
Category Code: G22 Flare Calculation
Category Code: G23 Sizing data for the relief and blowdown systems
Category Code: G30 Process Equipment Data Sheets
Category Code: G31 Process Instrument Data sheets
Category Code: G32 Process Safety Valve Data sheets
Category Code: G40 Block Flow Diagram
Category Code: G41 Process Flow Diagrams
Category Code: G42 Utility Flow Diagrams
Category Code: G43 Process and Instrument Diagrams (P&ID)
Category Code: G44 Heat and Material Balance
Category Code: G50 Interlocking Description/Cause and Effect Diagrams
Category Code: G51 Sequence of Operation
Category Code: G60 Battery Limit and Tie-in
Category Code: G61 Equipment List
Category Code: G62 Utility Summary
Category Code: G63 Plant Efffluent Summary
Category Code: G64 Catalyst, Adsobent, and Chemicals Summary
Category Code: G70 Materials specification and; Utilities specfication and; Catalyst, Adsobent,; and Chemicals specification and ; Fluid and Solid properties
Category Code: G71 Effluent and Waste specification
Category Code: G72 Standard and Specification
Category Code: G73 Guide to Safe Handling of Material
Category Code: G74 Material Selection Guideline
Category Code: G75 Engineering Procedure
Category Code: G76 Supervisory Level Operating Procedures for all Process/Utility System(s). (Shall include Steady State, Stat-Up, Shutdown & transient Operations
Category Code: G77 APC Functional specification
Category Code: G81 Appraisal Report for Consultancy Service
Category Code: G82 Appraisal Report for EPC Contractor Work
Category Code: G83 Appraisal Report for Vendor/Supplier
Category Code: G90 Vendor Document/drawings
Category Code: G91 Index/List
Category Code: G92 Procedures & Standards
Category Code: G93 Policy , Guidelines & Memo
Category Code: G94 Forms & Templates
Category Code: G95 Progress/Status Reports
Category Code: H01 Design basis
Category Code: H02 Abbreviation and standard symbols
Category Code: H03 Project HVAC specification
Category Code: H04 Equipment, material specification
Category Code: H05 Equipment datasheet
Category Code: H10 Calculation
Category Code: H20 System schematic diagram
Category Code: H21 Arrangement drawing
Category Code: H22 Electrical and control drawing/ document
Category Code: H60 Cable drum schedule
Category Code: H61 Cable schedule
Category Code: H62 Connection list
Category Code: H63 Construction material and Bill of quantities
Category Code: H64 Typical installation drawing
Category Code: H71 Appraisal Report for Consultancy Service
Category Code: H72 Appraisal Report for EPC Contractor Work
Category Code: H73 Appraisal Report for Vendor/Supplier
Category Code: H90 Vendor documents
Category Code: H91 Index/List
Category Code: H92 Procedures & Standards
Category Code: H93 Policy , Guidelines & Memo
Category Code: H94 Forms & Templates
Category Code: H95 Progress/Status Reports
Category Code: I10 MAC FEED Document
Category Code: I20 Instrument datasheet
Category Code: I20 Instrument datasheet
Category Code: I21 Instrument Calculation sheet
Category Code: I30 Interlock Logic and Sequence Diagram
Category Code: I31 Typical installation / fabrication drawing
Category Code: I32 Instrument installation key plan drawing
Category Code: I33 Instrument cable trays and support layout
Category Code: I34 Instrument main cable layout
Category Code: I35 Instrument, Junction box and instrument air supply station plot plan drawing
Category Code: I36 Local panel plot plan drawing
Category Code: I37 Local panel arrangement drawing
Category Code: I38 Layout of inst wiring (grounding)
Category Code: I39 Instrument air piping and tubing drawing
Category Code: I40 Instrument utilities tubing layout drawing
Category Code: I41 Instrument wiring connection list
Category Code: I42 Junction box Arrangement Drawing
Category Code: I43 Instrument cable list and cable cutting plan
Category Code: I44 Power Supply Distribution Drawing
Category Code: I45 Control Room and Rack Room Drawings
Category Code: I46 Layout of instrument cabinets / panels in Control Room and Rack Room
Category Code: I47 Layout of instrument main and secondary cable route in Control Room and Rack Room
Category Code: I48 Layout of instrument grounding wiring in Control Room and Rack Room
Category Code: I49 Instrument Hook-up Drawing
Category Code: I50 Hook-up drawing for process lead piping for each instrument
Category Code: I51 Hook-up drawing for IA and pneumatic
Category Code: I52 Hook-up drawing for Steam tracing
Category Code: I53 Instrument loop drawing diagram
Category Code: I54 Bill of bulk materials take-off
Category Code: I55 In-line & On equipment
| IE | OL1-2I55-0302 | MR THERMOCOUPLE/RTD WITH WELL |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-07-03
[6 empty] | Revised Plan | 2020-02-05 | 2020-07-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0304 | MR THERMOMETER WITH WELL |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-07-03
[6 empty] | Revised Plan | 2020-02-05 | 2020-07-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0305 | MR MULTIPLE THERMOCOUPLE / RTD |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2020-02-05 | 2020-07-03
[6 empty] | Revised Plan | 2020-02-05 | 2020-07-03
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
| IE | OL1-2I55-0505 | MR ANTISURGE VALVES |  |  | Purpose** | IFQ | IFP
Rev.
[6 empty] | Issue Plan | 2019-05-28 | 2019-11-13
[6 empty] | Revised Plan | 2020-01-10 | 2020-03-31
Issue Actual
Transmittal no.
Return Date
Owner Cmmt*
Category Code: I61 SIL Study Document
Category Code: I62 FAT Punch Lists
Category Code: I63 SAT Punch Lists
Category Code: I64 Operation and maintenance spare part for 2 years list
Category Code: I65 Initial Spare part list
Category Code: I66 Special tools book
Category Code: I70 Instruction Manual of Instrument
Category Code: I71 Control narative for complex loop
Category Code: I76 Appraisal Report for Consultancy Service
Category Code: I77 Appraisal Report for EPC Contractor Work
Category Code: I78 Appraisal Report for Vendor/Supplier
Category Code: I81 DCS System Document
Category Code: I82 ESD system Document
Category Code: I83 FGS system Document
Category Code: I84 Analyzer system Document
Category Code: I85 Custody meter Document
Category Code: I86 Tank gauging Document
Category Code: I87 Pelletizing system Document
Category Code: I90 Vendor documents of Instrument
Category Code: I91 Index/List
Category Code: I92 Procedures & Standards
Category Code: I93 Policy , Guidelines & Memo
Category Code: I94 SPARE NUMBER
Category Code: I94 Forms & Templates
Category Code: I95 SPARE NUMBER
Category Code: I95 Progress/Status Reports
Category Code: I96 SPARE NUMBER
Category Code: I97 SPARE NUMBER
Category Code: I98 SPARE NUMBER
Category Code: I99 SPARE NUMBER
Category Code: J71 Appraisal Report for Consultancy Service
Category Code: J72 Appraisal Report for EPC Contractor Work
Category Code: J73 Appraisal Report for Vendor/Supplier
Category Code: J91 Index/List
Category Code: J92 Procedures & Standards
Category Code: J93 Policy , Guidelines & Memo
Category Code: J94 Forms & Templates
Category Code: J95 Progress/Status Reports
Category Code: K01 Design Basis Reports
Category Code: K02 Design Verification Reports
Category Code: K03 Master Plan Document
Category Code: K04 Cadastal Map
Category Code: K08 Material Take Off UG
Category Code: K11 Design calculation for pile (including pile driven design)
Category Code: K12 Design calculation for paving
Category Code: K13 Design calculation for foundations
Category Code: K14 Design calculation for concrete structure (including reinforcement detail)
Category Code: K15 Design calculation for steel structure (including connection joint)
Category Code: K16 Design calculation for all drainage systems (including roof gutter, down spout, and grating cover)
Category Code: K17 Design calculation for all blast material i.e. door,wall
Category Code: K20 Standard drawing for civil work
Category Code: K21 Standard drawing for steel structure work
Category Code: K22 Standard drawing for architecture work
Category Code: K23 Land Developmemt Drawing
Category Code: K25 Plant Layouts
Category Code: K26 Underground communication Layouts
Category Code: K27 Road and Drainage Layouts
Category Code: K28 Fireproofing Plan
Category Code: K30 General Arrangement for Architectural drawings of Buildings
Category Code: K31 General Arrangement for Civil Concrete Works drawings
Category Code: K32 General Arrangement for Steel Structure drawings
Category Code: K33 Shop Detail Drawings
Category Code: K34 Foundation for equipment, basin, cooling tower, supports and miscellaneous
Category Code: K36 Major UG networks (Nuovo codice richiesto dal Cliente K26/K27)
Category Code: K40 Topographic survey report
Category Code: K41 Hydrological survey report
Category Code: K42 Bathymetric survey report
Category Code: K43 Soil investigation & resisitivity report
Category Code: K50 Concrete Test Results
Category Code: K71 Appraisal Report for Consultancy Service
Category Code: K72 Appraisal Report for EPC Contractor Work
Category Code: K73 Appraisal Report for Vendor/Supplier
Category Code: K90 Vendor Document/drawings
Category Code: K91 Index/List
Category Code: K92 Procedures & Standards
Category Code: K93 Policy , Guidelines & Memo
Category Code: K94 Forms & Templates
Category Code: K95 Progress/Status Reports
Category Code: K97 Technical Specification/Price list for Architectural Works
Category Code: L01 Passive & Active Fire Protection Philosophy
Category Code: L02 Active Fire Protection System
Category Code: L03 Firefighting equipment data sheet
Category Code: L08 Noise General Specification
Category Code: L09 Noise Map
Category Code: L10 Acoustic Calculation Note
Category Code: L11 Noise Rep
Category Code: L20 Fire system calculation
Category Code: L40 Active Fire Fighting Systems
Category Code: L41 Passive Fire Protection Drawings
Category Code: L42 Hazardous Area Classification
Category Code: L43 Risk Matrix
Category Code: L44 Life saving Equip & Escape Route Drawing
Category Code: L60 All project study and Report pertain to Loss control and Safety Process safety report; HAZOP Report; LOPA Report; PSSR Reports; Risk analysis dossiers; and and Project Response;
Category Code: L62 Recommendation Monitoring System
Category Code: L63 Record of Survey
Category Code: L64 Report of audit
Category Code: L65 Hazardous Source Data
Category Code: L66 Register of Safety Devices
Category Code: L67 Equipment Failure Information
Category Code: L70 Emergency Procedures Manual
Category Code: L71 Test Procedures
Category Code: L72 Loss Control and Safety procedure
Category Code: L81 Appraisal Report for Consultancy Service
Category Code: L82 Appraisal Report for EPC Contractor Work
Category Code: L83 Appraisal Report for Vendor/Supplier
Category Code: L90 Vendor Document/drawings
Category Code: L91 Index/List
Category Code: L92 Procedures & Standards
Category Code: L93 Policy , Guidelines & Memo
Category Code: L94 Forms & Templates
Category Code: L95 Progress/Status Reports
Category Code: M03 Mechanical datasheet
Category Code: M04 Mechanical design basic / philosophy / logic diagram
Category Code: M05 Mechanical calculation sheet / report
Category Code: M06 Mechanical equipment drawing
Category Code: M07 Mechanical certification, inspection and test record
Category Code: M20 Static Equipment Datasheet
Category Code: M21 Rotating Machinery Datasheet
Category Code: M22 Package Unit-Datasheet
Category Code: M55 Request for Quotation (RFQ) for Mechanical work
Category Code: M71 Appraisal Report for Consultancy Service
Category Code: M72 Appraisal Report for EPC Contractor Work
Category Code: M73 Appraisal Report for Vendor/Supplier
Category Code: M90 Vendor Document/drawings
Category Code: M91 Index/List
Category Code: M92 Procedures & Standards
Category Code: M93 Policy , Guidelines & Memo
Category Code: M94 Forms & Templates
Category Code: M95 Progress/Status Reports
Category Code: M96 Spare part list for construction/precommissioning/commissioning
Category Code: M97 Spare Part List for Maintenance During First Two Years Operation
Category Code: M98 Special tools books
Category Code: M99 Other
Category Code: O01 Precommissioning Plan and Schedule
Category Code: O02 Commissioning Plan and Schedule
Category Code: O03 Startup Plan and Schedule
Category Code: O04 Performance Test Plan and Schedule
Category Code: O05 Production Plan
Category Code: O06 Operating Manuals
Category Code: O07 Startup Lists
Category Code: O08 Startup Philosophy
Category Code: O09 Scope of Work
Category Code: O10 Maintenance Manuals
Category Code: O11 Operating Condition Calculation
Category Code: O12 Product Quality Calculation
Category Code: O13 Training Schedule
Category Code: O20 Precommissioning Form and Checksheet
Category Code: O21 Commissioning Form and Checksheet
Category Code: O22 Operation Form and Checksheet
Category Code: O23 Equipment Patrol Checksheet
Category Code: O51 Appraisal Report for Consultancy Service
Category Code: O52 Appraisal Report for EPC Contractor Work
Category Code: O53 Appraisal Report for Vendor/Supplier
Category Code: O60 Precommissioning Record and Report
Category Code: O61 Commissioning Record and Report
Category Code: O62 Startup, Shutdown and Emergency Shutdown Record and Report
Category Code: O63 Plant performance Test and record
Category Code: O64 Operation Record and Report Production Record,Report
Category Code: O65 Troubleshooting Record, Report
Category Code: O66 Modification Record,Report
Category Code: O67 List of set point and controller parameter
Category Code: O70 Precommissioning Procedure
Category Code: O71 Commissioning Procedure
Category Code: O72 Startup, Shutdown and Emergency Shutdown Procedure
Category Code: O73 Plant performance Test procedure
Category Code: O74 Tag-in Tag-out/Lock-out Tag-out Procedure
Category Code: O75 Operation Work instruction
Category Code: O80 Lab, Product QA and QC
Category Code: O91 Index/List
Category Code: O92 Procedures & Standards
Category Code: O93 Policy , Guidelines & Memo
Category Code: O94 Forms & Templates
Category Code: O95 Progress/Status Reports
Category Code: P03 Piping datasheet
Category Code: P04 Piping design basic / philosophy / logic diagram
Category Code: P05 Piping calculation sheet / report
Category Code: P06 Piping drawing
Category Code: P07 Piping certification, inspection and test record
Category Code: P08 Piping Material Take-off (MTO)
Category Code: P09 Painting Material Take-off (MTO)
Category Code: P10 Insulation Material Take-off (MTO)
Category Code: P20 Aboveground Piping General Arrangement Drawings
Category Code: P21 Underground Piping General Arrangement Drawings
Category Code: P22 Aboveground Piping Isometric Drawings
Category Code: P23 Underground Piping Isometric Drawings
Category Code: P25 Pipe support drawing
Category Code: P30 3D Model Review File
Category Code: P40 Piping Generic Lists
Category Code: P71 Appraisal Report for Consultancy Service
Category Code: P72 Appraisal Report for EPC Contractor Work
Category Code: P73 Appraisal Report for Vendor/Supplier
Category Code: P90 Vendor Document/drawings
Category Code: P91 Index/List
Category Code: P92 Procedures & Standards
Category Code: P93 Policy , Guidelines & Memo
Category Code: P94 Forms & Templates
Category Code: P95 Progress/Status Reports
Category Code: Q07 Quality Audit Reports
Category Code: Q10 QC Record and Report for Civil work (Engineerig and Procurement)
Category Code: Q11 QC Record and Report for Building work (Engineerig and Procurement)
Category Code: Q12 QC Record and Report for Steel Structure work (Engineerig and Procurement)
Category Code: Q13 QC Record and Report for Mechanical work (Engineerig and Procurement)
Category Code: Q14 QC Record and Report for Piping work (Engineerig and Procurement)
Category Code: Q15 QC Record and Report for Fire Fighting work (Engineerig and Procurement)
Category Code: Q16 QC Record and Report for Electrical work (Engineerig and Procurement)
Category Code: Q17 QC Record and Report for Instrumentation work (Engineerig and Procurement)
Category Code: Q20 QC Record and Report for Civil work (construction)
Category Code: Q21 QC Record and Report for Building work (construction)
Category Code: Q22 QC Record and Report for Steel Structure work (construction)
Category Code: Q23 QC Record and Report for Mechanical work (construction)
Category Code: Q24 QC Dossier for Piping work (construction)
Category Code: Q25 QC Record and Report for Fire Fighting work (construction)
Category Code: Q26 QC Record and Report for Electrical work (construction)
Category Code: Q27 QC Record and Report for Instrumentation work (construction)
Category Code: Q30 Shop Inspection Notice (Civil)
Category Code: Q31 Shop Inspection Notice (Mechanical)
Category Code: Q32 Shop Inspection Notice (Piping)
Category Code: Q33 Shop Inspection Notice (Electrical)
Category Code: Q34 Shop Inspection Notice (Instrumentation)
Category Code: Q35 Mechanical certification (Civil)
Category Code: Q36 Mechanical certification (Static)
Category Code: Q37 Mechanical certification (Rotating)
Category Code: Q38 Mechanical certification (Piping))
Category Code: Q40 Site Inspection Notice (Civil)
Category Code: Q41 Site Inspection Notice (Mechanical)
Category Code: Q42 Site Inspection Notice (Piping)
Category Code: Q43 Site Inspection Notice (Electrical)
Category Code: Q44 Site Inspection Notice (Instrumentation)
Category Code: Q60 Inspection and Test Plan (ITP) for Mechanical Work
Category Code: Q61 Inspection and Test Plan (ITP) for Piping Work
Category Code: Q62 Inspection and Test Plan (ITP) for Electrical work
Category Code: Q63 Inspection and Test Plan (ITP)for Instrumentation work
Category Code: Q64 Inspection and Test Plan (ITP) for Civil,Structure and Architecture.
Category Code: Q65 Inspection and Test Plan (ITP) for Mechanical Work (Construction)
Category Code: Q66 Inspection and Test Plan (ITP) for Piping Work (Construction)
Category Code: Q67 Inspection and Test Plan (ITP) for Electrical work (Construction)
Category Code: Q68 Inspection and Test Plan (ITP)for Instrumentation work (Construction)
Category Code: Q69 Inspection and Test Plan (ITP) for Civil,Structure and Architecture (Construction)
Category Code: Q71 Appraisal Report for Consultancy Service
Category Code: Q72 Appraisal Report for EPC Contractor Work
Category Code: Q73 Appraisal Report for Vendor/Supplier
Category Code: Q90 Vendor Document/drawings
Category Code: Q91 Index/List
Category Code: Q92 Procedures & Standards
Category Code: Q93 Policy , Guidelines,& Memo
Category Code: Q94 Forms & Templates
Category Code: Q95 Progress/Status Reports
Category Code: Q96 Quality Audit Reports
Category Code: Q97 Non-Conformance Record
Category Code: Q98 Addition Vendors/Subcontractors Assessment and Prequalification Report
Category Code: R01 Process Specification (PE)
Category Code: R02 Civil Specification (CV)
Category Code: R03 Mechanical Specification (ME)
Category Code: R04 Piping Specification (PIP)
Category Code: R05 Electrical Specification (EE)
Category Code: R06 Instrument Specification (INS)
Category Code: R07 Project Specification (SP)
Category Code: R08 Construction Specification (CON)
Category Code: R91 Index/List
Category Code: R92 Procedures & Standards
Category Code: R93 Policy , Guidelines & Memo
Category Code: R94 Forms & Templates
Category Code: R95 Progress/Status Reports
Category Code: S01 Environmental Management Plan and program;
Category Code: S02 Waste Material Management
Category Code: S03 Health/Social Management and Program; Community Affairs Management
Category Code: S04 Environmental Management Report
Category Code: S05 Health/Social Management Report
Category Code: S06 ESIA Report
Category Code: S07 ESIA Database
Category Code: S63 EH&S Monitoring report
Category Code: S64 OSHE Review/Audit Report
Category Code: S71 Appraisal Report for Consultancy Service
Category Code: S72 Appraisal Report for EPC Contractor Work
Category Code: S73 Appraisal Report for Vendor/Supplier
Category Code: S81 CSR Procedure & Standard
Category Code: S82 CSR Policy, Guideline & Memo
Category Code: S83 CSR Template & Form
Category Code: S84 CSR Report
Category Code: S85 CSR Audit Report
Category Code: S90 Vendor Document/drawings
Category Code: S91 Index/List
Category Code: S92 Procedures & Standards
Category Code: S93 Policy , Guidelines & Memo
Category Code: S94 Forms & Templates
Category Code: S95 Progress/Status Reports
Category Code: T01 Design basis
Category Code: T02 Abbreviation and standard symbols
Category Code: T03 Project Communication, IT, and Safety Supervisory System specification
Category Code: T04 System philosophy
Category Code: T05 Equipment datasheets
Category Code: T10 Intercom/Paging/Audible Alarm system equipment data sheets
Category Code: T11 Intercom/Paging/Audible Alarm system schematic diagram
Category Code: T12 Intercom/Paging/Audible Alarm aystem layout
Category Code: T13 Intercom/Paging/Audible Alarm aystem wiring layout
Category Code: T14 Cable drum schedule for Intercom/Paging/Audible Alarm aystem
Category Code: T15 Cable schedule for Intercom/Paging/Audible Alarm aystem
Category Code: T16 Connection List for Intercom/Paging/Audible Alarm aystem
Category Code: T17 Bill of quantities for Intercom/Paging/Audible Alarm aystem
Category Code: T18 Typical drawing for Intercom/Paging/Audible Alarm aystem
Category Code: T20 Computer Network (LAN) and Telephone system equipment data sheets
Category Code: T21 Computer Network (LAN) and Telephone system schematic diagram
Category Code: T22 Computer Network (LAN) and Telephone system layout
Category Code: T23 Computer Network (LAN) and Telephone system wiring layout
Category Code: T24 Cable drum schedule for Computer Network (LAN) and Telephone system
Category Code: T25 Cable schedule for Computer Network (LAN) and Telephone system
Category Code: T26 Connection List for Computer Network (LAN) and Telephone system
Category Code: T27 Bill of quantities for Computer Network (LAN) and Telephone system
Category Code: T28 Typical drawing for Computer Network (LAN) and Telephone system
Category Code: T30 CCTV, Access Control, and Intrusion Alarm system equipment data sheets
Category Code: T31 CCTV, Access Control, and Intrusion Alarm system schematic diagram
Category Code: T32 CCTV, Access Control, and Intrusion Alarm system layout
Category Code: T33 CCTV, Access Control, and Intrusion Alarm system wiring layout
Category Code: T34 Cable drum schedule for CCTV, Access Control, and Intrusion Alarm system
Category Code: T35 Cable schedule for CCTV, Access Control, and Intrusion Alarm system
Category Code: T36 Connection List for CCTV, Access Control, and Intrusion Alarm system
Category Code: T37 Bill of quantities for CCTV, Access Control, and Intrusion Alarm system
Category Code: T38 Typical drawing for CCTV, Access Control, and Intrusion Alarm system
Category Code: T40 Fire Alarm system equipment data sheets
Category Code: T41 Fire Alarm system schematic diagram
Category Code: T42 Fire alarm system layout
Category Code: T43 Fire alarm system wiring layout
Category Code: T44 Cable drum schedule for Fire alarm system
Category Code: T45 Cable schedule for Fire alarm system
Category Code: T46 Connection List for Fire alarm system
Category Code: T47 Bill of quantities forFire alarm system
Category Code: T48 Typical drawing for Fire alarm system
Category Code: T60 Application software system
Category Code: T61 Application software Procedure
Category Code: T71 Appraisal Report for Consultancy Service
Category Code: T72 Appraisal Report for EPC Contractor Work
Category Code: T73 Appraisal Report for Vendor/Supplier
Category Code: T90 Vendor documents
Category Code: T91 Index/List
Category Code: T92 Procedures & Standards
Category Code: T93 Policy , Guidelines & Memo
Category Code: T94 Forms & Templates
Category Code: T95 Progress/Status Reports
Category Code: U02 Finance Reports
Category Code: U03 Certification(Finance)
Category Code: U07 Bond and other financial security for Consultancy Service
Category Code: U08 Bond and other financial security for EPC Contractor
Category Code: U09 Bond and other financial security for Vendor/Supplier
Category Code: U11 Certificates of Insurance
Category Code: U12 Insurance Policies and Guarantees
Category Code: U71 Appraisal Report for Consultancy Service
Category Code: U72 Appraisal Report for EPC Contractor Work
Category Code: U73 Appraisal Report for Vendor/Supplier
Category Code: U91 Index/List
Category Code: U92 Procedures & Standards
Category Code: U93 Policy , Guidelines & Memo
Category Code: U94 Forms & Templates
Category Code: U95 Progress/Status Reports
Category Code: V04 Interface Matrix (Responsibility Matrix)
Category Code: V71 Appraisal Report for Consultancy Service
Category Code: V72 Appraisal Report for EPC Contractor Work
Category Code: V73 Appraisal Report for Vendor/Supplier
Category Code: V91 Index/List
Category Code: V92 Procedures & Standards
Category Code: V93 Policy , Guidelines & Memo
Category Code: V94 Forms & Templates
Category Code: V95 Progress/Status Reports
Category Code: W01 Work Breakdown Structure
Category Code: W71 Appraisal Report for Consultancy Service
Category Code: W72 Appraisal Report for EPC Contractor Work
Category Code: W73 Appraisal Report for Vendor/Supplier
Category Code: W90 Technical Report
Category Code: W91 Index/List
Category Code: W92 Procedures & Standards
Category Code: W93 Policy , Guidelines & Memo
Category Code: W94 Forms & Templates
Category Code: W95 Progress/Status Reports
Category Code: X71 Appraisal Report for Consultancy Service
Category Code: X72 Appraisal Report for EPC Contractor Work
Category Code: X73 Appraisal Report for Vendor/Supplier
Category Code: X91 Index/List
Category Code: X92 Procedures & Standards
Category Code: X93 Policy , Guidelines & Memo
Category Code: X94 Forms & Templates
Category Code: X95 Progress/Status Reports
Category Code: Y01 Bidding Guideline
Category Code: Y02 Bidding Committee Assignment
Category Code: Y03 Bidding Policy
Category Code: Y04 Pre-Qualification Document
Category Code: Y05 List of qualified Bidders
Category Code: Y06 Bidding Evaluation Criteria for Consultancy Service
Category Code: Y07 Bidding Evaluation Criteria for EPC Contractor
Category Code: Y08 Bidding Evaluation Criteria for Vendor/Supplier
Category Code: Y09 Contractor Selection Plan
Category Code: Y13 ITB Structure
Category Code: Y21 Tender or ITB Document for Consultancy service
Category Code: Y22 Tender or ITB Document for EPC Contractor
Category Code: Y23 Tender or ITB Document for Vendor/Supplier
Category Code: Y31 Tender or ITB clarification records for Consultancy service
Category Code: Y32 Tender or ITB clarification records for EPC Contractor
Category Code: Y33 Tender or ITB clarification records for Vendor/Supplier
Category Code: Y41 Proposal Document of Consultancy service bidding
Category Code: Y42 Proposal Document of EPC Contractor bidding
Category Code: Y43 Proposal Document of Vendor/Supplier bidding
Category Code: Y51 Proposal clarification records for Consultancy service
Category Code: Y52 Proposal clarification records for EPC Contractor
Category Code: Y53 Proposal clarification records for Vendor/Supplier
Category Code: Y61 Un-Priced Commerical proposals evaluation report
Category Code: Y62 Priced Commercial proposals evaluation report
Category Code: Y63 Bid Evaluation Report (Technical & Un-priced Commercial proposal )
Category Code: Y64 Bid Evaluation report (Executive Summary)
Category Code: Y65 Nomination of successful bidder for approval
Category Code: Y66 EPC Contract Negotiation, Compliance Report
Category Code: Y71 Appraisal Report for Consultancy Service
Category Code: Y72 Appraisal Report for EPC Contractor Work
Category Code: Y73 Appraisal Report for Vendor/Supplier
Category Code: Y81 Consultancy Service Bidding Records
Category Code: Y82 EPC Contractor Bidding Records
Category Code: Y83 Vendor/Supplier Bidding Records